## Client_Master
ClientID | ClientName | Sector | Tier | HQCity | AccountOwner | ContractValue_Cr | ActiveProjects
CL001 | Hitachi Payment Services | BFSI | Enterprise | Mumbai | Aryan Maharaj | 29.68 | 5
CL002 | Axis Bank | BFSI | Enterprise | Mumbai | Udant Dewan | 3.56 | 6
CL003 | State Bank of India | BFSI | Enterprise | Mumbai | Gagan Sami | 14.19 | 4
CL004 | Bajaj Finance | BFSI | Enterprise | Pune | Ayushman Chander | 11.99 | 5
CL005 | HDFC Bank | BFSI | Enterprise | Mumbai | Viraj Tiwari | 33.8 | 4
CL006 | ICICI Bank | BFSI | Enterprise | Mumbai | Rushil Saini | 31.26 | 5
CL007 | Tata Motors | Manufacturing | Large | Pune | Saumya Mall | 40.42 | 5
CL008 | Reliance Retail | Retail | Enterprise | Mumbai | Nathaniel Sami | 6.19 | 6

## Projects
ProjectID | ClientID | ClientName | ProjectName | ProjectType | Region | PMOwner | StartDate | PlannedEndDate | Budget_Cr | ActualSpend_Cr | PctComplete | DelayDays | RAGStatus | TotalSites | SitesLive | OpenIssues | OpenRisks
PRJ001 | CL001 | Hitachi Payment Services | Hitachi SD-WAN Rollout Phase 1 | SD-WAN Rollout | West | Gayathri Chaudry | 2025-07-22 | 2026-04-16 | 5.91 | 6.33 | 81 | 10 | Amber | 84 | 68 | 3 | 2
PRJ002 | CL001 | Hitachi Payment Services | Hitachi MPLS Backbone Phase 2 | MPLS Backbone | East | Hemangini Lalla | 2025-08-08 | 2026-06-18 | 10.6 | 10.02 | 40 | 12 | Red | 81 | 32 | 2 | 0
PRJ003 | CL001 | Hitachi Payment Services | Hitachi ATM Connectivity Phase 3 | ATM Connectivity | Central | Janaki Handa | 2025-06-21 | 2025-12-30 | 9.69 | 6.97 | 57 | 12 | Red | 86 | 49 | 2 | 2
PRJ004 | CL001 | Hitachi Payment Services | Hitachi SD-WAN Rollout Phase 4 | SD-WAN Rollout | East | Lajita Chatterjee | 2025-07-13 | 2026-05-31 | 3.9 | 3.1 | 82 | 17 | Amber | 67 | 54 | 0 | 0
PRJ005 | CL001 | Hitachi Payment Services | Hitachi MPLS Backbone Phase 5 | MPLS Backbone | West | Hemangini Lalla | 2025-06-23 | 2026-03-12 | 11.68 | 6.74 | 50 | 10 | Amber | 95 | 47 | 6 | 3
PRJ006 | CL002 | Axis Bank | Axis VSAT Backup Phase 1 | VSAT Backup | North | Janaki Handa | 2025-08-29 | 2026-03-10 | 11.71 | 7.9 | 90 | 6 | Amber | 80 | 72 | 0 | 1
PRJ007 | CL002 | Axis Bank | Axis VSAT Backup Phase 2 | VSAT Backup | Central | Lajita Mall | 2025-09-27 | 2026-07-15 | 11.9 | 10.22 | 80 | 11 | Amber | 92 | 73 | 6 | 1
PRJ008 | CL002 | Axis Bank | Axis ATM Connectivity Phase 3 | ATM Connectivity | West | Gayathri Chaudry | 2025-11-29 | 2026-08-26 | 3.51 | 2.35 | 59 | 13 | Red | 108 | 63 | 5 | 0
PRJ009 | CL002 | Axis Bank | Axis Branch Link Upgrade Phase 4 | Branch Link Upgrade | Central | Lajita Mall | 2026-01-09 | 2026-09-09 | 8.24 | 5.08 | 83 | 17 | Amber | 86 | 71 | 7 | 0
PRJ010 | CL002 | Axis Bank | Axis ATM Connectivity Phase 5 | ATM Connectivity | Central | Isha Kadakia | 2025-07-31 | 2026-07-13 | 3.04 | 2.28 | 53 | 13 | Red | 68 | 36 | 3 | 3
PRJ011 | CL002 | Axis Bank | Axis Branch Link Upgrade Phase 6 | Branch Link Upgrade | West | Fariq Kaul | 2026-03-01 | 2027-02-10 | 4.71 | 4.95 | 57 | 11 | Red | 76 | 43 | 2 | 3
PRJ012 | CL003 | State Bank of India | State MPLS Backbone Phase 1 | MPLS Backbone | South | Gayathri Chaudry | 2025-05-30 | 2025-11-27 | 4 | 3.86 | 94 | 1 | Green | 63 | 59 | 4 | 0
PRJ013 | CL003 | State Bank of India | State MPLS Backbone Phase 2 | MPLS Backbone | East | Fariq Kaul | 2025-11-27 | 2026-11-10 | 1.76 | 1.25 | 62 | 17 | Amber | 108 | 66 | 5 | 0
PRJ014 | CL003 | State Bank of India | State Branch Link Upgrade Phase 3 | Branch Link Upgrade | West | Tripti Yadav | 2025-08-18 | 2026-06-25 | 4.85 | 4.3 | 81 | 2 | Amber | 87 | 70 | 6 | 0
PRJ015 | CL003 | State Bank of India | State SD-WAN Rollout Phase 4 | SD-WAN Rollout | South | Tripti Yadav | 2025-10-11 | 2026-06-12 | 4.75 | 4.29 | 75 | 16 | Amber | 82 | 61 | 1 | 0
PRJ016 | CL004 | Bajaj Finance | Bajaj VSAT Backup Phase 1 | VSAT Backup | West | Hemangini Lalla | 2025-07-22 | 2026-07-06 | 2.83 | 2.98 | 92 | 5 | Amber | 66 | 60 | 0 | 3
PRJ017 | CL004 | Bajaj Finance | Bajaj Branch Link Upgrade Phase 2 | Branch Link Upgrade | Central | Isha Kadakia | 2025-09-18 | 2026-05-08 | 7.48 | 4.8 | 86 | 14 | Amber | 106 | 91 | 4 | 5
PRJ018 | CL004 | Bajaj Finance | Bajaj SD-WAN Rollout Phase 3 | SD-WAN Rollout | Central | Isha Kadakia | 2025-12-21 | 2026-08-17 | 3.41 | 2.62 | 61 | 1 | Amber | 64 | 39 | 1 | 5
PRJ019 | CL004 | Bajaj Finance | Bajaj SD-WAN Rollout Phase 4 | SD-WAN Rollout | East | Kritika Brar | 2025-12-20 | 2026-09-29 | 8.45 | 7.32 | 83 | 13 | Amber | 61 | 50 | 8 | 0
PRJ020 | CL004 | Bajaj Finance | Bajaj ATM Connectivity Phase 5 | ATM Connectivity | East | Gayathri Chaudry | 2025-12-20 | 2026-07-01 | 2.45 | 1.84 | 42 | 2 | Amber | 68 | 28 | 2 | 0
PRJ021 | CL005 | HDFC Bank | HDFC SD-WAN Rollout Phase 1 | SD-WAN Rollout | East | Isha Kadakia | 2025-10-22 | 2026-07-07 | 4.28 | 3.41 | 76 | 11 | Amber | 69 | 52 | 3 | 0
PRJ022 | CL005 | HDFC Bank | HDFC VSAT Backup Phase 2 | VSAT Backup | Central | Kritika Brar | 2026-01-12 | 2026-10-30 | 6.63 | 4.39 | 41 | 3 | Amber | 81 | 33 | 8 | 4
PRJ023 | CL005 | HDFC Bank | HDFC ATM Connectivity Phase 3 | ATM Connectivity | East | Arunima Dugal | 2025-11-08 | 2026-05-28 | 11.29 | 9.5 | 39 | 7 | Amber | 116 | 45 | 3 | 2
PRJ024 | CL005 | HDFC Bank | HDFC MPLS Backbone Phase 4 | MPLS Backbone | Central | Fariq Kaul | 2025-10-30 | 2026-08-26 | 6.13 | 6.15 | 66 | 5 | Amber | 98 | 64 | 6 | 5
PRJ025 | CL006 | ICICI Bank | ICICI MPLS Backbone Phase 1 | MPLS Backbone | West | Fariq Kaul | 2025-08-30 | 2026-03-14 | 1.5 | 0.99 | 63 | 3 | Amber | 89 | 56 | 1 | 2
PRJ026 | CL006 | ICICI Bank | ICICI Branch Link Upgrade Phase 2 | Branch Link Upgrade | West | Fariq Kaul | 2025-06-09 | 2026-05-18 | 6.11 | 4.66 | 92 | 2 | Green | 70 | 64 | 6 | 4
PRJ027 | CL006 | ICICI Bank | ICICI SD-WAN Rollout Phase 3 | SD-WAN Rollout | South | Chakradev Kari | 2025-10-15 | 2026-10-06 | 10.88 | 6.32 | 56 | 4 | Amber | 80 | 44 | 6 | 4
PRJ028 | CL006 | ICICI Bank | ICICI Branch Link Upgrade Phase 4 | Branch Link Upgrade | East | Gayathri Chaudry | 2025-10-28 | 2026-05-17 | 7.49 | 5.41 | 54 | 6 | Amber | 76 | 41 | 3 | 3
PRJ029 | CL006 | ICICI Bank | ICICI VSAT Backup Phase 5 | VSAT Backup | Central | Lajita Mall | 2025-08-30 | 2026-02-27 | 1.69 | 1.01 | 46 | 4 | Amber | 63 | 28 | 1 | 4
PRJ030 | CL007 | Tata Motors | Tata SD-WAN Rollout Phase 1 | SD-WAN Rollout | Central | Chakradev Kari | 2026-02-17 | 2027-01-06 | 4.22 | 4.16 | 84 | 10 | Amber | 116 | 97 | 1 | 3
PRJ031 | CL007 | Tata Motors | Tata MPLS Backbone Phase 2 | MPLS Backbone | Central | Janaki Handa | 2025-12-02 | 2026-06-09 | 3.81 | 2.87 | 75 | 5 | Amber | 87 | 65 | 6 | 4
PRJ032 | CL007 | Tata Motors | Tata SD-WAN Rollout Phase 3 | SD-WAN Rollout | Central | Fariq Kaul | 2025-06-08 | 2026-02-08 | 11.51 | 11.24 | 62 | 1 | Amber | 62 | 38 | 4 | 0
PRJ033 | CL007 | Tata Motors | Tata ATM Connectivity Phase 4 | ATM Connectivity | South | Janaki Handa | 2025-07-08 | 2026-02-11 | 9.73 | 6.13 | 67 | 18 | Amber | 103 | 69 | 3 | 2
PRJ034 | CL007 | Tata Motors | Tata SD-WAN Rollout Phase 5 | SD-WAN Rollout | West | Fariq Kaul | 2025-10-09 | 2026-07-28 | 5.52 | 4.79 | 53 | 16 | Red | 84 | 44 | 8 | 4
PRJ035 | CL008 | Reliance Retail | Reliance MPLS Backbone Phase 1 | MPLS Backbone | East | Kritika Brar | 2026-02-21 | 2026-10-06 | 2.82 | 2.39 | 95 | 5 | Amber | 120 | 114 | 5 | 5
PRJ036 | CL008 | Reliance Retail | Reliance SD-WAN Rollout Phase 2 | SD-WAN Rollout | North | Lajita Mall | 2025-10-04 | 2026-09-22 | 4.23 | 3.08 | 52 | 10 | Amber | 82 | 42 | 6 | 3
PRJ037 | CL008 | Reliance Retail | Reliance Branch Link Upgrade Phase 3 | Branch Link Upgrade | East | Gayathri Chaudry | 2025-05-25 | 2025-12-03 | 1.53 | 0.97 | 53 | 11 | Red | 69 | 36 | 0 | 1
PRJ038 | CL008 | Reliance Retail | Reliance SD-WAN Rollout Phase 4 | SD-WAN Rollout | North | Lajita Mall | 2025-11-10 | 2026-06-12 | 3.32 | 3.21 | 92 | 15 | Amber | 90 | 82 | 4 | 0
PRJ039 | CL008 | Reliance Retail | Reliance Branch Link Upgrade Phase 5 | Branch Link Upgrade | South | Tripti Yadav | 2025-09-29 | 2026-04-08 | 8.81 | 8.59 | 59 | 11 | Red | 119 | 70 | 5 | 1
PRJ040 | CL008 | Reliance Retail | Reliance ATM Connectivity Phase 6 | ATM Connectivity | Central | Gayathri Chaudry | 2025-12-18 | 2026-09-25 | 5.09 | 5.33 | 95 | 4 | Amber | 105 | 99 | 7 | 2

## Sites_Milestones
SiteID | ProjectID | ClientID | ClientName | SiteName | City | Region | Bandwidth_Mbps | SiteStatus | SurveyDate | InstallPlanned | InstallActual | GoLivePlanned | GoLiveActual | DelayDays | SLAStatus | Engineer | SiteCost_INR
ST00001 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-001 | Mumbai | West | 10 | Live | 2025-07-27 | 2025-09-18 | 2025-09-19 | 2025-10-09 | 2025-10-19 | 1 | Met | Irya Sampath | 208356
ST00002 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-002 | Ahmedabad | West | 100 | Live | 2025-07-30 | 2025-09-07 | 2025-09-11 | 2025-09-30 | 2025-10-07 | 4 | Met | Ekavir Varkey | 190335
ST00003 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-003 | Pune | West | 100 | ROW In Progress | 2025-08-17 | 2025-09-30 |  | 2025-10-15 |  | 4 | Met | Ekbal Garg | 124658
ST00004 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-004 | Ahmedabad | West | 100 | Installation Scheduled | 2025-08-21 | 2025-10-17 | 2025-10-22 | 2025-11-10 |  | 7 | Met | Kabir Soman | 179001
ST00005 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-005 | Surat | West | 10 | Live | 2025-08-21 | 2025-09-20 | 2025-09-17 | 2025-10-09 | 2025-10-16 | 0 | Met | Devika Rastogi | 221369
ST00006 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-006 | Ahmedabad | West | 100 | Installation Scheduled | 2025-08-02 | 2025-08-31 | 2025-08-26 | 2025-09-11 |  | 3 | Met | Priya Rastogi | 164384
ST00007 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-007 | Surat | West | 20 | Live | 2025-08-14 | 2025-09-15 | 2025-09-22 | 2025-10-10 | 2025-10-19 | 7 | Met | Aarush Lall | 216981
ST00008 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-008 | Mumbai | West | 200 | Live | 2025-08-20 | 2025-09-15 | 2025-09-23 | 2025-10-02 | 2025-10-04 | 8 | Marginal | Dipta Bhandari | 58164
ST00009 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-009 | Pune | West | 100 | Pending Acceptance | 2025-07-30 | 2025-09-17 | 2025-09-16 | 2025-10-11 | 2025-10-18 | 0 | Met | Yatin Baral | 156867
ST00010 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-010 | Surat | West | 50 | Live | 2025-08-19 | 2025-10-08 | 2025-10-17 | 2025-10-26 | 2025-10-30 | 9 | Marginal | Quincy Biswas | 209298
ST00011 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-011 | Pune | West | 50 | Installation Scheduled | 2025-07-29 | 2025-09-05 | 2025-09-07 | 2025-09-23 |  | 5 | Met | Theodore Devi | 81273
ST00012 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-012 | Pune | West | 100 | Installation Scheduled | 2025-08-18 | 2025-09-16 | 2025-09-17 | 2025-09-28 |  | 6 | Met | Irya Sampath | 187242
ST00013 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-013 | Surat | West | 10 | Installation Done | 2025-08-02 | 2025-09-17 | 2025-09-24 | 2025-10-15 |  | 12 | Marginal | Arya Shere | 170037
ST00014 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-014 | Mumbai | West | 100 | Pending Acceptance | 2025-08-05 | 2025-09-18 | 2025-09-26 | 2025-10-15 | 2025-10-19 | 8 | Marginal | Alka Wable | 116548
ST00015 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-015 | Surat | West | 100 | Installation Done | 2025-08-08 | 2025-09-18 | 2025-09-25 | 2025-10-03 |  | 12 | Marginal | Harini Choudhury | 208120
ST00016 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-016 | Mumbai | West | 20 | Live | 2025-08-14 | 2025-10-09 | 2025-10-04 | 2025-10-21 | 2025-10-31 | 0 | Met | Dipta Bhandari | 92639
ST00017 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-017 | Mumbai | West | 100 | Installation Scheduled | 2025-08-06 | 2025-09-08 | 2025-09-17 | 2025-09-28 |  | 5 | Met | Ekavir Bhargava | 242134
ST00018 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-018 | Surat | West | 50 | Installation Scheduled | 2025-07-29 | 2025-09-17 | 2025-09-12 | 2025-10-14 |  | 0 | Met | Alka Wable | 215431
ST00019 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-019 | Mumbai | West | 10 | Live | 2025-08-16 | 2025-09-07 | 2025-09-02 | 2025-09-24 | 2025-09-27 | 0 | Met | Yashica Cherian | 107533
ST00020 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-020 | Pune | West | 50 | Installation Done | 2025-07-30 | 2025-09-24 | 2025-09-25 | 2025-10-18 |  | 12 | Marginal | Logan Sami | 88984
ST00021 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-021 | Mumbai | West | 50 | Live | 2025-08-01 | 2025-09-09 | 2025-09-07 | 2025-10-07 | 2025-10-04 | 0 | Met | Arya Shere | 148980
ST00022 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-022 | Pune | West | 50 | Survey Pending | 2025-08-18 | 2025-10-17 |  | 2025-11-03 |  | 1 | Met | Advay Contractor | 253726
ST00023 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-023 | Mumbai | West | 10 | Installation Scheduled | 2025-08-09 | 2025-09-21 | 2025-09-18 | 2025-10-17 |  | 5 | Met | Tanay Rattan | 260569
ST00024 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-024 | Surat | West | 100 | ROW In Progress | 2025-08-07 | 2025-10-06 |  | 2025-10-30 |  | 2 | Met | Ekiya Suresh | 237360
ST00025 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-025 | Ahmedabad | West | 200 | Testing | 2025-08-13 | 2025-10-02 | 2025-10-11 | 2025-10-25 |  | 12 | Marginal | Victor Kannan | 129490
ST00026 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-026 | Pune | West | 200 | Live | 2025-07-29 | 2025-09-04 | 2025-09-13 | 2025-09-21 | 2025-10-02 | 9 | Marginal | Arya Shere | 133184
ST00027 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-027 | Mumbai | West | 50 | Installation Done | 2025-08-06 | 2025-09-06 | 2025-09-16 | 2025-09-22 |  | 12 | Marginal | Devansh Nigam | 134217
ST00028 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-028 | Ahmedabad | West | 10 | Live | 2025-08-18 | 2025-09-24 | 2025-09-19 | 2025-10-20 | 2025-10-23 | 0 | Met | Devika Rastogi | 233763
ST00029 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-029 | Surat | West | 100 | Installation Done | 2025-08-20 | 2025-09-24 | 2025-10-04 | 2025-10-24 |  | 12 | Marginal | Mohammed Gupta | 252862
ST00030 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-030 | Mumbai | West | 200 | ROW In Progress | 2025-08-03 | 2025-09-17 |  | 2025-10-04 |  | 4 | Met | Logan Sami | 169062
ST00031 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-031 | Ahmedabad | West | 100 | Installation Done | 2025-08-19 | 2025-10-13 | 2025-10-18 | 2025-11-03 |  | 12 | Marginal | Victor Kannan | 125379
ST00032 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-032 | Ahmedabad | West | 20 | Installation Scheduled | 2025-08-19 | 2025-09-20 | 2025-09-25 | 2025-10-03 |  | 8 | Marginal | Wriddhish Bhardwaj | 101723
ST00033 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-033 | Surat | West | 50 | Installation Scheduled | 2025-08-14 | 2025-10-06 | 2025-10-10 | 2025-10-19 |  | 3 | Met | Siddharth Zacharia | 139602
ST00034 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-034 | Pune | West | 10 | Installation Scheduled | 2025-08-18 | 2025-10-11 | 2025-10-10 | 2025-10-29 |  | 0 | Met | Ekavir Varkey | 227823
ST00035 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-035 | Pune | West | 100 | Live | 2025-08-20 | 2025-10-10 | 2025-10-08 | 2025-10-20 | 2025-10-26 | 0 | Met | Dakshesh Trivedi | 160466
ST00036 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-036 | Ahmedabad | West | 10 | ROW In Progress | 2025-07-28 | 2025-09-02 |  | 2025-09-27 |  | 1 | Met | Girik Khalsa | 173908
ST00037 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-037 | Mumbai | West | 200 | Testing | 2025-08-17 | 2025-09-09 | 2025-09-08 | 2025-09-23 |  | 12 | Marginal | Arya Sunder | 67329
ST00038 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-038 | Pune | West | 200 | ROW In Progress | 2025-08-20 | 2025-10-05 |  | 2025-11-03 |  | 3 | Met | Arya Shere | 163099
ST00039 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-039 | Surat | West | 200 | Installation Scheduled | 2025-08-14 | 2025-09-30 | 2025-10-04 | 2025-10-28 |  | 0 | Met | Michael Dutta | 244946
ST00040 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-040 | Pune | West | 20 | Testing | 2025-08-04 | 2025-08-29 | 2025-08-29 | 2025-09-15 |  | 12 | Marginal | Priya Rastogi | 86034
ST00041 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-041 | Mumbai | West | 10 | Installation Done | 2025-08-18 | 2025-10-15 | 2025-10-25 | 2025-11-03 |  | 12 | Marginal | Siddharth Zacharia | 120524
ST00042 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-042 | Ahmedabad | West | 100 | Live | 2025-08-10 | 2025-09-03 | 2025-09-05 | 2025-09-21 | 2025-09-24 | 2 | Met | Upadhriti Wadhwa | 187753
ST00043 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-043 | Pune | West | 50 | Live | 2025-08-04 | 2025-09-02 | 2025-08-30 | 2025-09-13 | 2025-09-15 | 0 | Met | Ekansh Balay | 160121
ST00044 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-044 | Mumbai | West | 200 | Installation Done | 2025-08-05 | 2025-09-19 | 2025-09-22 | 2025-10-15 |  | 12 | Marginal | Wahab Raval | 159755
ST00045 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-045 | Mumbai | West | 10 | Testing | 2025-08-09 | 2025-09-18 | 2025-09-21 | 2025-09-28 |  | 12 | Marginal | Siddharth Zacharia | 221763
ST00046 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-046 | Mumbai | West | 200 | Pending Acceptance | 2025-08-17 | 2025-09-23 | 2025-09-19 | 2025-10-08 | 2025-10-20 | 0 | Met | Bhavika Sampath | 117917
ST00047 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-047 | Pune | West | 50 | Pending Acceptance | 2025-08-09 | 2025-10-08 | 2025-10-18 | 2025-10-20 | 2025-11-01 | 10 | Marginal | Niharika Sunder | 132374
ST00048 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-048 | Ahmedabad | West | 100 | Live | 2025-08-01 | 2025-09-11 | 2025-09-19 | 2025-10-06 | 2025-10-12 | 8 | Marginal | Diya Rattan | 164229
ST00049 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-049 | Mumbai | West | 200 | Installation Scheduled | 2025-08-06 | 2025-09-02 | 2025-09-09 | 2025-09-28 |  | 0 | Met | Dipta Bhandari | 153330
ST00050 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-050 | Mumbai | West | 10 | ROW In Progress | 2025-08-07 | 2025-10-05 |  | 2025-10-30 |  | 7 | Met | Ekapad Walia | 115007
ST00051 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-051 | Pune | West | 20 | Pending Acceptance | 2025-08-10 | 2025-09-30 | 2025-09-28 | 2025-10-10 | 2025-10-14 | 0 | Met | Kevin Solanki | 189399
ST00052 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-052 | Mumbai | West | 10 | Testing | 2025-07-29 | 2025-09-01 | 2025-08-30 | 2025-09-25 |  | 12 | Marginal | Yashica Cherian | 175646
ST00053 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-053 | Ahmedabad | West | 20 | Installation Done | 2025-08-04 | 2025-09-19 | 2025-09-29 | 2025-10-14 |  | 12 | Marginal | Teerth Bhardwaj | 189510
ST00054 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-054 | Pune | West | 50 | Installation Done | 2025-08-15 | 2025-10-06 | 2025-10-05 | 2025-10-18 |  | 12 | Marginal | Tanay Rattan | 134096
ST00055 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-055 | Ahmedabad | West | 200 | Live | 2025-08-05 | 2025-09-13 | 2025-09-23 | 2025-09-27 | 2025-10-08 | 10 | Marginal | Dakshesh Trivedi | 135472
ST00056 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-056 | Ahmedabad | West | 20 | Testing | 2025-08-13 | 2025-09-26 | 2025-10-05 | 2025-10-16 |  | 12 | Marginal | Devika Rastogi | 194893
ST00057 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-057 | Surat | West | 100 | Installation Scheduled | 2025-08-20 | 2025-10-05 | 2025-10-01 | 2025-10-25 |  | 7 | Met | Faqid Savant | 218982
ST00058 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-058 | Pune | West | 100 | Installation Done | 2025-07-28 | 2025-08-25 | 2025-08-30 | 2025-09-07 |  | 12 | Marginal | Michael Dutta | 182874
ST00059 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-059 | Surat | West | 10 | Survey Pending | 2025-07-31 | 2025-09-15 |  | 2025-10-15 |  | 2 | Met | Vansha Thakkar | 249872
ST00060 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-060 | Ahmedabad | West | 100 | Installation Scheduled | 2025-08-18 | 2025-10-02 | 2025-09-29 | 2025-10-22 |  | 8 | Marginal | Urvashi Ray | 209311
ST00061 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-061 | Surat | West | 20 | Live | 2025-07-28 | 2025-09-25 | 2025-09-22 | 2025-10-12 | 2025-10-18 | 0 | Met | Gavin Batta | 158763
ST00062 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-062 | Mumbai | West | 10 | Live | 2025-08-18 | 2025-09-13 | 2025-09-22 | 2025-09-28 | 2025-10-04 | 9 | Marginal | Dominic Kakar | 130032
ST00063 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-063 | Mumbai | West | 100 | Installation Scheduled | 2025-08-07 | 2025-09-23 | 2025-09-22 | 2025-10-10 |  | 8 | Marginal | Isaac Patil | 89560
ST00064 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-064 | Pune | West | 200 | Survey Pending | 2025-08-08 | 2025-10-06 |  | 2025-10-23 |  | 7 | Met | Aarush Lall | 105866
ST00065 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-065 | Surat | West | 200 | Live | 2025-08-10 | 2025-09-15 | 2025-09-10 | 2025-10-09 | 2025-10-15 | 0 | Met | Yashica Issac | 64362
ST00066 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-066 | Surat | West | 50 | Pending Acceptance | 2025-08-14 | 2025-09-22 | 2025-09-30 | 2025-10-10 | 2025-10-21 | 8 | Marginal | Farhan Chada | 145845
ST00067 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-067 | Surat | West | 50 | ROW In Progress | 2025-08-08 | 2025-10-03 |  | 2025-10-24 |  | 4 | Met | Anamika Kanda | 262589
ST00068 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-068 | Surat | West | 200 | Installation Scheduled | 2025-08-14 | 2025-09-06 | 2025-09-16 | 2025-09-25 |  | 3 | Met | Ikbal Kothari | 102410
ST00069 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-069 | Pune | West | 10 | Testing | 2025-08-17 | 2025-09-14 | 2025-09-12 | 2025-10-14 |  | 12 | Marginal | Kevin Solanki | 251729
ST00070 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-070 | Surat | West | 50 | Survey Pending | 2025-08-07 | 2025-09-04 |  | 2025-09-16 |  | 4 | Met | Tanay Rattan | 91042
ST00071 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-071 | Pune | West | 50 | ROW In Progress | 2025-08-13 | 2025-09-25 |  | 2025-10-21 |  | 8 | Marginal | Kashvi Edwin | 112363
ST00072 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-072 | Surat | West | 20 | Pending Acceptance | 2025-08-05 | 2025-09-15 | 2025-09-13 | 2025-10-09 | 2025-10-08 | 0 | Met | Alka Wable | 270480
ST00073 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-073 | Surat | West | 10 | Pending Acceptance | 2025-08-21 | 2025-10-15 | 2025-10-21 | 2025-10-27 | 2025-11-05 | 6 | Met | Devansh Nigam | 185659
ST00074 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-074 | Mumbai | West | 50 | Installation Done | 2025-08-17 | 2025-09-22 | 2025-09-29 | 2025-10-22 |  | 12 | Marginal | Devansh Rajan | 221904
ST00075 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-075 | Pune | West | 20 | Installation Done | 2025-08-15 | 2025-10-09 | 2025-10-14 | 2025-11-07 |  | 12 | Marginal | Liam Koshy | 211567
ST00076 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-076 | Surat | West | 10 | Live | 2025-08-05 | 2025-09-20 | 2025-09-18 | 2025-10-04 | 2025-10-02 | 0 | Met | Arya Sunder | 174138
ST00077 | PRJ001 | CL001 | Hitachi Payment Services | Mumbai Site-077 | Mumbai | West | 50 | ROW In Progress | 2025-08-13 | 2025-09-10 |  | 2025-10-02 |  | 7 | Met | Tanay Rattan | 198967
ST00078 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-078 | Pune | West | 50 | Live | 2025-08-16 | 2025-09-11 | 2025-09-21 | 2025-10-10 | 2025-10-20 | 10 | Marginal | Diya Rattan | 225952
ST00079 | PRJ001 | CL001 | Hitachi Payment Services | Ahmedabad Site-079 | Ahmedabad | West | 200 | Installation Scheduled | 2025-08-10 | 2025-09-14 | 2025-09-20 | 2025-09-27 |  | 5 | Met | Ikbal Kothari | 60872
ST00080 | PRJ001 | CL001 | Hitachi Payment Services | Surat Site-080 | Surat | West | 10 | Installation Scheduled | 2025-07-30 | 2025-09-17 | 2025-09-14 | 2025-10-03 |  | 0 | Met | Irya Sampath | 108850
ST00081 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-081 | Pune | West | 20 | Live | 2025-08-02 | 2025-08-26 | 2025-08-27 | 2025-09-23 | 2025-09-26 | 1 | Met | Irya Sampath | 247996
ST00082 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-082 | Pune | West | 200 | Live | 2025-08-15 | 2025-09-04 | 2025-09-07 | 2025-09-18 | 2025-09-19 | 3 | Met | Jai Kota | 254325
ST00083 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-083 | Pune | West | 20 | ROW In Progress | 2025-07-27 | 2025-08-24 |  | 2025-09-03 |  | 5 | Met | Girindra Chatterjee | 49136
ST00084 | PRJ001 | CL001 | Hitachi Payment Services | Pune Site-084 | Pune | West | 100 | Installation Scheduled | 2025-07-31 | 2025-09-15 | 2025-09-13 | 2025-09-27 |  | 7 | Met | Ranveer Yadav | 179542
ST00085 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-001 | Patna | East | 20 | Live | 2025-08-29 | 2025-10-20 | 2025-10-21 | 2025-11-10 | 2025-11-18 | 1 | Met | Devika Rastogi | 71949
ST00086 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-002 | Kolkata | East | 20 | Installation Scheduled | 2025-08-18 | 2025-10-15 | 2025-10-14 | 2025-11-14 |  | 1 | Met | Wahab Raval | 166622
ST00087 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-003 | Patna | East | 20 | Live | 2025-08-27 | 2025-10-22 | 2025-10-27 | 2025-11-21 | 2025-11-28 | 5 | Met | Bhavika Sampath | 62900
ST00088 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-004 | Bhubaneswar | East | 200 | Installation Done | 2025-08-22 | 2025-09-28 | 2025-09-24 | 2025-10-19 |  | 12 | Marginal | Priya Rastogi | 126371
ST00089 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-005 | Bhubaneswar | East | 10 | Installation Done | 2025-08-14 | 2025-09-26 | 2025-09-30 | 2025-10-08 |  | 12 | Marginal | Yatin Baral | 145789
ST00090 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-006 | Bhubaneswar | East | 20 | Testing | 2025-09-07 | 2025-09-29 | 2025-10-08 | 2025-10-27 |  | 12 | Marginal | Girindra Chatterjee | 203598
ST00091 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-007 | Bhubaneswar | East | 10 | Installation Done | 2025-08-14 | 2025-10-01 | 2025-09-29 | 2025-10-21 |  | 12 | Marginal | Yatin Baral | 214378
ST00092 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-008 | Kolkata | East | 200 | Survey Pending | 2025-09-04 | 2025-10-22 |  | 2025-11-15 |  | 8 | Marginal | Yashica Issac | 140393
ST00093 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-009 | Bhubaneswar | East | 50 | Pending Acceptance | 2025-08-25 | 2025-10-10 | 2025-10-15 | 2025-11-08 | 2025-11-06 | 5 | Met | Liam Koshy | 131426
ST00094 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-010 | Kolkata | East | 20 | Testing | 2025-08-25 | 2025-10-02 | 2025-10-05 | 2025-10-31 |  | 12 | Marginal | Irya Sampath | 66365
ST00095 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-011 | Patna | East | 50 | Live | 2025-08-24 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-15 | 7 | Met | Arya Shere | 213687
ST00096 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-012 | Bhubaneswar | East | 200 | Live | 2025-09-03 | 2025-10-26 | 2025-10-23 | 2025-11-25 | 2025-12-05 | 0 | Met | Ranveer Yadav | 49779
ST00097 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-013 | Bhubaneswar | East | 20 | Installation Scheduled | 2025-08-19 | 2025-09-29 | 2025-10-09 | 2025-10-15 |  | 3 | Met | Yashica Cherian | 65228
ST00098 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-014 | Bhubaneswar | East | 200 | Live | 2025-08-16 | 2025-10-07 | 2025-10-03 | 2025-10-27 | 2025-10-28 | 0 | Met | Arya Shere | 85436
ST00099 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-015 | Kolkata | East | 10 | ROW In Progress | 2025-09-04 | 2025-11-02 |  | 2025-11-17 |  | 7 | Met | Niharika Sunder | 140498
ST00100 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-016 | Patna | East | 200 | Live | 2025-08-27 | 2025-10-25 | 2025-10-29 | 2025-11-18 | 2025-11-22 | 4 | Met | Devika Rastogi | 126125
ST00101 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-017 | Bhubaneswar | East | 100 | Live | 2025-08-19 | 2025-10-01 | 2025-10-10 | 2025-10-25 | 2025-10-31 | 9 | Marginal | Yatin Baral | 183270
ST00102 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-018 | Bhubaneswar | East | 100 | Pending Acceptance | 2025-08-19 | 2025-10-16 | 2025-10-15 | 2025-11-03 | 2025-11-01 | 0 | Met | Logan Sami | 190369
ST00103 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-019 | Kolkata | East | 50 | Live | 2025-08-29 | 2025-09-25 | 2025-09-29 | 2025-10-07 | 2025-10-09 | 4 | Met | Mohammed Gupta | 179572
ST00104 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-020 | Kolkata | East | 100 | Live | 2025-08-15 | 2025-09-18 | 2025-09-27 | 2025-10-09 | 2025-10-06 | 9 | Marginal | Simon Tata | 148928
ST00105 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-021 | Patna | East | 10 | Installation Done | 2025-08-25 | 2025-09-19 | 2025-09-25 | 2025-10-06 |  | 12 | Marginal | Urvashi Ray | 70974
ST00106 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-022 | Patna | East | 100 | Live | 2025-09-07 | 2025-10-06 | 2025-10-05 | 2025-10-17 | 2025-10-23 | 0 | Met | Radhika Dugar | 243925
ST00107 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-023 | Patna | East | 50 | Installation Done | 2025-09-01 | 2025-09-21 | 2025-09-18 | 2025-10-01 |  | 12 | Marginal | Kabir Soman | 263880
ST00108 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-024 | Kolkata | East | 50 | Testing | 2025-09-05 | 2025-11-02 | 2025-11-10 | 2025-11-15 |  | 12 | Marginal | Devika Rastogi | 123944
ST00109 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-025 | Kolkata | East | 10 | Survey Pending | 2025-08-26 | 2025-10-25 |  | 2025-11-23 |  | 7 | Met | Upadhriti Wadhwa | 264332
ST00110 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-026 | Bhubaneswar | East | 50 | Testing | 2025-08-13 | 2025-10-12 | 2025-10-14 | 2025-10-26 |  | 12 | Marginal | Nitesh Raghavan | 45410
ST00111 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-027 | Patna | East | 200 | Installation Done | 2025-08-31 | 2025-10-16 | 2025-10-16 | 2025-10-28 |  | 12 | Marginal | Ranveer Yadav | 62741
ST00112 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-028 | Patna | East | 100 | Testing | 2025-09-07 | 2025-10-29 | 2025-10-24 | 2025-11-20 |  | 12 | Marginal | Dominic Kakar | 211637
ST00113 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-029 | Bhubaneswar | East | 20 | Pending Acceptance | 2025-08-21 | 2025-09-11 | 2025-09-17 | 2025-09-23 | 2025-10-01 | 6 | Met | Devansh Rajan | 247244
ST00114 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-030 | Patna | East | 20 | Live | 2025-08-23 | 2025-09-20 | 2025-09-16 | 2025-10-11 | 2025-10-18 | 0 | Met | Dipta Bhandari | 227292
ST00115 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-031 | Bhubaneswar | East | 50 | Live | 2025-09-07 | 2025-10-05 | 2025-10-02 | 2025-10-29 | 2025-10-27 | 0 | Met | Farhan Chada | 56483
ST00116 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-032 | Kolkata | East | 50 | Live | 2025-08-23 | 2025-10-01 | 2025-10-08 | 2025-10-28 | 2025-11-09 | 7 | Met | Diya Rattan | 242470
ST00117 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-033 | Patna | East | 50 | ROW In Progress | 2025-08-24 | 2025-09-16 |  | 2025-10-16 |  | 5 | Met | Advay Contractor | 254542
ST00118 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-034 | Bhubaneswar | East | 20 | Installation Done | 2025-08-25 | 2025-10-12 | 2025-10-19 | 2025-11-01 |  | 12 | Marginal | Wahab Raval | 226421
ST00119 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-035 | Bhubaneswar | East | 100 | Installation Done | 2025-09-07 | 2025-10-30 | 2025-11-02 | 2025-11-11 |  | 12 | Marginal | Theodore Devi | 157881
ST00120 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-036 | Patna | East | 10 | Pending Acceptance | 2025-08-18 | 2025-10-11 | 2025-10-15 | 2025-10-31 | 2025-10-31 | 4 | Met | Girindra Chatterjee | 218256
ST00121 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-037 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-09-01 | 2025-10-18 | 2025-10-18 | 2025-11-11 |  | 5 | Met | Dominic Kakar | 235530
ST00122 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-038 | Bhubaneswar | East | 100 | Testing | 2025-08-26 | 2025-10-02 | 2025-09-28 | 2025-10-14 |  | 12 | Marginal | Ranveer Yadav | 179502
ST00123 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-039 | Patna | East | 10 | Live | 2025-08-13 | 2025-09-11 | 2025-09-20 | 2025-09-22 | 2025-09-23 | 9 | Marginal | Devika Rastogi | 249083
ST00124 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-040 | Patna | East | 20 | Installation Done | 2025-08-25 | 2025-10-20 | 2025-10-16 | 2025-11-18 |  | 12 | Marginal | Mohammed Gupta | 142246
ST00125 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-041 | Bhubaneswar | East | 50 | Installation Done | 2025-08-15 | 2025-10-10 | 2025-10-09 | 2025-11-05 |  | 12 | Marginal | Chandresh Zachariah | 127414
ST00126 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-042 | Patna | East | 100 | Installation Scheduled | 2025-08-16 | 2025-09-06 | 2025-09-06 | 2025-10-01 |  | 8 | Marginal | Advay Contractor | 113623
ST00127 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-043 | Bhubaneswar | East | 10 | Live | 2025-08-19 | 2025-10-17 | 2025-10-21 | 2025-11-11 | 2025-11-14 | 4 | Met | Radhika Dugar | 268563
ST00128 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-044 | Kolkata | East | 50 | Installation Done | 2025-09-04 | 2025-10-22 | 2025-10-19 | 2025-11-11 |  | 12 | Marginal | Liam Koshy | 189178
ST00129 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-045 | Patna | East | 20 | Installation Scheduled | 2025-08-22 | 2025-09-21 | 2025-09-21 | 2025-10-12 |  | 8 | Marginal | Advay Contractor | 97685
ST00130 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-046 | Kolkata | East | 100 | Installation Scheduled | 2025-08-28 | 2025-09-18 | 2025-09-24 | 2025-10-15 |  | 5 | Met | Harini Choudhury | 205418
ST00131 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-047 | Kolkata | East | 100 | Survey Pending | 2025-08-25 | 2025-10-14 |  | 2025-11-09 |  | 6 | Met | Priya Rastogi | 77853
ST00132 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-048 | Bhubaneswar | East | 20 | Live | 2025-08-27 | 2025-10-15 | 2025-10-21 | 2025-10-29 | 2025-10-31 | 6 | Met | Madhavi Lanka | 176822
ST00133 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-049 | Kolkata | East | 50 | Live | 2025-08-29 | 2025-09-27 | 2025-10-01 | 2025-10-12 | 2025-10-14 | 4 | Met | Alka Wable | 135707
ST00134 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-050 | Patna | East | 20 | Live | 2025-08-15 | 2025-09-20 | 2025-09-21 | 2025-10-20 | 2025-10-25 | 1 | Met | Arya Sunder | 206068
ST00135 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-051 | Patna | East | 20 | ROW In Progress | 2025-09-02 | 2025-10-02 |  | 2025-10-30 |  | 2 | Met | Unni Bhagat | 265864
ST00136 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-052 | Patna | East | 20 | Survey Pending | 2025-08-13 | 2025-09-07 |  | 2025-09-18 |  | 4 | Met | Tanay Rattan | 207033
ST00137 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-053 | Patna | East | 100 | Survey Pending | 2025-09-02 | 2025-10-26 |  | 2025-11-14 |  | 4 | Met | Raksha Varughese | 255944
ST00138 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-054 | Patna | East | 100 | Installation Done | 2025-08-27 | 2025-09-20 | 2025-09-16 | 2025-10-05 |  | 12 | Marginal | Tanay Rattan | 171943
ST00139 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-055 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-09-01 | 2025-09-30 | 2025-10-05 | 2025-10-20 |  | 5 | Met | Harini Choudhury | 244403
ST00140 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-056 | Bhubaneswar | East | 10 | Installation Done | 2025-08-16 | 2025-09-25 | 2025-09-27 | 2025-10-19 |  | 12 | Marginal | Victor Kannan | 162858
ST00141 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-057 | Kolkata | East | 20 | ROW In Progress | 2025-08-14 | 2025-09-21 |  | 2025-10-13 |  | 6 | Met | Yashica Issac | 258248
ST00142 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-058 | Bhubaneswar | East | 200 | Pending Acceptance | 2025-09-05 | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-11-11 | 1 | Met | Dipta Bhandari | 175746
ST00143 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-059 | Bhubaneswar | East | 20 | Installation Done | 2025-08-15 | 2025-09-29 | 2025-10-08 | 2025-10-16 |  | 12 | Marginal | Ikbal Kothari | 57755
ST00144 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-060 | Kolkata | East | 10 | Installation Scheduled | 2025-09-01 | 2025-10-21 | 2025-10-25 | 2025-11-17 |  | 0 | Met | Madhavi Lanka | 80110
ST00145 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-061 | Bhubaneswar | East | 10 | Live | 2025-09-06 | 2025-10-21 | 2025-10-27 | 2025-11-01 | 2025-11-10 | 6 | Met | Wriddhish Bhardwaj | 140033
ST00146 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-062 | Patna | East | 200 | Installation Scheduled | 2025-08-25 | 2025-10-16 | 2025-10-25 | 2025-11-12 |  | 4 | Met | Advay Contractor | 78728
ST00147 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-063 | Kolkata | East | 20 | Installation Done | 2025-09-07 | 2025-10-18 | 2025-10-24 | 2025-11-01 |  | 12 | Marginal | Girik Khalsa | 176092
ST00148 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-064 | Kolkata | East | 100 | Survey Pending | 2025-08-17 | 2025-09-27 |  | 2025-10-22 |  | 8 | Marginal | Yashica Cherian | 203927
ST00149 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-065 | Patna | East | 200 | ROW In Progress | 2025-09-01 | 2025-10-11 |  | 2025-10-26 |  | 6 | Met | Arya Sunder | 200641
ST00150 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-066 | Bhubaneswar | East | 50 | Installation Done | 2025-08-29 | 2025-10-22 | 2025-11-01 | 2025-11-19 |  | 12 | Marginal | Vansha Thakkar | 258843
ST00151 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-067 | Kolkata | East | 50 | Installation Done | 2025-09-03 | 2025-09-30 | 2025-10-08 | 2025-10-28 |  | 12 | Marginal | Daksh Karnik | 201476
ST00152 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-068 | Bhubaneswar | East | 20 | Installation Scheduled | 2025-09-02 | 2025-10-29 | 2025-10-31 | 2025-11-09 |  | 7 | Met | Arya Shere | 83738
ST00153 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-069 | Patna | East | 50 | Installation Scheduled | 2025-08-31 | 2025-09-27 | 2025-09-28 | 2025-10-07 |  | 7 | Met | Tanay Rattan | 84696
ST00154 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-070 | Bhubaneswar | East | 200 | Live | 2025-08-26 | 2025-10-17 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 10 | Marginal | Ekapad Walia | 192033
ST00155 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-071 | Bhubaneswar | East | 100 | Pending Acceptance | 2025-08-28 | 2025-10-20 | 2025-10-27 | 2025-11-09 | 2025-11-11 | 7 | Met | Unni Bhagat | 188202
ST00156 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-072 | Bhubaneswar | East | 50 | Live | 2025-09-05 | 2025-10-11 | 2025-10-21 | 2025-10-27 | 2025-10-31 | 10 | Marginal | Arya Sunder | 103947
ST00157 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-073 | Bhubaneswar | East | 50 | Live | 2025-09-04 | 2025-10-07 | 2025-10-17 | 2025-10-27 | 2025-11-08 | 10 | Marginal | Ekavir Bhargava | 120442
ST00158 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-074 | Kolkata | East | 20 | Testing | 2025-08-30 | 2025-10-13 | 2025-10-20 | 2025-11-03 |  | 12 | Marginal | Ekavir Varkey | 56027
ST00159 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-075 | Bhubaneswar | East | 100 | Pending Acceptance | 2025-08-15 | 2025-09-26 | 2025-10-05 | 2025-10-26 | 2025-10-31 | 9 | Marginal | Kabir Soman | 97970
ST00160 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-076 | Patna | East | 20 | Installation Scheduled | 2025-08-30 | 2025-10-06 | 2025-10-05 | 2025-10-19 |  | 3 | Met | Simon Tata | 220592
ST00161 | PRJ002 | CL001 | Hitachi Payment Services | Patna Site-077 | Patna | East | 100 | Installation Scheduled | 2025-08-20 | 2025-09-12 | 2025-09-10 | 2025-10-05 |  | 5 | Met | Michael Dutta | 223570
ST00162 | PRJ002 | CL001 | Hitachi Payment Services | Kolkata Site-078 | Kolkata | East | 100 | Survey Pending | 2025-08-30 | 2025-09-29 |  | 2025-10-22 |  | 7 | Met | Farhan Chada | 243157
ST00163 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-079 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-09-02 | 2025-09-25 | 2025-09-22 | 2025-10-25 |  | 3 | Met | Diya Rattan | 90892
ST00164 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-080 | Bhubaneswar | East | 50 | Live | 2025-08-18 | 2025-09-09 | 2025-09-16 | 2025-10-04 | 2025-10-06 | 7 | Met | Diya Rattan | 47429
ST00165 | PRJ002 | CL001 | Hitachi Payment Services | Bhubaneswar Site-081 | Bhubaneswar | East | 200 | Testing | 2025-08-16 | 2025-09-26 | 2025-09-30 | 2025-10-20 |  | 12 | Marginal | Wahab Raval | 278114
ST00166 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-001 | Indore | Central | 50 | ROW In Progress | 2025-07-13 | 2025-09-01 |  | 2025-09-18 |  | 3 | Met | Aarush Lall | 256229
ST00167 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-002 | Indore | Central | 100 | Pending Acceptance | 2025-07-13 | 2025-08-28 | 2025-09-05 | 2025-09-24 | 2025-09-25 | 8 | Marginal | Raksha Varughese | 111845
ST00168 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-003 | Bhopal | Central | 20 | Installation Scheduled | 2025-06-28 | 2025-08-15 | 2025-08-21 | 2025-08-27 |  | 8 | Marginal | Simon Tata | 115375
ST00169 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-004 | Indore | Central | 100 | Live | 2025-07-15 | 2025-08-06 | 2025-08-03 | 2025-08-22 | 2025-08-25 | 0 | Met | Ekapad Walia | 272927
ST00170 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-005 | Indore | Central | 20 | Installation Scheduled | 2025-06-26 | 2025-07-29 | 2025-07-30 | 2025-08-11 |  | 7 | Met | Ekapad Walia | 148974
ST00171 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-006 | Bhopal | Central | 200 | Testing | 2025-07-20 | 2025-08-27 | 2025-09-03 | 2025-09-20 |  | 12 | Marginal | Ikbal Kothari | 125851
ST00172 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-007 | Indore | Central | 50 | Installation Done | 2025-07-11 | 2025-08-29 | 2025-08-27 | 2025-09-23 |  | 12 | Marginal | Ekapad Walia | 142178
ST00173 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-008 | Indore | Central | 50 | Installation Done | 2025-07-14 | 2025-08-17 | 2025-08-16 | 2025-08-27 |  | 12 | Marginal | Tanay Rattan | 122382
ST00174 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-009 | Bhopal | Central | 100 | ROW In Progress | 2025-07-03 | 2025-08-16 |  | 2025-09-13 |  | 3 | Met | Unni Bhagat | 112456
ST00175 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-010 | Indore | Central | 20 | Pending Acceptance | 2025-07-16 | 2025-09-05 | 2025-09-14 | 2025-09-20 | 2025-09-28 | 9 | Marginal | Radhika Dugar | 233825
ST00176 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-011 | Nagpur | Central | 10 | Installation Done | 2025-07-13 | 2025-08-05 | 2025-08-01 | 2025-08-17 |  | 12 | Marginal | Ekbal Garg | 153106
ST00177 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-012 | Bhopal | Central | 200 | Live | 2025-07-03 | 2025-07-27 | 2025-07-26 | 2025-08-06 | 2025-08-09 | 0 | Met | Teerth Bhardwaj | 142832
ST00178 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-013 | Bhopal | Central | 10 | Testing | 2025-07-17 | 2025-09-14 | 2025-09-24 | 2025-10-09 |  | 12 | Marginal | Ekbal Garg | 184516
ST00179 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-014 | Nagpur | Central | 50 | Installation Done | 2025-06-26 | 2025-08-18 | 2025-08-21 | 2025-09-14 |  | 12 | Marginal | Anamika Kanda | 176652
ST00180 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-015 | Nagpur | Central | 20 | Live | 2025-07-21 | 2025-08-21 | 2025-08-19 | 2025-09-03 | 2025-09-04 | 0 | Met | Wriddhish Bhardwaj | 207471
ST00181 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-016 | Nagpur | Central | 100 | Installation Scheduled | 2025-07-07 | 2025-08-13 | 2025-08-20 | 2025-08-25 |  | 5 | Met | Teerth Bhardwaj | 193111
ST00182 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-017 | Bhopal | Central | 10 | Pending Acceptance | 2025-07-03 | 2025-08-11 | 2025-08-08 | 2025-09-10 | 2025-09-08 | 0 | Met | Girik Khalsa | 144421
ST00183 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-018 | Indore | Central | 10 | Testing | 2025-06-27 | 2025-08-26 | 2025-08-21 | 2025-09-10 |  | 12 | Marginal | Wahab Raval | 266598
ST00184 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-019 | Indore | Central | 20 | Live | 2025-07-06 | 2025-08-31 | 2025-08-29 | 2025-09-26 | 2025-09-24 | 0 | Met | Kabir Soman | 272571
ST00185 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-020 | Nagpur | Central | 200 | Live | 2025-07-11 | 2025-08-17 | 2025-08-13 | 2025-08-29 | 2025-09-03 | 0 | Met | Diya Rattan | 92016
ST00186 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-021 | Indore | Central | 10 | Survey Pending | 2025-07-02 | 2025-08-28 |  | 2025-09-11 |  | 6 | Met | Arya Sunder | 87585
ST00187 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-022 | Nagpur | Central | 10 | Installation Scheduled | 2025-07-08 | 2025-08-31 | 2025-09-05 | 2025-09-22 |  | 2 | Met | Yatin Baral | 240416
ST00188 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-023 | Indore | Central | 200 | Survey Pending | 2025-07-09 | 2025-08-12 |  | 2025-08-24 |  | 5 | Met | Chandresh Zachariah | 247782
ST00189 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-024 | Indore | Central | 50 | Survey Pending | 2025-07-04 | 2025-08-21 |  | 2025-09-15 |  | 3 | Met | Arya Shere | 158206
ST00190 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-025 | Bhopal | Central | 20 | Live | 2025-07-17 | 2025-08-30 | 2025-08-27 | 2025-09-28 | 2025-10-04 | 0 | Met | Priya Rastogi | 66505
ST00191 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-026 | Indore | Central | 50 | ROW In Progress | 2025-07-18 | 2025-09-16 |  | 2025-09-30 |  | 6 | Met | Ranveer Yadav | 72931
ST00192 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-027 | Bhopal | Central | 10 | Survey Pending | 2025-07-05 | 2025-08-22 |  | 2025-09-12 |  | 4 | Met | Harini Choudhury | 67884
ST00193 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-028 | Bhopal | Central | 10 | Installation Done | 2025-07-13 | 2025-09-06 | 2025-09-14 | 2025-09-19 |  | 12 | Marginal | Gavin Batta | 137776
ST00194 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-029 | Nagpur | Central | 50 | ROW In Progress | 2025-07-15 | 2025-08-24 |  | 2025-09-15 |  | 0 | Met | Niharika Sunder | 146659
ST00195 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-030 | Bhopal | Central | 20 | Live | 2025-07-13 | 2025-08-17 | 2025-08-17 | 2025-09-08 | 2025-09-10 | 0 | Met | Victor Kannan | 123939
ST00196 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-031 | Indore | Central | 100 | Installation Done | 2025-06-28 | 2025-07-28 | 2025-08-05 | 2025-08-15 |  | 12 | Marginal | Arya Sunder | 171938
ST00197 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-032 | Bhopal | Central | 200 | Installation Done | 2025-07-03 | 2025-09-01 | 2025-09-11 | 2025-09-30 |  | 12 | Marginal | Farhan Chada | 165025
ST00198 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-033 | Bhopal | Central | 50 | ROW In Progress | 2025-06-26 | 2025-08-10 |  | 2025-08-30 |  | 6 | Met | Bhavika Sampath | 132749
ST00199 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-034 | Indore | Central | 200 | Live | 2025-07-16 | 2025-09-12 | 2025-09-11 | 2025-10-01 | 2025-10-08 | 0 | Met | Farhan Chada | 170569
ST00200 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-035 | Indore | Central | 200 | ROW In Progress | 2025-07-08 | 2025-08-17 |  | 2025-09-05 |  | 7 | Met | Raksha Varughese | 130429
ST00201 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-036 | Indore | Central | 200 | Installation Scheduled | 2025-07-21 | 2025-09-04 | 2025-09-10 | 2025-09-17 |  | 3 | Met | Isaac Patil | 223706
ST00202 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-037 | Nagpur | Central | 50 | Survey Pending | 2025-07-19 | 2025-09-06 |  | 2025-09-22 |  | 7 | Met | Liam Koshy | 259686
ST00203 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-038 | Indore | Central | 20 | Live | 2025-06-30 | 2025-08-29 | 2025-09-02 | 2025-09-15 | 2025-09-20 | 4 | Met | Nitesh Raghavan | 251851
ST00204 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-039 | Indore | Central | 200 | Survey Pending | 2025-07-15 | 2025-09-03 |  | 2025-10-01 |  | 6 | Met | Yatin Baral | 272969
ST00205 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-040 | Nagpur | Central | 20 | Installation Done | 2025-06-27 | 2025-08-09 | 2025-08-06 | 2025-08-22 |  | 12 | Marginal | Ikbal Kothari | 88604
ST00206 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-041 | Nagpur | Central | 10 | Testing | 2025-07-14 | 2025-08-28 | 2025-09-02 | 2025-09-20 |  | 12 | Marginal | Nihal Shere | 70849
ST00207 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-042 | Indore | Central | 100 | Installation Scheduled | 2025-07-19 | 2025-09-10 | 2025-09-12 | 2025-10-04 |  | 5 | Met | Dipta Bhandari | 247464
ST00208 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-043 | Nagpur | Central | 100 | Testing | 2025-07-12 | 2025-08-10 | 2025-08-16 | 2025-08-20 |  | 12 | Marginal | Devansh Rajan | 122445
ST00209 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-044 | Indore | Central | 50 | Pending Acceptance | 2025-06-28 | 2025-07-25 | 2025-07-24 | 2025-08-15 | 2025-08-21 | 0 | Met | Teerth Bhardwaj | 250591
ST00210 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-045 | Bhopal | Central | 100 | Installation Done | 2025-07-07 | 2025-08-26 | 2025-08-24 | 2025-09-19 |  | 12 | Marginal | Urvashi Ray | 62609
ST00211 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-046 | Indore | Central | 10 | Survey Pending | 2025-07-18 | 2025-08-14 |  | 2025-08-24 |  | 5 | Met | Kashvi Edwin | 239114
ST00212 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-047 | Bhopal | Central | 100 | Installation Done | 2025-07-13 | 2025-08-12 | 2025-08-17 | 2025-09-08 |  | 12 | Marginal | Dipta Bhandari | 105779
ST00213 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-048 | Indore | Central | 10 | Testing | 2025-07-01 | 2025-08-30 | 2025-09-07 | 2025-09-21 |  | 12 | Marginal | Farhan Chada | 162853
ST00214 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-049 | Nagpur | Central | 10 | Installation Done | 2025-06-26 | 2025-07-29 | 2025-07-30 | 2025-08-16 |  | 12 | Marginal | Devansh Rajan | 254584
ST00215 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-050 | Nagpur | Central | 50 | ROW In Progress | 2025-07-06 | 2025-08-07 |  | 2025-08-31 |  | 1 | Met | Quincy Biswas | 183337
ST00216 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-051 | Nagpur | Central | 50 | Installation Scheduled | 2025-07-08 | 2025-09-05 | 2025-09-12 | 2025-10-03 |  | 1 | Met | Ikbal Kothari | 266647
ST00217 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-052 | Indore | Central | 50 | Testing | 2025-07-17 | 2025-08-25 | 2025-08-22 | 2025-09-08 |  | 12 | Marginal | Advay Contractor | 107540
ST00218 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-053 | Indore | Central | 100 | ROW In Progress | 2025-07-07 | 2025-08-05 |  | 2025-08-31 |  | 6 | Met | Radhika Dugar | 195681
ST00219 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-054 | Indore | Central | 20 | Installation Done | 2025-07-11 | 2025-09-09 | 2025-09-09 | 2025-10-06 |  | 12 | Marginal | Quincy Biswas | 120716
ST00220 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-055 | Bhopal | Central | 10 | ROW In Progress | 2025-07-10 | 2025-09-07 |  | 2025-09-18 |  | 5 | Met | Quincy Biswas | 80791
ST00221 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-056 | Bhopal | Central | 100 | Live | 2025-07-13 | 2025-09-03 | 2025-09-13 | 2025-09-26 | 2025-10-08 | 10 | Marginal | Bhavika Sampath | 173109
ST00222 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-057 | Bhopal | Central | 50 | ROW In Progress | 2025-06-26 | 2025-07-30 |  | 2025-08-18 |  | 0 | Met | Alka Wable | 185930
ST00223 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-058 | Indore | Central | 200 | ROW In Progress | 2025-07-10 | 2025-09-04 |  | 2025-09-29 |  | 8 | Marginal | Upadhriti Wadhwa | 195133
ST00224 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-059 | Bhopal | Central | 20 | Installation Scheduled | 2025-07-13 | 2025-08-25 | 2025-08-21 | 2025-09-18 |  | 8 | Marginal | Nitesh Raghavan | 71847
ST00225 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-060 | Nagpur | Central | 50 | Live | 2025-07-20 | 2025-08-24 | 2025-08-28 | 2025-09-04 | 2025-09-15 | 4 | Met | Darsh Rau | 271020
ST00226 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-061 | Bhopal | Central | 50 | Installation Done | 2025-06-29 | 2025-08-03 | 2025-08-04 | 2025-08-31 |  | 12 | Marginal | Nitesh Raghavan | 88511
ST00227 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-062 | Nagpur | Central | 200 | ROW In Progress | 2025-07-02 | 2025-08-04 |  | 2025-08-15 |  | 5 | Met | Ekavir Bhargava | 201462
ST00228 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-063 | Nagpur | Central | 200 | ROW In Progress | 2025-07-18 | 2025-08-25 |  | 2025-09-13 |  | 4 | Met | Michael Dutta | 80543
ST00229 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-064 | Indore | Central | 50 | Pending Acceptance | 2025-07-04 | 2025-08-01 | 2025-07-31 | 2025-08-18 | 2025-08-19 | 0 | Met | Raksha Varughese | 244615
ST00230 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-065 | Nagpur | Central | 100 | Installation Done | 2025-06-30 | 2025-08-25 | 2025-08-28 | 2025-09-24 |  | 12 | Marginal | Arya Shere | 163486
ST00231 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-066 | Bhopal | Central | 50 | Live | 2025-07-20 | 2025-08-14 | 2025-08-21 | 2025-09-09 | 2025-09-14 | 7 | Met | Teerth Bhardwaj | 172937
ST00232 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-067 | Indore | Central | 50 | Testing | 2025-07-20 | 2025-08-14 | 2025-08-23 | 2025-09-13 |  | 12 | Marginal | Liam Koshy | 253582
ST00233 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-068 | Nagpur | Central | 50 | Installation Done | 2025-07-09 | 2025-08-11 | 2025-08-21 | 2025-08-29 |  | 12 | Marginal | Ekansh Balay | 133540
ST00234 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-069 | Nagpur | Central | 10 | Testing | 2025-07-14 | 2025-09-03 | 2025-09-08 | 2025-09-14 |  | 12 | Marginal | Michael Dutta | 209149
ST00235 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-070 | Indore | Central | 100 | Survey Pending | 2025-07-01 | 2025-08-18 |  | 2025-09-11 |  | 0 | Met | Farhan Chada | 225510
ST00236 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-071 | Bhopal | Central | 50 | Live | 2025-07-05 | 2025-08-04 | 2025-08-07 | 2025-08-16 | 2025-08-24 | 3 | Met | Theodore Devi | 142476
ST00237 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-072 | Nagpur | Central | 20 | Live | 2025-07-01 | 2025-07-24 | 2025-07-31 | 2025-08-23 | 2025-08-29 | 7 | Met | Nitesh Raghavan | 216831
ST00238 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-073 | Bhopal | Central | 200 | Live | 2025-06-26 | 2025-07-29 | 2025-08-08 | 2025-08-10 | 2025-08-11 | 10 | Marginal | Alka Wable | 181169
ST00239 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-074 | Nagpur | Central | 20 | Installation Done | 2025-06-26 | 2025-08-06 | 2025-08-04 | 2025-08-29 |  | 12 | Marginal | Dakshesh Trivedi | 63567
ST00240 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-075 | Bhopal | Central | 50 | Installation Done | 2025-07-19 | 2025-08-14 | 2025-08-12 | 2025-09-03 |  | 12 | Marginal | Arya Sunder | 80947
ST00241 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-076 | Indore | Central | 200 | Live | 2025-07-20 | 2025-08-17 | 2025-08-16 | 2025-08-29 | 2025-08-26 | 0 | Met | Kashvi Edwin | 160369
ST00242 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-077 | Indore | Central | 20 | Live | 2025-07-16 | 2025-08-14 | 2025-08-22 | 2025-09-12 | 2025-09-23 | 8 | Marginal | Gavin Batta | 71336
ST00243 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-078 | Bhopal | Central | 20 | Live | 2025-07-14 | 2025-08-27 | 2025-09-02 | 2025-09-19 | 2025-09-26 | 6 | Met | Raksha Varughese | 117605
ST00244 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-079 | Nagpur | Central | 10 | ROW In Progress | 2025-07-13 | 2025-09-09 |  | 2025-10-08 |  | 4 | Met | Arya Sunder | 98856
ST00245 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-080 | Nagpur | Central | 10 | Testing | 2025-07-02 | 2025-08-16 | 2025-08-20 | 2025-09-15 |  | 12 | Marginal | Devika Rastogi | 174731
ST00246 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-081 | Indore | Central | 200 | ROW In Progress | 2025-07-11 | 2025-09-09 |  | 2025-10-08 |  | 1 | Met | Nihal Shere | 139659
ST00247 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-082 | Indore | Central | 20 | ROW In Progress | 2025-07-14 | 2025-08-29 |  | 2025-09-19 |  | 8 | Marginal | Vansha Thakkar | 246947
ST00248 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-083 | Bhopal | Central | 10 | Survey Pending | 2025-06-28 | 2025-07-18 |  | 2025-08-05 |  | 3 | Met | Tara Dhar | 251907
ST00249 | PRJ003 | CL001 | Hitachi Payment Services | Indore Site-084 | Indore | Central | 100 | Installation Done | 2025-07-16 | 2025-09-06 | 2025-09-14 | 2025-09-29 |  | 12 | Marginal | Theodore Devi | 212913
ST00250 | PRJ003 | CL001 | Hitachi Payment Services | Nagpur Site-085 | Nagpur | Central | 10 | Testing | 2025-06-30 | 2025-08-06 | 2025-08-03 | 2025-08-25 |  | 12 | Marginal | Ekapad Walia | 256828
ST00251 | PRJ003 | CL001 | Hitachi Payment Services | Bhopal Site-086 | Bhopal | Central | 100 | Testing | 2025-07-08 | 2025-09-03 | 2025-08-31 | 2025-09-22 |  | 12 | Marginal | Devika Rastogi | 60179
ST00252 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-001 | Kolkata | East | 200 | ROW In Progress | 2025-07-30 | 2025-09-11 |  | 2025-10-11 |  | 1 | Met | Devansh Nigam | 258056
ST00253 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-002 | Kolkata | East | 20 | Survey Pending | 2025-07-20 | 2025-08-21 |  | 2025-09-20 |  | 7 | Met | Gavin Batta | 267108
ST00254 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-003 | Bhubaneswar | East | 100 | ROW In Progress | 2025-08-01 | 2025-08-24 |  | 2025-09-08 |  | 6 | Met | Wahab Raval | 52728
ST00255 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-004 | Bhubaneswar | East | 50 | Live | 2025-07-23 | 2025-09-03 | 2025-09-04 | 2025-09-18 | 2025-09-23 | 1 | Met | Mohammed Gupta | 276584
ST00256 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-005 | Kolkata | East | 100 | Survey Pending | 2025-08-06 | 2025-10-04 |  | 2025-10-21 |  | 4 | Met | Niharika Sunder | 276415
ST00257 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-006 | Patna | East | 100 | Installation Done | 2025-07-20 | 2025-08-26 | 2025-09-02 | 2025-09-09 |  | 12 | Marginal | Farhan Chada | 213467
ST00258 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-007 | Patna | East | 100 | Installation Scheduled | 2025-08-12 | 2025-10-05 | 2025-09-30 | 2025-10-27 |  | 5 | Met | Quincy Biswas | 135186
ST00259 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-008 | Patna | East | 50 | Installation Done | 2025-07-30 | 2025-09-05 | 2025-09-05 | 2025-09-15 |  | 12 | Marginal | Alka Wable | 52681
ST00260 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-009 | Bhubaneswar | East | 20 | Survey Pending | 2025-08-02 | 2025-09-24 |  | 2025-10-15 |  | 3 | Met | Michael Dutta | 109974
ST00261 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-010 | Patna | East | 50 | Installation Scheduled | 2025-08-04 | 2025-08-27 | 2025-08-29 | 2025-09-24 |  | 6 | Met | Ekiya Suresh | 91163
ST00262 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-011 | Kolkata | East | 200 | Testing | 2025-08-12 | 2025-09-23 | 2025-09-18 | 2025-10-14 |  | 12 | Marginal | Aarush Lall | 192615
ST00263 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-012 | Kolkata | East | 10 | Live | 2025-08-12 | 2025-10-02 | 2025-10-06 | 2025-10-17 | 2025-10-29 | 4 | Met | Gavin Batta | 59724
ST00264 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-013 | Kolkata | East | 50 | Testing | 2025-07-18 | 2025-09-09 | 2025-09-19 | 2025-09-19 |  | 12 | Marginal | Farhan Chada | 256404
ST00265 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-014 | Kolkata | East | 200 | Installation Scheduled | 2025-07-23 | 2025-09-01 | 2025-08-28 | 2025-09-11 |  | 2 | Met | Aarush Lall | 247995
ST00266 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-015 | Kolkata | East | 50 | Live | 2025-07-29 | 2025-08-22 | 2025-08-28 | 2025-09-13 | 2025-09-13 | 6 | Met | Arya Sunder | 129568
ST00267 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-016 | Kolkata | East | 20 | Pending Acceptance | 2025-08-10 | 2025-09-26 | 2025-10-06 | 2025-10-26 | 2025-11-02 | 10 | Marginal | Ikbal Kothari | 103520
ST00268 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-017 | Patna | East | 20 | Testing | 2025-07-23 | 2025-09-05 | 2025-09-09 | 2025-09-24 |  | 12 | Marginal | Ekiya Suresh | 236058
ST00269 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-018 | Kolkata | East | 200 | Pending Acceptance | 2025-08-05 | 2025-09-19 | 2025-09-15 | 2025-10-04 | 2025-10-11 | 0 | Met | Alka Wable | 212679
ST00270 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-019 | Patna | East | 20 | ROW In Progress | 2025-08-02 | 2025-08-31 |  | 2025-09-20 |  | 1 | Met | Darsh Rau | 128759
ST00271 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-020 | Kolkata | East | 50 | Live | 2025-07-20 | 2025-09-18 | 2025-09-23 | 2025-10-12 | 2025-10-09 | 5 | Met | Ekapad Walia | 110415
ST00272 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-021 | Patna | East | 100 | Survey Pending | 2025-07-26 | 2025-08-21 |  | 2025-08-31 |  | 0 | Met | Bhavika Sampath | 237042
ST00273 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-022 | Bhubaneswar | East | 10 | Pending Acceptance | 2025-07-31 | 2025-09-20 | 2025-09-27 | 2025-10-11 | 2025-10-20 | 7 | Met | Dakshesh Trivedi | 251760
ST00274 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-023 | Patna | East | 10 | Live | 2025-08-08 | 2025-09-11 | 2025-09-11 | 2025-10-05 | 2025-10-04 | 0 | Met | Ekavir Varkey | 50263
ST00275 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-024 | Bhubaneswar | East | 20 | Installation Scheduled | 2025-07-21 | 2025-08-14 | 2025-08-19 | 2025-08-29 |  | 6 | Met | Priya Rastogi | 188404
ST00276 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-025 | Kolkata | East | 200 | Installation Scheduled | 2025-08-06 | 2025-09-25 | 2025-09-20 | 2025-10-18 |  | 2 | Met | Madhavi Lanka | 86183
ST00277 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-026 | Kolkata | East | 200 | ROW In Progress | 2025-07-24 | 2025-08-25 |  | 2025-09-17 |  | 8 | Marginal | Devansh Nigam | 218171
ST00278 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-027 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-07-21 | 2025-08-13 | 2025-08-20 | 2025-09-10 |  | 8 | Marginal | Yashica Cherian | 59288
ST00279 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-028 | Bhubaneswar | East | 20 | Survey Pending | 2025-07-20 | 2025-08-27 |  | 2025-09-26 |  | 7 | Met | Michael Dutta | 51746
ST00280 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-029 | Kolkata | East | 50 | ROW In Progress | 2025-07-27 | 2025-08-21 |  | 2025-09-15 |  | 1 | Met | Chandresh Zachariah | 168455
ST00281 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-030 | Bhubaneswar | East | 100 | Live | 2025-07-26 | 2025-08-20 | 2025-08-27 | 2025-09-04 | 2025-09-12 | 7 | Met | Logan Sami | 93911
ST00282 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-031 | Bhubaneswar | East | 50 | Survey Pending | 2025-08-01 | 2025-09-19 |  | 2025-10-07 |  | 3 | Met | Tara Dhar | 84617
ST00283 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-032 | Patna | East | 200 | Live | 2025-07-20 | 2025-08-31 | 2025-09-08 | 2025-09-28 | 2025-10-02 | 8 | Marginal | Tara Dhar | 265409
ST00284 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-033 | Bhubaneswar | East | 100 | Live | 2025-07-31 | 2025-09-23 | 2025-10-03 | 2025-10-21 | 2025-10-25 | 10 | Marginal | Arya Sunder | 65697
ST00285 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-034 | Bhubaneswar | East | 20 | Live | 2025-08-09 | 2025-08-31 | 2025-08-30 | 2025-09-13 | 2025-09-24 | 0 | Met | Kashvi Edwin | 100545
ST00286 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-035 | Kolkata | East | 20 | ROW In Progress | 2025-07-31 | 2025-08-25 |  | 2025-09-17 |  | 3 | Met | Devansh Nigam | 128820
ST00287 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-036 | Patna | East | 200 | Pending Acceptance | 2025-07-20 | 2025-08-14 | 2025-08-21 | 2025-09-10 | 2025-09-19 | 7 | Met | Girindra Chatterjee | 269558
ST00288 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-037 | Bhubaneswar | East | 100 | Installation Done | 2025-07-18 | 2025-09-15 | 2025-09-23 | 2025-09-28 |  | 12 | Marginal | Yashica Cherian | 83849
ST00289 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-038 | Patna | East | 10 | Testing | 2025-08-11 | 2025-09-06 | 2025-09-04 | 2025-10-04 |  | 12 | Marginal | Ekansh Balay | 272403
ST00290 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-039 | Patna | East | 200 | Live | 2025-07-31 | 2025-09-05 | 2025-09-12 | 2025-10-05 | 2025-10-17 | 7 | Met | Vansha Thakkar | 54821
ST00291 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-040 | Kolkata | East | 50 | Installation Scheduled | 2025-07-22 | 2025-09-19 | 2025-09-26 | 2025-09-30 |  | 6 | Met | Devika Rastogi | 57921
ST00292 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-041 | Patna | East | 50 | Installation Done | 2025-07-26 | 2025-09-07 | 2025-09-02 | 2025-09-27 |  | 12 | Marginal | Kevin Solanki | 118491
ST00293 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-042 | Bhubaneswar | East | 100 | Live | 2025-08-08 | 2025-09-03 | 2025-09-05 | 2025-09-17 | 2025-09-23 | 2 | Met | Girindra Chatterjee | 115626
ST00294 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-043 | Patna | East | 20 | Installation Done | 2025-08-07 | 2025-09-01 | 2025-09-02 | 2025-09-25 |  | 12 | Marginal | Niharika Sunder | 239234
ST00295 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-044 | Bhubaneswar | East | 200 | Live | 2025-07-29 | 2025-08-21 | 2025-08-21 | 2025-09-02 | 2025-09-08 | 0 | Met | Girik Khalsa | 80559
ST00296 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-045 | Patna | East | 20 | Live | 2025-07-18 | 2025-08-18 | 2025-08-19 | 2025-09-03 | 2025-09-01 | 1 | Met | Diya Rattan | 164655
ST00297 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-046 | Kolkata | East | 200 | Pending Acceptance | 2025-08-09 | 2025-09-10 | 2025-09-13 | 2025-10-01 | 2025-10-12 | 3 | Met | Chandresh Zachariah | 211568
ST00298 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-047 | Kolkata | East | 20 | Live | 2025-07-25 | 2025-09-06 | 2025-09-16 | 2025-10-05 | 2025-10-16 | 10 | Marginal | Vansha Thakkar | 198847
ST00299 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-048 | Patna | East | 100 | Installation Scheduled | 2025-07-23 | 2025-08-28 | 2025-08-25 | 2025-09-16 |  | 0 | Met | Simon Tata | 87705
ST00300 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-049 | Patna | East | 100 | Live | 2025-07-24 | 2025-08-27 | 2025-08-29 | 2025-09-12 | 2025-09-17 | 2 | Met | Anamika Kanda | 271657
ST00301 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-050 | Patna | East | 20 | Survey Pending | 2025-07-22 | 2025-08-22 |  | 2025-09-20 |  | 0 | Met | Jai Kota | 204473
ST00302 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-051 | Bhubaneswar | East | 100 | Live | 2025-08-09 | 2025-09-15 | 2025-09-23 | 2025-10-07 | 2025-10-15 | 8 | Marginal | Jai Kota | 102202
ST00303 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-052 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-08-03 | 2025-10-01 | 2025-10-08 | 2025-10-29 |  | 1 | Met | Logan Sami | 192182
ST00304 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-053 | Patna | East | 10 | Testing | 2025-07-27 | 2025-09-04 | 2025-09-02 | 2025-09-29 |  | 12 | Marginal | Unni Bhagat | 117478
ST00305 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-054 | Patna | East | 200 | Installation Scheduled | 2025-07-26 | 2025-08-31 | 2025-09-04 | 2025-09-16 |  | 2 | Met | Devika Rastogi | 59883
ST00306 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-055 | Patna | East | 100 | Installation Done | 2025-07-28 | 2025-08-25 | 2025-08-20 | 2025-09-24 |  | 12 | Marginal | Ekavir Varkey | 113007
ST00307 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-056 | Bhubaneswar | East | 20 | Installation Done | 2025-08-10 | 2025-09-01 | 2025-09-02 | 2025-09-21 |  | 12 | Marginal | Vansha Thakkar | 221126
ST00308 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-057 | Bhubaneswar | East | 10 | Installation Done | 2025-07-23 | 2025-09-16 | 2025-09-16 | 2025-10-05 |  | 12 | Marginal | Vansha Thakkar | 78539
ST00309 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-058 | Patna | East | 20 | Installation Scheduled | 2025-08-12 | 2025-10-06 | 2025-10-06 | 2025-10-26 |  | 1 | Met | Ikbal Kothari | 103544
ST00310 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-059 | Patna | East | 100 | Live | 2025-07-31 | 2025-09-10 | 2025-09-16 | 2025-09-28 | 2025-10-04 | 6 | Met | Advay Contractor | 168348
ST00311 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-060 | Kolkata | East | 200 | Live | 2025-08-05 | 2025-10-01 | 2025-09-28 | 2025-10-26 | 2025-10-29 | 0 | Met | Advay Contractor | 272409
ST00312 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-061 | Patna | East | 20 | Installation Done | 2025-07-27 | 2025-09-11 | 2025-09-07 | 2025-09-25 |  | 12 | Marginal | Farhan Chada | 134828
ST00313 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-062 | Bhubaneswar | East | 100 | Pending Acceptance | 2025-08-01 | 2025-08-30 | 2025-09-04 | 2025-09-14 | 2025-09-13 | 5 | Met | Irya Sampath | 210421
ST00314 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-063 | Kolkata | East | 20 | Installation Scheduled | 2025-07-19 | 2025-08-08 | 2025-08-17 | 2025-08-26 |  | 3 | Met | Yashica Issac | 173339
ST00315 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-064 | Kolkata | East | 100 | ROW In Progress | 2025-07-31 | 2025-09-29 |  | 2025-10-22 |  | 6 | Met | Dakshesh Trivedi | 145484
ST00316 | PRJ004 | CL001 | Hitachi Payment Services | Kolkata Site-065 | Kolkata | East | 200 | Survey Pending | 2025-07-24 | 2025-09-05 |  | 2025-09-15 |  | 5 | Met | Wriddhish Bhardwaj | 49696
ST00317 | PRJ004 | CL001 | Hitachi Payment Services | Patna Site-066 | Patna | East | 50 | Survey Pending | 2025-08-10 | 2025-09-14 |  | 2025-10-01 |  | 5 | Met | Harini Choudhury | 71924
ST00318 | PRJ004 | CL001 | Hitachi Payment Services | Bhubaneswar Site-067 | Bhubaneswar | East | 50 | Installation Done | 2025-07-27 | 2025-08-26 | 2025-08-23 | 2025-09-06 |  | 12 | Marginal | Ekavir Varkey | 164518
ST00319 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-001 | Pune | West | 100 | Survey Pending | 2025-07-12 | 2025-09-06 |  | 2025-09-30 |  | 1 | Met | Mohammed Gupta | 127853
ST00320 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-002 | Mumbai | West | 10 | Pending Acceptance | 2025-07-21 | 2025-08-11 | 2025-08-09 | 2025-09-02 | 2025-09-12 | 0 | Met | Ekbal Garg | 261507
ST00321 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-003 | Mumbai | West | 100 | Live | 2025-07-17 | 2025-09-15 | 2025-09-19 | 2025-10-11 | 2025-10-14 | 4 | Met | Unni Bhagat | 140248
ST00322 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-004 | Mumbai | West | 10 | Live | 2025-07-12 | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-23 | 10 | Marginal | Michael Dutta | 244051
ST00323 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-005 | Pune | West | 200 | Survey Pending | 2025-07-09 | 2025-09-07 |  | 2025-09-26 |  | 8 | Marginal | Logan Sami | 229050
ST00324 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-006 | Mumbai | West | 10 | Survey Pending | 2025-07-03 | 2025-08-23 |  | 2025-09-06 |  | 6 | Met | Jai Kota | 205131
ST00325 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-007 | Pune | West | 50 | ROW In Progress | 2025-07-10 | 2025-08-12 |  | 2025-09-05 |  | 3 | Met | Devansh Rajan | 243482
ST00326 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-008 | Surat | West | 100 | Survey Pending | 2025-07-18 | 2025-09-13 |  | 2025-09-26 |  | 7 | Met | Yatin Baral | 80294
ST00327 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-009 | Surat | West | 200 | Survey Pending | 2025-07-21 | 2025-08-13 |  | 2025-09-09 |  | 6 | Met | Dakshesh Trivedi | 178256
ST00328 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-010 | Pune | West | 200 | Live | 2025-07-03 | 2025-07-31 | 2025-07-29 | 2025-08-22 | 2025-08-29 | 0 | Met | Faqid Savant | 154750
ST00329 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-011 | Pune | West | 100 | Installation Scheduled | 2025-07-08 | 2025-08-15 | 2025-08-24 | 2025-08-29 |  | 2 | Met | Arya Sunder | 266006
ST00330 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-012 | Ahmedabad | West | 200 | Live | 2025-07-15 | 2025-09-13 | 2025-09-14 | 2025-09-29 | 2025-10-02 | 1 | Met | Ekavir Varkey | 224991
ST00331 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-013 | Ahmedabad | West | 200 | Pending Acceptance | 2025-07-02 | 2025-08-02 | 2025-08-07 | 2025-08-15 | 2025-08-23 | 5 | Met | Dakshesh Trivedi | 197779
ST00332 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-014 | Surat | West | 10 | Live | 2025-07-15 | 2025-08-22 | 2025-08-30 | 2025-09-01 | 2025-09-01 | 8 | Marginal | Arya Shere | 83096
ST00333 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-015 | Mumbai | West | 20 | Live | 2025-07-04 | 2025-08-10 | 2025-08-10 | 2025-08-29 | 2025-09-03 | 0 | Met | Tara Dhar | 226035
ST00334 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-016 | Ahmedabad | West | 200 | Installation Scheduled | 2025-07-15 | 2025-08-06 | 2025-08-12 | 2025-08-30 |  | 1 | Met | Alka Wable | 239619
ST00335 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-017 | Surat | West | 100 | Installation Scheduled | 2025-07-23 | 2025-08-30 | 2025-08-26 | 2025-09-21 |  | 6 | Met | Urvashi Ray | 189736
ST00336 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-018 | Mumbai | West | 20 | Survey Pending | 2025-07-06 | 2025-08-07 |  | 2025-09-05 |  | 7 | Met | Logan Sami | 242946
ST00337 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-019 | Pune | West | 20 | Live | 2025-07-04 | 2025-08-11 | 2025-08-20 | 2025-08-26 | 2025-08-25 | 9 | Marginal | Ekiya Suresh | 237696
ST00338 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-020 | Mumbai | West | 20 | Installation Done | 2025-07-11 | 2025-08-17 | 2025-08-20 | 2025-08-31 |  | 12 | Marginal | Jai Kota | 46479
ST00339 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-021 | Ahmedabad | West | 200 | Installation Done | 2025-07-02 | 2025-07-24 | 2025-07-23 | 2025-08-13 |  | 12 | Marginal | Simon Tata | 247810
ST00340 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-022 | Ahmedabad | West | 50 | Installation Done | 2025-07-16 | 2025-09-09 | 2025-09-15 | 2025-09-21 |  | 12 | Marginal | Alka Wable | 93200
ST00341 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-023 | Mumbai | West | 20 | Live | 2025-07-03 | 2025-08-18 | 2025-08-25 | 2025-08-30 | 2025-09-07 | 7 | Met | Kabir Soman | 218889
ST00342 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-024 | Ahmedabad | West | 10 | Installation Scheduled | 2025-07-07 | 2025-08-09 | 2025-08-19 | 2025-09-05 |  | 0 | Met | Darsh Rau | 161828
ST00343 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-025 | Pune | West | 100 | Live | 2025-07-17 | 2025-09-14 | 2025-09-16 | 2025-09-25 | 2025-10-02 | 2 | Met | Upadhriti Wadhwa | 146155
ST00344 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-026 | Ahmedabad | West | 200 | Testing | 2025-07-07 | 2025-07-28 | 2025-08-03 | 2025-08-23 |  | 12 | Marginal | Mohammed Gupta | 172612
ST00345 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-027 | Mumbai | West | 10 | Installation Scheduled | 2025-07-18 | 2025-08-19 | 2025-08-24 | 2025-09-14 |  | 1 | Met | Kashvi Edwin | 247720
ST00346 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-028 | Mumbai | West | 10 | Testing | 2025-07-04 | 2025-09-02 | 2025-09-03 | 2025-09-25 |  | 12 | Marginal | Ekapad Walia | 185969
ST00347 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-029 | Surat | West | 10 | Live | 2025-06-30 | 2025-07-29 | 2025-07-24 | 2025-08-22 | 2025-08-29 | 0 | Met | Gavin Batta | 64201
ST00348 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-030 | Mumbai | West | 50 | ROW In Progress | 2025-07-06 | 2025-08-30 |  | 2025-09-11 |  | 3 | Met | Niharika Sunder | 146720
ST00349 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-031 | Surat | West | 200 | Live | 2025-07-11 | 2025-08-20 | 2025-08-15 | 2025-09-11 | 2025-09-11 | 0 | Met | Ekbal Garg | 213145
ST00350 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-032 | Mumbai | West | 50 | Live | 2025-07-16 | 2025-08-07 | 2025-08-04 | 2025-08-28 | 2025-08-28 | 0 | Met | Arya Sunder | 204007
ST00351 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-033 | Mumbai | West | 20 | Installation Scheduled | 2025-07-12 | 2025-08-25 | 2025-09-01 | 2025-09-04 |  | 7 | Met | Alka Wable | 80751
ST00352 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-034 | Surat | West | 10 | Live | 2025-07-15 | 2025-08-22 | 2025-08-21 | 2025-09-10 | 2025-09-18 | 0 | Met | Aarush Lall | 77305
ST00353 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-035 | Mumbai | West | 10 | Survey Pending | 2025-07-17 | 2025-08-31 |  | 2025-09-27 |  | 8 | Marginal | Kevin Solanki | 100064
ST00354 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-036 | Ahmedabad | West | 20 | Installation Scheduled | 2025-07-18 | 2025-09-08 | 2025-09-07 | 2025-09-23 |  | 2 | Met | Jai Kota | 95941
ST00355 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-037 | Mumbai | West | 100 | ROW In Progress | 2025-07-23 | 2025-09-17 |  | 2025-09-28 |  | 8 | Marginal | Priya Rastogi | 121192
ST00356 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-038 | Mumbai | West | 20 | Installation Scheduled | 2025-07-04 | 2025-08-30 | 2025-09-09 | 2025-09-19 |  | 5 | Met | Devika Rastogi | 71226
ST00357 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-039 | Ahmedabad | West | 50 | Testing | 2025-07-04 | 2025-08-13 | 2025-08-23 | 2025-09-06 |  | 12 | Marginal | Kevin Solanki | 226785
ST00358 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-040 | Pune | West | 10 | Testing | 2025-07-09 | 2025-08-18 | 2025-08-26 | 2025-09-02 |  | 12 | Marginal | Urvashi Ray | 109533
ST00359 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-041 | Pune | West | 50 | Live | 2025-07-18 | 2025-09-03 | 2025-09-06 | 2025-09-24 | 2025-09-25 | 3 | Met | Dakshesh Trivedi | 166332
ST00360 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-042 | Surat | West | 200 | Installation Done | 2025-07-07 | 2025-08-27 | 2025-08-25 | 2025-09-11 |  | 12 | Marginal | Theodore Devi | 265670
ST00361 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-043 | Ahmedabad | West | 10 | Live | 2025-07-02 | 2025-08-25 | 2025-08-26 | 2025-09-12 | 2025-09-11 | 1 | Met | Anamika Kanda | 267714
ST00362 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-044 | Mumbai | West | 200 | Live | 2025-07-16 | 2025-08-30 | 2025-08-31 | 2025-09-10 | 2025-09-15 | 1 | Met | Vansha Thakkar | 216418
ST00363 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-045 | Pune | West | 100 | Installation Done | 2025-07-05 | 2025-08-31 | 2025-09-04 | 2025-09-14 |  | 12 | Marginal | Yatin Baral | 178801
ST00364 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-046 | Mumbai | West | 20 | Installation Done | 2025-07-14 | 2025-08-03 | 2025-08-05 | 2025-09-01 |  | 12 | Marginal | Radhika Dugar | 161974
ST00365 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-047 | Pune | West | 10 | ROW In Progress | 2025-07-16 | 2025-08-14 |  | 2025-09-08 |  | 5 | Met | Alka Wable | 244615
ST00366 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-048 | Surat | West | 200 | Installation Scheduled | 2025-07-06 | 2025-08-18 | 2025-08-20 | 2025-08-29 |  | 3 | Met | Ranveer Yadav | 146736
ST00367 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-049 | Surat | West | 50 | Pending Acceptance | 2025-06-29 | 2025-07-21 | 2025-07-26 | 2025-08-03 | 2025-08-08 | 5 | Met | Ekiya Suresh | 143739
ST00368 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-050 | Surat | West | 20 | Installation Done | 2025-07-18 | 2025-08-11 | 2025-08-14 | 2025-09-02 |  | 12 | Marginal | Girik Khalsa | 137510
ST00369 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-051 | Ahmedabad | West | 20 | Installation Done | 2025-07-13 | 2025-09-09 | 2025-09-04 | 2025-10-05 |  | 12 | Marginal | Bhavika Sampath | 88412
ST00370 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-052 | Pune | West | 20 | Survey Pending | 2025-07-18 | 2025-08-24 |  | 2025-09-09 |  | 2 | Met | Yashica Issac | 139954
ST00371 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-053 | Mumbai | West | 100 | Live | 2025-07-11 | 2025-08-21 | 2025-08-19 | 2025-09-15 | 2025-09-27 | 0 | Met | Ekapad Walia | 199872
ST00372 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-054 | Pune | West | 200 | Live | 2025-07-11 | 2025-08-01 | 2025-08-03 | 2025-08-12 | 2025-08-13 | 2 | Met | Yashica Issac | 80317
ST00373 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-055 | Mumbai | West | 200 | Live | 2025-07-02 | 2025-07-25 | 2025-07-25 | 2025-08-12 | 2025-08-14 | 0 | Met | Girik Khalsa | 202117
ST00374 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-056 | Mumbai | West | 200 | Live | 2025-07-21 | 2025-08-28 | 2025-08-25 | 2025-09-13 | 2025-09-24 | 0 | Met | Vansha Thakkar | 272358
ST00375 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-057 | Surat | West | 200 | ROW In Progress | 2025-07-11 | 2025-09-07 |  | 2025-09-21 |  | 2 | Met | Devansh Nigam | 88967
ST00376 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-058 | Ahmedabad | West | 100 | Pending Acceptance | 2025-07-17 | 2025-09-12 | 2025-09-09 | 2025-09-29 | 2025-10-08 | 0 | Met | Harini Choudhury | 73461
ST00377 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-059 | Mumbai | West | 20 | Installation Scheduled | 2025-07-14 | 2025-08-29 | 2025-08-28 | 2025-09-27 |  | 1 | Met | Vansha Thakkar | 206152
ST00378 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-060 | Mumbai | West | 20 | Live | 2025-07-15 | 2025-09-05 | 2025-09-03 | 2025-09-17 | 2025-09-29 | 0 | Met | Ekbal Garg | 248127
ST00379 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-061 | Surat | West | 100 | Installation Done | 2025-07-09 | 2025-07-31 | 2025-08-08 | 2025-08-17 |  | 12 | Marginal | Arya Shere | 136886
ST00380 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-062 | Mumbai | West | 50 | Installation Done | 2025-07-06 | 2025-08-25 | 2025-08-27 | 2025-09-06 |  | 12 | Marginal | Niharika Sunder | 112582
ST00381 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-063 | Pune | West | 10 | Survey Pending | 2025-07-21 | 2025-08-10 |  | 2025-09-07 |  | 8 | Marginal | Ekbal Garg | 143311
ST00382 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-064 | Pune | West | 100 | Live | 2025-07-08 | 2025-08-23 | 2025-08-29 | 2025-09-05 | 2025-09-06 | 6 | Met | Jai Kota | 113498
ST00383 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-065 | Surat | West | 100 | Testing | 2025-07-17 | 2025-08-23 | 2025-08-30 | 2025-09-08 |  | 12 | Marginal | Dakshesh Trivedi | 91850
ST00384 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-066 | Ahmedabad | West | 50 | Testing | 2025-07-13 | 2025-08-18 | 2025-08-22 | 2025-09-15 |  | 12 | Marginal | Chandresh Zachariah | 237880
ST00385 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-067 | Pune | West | 10 | Live | 2025-07-19 | 2025-08-15 | 2025-08-17 | 2025-09-08 | 2025-09-10 | 2 | Met | Kabir Soman | 178259
ST00386 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-068 | Surat | West | 10 | Live | 2025-07-23 | 2025-09-16 | 2025-09-12 | 2025-10-01 | 2025-10-10 | 0 | Met | Gavin Batta | 260811
ST00387 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-069 | Pune | West | 50 | Installation Done | 2025-07-17 | 2025-09-02 | 2025-08-30 | 2025-09-14 |  | 12 | Marginal | Alka Wable | 142212
ST00388 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-070 | Mumbai | West | 200 | Testing | 2025-07-21 | 2025-09-03 | 2025-09-10 | 2025-10-02 |  | 12 | Marginal | Ekansh Balay | 231543
ST00389 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-071 | Mumbai | West | 20 | Pending Acceptance | 2025-07-03 | 2025-09-01 | 2025-09-11 | 2025-09-25 | 2025-09-22 | 10 | Marginal | Ekansh Balay | 96051
ST00390 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-072 | Mumbai | West | 10 | Live | 2025-07-14 | 2025-09-05 | 2025-09-07 | 2025-10-04 | 2025-10-06 | 2 | Met | Ranveer Yadav | 107719
ST00391 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-073 | Mumbai | West | 100 | Pending Acceptance | 2025-06-30 | 2025-08-06 | 2025-08-13 | 2025-08-27 | 2025-09-05 | 7 | Met | Farhan Chada | 180723
ST00392 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-074 | Mumbai | West | 50 | Live | 2025-06-30 | 2025-07-25 | 2025-07-29 | 2025-08-21 | 2025-08-29 | 4 | Met | Ekavir Bhargava | 104322
ST00393 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-075 | Pune | West | 20 | Installation Done | 2025-07-10 | 2025-09-04 | 2025-08-30 | 2025-09-22 |  | 12 | Marginal | Niharika Sunder | 177707
ST00394 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-076 | Mumbai | West | 200 | Testing | 2025-07-14 | 2025-08-21 | 2025-08-26 | 2025-09-03 |  | 12 | Marginal | Jai Kota | 274667
ST00395 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-077 | Ahmedabad | West | 100 | Live | 2025-07-10 | 2025-09-04 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 10 | Marginal | Teerth Bhardwaj | 198833
ST00396 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-078 | Mumbai | West | 20 | Installation Done | 2025-07-06 | 2025-07-30 | 2025-08-06 | 2025-08-29 |  | 12 | Marginal | Siddharth Zacharia | 254757
ST00397 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-079 | Ahmedabad | West | 20 | Installation Done | 2025-07-09 | 2025-08-31 | 2025-08-26 | 2025-09-18 |  | 12 | Marginal | Ekansh Balay | 69381
ST00398 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-080 | Surat | West | 50 | Live | 2025-07-08 | 2025-08-01 | 2025-08-01 | 2025-08-26 | 2025-09-02 | 0 | Met | Kabir Soman | 279439
ST00399 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-081 | Ahmedabad | West | 20 | ROW In Progress | 2025-07-21 | 2025-08-22 |  | 2025-09-16 |  | 3 | Met | Devika Rastogi | 273784
ST00400 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-082 | Ahmedabad | West | 10 | Installation Scheduled | 2025-07-04 | 2025-08-08 | 2025-08-14 | 2025-08-22 |  | 1 | Met | Theodore Devi | 222160
ST00401 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-083 | Surat | West | 50 | Testing | 2025-07-22 | 2025-09-14 | 2025-09-10 | 2025-10-09 |  | 12 | Marginal | Urvashi Ray | 174064
ST00402 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-084 | Ahmedabad | West | 20 | Installation Done | 2025-07-22 | 2025-09-12 | 2025-09-15 | 2025-10-04 |  | 12 | Marginal | Harini Choudhury | 59194
ST00403 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-085 | Surat | West | 20 | Installation Done | 2025-07-15 | 2025-08-06 | 2025-08-12 | 2025-08-28 |  | 12 | Marginal | Teerth Bhardwaj | 76553
ST00404 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-086 | Surat | West | 50 | Installation Scheduled | 2025-06-28 | 2025-07-18 | 2025-07-19 | 2025-08-09 |  | 1 | Met | Ranveer Yadav | 205636
ST00405 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-087 | Ahmedabad | West | 200 | ROW In Progress | 2025-07-06 | 2025-08-10 |  | 2025-08-28 |  | 7 | Met | Unni Bhagat | 140924
ST00406 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-088 | Pune | West | 100 | Installation Done | 2025-07-04 | 2025-08-19 | 2025-08-25 | 2025-09-09 |  | 12 | Marginal | Ekavir Bhargava | 163155
ST00407 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-089 | Pune | West | 20 | Testing | 2025-07-16 | 2025-08-19 | 2025-08-17 | 2025-09-06 |  | 12 | Marginal | Madhavi Lanka | 269476
ST00408 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-090 | Surat | West | 20 | ROW In Progress | 2025-07-23 | 2025-08-21 |  | 2025-09-15 |  | 0 | Met | Tanay Rattan | 175966
ST00409 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-091 | Pune | West | 50 | Pending Acceptance | 2025-07-18 | 2025-09-09 | 2025-09-14 | 2025-10-04 | 2025-10-10 | 5 | Met | Simon Tata | 149438
ST00410 | PRJ005 | CL001 | Hitachi Payment Services | Mumbai Site-092 | Mumbai | West | 100 | Live | 2025-06-29 | 2025-08-01 | 2025-08-04 | 2025-08-26 | 2025-08-26 | 3 | Met | Irya Sampath | 113096
ST00411 | PRJ005 | CL001 | Hitachi Payment Services | Ahmedabad Site-093 | Ahmedabad | West | 100 | Installation Done | 2025-07-15 | 2025-08-20 | 2025-08-26 | 2025-08-30 |  | 12 | Marginal | Advay Contractor | 137036
ST00412 | PRJ005 | CL001 | Hitachi Payment Services | Pune Site-094 | Pune | West | 50 | Testing | 2025-07-18 | 2025-09-10 | 2025-09-10 | 2025-09-29 |  | 12 | Marginal | Girindra Chatterjee | 221473
ST00413 | PRJ005 | CL001 | Hitachi Payment Services | Surat Site-095 | Surat | West | 100 | Live | 2025-07-12 | 2025-08-06 | 2025-08-13 | 2025-09-04 | 2025-09-10 | 7 | Met | Aarush Lall | 272608
ST00414 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-001 | Gurgaon | North | 200 | Testing | 2025-09-15 | 2025-10-20 | 2025-10-15 | 2025-10-31 |  | 12 | Marginal | Vansha Thakkar | 225461
ST00415 | PRJ006 | CL002 | Axis Bank | Noida Site-002 | Noida | North | 10 | Installation Done | 2025-09-05 | 2025-10-10 | 2025-10-10 | 2025-11-04 |  | 12 | Marginal | Unni Bhagat | 244114
ST00416 | PRJ006 | CL002 | Axis Bank | Delhi Site-003 | Delhi | North | 20 | Survey Pending | 2025-09-23 | 2025-10-22 |  | 2025-11-18 |  | 1 | Met | Quincy Biswas | 105994
ST00417 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-004 | Gurgaon | North | 100 | Pending Acceptance | 2025-09-28 | 2025-11-09 | 2025-11-18 | 2025-11-25 | 2025-11-22 | 9 | Marginal | Ikbal Kothari | 234896
ST00418 | PRJ006 | CL002 | Axis Bank | Noida Site-005 | Noida | North | 200 | Installation Scheduled | 2025-09-04 | 2025-10-25 | 2025-11-03 | 2025-11-21 |  | 4 | Met | Quincy Biswas | 94748
ST00419 | PRJ006 | CL002 | Axis Bank | Noida Site-006 | Noida | North | 200 | Testing | 2025-09-13 | 2025-11-01 | 2025-11-04 | 2025-11-30 |  | 12 | Marginal | Yashica Issac | 63055
ST00420 | PRJ006 | CL002 | Axis Bank | Noida Site-007 | Noida | North | 10 | Installation Done | 2025-09-11 | 2025-11-04 | 2025-11-10 | 2025-11-28 |  | 12 | Marginal | Yatin Baral | 144363
ST00421 | PRJ006 | CL002 | Axis Bank | Noida Site-008 | Noida | North | 200 | Live | 2025-09-22 | 2025-11-04 | 2025-11-06 | 2025-11-24 | 2025-11-23 | 2 | Met | Faqid Savant | 94773
ST00422 | PRJ006 | CL002 | Axis Bank | Jaipur Site-009 | Jaipur | North | 50 | Live | 2025-09-07 | 2025-11-05 | 2025-11-09 | 2025-11-25 | 2025-12-05 | 4 | Met | Upadhriti Wadhwa | 70233
ST00423 | PRJ006 | CL002 | Axis Bank | Delhi Site-010 | Delhi | North | 10 | Survey Pending | 2025-09-07 | 2025-10-08 |  | 2025-10-19 |  | 3 | Met | Quincy Biswas | 95231
ST00424 | PRJ006 | CL002 | Axis Bank | Delhi Site-011 | Delhi | North | 200 | Survey Pending | 2025-09-23 | 2025-11-06 |  | 2025-12-01 |  | 8 | Marginal | Jai Kota | 57867
ST00425 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-012 | Gurgaon | North | 10 | Installation Scheduled | 2025-09-25 | 2025-10-19 | 2025-10-14 | 2025-11-04 |  | 7 | Met | Dipta Bhandari | 254982
ST00426 | PRJ006 | CL002 | Axis Bank | Delhi Site-013 | Delhi | North | 200 | Installation Done | 2025-09-26 | 2025-11-11 | 2025-11-17 | 2025-11-22 |  | 12 | Marginal | Victor Kannan | 183679
ST00427 | PRJ006 | CL002 | Axis Bank | Delhi Site-014 | Delhi | North | 10 | Live | 2025-09-12 | 2025-10-06 | 2025-10-07 | 2025-11-01 | 2025-11-01 | 1 | Met | Siddharth Zacharia | 184371
ST00428 | PRJ006 | CL002 | Axis Bank | Jaipur Site-015 | Jaipur | North | 200 | ROW In Progress | 2025-09-19 | 2025-10-24 |  | 2025-11-21 |  | 2 | Met | Tanay Rattan | 240587
ST00429 | PRJ006 | CL002 | Axis Bank | Delhi Site-016 | Delhi | North | 20 | Live | 2025-09-21 | 2025-11-02 | 2025-11-11 | 2025-11-25 | 2025-11-25 | 9 | Marginal | Isaac Patil | 189170
ST00430 | PRJ006 | CL002 | Axis Bank | Jaipur Site-017 | Jaipur | North | 50 | Installation Done | 2025-09-24 | 2025-10-24 | 2025-11-02 | 2025-11-14 |  | 12 | Marginal | Girindra Chatterjee | 266473
ST00431 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-018 | Gurgaon | North | 20 | Installation Done | 2025-09-23 | 2025-11-09 | 2025-11-14 | 2025-12-08 |  | 12 | Marginal | Kabir Soman | 143320
ST00432 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-019 | Gurgaon | North | 10 | Installation Done | 2025-09-17 | 2025-11-04 | 2025-11-11 | 2025-11-14 |  | 12 | Marginal | Ekansh Balay | 201175
ST00433 | PRJ006 | CL002 | Axis Bank | Delhi Site-020 | Delhi | North | 20 | Installation Done | 2025-09-12 | 2025-10-02 | 2025-10-06 | 2025-10-19 |  | 12 | Marginal | Urvashi Ray | 50688
ST00434 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-021 | Gurgaon | North | 100 | Pending Acceptance | 2025-09-19 | 2025-11-13 | 2025-11-12 | 2025-11-26 | 2025-11-24 | 0 | Met | Ikbal Kothari | 85922
ST00435 | PRJ006 | CL002 | Axis Bank | Noida Site-022 | Noida | North | 10 | Installation Scheduled | 2025-09-21 | 2025-10-26 | 2025-10-28 | 2025-11-13 |  | 4 | Met | Girik Khalsa | 194176
ST00436 | PRJ006 | CL002 | Axis Bank | Noida Site-023 | Noida | North | 200 | Live | 2025-09-26 | 2025-11-05 | 2025-11-15 | 2025-11-20 | 2025-12-02 | 10 | Marginal | Michael Dutta | 201036
ST00437 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-024 | Gurgaon | North | 10 | Survey Pending | 2025-09-28 | 2025-11-23 |  | 2025-12-15 |  | 1 | Met | Irya Sampath | 136207
ST00438 | PRJ006 | CL002 | Axis Bank | Jaipur Site-025 | Jaipur | North | 100 | Installation Done | 2025-09-06 | 2025-10-10 | 2025-10-05 | 2025-11-09 |  | 12 | Marginal | Simon Tata | 124897
ST00439 | PRJ006 | CL002 | Axis Bank | Delhi Site-026 | Delhi | North | 20 | Installation Scheduled | 2025-09-21 | 2025-10-20 | 2025-10-25 | 2025-11-15 |  | 3 | Met | Simon Tata | 221589
ST00440 | PRJ006 | CL002 | Axis Bank | Jaipur Site-027 | Jaipur | North | 50 | Pending Acceptance | 2025-09-27 | 2025-11-24 | 2025-11-21 | 2025-12-11 | 2025-12-21 | 0 | Met | Chandresh Zachariah | 83800
ST00441 | PRJ006 | CL002 | Axis Bank | Noida Site-028 | Noida | North | 50 | Installation Scheduled | 2025-09-18 | 2025-11-13 | 2025-11-09 | 2025-12-10 |  | 6 | Met | Theodore Devi | 149471
ST00442 | PRJ006 | CL002 | Axis Bank | Jaipur Site-029 | Jaipur | North | 100 | Live | 2025-09-07 | 2025-10-05 | 2025-10-15 | 2025-11-01 | 2025-11-04 | 10 | Marginal | Chandresh Zachariah | 215983
ST00443 | PRJ006 | CL002 | Axis Bank | Noida Site-030 | Noida | North | 10 | Testing | 2025-09-26 | 2025-11-18 | 2025-11-20 | 2025-12-05 |  | 12 | Marginal | Victor Kannan | 248626
ST00444 | PRJ006 | CL002 | Axis Bank | Jaipur Site-031 | Jaipur | North | 50 | Installation Scheduled | 2025-09-21 | 2025-10-16 | 2025-10-14 | 2025-11-08 |  | 6 | Met | Darsh Rau | 94935
ST00445 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-032 | Gurgaon | North | 200 | Installation Scheduled | 2025-09-23 | 2025-10-14 | 2025-10-18 | 2025-10-29 |  | 5 | Met | Bhavika Sampath | 208363
ST00446 | PRJ006 | CL002 | Axis Bank | Noida Site-033 | Noida | North | 10 | Installation Done | 2025-09-10 | 2025-10-12 | 2025-10-18 | 2025-10-26 |  | 12 | Marginal | Upadhriti Wadhwa | 238876
ST00447 | PRJ006 | CL002 | Axis Bank | Delhi Site-034 | Delhi | North | 10 | Installation Scheduled | 2025-09-22 | 2025-10-21 | 2025-10-25 | 2025-10-31 |  | 5 | Met | Kevin Solanki | 162980
ST00448 | PRJ006 | CL002 | Axis Bank | Jaipur Site-035 | Jaipur | North | 200 | Survey Pending | 2025-09-09 | 2025-11-02 |  | 2025-11-18 |  | 3 | Met | Devansh Nigam | 188864
ST00449 | PRJ006 | CL002 | Axis Bank | Jaipur Site-036 | Jaipur | North | 200 | Testing | 2025-09-07 | 2025-09-28 | 2025-10-05 | 2025-10-26 |  | 12 | Marginal | Dominic Kakar | 111966
ST00450 | PRJ006 | CL002 | Axis Bank | Noida Site-037 | Noida | North | 100 | Survey Pending | 2025-09-09 | 2025-11-07 |  | 2025-11-25 |  | 0 | Met | Nihal Shere | 62458
ST00451 | PRJ006 | CL002 | Axis Bank | Jaipur Site-038 | Jaipur | North | 100 | Live | 2025-09-24 | 2025-11-06 | 2025-11-04 | 2025-11-16 | 2025-11-22 | 0 | Met | Siddharth Zacharia | 144798
ST00452 | PRJ006 | CL002 | Axis Bank | Delhi Site-039 | Delhi | North | 200 | Live | 2025-09-18 | 2025-11-15 | 2025-11-12 | 2025-11-30 | 2025-12-03 | 0 | Met | Teerth Bhardwaj | 191980
ST00453 | PRJ006 | CL002 | Axis Bank | Delhi Site-040 | Delhi | North | 100 | Survey Pending | 2025-09-19 | 2025-10-28 |  | 2025-11-17 |  | 7 | Met | Yashica Issac | 49816
ST00454 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-041 | Gurgaon | North | 10 | Live | 2025-09-14 | 2025-11-13 | 2025-11-17 | 2025-11-30 | 2025-12-05 | 4 | Met | Jai Kota | 275339
ST00455 | PRJ006 | CL002 | Axis Bank | Jaipur Site-042 | Jaipur | North | 50 | Live | 2025-09-03 | 2025-10-28 | 2025-10-31 | 2025-11-14 | 2025-11-15 | 3 | Met | Chandresh Zachariah | 217210
ST00456 | PRJ006 | CL002 | Axis Bank | Noida Site-043 | Noida | North | 100 | ROW In Progress | 2025-09-15 | 2025-11-07 |  | 2025-12-06 |  | 3 | Met | Devika Rastogi | 195181
ST00457 | PRJ006 | CL002 | Axis Bank | Noida Site-044 | Noida | North | 200 | Installation Done | 2025-09-12 | 2025-11-09 | 2025-11-14 | 2025-12-03 |  | 12 | Marginal | Harini Choudhury | 99200
ST00458 | PRJ006 | CL002 | Axis Bank | Noida Site-045 | Noida | North | 200 | Testing | 2025-09-24 | 2025-10-26 | 2025-10-25 | 2025-11-14 |  | 12 | Marginal | Radhika Dugar | 157738
ST00459 | PRJ006 | CL002 | Axis Bank | Noida Site-046 | Noida | North | 20 | Live | 2025-09-21 | 2025-10-21 | 2025-10-26 | 2025-11-02 | 2025-11-02 | 5 | Met | Urvashi Ray | 265075
ST00460 | PRJ006 | CL002 | Axis Bank | Noida Site-047 | Noida | North | 100 | Live | 2025-09-27 | 2025-11-06 | 2025-11-14 | 2025-11-29 | 2025-12-05 | 8 | Marginal | Ekavir Bhargava | 84834
ST00461 | PRJ006 | CL002 | Axis Bank | Noida Site-048 | Noida | North | 200 | ROW In Progress | 2025-09-08 | 2025-09-29 |  | 2025-10-28 |  | 4 | Met | Siddharth Zacharia | 201332
ST00462 | PRJ006 | CL002 | Axis Bank | Noida Site-049 | Noida | North | 200 | Installation Scheduled | 2025-09-03 | 2025-10-15 | 2025-10-12 | 2025-11-09 |  | 2 | Met | Vansha Thakkar | 231651
ST00463 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-050 | Gurgaon | North | 20 | ROW In Progress | 2025-09-15 | 2025-11-05 |  | 2025-11-30 |  | 2 | Met | Wriddhish Bhardwaj | 104316
ST00464 | PRJ006 | CL002 | Axis Bank | Delhi Site-051 | Delhi | North | 20 | Installation Done | 2025-09-03 | 2025-10-10 | 2025-10-18 | 2025-10-27 |  | 12 | Marginal | Ekapad Walia | 62337
ST00465 | PRJ006 | CL002 | Axis Bank | Noida Site-052 | Noida | North | 20 | Pending Acceptance | 2025-09-17 | 2025-11-15 | 2025-11-25 | 2025-12-05 | 2025-12-16 | 10 | Marginal | Nitesh Raghavan | 151133
ST00466 | PRJ006 | CL002 | Axis Bank | Delhi Site-053 | Delhi | North | 200 | Testing | 2025-09-15 | 2025-10-25 | 2025-11-01 | 2025-11-23 |  | 12 | Marginal | Diya Rattan | 181485
ST00467 | PRJ006 | CL002 | Axis Bank | Delhi Site-054 | Delhi | North | 200 | Installation Done | 2025-09-04 | 2025-10-09 | 2025-10-16 | 2025-10-20 |  | 12 | Marginal | Faqid Savant | 180299
ST00468 | PRJ006 | CL002 | Axis Bank | Delhi Site-055 | Delhi | North | 100 | ROW In Progress | 2025-09-17 | 2025-11-01 |  | 2025-11-20 |  | 4 | Met | Kashvi Edwin | 155745
ST00469 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-056 | Gurgaon | North | 100 | Testing | 2025-09-04 | 2025-10-27 | 2025-10-26 | 2025-11-20 |  | 12 | Marginal | Gavin Batta | 234437
ST00470 | PRJ006 | CL002 | Axis Bank | Delhi Site-057 | Delhi | North | 100 | ROW In Progress | 2025-09-21 | 2025-11-14 |  | 2025-11-28 |  | 6 | Met | Girindra Chatterjee | 163197
ST00471 | PRJ006 | CL002 | Axis Bank | Delhi Site-058 | Delhi | North | 50 | ROW In Progress | 2025-09-21 | 2025-10-23 |  | 2025-11-16 |  | 1 | Met | Girindra Chatterjee | 226329
ST00472 | PRJ006 | CL002 | Axis Bank | Noida Site-059 | Noida | North | 10 | Live | 2025-09-06 | 2025-10-01 | 2025-09-29 | 2025-10-25 | 2025-11-02 | 0 | Met | Faqid Savant | 235545
ST00473 | PRJ006 | CL002 | Axis Bank | Noida Site-060 | Noida | North | 200 | Installation Done | 2025-09-15 | 2025-10-07 | 2025-10-07 | 2025-10-27 |  | 12 | Marginal | Yashica Cherian | 87499
ST00474 | PRJ006 | CL002 | Axis Bank | Noida Site-061 | Noida | North | 50 | ROW In Progress | 2025-09-25 | 2025-10-18 |  | 2025-11-10 |  | 4 | Met | Mohammed Gupta | 120702
ST00475 | PRJ006 | CL002 | Axis Bank | Noida Site-062 | Noida | North | 10 | ROW In Progress | 2025-09-07 | 2025-10-09 |  | 2025-10-19 |  | 4 | Met | Teerth Bhardwaj | 175450
ST00476 | PRJ006 | CL002 | Axis Bank | Jaipur Site-063 | Jaipur | North | 20 | Testing | 2025-09-03 | 2025-10-31 | 2025-11-10 | 2025-11-17 |  | 12 | Marginal | Vansha Thakkar | 163944
ST00477 | PRJ006 | CL002 | Axis Bank | Jaipur Site-064 | Jaipur | North | 200 | Installation Done | 2025-09-22 | 2025-11-19 | 2025-11-14 | 2025-12-06 |  | 12 | Marginal | Ekavir Bhargava | 207467
ST00478 | PRJ006 | CL002 | Axis Bank | Noida Site-065 | Noida | North | 10 | Survey Pending | 2025-09-07 | 2025-09-30 |  | 2025-10-30 |  | 5 | Met | Aarush Lall | 268826
ST00479 | PRJ006 | CL002 | Axis Bank | Delhi Site-066 | Delhi | North | 10 | Live | 2025-09-22 | 2025-10-31 | 2025-11-05 | 2025-11-12 | 2025-11-10 | 5 | Met | Tanay Rattan | 91726
ST00480 | PRJ006 | CL002 | Axis Bank | Noida Site-067 | Noida | North | 10 | Live | 2025-09-22 | 2025-11-19 | 2025-11-19 | 2025-12-13 | 2025-12-21 | 0 | Met | Gavin Batta | 246460
ST00481 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-068 | Gurgaon | North | 50 | Installation Scheduled | 2025-09-15 | 2025-10-09 | 2025-10-17 | 2025-11-05 |  | 1 | Met | Vansha Thakkar | 80270
ST00482 | PRJ006 | CL002 | Axis Bank | Delhi Site-069 | Delhi | North | 20 | Live | 2025-09-11 | 2025-10-22 | 2025-10-30 | 2025-11-17 | 2025-11-20 | 8 | Marginal | Tara Dhar | 73652
ST00483 | PRJ006 | CL002 | Axis Bank | Delhi Site-070 | Delhi | North | 200 | Installation Done | 2025-09-25 | 2025-11-22 | 2025-11-26 | 2025-12-15 |  | 12 | Marginal | Urvashi Ray | 113068
ST00484 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-071 | Gurgaon | North | 100 | Pending Acceptance | 2025-09-22 | 2025-11-17 | 2025-11-27 | 2025-12-13 | 2025-12-25 | 10 | Marginal | Isaac Patil | 276647
ST00485 | PRJ006 | CL002 | Axis Bank | Noida Site-072 | Noida | North | 10 | Live | 2025-09-09 | 2025-09-29 | 2025-09-27 | 2025-10-09 | 2025-10-20 | 0 | Met | Ekapad Walia | 254600
ST00486 | PRJ006 | CL002 | Axis Bank | Jaipur Site-073 | Jaipur | North | 20 | Installation Done | 2025-09-13 | 2025-10-25 | 2025-10-26 | 2025-11-04 |  | 12 | Marginal | Ekansh Balay | 111694
ST00487 | PRJ006 | CL002 | Axis Bank | Delhi Site-074 | Delhi | North | 50 | Installation Scheduled | 2025-09-19 | 2025-11-13 | 2025-11-18 | 2025-11-23 |  | 1 | Met | Unni Bhagat | 148821
ST00488 | PRJ006 | CL002 | Axis Bank | Delhi Site-075 | Delhi | North | 10 | Live | 2025-09-09 | 2025-10-20 | 2025-10-25 | 2025-11-14 | 2025-11-26 | 5 | Met | Radhika Dugar | 171221
ST00489 | PRJ006 | CL002 | Axis Bank | Noida Site-076 | Noida | North | 10 | Testing | 2025-09-20 | 2025-10-31 | 2025-11-09 | 2025-11-23 |  | 12 | Marginal | Arya Sunder | 193096
ST00490 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-077 | Gurgaon | North | 10 | Testing | 2025-09-03 | 2025-10-06 | 2025-10-11 | 2025-10-27 |  | 12 | Marginal | Yashica Cherian | 118520
ST00491 | PRJ006 | CL002 | Axis Bank | Delhi Site-078 | Delhi | North | 20 | Installation Scheduled | 2025-09-15 | 2025-11-14 | 2025-11-14 | 2025-12-12 |  | 6 | Met | Upadhriti Wadhwa | 271648
ST00492 | PRJ006 | CL002 | Axis Bank | Gurgaon Site-079 | Gurgaon | North | 100 | Live | 2025-09-13 | 2025-10-05 | 2025-10-08 | 2025-10-28 | 2025-10-27 | 3 | Met | Devika Rastogi | 142408
ST00493 | PRJ006 | CL002 | Axis Bank | Jaipur Site-080 | Jaipur | North | 50 | Live | 2025-09-12 | 2025-10-15 | 2025-10-19 | 2025-10-30 | 2025-10-30 | 4 | Met | Diya Rattan | 248893
ST00494 | PRJ007 | CL002 | Axis Bank | Indore Site-001 | Indore | Central | 50 | Survey Pending | 2025-10-19 | 2025-11-11 |  | 2025-11-21 |  | 8 | Marginal | Upadhriti Wadhwa | 270770
ST00495 | PRJ007 | CL002 | Axis Bank | Indore Site-002 | Indore | Central | 100 | Live | 2025-10-09 | 2025-11-25 | 2025-12-02 | 2025-12-25 | 2026-01-01 | 7 | Met | Girik Khalsa | 145024
ST00496 | PRJ007 | CL002 | Axis Bank | Indore Site-003 | Indore | Central | 20 | Testing | 2025-10-23 | 2025-11-23 | 2025-12-03 | 2025-12-07 |  | 12 | Marginal | Faqid Savant | 266073
ST00497 | PRJ007 | CL002 | Axis Bank | Indore Site-004 | Indore | Central | 10 | Live | 2025-10-06 | 2025-11-13 | 2025-11-12 | 2025-11-27 | 2025-11-24 | 0 | Met | Anamika Kanda | 82747
ST00498 | PRJ007 | CL002 | Axis Bank | Nagpur Site-005 | Nagpur | Central | 100 | Live | 2025-10-23 | 2025-12-09 | 2025-12-08 | 2025-12-21 | 2025-12-22 | 0 | Met | Teerth Bhardwaj | 279247
ST00499 | PRJ007 | CL002 | Axis Bank | Nagpur Site-006 | Nagpur | Central | 200 | Testing | 2025-10-15 | 2025-12-13 | 2025-12-13 | 2026-01-06 |  | 12 | Marginal | Nitesh Raghavan | 189716
ST00500 | PRJ007 | CL002 | Axis Bank | Indore Site-007 | Indore | Central | 10 | Installation Done | 2025-10-09 | 2025-11-09 | 2025-11-17 | 2025-12-08 |  | 12 | Marginal | Wahab Raval | 266984
ST00501 | PRJ007 | CL002 | Axis Bank | Nagpur Site-008 | Nagpur | Central | 10 | Installation Scheduled | 2025-10-18 | 2025-11-24 | 2025-12-02 | 2025-12-21 |  | 5 | Met | Diya Rattan | 193937
ST00502 | PRJ007 | CL002 | Axis Bank | Indore Site-009 | Indore | Central | 200 | Live | 2025-10-05 | 2025-12-01 | 2025-12-11 | 2025-12-13 | 2025-12-14 | 10 | Marginal | Ekavir Bhargava | 166880
ST00503 | PRJ007 | CL002 | Axis Bank | Nagpur Site-010 | Nagpur | Central | 10 | Survey Pending | 2025-10-21 | 2025-11-15 |  | 2025-12-02 |  | 7 | Met | Kevin Solanki | 205704
ST00504 | PRJ007 | CL002 | Axis Bank | Bhopal Site-011 | Bhopal | Central | 200 | Live | 2025-10-19 | 2025-11-08 | 2025-11-18 | 2025-12-02 | 2025-12-14 | 10 | Marginal | Irya Sampath | 155366
ST00505 | PRJ007 | CL002 | Axis Bank | Indore Site-012 | Indore | Central | 200 | Pending Acceptance | 2025-10-27 | 2025-12-04 | 2025-12-08 | 2025-12-19 | 2025-12-17 | 4 | Met | Arya Sunder | 235571
ST00506 | PRJ007 | CL002 | Axis Bank | Nagpur Site-013 | Nagpur | Central | 50 | Installation Scheduled | 2025-10-22 | 2025-12-11 | 2025-12-11 | 2026-01-08 |  | 0 | Met | Daksh Karnik | 120187
ST00507 | PRJ007 | CL002 | Axis Bank | Indore Site-014 | Indore | Central | 20 | ROW In Progress | 2025-10-18 | 2025-11-11 |  | 2025-11-29 |  | 4 | Met | Ekavir Bhargava | 117146
ST00508 | PRJ007 | CL002 | Axis Bank | Indore Site-015 | Indore | Central | 100 | Survey Pending | 2025-10-05 | 2025-12-02 |  | 2025-12-17 |  | 2 | Met | Logan Sami | 256770
ST00509 | PRJ007 | CL002 | Axis Bank | Bhopal Site-016 | Bhopal | Central | 10 | Installation Scheduled | 2025-10-24 | 2025-11-28 | 2025-12-08 | 2025-12-13 |  | 8 | Marginal | Unni Bhagat | 67125
ST00510 | PRJ007 | CL002 | Axis Bank | Bhopal Site-017 | Bhopal | Central | 20 | Testing | 2025-10-06 | 2025-11-26 | 2025-12-04 | 2025-12-18 |  | 12 | Marginal | Bhavika Sampath | 235316
ST00511 | PRJ007 | CL002 | Axis Bank | Nagpur Site-018 | Nagpur | Central | 10 | ROW In Progress | 2025-10-20 | 2025-12-01 |  | 2025-12-12 |  | 4 | Met | Simon Tata | 88935
ST00512 | PRJ007 | CL002 | Axis Bank | Indore Site-019 | Indore | Central | 100 | Installation Done | 2025-10-11 | 2025-11-30 | 2025-12-02 | 2025-12-22 |  | 12 | Marginal | Vansha Thakkar | 113845
ST00513 | PRJ007 | CL002 | Axis Bank | Bhopal Site-020 | Bhopal | Central | 100 | Testing | 2025-10-15 | 2025-11-04 | 2025-11-08 | 2025-11-28 |  | 12 | Marginal | Urvashi Ray | 184002
ST00514 | PRJ007 | CL002 | Axis Bank | Nagpur Site-021 | Nagpur | Central | 50 | Pending Acceptance | 2025-10-05 | 2025-11-28 | 2025-12-04 | 2025-12-21 | 2025-12-26 | 6 | Met | Victor Kannan | 115015
ST00515 | PRJ007 | CL002 | Axis Bank | Bhopal Site-022 | Bhopal | Central | 200 | Installation Scheduled | 2025-10-20 | 2025-12-04 | 2025-12-13 | 2025-12-21 |  | 3 | Met | Unni Bhagat | 222659
ST00516 | PRJ007 | CL002 | Axis Bank | Nagpur Site-023 | Nagpur | Central | 10 | Pending Acceptance | 2025-10-12 | 2025-12-06 | 2025-12-01 | 2025-12-16 | 2025-12-15 | 0 | Met | Niharika Sunder | 70611
ST00517 | PRJ007 | CL002 | Axis Bank | Nagpur Site-024 | Nagpur | Central | 50 | ROW In Progress | 2025-10-16 | 2025-11-27 |  | 2025-12-14 |  | 4 | Met | Wriddhish Bhardwaj | 53923
ST00518 | PRJ007 | CL002 | Axis Bank | Bhopal Site-025 | Bhopal | Central | 10 | Testing | 2025-10-03 | 2025-11-30 | 2025-12-01 | 2025-12-29 |  | 12 | Marginal | Advay Contractor | 67645
ST00519 | PRJ007 | CL002 | Axis Bank | Nagpur Site-026 | Nagpur | Central | 20 | ROW In Progress | 2025-10-23 | 2025-12-18 |  | 2026-01-02 |  | 1 | Met | Jai Kota | 122219
ST00520 | PRJ007 | CL002 | Axis Bank | Indore Site-027 | Indore | Central | 50 | Live | 2025-10-04 | 2025-12-03 | 2025-12-12 | 2025-12-21 | 2025-12-31 | 9 | Marginal | Jai Kota | 87458
ST00521 | PRJ007 | CL002 | Axis Bank | Bhopal Site-028 | Bhopal | Central | 50 | Installation Scheduled | 2025-10-03 | 2025-11-16 | 2025-11-23 | 2025-12-06 |  | 0 | Met | Devansh Nigam | 91643
ST00522 | PRJ007 | CL002 | Axis Bank | Indore Site-029 | Indore | Central | 100 | Survey Pending | 2025-10-08 | 2025-12-06 |  | 2025-12-28 |  | 2 | Met | Devansh Rajan | 82715
ST00523 | PRJ007 | CL002 | Axis Bank | Nagpur Site-030 | Nagpur | Central | 10 | Live | 2025-10-08 | 2025-12-06 | 2025-12-04 | 2025-12-30 | 2026-01-04 | 0 | Met | Diya Rattan | 64115
ST00524 | PRJ007 | CL002 | Axis Bank | Bhopal Site-031 | Bhopal | Central | 20 | Testing | 2025-10-10 | 2025-11-27 | 2025-11-22 | 2025-12-22 |  | 12 | Marginal | Ekbal Garg | 54918
ST00525 | PRJ007 | CL002 | Axis Bank | Nagpur Site-032 | Nagpur | Central | 10 | Installation Done | 2025-10-06 | 2025-11-16 | 2025-11-23 | 2025-12-14 |  | 12 | Marginal | Quincy Biswas | 170341
ST00526 | PRJ007 | CL002 | Axis Bank | Indore Site-033 | Indore | Central | 100 | Installation Done | 2025-10-25 | 2025-11-18 | 2025-11-20 | 2025-11-28 |  | 12 | Marginal | Dakshesh Trivedi | 76772
ST00527 | PRJ007 | CL002 | Axis Bank | Nagpur Site-034 | Nagpur | Central | 10 | Testing | 2025-10-13 | 2025-11-23 | 2025-11-27 | 2025-12-15 |  | 12 | Marginal | Gavin Batta | 140775
ST00528 | PRJ007 | CL002 | Axis Bank | Nagpur Site-035 | Nagpur | Central | 20 | Live | 2025-10-12 | 2025-11-06 | 2025-11-15 | 2025-11-25 | 2025-11-28 | 9 | Marginal | Dominic Kakar | 145706
ST00529 | PRJ007 | CL002 | Axis Bank | Nagpur Site-036 | Nagpur | Central | 100 | ROW In Progress | 2025-10-24 | 2025-12-07 |  | 2025-12-20 |  | 5 | Met | Theodore Devi | 277053
ST00530 | PRJ007 | CL002 | Axis Bank | Nagpur Site-037 | Nagpur | Central | 10 | Installation Done | 2025-10-08 | 2025-11-05 | 2025-11-01 | 2025-11-21 |  | 12 | Marginal | Devika Rastogi | 173249
ST00531 | PRJ007 | CL002 | Axis Bank | Indore Site-038 | Indore | Central | 100 | Survey Pending | 2025-10-19 | 2025-11-27 |  | 2025-12-22 |  | 8 | Marginal | Anamika Kanda | 54710
ST00532 | PRJ007 | CL002 | Axis Bank | Indore Site-039 | Indore | Central | 20 | Survey Pending | 2025-10-27 | 2025-11-18 |  | 2025-12-10 |  | 1 | Met | Teerth Bhardwaj | 222754
ST00533 | PRJ007 | CL002 | Axis Bank | Nagpur Site-040 | Nagpur | Central | 20 | ROW In Progress | 2025-10-20 | 2025-11-23 |  | 2025-12-05 |  | 0 | Met | Quincy Biswas | 216398
ST00534 | PRJ007 | CL002 | Axis Bank | Bhopal Site-041 | Bhopal | Central | 20 | Installation Done | 2025-10-21 | 2025-11-12 | 2025-11-14 | 2025-12-12 |  | 12 | Marginal | Nihal Shere | 90154
ST00535 | PRJ007 | CL002 | Axis Bank | Nagpur Site-042 | Nagpur | Central | 200 | Survey Pending | 2025-10-11 | 2025-11-06 |  | 2025-11-30 |  | 2 | Met | Liam Koshy | 259381
ST00536 | PRJ007 | CL002 | Axis Bank | Bhopal Site-043 | Bhopal | Central | 20 | ROW In Progress | 2025-10-21 | 2025-12-19 |  | 2026-01-05 |  | 1 | Met | Nitesh Raghavan | 133432
ST00537 | PRJ007 | CL002 | Axis Bank | Nagpur Site-044 | Nagpur | Central | 10 | Live | 2025-10-12 | 2025-11-08 | 2025-11-07 | 2025-11-28 | 2025-12-01 | 0 | Met | Ekiya Suresh | 132950
ST00538 | PRJ007 | CL002 | Axis Bank | Bhopal Site-045 | Bhopal | Central | 200 | ROW In Progress | 2025-10-06 | 2025-11-21 |  | 2025-12-06 |  | 5 | Met | Kashvi Edwin | 159992
ST00539 | PRJ007 | CL002 | Axis Bank | Bhopal Site-046 | Bhopal | Central | 20 | Pending Acceptance | 2025-10-03 | 2025-10-31 | 2025-10-29 | 2025-11-30 | 2025-12-09 | 0 | Met | Anamika Kanda | 275588
ST00540 | PRJ007 | CL002 | Axis Bank | Indore Site-047 | Indore | Central | 100 | ROW In Progress | 2025-10-02 | 2025-11-02 |  | 2025-11-14 |  | 4 | Met | Vansha Thakkar | 226497
ST00541 | PRJ007 | CL002 | Axis Bank | Bhopal Site-048 | Bhopal | Central | 20 | Installation Scheduled | 2025-10-22 | 2025-11-28 | 2025-12-07 | 2025-12-21 |  | 3 | Met | Diya Rattan | 201309
ST00542 | PRJ007 | CL002 | Axis Bank | Bhopal Site-049 | Bhopal | Central | 10 | Live | 2025-10-21 | 2025-11-15 | 2025-11-19 | 2025-12-06 | 2025-12-16 | 4 | Met | Devika Rastogi | 95306
ST00543 | PRJ007 | CL002 | Axis Bank | Bhopal Site-050 | Bhopal | Central | 100 | Pending Acceptance | 2025-10-05 | 2025-12-03 | 2025-12-09 | 2025-12-30 | 2026-01-03 | 6 | Met | Ekapad Walia | 117463
ST00544 | PRJ007 | CL002 | Axis Bank | Bhopal Site-051 | Bhopal | Central | 20 | ROW In Progress | 2025-10-27 | 2025-11-25 |  | 2025-12-20 |  | 7 | Met | Yashica Issac | 220673
ST00545 | PRJ007 | CL002 | Axis Bank | Bhopal Site-052 | Bhopal | Central | 50 | Survey Pending | 2025-10-13 | 2025-11-20 |  | 2025-12-06 |  | 6 | Met | Irya Sampath | 206695
ST00546 | PRJ007 | CL002 | Axis Bank | Indore Site-053 | Indore | Central | 20 | Survey Pending | 2025-10-25 | 2025-11-17 |  | 2025-12-14 |  | 2 | Met | Daksh Karnik | 172155
ST00547 | PRJ007 | CL002 | Axis Bank | Nagpur Site-054 | Nagpur | Central | 100 | ROW In Progress | 2025-10-09 | 2025-11-26 |  | 2025-12-24 |  | 5 | Met | Farhan Chada | 240844
ST00548 | PRJ007 | CL002 | Axis Bank | Nagpur Site-055 | Nagpur | Central | 20 | Live | 2025-10-09 | 2025-11-05 | 2025-11-10 | 2025-11-22 | 2025-11-22 | 5 | Met | Niharika Sunder | 273035
ST00549 | PRJ007 | CL002 | Axis Bank | Bhopal Site-056 | Bhopal | Central | 100 | Installation Done | 2025-10-09 | 2025-11-02 | 2025-11-12 | 2025-11-30 |  | 12 | Marginal | Simon Tata | 278436
ST00550 | PRJ007 | CL002 | Axis Bank | Indore Site-057 | Indore | Central | 50 | ROW In Progress | 2025-10-21 | 2025-12-09 |  | 2025-12-24 |  | 6 | Met | Radhika Dugar | 164993
ST00551 | PRJ007 | CL002 | Axis Bank | Nagpur Site-058 | Nagpur | Central | 20 | ROW In Progress | 2025-10-13 | 2025-11-19 |  | 2025-12-05 |  | 5 | Met | Diya Rattan | 226458
ST00552 | PRJ007 | CL002 | Axis Bank | Nagpur Site-059 | Nagpur | Central | 100 | Survey Pending | 2025-10-06 | 2025-11-02 |  | 2025-11-26 |  | 7 | Met | Kashvi Edwin | 244318
ST00553 | PRJ007 | CL002 | Axis Bank | Indore Site-060 | Indore | Central | 200 | Installation Scheduled | 2025-10-11 | 2025-12-08 | 2025-12-08 | 2026-01-07 |  | 2 | Met | Siddharth Zacharia | 67668
ST00554 | PRJ007 | CL002 | Axis Bank | Indore Site-061 | Indore | Central | 10 | Live | 2025-10-17 | 2025-11-19 | 2025-11-29 | 2025-12-13 | 2025-12-18 | 10 | Marginal | Nitesh Raghavan | 237984
ST00555 | PRJ007 | CL002 | Axis Bank | Bhopal Site-062 | Bhopal | Central | 200 | Installation Scheduled | 2025-10-15 | 2025-12-11 | 2025-12-13 | 2026-01-08 |  | 2 | Met | Ekbal Garg | 154516
ST00556 | PRJ007 | CL002 | Axis Bank | Bhopal Site-063 | Bhopal | Central | 200 | Survey Pending | 2025-10-17 | 2025-12-08 |  | 2025-12-19 |  | 6 | Met | Chandresh Zachariah | 170637
ST00557 | PRJ007 | CL002 | Axis Bank | Nagpur Site-064 | Nagpur | Central | 100 | Live | 2025-10-16 | 2025-12-06 | 2025-12-08 | 2025-12-18 | 2025-12-15 | 2 | Met | Kabir Soman | 79789
ST00558 | PRJ007 | CL002 | Axis Bank | Indore Site-065 | Indore | Central | 20 | Installation Scheduled | 2025-10-22 | 2025-11-16 | 2025-11-11 | 2025-12-11 |  | 4 | Met | Teerth Bhardwaj | 269899
ST00559 | PRJ007 | CL002 | Axis Bank | Nagpur Site-066 | Nagpur | Central | 20 | Live | 2025-10-02 | 2025-11-20 | 2025-11-29 | 2025-12-04 | 2025-12-13 | 9 | Marginal | Logan Sami | 209314
ST00560 | PRJ007 | CL002 | Axis Bank | Indore Site-067 | Indore | Central | 200 | Live | 2025-10-02 | 2025-12-01 | 2025-11-28 | 2025-12-23 | 2025-12-30 | 0 | Met | Diya Rattan | 122749
ST00561 | PRJ007 | CL002 | Axis Bank | Indore Site-068 | Indore | Central | 10 | Live | 2025-10-24 | 2025-12-22 | 2025-12-23 | 2026-01-03 | 2026-01-10 | 1 | Met | Ranveer Yadav | 277778
ST00562 | PRJ007 | CL002 | Axis Bank | Bhopal Site-069 | Bhopal | Central | 50 | ROW In Progress | 2025-10-13 | 2025-12-01 |  | 2025-12-30 |  | 0 | Met | Ranveer Yadav | 90945
ST00563 | PRJ007 | CL002 | Axis Bank | Nagpur Site-070 | Nagpur | Central | 50 | Testing | 2025-10-04 | 2025-11-28 | 2025-11-29 | 2025-12-12 |  | 12 | Marginal | Devika Rastogi | 186461
ST00564 | PRJ007 | CL002 | Axis Bank | Bhopal Site-071 | Bhopal | Central | 50 | Live | 2025-10-25 | 2025-12-21 | 2025-12-22 | 2026-01-07 | 2026-01-14 | 1 | Met | Victor Kannan | 177006
ST00565 | PRJ007 | CL002 | Axis Bank | Nagpur Site-072 | Nagpur | Central | 100 | Installation Done | 2025-10-03 | 2025-10-27 | 2025-11-02 | 2025-11-17 |  | 12 | Marginal | Quincy Biswas | 176452
ST00566 | PRJ007 | CL002 | Axis Bank | Nagpur Site-073 | Nagpur | Central | 10 | Live | 2025-10-17 | 2025-12-10 | 2025-12-14 | 2026-01-03 | 2026-01-11 | 4 | Met | Wriddhish Bhardwaj | 278807
ST00567 | PRJ007 | CL002 | Axis Bank | Indore Site-074 | Indore | Central | 10 | ROW In Progress | 2025-10-14 | 2025-11-14 |  | 2025-12-03 |  | 1 | Met | Kashvi Edwin | 117336
ST00568 | PRJ007 | CL002 | Axis Bank | Bhopal Site-075 | Bhopal | Central | 50 | Live | 2025-10-17 | 2025-11-15 | 2025-11-16 | 2025-12-11 | 2025-12-08 | 1 | Met | Tanay Rattan | 223887
ST00569 | PRJ007 | CL002 | Axis Bank | Nagpur Site-076 | Nagpur | Central | 50 | Pending Acceptance | 2025-10-17 | 2025-11-28 | 2025-12-06 | 2025-12-22 | 2025-12-19 | 8 | Marginal | Wriddhish Bhardwaj | 61501
ST00570 | PRJ007 | CL002 | Axis Bank | Bhopal Site-077 | Bhopal | Central | 50 | Live | 2025-10-09 | 2025-12-01 | 2025-12-06 | 2025-12-24 | 2025-12-31 | 5 | Met | Quincy Biswas | 200545
ST00571 | PRJ007 | CL002 | Axis Bank | Nagpur Site-078 | Nagpur | Central | 50 | Live | 2025-10-19 | 2025-12-06 | 2025-12-15 | 2025-12-25 | 2025-12-26 | 9 | Marginal | Kashvi Edwin | 251901
ST00572 | PRJ007 | CL002 | Axis Bank | Indore Site-079 | Indore | Central | 50 | Installation Scheduled | 2025-10-13 | 2025-11-20 | 2025-11-16 | 2025-12-04 |  | 5 | Met | Teerth Bhardwaj | 88611
ST00573 | PRJ007 | CL002 | Axis Bank | Nagpur Site-080 | Nagpur | Central | 20 | Pending Acceptance | 2025-10-24 | 2025-12-17 | 2025-12-21 | 2026-01-01 | 2026-01-03 | 4 | Met | Yashica Issac | 107365
ST00574 | PRJ007 | CL002 | Axis Bank | Bhopal Site-081 | Bhopal | Central | 50 | Survey Pending | 2025-10-12 | 2025-12-07 |  | 2025-12-21 |  | 7 | Met | Logan Sami | 93364
ST00575 | PRJ007 | CL002 | Axis Bank | Bhopal Site-082 | Bhopal | Central | 50 | Testing | 2025-10-03 | 2025-11-12 | 2025-11-18 | 2025-11-26 |  | 12 | Marginal | Mohammed Gupta | 186522
ST00576 | PRJ007 | CL002 | Axis Bank | Bhopal Site-083 | Bhopal | Central | 20 | Testing | 2025-10-05 | 2025-10-26 | 2025-11-02 | 2025-11-20 |  | 12 | Marginal | Teerth Bhardwaj | 128943
ST00577 | PRJ007 | CL002 | Axis Bank | Bhopal Site-084 | Bhopal | Central | 50 | Survey Pending | 2025-10-25 | 2025-12-18 |  | 2026-01-13 |  | 5 | Met | Vansha Thakkar | 279875
ST00578 | PRJ007 | CL002 | Axis Bank | Indore Site-085 | Indore | Central | 50 | Pending Acceptance | 2025-10-26 | 2025-12-21 | 2025-12-20 | 2026-01-18 | 2026-01-29 | 0 | Met | Upadhriti Wadhwa | 236795
ST00579 | PRJ007 | CL002 | Axis Bank | Indore Site-086 | Indore | Central | 100 | Live | 2025-10-06 | 2025-11-30 | 2025-11-28 | 2025-12-19 | 2025-12-16 | 0 | Met | Alka Wable | 161909
ST00580 | PRJ007 | CL002 | Axis Bank | Indore Site-087 | Indore | Central | 200 | ROW In Progress | 2025-10-03 | 2025-11-30 |  | 2025-12-30 |  | 3 | Met | Alka Wable | 249808
ST00581 | PRJ007 | CL002 | Axis Bank | Indore Site-088 | Indore | Central | 200 | ROW In Progress | 2025-10-04 | 2025-11-27 |  | 2025-12-21 |  | 1 | Met | Chandresh Zachariah | 95973
ST00582 | PRJ007 | CL002 | Axis Bank | Indore Site-089 | Indore | Central | 20 | Installation Scheduled | 2025-10-21 | 2025-12-12 | 2025-12-08 | 2026-01-02 |  | 6 | Met | Nitesh Raghavan | 141896
ST00583 | PRJ007 | CL002 | Axis Bank | Indore Site-090 | Indore | Central | 100 | Installation Done | 2025-10-11 | 2025-11-22 | 2025-11-28 | 2025-12-11 |  | 12 | Marginal | Gavin Batta | 101543
ST00584 | PRJ007 | CL002 | Axis Bank | Nagpur Site-091 | Nagpur | Central | 100 | Live | 2025-10-25 | 2025-12-10 | 2025-12-19 | 2025-12-29 | 2025-12-31 | 9 | Marginal | Tanay Rattan | 81586
ST00585 | PRJ007 | CL002 | Axis Bank | Nagpur Site-092 | Nagpur | Central | 200 | Testing | 2025-10-06 | 2025-11-08 | 2025-11-12 | 2025-12-03 |  | 12 | Marginal | Irya Sampath | 62331
ST00586 | PRJ008 | CL002 | Axis Bank | Surat Site-001 | Surat | West | 200 | ROW In Progress | 2025-12-08 | 2026-01-28 |  | 2026-02-18 |  | 4 | Met | Dominic Kakar | 66560
ST00587 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-002 | Ahmedabad | West | 50 | Installation Done | 2025-12-16 | 2026-01-23 | 2026-02-01 | 2026-02-21 |  | 12 | Marginal | Bhavika Sampath | 104211
ST00588 | PRJ008 | CL002 | Axis Bank | Surat Site-003 | Surat | West | 20 | Installation Scheduled | 2025-12-17 | 2026-01-18 | 2026-01-15 | 2026-02-12 |  | 5 | Met | Nihal Shere | 221726
ST00589 | PRJ008 | CL002 | Axis Bank | Surat Site-004 | Surat | West | 100 | Live | 2025-12-16 | 2026-02-02 | 2026-01-30 | 2026-02-15 | 2026-02-16 | 0 | Met | Girik Khalsa | 227199
ST00590 | PRJ008 | CL002 | Axis Bank | Mumbai Site-005 | Mumbai | West | 20 | Live | 2025-12-09 | 2026-01-02 | 2026-01-08 | 2026-01-18 | 2026-01-25 | 6 | Met | Girik Khalsa | 77181
ST00591 | PRJ008 | CL002 | Axis Bank | Pune Site-006 | Pune | West | 100 | Live | 2025-12-27 | 2026-02-16 | 2026-02-19 | 2026-03-16 | 2026-03-21 | 3 | Met | Ikbal Kothari | 169735
ST00592 | PRJ008 | CL002 | Axis Bank | Surat Site-007 | Surat | West | 10 | Pending Acceptance | 2025-12-20 | 2026-01-26 | 2026-01-25 | 2026-02-19 | 2026-02-19 | 0 | Met | Jai Kota | 173277
ST00593 | PRJ008 | CL002 | Axis Bank | Surat Site-008 | Surat | West | 100 | Installation Scheduled | 2025-12-08 | 2025-12-29 | 2025-12-27 | 2026-01-09 |  | 1 | Met | Daksh Karnik | 91948
ST00594 | PRJ008 | CL002 | Axis Bank | Surat Site-009 | Surat | West | 200 | Testing | 2025-12-14 | 2026-01-12 | 2026-01-16 | 2026-02-10 |  | 12 | Marginal | Michael Dutta | 244274
ST00595 | PRJ008 | CL002 | Axis Bank | Mumbai Site-010 | Mumbai | West | 100 | Live | 2025-12-20 | 2026-02-09 | 2026-02-18 | 2026-02-25 | 2026-03-03 | 9 | Marginal | Quincy Biswas | 177328
ST00596 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-011 | Ahmedabad | West | 100 | Testing | 2025-12-29 | 2026-02-21 | 2026-02-16 | 2026-03-04 |  | 12 | Marginal | Advay Contractor | 145566
ST00597 | PRJ008 | CL002 | Axis Bank | Surat Site-012 | Surat | West | 20 | Installation Scheduled | 2025-12-16 | 2026-02-02 | 2026-02-11 | 2026-02-13 |  | 0 | Met | Arya Sunder | 276918
ST00598 | PRJ008 | CL002 | Axis Bank | Pune Site-013 | Pune | West | 10 | Installation Done | 2025-12-08 | 2026-01-16 | 2026-01-23 | 2026-02-10 |  | 12 | Marginal | Quincy Biswas | 218035
ST00599 | PRJ008 | CL002 | Axis Bank | Surat Site-014 | Surat | West | 50 | Installation Done | 2025-12-09 | 2026-01-30 | 2026-01-26 | 2026-02-21 |  | 12 | Marginal | Wahab Raval | 199938
ST00600 | PRJ008 | CL002 | Axis Bank | Surat Site-015 | Surat | West | 10 | Testing | 2025-12-15 | 2026-01-22 | 2026-01-27 | 2026-02-02 |  | 12 | Marginal | Dominic Kakar | 78606
ST00601 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-016 | Ahmedabad | West | 100 | Installation Scheduled | 2025-12-27 | 2026-02-22 | 2026-02-17 | 2026-03-24 |  | 5 | Met | Michael Dutta | 157236
ST00602 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-017 | Ahmedabad | West | 20 | Pending Acceptance | 2025-12-17 | 2026-01-28 | 2026-01-24 | 2026-02-14 | 2026-02-18 | 0 | Met | Kevin Solanki | 200328
ST00603 | PRJ008 | CL002 | Axis Bank | Mumbai Site-018 | Mumbai | West | 10 | Pending Acceptance | 2025-12-06 | 2026-01-14 | 2026-01-12 | 2026-02-03 | 2026-02-05 | 0 | Met | Girindra Chatterjee | 54798
ST00604 | PRJ008 | CL002 | Axis Bank | Surat Site-019 | Surat | West | 100 | Live | 2025-12-17 | 2026-02-11 | 2026-02-19 | 2026-03-01 | 2026-02-26 | 8 | Marginal | Anamika Kanda | 127972
ST00605 | PRJ008 | CL002 | Axis Bank | Surat Site-020 | Surat | West | 10 | Testing | 2025-12-14 | 2026-02-08 | 2026-02-06 | 2026-03-05 |  | 12 | Marginal | Ekapad Walia | 133071
ST00606 | PRJ008 | CL002 | Axis Bank | Surat Site-021 | Surat | West | 50 | Installation Done | 2025-12-28 | 2026-02-07 | 2026-02-07 | 2026-03-08 |  | 12 | Marginal | Ranveer Yadav | 159292
ST00607 | PRJ008 | CL002 | Axis Bank | Pune Site-022 | Pune | West | 50 | Installation Done | 2025-12-29 | 2026-01-22 | 2026-01-23 | 2026-02-10 |  | 12 | Marginal | Simon Tata | 122940
ST00608 | PRJ008 | CL002 | Axis Bank | Surat Site-023 | Surat | West | 50 | Live | 2025-12-23 | 2026-01-17 | 2026-01-15 | 2026-02-14 | 2026-02-21 | 0 | Met | Liam Koshy | 193485
ST00609 | PRJ008 | CL002 | Axis Bank | Surat Site-024 | Surat | West | 50 | Installation Done | 2025-12-15 | 2026-01-08 | 2026-01-12 | 2026-02-03 |  | 12 | Marginal | Madhavi Lanka | 218921
ST00610 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-025 | Ahmedabad | West | 10 | Installation Scheduled | 2025-12-16 | 2026-01-21 | 2026-01-30 | 2026-02-17 |  | 2 | Met | Isaac Patil | 196216
ST00611 | PRJ008 | CL002 | Axis Bank | Surat Site-026 | Surat | West | 200 | Installation Scheduled | 2025-12-27 | 2026-02-14 | 2026-02-17 | 2026-03-16 |  | 8 | Marginal | Madhavi Lanka | 193404
ST00612 | PRJ008 | CL002 | Axis Bank | Mumbai Site-027 | Mumbai | West | 20 | Installation Done | 2025-12-15 | 2026-02-02 | 2026-02-01 | 2026-02-19 |  | 12 | Marginal | Arya Sunder | 266281
ST00613 | PRJ008 | CL002 | Axis Bank | Surat Site-028 | Surat | West | 50 | Installation Done | 2025-12-06 | 2026-02-04 | 2026-02-05 | 2026-02-27 |  | 12 | Marginal | Ekansh Balay | 214356
ST00614 | PRJ008 | CL002 | Axis Bank | Pune Site-029 | Pune | West | 20 | Installation Scheduled | 2025-12-23 | 2026-01-27 | 2026-02-03 | 2026-02-13 |  | 1 | Met | Wriddhish Bhardwaj | 52262
ST00615 | PRJ008 | CL002 | Axis Bank | Pune Site-030 | Pune | West | 100 | Live | 2025-12-13 | 2026-01-31 | 2026-02-10 | 2026-02-27 | 2026-03-09 | 10 | Marginal | Diya Rattan | 97950
ST00616 | PRJ008 | CL002 | Axis Bank | Pune Site-031 | Pune | West | 10 | Installation Scheduled | 2025-12-04 | 2026-01-09 | 2026-01-12 | 2026-02-05 |  | 2 | Met | Quincy Biswas | 250057
ST00617 | PRJ008 | CL002 | Axis Bank | Mumbai Site-032 | Mumbai | West | 10 | Survey Pending | 2025-12-06 | 2026-01-15 |  | 2026-02-13 |  | 4 | Met | Niharika Sunder | 140272
ST00618 | PRJ008 | CL002 | Axis Bank | Mumbai Site-033 | Mumbai | West | 200 | Installation Done | 2025-12-27 | 2026-01-24 | 2026-01-26 | 2026-02-06 |  | 12 | Marginal | Yatin Baral | 76625
ST00619 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-034 | Ahmedabad | West | 50 | Installation Done | 2025-12-06 | 2026-01-10 | 2026-01-08 | 2026-01-30 |  | 12 | Marginal | Faqid Savant | 256246
ST00620 | PRJ008 | CL002 | Axis Bank | Pune Site-035 | Pune | West | 50 | Pending Acceptance | 2025-12-10 | 2026-01-08 | 2026-01-06 | 2026-01-23 | 2026-01-26 | 0 | Met | Bhavika Sampath | 152053
ST00621 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-036 | Ahmedabad | West | 200 | Live | 2025-12-05 | 2026-01-25 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 6 | Met | Nitesh Raghavan | 169480
ST00622 | PRJ008 | CL002 | Axis Bank | Pune Site-037 | Pune | West | 50 | Pending Acceptance | 2025-12-29 | 2026-01-27 | 2026-02-02 | 2026-02-21 | 2026-03-01 | 6 | Met | Anamika Kanda | 214187
ST00623 | PRJ008 | CL002 | Axis Bank | Mumbai Site-038 | Mumbai | West | 50 | Live | 2025-12-25 | 2026-01-17 | 2026-01-19 | 2026-02-04 | 2026-02-13 | 2 | Met | Ranveer Yadav | 257926
ST00624 | PRJ008 | CL002 | Axis Bank | Mumbai Site-039 | Mumbai | West | 100 | Testing | 2025-12-11 | 2026-01-28 | 2026-02-04 | 2026-02-07 |  | 12 | Marginal | Jai Kota | 123876
ST00625 | PRJ008 | CL002 | Axis Bank | Mumbai Site-040 | Mumbai | West | 100 | Pending Acceptance | 2025-12-28 | 2026-02-01 | 2026-02-05 | 2026-02-17 | 2026-02-19 | 4 | Met | Urvashi Ray | 275547
ST00626 | PRJ008 | CL002 | Axis Bank | Surat Site-041 | Surat | West | 50 | Live | 2025-12-12 | 2026-01-06 | 2026-01-16 | 2026-01-31 | 2026-02-10 | 10 | Marginal | Nitesh Raghavan | 274837
ST00627 | PRJ008 | CL002 | Axis Bank | Mumbai Site-042 | Mumbai | West | 200 | Live | 2025-12-26 | 2026-01-31 | 2026-01-28 | 2026-02-21 | 2026-03-03 | 0 | Met | Girindra Chatterjee | 163819
ST00628 | PRJ008 | CL002 | Axis Bank | Mumbai Site-043 | Mumbai | West | 10 | Live | 2025-12-24 | 2026-01-24 | 2026-02-02 | 2026-02-23 | 2026-02-24 | 9 | Marginal | Girik Khalsa | 97448
ST00629 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-044 | Ahmedabad | West | 20 | Installation Scheduled | 2025-12-06 | 2026-01-02 | 2026-01-02 | 2026-01-19 |  | 8 | Marginal | Niharika Sunder | 252786
ST00630 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-045 | Ahmedabad | West | 200 | Installation Done | 2025-12-27 | 2026-01-24 | 2026-01-27 | 2026-02-08 |  | 12 | Marginal | Girindra Chatterjee | 254591
ST00631 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-046 | Ahmedabad | West | 100 | ROW In Progress | 2025-12-17 | 2026-01-29 |  | 2026-02-13 |  | 6 | Met | Alka Wable | 50435
ST00632 | PRJ008 | CL002 | Axis Bank | Mumbai Site-047 | Mumbai | West | 20 | Pending Acceptance | 2025-12-24 | 2026-02-21 | 2026-02-23 | 2026-03-05 | 2026-03-16 | 2 | Met | Devansh Nigam | 228831
ST00633 | PRJ008 | CL002 | Axis Bank | Pune Site-048 | Pune | West | 20 | Survey Pending | 2025-12-23 | 2026-02-08 |  | 2026-03-09 |  | 4 | Met | Gavin Batta | 141448
ST00634 | PRJ008 | CL002 | Axis Bank | Pune Site-049 | Pune | West | 10 | Pending Acceptance | 2025-12-07 | 2025-12-27 | 2026-01-04 | 2026-01-20 | 2026-02-01 | 8 | Marginal | Alka Wable | 232056
ST00635 | PRJ008 | CL002 | Axis Bank | Pune Site-050 | Pune | West | 100 | ROW In Progress | 2025-12-29 | 2026-02-04 |  | 2026-02-23 |  | 7 | Met | Harini Choudhury | 158064
ST00636 | PRJ008 | CL002 | Axis Bank | Pune Site-051 | Pune | West | 100 | Testing | 2025-12-13 | 2026-01-14 | 2026-01-22 | 2026-01-29 |  | 12 | Marginal | Aarush Lall | 52542
ST00637 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-052 | Ahmedabad | West | 200 | Pending Acceptance | 2025-12-11 | 2026-02-08 | 2026-02-17 | 2026-02-25 | 2026-03-05 | 9 | Marginal | Teerth Bhardwaj | 67475
ST00638 | PRJ008 | CL002 | Axis Bank | Mumbai Site-053 | Mumbai | West | 100 | Installation Done | 2025-12-14 | 2026-01-28 | 2026-01-29 | 2026-02-19 |  | 12 | Marginal | Jai Kota | 64151
ST00639 | PRJ008 | CL002 | Axis Bank | Mumbai Site-054 | Mumbai | West | 50 | Testing | 2025-12-05 | 2026-01-15 | 2026-01-17 | 2026-02-09 |  | 12 | Marginal | Dominic Kakar | 46405
ST00640 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-055 | Ahmedabad | West | 20 | Installation Done | 2025-12-16 | 2026-01-24 | 2026-01-31 | 2026-02-14 |  | 12 | Marginal | Dominic Kakar | 197171
ST00641 | PRJ008 | CL002 | Axis Bank | Pune Site-056 | Pune | West | 10 | Installation Scheduled | 2025-12-20 | 2026-02-09 | 2026-02-14 | 2026-03-05 |  | 2 | Met | Urvashi Ray | 231189
ST00642 | PRJ008 | CL002 | Axis Bank | Surat Site-057 | Surat | West | 100 | ROW In Progress | 2025-12-07 | 2026-01-16 |  | 2026-01-27 |  | 2 | Met | Ekavir Bhargava | 241037
ST00643 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-058 | Ahmedabad | West | 100 | Pending Acceptance | 2025-12-13 | 2026-01-18 | 2026-01-21 | 2026-02-13 | 2026-02-20 | 3 | Met | Kashvi Edwin | 127717
ST00644 | PRJ008 | CL002 | Axis Bank | Surat Site-059 | Surat | West | 20 | Live | 2025-12-08 | 2026-02-01 | 2026-02-10 | 2026-02-12 | 2026-02-15 | 9 | Marginal | Simon Tata | 105256
ST00645 | PRJ008 | CL002 | Axis Bank | Pune Site-060 | Pune | West | 10 | Survey Pending | 2025-12-12 | 2026-01-11 |  | 2026-02-04 |  | 6 | Met | Wahab Raval | 55693
ST00646 | PRJ008 | CL002 | Axis Bank | Surat Site-061 | Surat | West | 100 | Installation Done | 2025-12-26 | 2026-02-19 | 2026-03-01 | 2026-03-15 |  | 12 | Marginal | Upadhriti Wadhwa | 266731
ST00647 | PRJ008 | CL002 | Axis Bank | Pune Site-062 | Pune | West | 20 | ROW In Progress | 2025-12-06 | 2026-01-08 |  | 2026-01-27 |  | 2 | Met | Victor Kannan | 192651
ST00648 | PRJ008 | CL002 | Axis Bank | Pune Site-063 | Pune | West | 10 | Testing | 2025-12-04 | 2026-01-26 | 2026-01-26 | 2026-02-18 |  | 12 | Marginal | Raksha Varughese | 246393
ST00649 | PRJ008 | CL002 | Axis Bank | Surat Site-064 | Surat | West | 50 | Live | 2025-12-14 | 2026-01-04 | 2026-01-08 | 2026-01-17 | 2026-01-26 | 4 | Met | Devansh Rajan | 264408
ST00650 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-065 | Ahmedabad | West | 50 | ROW In Progress | 2025-12-06 | 2026-01-24 |  | 2026-02-18 |  | 7 | Met | Ekbal Garg | 131357
ST00651 | PRJ008 | CL002 | Axis Bank | Mumbai Site-066 | Mumbai | West | 50 | Live | 2025-12-18 | 2026-01-27 | 2026-01-26 | 2026-02-12 | 2026-02-10 | 0 | Met | Girindra Chatterjee | 254229
ST00652 | PRJ008 | CL002 | Axis Bank | Mumbai Site-067 | Mumbai | West | 50 | Live | 2025-12-21 | 2026-02-17 | 2026-02-24 | 2026-03-01 | 2026-03-10 | 7 | Met | Ekiya Suresh | 107935
ST00653 | PRJ008 | CL002 | Axis Bank | Surat Site-068 | Surat | West | 50 | ROW In Progress | 2025-12-10 | 2026-01-09 |  | 2026-01-31 |  | 6 | Met | Yashica Cherian | 76615
ST00654 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-069 | Ahmedabad | West | 10 | Installation Done | 2025-12-17 | 2026-01-25 | 2026-01-24 | 2026-02-15 |  | 12 | Marginal | Logan Sami | 179388
ST00655 | PRJ008 | CL002 | Axis Bank | Pune Site-070 | Pune | West | 200 | Installation Done | 2025-12-16 | 2026-02-04 | 2026-02-07 | 2026-03-04 |  | 12 | Marginal | Nitesh Raghavan | 68651
ST00656 | PRJ008 | CL002 | Axis Bank | Surat Site-071 | Surat | West | 10 | Live | 2025-12-23 | 2026-01-23 | 2026-01-31 | 2026-02-22 | 2026-03-04 | 8 | Marginal | Dominic Kakar | 179569
ST00657 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-072 | Ahmedabad | West | 50 | Pending Acceptance | 2025-12-25 | 2026-01-28 | 2026-01-27 | 2026-02-22 | 2026-02-21 | 0 | Met | Dipta Bhandari | 159650
ST00658 | PRJ008 | CL002 | Axis Bank | Mumbai Site-073 | Mumbai | West | 20 | Live | 2025-12-19 | 2026-01-27 | 2026-01-26 | 2026-02-10 | 2026-02-16 | 0 | Met | Nitesh Raghavan | 122458
ST00659 | PRJ008 | CL002 | Axis Bank | Mumbai Site-074 | Mumbai | West | 100 | Testing | 2025-12-05 | 2026-01-26 | 2026-01-24 | 2026-02-21 |  | 12 | Marginal | Niharika Sunder | 69768
ST00660 | PRJ008 | CL002 | Axis Bank | Surat Site-075 | Surat | West | 200 | Live | 2025-12-22 | 2026-01-27 | 2026-02-02 | 2026-02-14 | 2026-02-13 | 6 | Met | Anamika Kanda | 74867
ST00661 | PRJ008 | CL002 | Axis Bank | Surat Site-076 | Surat | West | 100 | ROW In Progress | 2025-12-09 | 2026-01-23 |  | 2026-02-03 |  | 1 | Met | Arya Sunder | 127299
ST00662 | PRJ008 | CL002 | Axis Bank | Surat Site-077 | Surat | West | 20 | Live | 2025-12-18 | 2026-02-15 | 2026-02-18 | 2026-03-07 | 2026-03-09 | 3 | Met | Isaac Patil | 65505
ST00663 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-078 | Ahmedabad | West | 10 | Live | 2025-12-07 | 2026-01-23 | 2026-01-18 | 2026-02-02 | 2026-02-11 | 0 | Met | Nihal Shere | 90019
ST00664 | PRJ008 | CL002 | Axis Bank | Surat Site-079 | Surat | West | 200 | Installation Done | 2025-12-16 | 2026-02-12 | 2026-02-22 | 2026-03-03 |  | 12 | Marginal | Ranveer Yadav | 226052
ST00665 | PRJ008 | CL002 | Axis Bank | Surat Site-080 | Surat | West | 10 | Live | 2025-12-06 | 2026-01-03 | 2026-01-02 | 2026-01-13 | 2026-01-16 | 0 | Met | Anamika Kanda | 227460
ST00666 | PRJ008 | CL002 | Axis Bank | Pune Site-081 | Pune | West | 100 | Live | 2025-12-10 | 2026-01-29 | 2026-01-28 | 2026-02-28 | 2026-03-04 | 0 | Met | Wriddhish Bhardwaj | 67568
ST00667 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-082 | Ahmedabad | West | 20 | Live | 2025-12-08 | 2026-01-27 | 2026-02-04 | 2026-02-06 | 2026-02-06 | 8 | Marginal | Yashica Cherian | 238667
ST00668 | PRJ008 | CL002 | Axis Bank | Surat Site-083 | Surat | West | 20 | Pending Acceptance | 2025-12-19 | 2026-01-09 | 2026-01-18 | 2026-02-06 | 2026-02-10 | 9 | Marginal | Ekavir Varkey | 194272
ST00669 | PRJ008 | CL002 | Axis Bank | Surat Site-084 | Surat | West | 100 | Survey Pending | 2025-12-04 | 2025-12-30 |  | 2026-01-29 |  | 6 | Met | Wahab Raval | 238220
ST00670 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-085 | Ahmedabad | West | 20 | Survey Pending | 2025-12-16 | 2026-02-05 |  | 2026-03-03 |  | 7 | Met | Tara Dhar | 183492
ST00671 | PRJ008 | CL002 | Axis Bank | Mumbai Site-086 | Mumbai | West | 100 | Installation Done | 2025-12-14 | 2026-02-07 | 2026-02-04 | 2026-02-25 |  | 12 | Marginal | Vansha Thakkar | 75655
ST00672 | PRJ008 | CL002 | Axis Bank | Surat Site-087 | Surat | West | 10 | Testing | 2025-12-24 | 2026-02-04 | 2026-02-13 | 2026-02-27 |  | 12 | Marginal | Yashica Issac | 120500
ST00673 | PRJ008 | CL002 | Axis Bank | Pune Site-088 | Pune | West | 50 | Installation Done | 2025-12-18 | 2026-01-21 | 2026-01-23 | 2026-02-18 |  | 12 | Marginal | Dipta Bhandari | 79382
ST00674 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-089 | Ahmedabad | West | 200 | Live | 2025-12-16 | 2026-01-31 | 2026-02-06 | 2026-02-25 | 2026-02-27 | 6 | Met | Ekapad Walia | 119044
ST00675 | PRJ008 | CL002 | Axis Bank | Mumbai Site-090 | Mumbai | West | 10 | Live | 2025-12-08 | 2026-01-08 | 2026-01-09 | 2026-01-23 | 2026-02-04 | 1 | Met | Tanay Rattan | 174427
ST00676 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-091 | Ahmedabad | West | 50 | Installation Scheduled | 2025-12-21 | 2026-01-13 | 2026-01-08 | 2026-02-03 |  | 4 | Met | Yashica Issac | 90800
ST00677 | PRJ008 | CL002 | Axis Bank | Mumbai Site-092 | Mumbai | West | 10 | Live | 2025-12-14 | 2026-01-30 | 2026-01-28 | 2026-02-28 | 2026-03-04 | 0 | Met | Alka Wable | 172497
ST00678 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-093 | Ahmedabad | West | 20 | Pending Acceptance | 2025-12-29 | 2026-02-09 | 2026-02-05 | 2026-03-08 | 2026-03-13 | 0 | Met | Devansh Rajan | 230179
ST00679 | PRJ008 | CL002 | Axis Bank | Mumbai Site-094 | Mumbai | West | 200 | Pending Acceptance | 2025-12-18 | 2026-02-05 | 2026-02-03 | 2026-02-18 | 2026-02-18 | 0 | Met | Dominic Kakar | 177987
ST00680 | PRJ008 | CL002 | Axis Bank | Mumbai Site-095 | Mumbai | West | 50 | ROW In Progress | 2025-12-07 | 2026-01-09 |  | 2026-01-30 |  | 2 | Met | Bhavika Sampath | 244744
ST00681 | PRJ008 | CL002 | Axis Bank | Surat Site-096 | Surat | West | 10 | Live | 2025-12-07 | 2026-01-05 | 2026-01-11 | 2026-01-25 | 2026-01-26 | 6 | Met | Farhan Chada | 160109
ST00682 | PRJ008 | CL002 | Axis Bank | Surat Site-097 | Surat | West | 200 | Live | 2025-12-04 | 2026-01-08 | 2026-01-18 | 2026-01-28 | 2026-02-03 | 10 | Marginal | Kashvi Edwin | 67343
ST00683 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-098 | Ahmedabad | West | 20 | Installation Done | 2025-12-28 | 2026-02-12 | 2026-02-18 | 2026-03-14 |  | 12 | Marginal | Yashica Cherian | 242448
ST00684 | PRJ008 | CL002 | Axis Bank | Surat Site-099 | Surat | West | 200 | Live | 2025-12-08 | 2026-01-24 | 2026-02-01 | 2026-02-16 | 2026-02-27 | 8 | Marginal | Ranveer Yadav | 52802
ST00685 | PRJ008 | CL002 | Axis Bank | Surat Site-100 | Surat | West | 50 | ROW In Progress | 2025-12-04 | 2026-01-26 |  | 2026-02-07 |  | 1 | Met | Urvashi Ray | 150290
ST00686 | PRJ008 | CL002 | Axis Bank | Pune Site-101 | Pune | West | 10 | Installation Done | 2025-12-16 | 2026-01-07 | 2026-01-06 | 2026-02-04 |  | 12 | Marginal | Ekavir Varkey | 154918
ST00687 | PRJ008 | CL002 | Axis Bank | Surat Site-102 | Surat | West | 10 | Live | 2025-12-26 | 2026-02-19 | 2026-02-23 | 2026-03-11 | 2026-03-19 | 4 | Met | Ekavir Bhargava | 183357
ST00688 | PRJ008 | CL002 | Axis Bank | Pune Site-103 | Pune | West | 20 | Live | 2025-12-18 | 2026-01-20 | 2026-01-29 | 2026-02-10 | 2026-02-19 | 9 | Marginal | Arya Sunder | 67093
ST00689 | PRJ008 | CL002 | Axis Bank | Mumbai Site-104 | Mumbai | West | 10 | Testing | 2025-12-16 | 2026-01-13 | 2026-01-17 | 2026-01-29 |  | 12 | Marginal | Kevin Solanki | 181665
ST00690 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-105 | Ahmedabad | West | 20 | Live | 2025-12-09 | 2025-12-30 | 2025-12-25 | 2026-01-26 | 2026-01-31 | 0 | Met | Arya Sunder | 235450
ST00691 | PRJ008 | CL002 | Axis Bank | Surat Site-106 | Surat | West | 10 | Pending Acceptance | 2025-12-07 | 2025-12-30 | 2026-01-05 | 2026-01-17 | 2026-01-25 | 6 | Met | Simon Tata | 243327
ST00692 | PRJ008 | CL002 | Axis Bank | Mumbai Site-107 | Mumbai | West | 20 | Installation Done | 2025-12-22 | 2026-01-11 | 2026-01-20 | 2026-01-31 |  | 12 | Marginal | Siddharth Zacharia | 136838
ST00693 | PRJ008 | CL002 | Axis Bank | Ahmedabad Site-108 | Ahmedabad | West | 20 | Installation Scheduled | 2025-12-29 | 2026-02-23 | 2026-02-22 | 2026-03-17 |  | 8 | Marginal | Devansh Rajan | 130943
ST00694 | PRJ009 | CL002 | Axis Bank | Nagpur Site-001 | Nagpur | Central | 20 | Installation Done | 2026-02-08 | 2026-03-09 | 2026-03-15 | 2026-04-05 |  | 12 | Marginal | Raksha Varughese | 185911
ST00695 | PRJ009 | CL002 | Axis Bank | Indore Site-002 | Indore | Central | 200 | Pending Acceptance | 2026-01-31 | 2026-03-20 | 2026-03-16 | 2026-03-30 | 2026-04-10 | 0 | Met | Ekavir Varkey | 216195
ST00696 | PRJ009 | CL002 | Axis Bank | Bhopal Site-003 | Bhopal | Central | 100 | Survey Pending | 2026-01-29 | 2026-03-07 |  | 2026-04-05 |  | 4 | Met | Darsh Rau | 265840
ST00697 | PRJ009 | CL002 | Axis Bank | Nagpur Site-004 | Nagpur | Central | 200 | Installation Scheduled | 2026-01-30 | 2026-03-09 | 2026-03-05 | 2026-03-24 |  | 8 | Marginal | Liam Koshy | 123810
ST00698 | PRJ009 | CL002 | Axis Bank | Bhopal Site-005 | Bhopal | Central | 20 | Installation Done | 2026-01-17 | 2026-02-14 | 2026-02-17 | 2026-03-09 |  | 12 | Marginal | Yatin Baral | 255254
ST00699 | PRJ009 | CL002 | Axis Bank | Indore Site-006 | Indore | Central | 20 | Live | 2026-01-24 | 2026-03-25 | 2026-03-28 | 2026-04-18 | 2026-04-23 | 3 | Met | Girindra Chatterjee | 134556
ST00700 | PRJ009 | CL002 | Axis Bank | Bhopal Site-007 | Bhopal | Central | 10 | Installation Done | 2026-02-02 | 2026-03-15 | 2026-03-10 | 2026-03-29 |  | 12 | Marginal | Vansha Thakkar | 46121
ST00701 | PRJ009 | CL002 | Axis Bank | Bhopal Site-008 | Bhopal | Central | 10 | Live | 2026-01-27 | 2026-03-23 | 2026-04-02 | 2026-04-14 | 2026-04-13 | 10 | Marginal | Daksh Karnik | 278982
ST00702 | PRJ009 | CL002 | Axis Bank | Nagpur Site-009 | Nagpur | Central | 50 | Installation Done | 2026-01-17 | 2026-02-28 | 2026-03-07 | 2026-03-29 |  | 12 | Marginal | Faqid Savant | 91448
ST00703 | PRJ009 | CL002 | Axis Bank | Nagpur Site-010 | Nagpur | Central | 10 | Pending Acceptance | 2026-01-17 | 2026-03-07 | 2026-03-13 | 2026-03-23 | 2026-04-03 | 6 | Met | Alka Wable | 239810
ST00704 | PRJ009 | CL002 | Axis Bank | Bhopal Site-011 | Bhopal | Central | 20 | Live | 2026-02-04 | 2026-03-18 | 2026-03-19 | 2026-03-30 | 2026-04-05 | 1 | Met | Siddharth Zacharia | 174448
ST00705 | PRJ009 | CL002 | Axis Bank | Indore Site-012 | Indore | Central | 20 | Survey Pending | 2026-01-29 | 2026-03-28 |  | 2026-04-13 |  | 0 | Met | Chandresh Zachariah | 74083
ST00706 | PRJ009 | CL002 | Axis Bank | Indore Site-013 | Indore | Central | 200 | Testing | 2026-01-29 | 2026-02-28 | 2026-03-01 | 2026-03-28 |  | 12 | Marginal | Ekiya Suresh | 62133
ST00707 | PRJ009 | CL002 | Axis Bank | Nagpur Site-014 | Nagpur | Central | 200 | ROW In Progress | 2026-01-16 | 2026-02-13 |  | 2026-03-03 |  | 3 | Met | Ekavir Bhargava | 95292
ST00708 | PRJ009 | CL002 | Axis Bank | Nagpur Site-015 | Nagpur | Central | 200 | Survey Pending | 2026-02-05 | 2026-03-31 |  | 2026-04-29 |  | 4 | Met | Teerth Bhardwaj | 45512
ST00709 | PRJ009 | CL002 | Axis Bank | Indore Site-016 | Indore | Central | 50 | Live | 2026-02-03 | 2026-02-26 | 2026-03-03 | 2026-03-21 | 2026-03-31 | 5 | Met | Advay Contractor | 223303
ST00710 | PRJ009 | CL002 | Axis Bank | Nagpur Site-017 | Nagpur | Central | 10 | Installation Done | 2026-01-25 | 2026-03-19 | 2026-03-15 | 2026-04-05 |  | 12 | Marginal | Ekavir Bhargava | 155116
ST00711 | PRJ009 | CL002 | Axis Bank | Nagpur Site-018 | Nagpur | Central | 10 | Installation Done | 2026-01-14 | 2026-02-28 | 2026-03-01 | 2026-03-20 |  | 12 | Marginal | Daksh Karnik | 238316
ST00712 | PRJ009 | CL002 | Axis Bank | Bhopal Site-019 | Bhopal | Central | 50 | Pending Acceptance | 2026-01-27 | 2026-02-20 | 2026-02-22 | 2026-03-08 | 2026-03-10 | 2 | Met | Kevin Solanki | 61474
ST00713 | PRJ009 | CL002 | Axis Bank | Nagpur Site-020 | Nagpur | Central | 200 | Testing | 2026-01-14 | 2026-03-05 | 2026-03-13 | 2026-03-15 |  | 12 | Marginal | Irya Sampath | 265334
ST00714 | PRJ009 | CL002 | Axis Bank | Indore Site-021 | Indore | Central | 200 | Installation Scheduled | 2026-01-29 | 2026-03-05 | 2026-03-10 | 2026-03-16 |  | 5 | Met | Devika Rastogi | 64113
ST00715 | PRJ009 | CL002 | Axis Bank | Nagpur Site-022 | Nagpur | Central | 10 | Testing | 2026-02-07 | 2026-03-05 | 2026-03-14 | 2026-04-02 |  | 12 | Marginal | Theodore Devi | 60908
ST00716 | PRJ009 | CL002 | Axis Bank | Bhopal Site-023 | Bhopal | Central | 100 | Installation Done | 2026-02-05 | 2026-03-01 | 2026-02-28 | 2026-03-12 |  | 12 | Marginal | Tara Dhar | 124028
ST00717 | PRJ009 | CL002 | Axis Bank | Nagpur Site-024 | Nagpur | Central | 10 | Testing | 2026-01-16 | 2026-02-11 | 2026-02-07 | 2026-03-10 |  | 12 | Marginal | Ekavir Varkey | 267803
ST00718 | PRJ009 | CL002 | Axis Bank | Indore Site-025 | Indore | Central | 200 | Installation Done | 2026-02-02 | 2026-03-20 | 2026-03-22 | 2026-04-18 |  | 12 | Marginal | Nihal Shere | 163859
ST00719 | PRJ009 | CL002 | Axis Bank | Indore Site-026 | Indore | Central | 10 | Installation Done | 2026-01-27 | 2026-03-27 | 2026-03-25 | 2026-04-16 |  | 12 | Marginal | Teerth Bhardwaj | 180584
ST00720 | PRJ009 | CL002 | Axis Bank | Indore Site-027 | Indore | Central | 10 | Testing | 2026-01-17 | 2026-02-12 | 2026-02-07 | 2026-03-13 |  | 12 | Marginal | Wriddhish Bhardwaj | 195264
ST00721 | PRJ009 | CL002 | Axis Bank | Bhopal Site-028 | Bhopal | Central | 20 | Live | 2026-01-22 | 2026-03-05 | 2026-03-13 | 2026-03-30 | 2026-04-10 | 8 | Marginal | Raksha Varughese | 81090
ST00722 | PRJ009 | CL002 | Axis Bank | Bhopal Site-029 | Bhopal | Central | 50 | Survey Pending | 2026-01-23 | 2026-03-21 |  | 2026-04-13 |  | 8 | Marginal | Kevin Solanki | 198004
ST00723 | PRJ009 | CL002 | Axis Bank | Nagpur Site-030 | Nagpur | Central | 50 | Live | 2026-01-18 | 2026-03-09 | 2026-03-13 | 2026-04-07 | 2026-04-14 | 4 | Met | Logan Sami | 47118
ST00724 | PRJ009 | CL002 | Axis Bank | Nagpur Site-031 | Nagpur | Central | 200 | Testing | 2026-02-04 | 2026-03-05 | 2026-03-01 | 2026-03-22 |  | 12 | Marginal | Simon Tata | 155640
ST00725 | PRJ009 | CL002 | Axis Bank | Indore Site-032 | Indore | Central | 50 | ROW In Progress | 2026-01-20 | 2026-03-21 |  | 2026-04-06 |  | 1 | Met | Wriddhish Bhardwaj | 220075
ST00726 | PRJ009 | CL002 | Axis Bank | Indore Site-033 | Indore | Central | 200 | Live | 2026-01-28 | 2026-03-27 | 2026-04-01 | 2026-04-24 | 2026-05-01 | 5 | Met | Arya Sunder | 154758
ST00727 | PRJ009 | CL002 | Axis Bank | Indore Site-034 | Indore | Central | 10 | ROW In Progress | 2026-01-28 | 2026-02-19 |  | 2026-03-16 |  | 3 | Met | Alka Wable | 226723
ST00728 | PRJ009 | CL002 | Axis Bank | Bhopal Site-035 | Bhopal | Central | 100 | Installation Done | 2026-01-20 | 2026-02-24 | 2026-03-06 | 2026-03-16 |  | 12 | Marginal | Ekapad Walia | 149939
ST00729 | PRJ009 | CL002 | Axis Bank | Bhopal Site-036 | Bhopal | Central | 10 | Live | 2026-01-14 | 2026-02-26 | 2026-02-21 | 2026-03-10 | 2026-03-18 | 0 | Met | Upadhriti Wadhwa | 82329
ST00730 | PRJ009 | CL002 | Axis Bank | Indore Site-037 | Indore | Central | 10 | Installation Done | 2026-02-03 | 2026-04-01 | 2026-04-07 | 2026-04-12 |  | 12 | Marginal | Farhan Chada | 96858
ST00731 | PRJ009 | CL002 | Axis Bank | Indore Site-038 | Indore | Central | 20 | ROW In Progress | 2026-01-22 | 2026-02-22 |  | 2026-03-14 |  | 8 | Marginal | Ekiya Suresh | 96376
ST00732 | PRJ009 | CL002 | Axis Bank | Bhopal Site-039 | Bhopal | Central | 100 | ROW In Progress | 2026-01-22 | 2026-02-17 |  | 2026-02-27 |  | 2 | Met | Upadhriti Wadhwa | 133705
ST00733 | PRJ009 | CL002 | Axis Bank | Bhopal Site-040 | Bhopal | Central | 200 | Installation Scheduled | 2026-01-21 | 2026-03-05 | 2026-03-11 | 2026-03-20 |  | 8 | Marginal | Madhavi Lanka | 275264
ST00734 | PRJ009 | CL002 | Axis Bank | Nagpur Site-041 | Nagpur | Central | 200 | Survey Pending | 2026-01-18 | 2026-02-15 |  | 2026-03-03 |  | 3 | Met | Arya Shere | 227020
ST00735 | PRJ009 | CL002 | Axis Bank | Indore Site-042 | Indore | Central | 200 | Installation Scheduled | 2026-01-27 | 2026-03-28 | 2026-03-30 | 2026-04-08 |  | 3 | Met | Ekavir Varkey | 251985
ST00736 | PRJ009 | CL002 | Axis Bank | Bhopal Site-043 | Bhopal | Central | 200 | Installation Scheduled | 2026-01-15 | 2026-03-16 | 2026-03-19 | 2026-03-30 |  | 8 | Marginal | Quincy Biswas | 99850
ST00737 | PRJ009 | CL002 | Axis Bank | Nagpur Site-044 | Nagpur | Central | 200 | ROW In Progress | 2026-01-29 | 2026-03-29 |  | 2026-04-10 |  | 2 | Met | Faqid Savant | 241950
ST00738 | PRJ009 | CL002 | Axis Bank | Nagpur Site-045 | Nagpur | Central | 50 | Live | 2026-01-25 | 2026-03-17 | 2026-03-26 | 2026-04-01 | 2026-04-08 | 9 | Marginal | Dakshesh Trivedi | 232603
ST00739 | PRJ009 | CL002 | Axis Bank | Indore Site-046 | Indore | Central | 20 | Installation Done | 2026-02-01 | 2026-03-18 | 2026-03-14 | 2026-04-03 |  | 12 | Marginal | Farhan Chada | 163510
ST00740 | PRJ009 | CL002 | Axis Bank | Bhopal Site-047 | Bhopal | Central | 20 | Installation Done | 2026-01-23 | 2026-03-11 | 2026-03-18 | 2026-04-08 |  | 12 | Marginal | Logan Sami | 111723
ST00741 | PRJ009 | CL002 | Axis Bank | Nagpur Site-048 | Nagpur | Central | 200 | ROW In Progress | 2026-02-07 | 2026-03-04 |  | 2026-03-23 |  | 7 | Met | Ikbal Kothari | 105339
ST00742 | PRJ009 | CL002 | Axis Bank | Nagpur Site-049 | Nagpur | Central | 100 | Survey Pending | 2026-01-30 | 2026-03-30 |  | 2026-04-19 |  | 6 | Met | Dipta Bhandari | 158378
ST00743 | PRJ009 | CL002 | Axis Bank | Indore Site-050 | Indore | Central | 10 | Installation Done | 2026-01-29 | 2026-03-10 | 2026-03-13 | 2026-04-01 |  | 12 | Marginal | Ekiya Suresh | 160785
ST00744 | PRJ009 | CL002 | Axis Bank | Bhopal Site-051 | Bhopal | Central | 200 | Installation Scheduled | 2026-01-16 | 2026-02-27 | 2026-02-24 | 2026-03-18 |  | 8 | Marginal | Theodore Devi | 251011
ST00745 | PRJ009 | CL002 | Axis Bank | Indore Site-052 | Indore | Central | 200 | Pending Acceptance | 2026-01-17 | 2026-02-13 | 2026-02-10 | 2026-03-06 | 2026-03-04 | 0 | Met | Farhan Chada | 132492
ST00746 | PRJ009 | CL002 | Axis Bank | Bhopal Site-053 | Bhopal | Central | 200 | Live | 2026-01-22 | 2026-03-02 | 2026-03-05 | 2026-03-18 | 2026-03-19 | 3 | Met | Devansh Nigam | 47237
ST00747 | PRJ009 | CL002 | Axis Bank | Indore Site-054 | Indore | Central | 100 | Installation Scheduled | 2026-01-25 | 2026-03-11 | 2026-03-18 | 2026-04-08 |  | 0 | Met | Yashica Cherian | 271876
ST00748 | PRJ009 | CL002 | Axis Bank | Indore Site-055 | Indore | Central | 200 | Installation Scheduled | 2026-02-06 | 2026-03-11 | 2026-03-21 | 2026-03-28 |  | 8 | Marginal | Dipta Bhandari | 234401
ST00749 | PRJ009 | CL002 | Axis Bank | Indore Site-056 | Indore | Central | 20 | Installation Scheduled | 2026-01-16 | 2026-02-25 | 2026-02-26 | 2026-03-20 |  | 6 | Met | Bhavika Sampath | 162957
ST00750 | PRJ009 | CL002 | Axis Bank | Nagpur Site-057 | Nagpur | Central | 10 | Survey Pending | 2026-01-18 | 2026-03-15 |  | 2026-03-29 |  | 4 | Met | Wahab Raval | 257441
ST00751 | PRJ009 | CL002 | Axis Bank | Nagpur Site-058 | Nagpur | Central | 200 | Live | 2026-01-24 | 2026-02-27 | 2026-03-07 | 2026-03-22 | 2026-03-31 | 8 | Marginal | Arya Sunder | 130479
ST00752 | PRJ009 | CL002 | Axis Bank | Nagpur Site-059 | Nagpur | Central | 50 | Survey Pending | 2026-02-08 | 2026-03-02 |  | 2026-03-16 |  | 2 | Met | Chandresh Zachariah | 144960
ST00753 | PRJ009 | CL002 | Axis Bank | Bhopal Site-060 | Bhopal | Central | 10 | Pending Acceptance | 2026-01-16 | 2026-03-11 | 2026-03-18 | 2026-03-27 | 2026-04-08 | 7 | Met | Irya Sampath | 194294
ST00754 | PRJ009 | CL002 | Axis Bank | Indore Site-061 | Indore | Central | 10 | Live | 2026-01-23 | 2026-02-17 | 2026-02-17 | 2026-03-02 | 2026-03-04 | 0 | Met | Quincy Biswas | 52035
ST00755 | PRJ009 | CL002 | Axis Bank | Bhopal Site-062 | Bhopal | Central | 50 | ROW In Progress | 2026-01-26 | 2026-03-05 |  | 2026-03-21 |  | 3 | Met | Liam Koshy | 164187
ST00756 | PRJ009 | CL002 | Axis Bank | Bhopal Site-063 | Bhopal | Central | 100 | Installation Done | 2026-01-14 | 2026-02-13 | 2026-02-18 | 2026-03-08 |  | 12 | Marginal | Yashica Issac | 74030
ST00757 | PRJ009 | CL002 | Axis Bank | Bhopal Site-064 | Bhopal | Central | 20 | Testing | 2026-01-29 | 2026-02-22 | 2026-03-01 | 2026-03-10 |  | 12 | Marginal | Ekapad Walia | 126200
ST00758 | PRJ009 | CL002 | Axis Bank | Indore Site-065 | Indore | Central | 200 | Live | 2026-02-04 | 2026-03-26 | 2026-03-26 | 2026-04-24 | 2026-04-30 | 0 | Met | Farhan Chada | 176720
ST00759 | PRJ009 | CL002 | Axis Bank | Nagpur Site-066 | Nagpur | Central | 10 | Live | 2026-01-22 | 2026-02-23 | 2026-02-18 | 2026-03-09 | 2026-03-20 | 0 | Met | Girik Khalsa | 203557
ST00760 | PRJ009 | CL002 | Axis Bank | Bhopal Site-067 | Bhopal | Central | 200 | Installation Done | 2026-02-01 | 2026-03-24 | 2026-04-02 | 2026-04-17 |  | 12 | Marginal | Dominic Kakar | 238276
ST00761 | PRJ009 | CL002 | Axis Bank | Bhopal Site-068 | Bhopal | Central | 100 | Installation Scheduled | 2026-01-28 | 2026-03-11 | 2026-03-15 | 2026-04-02 |  | 2 | Met | Raksha Varughese | 92075
ST00762 | PRJ009 | CL002 | Axis Bank | Nagpur Site-069 | Nagpur | Central | 100 | Live | 2026-01-28 | 2026-03-13 | 2026-03-13 | 2026-04-10 | 2026-04-10 | 0 | Met | Dominic Kakar | 107834
ST00763 | PRJ009 | CL002 | Axis Bank | Bhopal Site-070 | Bhopal | Central | 100 | Installation Scheduled | 2026-02-03 | 2026-03-29 | 2026-04-02 | 2026-04-10 |  | 3 | Met | Niharika Sunder | 244717
ST00764 | PRJ009 | CL002 | Axis Bank | Nagpur Site-071 | Nagpur | Central | 50 | ROW In Progress | 2026-01-25 | 2026-02-18 |  | 2026-03-03 |  | 8 | Marginal | Niharika Sunder | 163210
ST00765 | PRJ009 | CL002 | Axis Bank | Bhopal Site-072 | Bhopal | Central | 100 | Installation Scheduled | 2026-01-30 | 2026-02-21 | 2026-03-02 | 2026-03-03 |  | 1 | Met | Arya Shere | 135087
ST00766 | PRJ009 | CL002 | Axis Bank | Nagpur Site-073 | Nagpur | Central | 50 | Installation Done | 2026-01-20 | 2026-03-06 | 2026-03-02 | 2026-03-16 |  | 12 | Marginal | Upadhriti Wadhwa | 230886
ST00767 | PRJ009 | CL002 | Axis Bank | Bhopal Site-074 | Bhopal | Central | 10 | Installation Scheduled | 2026-02-06 | 2026-03-27 | 2026-04-06 | 2026-04-20 |  | 1 | Met | Raksha Varughese | 232061
ST00768 | PRJ009 | CL002 | Axis Bank | Indore Site-075 | Indore | Central | 200 | ROW In Progress | 2026-01-22 | 2026-02-21 |  | 2026-03-08 |  | 0 | Met | Michael Dutta | 91461
ST00769 | PRJ009 | CL002 | Axis Bank | Indore Site-076 | Indore | Central | 10 | ROW In Progress | 2026-02-06 | 2026-03-23 |  | 2026-04-07 |  | 1 | Met | Victor Kannan | 85238
ST00770 | PRJ009 | CL002 | Axis Bank | Indore Site-077 | Indore | Central | 10 | Installation Done | 2026-01-20 | 2026-02-11 | 2026-02-12 | 2026-03-07 |  | 12 | Marginal | Devansh Rajan | 147398
ST00771 | PRJ009 | CL002 | Axis Bank | Nagpur Site-078 | Nagpur | Central | 20 | Installation Scheduled | 2026-01-15 | 2026-03-14 | 2026-03-09 | 2026-03-25 |  | 6 | Met | Raksha Varughese | 143210
ST00772 | PRJ009 | CL002 | Axis Bank | Bhopal Site-079 | Bhopal | Central | 50 | ROW In Progress | 2026-01-14 | 2026-03-01 |  | 2026-03-11 |  | 0 | Met | Wriddhish Bhardwaj | 223247
ST00773 | PRJ009 | CL002 | Axis Bank | Nagpur Site-080 | Nagpur | Central | 100 | Survey Pending | 2026-01-17 | 2026-02-16 |  | 2026-03-03 |  | 0 | Met | Devansh Rajan | 258811
ST00774 | PRJ009 | CL002 | Axis Bank | Indore Site-081 | Indore | Central | 100 | Installation Scheduled | 2026-02-03 | 2026-03-07 | 2026-03-08 | 2026-04-03 |  | 6 | Met | Advay Contractor | 105924
ST00775 | PRJ009 | CL002 | Axis Bank | Bhopal Site-082 | Bhopal | Central | 50 | ROW In Progress | 2026-01-24 | 2026-02-24 |  | 2026-03-06 |  | 6 | Met | Nihal Shere | 147022
ST00776 | PRJ009 | CL002 | Axis Bank | Bhopal Site-083 | Bhopal | Central | 10 | Installation Done | 2026-01-16 | 2026-02-22 | 2026-02-28 | 2026-03-05 |  | 12 | Marginal | Kabir Soman | 152766
ST00777 | PRJ009 | CL002 | Axis Bank | Indore Site-084 | Indore | Central | 200 | Live | 2026-01-29 | 2026-02-24 | 2026-02-24 | 2026-03-14 | 2026-03-14 | 0 | Met | Girindra Chatterjee | 210379
ST00778 | PRJ009 | CL002 | Axis Bank | Nagpur Site-085 | Nagpur | Central | 50 | Installation Done | 2026-02-07 | 2026-03-07 | 2026-03-12 | 2026-03-22 |  | 12 | Marginal | Dakshesh Trivedi | 62698
ST00779 | PRJ009 | CL002 | Axis Bank | Indore Site-086 | Indore | Central | 20 | Survey Pending | 2026-02-01 | 2026-03-21 |  | 2026-04-12 |  | 8 | Marginal | Yatin Baral | 199001
ST00780 | PRJ010 | CL002 | Axis Bank | Bhopal Site-001 | Bhopal | Central | 20 | Installation Done | 2025-08-08 | 2025-09-25 | 2025-09-26 | 2025-10-10 |  | 12 | Marginal | Tara Dhar | 241585
ST00781 | PRJ010 | CL002 | Axis Bank | Bhopal Site-002 | Bhopal | Central | 20 | Live | 2025-08-11 | 2025-09-16 | 2025-09-24 | 2025-10-10 | 2025-10-10 | 8 | Marginal | Theodore Devi | 121841
ST00782 | PRJ010 | CL002 | Axis Bank | Bhopal Site-003 | Bhopal | Central | 200 | Installation Done | 2025-08-13 | 2025-09-06 | 2025-09-11 | 2025-09-16 |  | 12 | Marginal | Devika Rastogi | 170277
ST00783 | PRJ010 | CL002 | Axis Bank | Indore Site-004 | Indore | Central | 200 | Live | 2025-08-08 | 2025-08-28 | 2025-08-24 | 2025-09-15 | 2025-09-12 | 0 | Met | Dominic Kakar | 70386
ST00784 | PRJ010 | CL002 | Axis Bank | Bhopal Site-005 | Bhopal | Central | 100 | Installation Done | 2025-08-05 | 2025-09-18 | 2025-09-21 | 2025-10-13 |  | 12 | Marginal | Unni Bhagat | 203432
ST00785 | PRJ010 | CL002 | Axis Bank | Indore Site-006 | Indore | Central | 100 | Installation Scheduled | 2025-08-26 | 2025-10-06 | 2025-10-11 | 2025-10-23 |  | 5 | Met | Arya Shere | 205119
ST00786 | PRJ010 | CL002 | Axis Bank | Bhopal Site-007 | Bhopal | Central | 20 | Pending Acceptance | 2025-08-15 | 2025-09-10 | 2025-09-05 | 2025-10-04 | 2025-10-13 | 0 | Met | Daksh Karnik | 202786
ST00787 | PRJ010 | CL002 | Axis Bank | Bhopal Site-008 | Bhopal | Central | 200 | Live | 2025-08-13 | 2025-09-17 | 2025-09-23 | 2025-10-11 | 2025-10-23 | 6 | Met | Niharika Sunder | 218074
ST00788 | PRJ010 | CL002 | Axis Bank | Bhopal Site-009 | Bhopal | Central | 10 | Survey Pending | 2025-08-25 | 2025-10-04 |  | 2025-10-14 |  | 5 | Met | Girindra Chatterjee | 222715
ST00789 | PRJ010 | CL002 | Axis Bank | Indore Site-010 | Indore | Central | 100 | Installation Scheduled | 2025-08-20 | 2025-10-04 | 2025-10-01 | 2025-10-25 |  | 6 | Met | Michael Dutta | 237486
ST00790 | PRJ010 | CL002 | Axis Bank | Indore Site-011 | Indore | Central | 10 | Installation Scheduled | 2025-08-11 | 2025-09-09 | 2025-09-05 | 2025-09-23 |  | 7 | Met | Arya Sunder | 263196
ST00791 | PRJ010 | CL002 | Axis Bank | Nagpur Site-012 | Nagpur | Central | 200 | Pending Acceptance | 2025-08-19 | 2025-09-18 | 2025-09-27 | 2025-10-01 | 2025-10-13 | 9 | Marginal | Devika Rastogi | 108794
ST00792 | PRJ010 | CL002 | Axis Bank | Bhopal Site-013 | Bhopal | Central | 10 | ROW In Progress | 2025-08-26 | 2025-09-20 |  | 2025-10-03 |  | 6 | Met | Yashica Issac | 130590
ST00793 | PRJ010 | CL002 | Axis Bank | Indore Site-014 | Indore | Central | 200 | Live | 2025-08-12 | 2025-09-17 | 2025-09-27 | 2025-09-30 | 2025-10-01 | 10 | Marginal | Quincy Biswas | 68708
ST00794 | PRJ010 | CL002 | Axis Bank | Nagpur Site-015 | Nagpur | Central | 100 | Installation Scheduled | 2025-08-12 | 2025-10-07 | 2025-10-04 | 2025-11-06 |  | 5 | Met | Arya Shere | 216421
ST00795 | PRJ010 | CL002 | Axis Bank | Nagpur Site-016 | Nagpur | Central | 50 | Live | 2025-08-18 | 2025-09-21 | 2025-09-23 | 2025-10-09 | 2025-10-09 | 2 | Met | Gavin Batta | 74198
ST00796 | PRJ010 | CL002 | Axis Bank | Bhopal Site-017 | Bhopal | Central | 20 | Installation Scheduled | 2025-08-23 | 2025-09-24 | 2025-09-22 | 2025-10-22 |  | 5 | Met | Urvashi Ray | 144665
ST00797 | PRJ010 | CL002 | Axis Bank | Nagpur Site-018 | Nagpur | Central | 50 | Live | 2025-08-14 | 2025-09-06 | 2025-09-07 | 2025-09-28 | 2025-10-08 | 1 | Met | Ranveer Yadav | 254064
ST00798 | PRJ010 | CL002 | Axis Bank | Nagpur Site-019 | Nagpur | Central | 10 | Pending Acceptance | 2025-08-09 | 2025-10-01 | 2025-10-03 | 2025-10-14 | 2025-10-23 | 2 | Met | Teerth Bhardwaj | 127818
ST00799 | PRJ010 | CL002 | Axis Bank | Bhopal Site-020 | Bhopal | Central | 200 | Live | 2025-08-14 | 2025-09-17 | 2025-09-27 | 2025-10-11 | 2025-10-12 | 10 | Marginal | Ekansh Balay | 83239
ST00800 | PRJ010 | CL002 | Axis Bank | Nagpur Site-021 | Nagpur | Central | 50 | Live | 2025-08-30 | 2025-09-21 | 2025-09-26 | 2025-10-10 | 2025-10-10 | 5 | Met | Dakshesh Trivedi | 210433
ST00801 | PRJ010 | CL002 | Axis Bank | Bhopal Site-022 | Bhopal | Central | 20 | Installation Done | 2025-08-27 | 2025-10-10 | 2025-10-06 | 2025-10-30 |  | 12 | Marginal | Ekapad Walia | 267316
ST00802 | PRJ010 | CL002 | Axis Bank | Nagpur Site-023 | Nagpur | Central | 50 | Pending Acceptance | 2025-08-12 | 2025-09-04 | 2025-09-04 | 2025-09-29 | 2025-10-08 | 0 | Met | Yashica Issac | 50653
ST00803 | PRJ010 | CL002 | Axis Bank | Nagpur Site-024 | Nagpur | Central | 100 | Installation Done | 2025-08-18 | 2025-10-07 | 2025-10-13 | 2025-10-29 |  | 12 | Marginal | Priya Rastogi | 183371
ST00804 | PRJ010 | CL002 | Axis Bank | Nagpur Site-025 | Nagpur | Central | 50 | Installation Scheduled | 2025-08-27 | 2025-09-28 | 2025-10-05 | 2025-10-11 |  | 2 | Met | Simon Tata | 267772
ST00805 | PRJ010 | CL002 | Axis Bank | Nagpur Site-026 | Nagpur | Central | 50 | Installation Scheduled | 2025-08-25 | 2025-09-24 | 2025-09-23 | 2025-10-18 |  | 7 | Met | Aarush Lall | 99988
ST00806 | PRJ010 | CL002 | Axis Bank | Bhopal Site-027 | Bhopal | Central | 20 | Live | 2025-08-11 | 2025-08-31 | 2025-09-06 | 2025-09-28 | 2025-09-28 | 6 | Met | Arya Shere | 156964
ST00807 | PRJ010 | CL002 | Axis Bank | Nagpur Site-028 | Nagpur | Central | 10 | Live | 2025-08-06 | 2025-09-01 | 2025-09-07 | 2025-09-26 | 2025-09-28 | 6 | Met | Advay Contractor | 180118
ST00808 | PRJ010 | CL002 | Axis Bank | Nagpur Site-029 | Nagpur | Central | 10 | Installation Scheduled | 2025-08-18 | 2025-09-16 | 2025-09-23 | 2025-10-03 |  | 0 | Met | Devika Rastogi | 148978
ST00809 | PRJ010 | CL002 | Axis Bank | Indore Site-030 | Indore | Central | 100 | Installation Scheduled | 2025-08-24 | 2025-09-24 | 2025-10-01 | 2025-10-06 |  | 7 | Met | Ekavir Bhargava | 210762
ST00810 | PRJ010 | CL002 | Axis Bank | Nagpur Site-031 | Nagpur | Central | 10 | Installation Done | 2025-08-05 | 2025-09-01 | 2025-08-30 | 2025-09-13 |  | 12 | Marginal | Quincy Biswas | 213141
ST00811 | PRJ010 | CL002 | Axis Bank | Nagpur Site-032 | Nagpur | Central | 200 | Live | 2025-08-12 | 2025-09-02 | 2025-09-12 | 2025-09-20 | 2025-09-20 | 10 | Marginal | Isaac Patil | 145652
ST00812 | PRJ010 | CL002 | Axis Bank | Indore Site-033 | Indore | Central | 10 | Pending Acceptance | 2025-08-27 | 2025-10-13 | 2025-10-17 | 2025-11-10 | 2025-11-11 | 4 | Met | Girindra Chatterjee | 61645
ST00813 | PRJ010 | CL002 | Axis Bank | Nagpur Site-034 | Nagpur | Central | 100 | Live | 2025-08-30 | 2025-10-23 | 2025-10-23 | 2025-11-14 | 2025-11-11 | 0 | Met | Quincy Biswas | 61759
ST00814 | PRJ010 | CL002 | Axis Bank | Nagpur Site-035 | Nagpur | Central | 200 | Live | 2025-08-22 | 2025-09-18 | 2025-09-19 | 2025-10-01 | 2025-10-03 | 1 | Met | Isaac Patil | 46395
ST00815 | PRJ010 | CL002 | Axis Bank | Nagpur Site-036 | Nagpur | Central | 200 | Installation Done | 2025-08-15 | 2025-09-11 | 2025-09-07 | 2025-09-25 |  | 12 | Marginal | Ekapad Walia | 216085
ST00816 | PRJ010 | CL002 | Axis Bank | Bhopal Site-037 | Bhopal | Central | 200 | ROW In Progress | 2025-08-13 | 2025-09-04 |  | 2025-09-16 |  | 1 | Met | Arya Sunder | 140304
ST00817 | PRJ010 | CL002 | Axis Bank | Nagpur Site-038 | Nagpur | Central | 10 | ROW In Progress | 2025-08-26 | 2025-09-15 |  | 2025-10-02 |  | 4 | Met | Ekavir Varkey | 217794
ST00818 | PRJ010 | CL002 | Axis Bank | Nagpur Site-039 | Nagpur | Central | 50 | Installation Done | 2025-08-23 | 2025-10-13 | 2025-10-18 | 2025-11-08 |  | 12 | Marginal | Ekapad Walia | 225336
ST00819 | PRJ010 | CL002 | Axis Bank | Bhopal Site-040 | Bhopal | Central | 50 | Live | 2025-08-06 | 2025-09-10 | 2025-09-06 | 2025-09-26 | 2025-09-27 | 0 | Met | Kabir Soman | 80181
ST00820 | PRJ010 | CL002 | Axis Bank | Nagpur Site-041 | Nagpur | Central | 200 | Testing | 2025-08-23 | 2025-10-04 | 2025-10-07 | 2025-10-18 |  | 12 | Marginal | Nitesh Raghavan | 64492
ST00821 | PRJ010 | CL002 | Axis Bank | Nagpur Site-042 | Nagpur | Central | 50 | Installation Scheduled | 2025-08-17 | 2025-09-16 | 2025-09-23 | 2025-10-10 |  | 1 | Met | Nitesh Raghavan | 227063
ST00822 | PRJ010 | CL002 | Axis Bank | Bhopal Site-043 | Bhopal | Central | 20 | Testing | 2025-08-07 | 2025-10-06 | 2025-10-09 | 2025-11-05 |  | 12 | Marginal | Logan Sami | 192755
ST00823 | PRJ010 | CL002 | Axis Bank | Nagpur Site-044 | Nagpur | Central | 50 | Live | 2025-08-21 | 2025-10-18 | 2025-10-18 | 2025-11-10 | 2025-11-11 | 0 | Met | Madhavi Lanka | 144337
ST00824 | PRJ010 | CL002 | Axis Bank | Bhopal Site-045 | Bhopal | Central | 200 | Pending Acceptance | 2025-08-12 | 2025-09-05 | 2025-09-08 | 2025-09-18 | 2025-09-18 | 3 | Met | Niharika Sunder | 62290
ST00825 | PRJ010 | CL002 | Axis Bank | Indore Site-046 | Indore | Central | 50 | Live | 2025-08-16 | 2025-09-26 | 2025-09-29 | 2025-10-10 | 2025-10-14 | 3 | Met | Nihal Shere | 70676
ST00826 | PRJ010 | CL002 | Axis Bank | Indore Site-047 | Indore | Central | 200 | Pending Acceptance | 2025-08-12 | 2025-09-25 | 2025-09-23 | 2025-10-08 | 2025-10-10 | 0 | Met | Kevin Solanki | 199357
ST00827 | PRJ010 | CL002 | Axis Bank | Indore Site-048 | Indore | Central | 50 | ROW In Progress | 2025-08-16 | 2025-10-11 |  | 2025-10-30 |  | 8 | Marginal | Michael Dutta | 57573
ST00828 | PRJ010 | CL002 | Axis Bank | Bhopal Site-049 | Bhopal | Central | 200 | Installation Scheduled | 2025-08-29 | 2025-10-12 | 2025-10-12 | 2025-11-02 |  | 8 | Marginal | Girik Khalsa | 170006
ST00829 | PRJ010 | CL002 | Axis Bank | Nagpur Site-050 | Nagpur | Central | 20 | ROW In Progress | 2025-08-05 | 2025-09-26 |  | 2025-10-10 |  | 2 | Met | Arya Shere | 193782
ST00830 | PRJ010 | CL002 | Axis Bank | Nagpur Site-051 | Nagpur | Central | 100 | Installation Scheduled | 2025-08-28 | 2025-10-27 | 2025-11-02 | 2025-11-13 |  | 6 | Met | Isaac Patil | 160070
ST00831 | PRJ010 | CL002 | Axis Bank | Indore Site-052 | Indore | Central | 50 | Live | 2025-08-21 | 2025-09-28 | 2025-10-01 | 2025-10-21 | 2025-10-25 | 3 | Met | Gavin Batta | 125127
ST00832 | PRJ010 | CL002 | Axis Bank | Indore Site-053 | Indore | Central | 10 | Live | 2025-08-07 | 2025-10-06 | 2025-10-03 | 2025-10-18 | 2025-10-22 | 0 | Met | Kashvi Edwin | 195815
ST00833 | PRJ010 | CL002 | Axis Bank | Bhopal Site-054 | Bhopal | Central | 100 | ROW In Progress | 2025-08-14 | 2025-10-08 |  | 2025-11-02 |  | 0 | Met | Radhika Dugar | 170738
ST00834 | PRJ010 | CL002 | Axis Bank | Indore Site-055 | Indore | Central | 10 | Installation Done | 2025-08-26 | 2025-10-19 | 2025-10-17 | 2025-11-10 |  | 12 | Marginal | Wriddhish Bhardwaj | 262945
ST00835 | PRJ010 | CL002 | Axis Bank | Nagpur Site-056 | Nagpur | Central | 200 | Survey Pending | 2025-08-18 | 2025-10-11 |  | 2025-11-01 |  | 3 | Met | Dominic Kakar | 204219
ST00836 | PRJ010 | CL002 | Axis Bank | Indore Site-057 | Indore | Central | 50 | Pending Acceptance | 2025-08-26 | 2025-10-18 | 2025-10-20 | 2025-11-02 | 2025-11-01 | 2 | Met | Radhika Dugar | 179659
ST00837 | PRJ010 | CL002 | Axis Bank | Indore Site-058 | Indore | Central | 10 | Pending Acceptance | 2025-08-18 | 2025-10-08 | 2025-10-15 | 2025-10-23 | 2025-10-31 | 7 | Met | Unni Bhagat | 223012
ST00838 | PRJ010 | CL002 | Axis Bank | Bhopal Site-059 | Bhopal | Central | 50 | Live | 2025-08-29 | 2025-09-25 | 2025-09-29 | 2025-10-14 | 2025-10-26 | 4 | Met | Devansh Nigam | 100853
ST00839 | PRJ010 | CL002 | Axis Bank | Bhopal Site-060 | Bhopal | Central | 100 | Live | 2025-08-23 | 2025-10-07 | 2025-10-08 | 2025-10-26 | 2025-10-24 | 1 | Met | Quincy Biswas | 60072
ST00840 | PRJ010 | CL002 | Axis Bank | Indore Site-061 | Indore | Central | 10 | Survey Pending | 2025-08-19 | 2025-09-29 |  | 2025-10-18 |  | 5 | Met | Ekbal Garg | 136677
ST00841 | PRJ010 | CL002 | Axis Bank | Nagpur Site-062 | Nagpur | Central | 100 | ROW In Progress | 2025-08-16 | 2025-09-05 |  | 2025-09-18 |  | 6 | Met | Farhan Chada | 67215
ST00842 | PRJ010 | CL002 | Axis Bank | Nagpur Site-063 | Nagpur | Central | 10 | Installation Done | 2025-08-09 | 2025-09-24 | 2025-09-22 | 2025-10-19 |  | 12 | Marginal | Yashica Cherian | 246706
ST00843 | PRJ010 | CL002 | Axis Bank | Nagpur Site-064 | Nagpur | Central | 100 | Installation Scheduled | 2025-08-20 | 2025-10-04 | 2025-10-10 | 2025-10-23 |  | 5 | Met | Isaac Patil | 185621
ST00844 | PRJ010 | CL002 | Axis Bank | Indore Site-065 | Indore | Central | 50 | ROW In Progress | 2025-08-19 | 2025-10-06 |  | 2025-10-21 |  | 2 | Met | Madhavi Lanka | 46523
ST00845 | PRJ010 | CL002 | Axis Bank | Indore Site-066 | Indore | Central | 10 | Live | 2025-08-27 | 2025-09-28 | 2025-09-26 | 2025-10-14 | 2025-10-20 | 0 | Met | Radhika Dugar | 148427
ST00846 | PRJ010 | CL002 | Axis Bank | Indore Site-067 | Indore | Central | 10 | Live | 2025-08-06 | 2025-09-05 | 2025-09-06 | 2025-09-30 | 2025-10-05 | 1 | Met | Tanay Rattan | 173206
ST00847 | PRJ010 | CL002 | Axis Bank | Nagpur Site-068 | Nagpur | Central | 200 | Installation Done | 2025-08-26 | 2025-09-23 | 2025-09-28 | 2025-10-15 |  | 12 | Marginal | Faqid Savant | 79450
ST00848 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-001 | Ahmedabad | West | 50 | Installation Scheduled | 2026-03-07 | 2026-05-06 | 2026-05-01 | 2026-05-27 |  | 3 | Met | Ekiya Suresh | 112105
ST00849 | PRJ011 | CL002 | Axis Bank | Mumbai Site-002 | Mumbai | West | 50 | Testing | 2026-03-30 | 2026-05-26 | 2026-05-24 | 2026-06-17 |  | 12 | Marginal | Ekapad Walia | 259131
ST00850 | PRJ011 | CL002 | Axis Bank | Surat Site-003 | Surat | West | 20 | Installation Scheduled | 2026-03-14 | 2026-04-16 | 2026-04-23 | 2026-04-30 |  | 7 | Met | Madhavi Lanka | 141636
ST00851 | PRJ011 | CL002 | Axis Bank | Pune Site-004 | Pune | West | 20 | Live | 2026-03-08 | 2026-04-28 | 2026-04-28 | 2026-05-22 | 2026-05-24 | 0 | Met | Wriddhish Bhardwaj | 194332
ST00852 | PRJ011 | CL002 | Axis Bank | Surat Site-005 | Surat | West | 20 | Pending Acceptance | 2026-03-11 | 2026-04-18 | 2026-04-13 | 2026-05-07 | 2026-05-09 | 0 | Met | Chandresh Zachariah | 225189
ST00853 | PRJ011 | CL002 | Axis Bank | Pune Site-006 | Pune | West | 100 | Survey Pending | 2026-03-08 | 2026-04-24 |  | 2026-05-11 |  | 7 | Met | Michael Dutta | 234872
ST00854 | PRJ011 | CL002 | Axis Bank | Pune Site-007 | Pune | West | 10 | Live | 2026-03-31 | 2026-04-20 | 2026-04-18 | 2026-05-12 | 2026-05-21 | 0 | Met | Upadhriti Wadhwa | 261678
ST00855 | PRJ011 | CL002 | Axis Bank | Mumbai Site-008 | Mumbai | West | 50 | Live | 2026-03-26 | 2026-04-17 | 2026-04-16 | 2026-05-04 | 2026-05-03 | 0 | Met | Aarush Lall | 209465
ST00856 | PRJ011 | CL002 | Axis Bank | Mumbai Site-009 | Mumbai | West | 20 | Live | 2026-03-06 | 2026-04-01 | 2026-04-06 | 2026-04-13 | 2026-04-16 | 5 | Met | Dakshesh Trivedi | 244143
ST00857 | PRJ011 | CL002 | Axis Bank | Surat Site-010 | Surat | West | 10 | Live | 2026-03-15 | 2026-04-25 | 2026-05-05 | 2026-05-09 | 2026-05-13 | 10 | Marginal | Victor Kannan | 209491
ST00858 | PRJ011 | CL002 | Axis Bank | Mumbai Site-011 | Mumbai | West | 10 | Survey Pending | 2026-03-07 | 2026-04-02 |  | 2026-04-29 |  | 4 | Met | Tanay Rattan | 82181
ST00859 | PRJ011 | CL002 | Axis Bank | Mumbai Site-012 | Mumbai | West | 50 | Pending Acceptance | 2026-03-06 | 2026-04-09 | 2026-04-17 | 2026-05-01 | 2026-05-02 | 8 | Marginal | Ekansh Balay | 104214
ST00860 | PRJ011 | CL002 | Axis Bank | Surat Site-013 | Surat | West | 20 | Live | 2026-03-28 | 2026-04-24 | 2026-05-04 | 2026-05-09 | 2026-05-09 | 10 | Marginal | Devansh Rajan | 118875
ST00861 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-014 | Ahmedabad | West | 10 | Survey Pending | 2026-03-16 | 2026-04-12 |  | 2026-05-03 |  | 1 | Met | Yashica Cherian | 91679
ST00862 | PRJ011 | CL002 | Axis Bank | Surat Site-015 | Surat | West | 50 | Testing | 2026-03-25 | 2026-04-25 | 2026-05-03 | 2026-05-09 |  | 12 | Marginal | Ekansh Balay | 136327
ST00863 | PRJ011 | CL002 | Axis Bank | Mumbai Site-016 | Mumbai | West | 20 | Installation Scheduled | 2026-03-21 | 2026-05-03 | 2026-05-06 | 2026-05-15 |  | 0 | Met | Aarush Lall | 128953
ST00864 | PRJ011 | CL002 | Axis Bank | Pune Site-017 | Pune | West | 200 | Installation Done | 2026-03-29 | 2026-05-18 | 2026-05-15 | 2026-05-31 |  | 12 | Marginal | Nitesh Raghavan | 235502
ST00865 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-018 | Ahmedabad | West | 50 | ROW In Progress | 2026-03-16 | 2026-04-13 |  | 2026-04-28 |  | 6 | Met | Urvashi Ray | 174553
ST00866 | PRJ011 | CL002 | Axis Bank | Surat Site-019 | Surat | West | 20 | Installation Done | 2026-03-19 | 2026-05-16 | 2026-05-21 | 2026-05-30 |  | 12 | Marginal | Faqid Savant | 154749
ST00867 | PRJ011 | CL002 | Axis Bank | Surat Site-020 | Surat | West | 10 | Testing | 2026-03-21 | 2026-05-14 | 2026-05-16 | 2026-06-05 |  | 12 | Marginal | Tanay Rattan | 183135
ST00868 | PRJ011 | CL002 | Axis Bank | Pune Site-021 | Pune | West | 50 | Live | 2026-03-13 | 2026-04-25 | 2026-04-20 | 2026-05-11 | 2026-05-08 | 0 | Met | Vansha Thakkar | 80020
ST00869 | PRJ011 | CL002 | Axis Bank | Mumbai Site-022 | Mumbai | West | 100 | Survey Pending | 2026-03-17 | 2026-04-29 |  | 2026-05-13 |  | 4 | Met | Aarush Lall | 263956
ST00870 | PRJ011 | CL002 | Axis Bank | Surat Site-023 | Surat | West | 100 | Installation Scheduled | 2026-03-13 | 2026-04-05 | 2026-04-04 | 2026-04-18 |  | 2 | Met | Daksh Karnik | 227484
ST00871 | PRJ011 | CL002 | Axis Bank | Surat Site-024 | Surat | West | 200 | Installation Done | 2026-03-28 | 2026-04-23 | 2026-04-20 | 2026-05-18 |  | 12 | Marginal | Yashica Issac | 52913
ST00872 | PRJ011 | CL002 | Axis Bank | Pune Site-025 | Pune | West | 200 | Installation Done | 2026-03-08 | 2026-04-12 | 2026-04-09 | 2026-04-22 |  | 12 | Marginal | Tanay Rattan | 84247
ST00873 | PRJ011 | CL002 | Axis Bank | Pune Site-026 | Pune | West | 100 | Installation Done | 2026-03-10 | 2026-05-02 | 2026-05-06 | 2026-05-27 |  | 12 | Marginal | Unni Bhagat | 161385
ST00874 | PRJ011 | CL002 | Axis Bank | Mumbai Site-027 | Mumbai | West | 200 | Installation Scheduled | 2026-03-10 | 2026-04-02 | 2026-03-29 | 2026-05-01 |  | 2 | Met | Yashica Issac | 47848
ST00875 | PRJ011 | CL002 | Axis Bank | Surat Site-028 | Surat | West | 20 | Live | 2026-03-27 | 2026-05-15 | 2026-05-18 | 2026-06-12 | 2026-06-18 | 3 | Met | Nitesh Raghavan | 86104
ST00876 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-029 | Ahmedabad | West | 200 | Pending Acceptance | 2026-03-22 | 2026-05-05 | 2026-05-04 | 2026-05-21 | 2026-05-30 | 0 | Met | Tara Dhar | 102385
ST00877 | PRJ011 | CL002 | Axis Bank | Surat Site-030 | Surat | West | 100 | ROW In Progress | 2026-03-29 | 2026-05-23 |  | 2026-06-21 |  | 1 | Met | Dakshesh Trivedi | 127100
ST00878 | PRJ011 | CL002 | Axis Bank | Surat Site-031 | Surat | West | 20 | Live | 2026-03-11 | 2026-04-03 | 2026-04-09 | 2026-05-03 | 2026-05-13 | 6 | Met | Victor Kannan | 73416
ST00879 | PRJ011 | CL002 | Axis Bank | Mumbai Site-032 | Mumbai | West | 50 | Survey Pending | 2026-03-25 | 2026-05-05 |  | 2026-05-15 |  | 3 | Met | Yashica Issac | 186968
ST00880 | PRJ011 | CL002 | Axis Bank | Mumbai Site-033 | Mumbai | West | 200 | Survey Pending | 2026-03-25 | 2026-04-14 |  | 2026-05-03 |  | 3 | Met | Farhan Chada | 212349
ST00881 | PRJ011 | CL002 | Axis Bank | Mumbai Site-034 | Mumbai | West | 10 | Installation Scheduled | 2026-03-08 | 2026-05-03 | 2026-04-29 | 2026-05-31 |  | 7 | Met | Simon Tata | 127465
ST00882 | PRJ011 | CL002 | Axis Bank | Mumbai Site-035 | Mumbai | West | 50 | Pending Acceptance | 2026-03-06 | 2026-04-17 | 2026-04-21 | 2026-05-09 | 2026-05-12 | 4 | Met | Chandresh Zachariah | 235234
ST00883 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-036 | Ahmedabad | West | 200 | Pending Acceptance | 2026-03-28 | 2026-04-23 | 2026-04-28 | 2026-05-16 | 2026-05-16 | 5 | Met | Yashica Cherian | 51208
ST00884 | PRJ011 | CL002 | Axis Bank | Surat Site-037 | Surat | West | 100 | Installation Done | 2026-03-07 | 2026-04-14 | 2026-04-14 | 2026-04-28 |  | 12 | Marginal | Theodore Devi | 277050
ST00885 | PRJ011 | CL002 | Axis Bank | Mumbai Site-038 | Mumbai | West | 100 | Pending Acceptance | 2026-03-13 | 2026-04-15 | 2026-04-14 | 2026-04-30 | 2026-05-07 | 0 | Met | Harini Choudhury | 133872
ST00886 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-039 | Ahmedabad | West | 20 | Installation Done | 2026-03-19 | 2026-04-10 | 2026-04-17 | 2026-04-27 |  | 12 | Marginal | Priya Rastogi | 84951
ST00887 | PRJ011 | CL002 | Axis Bank | Surat Site-040 | Surat | West | 10 | ROW In Progress | 2026-03-06 | 2026-04-04 |  | 2026-04-23 |  | 8 | Marginal | Wahab Raval | 69671
ST00888 | PRJ011 | CL002 | Axis Bank | Surat Site-041 | Surat | West | 50 | Installation Scheduled | 2026-03-15 | 2026-04-14 | 2026-04-11 | 2026-05-02 |  | 5 | Met | Gavin Batta | 63647
ST00889 | PRJ011 | CL002 | Axis Bank | Pune Site-042 | Pune | West | 20 | Live | 2026-03-20 | 2026-04-25 | 2026-05-05 | 2026-05-13 | 2026-05-24 | 10 | Marginal | Advay Contractor | 194090
ST00890 | PRJ011 | CL002 | Axis Bank | Surat Site-043 | Surat | West | 100 | Survey Pending | 2026-03-15 | 2026-04-29 |  | 2026-05-22 |  | 2 | Met | Ranveer Yadav | 179343
ST00891 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-044 | Ahmedabad | West | 10 | Installation Done | 2026-03-27 | 2026-05-12 | 2026-05-21 | 2026-05-30 |  | 12 | Marginal | Tara Dhar | 239259
ST00892 | PRJ011 | CL002 | Axis Bank | Pune Site-045 | Pune | West | 100 | Live | 2026-03-23 | 2026-04-12 | 2026-04-11 | 2026-04-25 | 2026-05-01 | 0 | Met | Yashica Issac | 194457
ST00893 | PRJ011 | CL002 | Axis Bank | Surat Site-046 | Surat | West | 100 | Live | 2026-03-13 | 2026-04-26 | 2026-05-05 | 2026-05-08 | 2026-05-16 | 9 | Marginal | Dipta Bhandari | 213423
ST00894 | PRJ011 | CL002 | Axis Bank | Surat Site-047 | Surat | West | 20 | ROW In Progress | 2026-03-11 | 2026-04-06 |  | 2026-04-28 |  | 6 | Met | Girik Khalsa | 131172
ST00895 | PRJ011 | CL002 | Axis Bank | Mumbai Site-048 | Mumbai | West | 50 | Installation Scheduled | 2026-03-25 | 2026-05-15 | 2026-05-16 | 2026-06-09 |  | 1 | Met | Teerth Bhardwaj | 55035
ST00896 | PRJ011 | CL002 | Axis Bank | Pune Site-049 | Pune | West | 200 | Pending Acceptance | 2026-03-10 | 2026-05-09 | 2026-05-10 | 2026-05-29 | 2026-05-27 | 1 | Met | Arya Shere | 61357
ST00897 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-050 | Ahmedabad | West | 100 | Live | 2026-03-21 | 2026-04-23 | 2026-04-19 | 2026-05-09 | 2026-05-06 | 0 | Met | Victor Kannan | 111078
ST00898 | PRJ011 | CL002 | Axis Bank | Pune Site-051 | Pune | West | 50 | ROW In Progress | 2026-03-08 | 2026-04-14 |  | 2026-05-06 |  | 1 | Met | Mohammed Gupta | 273403
ST00899 | PRJ011 | CL002 | Axis Bank | Surat Site-052 | Surat | West | 10 | Installation Done | 2026-03-27 | 2026-05-02 | 2026-05-02 | 2026-05-13 |  | 12 | Marginal | Nitesh Raghavan | 134658
ST00900 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-053 | Ahmedabad | West | 200 | ROW In Progress | 2026-03-17 | 2026-05-02 |  | 2026-05-27 |  | 7 | Met | Yashica Issac | 227633
ST00901 | PRJ011 | CL002 | Axis Bank | Surat Site-054 | Surat | West | 200 | Installation Done | 2026-03-28 | 2026-05-23 | 2026-05-30 | 2026-06-02 |  | 12 | Marginal | Farhan Chada | 65397
ST00902 | PRJ011 | CL002 | Axis Bank | Pune Site-055 | Pune | West | 20 | Installation Scheduled | 2026-03-29 | 2026-05-08 | 2026-05-03 | 2026-05-22 |  | 7 | Met | Wahab Raval | 271571
ST00903 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-056 | Ahmedabad | West | 10 | ROW In Progress | 2026-03-27 | 2026-05-12 |  | 2026-05-30 |  | 8 | Marginal | Mohammed Gupta | 263237
ST00904 | PRJ011 | CL002 | Axis Bank | Pune Site-057 | Pune | West | 20 | Live | 2026-03-26 | 2026-05-22 | 2026-05-20 | 2026-06-02 | 2026-06-05 | 0 | Met | Tanay Rattan | 227569
ST00905 | PRJ011 | CL002 | Axis Bank | Pune Site-058 | Pune | West | 200 | Testing | 2026-03-12 | 2026-04-23 | 2026-04-24 | 2026-05-09 |  | 12 | Marginal | Nihal Shere | 142060
ST00906 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-059 | Ahmedabad | West | 100 | Survey Pending | 2026-03-15 | 2026-05-06 |  | 2026-05-19 |  | 7 | Met | Niharika Sunder | 152580
ST00907 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-060 | Ahmedabad | West | 20 | Installation Done | 2026-03-23 | 2026-05-09 | 2026-05-14 | 2026-05-22 |  | 12 | Marginal | Teerth Bhardwaj | 157298
ST00908 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-061 | Ahmedabad | West | 100 | ROW In Progress | 2026-03-25 | 2026-04-24 |  | 2026-05-21 |  | 6 | Met | Ekansh Balay | 266535
ST00909 | PRJ011 | CL002 | Axis Bank | Surat Site-062 | Surat | West | 10 | Live | 2026-03-28 | 2026-05-26 | 2026-05-24 | 2026-06-07 | 2026-06-07 | 0 | Met | Anamika Kanda | 206548
ST00910 | PRJ011 | CL002 | Axis Bank | Surat Site-063 | Surat | West | 100 | ROW In Progress | 2026-03-29 | 2026-05-27 |  | 2026-06-23 |  | 1 | Met | Yatin Baral | 197366
ST00911 | PRJ011 | CL002 | Axis Bank | Mumbai Site-064 | Mumbai | West | 10 | Live | 2026-03-19 | 2026-04-21 | 2026-04-23 | 2026-05-15 | 2026-05-24 | 2 | Met | Farhan Chada | 269485
ST00912 | PRJ011 | CL002 | Axis Bank | Surat Site-065 | Surat | West | 10 | Pending Acceptance | 2026-03-17 | 2026-05-05 | 2026-05-13 | 2026-06-04 | 2026-06-13 | 8 | Marginal | Logan Sami | 250048
ST00913 | PRJ011 | CL002 | Axis Bank | Pune Site-066 | Pune | West | 20 | Installation Done | 2026-03-14 | 2026-04-19 | 2026-04-23 | 2026-05-12 |  | 12 | Marginal | Ekbal Garg | 153673
ST00914 | PRJ011 | CL002 | Axis Bank | Mumbai Site-067 | Mumbai | West | 50 | Survey Pending | 2026-03-10 | 2026-04-22 |  | 2026-05-18 |  | 5 | Met | Kashvi Edwin | 194995
ST00915 | PRJ011 | CL002 | Axis Bank | Surat Site-068 | Surat | West | 20 | Installation Scheduled | 2026-03-18 | 2026-04-19 | 2026-04-26 | 2026-04-30 |  | 6 | Met | Faqid Savant | 235870
ST00916 | PRJ011 | CL002 | Axis Bank | Pune Site-069 | Pune | West | 20 | Installation Done | 2026-03-16 | 2026-05-08 | 2026-05-08 | 2026-05-31 |  | 12 | Marginal | Michael Dutta | 231128
ST00917 | PRJ011 | CL002 | Axis Bank | Pune Site-070 | Pune | West | 50 | Installation Done | 2026-03-26 | 2026-05-21 | 2026-05-28 | 2026-06-20 |  | 12 | Marginal | Yashica Issac | 129516
ST00918 | PRJ011 | CL002 | Axis Bank | Pune Site-071 | Pune | West | 10 | ROW In Progress | 2026-03-06 | 2026-04-22 |  | 2026-05-02 |  | 2 | Met | Theodore Devi | 194892
ST00919 | PRJ011 | CL002 | Axis Bank | Surat Site-072 | Surat | West | 20 | Survey Pending | 2026-03-29 | 2026-04-26 |  | 2026-05-20 |  | 5 | Met | Devika Rastogi | 216054
ST00920 | PRJ011 | CL002 | Axis Bank | Pune Site-073 | Pune | West | 50 | Installation Scheduled | 2026-03-23 | 2026-04-27 | 2026-05-04 | 2026-05-15 |  | 0 | Met | Theodore Devi | 82688
ST00921 | PRJ011 | CL002 | Axis Bank | Mumbai Site-074 | Mumbai | West | 10 | Live | 2026-03-24 | 2026-04-19 | 2026-04-17 | 2026-05-13 | 2026-05-13 | 0 | Met | Aarush Lall | 119045
ST00922 | PRJ011 | CL002 | Axis Bank | Ahmedabad Site-075 | Ahmedabad | West | 100 | Live | 2026-03-08 | 2026-04-01 | 2026-04-11 | 2026-04-22 | 2026-04-25 | 10 | Marginal | Michael Dutta | 173722
ST00923 | PRJ011 | CL002 | Axis Bank | Mumbai Site-076 | Mumbai | West | 100 | Installation Done | 2026-03-21 | 2026-05-20 | 2026-05-17 | 2026-06-05 |  | 12 | Marginal | Arya Shere | 278233
ST00924 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-001 | Hyderabad | South | 200 | Installation Scheduled | 2025-06-23 | 2025-08-06 | 2025-08-09 | 2025-08-21 |  | 2 | Met | Teerth Bhardwaj | 76431
ST00925 | PRJ012 | CL003 | State Bank of India | Chennai Site-002 | Chennai | South | 10 | Installation Scheduled | 2025-06-08 | 2025-08-04 | 2025-08-12 | 2025-09-03 |  | 7 | Met | Devika Rastogi | 196489
ST00926 | PRJ012 | CL003 | State Bank of India | Kochi Site-003 | Kochi | South | 50 | Live | 2025-06-12 | 2025-07-22 | 2025-08-01 | 2025-08-08 | 2025-08-07 | 10 | Marginal | Ekavir Varkey | 231484
ST00927 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-004 | Bengaluru | South | 100 | Installation Done | 2025-06-11 | 2025-07-14 | 2025-07-11 | 2025-07-26 |  | 12 | Marginal | Tara Dhar | 100699
ST00928 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-005 | Bengaluru | South | 50 | Live | 2025-06-18 | 2025-08-01 | 2025-08-02 | 2025-08-26 | 2025-08-26 | 1 | Met | Ekapad Walia | 258384
ST00929 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-006 | Hyderabad | South | 20 | Live | 2025-06-13 | 2025-08-01 | 2025-07-31 | 2025-08-27 | 2025-08-27 | 0 | Met | Alka Wable | 140327
ST00930 | PRJ012 | CL003 | State Bank of India | Kochi Site-007 | Kochi | South | 10 | Pending Acceptance | 2025-06-23 | 2025-08-14 | 2025-08-15 | 2025-09-05 | 2025-09-08 | 1 | Met | Ekavir Bhargava | 155911
ST00931 | PRJ012 | CL003 | State Bank of India | Chennai Site-008 | Chennai | South | 10 | Live | 2025-06-22 | 2025-07-18 | 2025-07-17 | 2025-08-11 | 2025-08-11 | 0 | Met | Devika Rastogi | 49348
ST00932 | PRJ012 | CL003 | State Bank of India | Kochi Site-009 | Kochi | South | 50 | ROW In Progress | 2025-06-04 | 2025-07-24 |  | 2025-08-19 |  | 7 | Met | Devansh Nigam | 76018
ST00933 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-010 | Bengaluru | South | 100 | Installation Done | 2025-06-10 | 2025-07-09 | 2025-07-16 | 2025-08-04 |  | 12 | Marginal | Irya Sampath | 58934
ST00934 | PRJ012 | CL003 | State Bank of India | Kochi Site-011 | Kochi | South | 50 | Installation Scheduled | 2025-06-07 | 2025-06-30 | 2025-07-07 | 2025-07-23 |  | 3 | Met | Wriddhish Bhardwaj | 150563
ST00935 | PRJ012 | CL003 | State Bank of India | Chennai Site-012 | Chennai | South | 100 | Testing | 2025-06-20 | 2025-08-17 | 2025-08-27 | 2025-09-12 |  | 12 | Marginal | Devansh Rajan | 223562
ST00936 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-013 | Bengaluru | South | 200 | Live | 2025-06-07 | 2025-07-11 | 2025-07-09 | 2025-07-22 | 2025-07-20 | 0 | Met | Victor Kannan | 107591
ST00937 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-014 | Bengaluru | South | 100 | Testing | 2025-06-12 | 2025-07-16 | 2025-07-23 | 2025-08-07 |  | 12 | Marginal | Michael Dutta | 102642
ST00938 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-015 | Hyderabad | South | 50 | Installation Done | 2025-06-09 | 2025-07-12 | 2025-07-18 | 2025-08-11 |  | 12 | Marginal | Ekansh Balay | 237382
ST00939 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-016 | Bengaluru | South | 20 | ROW In Progress | 2025-06-20 | 2025-08-18 |  | 2025-09-12 |  | 4 | Met | Kashvi Edwin | 127604
ST00940 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-017 | Bengaluru | South | 100 | ROW In Progress | 2025-06-14 | 2025-08-02 |  | 2025-08-16 |  | 0 | Met | Nitesh Raghavan | 132570
ST00941 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-018 | Bengaluru | South | 200 | ROW In Progress | 2025-06-12 | 2025-07-06 |  | 2025-07-21 |  | 0 | Met | Ikbal Kothari | 169211
ST00942 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-019 | Bengaluru | South | 10 | Installation Done | 2025-06-11 | 2025-07-31 | 2025-07-29 | 2025-08-11 |  | 12 | Marginal | Ekavir Varkey | 263984
ST00943 | PRJ012 | CL003 | State Bank of India | Chennai Site-020 | Chennai | South | 50 | Installation Done | 2025-06-09 | 2025-07-08 | 2025-07-06 | 2025-07-21 |  | 12 | Marginal | Irya Sampath | 163650
ST00944 | PRJ012 | CL003 | State Bank of India | Kochi Site-021 | Kochi | South | 100 | Live | 2025-06-21 | 2025-07-27 | 2025-08-06 | 2025-08-14 | 2025-08-22 | 10 | Marginal | Nihal Shere | 261989
ST00945 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-022 | Hyderabad | South | 200 | Installation Scheduled | 2025-06-14 | 2025-08-06 | 2025-08-16 | 2025-08-19 |  | 4 | Met | Anamika Kanda | 83771
ST00946 | PRJ012 | CL003 | State Bank of India | Kochi Site-023 | Kochi | South | 20 | Live | 2025-06-25 | 2025-07-24 | 2025-07-30 | 2025-08-18 | 2025-08-15 | 6 | Met | Madhavi Lanka | 139219
ST00947 | PRJ012 | CL003 | State Bank of India | Chennai Site-024 | Chennai | South | 200 | Live | 2025-06-10 | 2025-07-24 | 2025-07-22 | 2025-08-11 | 2025-08-22 | 0 | Met | Ekiya Suresh | 114549
ST00948 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-025 | Hyderabad | South | 20 | Live | 2025-06-16 | 2025-08-12 | 2025-08-20 | 2025-08-30 | 2025-09-05 | 8 | Marginal | Dominic Kakar | 196916
ST00949 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-026 | Hyderabad | South | 50 | Live | 2025-06-07 | 2025-07-24 | 2025-08-02 | 2025-08-21 | 2025-08-29 | 9 | Marginal | Upadhriti Wadhwa | 47184
ST00950 | PRJ012 | CL003 | State Bank of India | Kochi Site-027 | Kochi | South | 200 | Pending Acceptance | 2025-06-08 | 2025-07-27 | 2025-07-26 | 2025-08-22 | 2025-08-28 | 0 | Met | Yashica Issac | 124598
ST00951 | PRJ012 | CL003 | State Bank of India | Kochi Site-028 | Kochi | South | 20 | Installation Scheduled | 2025-06-29 | 2025-08-06 | 2025-08-01 | 2025-08-30 |  | 0 | Met | Ekansh Balay | 261392
ST00952 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-029 | Bengaluru | South | 10 | Survey Pending | 2025-06-13 | 2025-07-03 |  | 2025-07-26 |  | 5 | Met | Simon Tata | 110911
ST00953 | PRJ012 | CL003 | State Bank of India | Chennai Site-030 | Chennai | South | 50 | Installation Done | 2025-06-13 | 2025-08-04 | 2025-08-03 | 2025-08-16 |  | 12 | Marginal | Aarush Lall | 237165
ST00954 | PRJ012 | CL003 | State Bank of India | Chennai Site-031 | Chennai | South | 100 | Installation Done | 2025-06-06 | 2025-07-14 | 2025-07-16 | 2025-07-25 |  | 12 | Marginal | Ikbal Kothari | 110202
ST00955 | PRJ012 | CL003 | State Bank of India | Kochi Site-032 | Kochi | South | 50 | Installation Done | 2025-06-07 | 2025-07-13 | 2025-07-17 | 2025-08-11 |  | 12 | Marginal | Ekiya Suresh | 192824
ST00956 | PRJ012 | CL003 | State Bank of India | Kochi Site-033 | Kochi | South | 20 | Live | 2025-06-14 | 2025-08-10 | 2025-08-09 | 2025-08-26 | 2025-08-31 | 0 | Met | Tanay Rattan | 190302
ST00957 | PRJ012 | CL003 | State Bank of India | Chennai Site-034 | Chennai | South | 100 | Installation Scheduled | 2025-06-06 | 2025-07-15 | 2025-07-24 | 2025-08-11 |  | 2 | Met | Madhavi Lanka | 70176
ST00958 | PRJ012 | CL003 | State Bank of India | Chennai Site-035 | Chennai | South | 50 | Installation Done | 2025-06-26 | 2025-08-05 | 2025-08-11 | 2025-08-29 |  | 12 | Marginal | Nitesh Raghavan | 167303
ST00959 | PRJ012 | CL003 | State Bank of India | Kochi Site-036 | Kochi | South | 20 | Pending Acceptance | 2025-06-18 | 2025-07-09 | 2025-07-04 | 2025-08-01 | 2025-07-31 | 0 | Met | Arya Sunder | 251210
ST00960 | PRJ012 | CL003 | State Bank of India | Chennai Site-037 | Chennai | South | 100 | Testing | 2025-06-15 | 2025-07-13 | 2025-07-17 | 2025-07-24 |  | 12 | Marginal | Harini Choudhury | 150628
ST00961 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-038 | Bengaluru | South | 10 | Installation Done | 2025-06-28 | 2025-08-20 | 2025-08-29 | 2025-08-31 |  | 12 | Marginal | Tara Dhar | 115824
ST00962 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-039 | Bengaluru | South | 10 | Installation Scheduled | 2025-06-07 | 2025-07-15 | 2025-07-25 | 2025-08-04 |  | 0 | Met | Simon Tata | 228913
ST00963 | PRJ012 | CL003 | State Bank of India | Chennai Site-040 | Chennai | South | 20 | Installation Done | 2025-06-21 | 2025-08-11 | 2025-08-10 | 2025-08-28 |  | 12 | Marginal | Arya Sunder | 209689
ST00964 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-041 | Hyderabad | South | 10 | Live | 2025-06-04 | 2025-07-25 | 2025-07-26 | 2025-08-07 | 2025-08-06 | 1 | Met | Yashica Cherian | 203280
ST00965 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-042 | Bengaluru | South | 10 | Installation Done | 2025-06-11 | 2025-07-14 | 2025-07-12 | 2025-08-08 |  | 12 | Marginal | Yatin Baral | 161343
ST00966 | PRJ012 | CL003 | State Bank of India | Kochi Site-043 | Kochi | South | 20 | Survey Pending | 2025-06-07 | 2025-07-16 |  | 2025-08-07 |  | 7 | Met | Devika Rastogi | 265652
ST00967 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-044 | Hyderabad | South | 10 | Live | 2025-06-25 | 2025-08-12 | 2025-08-10 | 2025-09-04 | 2025-09-05 | 0 | Met | Isaac Patil | 82142
ST00968 | PRJ012 | CL003 | State Bank of India | Chennai Site-045 | Chennai | South | 100 | ROW In Progress | 2025-06-27 | 2025-08-20 |  | 2025-09-05 |  | 7 | Met | Ekavir Varkey | 120877
ST00969 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-046 | Bengaluru | South | 10 | Pending Acceptance | 2025-06-19 | 2025-08-01 | 2025-08-04 | 2025-08-23 | 2025-09-01 | 3 | Met | Dipta Bhandari | 154286
ST00970 | PRJ012 | CL003 | State Bank of India | Kochi Site-047 | Kochi | South | 10 | ROW In Progress | 2025-06-13 | 2025-08-01 |  | 2025-08-14 |  | 6 | Met | Arya Sunder | 53934
ST00971 | PRJ012 | CL003 | State Bank of India | Kochi Site-048 | Kochi | South | 50 | Survey Pending | 2025-06-15 | 2025-07-13 |  | 2025-08-06 |  | 7 | Met | Nihal Shere | 86501
ST00972 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-049 | Hyderabad | South | 100 | Installation Done | 2025-06-20 | 2025-07-23 | 2025-07-29 | 2025-08-18 |  | 12 | Marginal | Liam Koshy | 90743
ST00973 | PRJ012 | CL003 | State Bank of India | Chennai Site-050 | Chennai | South | 20 | Installation Done | 2025-06-27 | 2025-08-22 | 2025-08-27 | 2025-09-15 |  | 12 | Marginal | Ekavir Bhargava | 250772
ST00974 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-051 | Hyderabad | South | 200 | Pending Acceptance | 2025-06-06 | 2025-07-26 | 2025-08-02 | 2025-08-20 | 2025-08-22 | 7 | Met | Yatin Baral | 248265
ST00975 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-052 | Hyderabad | South | 200 | ROW In Progress | 2025-06-14 | 2025-08-10 |  | 2025-09-07 |  | 5 | Met | Girik Khalsa | 62713
ST00976 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-053 | Bengaluru | South | 10 | Survey Pending | 2025-06-27 | 2025-07-27 |  | 2025-08-13 |  | 1 | Met | Wahab Raval | 223080
ST00977 | PRJ012 | CL003 | State Bank of India | Kochi Site-054 | Kochi | South | 100 | Installation Scheduled | 2025-06-11 | 2025-07-16 | 2025-07-14 | 2025-07-31 |  | 6 | Met | Liam Koshy | 61233
ST00978 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-055 | Hyderabad | South | 200 | ROW In Progress | 2025-06-27 | 2025-07-21 |  | 2025-08-14 |  | 5 | Met | Daksh Karnik | 90630
ST00979 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-056 | Hyderabad | South | 20 | ROW In Progress | 2025-06-18 | 2025-08-01 |  | 2025-08-15 |  | 8 | Marginal | Farhan Chada | 111190
ST00980 | PRJ012 | CL003 | State Bank of India | Kochi Site-057 | Kochi | South | 100 | Installation Done | 2025-06-13 | 2025-07-17 | 2025-07-18 | 2025-08-01 |  | 12 | Marginal | Wriddhish Bhardwaj | 67549
ST00981 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-058 | Bengaluru | South | 20 | Testing | 2025-06-25 | 2025-07-21 | 2025-07-22 | 2025-08-01 |  | 12 | Marginal | Ekbal Garg | 139256
ST00982 | PRJ012 | CL003 | State Bank of India | Kochi Site-059 | Kochi | South | 200 | Testing | 2025-06-06 | 2025-07-17 | 2025-07-17 | 2025-08-16 |  | 12 | Marginal | Wahab Raval | 94843
ST00983 | PRJ012 | CL003 | State Bank of India | Chennai Site-060 | Chennai | South | 200 | Testing | 2025-06-19 | 2025-08-10 | 2025-08-16 | 2025-08-31 |  | 12 | Marginal | Radhika Dugar | 255133
ST00984 | PRJ012 | CL003 | State Bank of India | Bengaluru Site-061 | Bengaluru | South | 10 | Installation Done | 2025-06-24 | 2025-08-07 | 2025-08-04 | 2025-09-04 |  | 12 | Marginal | Harini Choudhury | 250098
ST00985 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-062 | Hyderabad | South | 50 | ROW In Progress | 2025-06-19 | 2025-07-23 |  | 2025-08-03 |  | 8 | Marginal | Anamika Kanda | 103725
ST00986 | PRJ012 | CL003 | State Bank of India | Hyderabad Site-063 | Hyderabad | South | 50 | Pending Acceptance | 2025-06-12 | 2025-07-26 | 2025-08-01 | 2025-08-07 | 2025-08-09 | 6 | Met | Priya Rastogi | 185095
ST00987 | PRJ013 | CL003 | State Bank of India | Patna Site-001 | Patna | East | 200 | Live | 2025-12-12 | 2026-01-17 | 2026-01-18 | 2026-01-27 | 2026-02-03 | 1 | Met | Madhavi Lanka | 271949
ST00988 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-002 | Bhubaneswar | East | 50 | Live | 2025-12-25 | 2026-01-17 | 2026-01-15 | 2026-02-13 | 2026-02-22 | 0 | Met | Dipta Bhandari | 156105
ST00989 | PRJ013 | CL003 | State Bank of India | Patna Site-003 | Patna | East | 100 | Live | 2025-12-26 | 2026-02-17 | 2026-02-20 | 2026-03-04 | 2026-03-13 | 3 | Met | Devika Rastogi | 79569
ST00990 | PRJ013 | CL003 | State Bank of India | Kolkata Site-004 | Kolkata | East | 50 | Installation Scheduled | 2025-12-23 | 2026-01-29 | 2026-01-26 | 2026-02-15 |  | 8 | Marginal | Unni Bhagat | 194705
ST00991 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-005 | Bhubaneswar | East | 200 | Survey Pending | 2025-12-10 | 2026-01-22 |  | 2026-02-09 |  | 4 | Met | Nihal Shere | 77586
ST00992 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-006 | Bhubaneswar | East | 100 | Testing | 2025-12-12 | 2026-01-17 | 2026-01-17 | 2026-02-10 |  | 12 | Marginal | Anamika Kanda | 160319
ST00993 | PRJ013 | CL003 | State Bank of India | Kolkata Site-007 | Kolkata | East | 10 | Installation Done | 2025-12-13 | 2026-02-01 | 2026-02-02 | 2026-02-24 |  | 12 | Marginal | Theodore Devi | 117468
ST00994 | PRJ013 | CL003 | State Bank of India | Patna Site-008 | Patna | East | 50 | Testing | 2025-12-04 | 2026-01-21 | 2026-01-21 | 2026-02-08 |  | 12 | Marginal | Devansh Nigam | 272817
ST00995 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-009 | Bhubaneswar | East | 20 | ROW In Progress | 2025-12-22 | 2026-01-22 |  | 2026-02-05 |  | 0 | Met | Upadhriti Wadhwa | 216599
ST00996 | PRJ013 | CL003 | State Bank of India | Kolkata Site-010 | Kolkata | East | 10 | ROW In Progress | 2025-12-18 | 2026-02-04 |  | 2026-03-04 |  | 5 | Met | Siddharth Zacharia | 60941
ST00997 | PRJ013 | CL003 | State Bank of India | Patna Site-011 | Patna | East | 200 | Pending Acceptance | 2025-12-10 | 2025-12-31 | 2026-01-06 | 2026-01-27 | 2026-01-25 | 6 | Met | Devika Rastogi | 136679
ST00998 | PRJ013 | CL003 | State Bank of India | Kolkata Site-012 | Kolkata | East | 20 | Survey Pending | 2025-12-16 | 2026-01-12 |  | 2026-02-07 |  | 1 | Met | Ekapad Walia | 130403
ST00999 | PRJ013 | CL003 | State Bank of India | Patna Site-013 | Patna | East | 100 | Installation Done | 2025-12-23 | 2026-02-07 | 2026-02-04 | 2026-03-09 |  | 12 | Marginal | Ekansh Balay | 82507
ST01000 | PRJ013 | CL003 | State Bank of India | Kolkata Site-014 | Kolkata | East | 100 | Installation Scheduled | 2025-12-27 | 2026-02-08 | 2026-02-13 | 2026-03-03 |  | 5 | Met | Ekavir Varkey | 208031
ST01001 | PRJ013 | CL003 | State Bank of India | Kolkata Site-015 | Kolkata | East | 10 | ROW In Progress | 2025-12-03 | 2026-01-10 |  | 2026-01-24 |  | 0 | Met | Kabir Soman | 256821
ST01002 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-016 | Bhubaneswar | East | 100 | Installation Done | 2025-12-26 | 2026-02-16 | 2026-02-22 | 2026-03-04 |  | 12 | Marginal | Diya Rattan | 217244
ST01003 | PRJ013 | CL003 | State Bank of India | Patna Site-017 | Patna | East | 200 | ROW In Progress | 2025-12-26 | 2026-01-20 |  | 2026-02-01 |  | 3 | Met | Yatin Baral | 195585
ST01004 | PRJ013 | CL003 | State Bank of India | Patna Site-018 | Patna | East | 10 | Testing | 2025-12-15 | 2026-02-07 | 2026-02-05 | 2026-03-05 |  | 12 | Marginal | Vansha Thakkar | 217804
ST01005 | PRJ013 | CL003 | State Bank of India | Patna Site-019 | Patna | East | 50 | Installation Done | 2025-12-12 | 2026-01-18 | 2026-01-19 | 2026-02-15 |  | 12 | Marginal | Raksha Varughese | 131162
ST01006 | PRJ013 | CL003 | State Bank of India | Kolkata Site-020 | Kolkata | East | 20 | Live | 2025-12-13 | 2026-01-16 | 2026-01-25 | 2026-02-05 | 2026-02-05 | 9 | Marginal | Bhavika Sampath | 237098
ST01007 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-021 | Bhubaneswar | East | 100 | Installation Done | 2025-12-13 | 2026-02-06 | 2026-02-03 | 2026-02-27 |  | 12 | Marginal | Siddharth Zacharia | 162694
ST01008 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-022 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-12-06 | 2026-01-29 | 2026-01-31 | 2026-02-21 |  | 2 | Met | Devansh Nigam | 253628
ST01009 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-023 | Bhubaneswar | East | 20 | Installation Scheduled | 2025-12-05 | 2025-12-30 | 2026-01-07 | 2026-01-22 |  | 8 | Marginal | Wahab Raval | 210840
ST01010 | PRJ013 | CL003 | State Bank of India | Kolkata Site-024 | Kolkata | East | 50 | Live | 2025-12-16 | 2026-01-05 | 2026-01-05 | 2026-01-18 | 2026-01-28 | 0 | Met | Vansha Thakkar | 239734
ST01011 | PRJ013 | CL003 | State Bank of India | Kolkata Site-025 | Kolkata | East | 10 | ROW In Progress | 2025-12-03 | 2026-01-19 |  | 2026-01-29 |  | 2 | Met | Harini Choudhury | 179977
ST01012 | PRJ013 | CL003 | State Bank of India | Patna Site-026 | Patna | East | 50 | Pending Acceptance | 2025-12-15 | 2026-01-26 | 2026-01-25 | 2026-02-17 | 2026-02-21 | 0 | Met | Advay Contractor | 133292
ST01013 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-027 | Bhubaneswar | East | 50 | Testing | 2025-12-21 | 2026-01-16 | 2026-01-12 | 2026-01-28 |  | 12 | Marginal | Mohammed Gupta | 152184
ST01014 | PRJ013 | CL003 | State Bank of India | Patna Site-028 | Patna | East | 20 | Installation Done | 2025-12-15 | 2026-01-22 | 2026-02-01 | 2026-02-05 |  | 12 | Marginal | Theodore Devi | 84913
ST01015 | PRJ013 | CL003 | State Bank of India | Kolkata Site-029 | Kolkata | East | 100 | Testing | 2025-12-13 | 2026-01-31 | 2026-02-07 | 2026-02-20 |  | 12 | Marginal | Ekiya Suresh | 178344
ST01016 | PRJ013 | CL003 | State Bank of India | Patna Site-030 | Patna | East | 100 | Testing | 2025-12-26 | 2026-01-21 | 2026-01-23 | 2026-02-09 |  | 12 | Marginal | Unni Bhagat | 57658
ST01017 | PRJ013 | CL003 | State Bank of India | Patna Site-031 | Patna | East | 50 | Installation Done | 2025-12-18 | 2026-02-13 | 2026-02-21 | 2026-03-04 |  | 12 | Marginal | Faqid Savant | 128513
ST01018 | PRJ013 | CL003 | State Bank of India | Kolkata Site-032 | Kolkata | East | 200 | Pending Acceptance | 2025-12-03 | 2026-01-05 | 2026-01-13 | 2026-01-31 | 2026-02-05 | 8 | Marginal | Urvashi Ray | 71074
ST01019 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-033 | Bhubaneswar | East | 20 | Installation Scheduled | 2025-12-05 | 2026-01-12 | 2026-01-15 | 2026-02-06 |  | 7 | Met | Kashvi Edwin | 120622
ST01020 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-034 | Bhubaneswar | East | 10 | Pending Acceptance | 2025-12-26 | 2026-01-21 | 2026-01-23 | 2026-02-08 | 2026-02-09 | 2 | Met | Ekapad Walia | 189746
ST01021 | PRJ013 | CL003 | State Bank of India | Patna Site-035 | Patna | East | 10 | Live | 2025-12-02 | 2026-01-29 | 2026-01-25 | 2026-02-25 | 2026-02-28 | 0 | Met | Quincy Biswas | 263236
ST01022 | PRJ013 | CL003 | State Bank of India | Kolkata Site-036 | Kolkata | East | 200 | Installation Done | 2025-12-11 | 2026-02-05 | 2026-02-13 | 2026-03-01 |  | 12 | Marginal | Harini Choudhury | 262851
ST01023 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-037 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-12-05 | 2026-01-01 | 2026-01-10 | 2026-01-24 |  | 7 | Met | Gavin Batta | 271624
ST01024 | PRJ013 | CL003 | State Bank of India | Kolkata Site-038 | Kolkata | East | 10 | Pending Acceptance | 2025-12-25 | 2026-01-21 | 2026-01-27 | 2026-02-02 | 2026-02-06 | 6 | Met | Girindra Chatterjee | 86085
ST01025 | PRJ013 | CL003 | State Bank of India | Patna Site-039 | Patna | East | 100 | Installation Scheduled | 2025-12-16 | 2026-02-14 | 2026-02-11 | 2026-03-06 |  | 0 | Met | Michael Dutta | 229838
ST01026 | PRJ013 | CL003 | State Bank of India | Patna Site-040 | Patna | East | 20 | Installation Scheduled | 2025-12-19 | 2026-02-17 | 2026-02-13 | 2026-03-19 |  | 0 | Met | Radhika Dugar | 198706
ST01027 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-041 | Bhubaneswar | East | 100 | Live | 2025-12-09 | 2026-01-10 | 2026-01-13 | 2026-02-04 | 2026-02-05 | 3 | Met | Isaac Patil | 237298
ST01028 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-042 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-12-08 | 2026-02-06 | 2026-02-03 | 2026-03-04 |  | 3 | Met | Madhavi Lanka | 62632
ST01029 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-043 | Bhubaneswar | East | 50 | Testing | 2025-12-08 | 2026-01-08 | 2026-01-04 | 2026-01-31 |  | 12 | Marginal | Arya Shere | 210419
ST01030 | PRJ013 | CL003 | State Bank of India | Patna Site-044 | Patna | East | 50 | Installation Scheduled | 2025-12-13 | 2026-02-01 | 2026-02-01 | 2026-02-20 |  | 3 | Met | Quincy Biswas | 173508
ST01031 | PRJ013 | CL003 | State Bank of India | Patna Site-045 | Patna | East | 10 | Installation Done | 2025-12-13 | 2026-02-05 | 2026-02-15 | 2026-02-24 |  | 12 | Marginal | Alka Wable | 74456
ST01032 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-046 | Bhubaneswar | East | 10 | Installation Done | 2025-12-16 | 2026-01-25 | 2026-01-27 | 2026-02-17 |  | 12 | Marginal | Ekiya Suresh | 166827
ST01033 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-047 | Bhubaneswar | East | 200 | Live | 2025-12-13 | 2026-01-27 | 2026-01-26 | 2026-02-21 | 2026-03-05 | 0 | Met | Niharika Sunder | 225151
ST01034 | PRJ013 | CL003 | State Bank of India | Kolkata Site-048 | Kolkata | East | 10 | Survey Pending | 2025-12-10 | 2026-01-31 |  | 2026-02-16 |  | 6 | Met | Girindra Chatterjee | 113578
ST01035 | PRJ013 | CL003 | State Bank of India | Patna Site-049 | Patna | East | 10 | Installation Scheduled | 2025-12-14 | 2026-01-31 | 2026-02-08 | 2026-02-22 |  | 4 | Met | Victor Kannan | 172272
ST01036 | PRJ013 | CL003 | State Bank of India | Patna Site-050 | Patna | East | 20 | Installation Scheduled | 2025-12-22 | 2026-01-13 | 2026-01-17 | 2026-02-06 |  | 6 | Met | Kashvi Edwin | 185512
ST01037 | PRJ013 | CL003 | State Bank of India | Kolkata Site-051 | Kolkata | East | 10 | Live | 2025-12-05 | 2026-02-02 | 2026-02-07 | 2026-02-16 | 2026-02-13 | 5 | Met | Arya Shere | 68659
ST01038 | PRJ013 | CL003 | State Bank of India | Patna Site-052 | Patna | East | 200 | Installation Scheduled | 2025-12-13 | 2026-02-06 | 2026-02-03 | 2026-03-08 |  | 0 | Met | Ekapad Walia | 139921
ST01039 | PRJ013 | CL003 | State Bank of India | Patna Site-053 | Patna | East | 50 | ROW In Progress | 2025-12-07 | 2026-01-30 |  | 2026-02-21 |  | 3 | Met | Yashica Issac | 143010
ST01040 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-054 | Bhubaneswar | East | 10 | Installation Done | 2025-12-19 | 2026-01-23 | 2026-01-18 | 2026-02-03 |  | 12 | Marginal | Devansh Rajan | 176465
ST01041 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-055 | Bhubaneswar | East | 20 | Live | 2025-12-03 | 2026-01-02 | 2026-01-06 | 2026-01-21 | 2026-01-18 | 4 | Met | Raksha Varughese | 53854
ST01042 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-056 | Bhubaneswar | East | 10 | Live | 2025-12-27 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-02-28 | 7 | Met | Priya Rastogi | 64369
ST01043 | PRJ013 | CL003 | State Bank of India | Patna Site-057 | Patna | East | 10 | Live | 2025-12-26 | 2026-02-10 | 2026-02-05 | 2026-02-20 | 2026-02-21 | 0 | Met | Chandresh Zachariah | 95930
ST01044 | PRJ013 | CL003 | State Bank of India | Patna Site-058 | Patna | East | 50 | Live | 2025-12-27 | 2026-02-05 | 2026-02-13 | 2026-03-03 | 2026-02-28 | 8 | Marginal | Ekavir Bhargava | 165299
ST01045 | PRJ013 | CL003 | State Bank of India | Kolkata Site-059 | Kolkata | East | 50 | ROW In Progress | 2025-12-22 | 2026-02-16 |  | 2026-03-13 |  | 6 | Met | Nitesh Raghavan | 69395
ST01046 | PRJ013 | CL003 | State Bank of India | Kolkata Site-060 | Kolkata | East | 100 | Pending Acceptance | 2025-12-19 | 2026-01-25 | 2026-02-04 | 2026-02-13 | 2026-02-17 | 10 | Marginal | Anamika Kanda | 175294
ST01047 | PRJ013 | CL003 | State Bank of India | Patna Site-061 | Patna | East | 20 | Installation Done | 2025-12-13 | 2026-02-05 | 2026-02-03 | 2026-03-01 |  | 12 | Marginal | Daksh Karnik | 149162
ST01048 | PRJ013 | CL003 | State Bank of India | Kolkata Site-062 | Kolkata | East | 50 | Installation Done | 2025-12-17 | 2026-02-11 | 2026-02-09 | 2026-03-13 |  | 12 | Marginal | Irya Sampath | 82688
ST01049 | PRJ013 | CL003 | State Bank of India | Patna Site-063 | Patna | East | 200 | Pending Acceptance | 2025-12-05 | 2026-01-29 | 2026-01-29 | 2026-02-14 | 2026-02-26 | 0 | Met | Raksha Varughese | 66990
ST01050 | PRJ013 | CL003 | State Bank of India | Kolkata Site-064 | Kolkata | East | 100 | Installation Done | 2025-12-17 | 2026-02-08 | 2026-02-10 | 2026-02-19 |  | 12 | Marginal | Jai Kota | 152966
ST01051 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-065 | Bhubaneswar | East | 10 | Live | 2025-12-06 | 2025-12-28 | 2026-01-02 | 2026-01-25 | 2026-02-04 | 5 | Met | Victor Kannan | 225983
ST01052 | PRJ013 | CL003 | State Bank of India | Kolkata Site-066 | Kolkata | East | 50 | Live | 2025-12-27 | 2026-02-16 | 2026-02-26 | 2026-03-08 | 2026-03-12 | 10 | Marginal | Dipta Bhandari | 230825
ST01053 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-067 | Bhubaneswar | East | 10 | Installation Done | 2025-12-25 | 2026-01-19 | 2026-01-17 | 2026-02-11 |  | 12 | Marginal | Arya Shere | 78366
ST01054 | PRJ013 | CL003 | State Bank of India | Kolkata Site-068 | Kolkata | East | 100 | ROW In Progress | 2025-12-25 | 2026-01-21 |  | 2026-02-05 |  | 3 | Met | Upadhriti Wadhwa | 55239
ST01055 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-069 | Bhubaneswar | East | 200 | Installation Done | 2025-12-22 | 2026-02-13 | 2026-02-23 | 2026-02-27 |  | 12 | Marginal | Tanay Rattan | 149701
ST01056 | PRJ013 | CL003 | State Bank of India | Kolkata Site-070 | Kolkata | East | 200 | Installation Scheduled | 2025-12-15 | 2026-01-22 | 2026-01-25 | 2026-02-17 |  | 5 | Met | Logan Sami | 192799
ST01057 | PRJ013 | CL003 | State Bank of India | Patna Site-071 | Patna | East | 200 | ROW In Progress | 2025-12-11 | 2026-02-02 |  | 2026-02-18 |  | 5 | Met | Jai Kota | 168760
ST01058 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-072 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-12-12 | 2026-01-09 | 2026-01-09 | 2026-02-04 |  | 7 | Met | Urvashi Ray | 154131
ST01059 | PRJ013 | CL003 | State Bank of India | Kolkata Site-073 | Kolkata | East | 20 | ROW In Progress | 2025-12-04 | 2025-12-24 |  | 2026-01-12 |  | 3 | Met | Michael Dutta | 185963
ST01060 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-074 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-12-03 | 2026-01-31 | 2026-02-09 | 2026-03-01 |  | 2 | Met | Darsh Rau | 211813
ST01061 | PRJ013 | CL003 | State Bank of India | Patna Site-075 | Patna | East | 50 | Live | 2025-12-13 | 2026-02-11 | 2026-02-06 | 2026-02-27 | 2026-03-04 | 0 | Met | Nitesh Raghavan | 198214
ST01062 | PRJ013 | CL003 | State Bank of India | Patna Site-076 | Patna | East | 20 | Installation Scheduled | 2025-12-21 | 2026-02-04 | 2026-02-07 | 2026-03-03 |  | 8 | Marginal | Priya Rastogi | 200356
ST01063 | PRJ013 | CL003 | State Bank of India | Kolkata Site-077 | Kolkata | East | 200 | ROW In Progress | 2025-12-08 | 2026-01-14 |  | 2026-01-29 |  | 4 | Met | Devansh Rajan | 78214
ST01064 | PRJ013 | CL003 | State Bank of India | Patna Site-078 | Patna | East | 200 | Testing | 2025-12-26 | 2026-02-08 | 2026-02-13 | 2026-03-08 |  | 12 | Marginal | Ekavir Bhargava | 256628
ST01065 | PRJ013 | CL003 | State Bank of India | Patna Site-079 | Patna | East | 20 | Live | 2025-12-23 | 2026-02-11 | 2026-02-12 | 2026-02-26 | 2026-02-23 | 1 | Met | Kabir Soman | 68943
ST01066 | PRJ013 | CL003 | State Bank of India | Patna Site-080 | Patna | East | 10 | ROW In Progress | 2025-12-07 | 2026-01-26 |  | 2026-02-05 |  | 5 | Met | Simon Tata | 80907
ST01067 | PRJ013 | CL003 | State Bank of India | Patna Site-081 | Patna | East | 20 | Live | 2025-12-15 | 2026-02-03 | 2026-02-08 | 2026-02-22 | 2026-02-22 | 5 | Met | Chandresh Zachariah | 143909
ST01068 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-082 | Bhubaneswar | East | 200 | Live | 2025-12-13 | 2026-01-21 | 2026-01-26 | 2026-02-16 | 2026-02-15 | 5 | Met | Kabir Soman | 88546
ST01069 | PRJ013 | CL003 | State Bank of India | Patna Site-083 | Patna | East | 100 | Live | 2025-12-24 | 2026-01-22 | 2026-01-30 | 2026-02-18 | 2026-03-01 | 8 | Marginal | Jai Kota | 224665
ST01070 | PRJ013 | CL003 | State Bank of India | Kolkata Site-084 | Kolkata | East | 50 | Testing | 2025-12-15 | 2026-01-26 | 2026-01-26 | 2026-02-05 |  | 12 | Marginal | Dipta Bhandari | 247046
ST01071 | PRJ013 | CL003 | State Bank of India | Patna Site-085 | Patna | East | 20 | Installation Scheduled | 2025-12-15 | 2026-01-17 | 2026-01-18 | 2026-02-08 |  | 5 | Met | Nihal Shere | 96337
ST01072 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-086 | Bhubaneswar | East | 10 | Installation Done | 2025-12-08 | 2025-12-28 | 2026-01-01 | 2026-01-17 |  | 12 | Marginal | Logan Sami | 111521
ST01073 | PRJ013 | CL003 | State Bank of India | Patna Site-087 | Patna | East | 100 | Pending Acceptance | 2025-12-21 | 2026-01-27 | 2026-01-23 | 2026-02-26 | 2026-03-03 | 0 | Met | Chandresh Zachariah | 56512
ST01074 | PRJ013 | CL003 | State Bank of India | Patna Site-088 | Patna | East | 100 | Live | 2025-12-10 | 2026-02-08 | 2026-02-04 | 2026-03-08 | 2026-03-05 | 0 | Met | Teerth Bhardwaj | 173529
ST01075 | PRJ013 | CL003 | State Bank of India | Kolkata Site-089 | Kolkata | East | 50 | Installation Done | 2025-12-22 | 2026-02-14 | 2026-02-12 | 2026-02-25 |  | 12 | Marginal | Daksh Karnik | 205673
ST01076 | PRJ013 | CL003 | State Bank of India | Patna Site-090 | Patna | East | 100 | ROW In Progress | 2025-12-25 | 2026-01-25 |  | 2026-02-08 |  | 1 | Met | Advay Contractor | 59692
ST01077 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-091 | Bhubaneswar | East | 20 | Live | 2025-12-03 | 2026-01-12 | 2026-01-10 | 2026-02-08 | 2026-02-13 | 0 | Met | Anamika Kanda | 132206
ST01078 | PRJ013 | CL003 | State Bank of India | Patna Site-092 | Patna | East | 100 | Live | 2025-12-12 | 2026-01-11 | 2026-01-17 | 2026-02-06 | 2026-02-03 | 6 | Met | Tanay Rattan | 264602
ST01079 | PRJ013 | CL003 | State Bank of India | Patna Site-093 | Patna | East | 20 | Live | 2025-12-04 | 2026-01-05 | 2026-01-04 | 2026-01-23 | 2026-01-22 | 0 | Met | Bhavika Sampath | 56667
ST01080 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-094 | Bhubaneswar | East | 10 | Testing | 2025-12-24 | 2026-02-14 | 2026-02-22 | 2026-03-01 |  | 12 | Marginal | Kevin Solanki | 116765
ST01081 | PRJ013 | CL003 | State Bank of India | Patna Site-095 | Patna | East | 100 | Installation Done | 2025-12-12 | 2026-01-30 | 2026-01-27 | 2026-02-27 |  | 12 | Marginal | Gavin Batta | 75477
ST01082 | PRJ013 | CL003 | State Bank of India | Kolkata Site-096 | Kolkata | East | 20 | ROW In Progress | 2025-12-04 | 2026-01-04 |  | 2026-01-24 |  | 0 | Met | Nihal Shere | 102023
ST01083 | PRJ013 | CL003 | State Bank of India | Patna Site-097 | Patna | East | 20 | Installation Done | 2025-12-04 | 2026-01-08 | 2026-01-12 | 2026-02-07 |  | 12 | Marginal | Harini Choudhury | 126392
ST01084 | PRJ013 | CL003 | State Bank of India | Kolkata Site-098 | Kolkata | East | 200 | Installation Done | 2025-12-11 | 2026-01-11 | 2026-01-14 | 2026-01-25 |  | 12 | Marginal | Urvashi Ray | 153523
ST01085 | PRJ013 | CL003 | State Bank of India | Kolkata Site-099 | Kolkata | East | 100 | Live | 2025-12-10 | 2026-01-11 | 2026-01-11 | 2026-01-30 | 2026-02-04 | 0 | Met | Devansh Nigam | 69225
ST01086 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-100 | Bhubaneswar | East | 20 | Installation Done | 2025-12-13 | 2026-01-24 | 2026-02-02 | 2026-02-23 |  | 12 | Marginal | Diya Rattan | 263817
ST01087 | PRJ013 | CL003 | State Bank of India | Patna Site-101 | Patna | East | 50 | Installation Done | 2025-12-19 | 2026-02-13 | 2026-02-14 | 2026-03-08 |  | 12 | Marginal | Ekansh Balay | 99380
ST01088 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-102 | Bhubaneswar | East | 50 | Live | 2025-12-18 | 2026-02-11 | 2026-02-14 | 2026-02-23 | 2026-02-26 | 3 | Met | Kabir Soman | 167601
ST01089 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-103 | Bhubaneswar | East | 100 | Survey Pending | 2025-12-05 | 2026-01-27 |  | 2026-02-26 |  | 2 | Met | Radhika Dugar | 167485
ST01090 | PRJ013 | CL003 | State Bank of India | Patna Site-104 | Patna | East | 50 | Installation Scheduled | 2025-12-20 | 2026-02-02 | 2026-01-29 | 2026-02-22 |  | 1 | Met | Nihal Shere | 86615
ST01091 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-105 | Bhubaneswar | East | 50 | Installation Done | 2025-12-12 | 2026-01-07 | 2026-01-07 | 2026-01-28 |  | 12 | Marginal | Yashica Issac | 167379
ST01092 | PRJ013 | CL003 | State Bank of India | Patna Site-106 | Patna | East | 200 | ROW In Progress | 2025-12-02 | 2026-01-19 |  | 2026-02-17 |  | 7 | Met | Madhavi Lanka | 236615
ST01093 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-107 | Bhubaneswar | East | 50 | Installation Done | 2025-12-09 | 2026-01-14 | 2026-01-20 | 2026-02-12 |  | 12 | Marginal | Dakshesh Trivedi | 222879
ST01094 | PRJ013 | CL003 | State Bank of India | Bhubaneswar Site-108 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-12-09 | 2026-01-30 | 2026-01-28 | 2026-02-22 |  | 6 | Met | Girik Khalsa | 200471
ST01095 | PRJ014 | CL003 | State Bank of India | Pune Site-001 | Pune | West | 200 | Pending Acceptance | 2025-08-31 | 2025-09-25 | 2025-10-03 | 2025-10-08 | 2025-10-11 | 8 | Marginal | Devansh Nigam | 124482
ST01096 | PRJ014 | CL003 | State Bank of India | Pune Site-002 | Pune | West | 50 | Live | 2025-08-24 | 2025-10-06 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 10 | Marginal | Isaac Patil | 117575
ST01097 | PRJ014 | CL003 | State Bank of India | Mumbai Site-003 | Mumbai | West | 100 | Testing | 2025-08-28 | 2025-10-05 | 2025-10-08 | 2025-10-15 |  | 12 | Marginal | Ekapad Walia | 49907
ST01098 | PRJ014 | CL003 | State Bank of India | Surat Site-004 | Surat | West | 10 | Live | 2025-08-31 | 2025-10-07 | 2025-10-16 | 2025-11-05 | 2025-11-12 | 9 | Marginal | Alka Wable | 103936
ST01099 | PRJ014 | CL003 | State Bank of India | Mumbai Site-005 | Mumbai | West | 200 | Live | 2025-08-30 | 2025-09-23 | 2025-09-27 | 2025-10-22 | 2025-11-02 | 4 | Met | Tanay Rattan | 211401
ST01100 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-006 | Ahmedabad | West | 50 | Testing | 2025-09-07 | 2025-11-01 | 2025-10-27 | 2025-11-21 |  | 12 | Marginal | Urvashi Ray | 135797
ST01101 | PRJ014 | CL003 | State Bank of India | Surat Site-007 | Surat | West | 20 | ROW In Progress | 2025-09-15 | 2025-11-05 |  | 2025-11-21 |  | 8 | Marginal | Faqid Savant | 112028
ST01102 | PRJ014 | CL003 | State Bank of India | Surat Site-008 | Surat | West | 200 | Survey Pending | 2025-09-10 | 2025-10-05 |  | 2025-11-04 |  | 7 | Met | Darsh Rau | 66782
ST01103 | PRJ014 | CL003 | State Bank of India | Pune Site-009 | Pune | West | 100 | Live | 2025-09-08 | 2025-10-21 | 2025-10-25 | 2025-11-09 | 2025-11-16 | 4 | Met | Dipta Bhandari | 52750
ST01104 | PRJ014 | CL003 | State Bank of India | Pune Site-010 | Pune | West | 100 | Testing | 2025-08-28 | 2025-10-26 | 2025-11-01 | 2025-11-23 |  | 12 | Marginal | Tanay Rattan | 245524
ST01105 | PRJ014 | CL003 | State Bank of India | Mumbai Site-011 | Mumbai | West | 200 | Live | 2025-09-01 | 2025-10-26 | 2025-11-05 | 2025-11-12 | 2025-11-21 | 10 | Marginal | Harini Choudhury | 144202
ST01106 | PRJ014 | CL003 | State Bank of India | Mumbai Site-012 | Mumbai | West | 20 | ROW In Progress | 2025-08-29 | 2025-10-01 |  | 2025-10-14 |  | 4 | Met | Yashica Issac | 246031
ST01107 | PRJ014 | CL003 | State Bank of India | Surat Site-013 | Surat | West | 50 | Testing | 2025-09-03 | 2025-10-06 | 2025-10-14 | 2025-11-04 |  | 12 | Marginal | Urvashi Ray | 246981
ST01108 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-014 | Ahmedabad | West | 20 | Live | 2025-09-13 | 2025-11-12 | 2025-11-17 | 2025-12-08 | 2025-12-17 | 5 | Met | Girik Khalsa | 174717
ST01109 | PRJ014 | CL003 | State Bank of India | Surat Site-015 | Surat | West | 10 | Installation Scheduled | 2025-09-06 | 2025-10-06 | 2025-10-06 | 2025-10-28 |  | 4 | Met | Irya Sampath | 244998
ST01110 | PRJ014 | CL003 | State Bank of India | Surat Site-016 | Surat | West | 100 | Live | 2025-09-13 | 2025-10-09 | 2025-10-16 | 2025-11-06 | 2025-11-16 | 7 | Met | Niharika Sunder | 94512
ST01111 | PRJ014 | CL003 | State Bank of India | Mumbai Site-017 | Mumbai | West | 200 | Testing | 2025-08-27 | 2025-10-25 | 2025-10-22 | 2025-11-23 |  | 12 | Marginal | Niharika Sunder | 50985
ST01112 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-018 | Ahmedabad | West | 50 | Testing | 2025-08-28 | 2025-10-23 | 2025-11-02 | 2025-11-04 |  | 12 | Marginal | Anamika Kanda | 239763
ST01113 | PRJ014 | CL003 | State Bank of India | Surat Site-019 | Surat | West | 20 | Testing | 2025-08-29 | 2025-09-28 | 2025-10-07 | 2025-10-19 |  | 12 | Marginal | Ekiya Suresh | 168776
ST01114 | PRJ014 | CL003 | State Bank of India | Pune Site-020 | Pune | West | 100 | Installation Scheduled | 2025-09-01 | 2025-09-25 | 2025-09-20 | 2025-10-11 |  | 7 | Met | Raksha Varughese | 224220
ST01115 | PRJ014 | CL003 | State Bank of India | Surat Site-021 | Surat | West | 200 | Pending Acceptance | 2025-09-17 | 2025-10-18 | 2025-10-27 | 2025-11-13 | 2025-11-13 | 9 | Marginal | Irya Sampath | 273611
ST01116 | PRJ014 | CL003 | State Bank of India | Pune Site-022 | Pune | West | 200 | Installation Scheduled | 2025-09-15 | 2025-10-09 | 2025-10-04 | 2025-10-20 |  | 6 | Met | Vansha Thakkar | 271012
ST01117 | PRJ014 | CL003 | State Bank of India | Surat Site-023 | Surat | West | 200 | Survey Pending | 2025-09-05 | 2025-10-11 |  | 2025-11-07 |  | 1 | Met | Daksh Karnik | 159955
ST01118 | PRJ014 | CL003 | State Bank of India | Surat Site-024 | Surat | West | 100 | Live | 2025-08-24 | 2025-10-01 | 2025-10-08 | 2025-10-12 | 2025-10-20 | 7 | Met | Bhavika Sampath | 157351
ST01119 | PRJ014 | CL003 | State Bank of India | Mumbai Site-025 | Mumbai | West | 50 | ROW In Progress | 2025-08-31 | 2025-10-27 |  | 2025-11-09 |  | 2 | Met | Niharika Sunder | 217107
ST01120 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-026 | Ahmedabad | West | 10 | ROW In Progress | 2025-08-30 | 2025-10-19 |  | 2025-11-04 |  | 4 | Met | Irya Sampath | 213305
ST01121 | PRJ014 | CL003 | State Bank of India | Mumbai Site-027 | Mumbai | West | 50 | Installation Done | 2025-09-14 | 2025-11-04 | 2025-11-06 | 2025-11-22 |  | 12 | Marginal | Ekavir Varkey | 225668
ST01122 | PRJ014 | CL003 | State Bank of India | Surat Site-028 | Surat | West | 20 | Installation Scheduled | 2025-09-06 | 2025-10-12 | 2025-10-15 | 2025-11-10 |  | 0 | Met | Aarush Lall | 181781
ST01123 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-029 | Ahmedabad | West | 50 | Survey Pending | 2025-09-03 | 2025-10-29 |  | 2025-11-19 |  | 4 | Met | Yashica Issac | 193803
ST01124 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-030 | Ahmedabad | West | 20 | Installation Done | 2025-09-06 | 2025-10-14 | 2025-10-13 | 2025-10-28 |  | 12 | Marginal | Ekavir Varkey | 270220
ST01125 | PRJ014 | CL003 | State Bank of India | Surat Site-031 | Surat | West | 20 | Installation Scheduled | 2025-08-30 | 2025-09-20 | 2025-09-21 | 2025-10-18 |  | 4 | Met | Nihal Shere | 113005
ST01126 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-032 | Ahmedabad | West | 50 | Live | 2025-09-15 | 2025-11-07 | 2025-11-14 | 2025-12-02 | 2025-12-04 | 7 | Met | Yashica Cherian | 198914
ST01127 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-033 | Ahmedabad | West | 100 | Installation Done | 2025-09-04 | 2025-10-25 | 2025-10-25 | 2025-11-20 |  | 12 | Marginal | Ekiya Suresh | 171877
ST01128 | PRJ014 | CL003 | State Bank of India | Surat Site-034 | Surat | West | 20 | Survey Pending | 2025-08-25 | 2025-10-05 |  | 2025-10-22 |  | 4 | Met | Alka Wable | 84344
ST01129 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-035 | Ahmedabad | West | 100 | Testing | 2025-09-15 | 2025-10-12 | 2025-10-13 | 2025-11-02 |  | 12 | Marginal | Teerth Bhardwaj | 194266
ST01130 | PRJ014 | CL003 | State Bank of India | Mumbai Site-036 | Mumbai | West | 10 | Live | 2025-09-17 | 2025-11-09 | 2025-11-11 | 2025-11-25 | 2025-12-03 | 2 | Met | Girik Khalsa | 209207
ST01131 | PRJ014 | CL003 | State Bank of India | Mumbai Site-037 | Mumbai | West | 10 | Pending Acceptance | 2025-09-08 | 2025-10-02 | 2025-10-05 | 2025-10-29 | 2025-10-28 | 3 | Met | Mohammed Gupta | 193557
ST01132 | PRJ014 | CL003 | State Bank of India | Pune Site-038 | Pune | West | 20 | Installation Scheduled | 2025-09-17 | 2025-10-18 | 2025-10-20 | 2025-11-04 |  | 7 | Met | Dominic Kakar | 204681
ST01133 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-039 | Ahmedabad | West | 200 | Testing | 2025-08-25 | 2025-09-26 | 2025-09-23 | 2025-10-10 |  | 12 | Marginal | Arya Sunder | 60955
ST01134 | PRJ014 | CL003 | State Bank of India | Pune Site-040 | Pune | West | 200 | Installation Scheduled | 2025-09-10 | 2025-11-06 | 2025-11-16 | 2025-11-30 |  | 1 | Met | Simon Tata | 128586
ST01135 | PRJ014 | CL003 | State Bank of India | Mumbai Site-041 | Mumbai | West | 20 | ROW In Progress | 2025-08-26 | 2025-10-13 |  | 2025-10-25 |  | 7 | Met | Michael Dutta | 187178
ST01136 | PRJ014 | CL003 | State Bank of India | Pune Site-042 | Pune | West | 100 | Testing | 2025-09-01 | 2025-10-27 | 2025-10-22 | 2025-11-24 |  | 12 | Marginal | Upadhriti Wadhwa | 233738
ST01137 | PRJ014 | CL003 | State Bank of India | Surat Site-043 | Surat | West | 100 | Live | 2025-08-29 | 2025-10-25 | 2025-11-03 | 2025-11-04 | 2025-11-09 | 9 | Marginal | Victor Kannan | 174133
ST01138 | PRJ014 | CL003 | State Bank of India | Pune Site-044 | Pune | West | 50 | Installation Scheduled | 2025-09-07 | 2025-10-29 | 2025-11-02 | 2025-11-28 |  | 4 | Met | Raksha Varughese | 134428
ST01139 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-045 | Ahmedabad | West | 100 | Live | 2025-09-08 | 2025-10-17 | 2025-10-26 | 2025-10-30 | 2025-11-01 | 9 | Marginal | Ekbal Garg | 128678
ST01140 | PRJ014 | CL003 | State Bank of India | Surat Site-046 | Surat | West | 10 | Installation Done | 2025-08-28 | 2025-09-21 | 2025-09-29 | 2025-10-10 |  | 12 | Marginal | Bhavika Sampath | 134766
ST01141 | PRJ014 | CL003 | State Bank of India | Pune Site-047 | Pune | West | 200 | ROW In Progress | 2025-08-26 | 2025-09-29 |  | 2025-10-15 |  | 4 | Met | Kevin Solanki | 128890
ST01142 | PRJ014 | CL003 | State Bank of India | Surat Site-048 | Surat | West | 50 | ROW In Progress | 2025-09-01 | 2025-10-30 |  | 2025-11-15 |  | 2 | Met | Yashica Issac | 95306
ST01143 | PRJ014 | CL003 | State Bank of India | Surat Site-049 | Surat | West | 200 | Live | 2025-08-28 | 2025-10-26 | 2025-10-26 | 2025-11-15 | 2025-11-27 | 0 | Met | Tanay Rattan | 249408
ST01144 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-050 | Ahmedabad | West | 50 | Installation Scheduled | 2025-08-31 | 2025-10-20 | 2025-10-24 | 2025-11-10 |  | 2 | Met | Irya Sampath | 235502
ST01145 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-051 | Ahmedabad | West | 100 | Live | 2025-09-02 | 2025-10-20 | 2025-10-24 | 2025-11-12 | 2025-11-21 | 4 | Met | Ekbal Garg | 244812
ST01146 | PRJ014 | CL003 | State Bank of India | Surat Site-052 | Surat | West | 100 | Survey Pending | 2025-09-05 | 2025-10-17 |  | 2025-11-16 |  | 2 | Met | Ekavir Bhargava | 50106
ST01147 | PRJ014 | CL003 | State Bank of India | Pune Site-053 | Pune | West | 50 | Installation Scheduled | 2025-09-14 | 2025-10-20 | 2025-10-24 | 2025-11-10 |  | 0 | Met | Nitesh Raghavan | 252334
ST01148 | PRJ014 | CL003 | State Bank of India | Surat Site-054 | Surat | West | 100 | Installation Scheduled | 2025-09-09 | 2025-10-11 | 2025-10-12 | 2025-11-09 |  | 8 | Marginal | Ekavir Bhargava | 73006
ST01149 | PRJ014 | CL003 | State Bank of India | Mumbai Site-055 | Mumbai | West | 100 | Installation Scheduled | 2025-09-02 | 2025-10-22 | 2025-11-01 | 2025-11-02 |  | 6 | Met | Raksha Varughese | 118437
ST01150 | PRJ014 | CL003 | State Bank of India | Surat Site-056 | Surat | West | 200 | Survey Pending | 2025-08-24 | 2025-10-23 |  | 2025-11-12 |  | 4 | Met | Logan Sami | 159851
ST01151 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-057 | Ahmedabad | West | 20 | ROW In Progress | 2025-08-27 | 2025-09-20 |  | 2025-10-10 |  | 6 | Met | Yashica Cherian | 199614
ST01152 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-058 | Ahmedabad | West | 50 | Testing | 2025-09-09 | 2025-10-04 | 2025-10-13 | 2025-10-21 |  | 12 | Marginal | Devansh Nigam | 190928
ST01153 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-059 | Ahmedabad | West | 20 | Live | 2025-08-27 | 2025-09-20 | 2025-09-25 | 2025-10-11 | 2025-10-22 | 5 | Met | Isaac Patil | 129218
ST01154 | PRJ014 | CL003 | State Bank of India | Surat Site-060 | Surat | West | 200 | Installation Scheduled | 2025-09-03 | 2025-10-14 | 2025-10-15 | 2025-11-01 |  | 4 | Met | Anamika Kanda | 81770
ST01155 | PRJ014 | CL003 | State Bank of India | Mumbai Site-061 | Mumbai | West | 200 | Live | 2025-09-05 | 2025-10-20 | 2025-10-30 | 2025-10-31 | 2025-10-29 | 10 | Marginal | Logan Sami | 49247
ST01156 | PRJ014 | CL003 | State Bank of India | Surat Site-062 | Surat | West | 10 | Pending Acceptance | 2025-09-08 | 2025-10-18 | 2025-10-28 | 2025-11-06 | 2025-11-13 | 10 | Marginal | Priya Rastogi | 193191
ST01157 | PRJ014 | CL003 | State Bank of India | Mumbai Site-063 | Mumbai | West | 200 | Pending Acceptance | 2025-09-16 | 2025-10-13 | 2025-10-13 | 2025-11-08 | 2025-11-07 | 0 | Met | Dipta Bhandari | 204916
ST01158 | PRJ014 | CL003 | State Bank of India | Pune Site-064 | Pune | West | 20 | Live | 2025-09-16 | 2025-11-02 | 2025-11-05 | 2025-11-26 | 2025-12-07 | 3 | Met | Irya Sampath | 64143
ST01159 | PRJ014 | CL003 | State Bank of India | Pune Site-065 | Pune | West | 200 | Live | 2025-09-02 | 2025-10-21 | 2025-10-29 | 2025-10-31 | 2025-11-09 | 8 | Marginal | Ekavir Varkey | 46665
ST01160 | PRJ014 | CL003 | State Bank of India | Surat Site-066 | Surat | West | 50 | Survey Pending | 2025-08-30 | 2025-10-09 |  | 2025-11-01 |  | 2 | Met | Alka Wable | 198190
ST01161 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-067 | Ahmedabad | West | 20 | Testing | 2025-09-12 | 2025-10-14 | 2025-10-20 | 2025-11-11 |  | 12 | Marginal | Wriddhish Bhardwaj | 247635
ST01162 | PRJ014 | CL003 | State Bank of India | Pune Site-068 | Pune | West | 20 | Installation Scheduled | 2025-08-28 | 2025-09-23 | 2025-09-18 | 2025-10-20 |  | 0 | Met | Darsh Rau | 63157
ST01163 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-069 | Ahmedabad | West | 100 | Live | 2025-08-30 | 2025-10-02 | 2025-10-03 | 2025-10-21 | 2025-10-23 | 1 | Met | Victor Kannan | 106074
ST01164 | PRJ014 | CL003 | State Bank of India | Pune Site-070 | Pune | West | 10 | Live | 2025-08-23 | 2025-09-20 | 2025-09-29 | 2025-10-03 | 2025-10-12 | 9 | Marginal | Bhavika Sampath | 272418
ST01165 | PRJ014 | CL003 | State Bank of India | Pune Site-071 | Pune | West | 20 | Installation Done | 2025-09-06 | 2025-10-24 | 2025-10-31 | 2025-11-09 |  | 12 | Marginal | Arya Shere | 199721
ST01166 | PRJ014 | CL003 | State Bank of India | Mumbai Site-072 | Mumbai | West | 10 | ROW In Progress | 2025-08-28 | 2025-10-19 |  | 2025-11-16 |  | 8 | Marginal | Yashica Issac | 243339
ST01167 | PRJ014 | CL003 | State Bank of India | Pune Site-073 | Pune | West | 100 | ROW In Progress | 2025-09-07 | 2025-11-04 |  | 2025-11-25 |  | 5 | Met | Wriddhish Bhardwaj | 100136
ST01168 | PRJ014 | CL003 | State Bank of India | Mumbai Site-074 | Mumbai | West | 100 | Live | 2025-09-03 | 2025-10-23 | 2025-10-26 | 2025-11-18 | 2025-11-18 | 3 | Met | Anamika Kanda | 46902
ST01169 | PRJ014 | CL003 | State Bank of India | Surat Site-075 | Surat | West | 10 | Live | 2025-09-04 | 2025-09-30 | 2025-10-06 | 2025-10-21 | 2025-10-27 | 6 | Met | Madhavi Lanka | 267247
ST01170 | PRJ014 | CL003 | State Bank of India | Ahmedabad Site-076 | Ahmedabad | West | 50 | Installation Scheduled | 2025-09-14 | 2025-10-09 | 2025-10-16 | 2025-11-03 |  | 0 | Met | Girindra Chatterjee | 56893
ST01171 | PRJ014 | CL003 | State Bank of India | Pune Site-077 | Pune | West | 20 | Live | 2025-08-28 | 2025-10-23 | 2025-10-18 | 2025-11-06 | 2025-11-07 | 0 | Met | Vansha Thakkar | 244829
ST01172 | PRJ014 | CL003 | State Bank of India | Mumbai Site-078 | Mumbai | West | 200 | Survey Pending | 2025-09-17 | 2025-10-20 |  | 2025-11-08 |  | 5 | Met | Tanay Rattan | 260810
ST01173 | PRJ014 | CL003 | State Bank of India | Pune Site-079 | Pune | West | 50 | Installation Done | 2025-08-28 | 2025-10-20 | 2025-10-19 | 2025-11-04 |  | 12 | Marginal | Upadhriti Wadhwa | 251191
ST01174 | PRJ014 | CL003 | State Bank of India | Pune Site-080 | Pune | West | 50 | Survey Pending | 2025-08-29 | 2025-10-07 |  | 2025-10-29 |  | 5 | Met | Girindra Chatterjee | 52465
ST01175 | PRJ014 | CL003 | State Bank of India | Mumbai Site-081 | Mumbai | West | 200 | Installation Scheduled | 2025-09-07 | 2025-09-29 | 2025-09-28 | 2025-10-22 |  | 0 | Met | Arya Shere | 244885
ST01176 | PRJ014 | CL003 | State Bank of India | Pune Site-082 | Pune | West | 100 | ROW In Progress | 2025-08-23 | 2025-10-04 |  | 2025-10-21 |  | 1 | Met | Liam Koshy | 74467
ST01177 | PRJ014 | CL003 | State Bank of India | Surat Site-083 | Surat | West | 200 | Installation Done | 2025-09-05 | 2025-10-29 | 2025-11-07 | 2025-11-12 |  | 12 | Marginal | Ekbal Garg | 126639
ST01178 | PRJ014 | CL003 | State Bank of India | Surat Site-084 | Surat | West | 50 | Installation Done | 2025-08-31 | 2025-09-28 | 2025-10-03 | 2025-10-25 |  | 12 | Marginal | Michael Dutta | 170249
ST01179 | PRJ014 | CL003 | State Bank of India | Surat Site-085 | Surat | West | 20 | Live | 2025-09-10 | 2025-10-12 | 2025-10-11 | 2025-10-29 | 2025-10-30 | 0 | Met | Alka Wable | 217807
ST01180 | PRJ014 | CL003 | State Bank of India | Mumbai Site-086 | Mumbai | West | 20 | Live | 2025-09-14 | 2025-10-29 | 2025-11-02 | 2025-11-27 | 2025-11-27 | 4 | Met | Alka Wable | 110711
ST01181 | PRJ014 | CL003 | State Bank of India | Pune Site-087 | Pune | West | 20 | Live | 2025-09-01 | 2025-10-12 | 2025-10-21 | 2025-11-09 | 2025-11-14 | 9 | Marginal | Girindra Chatterjee | 155630
ST01182 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-001 | Bengaluru | South | 50 | Live | 2025-10-31 | 2025-12-05 | 2025-12-15 | 2025-12-22 | 2026-01-01 | 10 | Marginal | Devansh Rajan | 249713
ST01183 | PRJ015 | CL003 | State Bank of India | Kochi Site-002 | Kochi | South | 200 | Testing | 2025-11-03 | 2025-12-17 | 2025-12-24 | 2025-12-28 |  | 12 | Marginal | Devansh Rajan | 199754
ST01184 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-003 | Bengaluru | South | 200 | Testing | 2025-10-19 | 2025-11-23 | 2025-11-29 | 2025-12-21 |  | 12 | Marginal | Tanay Rattan | 258721
ST01185 | PRJ015 | CL003 | State Bank of India | Kochi Site-004 | Kochi | South | 100 | Live | 2025-10-17 | 2025-11-28 | 2025-12-07 | 2025-12-22 | 2025-12-20 | 9 | Marginal | Madhavi Lanka | 220392
ST01186 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-005 | Bengaluru | South | 100 | Installation Scheduled | 2025-10-21 | 2025-11-11 | 2025-11-16 | 2025-11-24 |  | 4 | Met | Daksh Karnik | 236118
ST01187 | PRJ015 | CL003 | State Bank of India | Kochi Site-006 | Kochi | South | 50 | Live | 2025-10-24 | 2025-12-05 | 2025-12-11 | 2025-12-26 | 2025-12-30 | 6 | Met | Mohammed Gupta | 250444
ST01188 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-007 | Bengaluru | South | 200 | Installation Scheduled | 2025-11-07 | 2026-01-06 | 2026-01-09 | 2026-01-21 |  | 3 | Met | Girindra Chatterjee | 239171
ST01189 | PRJ015 | CL003 | State Bank of India | Kochi Site-008 | Kochi | South | 50 | Live | 2025-11-09 | 2025-12-10 | 2025-12-20 | 2025-12-22 | 2025-12-29 | 10 | Marginal | Siddharth Zacharia | 127977
ST01190 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-009 | Hyderabad | South | 50 | ROW In Progress | 2025-11-08 | 2025-12-03 |  | 2026-01-02 |  | 6 | Met | Wahab Raval | 212634
ST01191 | PRJ015 | CL003 | State Bank of India | Chennai Site-010 | Chennai | South | 100 | Live | 2025-10-22 | 2025-11-27 | 2025-12-07 | 2025-12-18 | 2025-12-25 | 10 | Marginal | Ranveer Yadav | 242858
ST01192 | PRJ015 | CL003 | State Bank of India | Chennai Site-011 | Chennai | South | 200 | Pending Acceptance | 2025-10-26 | 2025-11-16 | 2025-11-14 | 2025-12-02 | 2025-12-08 | 0 | Met | Ekavir Varkey | 243382
ST01193 | PRJ015 | CL003 | State Bank of India | Chennai Site-012 | Chennai | South | 10 | Installation Done | 2025-11-07 | 2025-12-01 | 2025-12-02 | 2025-12-13 |  | 12 | Marginal | Girik Khalsa | 268401
ST01194 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-013 | Hyderabad | South | 20 | ROW In Progress | 2025-10-26 | 2025-12-19 |  | 2026-01-09 |  | 6 | Met | Faqid Savant | 72164
ST01195 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-014 | Hyderabad | South | 10 | Testing | 2025-10-18 | 2025-11-27 | 2025-11-29 | 2025-12-21 |  | 12 | Marginal | Raksha Varughese | 188651
ST01196 | PRJ015 | CL003 | State Bank of India | Chennai Site-015 | Chennai | South | 20 | Live | 2025-10-24 | 2025-11-14 | 2025-11-24 | 2025-12-01 | 2025-12-05 | 10 | Marginal | Alka Wable | 160436
ST01197 | PRJ015 | CL003 | State Bank of India | Chennai Site-016 | Chennai | South | 100 | ROW In Progress | 2025-10-25 | 2025-11-29 |  | 2025-12-09 |  | 7 | Met | Tanay Rattan | 190836
ST01198 | PRJ015 | CL003 | State Bank of India | Chennai Site-017 | Chennai | South | 200 | Installation Done | 2025-11-01 | 2025-12-28 | 2026-01-04 | 2026-01-27 |  | 12 | Marginal | Faqid Savant | 240767
ST01199 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-018 | Hyderabad | South | 20 | Live | 2025-10-27 | 2025-12-02 | 2025-12-10 | 2025-12-23 | 2025-12-31 | 8 | Marginal | Urvashi Ray | 186654
ST01200 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-019 | Hyderabad | South | 200 | Survey Pending | 2025-11-07 | 2025-12-05 |  | 2025-12-25 |  | 3 | Met | Harini Choudhury | 70328
ST01201 | PRJ015 | CL003 | State Bank of India | Kochi Site-020 | Kochi | South | 200 | Testing | 2025-10-19 | 2025-12-16 | 2025-12-18 | 2026-01-06 |  | 12 | Marginal | Alka Wable | 166972
ST01202 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-021 | Hyderabad | South | 200 | Testing | 2025-10-17 | 2025-12-05 | 2025-12-14 | 2025-12-30 |  | 12 | Marginal | Madhavi Lanka | 61949
ST01203 | PRJ015 | CL003 | State Bank of India | Chennai Site-022 | Chennai | South | 50 | Survey Pending | 2025-10-30 | 2025-12-24 |  | 2026-01-23 |  | 0 | Met | Dakshesh Trivedi | 272430
ST01204 | PRJ015 | CL003 | State Bank of India | Chennai Site-023 | Chennai | South | 10 | Survey Pending | 2025-10-27 | 2025-11-20 |  | 2025-12-08 |  | 4 | Met | Quincy Biswas | 157939
ST01205 | PRJ015 | CL003 | State Bank of India | Chennai Site-024 | Chennai | South | 50 | Pending Acceptance | 2025-10-22 | 2025-12-09 | 2025-12-13 | 2026-01-05 | 2026-01-11 | 4 | Met | Siddharth Zacharia | 194384
ST01206 | PRJ015 | CL003 | State Bank of India | Kochi Site-025 | Kochi | South | 200 | ROW In Progress | 2025-11-02 | 2025-12-29 |  | 2026-01-18 |  | 0 | Met | Simon Tata | 231676
ST01207 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-026 | Hyderabad | South | 100 | Testing | 2025-11-09 | 2025-12-03 | 2025-11-30 | 2025-12-29 |  | 12 | Marginal | Yashica Issac | 237035
ST01208 | PRJ015 | CL003 | State Bank of India | Chennai Site-027 | Chennai | South | 10 | Installation Scheduled | 2025-11-04 | 2025-12-05 | 2025-12-05 | 2025-12-15 |  | 7 | Met | Irya Sampath | 68358
ST01209 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-028 | Bengaluru | South | 20 | Pending Acceptance | 2025-11-03 | 2025-12-17 | 2025-12-25 | 2026-01-08 | 2026-01-20 | 8 | Marginal | Unni Bhagat | 92969
ST01210 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-029 | Bengaluru | South | 20 | Installation Scheduled | 2025-10-21 | 2025-12-07 | 2025-12-10 | 2026-01-01 |  | 1 | Met | Devansh Nigam | 150231
ST01211 | PRJ015 | CL003 | State Bank of India | Chennai Site-030 | Chennai | South | 10 | Installation Scheduled | 2025-11-05 | 2026-01-04 | 2026-01-01 | 2026-01-24 |  | 7 | Met | Jai Kota | 50347
ST01212 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-031 | Bengaluru | South | 200 | Pending Acceptance | 2025-10-17 | 2025-11-29 | 2025-11-27 | 2025-12-14 | 2025-12-11 | 0 | Met | Nihal Shere | 46221
ST01213 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-032 | Hyderabad | South | 20 | Installation Done | 2025-10-16 | 2025-12-11 | 2025-12-17 | 2025-12-23 |  | 12 | Marginal | Wriddhish Bhardwaj | 211849
ST01214 | PRJ015 | CL003 | State Bank of India | Kochi Site-033 | Kochi | South | 200 | ROW In Progress | 2025-10-22 | 2025-12-03 |  | 2025-12-16 |  | 2 | Met | Logan Sami | 195466
ST01215 | PRJ015 | CL003 | State Bank of India | Chennai Site-034 | Chennai | South | 200 | Live | 2025-11-07 | 2025-12-08 | 2025-12-07 | 2026-01-01 | 2025-12-29 | 0 | Met | Diya Rattan | 185925
ST01216 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-035 | Bengaluru | South | 200 | Live | 2025-10-25 | 2025-12-02 | 2025-11-30 | 2025-12-23 | 2025-12-25 | 0 | Met | Kashvi Edwin | 71141
ST01217 | PRJ015 | CL003 | State Bank of India | Kochi Site-036 | Kochi | South | 200 | ROW In Progress | 2025-10-20 | 2025-12-18 |  | 2026-01-07 |  | 7 | Met | Faqid Savant | 250537
ST01218 | PRJ015 | CL003 | State Bank of India | Kochi Site-037 | Kochi | South | 50 | Pending Acceptance | 2025-11-06 | 2025-12-31 | 2025-12-28 | 2026-01-20 | 2026-01-24 | 0 | Met | Aarush Lall | 107770
ST01219 | PRJ015 | CL003 | State Bank of India | Kochi Site-038 | Kochi | South | 100 | ROW In Progress | 2025-10-28 | 2025-11-19 |  | 2025-12-10 |  | 0 | Met | Michael Dutta | 267238
ST01220 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-039 | Bengaluru | South | 50 | Live | 2025-10-26 | 2025-12-18 | 2025-12-25 | 2026-01-14 | 2026-01-17 | 7 | Met | Girindra Chatterjee | 80514
ST01221 | PRJ015 | CL003 | State Bank of India | Kochi Site-040 | Kochi | South | 100 | Live | 2025-10-25 | 2025-12-24 | 2026-01-01 | 2026-01-15 | 2026-01-25 | 8 | Marginal | Theodore Devi | 173572
ST01222 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-041 | Bengaluru | South | 100 | Installation Done | 2025-10-26 | 2025-12-20 | 2025-12-30 | 2026-01-18 |  | 12 | Marginal | Kevin Solanki | 175446
ST01223 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-042 | Hyderabad | South | 50 | Live | 2025-11-07 | 2025-11-30 | 2025-11-26 | 2025-12-16 | 2025-12-15 | 0 | Met | Ekiya Suresh | 213016
ST01224 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-043 | Hyderabad | South | 20 | Live | 2025-11-02 | 2025-11-23 | 2025-11-19 | 2025-12-12 | 2025-12-21 | 0 | Met | Ikbal Kothari | 185971
ST01225 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-044 | Bengaluru | South | 10 | Live | 2025-11-06 | 2025-12-23 | 2025-12-23 | 2026-01-18 | 2026-01-26 | 0 | Met | Kabir Soman | 70860
ST01226 | PRJ015 | CL003 | State Bank of India | Kochi Site-045 | Kochi | South | 20 | Pending Acceptance | 2025-10-23 | 2025-12-02 | 2025-11-29 | 2025-12-18 | 2025-12-30 | 0 | Met | Nihal Shere | 56857
ST01227 | PRJ015 | CL003 | State Bank of India | Kochi Site-046 | Kochi | South | 50 | Installation Scheduled | 2025-11-07 | 2025-12-04 | 2025-12-08 | 2025-12-14 |  | 3 | Met | Ekiya Suresh | 147214
ST01228 | PRJ015 | CL003 | State Bank of India | Chennai Site-047 | Chennai | South | 200 | Installation Done | 2025-10-28 | 2025-11-19 | 2025-11-18 | 2025-12-03 |  | 12 | Marginal | Raksha Varughese | 207991
ST01229 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-048 | Hyderabad | South | 100 | Live | 2025-10-29 | 2025-12-24 | 2025-12-28 | 2026-01-09 | 2026-01-14 | 4 | Met | Nihal Shere | 154022
ST01230 | PRJ015 | CL003 | State Bank of India | Kochi Site-049 | Kochi | South | 10 | Installation Done | 2025-10-22 | 2025-12-12 | 2025-12-15 | 2026-01-10 |  | 12 | Marginal | Chandresh Zachariah | 55957
ST01231 | PRJ015 | CL003 | State Bank of India | Kochi Site-050 | Kochi | South | 10 | ROW In Progress | 2025-11-07 | 2025-12-11 |  | 2025-12-23 |  | 1 | Met | Yashica Issac | 252405
ST01232 | PRJ015 | CL003 | State Bank of India | Kochi Site-051 | Kochi | South | 100 | Survey Pending | 2025-11-02 | 2025-12-12 |  | 2025-12-27 |  | 4 | Met | Ekansh Balay | 185577
ST01233 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-052 | Hyderabad | South | 20 | Installation Scheduled | 2025-11-03 | 2025-12-09 | 2025-12-07 | 2025-12-22 |  | 6 | Met | Gavin Batta | 190424
ST01234 | PRJ015 | CL003 | State Bank of India | Kochi Site-053 | Kochi | South | 10 | Installation Scheduled | 2025-11-01 | 2025-11-23 | 2025-12-03 | 2025-12-18 |  | 1 | Met | Siddharth Zacharia | 54969
ST01235 | PRJ015 | CL003 | State Bank of India | Kochi Site-054 | Kochi | South | 200 | ROW In Progress | 2025-11-09 | 2025-12-03 |  | 2025-12-20 |  | 6 | Met | Logan Sami | 159847
ST01236 | PRJ015 | CL003 | State Bank of India | Chennai Site-055 | Chennai | South | 50 | Installation Done | 2025-11-09 | 2025-12-01 | 2025-12-02 | 2025-12-17 |  | 12 | Marginal | Dominic Kakar | 194107
ST01237 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-056 | Bengaluru | South | 20 | Pending Acceptance | 2025-10-26 | 2025-12-01 | 2025-12-01 | 2025-12-22 | 2026-01-02 | 0 | Met | Tara Dhar | 147580
ST01238 | PRJ015 | CL003 | State Bank of India | Kochi Site-057 | Kochi | South | 20 | ROW In Progress | 2025-10-25 | 2025-12-16 |  | 2025-12-28 |  | 3 | Met | Wriddhish Bhardwaj | 133051
ST01239 | PRJ015 | CL003 | State Bank of India | Kochi Site-058 | Kochi | South | 50 | Survey Pending | 2025-10-30 | 2025-11-23 |  | 2025-12-10 |  | 8 | Marginal | Yashica Issac | 82581
ST01240 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-059 | Hyderabad | South | 200 | Survey Pending | 2025-11-06 | 2025-11-30 |  | 2025-12-23 |  | 8 | Marginal | Anamika Kanda | 207158
ST01241 | PRJ015 | CL003 | State Bank of India | Chennai Site-060 | Chennai | South | 20 | Live | 2025-10-26 | 2025-12-08 | 2025-12-04 | 2025-12-22 | 2025-12-22 | 0 | Met | Ekbal Garg | 144932
ST01242 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-061 | Bengaluru | South | 10 | Testing | 2025-10-28 | 2025-12-23 | 2025-12-21 | 2026-01-09 |  | 12 | Marginal | Priya Rastogi | 50188
ST01243 | PRJ015 | CL003 | State Bank of India | Kochi Site-062 | Kochi | South | 100 | Pending Acceptance | 2025-11-05 | 2025-12-19 | 2025-12-23 | 2026-01-17 | 2026-01-26 | 4 | Met | Devika Rastogi | 224013
ST01244 | PRJ015 | CL003 | State Bank of India | Kochi Site-063 | Kochi | South | 20 | Testing | 2025-10-27 | 2025-12-26 | 2026-01-04 | 2026-01-20 |  | 12 | Marginal | Teerth Bhardwaj | 185628
ST01245 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-064 | Hyderabad | South | 20 | Installation Scheduled | 2025-10-25 | 2025-12-24 | 2025-12-24 | 2026-01-15 |  | 4 | Met | Logan Sami | 238988
ST01246 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-065 | Bengaluru | South | 100 | Installation Done | 2025-10-25 | 2025-11-23 | 2025-11-19 | 2025-12-17 |  | 12 | Marginal | Siddharth Zacharia | 150442
ST01247 | PRJ015 | CL003 | State Bank of India | Chennai Site-066 | Chennai | South | 100 | Live | 2025-10-27 | 2025-11-29 | 2025-12-06 | 2025-12-22 | 2026-01-01 | 7 | Met | Mohammed Gupta | 161363
ST01248 | PRJ015 | CL003 | State Bank of India | Kochi Site-067 | Kochi | South | 200 | Installation Done | 2025-10-26 | 2025-12-05 | 2025-12-12 | 2025-12-19 |  | 12 | Marginal | Ekapad Walia | 109489
ST01249 | PRJ015 | CL003 | State Bank of India | Chennai Site-068 | Chennai | South | 50 | Live | 2025-11-03 | 2025-12-05 | 2025-12-11 | 2025-12-29 | 2026-01-08 | 6 | Met | Kevin Solanki | 100971
ST01250 | PRJ015 | CL003 | State Bank of India | Kochi Site-069 | Kochi | South | 50 | ROW In Progress | 2025-10-19 | 2025-12-12 |  | 2026-01-11 |  | 7 | Met | Niharika Sunder | 58339
ST01251 | PRJ015 | CL003 | State Bank of India | Chennai Site-070 | Chennai | South | 20 | Installation Scheduled | 2025-11-02 | 2025-12-02 | 2025-12-09 | 2025-12-28 |  | 6 | Met | Bhavika Sampath | 51248
ST01252 | PRJ015 | CL003 | State Bank of India | Chennai Site-071 | Chennai | South | 20 | Installation Done | 2025-11-06 | 2025-12-07 | 2025-12-10 | 2026-01-04 |  | 12 | Marginal | Girik Khalsa | 195750
ST01253 | PRJ015 | CL003 | State Bank of India | Chennai Site-072 | Chennai | South | 100 | ROW In Progress | 2025-10-26 | 2025-12-14 |  | 2025-12-31 |  | 2 | Met | Urvashi Ray | 205001
ST01254 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-073 | Bengaluru | South | 10 | Live | 2025-11-10 | 2025-12-04 | 2025-12-01 | 2025-12-14 | 2025-12-11 | 0 | Met | Irya Sampath | 268504
ST01255 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-074 | Bengaluru | South | 10 | Installation Scheduled | 2025-10-27 | 2025-11-28 | 2025-11-27 | 2025-12-14 |  | 4 | Met | Ranveer Yadav | 208376
ST01256 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-075 | Hyderabad | South | 50 | Testing | 2025-10-30 | 2025-12-19 | 2025-12-24 | 2026-01-03 |  | 12 | Marginal | Arya Sunder | 71607
ST01257 | PRJ015 | CL003 | State Bank of India | Chennai Site-076 | Chennai | South | 20 | Live | 2025-10-20 | 2025-11-19 | 2025-11-27 | 2025-12-02 | 2025-12-12 | 8 | Marginal | Vansha Thakkar | 228464
ST01258 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-077 | Hyderabad | South | 10 | Live | 2025-10-23 | 2025-11-19 | 2025-11-18 | 2025-12-13 | 2025-12-13 | 0 | Met | Radhika Dugar | 275747
ST01259 | PRJ015 | CL003 | State Bank of India | Kochi Site-078 | Kochi | South | 50 | Installation Done | 2025-10-31 | 2025-11-30 | 2025-11-25 | 2025-12-28 |  | 12 | Marginal | Bhavika Sampath | 198325
ST01260 | PRJ015 | CL003 | State Bank of India | Chennai Site-079 | Chennai | South | 10 | Installation Done | 2025-10-16 | 2025-12-06 | 2025-12-12 | 2025-12-26 |  | 12 | Marginal | Logan Sami | 63059
ST01261 | PRJ015 | CL003 | State Bank of India | Chennai Site-080 | Chennai | South | 20 | ROW In Progress | 2025-10-25 | 2025-12-09 |  | 2025-12-23 |  | 1 | Met | Girindra Chatterjee | 121637
ST01262 | PRJ015 | CL003 | State Bank of India | Bengaluru Site-081 | Bengaluru | South | 200 | Installation Done | 2025-11-10 | 2025-12-31 | 2025-12-26 | 2026-01-29 |  | 12 | Marginal | Tanay Rattan | 89318
ST01263 | PRJ015 | CL003 | State Bank of India | Hyderabad Site-082 | Hyderabad | South | 100 | Live | 2025-10-22 | 2025-12-13 | 2025-12-16 | 2026-01-08 | 2026-01-05 | 3 | Met | Urvashi Ray | 88747
ST01264 | PRJ016 | CL004 | Bajaj Finance | Surat Site-001 | Surat | West | 100 | ROW In Progress | 2025-08-06 | 2025-09-07 |  | 2025-09-17 |  | 7 | Met | Yashica Issac | 124566
ST01265 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-002 | Ahmedabad | West | 20 | Installation Scheduled | 2025-08-11 | 2025-10-08 | 2025-10-18 | 2025-10-31 |  | 6 | Met | Quincy Biswas | 219532
ST01266 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-003 | Mumbai | West | 200 | Installation Done | 2025-07-30 | 2025-08-23 | 2025-08-28 | 2025-09-17 |  | 12 | Marginal | Ekavir Varkey | 82087
ST01267 | PRJ016 | CL004 | Bajaj Finance | Pune Site-004 | Pune | West | 10 | Installation Done | 2025-08-11 | 2025-09-13 | 2025-09-21 | 2025-10-08 |  | 12 | Marginal | Kevin Solanki | 210546
ST01268 | PRJ016 | CL004 | Bajaj Finance | Pune Site-005 | Pune | West | 200 | Installation Scheduled | 2025-08-05 | 2025-10-03 | 2025-10-11 | 2025-11-01 |  | 1 | Met | Harini Choudhury | 183841
ST01269 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-006 | Ahmedabad | West | 10 | Installation Scheduled | 2025-08-07 | 2025-09-04 | 2025-09-10 | 2025-10-02 |  | 7 | Met | Anamika Kanda | 162198
ST01270 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-007 | Ahmedabad | West | 100 | Installation Done | 2025-08-02 | 2025-09-11 | 2025-09-13 | 2025-10-01 |  | 12 | Marginal | Ekavir Bhargava | 190488
ST01271 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-008 | Ahmedabad | West | 200 | Testing | 2025-08-06 | 2025-09-07 | 2025-09-06 | 2025-09-27 |  | 12 | Marginal | Siddharth Zacharia | 230625
ST01272 | PRJ016 | CL004 | Bajaj Finance | Pune Site-009 | Pune | West | 200 | Live | 2025-08-03 | 2025-09-23 | 2025-10-03 | 2025-10-03 | 2025-10-10 | 10 | Marginal | Michael Dutta | 145700
ST01273 | PRJ016 | CL004 | Bajaj Finance | Pune Site-010 | Pune | West | 200 | Testing | 2025-07-29 | 2025-09-20 | 2025-09-30 | 2025-10-14 |  | 12 | Marginal | Victor Kannan | 62544
ST01274 | PRJ016 | CL004 | Bajaj Finance | Surat Site-011 | Surat | West | 10 | Installation Done | 2025-08-02 | 2025-09-08 | 2025-09-07 | 2025-09-29 |  | 12 | Marginal | Vansha Thakkar | 109640
ST01275 | PRJ016 | CL004 | Bajaj Finance | Pune Site-012 | Pune | West | 50 | Live | 2025-08-06 | 2025-09-17 | 2025-09-27 | 2025-10-14 | 2025-10-15 | 10 | Marginal | Urvashi Ray | 172060
ST01276 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-013 | Ahmedabad | West | 200 | Testing | 2025-08-13 | 2025-09-14 | 2025-09-15 | 2025-10-13 |  | 12 | Marginal | Advay Contractor | 122494
ST01277 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-014 | Mumbai | West | 100 | Live | 2025-08-02 | 2025-09-24 | 2025-09-28 | 2025-10-11 | 2025-10-20 | 4 | Met | Nihal Shere | 123165
ST01278 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-015 | Ahmedabad | West | 10 | Installation Scheduled | 2025-08-05 | 2025-08-26 | 2025-08-21 | 2025-09-25 |  | 6 | Met | Logan Sami | 166881
ST01279 | PRJ016 | CL004 | Bajaj Finance | Pune Site-016 | Pune | West | 100 | Installation Done | 2025-08-08 | 2025-10-02 | 2025-10-02 | 2025-10-31 |  | 12 | Marginal | Urvashi Ray | 73244
ST01280 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-017 | Ahmedabad | West | 20 | Installation Done | 2025-08-02 | 2025-09-29 | 2025-10-08 | 2025-10-18 |  | 12 | Marginal | Harini Choudhury | 129621
ST01281 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-018 | Mumbai | West | 20 | ROW In Progress | 2025-08-06 | 2025-09-30 |  | 2025-10-25 |  | 5 | Met | Urvashi Ray | 263052
ST01282 | PRJ016 | CL004 | Bajaj Finance | Surat Site-019 | Surat | West | 20 | Testing | 2025-08-16 | 2025-10-02 | 2025-10-07 | 2025-10-24 |  | 12 | Marginal | Girindra Chatterjee | 205715
ST01283 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-020 | Mumbai | West | 20 | Live | 2025-08-06 | 2025-10-01 | 2025-09-27 | 2025-10-27 | 2025-10-25 | 0 | Met | Wahab Raval | 61745
ST01284 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-021 | Mumbai | West | 10 | ROW In Progress | 2025-07-30 | 2025-09-21 |  | 2025-10-06 |  | 3 | Met | Ranveer Yadav | 138606
ST01285 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-022 | Ahmedabad | West | 200 | ROW In Progress | 2025-08-06 | 2025-08-30 |  | 2025-09-24 |  | 6 | Met | Tara Dhar | 182541
ST01286 | PRJ016 | CL004 | Bajaj Finance | Surat Site-023 | Surat | West | 20 | Live | 2025-08-08 | 2025-09-06 | 2025-09-03 | 2025-09-22 | 2025-10-03 | 0 | Met | Upadhriti Wadhwa | 244954
ST01287 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-024 | Ahmedabad | West | 100 | Installation Scheduled | 2025-07-28 | 2025-09-21 | 2025-09-16 | 2025-10-02 |  | 3 | Met | Dominic Kakar | 56056
ST01288 | PRJ016 | CL004 | Bajaj Finance | Pune Site-025 | Pune | West | 100 | Live | 2025-07-31 | 2025-08-28 | 2025-09-02 | 2025-09-17 | 2025-09-26 | 5 | Met | Anamika Kanda | 178758
ST01289 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-026 | Ahmedabad | West | 20 | Installation Done | 2025-08-17 | 2025-10-02 | 2025-09-29 | 2025-10-13 |  | 12 | Marginal | Diya Rattan | 99745
ST01290 | PRJ016 | CL004 | Bajaj Finance | Pune Site-027 | Pune | West | 50 | Testing | 2025-07-27 | 2025-09-07 | 2025-09-04 | 2025-10-05 |  | 12 | Marginal | Kashvi Edwin | 149118
ST01291 | PRJ016 | CL004 | Bajaj Finance | Pune Site-028 | Pune | West | 50 | ROW In Progress | 2025-07-27 | 2025-09-25 |  | 2025-10-24 |  | 4 | Met | Logan Sami | 178924
ST01292 | PRJ016 | CL004 | Bajaj Finance | Surat Site-029 | Surat | West | 20 | ROW In Progress | 2025-08-02 | 2025-09-29 |  | 2025-10-17 |  | 5 | Met | Girindra Chatterjee | 113247
ST01293 | PRJ016 | CL004 | Bajaj Finance | Surat Site-030 | Surat | West | 200 | ROW In Progress | 2025-08-05 | 2025-09-22 |  | 2025-10-02 |  | 7 | Met | Girik Khalsa | 98632
ST01294 | PRJ016 | CL004 | Bajaj Finance | Pune Site-031 | Pune | West | 200 | ROW In Progress | 2025-08-08 | 2025-09-03 |  | 2025-09-19 |  | 3 | Met | Arya Sunder | 263347
ST01295 | PRJ016 | CL004 | Bajaj Finance | Pune Site-032 | Pune | West | 200 | Live | 2025-08-05 | 2025-09-17 | 2025-09-26 | 2025-09-28 | 2025-10-02 | 9 | Marginal | Jai Kota | 101834
ST01296 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-033 | Mumbai | West | 100 | Installation Scheduled | 2025-08-02 | 2025-09-02 | 2025-09-07 | 2025-09-18 |  | 7 | Met | Girindra Chatterjee | 165031
ST01297 | PRJ016 | CL004 | Bajaj Finance | Surat Site-034 | Surat | West | 200 | Testing | 2025-08-01 | 2025-09-21 | 2025-10-01 | 2025-10-18 |  | 12 | Marginal | Ekansh Balay | 253405
ST01298 | PRJ016 | CL004 | Bajaj Finance | Pune Site-035 | Pune | West | 10 | Survey Pending | 2025-07-30 | 2025-08-19 |  | 2025-08-29 |  | 0 | Met | Ekavir Bhargava | 45002
ST01299 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-036 | Ahmedabad | West | 10 | Installation Done | 2025-08-19 | 2025-10-14 | 2025-10-14 | 2025-10-27 |  | 12 | Marginal | Logan Sami | 101441
ST01300 | PRJ016 | CL004 | Bajaj Finance | Pune Site-037 | Pune | West | 10 | Pending Acceptance | 2025-08-19 | 2025-10-01 | 2025-09-28 | 2025-10-19 | 2025-10-29 | 0 | Met | Arya Sunder | 246967
ST01301 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-038 | Mumbai | West | 10 | Live | 2025-08-05 | 2025-09-03 | 2025-09-06 | 2025-09-27 | 2025-09-30 | 3 | Met | Daksh Karnik | 275762
ST01302 | PRJ016 | CL004 | Bajaj Finance | Surat Site-039 | Surat | West | 200 | ROW In Progress | 2025-07-30 | 2025-08-24 |  | 2025-09-10 |  | 7 | Met | Victor Kannan | 115796
ST01303 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-040 | Mumbai | West | 100 | Live | 2025-08-11 | 2025-09-04 | 2025-09-03 | 2025-09-20 | 2025-09-19 | 0 | Met | Arya Shere | 52837
ST01304 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-041 | Mumbai | West | 200 | Installation Done | 2025-08-10 | 2025-09-25 | 2025-09-25 | 2025-10-05 |  | 12 | Marginal | Dominic Kakar | 217126
ST01305 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-042 | Mumbai | West | 10 | Pending Acceptance | 2025-08-04 | 2025-09-11 | 2025-09-21 | 2025-09-27 | 2025-10-02 | 10 | Marginal | Victor Kannan | 273587
ST01306 | PRJ016 | CL004 | Bajaj Finance | Pune Site-043 | Pune | West | 200 | Installation Scheduled | 2025-08-10 | 2025-08-30 | 2025-08-26 | 2025-09-27 |  | 6 | Met | Quincy Biswas | 252608
ST01307 | PRJ016 | CL004 | Bajaj Finance | Pune Site-044 | Pune | West | 200 | Live | 2025-08-19 | 2025-09-11 | 2025-09-15 | 2025-10-02 | 2025-10-01 | 4 | Met | Logan Sami | 164605
ST01308 | PRJ016 | CL004 | Bajaj Finance | Surat Site-045 | Surat | West | 50 | Testing | 2025-08-07 | 2025-09-19 | 2025-09-18 | 2025-10-09 |  | 12 | Marginal | Niharika Sunder | 90603
ST01309 | PRJ016 | CL004 | Bajaj Finance | Surat Site-046 | Surat | West | 200 | Installation Done | 2025-08-07 | 2025-09-14 | 2025-09-13 | 2025-10-09 |  | 12 | Marginal | Niharika Sunder | 139458
ST01310 | PRJ016 | CL004 | Bajaj Finance | Surat Site-047 | Surat | West | 100 | ROW In Progress | 2025-08-04 | 2025-09-01 |  | 2025-09-21 |  | 5 | Met | Mohammed Gupta | 242578
ST01311 | PRJ016 | CL004 | Bajaj Finance | Pune Site-048 | Pune | West | 200 | Live | 2025-08-06 | 2025-09-27 | 2025-09-26 | 2025-10-26 | 2025-11-02 | 0 | Met | Yashica Issac | 268110
ST01312 | PRJ016 | CL004 | Bajaj Finance | Pune Site-049 | Pune | West | 10 | Pending Acceptance | 2025-08-21 | 2025-09-23 | 2025-09-30 | 2025-10-05 | 2025-10-15 | 7 | Met | Yatin Baral | 187605
ST01313 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-050 | Mumbai | West | 20 | Installation Done | 2025-08-14 | 2025-09-03 | 2025-09-06 | 2025-09-30 |  | 12 | Marginal | Siddharth Zacharia | 224309
ST01314 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-051 | Ahmedabad | West | 100 | Installation Done | 2025-08-06 | 2025-09-18 | 2025-09-25 | 2025-10-14 |  | 12 | Marginal | Alka Wable | 196262
ST01315 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-052 | Ahmedabad | West | 20 | Live | 2025-08-18 | 2025-09-13 | 2025-09-15 | 2025-10-13 | 2025-10-24 | 2 | Met | Wriddhish Bhardwaj | 232748
ST01316 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-053 | Mumbai | West | 50 | Live | 2025-08-12 | 2025-09-07 | 2025-09-17 | 2025-09-21 | 2025-09-20 | 10 | Marginal | Devika Rastogi | 243128
ST01317 | PRJ016 | CL004 | Bajaj Finance | Surat Site-054 | Surat | West | 10 | Installation Scheduled | 2025-08-02 | 2025-09-25 | 2025-09-23 | 2025-10-11 |  | 0 | Met | Daksh Karnik | 122538
ST01318 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-055 | Mumbai | West | 10 | Installation Scheduled | 2025-08-20 | 2025-09-13 | 2025-09-10 | 2025-10-01 |  | 7 | Met | Nitesh Raghavan | 138720
ST01319 | PRJ016 | CL004 | Bajaj Finance | Surat Site-056 | Surat | West | 50 | Survey Pending | 2025-08-15 | 2025-09-23 |  | 2025-10-13 |  | 6 | Met | Ekapad Walia | 124635
ST01320 | PRJ016 | CL004 | Bajaj Finance | Surat Site-057 | Surat | West | 10 | Testing | 2025-08-11 | 2025-10-10 | 2025-10-06 | 2025-11-04 |  | 12 | Marginal | Wahab Raval | 128789
ST01321 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-058 | Ahmedabad | West | 10 | Survey Pending | 2025-08-18 | 2025-10-07 |  | 2025-10-29 |  | 8 | Marginal | Nitesh Raghavan | 225510
ST01322 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-059 | Ahmedabad | West | 100 | Pending Acceptance | 2025-08-17 | 2025-10-07 | 2025-10-02 | 2025-10-29 | 2025-10-27 | 0 | Met | Gavin Batta | 169484
ST01323 | PRJ016 | CL004 | Bajaj Finance | Ahmedabad Site-060 | Ahmedabad | West | 100 | Testing | 2025-07-29 | 2025-09-02 | 2025-08-31 | 2025-09-26 |  | 12 | Marginal | Unni Bhagat | 108275
ST01324 | PRJ016 | CL004 | Bajaj Finance | Surat Site-061 | Surat | West | 200 | Survey Pending | 2025-08-05 | 2025-09-29 |  | 2025-10-23 |  | 3 | Met | Niharika Sunder | 69891
ST01325 | PRJ016 | CL004 | Bajaj Finance | Mumbai Site-062 | Mumbai | West | 100 | Live | 2025-08-14 | 2025-09-04 | 2025-09-13 | 2025-09-16 | 2025-09-18 | 9 | Marginal | Ekavir Bhargava | 227748
ST01326 | PRJ016 | CL004 | Bajaj Finance | Surat Site-063 | Surat | West | 200 | Live | 2025-08-13 | 2025-09-05 | 2025-09-08 | 2025-10-03 | 2025-10-03 | 3 | Met | Quincy Biswas | 90591
ST01327 | PRJ016 | CL004 | Bajaj Finance | Surat Site-064 | Surat | West | 100 | Installation Scheduled | 2025-08-01 | 2025-08-23 | 2025-08-27 | 2025-09-21 |  | 5 | Met | Upadhriti Wadhwa | 225042
ST01328 | PRJ016 | CL004 | Bajaj Finance | Pune Site-065 | Pune | West | 10 | Pending Acceptance | 2025-07-29 | 2025-08-30 | 2025-09-09 | 2025-09-24 | 2025-09-28 | 10 | Marginal | Faqid Savant | 248355
ST01329 | PRJ016 | CL004 | Bajaj Finance | Pune Site-066 | Pune | West | 200 | Live | 2025-07-28 | 2025-09-05 | 2025-09-05 | 2025-09-22 | 2025-09-29 | 0 | Met | Wahab Raval | 104960
ST01330 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-001 | Bhopal | Central | 50 | Installation Scheduled | 2025-10-18 | 2025-12-17 | 2025-12-22 | 2026-01-01 |  | 7 | Met | Raksha Varughese | 147663
ST01331 | PRJ017 | CL004 | Bajaj Finance | Indore Site-002 | Indore | Central | 200 | Live | 2025-10-11 | 2025-11-29 | 2025-12-04 | 2025-12-13 | 2025-12-18 | 5 | Met | Priya Rastogi | 111200
ST01332 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-003 | Bhopal | Central | 50 | Pending Acceptance | 2025-10-10 | 2025-11-24 | 2025-11-19 | 2025-12-06 | 2025-12-09 | 0 | Met | Wahab Raval | 164212
ST01333 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-004 | Nagpur | Central | 50 | Testing | 2025-10-01 | 2025-11-22 | 2025-11-30 | 2025-12-08 |  | 12 | Marginal | Simon Tata | 157120
ST01334 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-005 | Nagpur | Central | 50 | Pending Acceptance | 2025-10-12 | 2025-11-07 | 2025-11-17 | 2025-11-30 | 2025-12-09 | 10 | Marginal | Advay Contractor | 81628
ST01335 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-006 | Bhopal | Central | 50 | ROW In Progress | 2025-10-17 | 2025-11-09 |  | 2025-11-20 |  | 1 | Met | Devansh Rajan | 188783
ST01336 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-007 | Nagpur | Central | 200 | Installation Scheduled | 2025-10-18 | 2025-11-13 | 2025-11-21 | 2025-11-29 |  | 0 | Met | Tara Dhar | 47583
ST01337 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-008 | Bhopal | Central | 20 | Installation Scheduled | 2025-10-12 | 2025-11-18 | 2025-11-22 | 2025-12-11 |  | 3 | Met | Alka Wable | 207086
ST01338 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-009 | Nagpur | Central | 20 | Testing | 2025-10-01 | 2025-11-25 | 2025-12-01 | 2025-12-12 |  | 12 | Marginal | Anamika Kanda | 190151
ST01339 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-010 | Nagpur | Central | 200 | Installation Scheduled | 2025-09-30 | 2025-10-30 | 2025-11-06 | 2025-11-15 |  | 8 | Marginal | Anamika Kanda | 87046
ST01340 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-011 | Bhopal | Central | 10 | Testing | 2025-10-12 | 2025-11-18 | 2025-11-28 | 2025-12-01 |  | 12 | Marginal | Raksha Varughese | 266611
ST01341 | PRJ017 | CL004 | Bajaj Finance | Indore Site-012 | Indore | Central | 50 | Installation Scheduled | 2025-10-07 | 2025-12-05 | 2025-12-05 | 2025-12-20 |  | 3 | Met | Devansh Rajan | 45830
ST01342 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-013 | Bhopal | Central | 20 | Live | 2025-10-06 | 2025-12-02 | 2025-12-09 | 2025-12-26 | 2025-12-29 | 7 | Met | Michael Dutta | 267109
ST01343 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-014 | Bhopal | Central | 200 | Installation Done | 2025-10-07 | 2025-11-24 | 2025-11-23 | 2025-12-16 |  | 12 | Marginal | Arya Shere | 51036
ST01344 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-015 | Nagpur | Central | 50 | Live | 2025-09-29 | 2025-11-19 | 2025-11-27 | 2025-12-15 | 2025-12-22 | 8 | Marginal | Anamika Kanda | 175818
ST01345 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-016 | Nagpur | Central | 20 | Testing | 2025-10-07 | 2025-12-04 | 2025-12-05 | 2025-12-25 |  | 12 | Marginal | Priya Rastogi | 202536
ST01346 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-017 | Nagpur | Central | 50 | Live | 2025-09-28 | 2025-11-12 | 2025-11-13 | 2025-11-28 | 2025-12-05 | 1 | Met | Girik Khalsa | 116864
ST01347 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-018 | Bhopal | Central | 10 | Live | 2025-09-30 | 2025-11-13 | 2025-11-23 | 2025-11-23 | 2025-11-27 | 10 | Marginal | Mohammed Gupta | 231926
ST01348 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-019 | Bhopal | Central | 100 | Installation Done | 2025-10-04 | 2025-11-16 | 2025-11-23 | 2025-11-26 |  | 12 | Marginal | Madhavi Lanka | 234839
ST01349 | PRJ017 | CL004 | Bajaj Finance | Indore Site-020 | Indore | Central | 50 | Live | 2025-09-25 | 2025-11-11 | 2025-11-14 | 2025-12-02 | 2025-12-06 | 3 | Met | Ranveer Yadav | 113120
ST01350 | PRJ017 | CL004 | Bajaj Finance | Indore Site-021 | Indore | Central | 200 | ROW In Progress | 2025-09-30 | 2025-11-26 |  | 2025-12-26 |  | 8 | Marginal | Farhan Chada | 266748
ST01351 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-022 | Bhopal | Central | 10 | Pending Acceptance | 2025-10-04 | 2025-10-27 | 2025-10-29 | 2025-11-08 | 2025-11-10 | 2 | Met | Simon Tata | 110638
ST01352 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-023 | Bhopal | Central | 20 | Installation Done | 2025-10-01 | 2025-11-18 | 2025-11-17 | 2025-12-07 |  | 12 | Marginal | Madhavi Lanka | 118010
ST01353 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-024 | Bhopal | Central | 200 | Installation Scheduled | 2025-10-02 | 2025-11-01 | 2025-10-29 | 2025-11-18 |  | 1 | Met | Simon Tata | 195106
ST01354 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-025 | Nagpur | Central | 100 | Live | 2025-10-16 | 2025-11-16 | 2025-11-20 | 2025-12-13 | 2025-12-25 | 4 | Met | Kashvi Edwin | 106930
ST01355 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-026 | Bhopal | Central | 50 | Live | 2025-09-29 | 2025-11-26 | 2025-11-23 | 2025-12-08 | 2025-12-08 | 0 | Met | Ekiya Suresh | 184972
ST01356 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-027 | Bhopal | Central | 20 | Live | 2025-10-10 | 2025-11-22 | 2025-11-22 | 2025-12-06 | 2025-12-08 | 0 | Met | Nihal Shere | 130322
ST01357 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-028 | Bhopal | Central | 20 | Live | 2025-10-09 | 2025-10-30 | 2025-10-26 | 2025-11-21 | 2025-11-22 | 0 | Met | Simon Tata | 167963
ST01358 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-029 | Bhopal | Central | 100 | Live | 2025-09-30 | 2025-11-27 | 2025-12-03 | 2025-12-25 | 2025-12-30 | 6 | Met | Raksha Varughese | 164260
ST01359 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-030 | Bhopal | Central | 10 | Live | 2025-10-15 | 2025-11-19 | 2025-11-19 | 2025-12-19 | 2025-12-17 | 0 | Met | Arya Shere | 80626
ST01360 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-031 | Bhopal | Central | 100 | Installation Scheduled | 2025-10-09 | 2025-11-29 | 2025-12-06 | 2025-12-26 |  | 8 | Marginal | Dipta Bhandari | 214699
ST01361 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-032 | Nagpur | Central | 200 | Installation Done | 2025-10-12 | 2025-12-07 | 2025-12-14 | 2025-12-25 |  | 12 | Marginal | Niharika Sunder | 88750
ST01362 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-033 | Nagpur | Central | 50 | Live | 2025-09-27 | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-08 | 1 | Met | Upadhriti Wadhwa | 203438
ST01363 | PRJ017 | CL004 | Bajaj Finance | Indore Site-034 | Indore | Central | 100 | Installation Done | 2025-10-02 | 2025-11-14 | 2025-11-09 | 2025-12-04 |  | 12 | Marginal | Farhan Chada | 241689
ST01364 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-035 | Bhopal | Central | 50 | Installation Scheduled | 2025-10-17 | 2025-12-16 | 2025-12-15 | 2026-01-09 |  | 2 | Met | Chandresh Zachariah | 109092
ST01365 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-036 | Bhopal | Central | 100 | Survey Pending | 2025-09-30 | 2025-11-17 |  | 2025-12-05 |  | 7 | Met | Dipta Bhandari | 231879
ST01366 | PRJ017 | CL004 | Bajaj Finance | Indore Site-037 | Indore | Central | 10 | Installation Done | 2025-09-29 | 2025-11-17 | 2025-11-16 | 2025-12-10 |  | 12 | Marginal | Raksha Varughese | 83151
ST01367 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-038 | Nagpur | Central | 100 | Pending Acceptance | 2025-10-02 | 2025-11-14 | 2025-11-10 | 2025-12-05 | 2025-12-16 | 0 | Met | Madhavi Lanka | 65479
ST01368 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-039 | Nagpur | Central | 10 | Installation Scheduled | 2025-10-09 | 2025-12-03 | 2025-12-13 | 2025-12-14 |  | 7 | Met | Ikbal Kothari | 131888
ST01369 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-040 | Bhopal | Central | 200 | Installation Scheduled | 2025-10-09 | 2025-11-08 | 2025-11-03 | 2025-11-21 |  | 2 | Met | Victor Kannan | 60699
ST01370 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-041 | Bhopal | Central | 100 | Installation Done | 2025-10-13 | 2025-12-05 | 2025-12-11 | 2025-12-15 |  | 12 | Marginal | Girik Khalsa | 132566
ST01371 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-042 | Nagpur | Central | 10 | Installation Done | 2025-10-12 | 2025-11-21 | 2025-11-25 | 2025-12-12 |  | 12 | Marginal | Advay Contractor | 276612
ST01372 | PRJ017 | CL004 | Bajaj Finance | Indore Site-043 | Indore | Central | 20 | Live | 2025-10-06 | 2025-11-27 | 2025-11-23 | 2025-12-24 | 2025-12-23 | 0 | Met | Arya Shere | 131547
ST01373 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-044 | Nagpur | Central | 20 | Live | 2025-10-16 | 2025-12-15 | 2025-12-18 | 2025-12-29 | 2025-12-30 | 3 | Met | Gavin Batta | 206709
ST01374 | PRJ017 | CL004 | Bajaj Finance | Indore Site-045 | Indore | Central | 20 | Installation Scheduled | 2025-09-30 | 2025-10-22 | 2025-10-18 | 2025-11-10 |  | 0 | Met | Wriddhish Bhardwaj | 154674
ST01375 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-046 | Nagpur | Central | 200 | ROW In Progress | 2025-10-18 | 2025-11-16 |  | 2025-12-09 |  | 8 | Marginal | Jai Kota | 100211
ST01376 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-047 | Bhopal | Central | 20 | Pending Acceptance | 2025-09-28 | 2025-10-20 | 2025-10-23 | 2025-11-14 | 2025-11-13 | 3 | Met | Dipta Bhandari | 88412
ST01377 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-048 | Nagpur | Central | 50 | Installation Done | 2025-09-25 | 2025-11-13 | 2025-11-18 | 2025-12-12 |  | 12 | Marginal | Vansha Thakkar | 112655
ST01378 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-049 | Nagpur | Central | 20 | Testing | 2025-10-16 | 2025-11-26 | 2025-12-01 | 2025-12-22 |  | 12 | Marginal | Ekavir Bhargava | 256337
ST01379 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-050 | Nagpur | Central | 50 | Live | 2025-09-30 | 2025-11-03 | 2025-10-29 | 2025-11-26 | 2025-12-08 | 0 | Met | Irya Sampath | 178388
ST01380 | PRJ017 | CL004 | Bajaj Finance | Indore Site-051 | Indore | Central | 50 | Installation Done | 2025-10-16 | 2025-11-30 | 2025-11-26 | 2025-12-28 |  | 12 | Marginal | Jai Kota | 72917
ST01381 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-052 | Bhopal | Central | 20 | Testing | 2025-10-18 | 2025-11-21 | 2025-11-23 | 2025-12-15 |  | 12 | Marginal | Michael Dutta | 227814
ST01382 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-053 | Nagpur | Central | 50 | Installation Done | 2025-10-06 | 2025-11-20 | 2025-11-28 | 2025-12-18 |  | 12 | Marginal | Arya Sunder | 66267
ST01383 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-054 | Bhopal | Central | 100 | ROW In Progress | 2025-10-08 | 2025-11-01 |  | 2025-11-21 |  | 0 | Met | Girik Khalsa | 258663
ST01384 | PRJ017 | CL004 | Bajaj Finance | Indore Site-055 | Indore | Central | 10 | ROW In Progress | 2025-10-08 | 2025-10-29 |  | 2025-11-18 |  | 5 | Met | Kevin Solanki | 106782
ST01385 | PRJ017 | CL004 | Bajaj Finance | Indore Site-056 | Indore | Central | 20 | Live | 2025-10-08 | 2025-11-22 | 2025-11-23 | 2025-12-14 | 2025-12-24 | 1 | Met | Ekansh Balay | 108762
ST01386 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-057 | Nagpur | Central | 10 | Live | 2025-10-03 | 2025-11-02 | 2025-11-07 | 2025-11-30 | 2025-12-09 | 5 | Met | Michael Dutta | 66520
ST01387 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-058 | Bhopal | Central | 20 | Live | 2025-09-23 | 2025-10-22 | 2025-10-30 | 2025-11-16 | 2025-11-15 | 8 | Marginal | Simon Tata | 45547
ST01388 | PRJ017 | CL004 | Bajaj Finance | Indore Site-059 | Indore | Central | 200 | ROW In Progress | 2025-09-27 | 2025-11-04 |  | 2025-11-25 |  | 5 | Met | Gavin Batta | 55598
ST01389 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-060 | Bhopal | Central | 10 | Live | 2025-10-03 | 2025-10-29 | 2025-10-25 | 2025-11-26 | 2025-11-25 | 0 | Met | Ekbal Garg | 260332
ST01390 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-061 | Bhopal | Central | 200 | Live | 2025-10-05 | 2025-11-25 | 2025-11-23 | 2025-12-13 | 2025-12-19 | 0 | Met | Priya Rastogi | 263051
ST01391 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-062 | Nagpur | Central | 10 | Installation Scheduled | 2025-09-25 | 2025-11-13 | 2025-11-16 | 2025-11-28 |  | 8 | Marginal | Wahab Raval | 203986
ST01392 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-063 | Bhopal | Central | 100 | Live | 2025-09-24 | 2025-11-08 | 2025-11-13 | 2025-11-23 | 2025-12-05 | 5 | Met | Ikbal Kothari | 178398
ST01393 | PRJ017 | CL004 | Bajaj Finance | Indore Site-064 | Indore | Central | 50 | Installation Scheduled | 2025-10-15 | 2025-11-29 | 2025-12-07 | 2025-12-16 |  | 4 | Met | Ekapad Walia | 108093
ST01394 | PRJ017 | CL004 | Bajaj Finance | Indore Site-065 | Indore | Central | 200 | ROW In Progress | 2025-09-27 | 2025-10-19 |  | 2025-10-31 |  | 0 | Met | Advay Contractor | 83713
ST01395 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-066 | Bhopal | Central | 50 | Pending Acceptance | 2025-09-27 | 2025-10-26 | 2025-10-23 | 2025-11-14 | 2025-11-21 | 0 | Met | Devika Rastogi | 233387
ST01396 | PRJ017 | CL004 | Bajaj Finance | Indore Site-067 | Indore | Central | 100 | Installation Done | 2025-09-26 | 2025-11-20 | 2025-11-24 | 2025-12-06 |  | 12 | Marginal | Diya Rattan | 140475
ST01397 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-068 | Bhopal | Central | 50 | Installation Done | 2025-10-04 | 2025-10-28 | 2025-10-24 | 2025-11-08 |  | 12 | Marginal | Faqid Savant | 93906
ST01398 | PRJ017 | CL004 | Bajaj Finance | Indore Site-069 | Indore | Central | 50 | Installation Done | 2025-10-05 | 2025-11-14 | 2025-11-23 | 2025-11-28 |  | 12 | Marginal | Nitesh Raghavan | 217596
ST01399 | PRJ017 | CL004 | Bajaj Finance | Indore Site-070 | Indore | Central | 50 | Pending Acceptance | 2025-10-17 | 2025-12-12 | 2025-12-12 | 2025-12-22 | 2025-12-24 | 0 | Met | Tanay Rattan | 69436
ST01400 | PRJ017 | CL004 | Bajaj Finance | Indore Site-071 | Indore | Central | 200 | Live | 2025-10-03 | 2025-11-01 | 2025-10-28 | 2025-11-15 | 2025-11-19 | 0 | Met | Wahab Raval | 117839
ST01401 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-072 | Bhopal | Central | 50 | Live | 2025-10-06 | 2025-10-28 | 2025-10-23 | 2025-11-27 | 2025-12-05 | 0 | Met | Logan Sami | 133389
ST01402 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-073 | Bhopal | Central | 20 | ROW In Progress | 2025-10-17 | 2025-12-08 |  | 2025-12-24 |  | 3 | Met | Irya Sampath | 223351
ST01403 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-074 | Nagpur | Central | 200 | Live | 2025-10-16 | 2025-12-07 | 2025-12-10 | 2026-01-02 | 2026-01-11 | 3 | Met | Farhan Chada | 159016
ST01404 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-075 | Nagpur | Central | 10 | Live | 2025-10-07 | 2025-12-03 | 2025-12-07 | 2025-12-30 | 2026-01-10 | 4 | Met | Ekansh Balay | 132190
ST01405 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-076 | Bhopal | Central | 100 | Installation Done | 2025-10-13 | 2025-11-06 | 2025-11-16 | 2025-11-29 |  | 12 | Marginal | Siddharth Zacharia | 127622
ST01406 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-077 | Nagpur | Central | 100 | Installation Scheduled | 2025-10-01 | 2025-11-09 | 2025-11-05 | 2025-11-26 |  | 4 | Met | Devansh Nigam | 46123
ST01407 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-078 | Nagpur | Central | 100 | Installation Scheduled | 2025-09-30 | 2025-11-17 | 2025-11-19 | 2025-12-09 |  | 0 | Met | Simon Tata | 64950
ST01408 | PRJ017 | CL004 | Bajaj Finance | Indore Site-079 | Indore | Central | 50 | Testing | 2025-10-10 | 2025-11-25 | 2025-11-20 | 2025-12-21 |  | 12 | Marginal | Simon Tata | 175190
ST01409 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-080 | Nagpur | Central | 100 | Installation Scheduled | 2025-10-14 | 2025-12-08 | 2025-12-12 | 2025-12-21 |  | 3 | Met | Irya Sampath | 91461
ST01410 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-081 | Nagpur | Central | 100 | Live | 2025-09-23 | 2025-11-09 | 2025-11-06 | 2025-11-29 | 2025-12-03 | 0 | Met | Anamika Kanda | 71072
ST01411 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-082 | Bhopal | Central | 100 | Pending Acceptance | 2025-10-16 | 2025-11-21 | 2025-11-21 | 2025-12-10 | 2025-12-15 | 0 | Met | Yashica Issac | 156791
ST01412 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-083 | Bhopal | Central | 10 | Live | 2025-10-04 | 2025-10-30 | 2025-11-03 | 2025-11-18 | 2025-11-17 | 4 | Met | Yashica Cherian | 273909
ST01413 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-084 | Bhopal | Central | 10 | Live | 2025-09-23 | 2025-10-28 | 2025-10-25 | 2025-11-15 | 2025-11-17 | 0 | Met | Mohammed Gupta | 133481
ST01414 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-085 | Bhopal | Central | 10 | Installation Done | 2025-10-17 | 2025-12-10 | 2025-12-19 | 2026-01-05 |  | 12 | Marginal | Dakshesh Trivedi | 220111
ST01415 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-086 | Nagpur | Central | 100 | Installation Scheduled | 2025-09-25 | 2025-11-06 | 2025-11-03 | 2025-11-27 |  | 2 | Met | Wriddhish Bhardwaj | 187948
ST01416 | PRJ017 | CL004 | Bajaj Finance | Indore Site-087 | Indore | Central | 50 | Live | 2025-10-12 | 2025-11-06 | 2025-11-03 | 2025-11-21 | 2025-11-22 | 0 | Met | Yashica Issac | 181861
ST01417 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-088 | Nagpur | Central | 50 | Testing | 2025-10-08 | 2025-12-07 | 2025-12-13 | 2025-12-17 |  | 12 | Marginal | Faqid Savant | 252792
ST01418 | PRJ017 | CL004 | Bajaj Finance | Indore Site-089 | Indore | Central | 20 | ROW In Progress | 2025-10-09 | 2025-11-23 |  | 2025-12-09 |  | 2 | Met | Dakshesh Trivedi | 247758
ST01419 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-090 | Nagpur | Central | 100 | Live | 2025-09-25 | 2025-10-29 | 2025-11-08 | 2025-11-25 | 2025-12-06 | 10 | Marginal | Girindra Chatterjee | 213434
ST01420 | PRJ017 | CL004 | Bajaj Finance | Indore Site-091 | Indore | Central | 10 | ROW In Progress | 2025-09-24 | 2025-10-16 |  | 2025-11-09 |  | 3 | Met | Ikbal Kothari | 49488
ST01421 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-092 | Nagpur | Central | 100 | Pending Acceptance | 2025-10-13 | 2025-11-23 | 2025-12-01 | 2025-12-03 | 2025-12-10 | 8 | Marginal | Theodore Devi | 80148
ST01422 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-093 | Bhopal | Central | 100 | Testing | 2025-10-10 | 2025-11-06 | 2025-11-05 | 2025-12-01 |  | 12 | Marginal | Unni Bhagat | 76392
ST01423 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-094 | Nagpur | Central | 200 | Live | 2025-10-18 | 2025-12-17 | 2025-12-22 | 2026-01-03 | 2026-01-09 | 5 | Met | Nitesh Raghavan | 121926
ST01424 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-095 | Bhopal | Central | 20 | Live | 2025-09-24 | 2025-11-02 | 2025-11-01 | 2025-11-20 | 2025-11-29 | 0 | Met | Ekavir Bhargava | 134113
ST01425 | PRJ017 | CL004 | Bajaj Finance | Indore Site-096 | Indore | Central | 50 | Pending Acceptance | 2025-10-09 | 2025-11-21 | 2025-11-18 | 2025-12-16 | 2025-12-22 | 0 | Met | Niharika Sunder | 50959
ST01426 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-097 | Bhopal | Central | 50 | Pending Acceptance | 2025-10-03 | 2025-11-03 | 2025-10-31 | 2025-11-17 | 2025-11-17 | 0 | Met | Upadhriti Wadhwa | 69944
ST01427 | PRJ017 | CL004 | Bajaj Finance | Indore Site-098 | Indore | Central | 200 | Live | 2025-10-03 | 2025-10-30 | 2025-10-30 | 2025-11-27 | 2025-11-30 | 0 | Met | Theodore Devi | 105691
ST01428 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-099 | Bhopal | Central | 50 | Installation Scheduled | 2025-10-17 | 2025-12-11 | 2025-12-08 | 2026-01-07 |  | 8 | Marginal | Arya Sunder | 71328
ST01429 | PRJ017 | CL004 | Bajaj Finance | Indore Site-100 | Indore | Central | 50 | Live | 2025-09-24 | 2025-11-02 | 2025-11-10 | 2025-11-14 | 2025-11-21 | 8 | Marginal | Simon Tata | 80885
ST01430 | PRJ017 | CL004 | Bajaj Finance | Bhopal Site-101 | Bhopal | Central | 10 | ROW In Progress | 2025-10-11 | 2025-10-31 |  | 2025-11-13 |  | 7 | Met | Vansha Thakkar | 257205
ST01431 | PRJ017 | CL004 | Bajaj Finance | Indore Site-102 | Indore | Central | 200 | Installation Done | 2025-09-26 | 2025-11-01 | 2025-11-01 | 2025-11-29 |  | 12 | Marginal | Raksha Varughese | 66498
ST01432 | PRJ017 | CL004 | Bajaj Finance | Indore Site-103 | Indore | Central | 100 | ROW In Progress | 2025-10-13 | 2025-12-08 |  | 2025-12-21 |  | 0 | Met | Kabir Soman | 236037
ST01433 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-104 | Nagpur | Central | 10 | ROW In Progress | 2025-10-16 | 2025-12-07 |  | 2025-12-24 |  | 6 | Met | Victor Kannan | 196176
ST01434 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-105 | Nagpur | Central | 20 | Live | 2025-09-29 | 2025-11-19 | 2025-11-21 | 2025-11-30 | 2025-12-10 | 2 | Met | Faqid Savant | 95455
ST01435 | PRJ017 | CL004 | Bajaj Finance | Nagpur Site-106 | Nagpur | Central | 50 | Installation Scheduled | 2025-09-27 | 2025-11-11 | 2025-11-19 | 2025-12-09 |  | 4 | Met | Raksha Varughese | 206581
ST01436 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-001 | Nagpur | Central | 50 | Installation Done | 2025-12-30 | 2026-02-02 | 2026-02-03 | 2026-02-18 |  | 12 | Marginal | Michael Dutta | 54598
ST01437 | PRJ018 | CL004 | Bajaj Finance | Indore Site-002 | Indore | Central | 200 | Survey Pending | 2026-01-13 | 2026-02-28 |  | 2026-03-13 |  | 4 | Met | Mohammed Gupta | 279121
ST01438 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-003 | Bhopal | Central | 50 | ROW In Progress | 2026-01-02 | 2026-03-02 |  | 2026-03-15 |  | 1 | Met | Devika Rastogi | 56579
ST01439 | PRJ018 | CL004 | Bajaj Finance | Indore Site-004 | Indore | Central | 100 | Live | 2026-01-12 | 2026-02-11 | 2026-02-06 | 2026-03-08 | 2026-03-11 | 0 | Met | Irya Sampath | 71238
ST01440 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-005 | Bhopal | Central | 100 | Installation Done | 2026-01-02 | 2026-02-27 | 2026-03-02 | 2026-03-09 |  | 12 | Marginal | Darsh Rau | 138559
ST01441 | PRJ018 | CL004 | Bajaj Finance | Indore Site-006 | Indore | Central | 200 | Testing | 2025-12-31 | 2026-01-21 | 2026-01-19 | 2026-02-20 |  | 12 | Marginal | Anamika Kanda | 219928
ST01442 | PRJ018 | CL004 | Bajaj Finance | Indore Site-007 | Indore | Central | 20 | ROW In Progress | 2025-12-31 | 2026-02-03 |  | 2026-02-14 |  | 2 | Met | Ekapad Walia | 96811
ST01443 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-008 | Bhopal | Central | 10 | Installation Scheduled | 2025-12-27 | 2026-02-13 | 2026-02-15 | 2026-03-14 |  | 2 | Met | Advay Contractor | 235249
ST01444 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-009 | Nagpur | Central | 20 | Installation Scheduled | 2026-01-15 | 2026-02-23 | 2026-03-03 | 2026-03-09 |  | 1 | Met | Vansha Thakkar | 144113
ST01445 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-010 | Bhopal | Central | 10 | ROW In Progress | 2025-12-27 | 2026-02-19 |  | 2026-03-06 |  | 6 | Met | Theodore Devi | 245387
ST01446 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-011 | Bhopal | Central | 20 | Installation Scheduled | 2025-12-30 | 2026-02-14 | 2026-02-12 | 2026-03-09 |  | 3 | Met | Victor Kannan | 232091
ST01447 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-012 | Nagpur | Central | 200 | Live | 2026-01-16 | 2026-03-10 | 2026-03-15 | 2026-04-03 | 2026-04-05 | 5 | Met | Kabir Soman | 162718
ST01448 | PRJ018 | CL004 | Bajaj Finance | Indore Site-013 | Indore | Central | 50 | ROW In Progress | 2026-01-20 | 2026-03-09 |  | 2026-03-27 |  | 5 | Met | Kabir Soman | 237260
ST01449 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-014 | Bhopal | Central | 10 | ROW In Progress | 2026-01-04 | 2026-02-17 |  | 2026-03-16 |  | 7 | Met | Upadhriti Wadhwa | 253824
ST01450 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-015 | Nagpur | Central | 200 | ROW In Progress | 2025-12-27 | 2026-01-30 |  | 2026-02-26 |  | 1 | Met | Dakshesh Trivedi | 148443
ST01451 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-016 | Nagpur | Central | 20 | Testing | 2026-01-18 | 2026-02-15 | 2026-02-11 | 2026-03-13 |  | 12 | Marginal | Siddharth Zacharia | 254438
ST01452 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-017 | Bhopal | Central | 200 | Installation Scheduled | 2025-12-27 | 2026-02-17 | 2026-02-14 | 2026-03-06 |  | 8 | Marginal | Theodore Devi | 133896
ST01453 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-018 | Nagpur | Central | 20 | Testing | 2026-01-03 | 2026-02-08 | 2026-02-13 | 2026-03-07 |  | 12 | Marginal | Ekiya Suresh | 56539
ST01454 | PRJ018 | CL004 | Bajaj Finance | Indore Site-019 | Indore | Central | 10 | Installation Done | 2026-01-01 | 2026-01-29 | 2026-01-31 | 2026-02-28 |  | 12 | Marginal | Aarush Lall | 208798
ST01455 | PRJ018 | CL004 | Bajaj Finance | Indore Site-020 | Indore | Central | 50 | Survey Pending | 2026-01-18 | 2026-03-19 |  | 2026-04-15 |  | 1 | Met | Teerth Bhardwaj | 88157
ST01456 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-021 | Nagpur | Central | 10 | Installation Scheduled | 2026-01-05 | 2026-01-26 | 2026-01-22 | 2026-02-05 |  | 0 | Met | Daksh Karnik | 66924
ST01457 | PRJ018 | CL004 | Bajaj Finance | Indore Site-022 | Indore | Central | 10 | ROW In Progress | 2026-01-18 | 2026-03-19 |  | 2026-04-16 |  | 1 | Met | Wriddhish Bhardwaj | 171033
ST01458 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-023 | Bhopal | Central | 200 | Installation Done | 2026-01-12 | 2026-02-24 | 2026-02-20 | 2026-03-26 |  | 12 | Marginal | Daksh Karnik | 233540
ST01459 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-024 | Bhopal | Central | 50 | Pending Acceptance | 2026-01-05 | 2026-02-18 | 2026-02-16 | 2026-03-16 | 2026-03-22 | 0 | Met | Devansh Nigam | 86752
ST01460 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-025 | Bhopal | Central | 100 | Testing | 2025-12-30 | 2026-02-26 | 2026-03-08 | 2026-03-17 |  | 12 | Marginal | Priya Rastogi | 84472
ST01461 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-026 | Bhopal | Central | 100 | Live | 2026-01-04 | 2026-02-25 | 2026-02-21 | 2026-03-17 | 2026-03-26 | 0 | Met | Dominic Kakar | 177944
ST01462 | PRJ018 | CL004 | Bajaj Finance | Indore Site-027 | Indore | Central | 50 | Installation Done | 2025-12-27 | 2026-02-23 | 2026-02-19 | 2026-03-05 |  | 12 | Marginal | Raksha Varughese | 144063
ST01463 | PRJ018 | CL004 | Bajaj Finance | Indore Site-028 | Indore | Central | 100 | Live | 2025-12-28 | 2026-02-09 | 2026-02-12 | 2026-03-07 | 2026-03-08 | 3 | Met | Arya Shere | 192587
ST01464 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-029 | Bhopal | Central | 10 | Installation Scheduled | 2025-12-30 | 2026-02-05 | 2026-02-07 | 2026-02-25 |  | 5 | Met | Ranveer Yadav | 126297
ST01465 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-030 | Bhopal | Central | 10 | Live | 2026-01-07 | 2026-01-29 | 2026-01-25 | 2026-02-28 | 2026-03-12 | 0 | Met | Niharika Sunder | 99504
ST01466 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-031 | Bhopal | Central | 50 | Installation Done | 2026-01-14 | 2026-03-10 | 2026-03-19 | 2026-04-08 |  | 12 | Marginal | Anamika Kanda | 247471
ST01467 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-032 | Nagpur | Central | 50 | Live | 2026-01-11 | 2026-02-11 | 2026-02-10 | 2026-02-23 | 2026-02-21 | 0 | Met | Simon Tata | 77089
ST01468 | PRJ018 | CL004 | Bajaj Finance | Indore Site-033 | Indore | Central | 20 | Installation Scheduled | 2026-01-11 | 2026-02-07 | 2026-02-02 | 2026-02-25 |  | 4 | Met | Vansha Thakkar | 175664
ST01469 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-034 | Bhopal | Central | 50 | Installation Done | 2026-01-07 | 2026-02-08 | 2026-02-05 | 2026-03-02 |  | 12 | Marginal | Raksha Varughese | 85595
ST01470 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-035 | Nagpur | Central | 20 | Survey Pending | 2026-01-17 | 2026-03-03 |  | 2026-04-01 |  | 4 | Met | Kevin Solanki | 151860
ST01471 | PRJ018 | CL004 | Bajaj Finance | Indore Site-036 | Indore | Central | 200 | ROW In Progress | 2026-01-02 | 2026-02-17 |  | 2026-03-03 |  | 5 | Met | Madhavi Lanka | 101065
ST01472 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-037 | Bhopal | Central | 100 | Installation Scheduled | 2026-01-19 | 2026-02-24 | 2026-02-21 | 2026-03-20 |  | 0 | Met | Ekavir Varkey | 210578
ST01473 | PRJ018 | CL004 | Bajaj Finance | Indore Site-038 | Indore | Central | 20 | ROW In Progress | 2026-01-19 | 2026-03-03 |  | 2026-03-22 |  | 0 | Met | Girik Khalsa | 251742
ST01474 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-039 | Bhopal | Central | 10 | Live | 2026-01-06 | 2026-02-16 | 2026-02-16 | 2026-03-07 | 2026-03-10 | 0 | Met | Theodore Devi | 168163
ST01475 | PRJ018 | CL004 | Bajaj Finance | Indore Site-040 | Indore | Central | 200 | Installation Scheduled | 2026-01-20 | 2026-02-26 | 2026-03-02 | 2026-03-24 |  | 8 | Marginal | Anamika Kanda | 247384
ST01476 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-041 | Bhopal | Central | 20 | Live | 2026-01-06 | 2026-02-10 | 2026-02-10 | 2026-02-28 | 2026-03-07 | 0 | Met | Dipta Bhandari | 204932
ST01477 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-042 | Nagpur | Central | 10 | Survey Pending | 2026-01-17 | 2026-02-27 |  | 2026-03-10 |  | 4 | Met | Ekavir Varkey | 107604
ST01478 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-043 | Bhopal | Central | 200 | Pending Acceptance | 2026-01-01 | 2026-02-12 | 2026-02-13 | 2026-03-10 | 2026-03-15 | 1 | Met | Urvashi Ray | 276599
ST01479 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-044 | Nagpur | Central | 10 | ROW In Progress | 2026-01-18 | 2026-02-21 |  | 2026-03-07 |  | 1 | Met | Michael Dutta | 231464
ST01480 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-045 | Nagpur | Central | 20 | Installation Done | 2026-01-09 | 2026-02-05 | 2026-02-01 | 2026-03-06 |  | 12 | Marginal | Devika Rastogi | 200534
ST01481 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-046 | Bhopal | Central | 50 | Live | 2026-01-01 | 2026-02-21 | 2026-02-22 | 2026-03-07 | 2026-03-16 | 1 | Met | Alka Wable | 55278
ST01482 | PRJ018 | CL004 | Bajaj Finance | Indore Site-047 | Indore | Central | 50 | Live | 2026-01-18 | 2026-02-11 | 2026-02-08 | 2026-03-12 | 2026-03-24 | 0 | Met | Faqid Savant | 69984
ST01483 | PRJ018 | CL004 | Bajaj Finance | Indore Site-048 | Indore | Central | 20 | Pending Acceptance | 2026-01-08 | 2026-03-04 | 2026-02-27 | 2026-03-14 | 2026-03-16 | 0 | Met | Daksh Karnik | 257516
ST01484 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-049 | Bhopal | Central | 20 | Testing | 2026-01-05 | 2026-02-20 | 2026-02-18 | 2026-03-19 |  | 12 | Marginal | Nihal Shere | 109064
ST01485 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-050 | Nagpur | Central | 50 | Installation Done | 2026-01-10 | 2026-03-11 | 2026-03-21 | 2026-03-29 |  | 12 | Marginal | Advay Contractor | 234996
ST01486 | PRJ018 | CL004 | Bajaj Finance | Indore Site-051 | Indore | Central | 20 | Pending Acceptance | 2026-01-14 | 2026-02-16 | 2026-02-23 | 2026-03-09 | 2026-03-17 | 7 | Met | Tara Dhar | 64988
ST01487 | PRJ018 | CL004 | Bajaj Finance | Indore Site-052 | Indore | Central | 200 | Testing | 2026-01-20 | 2026-02-16 | 2026-02-20 | 2026-03-01 |  | 12 | Marginal | Ekavir Varkey | 104203
ST01488 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-053 | Bhopal | Central | 20 | Installation Done | 2026-01-10 | 2026-02-20 | 2026-02-15 | 2026-03-20 |  | 12 | Marginal | Niharika Sunder | 96040
ST01489 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-054 | Bhopal | Central | 100 | Live | 2025-12-31 | 2026-02-02 | 2026-02-01 | 2026-02-14 | 2026-02-18 | 0 | Met | Ekavir Bhargava | 132868
ST01490 | PRJ018 | CL004 | Bajaj Finance | Indore Site-055 | Indore | Central | 20 | Installation Done | 2025-12-28 | 2026-02-02 | 2026-01-29 | 2026-02-21 |  | 12 | Marginal | Niharika Sunder | 240859
ST01491 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-056 | Bhopal | Central | 100 | Live | 2026-01-15 | 2026-02-05 | 2026-02-10 | 2026-02-22 | 2026-03-06 | 5 | Met | Nitesh Raghavan | 159129
ST01492 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-057 | Nagpur | Central | 100 | Survey Pending | 2026-01-17 | 2026-02-12 |  | 2026-02-25 |  | 2 | Met | Anamika Kanda | 56051
ST01493 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-058 | Bhopal | Central | 100 | Live | 2025-12-27 | 2026-02-18 | 2026-02-19 | 2026-03-11 | 2026-03-20 | 1 | Met | Gavin Batta | 259478
ST01494 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-059 | Bhopal | Central | 20 | Installation Done | 2026-01-16 | 2026-03-06 | 2026-03-03 | 2026-03-26 |  | 12 | Marginal | Michael Dutta | 91008
ST01495 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-060 | Bhopal | Central | 200 | Installation Scheduled | 2026-01-05 | 2026-02-16 | 2026-02-12 | 2026-03-11 |  | 8 | Marginal | Isaac Patil | 159357
ST01496 | PRJ018 | CL004 | Bajaj Finance | Nagpur Site-061 | Nagpur | Central | 20 | ROW In Progress | 2026-01-15 | 2026-03-07 |  | 2026-03-30 |  | 8 | Marginal | Ekapad Walia | 182492
ST01497 | PRJ018 | CL004 | Bajaj Finance | Indore Site-062 | Indore | Central | 10 | Installation Scheduled | 2025-12-27 | 2026-01-23 | 2026-01-25 | 2026-02-11 |  | 8 | Marginal | Mohammed Gupta | 249536
ST01498 | PRJ018 | CL004 | Bajaj Finance | Bhopal Site-063 | Bhopal | Central | 20 | Installation Scheduled | 2026-01-02 | 2026-02-21 | 2026-02-20 | 2026-03-16 |  | 0 | Met | Siddharth Zacharia | 214118
ST01499 | PRJ018 | CL004 | Bajaj Finance | Indore Site-064 | Indore | Central | 100 | Testing | 2025-12-29 | 2026-01-21 | 2026-01-19 | 2026-02-11 |  | 12 | Marginal | Anamika Kanda | 203775
ST01500 | PRJ019 | CL004 | Bajaj Finance | Patna Site-001 | Patna | East | 20 | Live | 2026-01-17 | 2026-03-18 | 2026-03-28 | 2026-04-09 | 2026-04-07 | 10 | Marginal | Liam Koshy | 246618
ST01501 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-002 | Bhubaneswar | East | 20 | Survey Pending | 2026-01-10 | 2026-03-05 |  | 2026-03-23 |  | 1 | Met | Farhan Chada | 98127
ST01502 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-003 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-12-29 | 2026-02-07 | 2026-02-13 | 2026-02-22 |  | 3 | Met | Girik Khalsa | 73498
ST01503 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-004 | Bhubaneswar | East | 20 | Testing | 2025-12-27 | 2026-02-14 | 2026-02-09 | 2026-03-02 |  | 12 | Marginal | Devansh Rajan | 65603
ST01504 | PRJ019 | CL004 | Bajaj Finance | Patna Site-005 | Patna | East | 20 | ROW In Progress | 2026-01-06 | 2026-02-02 |  | 2026-02-19 |  | 6 | Met | Urvashi Ray | 79696
ST01505 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-006 | Bhubaneswar | East | 20 | Installation Done | 2026-01-12 | 2026-02-23 | 2026-03-02 | 2026-03-08 |  | 12 | Marginal | Kabir Soman | 162306
ST01506 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-007 | Kolkata | East | 20 | Live | 2026-01-11 | 2026-02-18 | 2026-02-22 | 2026-03-08 | 2026-03-06 | 4 | Met | Girindra Chatterjee | 57526
ST01507 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-008 | Kolkata | East | 50 | Live | 2026-01-03 | 2026-02-24 | 2026-02-20 | 2026-03-09 | 2026-03-19 | 0 | Met | Ekansh Balay | 58867
ST01508 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-009 | Kolkata | East | 100 | Installation Done | 2026-01-15 | 2026-02-20 | 2026-02-18 | 2026-03-14 |  | 12 | Marginal | Devansh Rajan | 82165
ST01509 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-010 | Bhubaneswar | East | 10 | Live | 2026-01-09 | 2026-03-02 | 2026-03-02 | 2026-03-17 | 2026-03-16 | 0 | Met | Yashica Issac | 212526
ST01510 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-011 | Kolkata | East | 50 | Live | 2026-01-12 | 2026-03-07 | 2026-03-07 | 2026-03-20 | 2026-03-23 | 0 | Met | Tanay Rattan | 89989
ST01511 | PRJ019 | CL004 | Bajaj Finance | Patna Site-012 | Patna | East | 100 | Testing | 2026-01-17 | 2026-03-09 | 2026-03-18 | 2026-03-26 |  | 12 | Marginal | Siddharth Zacharia | 274306
ST01512 | PRJ019 | CL004 | Bajaj Finance | Patna Site-013 | Patna | East | 100 | Installation Scheduled | 2025-12-28 | 2026-02-18 | 2026-02-18 | 2026-03-17 |  | 5 | Met | Daksh Karnik | 133728
ST01513 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-014 | Kolkata | East | 200 | Testing | 2026-01-08 | 2026-01-29 | 2026-02-08 | 2026-02-26 |  | 12 | Marginal | Nitesh Raghavan | 150586
ST01514 | PRJ019 | CL004 | Bajaj Finance | Patna Site-015 | Patna | East | 100 | Pending Acceptance | 2025-12-28 | 2026-02-15 | 2026-02-25 | 2026-02-26 | 2026-03-07 | 10 | Marginal | Devika Rastogi | 151190
ST01515 | PRJ019 | CL004 | Bajaj Finance | Patna Site-016 | Patna | East | 200 | Live | 2025-12-29 | 2026-01-18 | 2026-01-24 | 2026-01-28 | 2026-02-06 | 6 | Met | Aarush Lall | 67112
ST01516 | PRJ019 | CL004 | Bajaj Finance | Patna Site-017 | Patna | East | 10 | Live | 2025-12-30 | 2026-02-02 | 2026-02-08 | 2026-02-22 | 2026-02-24 | 6 | Met | Chandresh Zachariah | 222929
ST01517 | PRJ019 | CL004 | Bajaj Finance | Patna Site-018 | Patna | East | 50 | Installation Done | 2026-01-18 | 2026-02-28 | 2026-03-09 | 2026-03-13 |  | 12 | Marginal | Girik Khalsa | 194273
ST01518 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-019 | Kolkata | East | 50 | Live | 2026-01-10 | 2026-02-10 | 2026-02-07 | 2026-03-10 | 2026-03-11 | 0 | Met | Chandresh Zachariah | 164727
ST01519 | PRJ019 | CL004 | Bajaj Finance | Patna Site-020 | Patna | East | 200 | Pending Acceptance | 2026-01-11 | 2026-03-09 | 2026-03-12 | 2026-03-26 | 2026-04-05 | 3 | Met | Ekansh Balay | 250350
ST01520 | PRJ019 | CL004 | Bajaj Finance | Patna Site-021 | Patna | East | 200 | Live | 2025-12-30 | 2026-01-27 | 2026-01-23 | 2026-02-16 | 2026-02-14 | 0 | Met | Siddharth Zacharia | 218621
ST01521 | PRJ019 | CL004 | Bajaj Finance | Patna Site-022 | Patna | East | 50 | Installation Done | 2026-01-17 | 2026-03-16 | 2026-03-19 | 2026-04-11 |  | 12 | Marginal | Harini Choudhury | 123154
ST01522 | PRJ019 | CL004 | Bajaj Finance | Patna Site-023 | Patna | East | 50 | Installation Scheduled | 2026-01-17 | 2026-03-17 | 2026-03-14 | 2026-04-16 |  | 1 | Met | Darsh Rau | 163453
ST01523 | PRJ019 | CL004 | Bajaj Finance | Patna Site-024 | Patna | East | 50 | Testing | 2026-01-08 | 2026-01-30 | 2026-02-08 | 2026-02-11 |  | 12 | Marginal | Ekiya Suresh | 106677
ST01524 | PRJ019 | CL004 | Bajaj Finance | Patna Site-025 | Patna | East | 20 | Installation Done | 2026-01-06 | 2026-02-25 | 2026-02-26 | 2026-03-24 |  | 12 | Marginal | Daksh Karnik | 206371
ST01525 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-026 | Bhubaneswar | East | 100 | Installation Scheduled | 2026-01-18 | 2026-02-11 | 2026-02-08 | 2026-03-13 |  | 7 | Met | Wahab Raval | 145787
ST01526 | PRJ019 | CL004 | Bajaj Finance | Patna Site-027 | Patna | East | 100 | ROW In Progress | 2026-01-13 | 2026-03-10 |  | 2026-04-02 |  | 8 | Marginal | Yashica Cherian | 264426
ST01527 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-028 | Kolkata | East | 50 | Installation Scheduled | 2026-01-12 | 2026-02-13 | 2026-02-23 | 2026-02-24 |  | 8 | Marginal | Ekbal Garg | 149488
ST01528 | PRJ019 | CL004 | Bajaj Finance | Patna Site-029 | Patna | East | 50 | ROW In Progress | 2026-01-14 | 2026-02-18 |  | 2026-03-11 |  | 0 | Met | Daksh Karnik | 218950
ST01529 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-030 | Bhubaneswar | East | 10 | Live | 2026-01-06 | 2026-02-19 | 2026-02-24 | 2026-03-15 | 2026-03-13 | 5 | Met | Advay Contractor | 89019
ST01530 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-031 | Bhubaneswar | East | 20 | Live | 2025-12-30 | 2026-02-09 | 2026-02-15 | 2026-02-27 | 2026-03-04 | 6 | Met | Chandresh Zachariah | 165766
ST01531 | PRJ019 | CL004 | Bajaj Finance | Patna Site-032 | Patna | East | 20 | Installation Done | 2025-12-29 | 2026-02-09 | 2026-02-13 | 2026-02-24 |  | 12 | Marginal | Radhika Dugar | 224182
ST01532 | PRJ019 | CL004 | Bajaj Finance | Patna Site-033 | Patna | East | 50 | Live | 2026-01-02 | 2026-02-16 | 2026-02-18 | 2026-03-04 | 2026-03-04 | 2 | Met | Girik Khalsa | 88102
ST01533 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-034 | Bhubaneswar | East | 50 | Survey Pending | 2026-01-15 | 2026-02-24 |  | 2026-03-11 |  | 8 | Marginal | Dakshesh Trivedi | 91635
ST01534 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-035 | Bhubaneswar | East | 20 | Installation Done | 2026-01-12 | 2026-02-11 | 2026-02-18 | 2026-03-11 |  | 12 | Marginal | Alka Wable | 135000
ST01535 | PRJ019 | CL004 | Bajaj Finance | Patna Site-036 | Patna | East | 200 | Testing | 2026-01-15 | 2026-02-27 | 2026-02-25 | 2026-03-16 |  | 12 | Marginal | Devansh Rajan | 191783
ST01536 | PRJ019 | CL004 | Bajaj Finance | Patna Site-037 | Patna | East | 50 | Installation Done | 2026-01-05 | 2026-01-26 | 2026-02-05 | 2026-02-21 |  | 12 | Marginal | Faqid Savant | 267854
ST01537 | PRJ019 | CL004 | Bajaj Finance | Patna Site-038 | Patna | East | 20 | Installation Scheduled | 2026-01-13 | 2026-02-22 | 2026-03-04 | 2026-03-13 |  | 4 | Met | Ekbal Garg | 95897
ST01538 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-039 | Bhubaneswar | East | 100 | Testing | 2025-12-28 | 2026-02-18 | 2026-02-15 | 2026-03-03 |  | 12 | Marginal | Dakshesh Trivedi | 88205
ST01539 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-040 | Kolkata | East | 50 | ROW In Progress | 2026-01-16 | 2026-02-26 |  | 2026-03-26 |  | 3 | Met | Diya Rattan | 67547
ST01540 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-041 | Bhubaneswar | East | 10 | Installation Scheduled | 2026-01-03 | 2026-01-28 | 2026-02-02 | 2026-02-16 |  | 7 | Met | Girindra Chatterjee | 261950
ST01541 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-042 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-12-31 | 2026-01-31 | 2026-02-06 | 2026-03-01 |  | 3 | Met | Vansha Thakkar | 235799
ST01542 | PRJ019 | CL004 | Bajaj Finance | Patna Site-043 | Patna | East | 10 | ROW In Progress | 2026-01-19 | 2026-03-07 |  | 2026-03-31 |  | 5 | Met | Anamika Kanda | 207731
ST01543 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-044 | Bhubaneswar | East | 50 | Pending Acceptance | 2025-12-29 | 2026-01-24 | 2026-01-28 | 2026-02-05 | 2026-02-03 | 4 | Met | Ekiya Suresh | 164703
ST01544 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-045 | Bhubaneswar | East | 10 | Testing | 2025-12-28 | 2026-02-23 | 2026-03-05 | 2026-03-22 |  | 12 | Marginal | Harini Choudhury | 243643
ST01545 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-046 | Bhubaneswar | East | 200 | Survey Pending | 2026-01-05 | 2026-02-02 |  | 2026-02-19 |  | 8 | Marginal | Darsh Rau | 150432
ST01546 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-047 | Kolkata | East | 50 | Live | 2026-01-04 | 2026-02-28 | 2026-03-08 | 2026-03-23 | 2026-03-21 | 8 | Marginal | Yatin Baral | 153924
ST01547 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-048 | Bhubaneswar | East | 100 | Testing | 2026-01-02 | 2026-02-10 | 2026-02-10 | 2026-02-24 |  | 12 | Marginal | Unni Bhagat | 178748
ST01548 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-049 | Bhubaneswar | East | 50 | Pending Acceptance | 2026-01-15 | 2026-02-21 | 2026-02-26 | 2026-03-21 | 2026-03-31 | 5 | Met | Urvashi Ray | 251466
ST01549 | PRJ019 | CL004 | Bajaj Finance | Patna Site-050 | Patna | East | 10 | Live | 2026-01-03 | 2026-02-03 | 2026-02-02 | 2026-02-22 | 2026-02-22 | 0 | Met | Nitesh Raghavan | 132109
ST01550 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-051 | Kolkata | East | 50 | ROW In Progress | 2025-12-25 | 2026-01-16 |  | 2026-01-27 |  | 2 | Met | Logan Sami | 212553
ST01551 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-052 | Kolkata | East | 10 | Testing | 2026-01-01 | 2026-01-25 | 2026-01-27 | 2026-02-08 |  | 12 | Marginal | Girindra Chatterjee | 272668
ST01552 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-053 | Bhubaneswar | East | 10 | Survey Pending | 2025-12-25 | 2026-02-03 |  | 2026-02-23 |  | 7 | Met | Ekapad Walia | 211046
ST01553 | PRJ019 | CL004 | Bajaj Finance | Patna Site-054 | Patna | East | 50 | Installation Done | 2026-01-17 | 2026-02-17 | 2026-02-15 | 2026-03-08 |  | 12 | Marginal | Ekansh Balay | 268116
ST01554 | PRJ019 | CL004 | Bajaj Finance | Patna Site-055 | Patna | East | 100 | Installation Done | 2026-01-06 | 2026-02-19 | 2026-03-01 | 2026-03-05 |  | 12 | Marginal | Alka Wable | 155905
ST01555 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-056 | Bhubaneswar | East | 20 | Live | 2026-01-19 | 2026-03-08 | 2026-03-12 | 2026-04-07 | 2026-04-17 | 4 | Met | Ekbal Garg | 79009
ST01556 | PRJ019 | CL004 | Bajaj Finance | Bhubaneswar Site-057 | Bhubaneswar | East | 10 | Live | 2026-01-17 | 2026-02-16 | 2026-02-22 | 2026-03-07 | 2026-03-10 | 6 | Met | Kabir Soman | 256126
ST01557 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-058 | Kolkata | East | 20 | Live | 2026-01-19 | 2026-02-14 | 2026-02-13 | 2026-03-02 | 2026-03-01 | 0 | Met | Farhan Chada | 204011
ST01558 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-059 | Kolkata | East | 10 | Live | 2026-01-14 | 2026-02-03 | 2026-02-07 | 2026-03-04 | 2026-03-03 | 4 | Met | Arya Shere | 238539
ST01559 | PRJ019 | CL004 | Bajaj Finance | Kolkata Site-060 | Kolkata | East | 20 | Live | 2026-01-10 | 2026-02-14 | 2026-02-22 | 2026-03-04 | 2026-03-16 | 8 | Marginal | Ekapad Walia | 233100
ST01560 | PRJ019 | CL004 | Bajaj Finance | Patna Site-061 | Patna | East | 100 | Installation Done | 2025-12-25 | 2026-02-17 | 2026-02-17 | 2026-03-14 |  | 12 | Marginal | Gavin Batta | 219366
ST01561 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-001 | Kolkata | East | 200 | Testing | 2025-12-26 | 2026-02-12 | 2026-02-11 | 2026-03-04 |  | 12 | Marginal | Bhavika Sampath | 110188
ST01562 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-002 | Kolkata | East | 100 | Pending Acceptance | 2026-01-17 | 2026-02-19 | 2026-02-15 | 2026-03-10 | 2026-03-13 | 0 | Met | Arya Shere | 133424
ST01563 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-003 | Kolkata | East | 50 | Testing | 2026-01-15 | 2026-02-15 | 2026-02-24 | 2026-03-17 |  | 12 | Marginal | Devansh Rajan | 84225
ST01564 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-004 | Bhubaneswar | East | 100 | ROW In Progress | 2025-12-27 | 2026-02-03 |  | 2026-02-13 |  | 8 | Marginal | Radhika Dugar | 133383
ST01565 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-005 | Kolkata | East | 50 | Testing | 2026-01-04 | 2026-02-01 | 2026-01-31 | 2026-03-02 |  | 12 | Marginal | Arya Shere | 78766
ST01566 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-006 | Kolkata | East | 10 | Live | 2026-01-12 | 2026-02-13 | 2026-02-19 | 2026-03-06 | 2026-03-15 | 6 | Met | Ekbal Garg | 256120
ST01567 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-007 | Kolkata | East | 10 | Live | 2026-01-12 | 2026-03-11 | 2026-03-17 | 2026-03-25 | 2026-04-06 | 6 | Met | Michael Dutta | 104995
ST01568 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-008 | Bhubaneswar | East | 200 | ROW In Progress | 2026-01-02 | 2026-02-03 |  | 2026-02-26 |  | 5 | Met | Girindra Chatterjee | 186463
ST01569 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-009 | Bhubaneswar | East | 50 | Installation Done | 2026-01-18 | 2026-02-15 | 2026-02-16 | 2026-02-25 |  | 12 | Marginal | Priya Rastogi | 277810
ST01570 | PRJ020 | CL004 | Bajaj Finance | Patna Site-010 | Patna | East | 10 | Live | 2025-12-25 | 2026-01-23 | 2026-02-02 | 2026-02-03 | 2026-02-13 | 10 | Marginal | Ranveer Yadav | 206022
ST01571 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-011 | Kolkata | East | 20 | Installation Done | 2026-01-11 | 2026-03-03 | 2026-03-06 | 2026-03-14 |  | 12 | Marginal | Tara Dhar | 161159
ST01572 | PRJ020 | CL004 | Bajaj Finance | Patna Site-012 | Patna | East | 100 | Live | 2025-12-27 | 2026-02-12 | 2026-02-20 | 2026-03-12 | 2026-03-09 | 8 | Marginal | Siddharth Zacharia | 79075
ST01573 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-013 | Kolkata | East | 20 | Live | 2026-01-10 | 2026-02-05 | 2026-02-10 | 2026-02-25 | 2026-03-02 | 5 | Met | Ekbal Garg | 103153
ST01574 | PRJ020 | CL004 | Bajaj Finance | Patna Site-014 | Patna | East | 10 | Live | 2026-01-03 | 2026-01-25 | 2026-01-27 | 2026-02-05 | 2026-02-05 | 2 | Met | Ranveer Yadav | 151309
ST01575 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-015 | Bhubaneswar | East | 100 | Testing | 2026-01-18 | 2026-03-19 | 2026-03-28 | 2026-04-09 |  | 12 | Marginal | Kevin Solanki | 208291
ST01576 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-016 | Kolkata | East | 100 | Installation Done | 2026-01-12 | 2026-02-23 | 2026-03-01 | 2026-03-14 |  | 12 | Marginal | Ekiya Suresh | 109512
ST01577 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-017 | Bhubaneswar | East | 100 | Installation Done | 2025-12-28 | 2026-01-25 | 2026-01-28 | 2026-02-18 |  | 12 | Marginal | Ekbal Garg | 73982
ST01578 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-018 | Kolkata | East | 20 | Testing | 2026-01-18 | 2026-02-14 | 2026-02-12 | 2026-02-25 |  | 12 | Marginal | Daksh Karnik | 256313
ST01579 | PRJ020 | CL004 | Bajaj Finance | Patna Site-019 | Patna | East | 50 | Live | 2026-01-11 | 2026-02-14 | 2026-02-12 | 2026-03-10 | 2026-03-19 | 0 | Met | Gavin Batta | 173184
ST01580 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-020 | Kolkata | East | 10 | Installation Done | 2025-12-26 | 2026-02-18 | 2026-02-13 | 2026-03-16 |  | 12 | Marginal | Ranveer Yadav | 162377
ST01581 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-021 | Kolkata | East | 100 | ROW In Progress | 2025-12-25 | 2026-01-20 |  | 2026-02-09 |  | 0 | Met | Theodore Devi | 96245
ST01582 | PRJ020 | CL004 | Bajaj Finance | Patna Site-022 | Patna | East | 100 | Survey Pending | 2026-01-08 | 2026-02-03 |  | 2026-02-20 |  | 0 | Met | Siddharth Zacharia | 132068
ST01583 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-023 | Kolkata | East | 20 | Pending Acceptance | 2026-01-03 | 2026-02-15 | 2026-02-18 | 2026-03-12 | 2026-03-18 | 3 | Met | Girik Khalsa | 90870
ST01584 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-024 | Kolkata | East | 200 | Live | 2025-12-25 | 2026-01-15 | 2026-01-23 | 2026-01-30 | 2026-02-07 | 8 | Marginal | Ikbal Kothari | 162131
ST01585 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-025 | Bhubaneswar | East | 10 | Live | 2026-01-13 | 2026-02-18 | 2026-02-28 | 2026-02-28 | 2026-03-03 | 10 | Marginal | Ekbal Garg | 132493
ST01586 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-026 | Kolkata | East | 50 | Pending Acceptance | 2026-01-19 | 2026-02-20 | 2026-02-27 | 2026-03-07 | 2026-03-18 | 7 | Met | Madhavi Lanka | 278212
ST01587 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-027 | Bhubaneswar | East | 10 | Installation Done | 2025-12-29 | 2026-01-23 | 2026-01-29 | 2026-02-20 |  | 12 | Marginal | Devika Rastogi | 262761
ST01588 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-028 | Kolkata | East | 100 | Live | 2026-01-09 | 2026-01-30 | 2026-01-26 | 2026-02-10 | 2026-02-15 | 0 | Met | Tanay Rattan | 156558
ST01589 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-029 | Kolkata | East | 10 | Installation Scheduled | 2026-01-04 | 2026-03-05 | 2026-02-28 | 2026-03-17 |  | 1 | Met | Mohammed Gupta | 199275
ST01590 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-030 | Bhubaneswar | East | 200 | Live | 2025-12-28 | 2026-02-02 | 2026-01-29 | 2026-02-12 | 2026-02-17 | 0 | Met | Devika Rastogi | 187574
ST01591 | PRJ020 | CL004 | Bajaj Finance | Patna Site-031 | Patna | East | 200 | Survey Pending | 2026-01-16 | 2026-03-13 |  | 2026-04-12 |  | 4 | Met | Ekbal Garg | 127587
ST01592 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-032 | Kolkata | East | 50 | Live | 2026-01-16 | 2026-02-09 | 2026-02-14 | 2026-02-24 | 2026-02-22 | 5 | Met | Yatin Baral | 54934
ST01593 | PRJ020 | CL004 | Bajaj Finance | Patna Site-033 | Patna | East | 100 | Installation Scheduled | 2026-01-13 | 2026-03-05 | 2026-03-12 | 2026-04-03 |  | 8 | Marginal | Alka Wable | 214876
ST01594 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-034 | Kolkata | East | 100 | ROW In Progress | 2026-01-12 | 2026-03-01 |  | 2026-03-14 |  | 6 | Met | Ekavir Varkey | 71753
ST01595 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-035 | Bhubaneswar | East | 10 | Live | 2025-12-28 | 2026-01-26 | 2026-01-27 | 2026-02-20 | 2026-02-26 | 1 | Met | Quincy Biswas | 170800
ST01596 | PRJ020 | CL004 | Bajaj Finance | Patna Site-036 | Patna | East | 20 | Installation Scheduled | 2026-01-01 | 2026-02-01 | 2026-02-06 | 2026-02-24 |  | 2 | Met | Ekavir Varkey | 197794
ST01597 | PRJ020 | CL004 | Bajaj Finance | Patna Site-037 | Patna | East | 20 | Pending Acceptance | 2026-01-13 | 2026-03-02 | 2026-02-25 | 2026-03-14 | 2026-03-19 | 0 | Met | Madhavi Lanka | 267329
ST01598 | PRJ020 | CL004 | Bajaj Finance | Patna Site-038 | Patna | East | 100 | ROW In Progress | 2025-12-31 | 2026-02-18 |  | 2026-03-01 |  | 8 | Marginal | Kashvi Edwin | 72706
ST01599 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-039 | Kolkata | East | 200 | Installation Done | 2025-12-30 | 2026-01-20 | 2026-01-23 | 2026-02-02 |  | 12 | Marginal | Theodore Devi | 106659
ST01600 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-040 | Bhubaneswar | East | 10 | Live | 2026-01-18 | 2026-03-18 | 2026-03-27 | 2026-04-01 | 2026-04-01 | 9 | Marginal | Bhavika Sampath | 50875
ST01601 | PRJ020 | CL004 | Bajaj Finance | Patna Site-041 | Patna | East | 10 | Live | 2026-01-10 | 2026-03-11 | 2026-03-15 | 2026-04-06 | 2026-04-03 | 4 | Met | Girik Khalsa | 279399
ST01602 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-042 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-12-29 | 2026-01-28 | 2026-01-26 | 2026-02-21 |  | 5 | Met | Siddharth Zacharia | 194707
ST01603 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-043 | Bhubaneswar | East | 10 | Pending Acceptance | 2026-01-05 | 2026-02-22 | 2026-02-17 | 2026-03-21 | 2026-03-23 | 0 | Met | Daksh Karnik | 113026
ST01604 | PRJ020 | CL004 | Bajaj Finance | Patna Site-044 | Patna | East | 20 | Survey Pending | 2026-01-09 | 2026-02-18 |  | 2026-03-15 |  | 1 | Met | Wriddhish Bhardwaj | 144680
ST01605 | PRJ020 | CL004 | Bajaj Finance | Patna Site-045 | Patna | East | 20 | ROW In Progress | 2026-01-13 | 2026-02-27 |  | 2026-03-11 |  | 1 | Met | Wahab Raval | 221774
ST01606 | PRJ020 | CL004 | Bajaj Finance | Patna Site-046 | Patna | East | 20 | Installation Scheduled | 2025-12-30 | 2026-02-26 | 2026-03-06 | 2026-03-25 |  | 8 | Marginal | Dipta Bhandari | 235370
ST01607 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-047 | Bhubaneswar | East | 10 | Testing | 2026-01-15 | 2026-03-06 | 2026-03-02 | 2026-03-24 |  | 12 | Marginal | Ikbal Kothari | 105119
ST01608 | PRJ020 | CL004 | Bajaj Finance | Patna Site-048 | Patna | East | 10 | ROW In Progress | 2026-01-19 | 2026-02-13 |  | 2026-03-13 |  | 6 | Met | Ikbal Kothari | 156974
ST01609 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-049 | Kolkata | East | 50 | Installation Done | 2026-01-11 | 2026-02-15 | 2026-02-15 | 2026-03-12 |  | 12 | Marginal | Alka Wable | 132374
ST01610 | PRJ020 | CL004 | Bajaj Finance | Patna Site-050 | Patna | East | 50 | Installation Done | 2025-12-28 | 2026-02-15 | 2026-02-22 | 2026-03-02 |  | 12 | Marginal | Dominic Kakar | 276936
ST01611 | PRJ020 | CL004 | Bajaj Finance | Patna Site-051 | Patna | East | 100 | Pending Acceptance | 2026-01-16 | 2026-03-17 | 2026-03-21 | 2026-04-15 | 2026-04-24 | 4 | Met | Raksha Varughese | 233836
ST01612 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-052 | Bhubaneswar | East | 20 | Pending Acceptance | 2026-01-07 | 2026-01-28 | 2026-01-31 | 2026-02-21 | 2026-02-27 | 3 | Met | Liam Koshy | 161377
ST01613 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-053 | Kolkata | East | 20 | ROW In Progress | 2026-01-04 | 2026-01-30 |  | 2026-02-21 |  | 2 | Met | Ikbal Kothari | 197042
ST01614 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-054 | Kolkata | East | 50 | Live | 2026-01-07 | 2026-02-13 | 2026-02-12 | 2026-02-23 | 2026-02-27 | 0 | Met | Girik Khalsa | 184645
ST01615 | PRJ020 | CL004 | Bajaj Finance | Patna Site-055 | Patna | East | 50 | Installation Done | 2026-01-13 | 2026-02-04 | 2026-02-12 | 2026-02-18 |  | 12 | Marginal | Chandresh Zachariah | 170704
ST01616 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-056 | Kolkata | East | 100 | Pending Acceptance | 2026-01-18 | 2026-03-12 | 2026-03-21 | 2026-04-10 | 2026-04-09 | 9 | Marginal | Anamika Kanda | 208378
ST01617 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-057 | Kolkata | East | 50 | ROW In Progress | 2025-12-27 | 2026-01-29 |  | 2026-02-11 |  | 3 | Met | Yashica Issac | 260154
ST01618 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-058 | Kolkata | East | 10 | Live | 2025-12-28 | 2026-01-31 | 2026-02-01 | 2026-02-25 | 2026-03-07 | 1 | Met | Unni Bhagat | 93910
ST01619 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-059 | Kolkata | East | 10 | Survey Pending | 2026-01-02 | 2026-02-11 |  | 2026-03-10 |  | 8 | Marginal | Girik Khalsa | 132149
ST01620 | PRJ020 | CL004 | Bajaj Finance | Patna Site-060 | Patna | East | 100 | Survey Pending | 2025-12-30 | 2026-02-11 |  | 2026-03-01 |  | 4 | Met | Aarush Lall | 113729
ST01621 | PRJ020 | CL004 | Bajaj Finance | Kolkata Site-061 | Kolkata | East | 50 | Testing | 2026-01-07 | 2026-02-16 | 2026-02-12 | 2026-03-04 |  | 12 | Marginal | Ekavir Bhargava | 52406
ST01622 | PRJ020 | CL004 | Bajaj Finance | Patna Site-062 | Patna | East | 200 | Installation Done | 2025-12-27 | 2026-02-15 | 2026-02-25 | 2026-02-27 |  | 12 | Marginal | Harini Choudhury | 228551
ST01623 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-063 | Bhubaneswar | East | 200 | Testing | 2026-01-12 | 2026-03-07 | 2026-03-03 | 2026-04-03 |  | 12 | Marginal | Ekbal Garg | 272095
ST01624 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-064 | Bhubaneswar | East | 10 | Installation Done | 2026-01-11 | 2026-02-09 | 2026-02-07 | 2026-02-27 |  | 12 | Marginal | Bhavika Sampath | 116006
ST01625 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-065 | Bhubaneswar | East | 20 | Installation Done | 2025-12-28 | 2026-01-31 | 2026-02-05 | 2026-03-01 |  | 12 | Marginal | Chandresh Zachariah | 209256
ST01626 | PRJ020 | CL004 | Bajaj Finance | Bhubaneswar Site-066 | Bhubaneswar | East | 200 | Pending Acceptance | 2026-01-11 | 2026-02-27 | 2026-03-01 | 2026-03-27 | 2026-04-05 | 2 | Met | Bhavika Sampath | 126688
ST01627 | PRJ020 | CL004 | Bajaj Finance | Patna Site-067 | Patna | East | 200 | Installation Done | 2026-01-03 | 2026-01-28 | 2026-02-02 | 2026-02-17 |  | 12 | Marginal | Devansh Nigam | 127196
ST01628 | PRJ020 | CL004 | Bajaj Finance | Patna Site-068 | Patna | East | 10 | Survey Pending | 2025-12-28 | 2026-02-25 |  | 2026-03-11 |  | 2 | Met | Dakshesh Trivedi | 139716
ST01629 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-001 | Kolkata | East | 200 | ROW In Progress | 2025-11-02 | 2025-12-01 |  | 2025-12-25 |  | 4 | Met | Quincy Biswas | 223827
ST01630 | PRJ021 | CL005 | HDFC Bank | Patna Site-002 | Patna | East | 20 | Live | 2025-10-29 | 2025-12-16 | 2025-12-25 | 2026-01-07 | 2026-01-10 | 9 | Marginal | Ekavir Varkey | 214099
ST01631 | PRJ021 | CL005 | HDFC Bank | Patna Site-003 | Patna | East | 200 | Live | 2025-11-01 | 2025-12-22 | 2025-12-22 | 2026-01-01 | 2026-01-04 | 0 | Met | Arya Shere | 224590
ST01632 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-004 | Kolkata | East | 10 | Live | 2025-11-11 | 2025-12-23 | 2025-12-18 | 2026-01-22 | 2026-01-20 | 0 | Met | Faqid Savant | 109733
ST01633 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-005 | Kolkata | East | 200 | Installation Scheduled | 2025-11-18 | 2026-01-17 | 2026-01-18 | 2026-01-28 |  | 6 | Met | Siddharth Zacharia | 130196
ST01634 | PRJ021 | CL005 | HDFC Bank | Patna Site-006 | Patna | East | 20 | Testing | 2025-10-31 | 2025-12-07 | 2025-12-09 | 2025-12-27 |  | 12 | Marginal | Kevin Solanki | 48097
ST01635 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-007 | Kolkata | East | 100 | Live | 2025-11-18 | 2026-01-17 | 2026-01-15 | 2026-02-12 | 2026-02-11 | 0 | Met | Bhavika Sampath | 169300
ST01636 | PRJ021 | CL005 | HDFC Bank | Patna Site-008 | Patna | East | 50 | Installation Scheduled | 2025-10-29 | 2025-12-15 | 2025-12-21 | 2025-12-30 |  | 4 | Met | Jai Kota | 220643
ST01637 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-009 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-11-09 | 2025-12-02 | 2025-12-03 | 2025-12-29 |  | 5 | Met | Vansha Thakkar | 203011
ST01638 | PRJ021 | CL005 | HDFC Bank | Patna Site-010 | Patna | East | 20 | Installation Scheduled | 2025-11-18 | 2026-01-12 | 2026-01-10 | 2026-01-22 |  | 5 | Met | Advay Contractor | 83557
ST01639 | PRJ021 | CL005 | HDFC Bank | Patna Site-011 | Patna | East | 100 | Installation Done | 2025-11-12 | 2026-01-03 | 2026-01-06 | 2026-01-30 |  | 12 | Marginal | Nitesh Raghavan | 198701
ST01640 | PRJ021 | CL005 | HDFC Bank | Patna Site-012 | Patna | East | 50 | Installation Done | 2025-10-31 | 2025-12-28 | 2025-12-24 | 2026-01-16 |  | 12 | Marginal | Dakshesh Trivedi | 196722
ST01641 | PRJ021 | CL005 | HDFC Bank | Patna Site-013 | Patna | East | 20 | ROW In Progress | 2025-11-11 | 2025-12-07 |  | 2025-12-25 |  | 7 | Met | Jai Kota | 143786
ST01642 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-014 | Kolkata | East | 50 | Survey Pending | 2025-10-29 | 2025-12-26 |  | 2026-01-22 |  | 6 | Met | Ekiya Suresh | 115202
ST01643 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-015 | Kolkata | East | 20 | Live | 2025-11-13 | 2025-12-17 | 2025-12-26 | 2026-01-01 | 2026-01-05 | 9 | Marginal | Devansh Rajan | 84570
ST01644 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-016 | Kolkata | East | 20 | Pending Acceptance | 2025-11-17 | 2026-01-11 | 2026-01-21 | 2026-01-21 | 2026-01-30 | 10 | Marginal | Ekapad Walia | 90194
ST01645 | PRJ021 | CL005 | HDFC Bank | Patna Site-017 | Patna | East | 10 | Live | 2025-10-28 | 2025-12-23 | 2025-12-24 | 2026-01-07 | 2026-01-08 | 1 | Met | Dominic Kakar | 258965
ST01646 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-018 | Kolkata | East | 10 | Survey Pending | 2025-11-03 | 2025-12-04 |  | 2025-12-14 |  | 0 | Met | Faqid Savant | 165929
ST01647 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-019 | Bhubaneswar | East | 10 | Installation Done | 2025-10-28 | 2025-11-18 | 2025-11-28 | 2025-12-10 |  | 12 | Marginal | Nihal Shere | 188587
ST01648 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-020 | Kolkata | East | 10 | Live | 2025-11-02 | 2025-12-15 | 2025-12-22 | 2025-12-27 | 2026-01-02 | 7 | Met | Devika Rastogi | 189974
ST01649 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-021 | Bhubaneswar | East | 100 | Pending Acceptance | 2025-11-16 | 2025-12-21 | 2025-12-18 | 2026-01-18 | 2026-01-16 | 0 | Met | Ekavir Bhargava | 155399
ST01650 | PRJ021 | CL005 | HDFC Bank | Patna Site-022 | Patna | East | 10 | Live | 2025-11-02 | 2025-12-12 | 2025-12-16 | 2026-01-04 | 2026-01-11 | 4 | Met | Diya Rattan | 45956
ST01651 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-023 | Kolkata | East | 50 | Live | 2025-10-27 | 2025-12-15 | 2025-12-22 | 2025-12-30 | 2025-12-27 | 7 | Met | Ekavir Bhargava | 131356
ST01652 | PRJ021 | CL005 | HDFC Bank | Patna Site-024 | Patna | East | 10 | Testing | 2025-11-10 | 2025-12-04 | 2025-12-09 | 2025-12-14 |  | 12 | Marginal | Madhavi Lanka | 158469
ST01653 | PRJ021 | CL005 | HDFC Bank | Patna Site-025 | Patna | East | 100 | Installation Done | 2025-11-04 | 2025-11-29 | 2025-11-26 | 2025-12-09 |  | 12 | Marginal | Logan Sami | 123404
ST01654 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-026 | Kolkata | East | 200 | Live | 2025-11-18 | 2025-12-22 | 2025-12-26 | 2026-01-01 | 2026-01-12 | 4 | Met | Girindra Chatterjee | 71364
ST01655 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-027 | Bhubaneswar | East | 200 | Testing | 2025-11-14 | 2025-12-21 | 2025-12-31 | 2026-01-01 |  | 12 | Marginal | Nihal Shere | 141281
ST01656 | PRJ021 | CL005 | HDFC Bank | Patna Site-028 | Patna | East | 100 | Live | 2025-11-09 | 2025-12-25 | 2025-12-26 | 2026-01-13 | 2026-01-14 | 1 | Met | Girik Khalsa | 86761
ST01657 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-029 | Bhubaneswar | East | 100 | Testing | 2025-11-21 | 2025-12-11 | 2025-12-13 | 2026-01-07 |  | 12 | Marginal | Advay Contractor | 168857
ST01658 | PRJ021 | CL005 | HDFC Bank | Patna Site-030 | Patna | East | 50 | Pending Acceptance | 2025-11-17 | 2026-01-07 | 2026-01-04 | 2026-01-28 | 2026-01-25 | 0 | Met | Nitesh Raghavan | 92345
ST01659 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-031 | Bhubaneswar | East | 10 | Installation Done | 2025-10-29 | 2025-12-24 | 2026-01-02 | 2026-01-15 |  | 12 | Marginal | Devika Rastogi | 78162
ST01660 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-032 | Kolkata | East | 100 | Pending Acceptance | 2025-10-31 | 2025-12-17 | 2025-12-23 | 2026-01-10 | 2026-01-12 | 6 | Met | Nihal Shere | 124357
ST01661 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-033 | Kolkata | East | 10 | Testing | 2025-10-27 | 2025-12-22 | 2025-12-28 | 2026-01-05 |  | 12 | Marginal | Dipta Bhandari | 139688
ST01662 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-034 | Bhubaneswar | East | 50 | Installation Done | 2025-10-30 | 2025-12-18 | 2025-12-28 | 2026-01-11 |  | 12 | Marginal | Gavin Batta | 220889
ST01663 | PRJ021 | CL005 | HDFC Bank | Patna Site-035 | Patna | East | 10 | ROW In Progress | 2025-11-05 | 2025-12-19 |  | 2026-01-17 |  | 2 | Met | Michael Dutta | 187032
ST01664 | PRJ021 | CL005 | HDFC Bank | Patna Site-036 | Patna | East | 200 | Live | 2025-11-16 | 2026-01-10 | 2026-01-09 | 2026-01-28 | 2026-01-27 | 0 | Met | Girik Khalsa | 81115
ST01665 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-037 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-11-01 | 2025-11-30 | 2025-12-10 | 2025-12-20 |  | 8 | Marginal | Priya Rastogi | 162775
ST01666 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-038 | Kolkata | East | 200 | Live | 2025-11-04 | 2025-12-17 | 2025-12-20 | 2025-12-31 | 2025-12-31 | 3 | Met | Darsh Rau | 223524
ST01667 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-039 | Bhubaneswar | East | 20 | Installation Done | 2025-10-28 | 2025-12-07 | 2025-12-15 | 2026-01-02 |  | 12 | Marginal | Ekbal Garg | 266491
ST01668 | PRJ021 | CL005 | HDFC Bank | Patna Site-040 | Patna | East | 10 | ROW In Progress | 2025-11-07 | 2025-12-28 |  | 2026-01-07 |  | 0 | Met | Liam Koshy | 210706
ST01669 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-041 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-11-18 | 2025-12-29 | 2026-01-06 | 2026-01-16 |  | 0 | Met | Kashvi Edwin | 100383
ST01670 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-042 | Kolkata | East | 50 | Installation Scheduled | 2025-11-11 | 2025-12-12 | 2025-12-12 | 2026-01-08 |  | 5 | Met | Ekbal Garg | 60312
ST01671 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-043 | Kolkata | East | 50 | Installation Done | 2025-11-16 | 2026-01-08 | 2026-01-08 | 2026-01-23 |  | 12 | Marginal | Mohammed Gupta | 108011
ST01672 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-044 | Kolkata | East | 50 | ROW In Progress | 2025-11-09 | 2025-12-03 |  | 2025-12-25 |  | 8 | Marginal | Ekbal Garg | 171214
ST01673 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-045 | Kolkata | East | 10 | Survey Pending | 2025-11-07 | 2026-01-01 |  | 2026-01-31 |  | 0 | Met | Upadhriti Wadhwa | 195565
ST01674 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-046 | Bhubaneswar | East | 50 | Pending Acceptance | 2025-11-15 | 2025-12-16 | 2025-12-25 | 2025-12-29 | 2025-12-28 | 9 | Marginal | Isaac Patil | 157041
ST01675 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-047 | Kolkata | East | 200 | Live | 2025-10-28 | 2025-12-10 | 2025-12-12 | 2026-01-03 | 2026-01-01 | 2 | Met | Radhika Dugar | 97326
ST01676 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-048 | Kolkata | East | 10 | Survey Pending | 2025-10-29 | 2025-12-15 |  | 2026-01-12 |  | 5 | Met | Ekbal Garg | 171842
ST01677 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-049 | Bhubaneswar | East | 50 | Live | 2025-11-16 | 2025-12-11 | 2025-12-15 | 2026-01-07 | 2026-01-14 | 4 | Met | Siddharth Zacharia | 257527
ST01678 | PRJ021 | CL005 | HDFC Bank | Patna Site-050 | Patna | East | 200 | ROW In Progress | 2025-11-14 | 2026-01-06 |  | 2026-01-30 |  | 6 | Met | Kabir Soman | 271808
ST01679 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-051 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-11-15 | 2025-12-21 | 2025-12-24 | 2026-01-15 |  | 1 | Met | Gavin Batta | 208684
ST01680 | PRJ021 | CL005 | HDFC Bank | Patna Site-052 | Patna | East | 200 | Installation Done | 2025-10-31 | 2025-12-20 | 2025-12-21 | 2026-01-08 |  | 12 | Marginal | Theodore Devi | 100893
ST01681 | PRJ021 | CL005 | HDFC Bank | Patna Site-053 | Patna | East | 50 | Live | 2025-10-28 | 2025-12-03 | 2025-12-08 | 2025-12-14 | 2025-12-15 | 5 | Met | Girik Khalsa | 103138
ST01682 | PRJ021 | CL005 | HDFC Bank | Patna Site-054 | Patna | East | 100 | ROW In Progress | 2025-11-10 | 2025-12-18 |  | 2026-01-03 |  | 5 | Met | Jai Kota | 182368
ST01683 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-055 | Kolkata | East | 200 | Installation Scheduled | 2025-10-31 | 2025-12-16 | 2025-12-12 | 2026-01-07 |  | 4 | Met | Madhavi Lanka | 55202
ST01684 | PRJ021 | CL005 | HDFC Bank | Patna Site-056 | Patna | East | 50 | Installation Done | 2025-11-02 | 2025-12-29 | 2025-12-31 | 2026-01-16 |  | 12 | Marginal | Yatin Baral | 96178
ST01685 | PRJ021 | CL005 | HDFC Bank | Patna Site-057 | Patna | East | 100 | Installation Scheduled | 2025-11-01 | 2025-12-11 | 2025-12-13 | 2026-01-02 |  | 4 | Met | Radhika Dugar | 186608
ST01686 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-058 | Kolkata | East | 100 | Installation Scheduled | 2025-10-28 | 2025-12-15 | 2025-12-24 | 2026-01-02 |  | 0 | Met | Ranveer Yadav | 162698
ST01687 | PRJ021 | CL005 | HDFC Bank | Patna Site-059 | Patna | East | 200 | Installation Scheduled | 2025-10-29 | 2025-12-11 | 2025-12-18 | 2025-12-26 |  | 3 | Met | Isaac Patil | 236151
ST01688 | PRJ021 | CL005 | HDFC Bank | Kolkata Site-060 | Kolkata | East | 10 | Testing | 2025-11-13 | 2025-12-24 | 2025-12-29 | 2026-01-06 |  | 12 | Marginal | Wahab Raval | 209873
ST01689 | PRJ021 | CL005 | HDFC Bank | Patna Site-061 | Patna | East | 10 | Installation Scheduled | 2025-10-27 | 2025-12-24 | 2025-12-22 | 2026-01-10 |  | 1 | Met | Michael Dutta | 166293
ST01690 | PRJ021 | CL005 | HDFC Bank | Patna Site-062 | Patna | East | 50 | Pending Acceptance | 2025-10-30 | 2025-12-27 | 2025-12-22 | 2026-01-10 | 2026-01-17 | 0 | Met | Bhavika Sampath | 223776
ST01691 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-063 | Bhubaneswar | East | 100 | Survey Pending | 2025-11-18 | 2025-12-19 |  | 2026-01-03 |  | 0 | Met | Logan Sami | 106291
ST01692 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-064 | Bhubaneswar | East | 20 | Live | 2025-11-04 | 2025-11-29 | 2025-11-29 | 2025-12-09 | 2025-12-08 | 0 | Met | Isaac Patil | 159750
ST01693 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-065 | Bhubaneswar | East | 100 | Live | 2025-11-14 | 2025-12-26 | 2025-12-22 | 2026-01-05 | 2026-01-07 | 0 | Met | Simon Tata | 65693
ST01694 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-066 | Bhubaneswar | East | 100 | ROW In Progress | 2025-11-02 | 2025-12-03 |  | 2025-12-24 |  | 4 | Met | Unni Bhagat | 53386
ST01695 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-067 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-11-11 | 2025-12-07 | 2025-12-16 | 2025-12-23 |  | 2 | Met | Simon Tata | 137763
ST01696 | PRJ021 | CL005 | HDFC Bank | Patna Site-068 | Patna | East | 10 | Live | 2025-11-17 | 2025-12-30 | 2025-12-25 | 2026-01-16 | 2026-01-15 | 0 | Met | Nihal Shere | 147936
ST01697 | PRJ021 | CL005 | HDFC Bank | Bhubaneswar Site-069 | Bhubaneswar | East | 200 | Pending Acceptance | 2025-11-15 | 2025-12-18 | 2025-12-22 | 2025-12-28 | 2025-12-31 | 4 | Met | Advay Contractor | 45787
ST01698 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-001 | Bhopal | Central | 10 | Live | 2026-01-27 | 2026-03-24 | 2026-04-02 | 2026-04-18 | 2026-04-20 | 9 | Marginal | Arya Shere | 190755
ST01699 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-002 | Nagpur | Central | 200 | Survey Pending | 2026-01-18 | 2026-02-28 |  | 2026-03-17 |  | 7 | Met | Kabir Soman | 62607
ST01700 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-003 | Nagpur | Central | 50 | Pending Acceptance | 2026-02-05 | 2026-03-06 | 2026-03-16 | 2026-03-21 | 2026-03-26 | 10 | Marginal | Kevin Solanki | 272077
ST01701 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-004 | Bhopal | Central | 10 | Live | 2026-02-02 | 2026-03-02 | 2026-03-02 | 2026-03-27 | 2026-03-29 | 0 | Met | Simon Tata | 91565
ST01702 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-005 | Nagpur | Central | 20 | Installation Scheduled | 2026-01-26 | 2026-03-21 | 2026-03-20 | 2026-04-20 |  | 3 | Met | Yashica Cherian | 60508
ST01703 | PRJ022 | CL005 | HDFC Bank | Indore Site-006 | Indore | Central | 20 | ROW In Progress | 2026-01-25 | 2026-03-17 |  | 2026-04-04 |  | 3 | Met | Upadhriti Wadhwa | 62311
ST01704 | PRJ022 | CL005 | HDFC Bank | Indore Site-007 | Indore | Central | 10 | Pending Acceptance | 2026-01-28 | 2026-03-25 | 2026-03-26 | 2026-04-04 | 2026-04-05 | 1 | Met | Harini Choudhury | 54467
ST01705 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-008 | Nagpur | Central | 20 | Installation Scheduled | 2026-01-18 | 2026-02-24 | 2026-02-23 | 2026-03-13 |  | 2 | Met | Bhavika Sampath | 175554
ST01706 | PRJ022 | CL005 | HDFC Bank | Indore Site-009 | Indore | Central | 10 | Live | 2026-01-21 | 2026-02-16 | 2026-02-18 | 2026-03-09 | 2026-03-12 | 2 | Met | Harini Choudhury | 176947
ST01707 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-010 | Bhopal | Central | 20 | Installation Done | 2026-01-18 | 2026-03-05 | 2026-03-08 | 2026-03-27 |  | 12 | Marginal | Ekbal Garg | 223829
ST01708 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-011 | Bhopal | Central | 100 | Installation Scheduled | 2026-02-11 | 2026-04-10 | 2026-04-12 | 2026-05-04 |  | 7 | Met | Ikbal Kothari | 149302
ST01709 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-012 | Nagpur | Central | 10 | ROW In Progress | 2026-02-03 | 2026-03-09 |  | 2026-03-23 |  | 1 | Met | Yashica Issac | 201818
ST01710 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-013 | Bhopal | Central | 100 | Installation Done | 2026-02-07 | 2026-03-03 | 2026-03-13 | 2026-03-22 |  | 12 | Marginal | Dominic Kakar | 270601
ST01711 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-014 | Bhopal | Central | 50 | Testing | 2026-02-02 | 2026-03-07 | 2026-03-05 | 2026-03-17 |  | 12 | Marginal | Raksha Varughese | 265763
ST01712 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-015 | Nagpur | Central | 20 | Testing | 2026-01-25 | 2026-02-18 | 2026-02-25 | 2026-03-12 |  | 12 | Marginal | Yashica Cherian | 193763
ST01713 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-016 | Bhopal | Central | 200 | Live | 2026-01-23 | 2026-02-19 | 2026-02-27 | 2026-03-16 | 2026-03-13 | 8 | Marginal | Tara Dhar | 141178
ST01714 | PRJ022 | CL005 | HDFC Bank | Indore Site-017 | Indore | Central | 10 | Testing | 2026-01-28 | 2026-03-15 | 2026-03-22 | 2026-04-08 |  | 12 | Marginal | Faqid Savant | 106307
ST01715 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-018 | Nagpur | Central | 50 | Installation Done | 2026-01-21 | 2026-02-15 | 2026-02-22 | 2026-03-08 |  | 12 | Marginal | Tara Dhar | 124481
ST01716 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-019 | Nagpur | Central | 100 | Installation Scheduled | 2026-02-10 | 2026-03-18 | 2026-03-22 | 2026-04-17 |  | 0 | Met | Madhavi Lanka | 147633
ST01717 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-020 | Bhopal | Central | 50 | Live | 2026-02-05 | 2026-03-09 | 2026-03-11 | 2026-04-06 | 2026-04-16 | 2 | Met | Nihal Shere | 124246
ST01718 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-021 | Nagpur | Central | 20 | Testing | 2026-01-22 | 2026-03-12 | 2026-03-13 | 2026-03-26 |  | 12 | Marginal | Faqid Savant | 80308
ST01719 | PRJ022 | CL005 | HDFC Bank | Indore Site-022 | Indore | Central | 20 | Live | 2026-01-20 | 2026-02-14 | 2026-02-18 | 2026-02-28 | 2026-03-05 | 4 | Met | Niharika Sunder | 219447
ST01720 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-023 | Bhopal | Central | 10 | Pending Acceptance | 2026-02-09 | 2026-03-22 | 2026-03-27 | 2026-04-09 | 2026-04-10 | 5 | Met | Dominic Kakar | 184932
ST01721 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-024 | Nagpur | Central | 100 | Installation Done | 2026-02-05 | 2026-04-05 | 2026-04-03 | 2026-05-04 |  | 12 | Marginal | Aarush Lall | 212633
ST01722 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-025 | Bhopal | Central | 20 | Live | 2026-02-08 | 2026-03-05 | 2026-03-12 | 2026-03-23 | 2026-03-27 | 7 | Met | Unni Bhagat | 256025
ST01723 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-026 | Bhopal | Central | 10 | Live | 2026-02-09 | 2026-03-19 | 2026-03-28 | 2026-04-03 | 2026-04-11 | 9 | Marginal | Ranveer Yadav | 184363
ST01724 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-027 | Bhopal | Central | 10 | Installation Scheduled | 2026-01-25 | 2026-02-26 | 2026-02-22 | 2026-03-15 |  | 1 | Met | Ranveer Yadav | 267387
ST01725 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-028 | Nagpur | Central | 50 | Installation Done | 2026-01-29 | 2026-02-19 | 2026-02-25 | 2026-03-09 |  | 12 | Marginal | Dipta Bhandari | 249042
ST01726 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-029 | Nagpur | Central | 50 | Installation Done | 2026-02-08 | 2026-04-05 | 2026-04-08 | 2026-04-30 |  | 12 | Marginal | Teerth Bhardwaj | 150218
ST01727 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-030 | Nagpur | Central | 20 | Live | 2026-02-09 | 2026-03-18 | 2026-03-23 | 2026-04-03 | 2026-04-11 | 5 | Met | Madhavi Lanka | 142181
ST01728 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-031 | Nagpur | Central | 200 | Installation Done | 2026-01-25 | 2026-03-11 | 2026-03-18 | 2026-04-09 |  | 12 | Marginal | Arya Shere | 256522
ST01729 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-032 | Bhopal | Central | 50 | Installation Done | 2026-01-25 | 2026-02-22 | 2026-02-19 | 2026-03-09 |  | 12 | Marginal | Ekansh Balay | 141977
ST01730 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-033 | Bhopal | Central | 50 | Testing | 2026-01-17 | 2026-03-14 | 2026-03-19 | 2026-04-12 |  | 12 | Marginal | Gavin Batta | 258586
ST01731 | PRJ022 | CL005 | HDFC Bank | Indore Site-034 | Indore | Central | 50 | ROW In Progress | 2026-01-29 | 2026-03-28 |  | 2026-04-11 |  | 5 | Met | Arya Shere | 149090
ST01732 | PRJ022 | CL005 | HDFC Bank | Indore Site-035 | Indore | Central | 50 | Live | 2026-01-22 | 2026-02-18 | 2026-02-20 | 2026-02-28 | 2026-03-11 | 2 | Met | Radhika Dugar | 107809
ST01733 | PRJ022 | CL005 | HDFC Bank | Indore Site-036 | Indore | Central | 10 | Live | 2026-02-04 | 2026-03-03 | 2026-03-06 | 2026-03-18 | 2026-03-27 | 3 | Met | Ekansh Balay | 58799
ST01734 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-037 | Nagpur | Central | 100 | Pending Acceptance | 2026-02-06 | 2026-04-01 | 2026-04-02 | 2026-04-18 | 2026-04-20 | 1 | Met | Upadhriti Wadhwa | 123904
ST01735 | PRJ022 | CL005 | HDFC Bank | Indore Site-038 | Indore | Central | 20 | Live | 2026-01-23 | 2026-02-15 | 2026-02-24 | 2026-03-15 | 2026-03-25 | 9 | Marginal | Teerth Bhardwaj | 104245
ST01736 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-039 | Bhopal | Central | 100 | Pending Acceptance | 2026-02-07 | 2026-02-28 | 2026-02-23 | 2026-03-27 | 2026-03-27 | 0 | Met | Ikbal Kothari | 88781
ST01737 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-040 | Bhopal | Central | 50 | Pending Acceptance | 2026-01-19 | 2026-03-03 | 2026-03-12 | 2026-03-15 | 2026-03-20 | 9 | Marginal | Yashica Issac | 99818
ST01738 | PRJ022 | CL005 | HDFC Bank | Indore Site-041 | Indore | Central | 50 | Live | 2026-02-07 | 2026-03-16 | 2026-03-16 | 2026-04-08 | 2026-04-19 | 0 | Met | Victor Kannan | 266286
ST01739 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-042 | Nagpur | Central | 20 | Live | 2026-02-07 | 2026-03-30 | 2026-03-26 | 2026-04-12 | 2026-04-24 | 0 | Met | Yashica Issac | 272984
ST01740 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-043 | Nagpur | Central | 20 | Pending Acceptance | 2026-02-07 | 2026-02-28 | 2026-03-08 | 2026-03-20 | 2026-03-21 | 8 | Marginal | Bhavika Sampath | 166320
ST01741 | PRJ022 | CL005 | HDFC Bank | Indore Site-044 | Indore | Central | 20 | ROW In Progress | 2026-01-30 | 2026-03-16 |  | 2026-04-05 |  | 6 | Met | Wriddhish Bhardwaj | 167691
ST01742 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-045 | Bhopal | Central | 20 | ROW In Progress | 2026-01-18 | 2026-02-09 |  | 2026-03-11 |  | 5 | Met | Bhavika Sampath | 185773
ST01743 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-046 | Bhopal | Central | 10 | Survey Pending | 2026-01-28 | 2026-03-09 |  | 2026-04-08 |  | 8 | Marginal | Diya Rattan | 51636
ST01744 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-047 | Bhopal | Central | 50 | Installation Done | 2026-02-07 | 2026-03-10 | 2026-03-09 | 2026-03-22 |  | 12 | Marginal | Isaac Patil | 128830
ST01745 | PRJ022 | CL005 | HDFC Bank | Indore Site-048 | Indore | Central | 20 | Live | 2026-01-23 | 2026-02-19 | 2026-02-27 | 2026-03-01 | 2026-03-07 | 8 | Marginal | Advay Contractor | 246651
ST01746 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-049 | Bhopal | Central | 10 | Live | 2026-02-02 | 2026-04-03 | 2026-03-31 | 2026-04-28 | 2026-04-30 | 0 | Met | Farhan Chada | 76882
ST01747 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-050 | Bhopal | Central | 100 | Installation Done | 2026-01-28 | 2026-03-11 | 2026-03-10 | 2026-04-06 |  | 12 | Marginal | Ekiya Suresh | 233965
ST01748 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-051 | Bhopal | Central | 50 | Testing | 2026-01-22 | 2026-03-19 | 2026-03-29 | 2026-04-05 |  | 12 | Marginal | Harini Choudhury | 233517
ST01749 | PRJ022 | CL005 | HDFC Bank | Indore Site-052 | Indore | Central | 20 | Pending Acceptance | 2026-01-28 | 2026-03-02 | 2026-03-04 | 2026-03-16 | 2026-03-18 | 2 | Met | Bhavika Sampath | 104464
ST01750 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-053 | Nagpur | Central | 50 | Testing | 2026-02-02 | 2026-04-01 | 2026-04-01 | 2026-04-11 |  | 12 | Marginal | Ranveer Yadav | 268573
ST01751 | PRJ022 | CL005 | HDFC Bank | Indore Site-054 | Indore | Central | 20 | Live | 2026-02-11 | 2026-03-17 | 2026-03-23 | 2026-04-03 | 2026-04-04 | 6 | Met | Nitesh Raghavan | 156888
ST01752 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-055 | Bhopal | Central | 10 | Installation Done | 2026-01-18 | 2026-03-09 | 2026-03-16 | 2026-03-21 |  | 12 | Marginal | Teerth Bhardwaj | 56943
ST01753 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-056 | Nagpur | Central | 20 | ROW In Progress | 2026-02-05 | 2026-03-28 |  | 2026-04-10 |  | 8 | Marginal | Farhan Chada | 144911
ST01754 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-057 | Bhopal | Central | 10 | ROW In Progress | 2026-02-01 | 2026-02-28 |  | 2026-03-14 |  | 6 | Met | Ikbal Kothari | 214032
ST01755 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-058 | Nagpur | Central | 100 | Installation Scheduled | 2026-02-03 | 2026-03-30 | 2026-03-30 | 2026-04-11 |  | 7 | Met | Devansh Nigam | 185019
ST01756 | PRJ022 | CL005 | HDFC Bank | Indore Site-059 | Indore | Central | 20 | Live | 2026-02-01 | 2026-03-05 | 2026-03-10 | 2026-03-29 | 2026-04-03 | 5 | Met | Aarush Lall | 100003
ST01757 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-060 | Bhopal | Central | 10 | Pending Acceptance | 2026-01-21 | 2026-02-19 | 2026-02-19 | 2026-03-17 | 2026-03-14 | 0 | Met | Ekavir Varkey | 111520
ST01758 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-061 | Bhopal | Central | 20 | Installation Scheduled | 2026-02-07 | 2026-04-04 | 2026-04-03 | 2026-05-04 |  | 2 | Met | Ikbal Kothari | 151175
ST01759 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-062 | Bhopal | Central | 10 | Installation Done | 2026-02-05 | 2026-03-18 | 2026-03-19 | 2026-04-08 |  | 12 | Marginal | Faqid Savant | 108502
ST01760 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-063 | Nagpur | Central | 200 | Live | 2026-02-01 | 2026-03-08 | 2026-03-05 | 2026-04-07 | 2026-04-07 | 0 | Met | Tara Dhar | 116186
ST01761 | PRJ022 | CL005 | HDFC Bank | Indore Site-064 | Indore | Central | 100 | Live | 2026-02-01 | 2026-03-10 | 2026-03-08 | 2026-03-27 | 2026-03-24 | 0 | Met | Urvashi Ray | 105061
ST01762 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-065 | Nagpur | Central | 10 | Pending Acceptance | 2026-02-10 | 2026-03-09 | 2026-03-14 | 2026-03-23 | 2026-03-20 | 5 | Met | Alka Wable | 248100
ST01763 | PRJ022 | CL005 | HDFC Bank | Indore Site-066 | Indore | Central | 100 | ROW In Progress | 2026-02-07 | 2026-03-02 |  | 2026-03-28 |  | 4 | Met | Siddharth Zacharia | 194660
ST01764 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-067 | Nagpur | Central | 50 | Installation Done | 2026-01-28 | 2026-03-13 | 2026-03-10 | 2026-04-02 |  | 12 | Marginal | Vansha Thakkar | 56805
ST01765 | PRJ022 | CL005 | HDFC Bank | Indore Site-068 | Indore | Central | 50 | Installation Scheduled | 2026-02-04 | 2026-02-28 | 2026-02-28 | 2026-03-30 |  | 1 | Met | Gavin Batta | 157228
ST01766 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-069 | Nagpur | Central | 50 | Installation Scheduled | 2026-01-19 | 2026-03-16 | 2026-03-21 | 2026-04-05 |  | 6 | Met | Anamika Kanda | 194310
ST01767 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-070 | Nagpur | Central | 200 | ROW In Progress | 2026-02-09 | 2026-03-25 |  | 2026-04-22 |  | 3 | Met | Girindra Chatterjee | 163190
ST01768 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-071 | Nagpur | Central | 10 | Installation Done | 2026-02-11 | 2026-03-14 | 2026-03-10 | 2026-04-08 |  | 12 | Marginal | Radhika Dugar | 49760
ST01769 | PRJ022 | CL005 | HDFC Bank | Indore Site-072 | Indore | Central | 10 | ROW In Progress | 2026-01-22 | 2026-02-11 |  | 2026-02-23 |  | 7 | Met | Radhika Dugar | 236093
ST01770 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-073 | Nagpur | Central | 100 | ROW In Progress | 2026-01-26 | 2026-02-19 |  | 2026-03-07 |  | 3 | Met | Girik Khalsa | 166309
ST01771 | PRJ022 | CL005 | HDFC Bank | Nagpur Site-074 | Nagpur | Central | 200 | Testing | 2026-01-31 | 2026-03-17 | 2026-03-13 | 2026-04-14 |  | 12 | Marginal | Vansha Thakkar | 101523
ST01772 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-075 | Bhopal | Central | 200 | ROW In Progress | 2026-02-01 | 2026-03-23 |  | 2026-04-09 |  | 1 | Met | Isaac Patil | 79564
ST01773 | PRJ022 | CL005 | HDFC Bank | Indore Site-076 | Indore | Central | 200 | Live | 2026-02-07 | 2026-02-28 | 2026-03-09 | 2026-03-20 | 2026-04-01 | 9 | Marginal | Tanay Rattan | 137383
ST01774 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-077 | Bhopal | Central | 200 | Live | 2026-01-23 | 2026-03-24 | 2026-03-28 | 2026-04-09 | 2026-04-09 | 4 | Met | Gavin Batta | 210141
ST01775 | PRJ022 | CL005 | HDFC Bank | Indore Site-078 | Indore | Central | 10 | Installation Scheduled | 2026-01-23 | 2026-02-13 | 2026-02-18 | 2026-02-28 |  | 3 | Met | Aarush Lall | 56974
ST01776 | PRJ022 | CL005 | HDFC Bank | Bhopal Site-079 | Bhopal | Central | 100 | ROW In Progress | 2026-01-19 | 2026-03-02 |  | 2026-03-12 |  | 5 | Met | Arya Shere | 116378
ST01777 | PRJ022 | CL005 | HDFC Bank | Indore Site-080 | Indore | Central | 10 | Testing | 2026-01-31 | 2026-03-10 | 2026-03-20 | 2026-03-20 |  | 12 | Marginal | Ekbal Garg | 81773
ST01778 | PRJ022 | CL005 | HDFC Bank | Indore Site-081 | Indore | Central | 100 | Pending Acceptance | 2026-01-31 | 2026-03-17 | 2026-03-21 | 2026-04-05 | 2026-04-15 | 4 | Met | Girik Khalsa | 123051
ST01779 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-001 | Kolkata | East | 20 | ROW In Progress | 2025-11-26 | 2025-12-26 |  | 2026-01-09 |  | 0 | Met | Wriddhish Bhardwaj | 126271
ST01780 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-002 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-11-21 | 2026-01-06 | 2026-01-07 | 2026-02-05 |  | 1 | Met | Arya Sunder | 105814
ST01781 | PRJ023 | CL005 | HDFC Bank | Patna Site-003 | Patna | East | 10 | Installation Done | 2025-12-01 | 2026-01-16 | 2026-01-23 | 2026-02-12 |  | 12 | Marginal | Diya Rattan | 189747
ST01782 | PRJ023 | CL005 | HDFC Bank | Patna Site-004 | Patna | East | 20 | Installation Scheduled | 2025-12-05 | 2026-01-03 | 2026-01-06 | 2026-01-25 |  | 0 | Met | Gavin Batta | 214511
ST01783 | PRJ023 | CL005 | HDFC Bank | Patna Site-005 | Patna | East | 20 | Pending Acceptance | 2025-11-27 | 2026-01-04 | 2026-01-01 | 2026-01-28 | 2026-02-02 | 0 | Met | Diya Rattan | 124193
ST01784 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-006 | Kolkata | East | 10 | Live | 2025-11-14 | 2025-12-13 | 2025-12-15 | 2026-01-09 | 2026-01-17 | 2 | Met | Yashica Issac | 87463
ST01785 | PRJ023 | CL005 | HDFC Bank | Patna Site-007 | Patna | East | 20 | Testing | 2025-11-21 | 2026-01-07 | 2026-01-14 | 2026-01-27 |  | 12 | Marginal | Mohammed Gupta | 242029
ST01786 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-008 | Bhubaneswar | East | 200 | Live | 2025-12-07 | 2026-01-06 | 2026-01-07 | 2026-01-22 | 2026-01-23 | 1 | Met | Yashica Cherian | 208475
ST01787 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-009 | Kolkata | East | 200 | Survey Pending | 2025-11-13 | 2025-12-11 |  | 2025-12-31 |  | 6 | Met | Devansh Rajan | 101498
ST01788 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-010 | Kolkata | East | 100 | Live | 2025-11-20 | 2025-12-11 | 2025-12-13 | 2025-12-27 | 2026-01-01 | 2 | Met | Dipta Bhandari | 160598
ST01789 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-011 | Kolkata | East | 100 | Live | 2025-11-16 | 2026-01-02 | 2026-01-11 | 2026-01-23 | 2026-01-20 | 9 | Marginal | Nitesh Raghavan | 82222
ST01790 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-012 | Bhubaneswar | East | 20 | Testing | 2025-11-24 | 2026-01-03 | 2026-01-05 | 2026-01-14 |  | 12 | Marginal | Ekavir Bhargava | 213232
ST01791 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-013 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-11-15 | 2025-12-16 | 2025-12-18 | 2026-01-13 |  | 8 | Marginal | Quincy Biswas | 89728
ST01792 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-014 | Kolkata | East | 200 | Survey Pending | 2025-11-21 | 2025-12-19 |  | 2025-12-30 |  | 2 | Met | Ekavir Varkey | 165180
ST01793 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-015 | Kolkata | East | 20 | Pending Acceptance | 2025-12-08 | 2026-02-03 | 2026-01-29 | 2026-02-15 | 2026-02-26 | 0 | Met | Yashica Issac | 218517
ST01794 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-016 | Kolkata | East | 200 | Installation Scheduled | 2025-11-24 | 2025-12-17 | 2025-12-26 | 2026-01-09 |  | 4 | Met | Dipta Bhandari | 236272
ST01795 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-017 | Kolkata | East | 100 | Live | 2025-11-28 | 2026-01-27 | 2026-02-06 | 2026-02-16 | 2026-02-21 | 10 | Marginal | Devansh Rajan | 208131
ST01796 | PRJ023 | CL005 | HDFC Bank | Patna Site-018 | Patna | East | 200 | Pending Acceptance | 2025-11-18 | 2025-12-24 | 2025-12-20 | 2026-01-15 | 2026-01-23 | 0 | Met | Siddharth Zacharia | 185724
ST01797 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-019 | Bhubaneswar | East | 50 | ROW In Progress | 2025-12-04 | 2026-01-23 |  | 2026-02-22 |  | 2 | Met | Yatin Baral | 273644
ST01798 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-020 | Kolkata | East | 100 | ROW In Progress | 2025-11-23 | 2026-01-20 |  | 2026-01-31 |  | 5 | Met | Chandresh Zachariah | 243770
ST01799 | PRJ023 | CL005 | HDFC Bank | Patna Site-021 | Patna | East | 20 | Installation Scheduled | 2025-11-21 | 2026-01-12 | 2026-01-11 | 2026-01-29 |  | 7 | Met | Wriddhish Bhardwaj | 163323
ST01800 | PRJ023 | CL005 | HDFC Bank | Patna Site-022 | Patna | East | 10 | Live | 2025-11-15 | 2025-12-16 | 2025-12-14 | 2025-12-30 | 2025-12-29 | 0 | Met | Simon Tata | 76254
ST01801 | PRJ023 | CL005 | HDFC Bank | Patna Site-023 | Patna | East | 200 | Installation Done | 2025-11-29 | 2025-12-21 | 2025-12-23 | 2026-01-11 |  | 12 | Marginal | Tanay Rattan | 256639
ST01802 | PRJ023 | CL005 | HDFC Bank | Patna Site-024 | Patna | East | 100 | Testing | 2025-12-04 | 2025-12-28 | 2026-01-06 | 2026-01-08 |  | 12 | Marginal | Ekavir Varkey | 226819
ST01803 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-025 | Kolkata | East | 200 | Live | 2025-11-20 | 2026-01-17 | 2026-01-16 | 2026-02-07 | 2026-02-07 | 0 | Met | Jai Kota | 227044
ST01804 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-026 | Bhubaneswar | East | 20 | ROW In Progress | 2025-11-23 | 2025-12-20 |  | 2026-01-14 |  | 1 | Met | Ekiya Suresh | 82251
ST01805 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-027 | Bhubaneswar | East | 20 | Pending Acceptance | 2025-12-06 | 2026-01-11 | 2026-01-13 | 2026-01-28 | 2026-02-08 | 2 | Met | Yashica Issac | 50626
ST01806 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-028 | Bhubaneswar | East | 100 | Live | 2025-11-17 | 2025-12-16 | 2025-12-14 | 2026-01-07 | 2026-01-09 | 0 | Met | Girindra Chatterjee | 224594
ST01807 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-029 | Bhubaneswar | East | 10 | Testing | 2025-12-03 | 2026-01-16 | 2026-01-17 | 2026-02-01 |  | 12 | Marginal | Farhan Chada | 98046
ST01808 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-030 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-11-27 | 2025-12-18 | 2025-12-22 | 2026-01-13 |  | 8 | Marginal | Irya Sampath | 48078
ST01809 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-031 | Bhubaneswar | East | 200 | Installation Done | 2025-12-08 | 2026-01-07 | 2026-01-02 | 2026-01-28 |  | 12 | Marginal | Arya Shere | 245790
ST01810 | PRJ023 | CL005 | HDFC Bank | Patna Site-032 | Patna | East | 100 | Live | 2025-11-15 | 2026-01-13 | 2026-01-18 | 2026-01-29 | 2026-02-09 | 5 | Met | Jai Kota | 208555
ST01811 | PRJ023 | CL005 | HDFC Bank | Patna Site-033 | Patna | East | 100 | Live | 2025-11-25 | 2026-01-11 | 2026-01-12 | 2026-01-26 | 2026-02-02 | 1 | Met | Siddharth Zacharia | 115256
ST01812 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-034 | Kolkata | East | 20 | Installation Done | 2025-11-28 | 2026-01-17 | 2026-01-22 | 2026-02-01 |  | 12 | Marginal | Ikbal Kothari | 193698
ST01813 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-035 | Kolkata | East | 10 | Survey Pending | 2025-11-15 | 2025-12-30 |  | 2026-01-20 |  | 8 | Marginal | Aarush Lall | 257211
ST01814 | PRJ023 | CL005 | HDFC Bank | Patna Site-036 | Patna | East | 20 | ROW In Progress | 2025-12-03 | 2026-01-15 |  | 2026-02-12 |  | 2 | Met | Ekansh Balay | 75677
ST01815 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-037 | Kolkata | East | 200 | Installation Scheduled | 2025-12-07 | 2026-01-22 | 2026-01-23 | 2026-02-02 |  | 2 | Met | Urvashi Ray | 127786
ST01816 | PRJ023 | CL005 | HDFC Bank | Patna Site-038 | Patna | East | 20 | Live | 2025-11-25 | 2025-12-29 | 2026-01-06 | 2026-01-15 | 2026-01-26 | 8 | Marginal | Niharika Sunder | 90183
ST01817 | PRJ023 | CL005 | HDFC Bank | Patna Site-039 | Patna | East | 10 | Live | 2025-12-04 | 2026-01-04 | 2025-12-31 | 2026-01-27 | 2026-02-05 | 0 | Met | Irya Sampath | 218865
ST01818 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-040 | Bhubaneswar | East | 20 | Testing | 2025-11-13 | 2026-01-07 | 2026-01-12 | 2026-01-20 |  | 12 | Marginal | Ekapad Walia | 234753
ST01819 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-041 | Kolkata | East | 20 | Installation Scheduled | 2025-11-30 | 2025-12-22 | 2025-12-18 | 2026-01-09 |  | 8 | Marginal | Yashica Issac | 61838
ST01820 | PRJ023 | CL005 | HDFC Bank | Patna Site-042 | Patna | East | 50 | ROW In Progress | 2025-11-17 | 2025-12-13 |  | 2025-12-28 |  | 1 | Met | Ekavir Varkey | 179050
ST01821 | PRJ023 | CL005 | HDFC Bank | Patna Site-043 | Patna | East | 200 | Pending Acceptance | 2025-11-16 | 2025-12-29 | 2025-12-28 | 2026-01-21 | 2026-01-31 | 0 | Met | Wahab Raval | 150241
ST01822 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-044 | Bhubaneswar | East | 50 | Live | 2025-11-16 | 2026-01-12 | 2026-01-10 | 2026-02-07 | 2026-02-14 | 0 | Met | Tara Dhar | 147095
ST01823 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-045 | Bhubaneswar | East | 20 | Pending Acceptance | 2025-12-07 | 2026-01-04 | 2025-12-30 | 2026-01-15 | 2026-01-24 | 0 | Met | Yatin Baral | 175502
ST01824 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-046 | Bhubaneswar | East | 100 | Live | 2025-11-28 | 2026-01-02 | 2026-01-07 | 2026-01-28 | 2026-02-04 | 5 | Met | Girik Khalsa | 118864
ST01825 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-047 | Bhubaneswar | East | 50 | Live | 2025-12-07 | 2026-01-03 | 2026-01-11 | 2026-01-17 | 2026-01-20 | 8 | Marginal | Isaac Patil | 74305
ST01826 | PRJ023 | CL005 | HDFC Bank | Patna Site-048 | Patna | East | 20 | ROW In Progress | 2025-11-26 | 2025-12-25 |  | 2026-01-09 |  | 1 | Met | Isaac Patil | 49484
ST01827 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-049 | Bhubaneswar | East | 200 | Live | 2025-11-14 | 2025-12-22 | 2025-12-22 | 2026-01-20 | 2026-01-25 | 0 | Met | Kabir Soman | 253624
ST01828 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-050 | Kolkata | East | 200 | Installation Scheduled | 2025-11-28 | 2026-01-19 | 2026-01-17 | 2026-01-31 |  | 7 | Met | Mohammed Gupta | 85219
ST01829 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-051 | Bhubaneswar | East | 200 | Testing | 2025-12-02 | 2026-01-30 | 2026-02-02 | 2026-02-27 |  | 12 | Marginal | Michael Dutta | 215836
ST01830 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-052 | Kolkata | East | 20 | Installation Done | 2025-11-19 | 2025-12-16 | 2025-12-11 | 2025-12-27 |  | 12 | Marginal | Madhavi Lanka | 155689
ST01831 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-053 | Bhubaneswar | East | 10 | Survey Pending | 2025-12-05 | 2026-01-04 |  | 2026-01-14 |  | 0 | Met | Darsh Rau | 96565
ST01832 | PRJ023 | CL005 | HDFC Bank | Patna Site-054 | Patna | East | 20 | ROW In Progress | 2025-11-23 | 2025-12-25 |  | 2026-01-21 |  | 6 | Met | Michael Dutta | 46008
ST01833 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-055 | Bhubaneswar | East | 200 | Live | 2025-11-23 | 2025-12-24 | 2025-12-27 | 2026-01-10 | 2026-01-14 | 3 | Met | Ekbal Garg | 138134
ST01834 | PRJ023 | CL005 | HDFC Bank | Patna Site-056 | Patna | East | 10 | Live | 2025-11-26 | 2026-01-24 | 2026-01-24 | 2026-02-21 | 2026-02-19 | 0 | Met | Mohammed Gupta | 149361
ST01835 | PRJ023 | CL005 | HDFC Bank | Patna Site-057 | Patna | East | 20 | Live | 2025-11-18 | 2026-01-06 | 2026-01-14 | 2026-01-23 | 2026-01-27 | 8 | Marginal | Ekapad Walia | 276214
ST01836 | PRJ023 | CL005 | HDFC Bank | Patna Site-058 | Patna | East | 100 | Testing | 2025-11-25 | 2025-12-28 | 2025-12-29 | 2026-01-22 |  | 12 | Marginal | Theodore Devi | 177555
ST01837 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-059 | Bhubaneswar | East | 100 | Live | 2025-12-03 | 2026-01-26 | 2026-02-02 | 2026-02-10 | 2026-02-19 | 7 | Met | Devansh Rajan | 109967
ST01838 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-060 | Bhubaneswar | East | 20 | Testing | 2025-12-07 | 2026-01-02 | 2025-12-28 | 2026-01-14 |  | 12 | Marginal | Yashica Cherian | 219017
ST01839 | PRJ023 | CL005 | HDFC Bank | Patna Site-061 | Patna | East | 50 | Live | 2025-11-19 | 2025-12-23 | 2025-12-22 | 2026-01-05 | 2026-01-09 | 0 | Met | Isaac Patil | 165871
ST01840 | PRJ023 | CL005 | HDFC Bank | Patna Site-062 | Patna | East | 10 | Testing | 2025-11-15 | 2026-01-07 | 2026-01-17 | 2026-01-27 |  | 12 | Marginal | Girik Khalsa | 279790
ST01841 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-063 | Bhubaneswar | East | 50 | Installation Done | 2025-11-16 | 2025-12-08 | 2025-12-16 | 2026-01-07 |  | 12 | Marginal | Kashvi Edwin | 46644
ST01842 | PRJ023 | CL005 | HDFC Bank | Patna Site-064 | Patna | East | 20 | Live | 2025-11-30 | 2026-01-22 | 2026-01-20 | 2026-02-21 | 2026-02-26 | 0 | Met | Priya Rastogi | 207835
ST01843 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-065 | Kolkata | East | 200 | Installation Done | 2025-11-27 | 2026-01-12 | 2026-01-10 | 2026-02-05 |  | 12 | Marginal | Upadhriti Wadhwa | 137364
ST01844 | PRJ023 | CL005 | HDFC Bank | Patna Site-066 | Patna | East | 100 | Installation Done | 2025-11-30 | 2026-01-04 | 2026-01-08 | 2026-01-25 |  | 12 | Marginal | Ekiya Suresh | 237524
ST01845 | PRJ023 | CL005 | HDFC Bank | Patna Site-067 | Patna | East | 50 | Survey Pending | 2025-12-05 | 2026-01-03 |  | 2026-01-25 |  | 6 | Met | Girik Khalsa | 184949
ST01846 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-068 | Bhubaneswar | East | 100 | Live | 2025-12-02 | 2026-01-13 | 2026-01-11 | 2026-01-27 | 2026-02-03 | 0 | Met | Ekapad Walia | 125752
ST01847 | PRJ023 | CL005 | HDFC Bank | Patna Site-069 | Patna | East | 20 | Installation Done | 2025-12-01 | 2025-12-31 | 2026-01-05 | 2026-01-20 |  | 12 | Marginal | Victor Kannan | 220941
ST01848 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-070 | Bhubaneswar | East | 200 | Testing | 2025-11-13 | 2025-12-31 | 2026-01-04 | 2026-01-14 |  | 12 | Marginal | Anamika Kanda | 161667
ST01849 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-071 | Bhubaneswar | East | 200 | Testing | 2025-11-17 | 2026-01-15 | 2026-01-23 | 2026-02-07 |  | 12 | Marginal | Arya Sunder | 61496
ST01850 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-072 | Bhubaneswar | East | 10 | Testing | 2025-11-25 | 2026-01-15 | 2026-01-10 | 2026-02-11 |  | 12 | Marginal | Teerth Bhardwaj | 125476
ST01851 | PRJ023 | CL005 | HDFC Bank | Patna Site-073 | Patna | East | 100 | Live | 2025-11-21 | 2026-01-15 | 2026-01-21 | 2026-02-13 | 2026-02-19 | 6 | Met | Ekavir Bhargava | 64731
ST01852 | PRJ023 | CL005 | HDFC Bank | Patna Site-074 | Patna | East | 100 | ROW In Progress | 2025-12-02 | 2026-01-23 |  | 2026-02-11 |  | 1 | Met | Dipta Bhandari | 108578
ST01853 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-075 | Bhubaneswar | East | 200 | Live | 2025-11-29 | 2026-01-28 | 2026-02-02 | 2026-02-13 | 2026-02-22 | 5 | Met | Devansh Rajan | 144829
ST01854 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-076 | Bhubaneswar | East | 10 | Live | 2025-11-30 | 2025-12-21 | 2025-12-24 | 2026-01-09 | 2026-01-16 | 3 | Met | Kashvi Edwin | 218770
ST01855 | PRJ023 | CL005 | HDFC Bank | Patna Site-077 | Patna | East | 10 | Installation Done | 2025-11-25 | 2025-12-15 | 2025-12-20 | 2025-12-30 |  | 12 | Marginal | Diya Rattan | 87998
ST01856 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-078 | Bhubaneswar | East | 50 | ROW In Progress | 2025-11-27 | 2025-12-19 |  | 2026-01-10 |  | 6 | Met | Tara Dhar | 49739
ST01857 | PRJ023 | CL005 | HDFC Bank | Patna Site-079 | Patna | East | 10 | ROW In Progress | 2025-11-30 | 2026-01-05 |  | 2026-01-26 |  | 8 | Marginal | Alka Wable | 45142
ST01858 | PRJ023 | CL005 | HDFC Bank | Patna Site-080 | Patna | East | 100 | Live | 2025-12-01 | 2026-01-25 | 2026-01-26 | 2026-02-05 | 2026-02-12 | 1 | Met | Kevin Solanki | 219786
ST01859 | PRJ023 | CL005 | HDFC Bank | Patna Site-081 | Patna | East | 10 | Testing | 2025-12-02 | 2026-01-29 | 2026-02-08 | 2026-02-16 |  | 12 | Marginal | Darsh Rau | 154050
ST01860 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-082 | Kolkata | East | 10 | Survey Pending | 2025-11-27 | 2026-01-09 |  | 2026-01-19 |  | 0 | Met | Kabir Soman | 57038
ST01861 | PRJ023 | CL005 | HDFC Bank | Patna Site-083 | Patna | East | 20 | Installation Scheduled | 2025-11-25 | 2026-01-09 | 2026-01-07 | 2026-02-06 |  | 5 | Met | Anamika Kanda | 138699
ST01862 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-084 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-11-30 | 2026-01-05 | 2026-01-06 | 2026-01-29 |  | 8 | Marginal | Madhavi Lanka | 162656
ST01863 | PRJ023 | CL005 | HDFC Bank | Patna Site-085 | Patna | East | 200 | Survey Pending | 2025-12-07 | 2026-01-26 |  | 2026-02-05 |  | 1 | Met | Vansha Thakkar | 87466
ST01864 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-086 | Bhubaneswar | East | 100 | Live | 2025-12-08 | 2025-12-30 | 2025-12-25 | 2026-01-12 | 2026-01-15 | 0 | Met | Logan Sami | 277929
ST01865 | PRJ023 | CL005 | HDFC Bank | Patna Site-087 | Patna | East | 50 | ROW In Progress | 2025-11-20 | 2025-12-27 |  | 2026-01-15 |  | 4 | Met | Harini Choudhury | 202667
ST01866 | PRJ023 | CL005 | HDFC Bank | Patna Site-088 | Patna | East | 200 | Pending Acceptance | 2025-11-25 | 2026-01-14 | 2026-01-17 | 2026-02-03 | 2026-02-13 | 3 | Met | Girik Khalsa | 259564
ST01867 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-089 | Bhubaneswar | East | 10 | ROW In Progress | 2025-11-14 | 2025-12-28 |  | 2026-01-11 |  | 2 | Met | Girindra Chatterjee | 135228
ST01868 | PRJ023 | CL005 | HDFC Bank | Patna Site-090 | Patna | East | 20 | Testing | 2025-11-28 | 2025-12-26 | 2025-12-31 | 2026-01-18 |  | 12 | Marginal | Isaac Patil | 269161
ST01869 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-091 | Kolkata | East | 50 | ROW In Progress | 2025-11-13 | 2025-12-24 |  | 2026-01-10 |  | 3 | Met | Bhavika Sampath | 252913
ST01870 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-092 | Kolkata | East | 50 | Installation Scheduled | 2025-11-22 | 2026-01-11 | 2026-01-18 | 2026-01-30 |  | 8 | Marginal | Girindra Chatterjee | 142613
ST01871 | PRJ023 | CL005 | HDFC Bank | Patna Site-093 | Patna | East | 200 | Installation Scheduled | 2025-11-26 | 2026-01-05 | 2026-01-05 | 2026-01-18 |  | 3 | Met | Alka Wable | 126930
ST01872 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-094 | Kolkata | East | 50 | Installation Done | 2025-11-15 | 2025-12-13 | 2025-12-17 | 2026-01-02 |  | 12 | Marginal | Kabir Soman | 71641
ST01873 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-095 | Kolkata | East | 20 | Live | 2025-12-02 | 2025-12-25 | 2025-12-20 | 2026-01-11 | 2026-01-20 | 0 | Met | Isaac Patil | 68961
ST01874 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-096 | Kolkata | East | 100 | Pending Acceptance | 2025-12-07 | 2026-01-26 | 2026-01-28 | 2026-02-25 | 2026-02-26 | 2 | Met | Wahab Raval | 86170
ST01875 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-097 | Bhubaneswar | East | 200 | Live | 2025-11-30 | 2026-01-23 | 2026-01-25 | 2026-02-21 | 2026-03-01 | 2 | Met | Girindra Chatterjee | 231742
ST01876 | PRJ023 | CL005 | HDFC Bank | Patna Site-098 | Patna | East | 20 | Installation Scheduled | 2025-11-23 | 2025-12-23 | 2025-12-23 | 2026-01-20 |  | 4 | Met | Darsh Rau | 81685
ST01877 | PRJ023 | CL005 | HDFC Bank | Patna Site-099 | Patna | East | 100 | Live | 2025-11-16 | 2025-12-31 | 2025-12-29 | 2026-01-26 | 2026-02-02 | 0 | Met | Logan Sami | 206204
ST01878 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-100 | Kolkata | East | 10 | Installation Done | 2025-11-14 | 2025-12-25 | 2025-12-21 | 2026-01-20 |  | 12 | Marginal | Ranveer Yadav | 125875
ST01879 | PRJ023 | CL005 | HDFC Bank | Patna Site-101 | Patna | East | 100 | ROW In Progress | 2025-11-27 | 2026-01-15 |  | 2026-02-03 |  | 4 | Met | Siddharth Zacharia | 245457
ST01880 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-102 | Bhubaneswar | East | 10 | Live | 2025-11-24 | 2025-12-23 | 2025-12-27 | 2026-01-16 | 2026-01-22 | 4 | Met | Dipta Bhandari | 76216
ST01881 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-103 | Bhubaneswar | East | 50 | Testing | 2025-12-05 | 2026-01-30 | 2026-02-08 | 2026-02-15 |  | 12 | Marginal | Ekavir Varkey | 267142
ST01882 | PRJ023 | CL005 | HDFC Bank | Patna Site-104 | Patna | East | 10 | Installation Scheduled | 2025-11-23 | 2025-12-27 | 2026-01-06 | 2026-01-22 |  | 8 | Marginal | Alka Wable | 96179
ST01883 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-105 | Kolkata | East | 20 | Installation Done | 2025-11-26 | 2025-12-21 | 2025-12-18 | 2026-01-06 |  | 12 | Marginal | Isaac Patil | 156967
ST01884 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-106 | Kolkata | East | 10 | Installation Done | 2025-11-29 | 2026-01-22 | 2026-01-22 | 2026-02-18 |  | 12 | Marginal | Ikbal Kothari | 253248
ST01885 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-107 | Kolkata | East | 200 | Installation Done | 2025-11-28 | 2025-12-30 | 2025-12-25 | 2026-01-18 |  | 12 | Marginal | Madhavi Lanka | 93222
ST01886 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-108 | Bhubaneswar | East | 100 | Live | 2025-11-23 | 2025-12-24 | 2025-12-22 | 2026-01-17 | 2026-01-23 | 0 | Met | Girindra Chatterjee | 263033
ST01887 | PRJ023 | CL005 | HDFC Bank | Patna Site-109 | Patna | East | 10 | Installation Scheduled | 2025-11-23 | 2025-12-27 | 2026-01-06 | 2026-01-22 |  | 0 | Met | Devansh Rajan | 138386
ST01888 | PRJ023 | CL005 | HDFC Bank | Bhubaneswar Site-110 | Bhubaneswar | East | 10 | Live | 2025-11-19 | 2025-12-27 | 2025-12-30 | 2026-01-18 | 2026-01-30 | 3 | Met | Dakshesh Trivedi | 161049
ST01889 | PRJ023 | CL005 | HDFC Bank | Patna Site-111 | Patna | East | 10 | Installation Done | 2025-11-18 | 2026-01-14 | 2026-01-21 | 2026-02-11 |  | 12 | Marginal | Kevin Solanki | 103847
ST01890 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-112 | Kolkata | East | 50 | Live | 2025-11-17 | 2026-01-13 | 2026-01-16 | 2026-02-04 | 2026-02-14 | 3 | Met | Unni Bhagat | 58804
ST01891 | PRJ023 | CL005 | HDFC Bank | Patna Site-113 | Patna | East | 10 | Testing | 2025-12-01 | 2025-12-22 | 2025-12-18 | 2026-01-04 |  | 12 | Marginal | Unni Bhagat | 170748
ST01892 | PRJ023 | CL005 | HDFC Bank | Kolkata Site-114 | Kolkata | East | 10 | Testing | 2025-11-30 | 2026-01-03 | 2026-01-08 | 2026-01-18 |  | 12 | Marginal | Theodore Devi | 186637
ST01893 | PRJ023 | CL005 | HDFC Bank | Patna Site-115 | Patna | East | 50 | Installation Done | 2025-11-29 | 2026-01-06 | 2026-01-10 | 2026-01-21 |  | 12 | Marginal | Faqid Savant | 117596
ST01894 | PRJ023 | CL005 | HDFC Bank | Patna Site-116 | Patna | East | 200 | Pending Acceptance | 2025-12-07 | 2026-01-29 | 2026-02-02 | 2026-02-27 | 2026-03-10 | 4 | Met | Logan Sami | 159829
ST01895 | PRJ024 | CL005 | HDFC Bank | Indore Site-001 | Indore | Central | 200 | Installation Done | 2025-11-14 | 2025-12-19 | 2025-12-23 | 2026-01-03 |  | 12 | Marginal | Theodore Devi | 144014
ST01896 | PRJ024 | CL005 | HDFC Bank | Indore Site-002 | Indore | Central | 200 | Installation Scheduled | 2025-11-26 | 2026-01-11 | 2026-01-08 | 2026-01-22 |  | 1 | Met | Dipta Bhandari | 129758
ST01897 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-003 | Nagpur | Central | 10 | Live | 2025-11-14 | 2026-01-07 | 2026-01-11 | 2026-01-30 | 2026-02-04 | 4 | Met | Logan Sami | 77621
ST01898 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-004 | Bhopal | Central | 100 | ROW In Progress | 2025-11-21 | 2026-01-14 |  | 2026-01-24 |  | 2 | Met | Kabir Soman | 47168
ST01899 | PRJ024 | CL005 | HDFC Bank | Indore Site-005 | Indore | Central | 200 | ROW In Progress | 2025-11-17 | 2025-12-20 |  | 2026-01-12 |  | 2 | Met | Devansh Rajan | 114021
ST01900 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-006 | Nagpur | Central | 200 | Installation Scheduled | 2025-11-12 | 2025-12-31 | 2025-12-29 | 2026-01-26 |  | 3 | Met | Urvashi Ray | 253207
ST01901 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-007 | Bhopal | Central | 100 | Pending Acceptance | 2025-11-22 | 2026-01-07 | 2026-01-03 | 2026-01-30 | 2026-02-11 | 0 | Met | Devansh Nigam | 227235
ST01902 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-008 | Nagpur | Central | 200 | Live | 2025-11-24 | 2025-12-14 | 2025-12-14 | 2025-12-29 | 2026-01-03 | 0 | Met | Teerth Bhardwaj | 245608
ST01903 | PRJ024 | CL005 | HDFC Bank | Indore Site-009 | Indore | Central | 200 | Live | 2025-11-28 | 2026-01-09 | 2026-01-07 | 2026-01-26 | 2026-02-02 | 0 | Met | Teerth Bhardwaj | 80595
ST01904 | PRJ024 | CL005 | HDFC Bank | Indore Site-010 | Indore | Central | 200 | ROW In Progress | 2025-11-12 | 2025-12-14 |  | 2025-12-24 |  | 6 | Met | Advay Contractor | 251788
ST01905 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-011 | Bhopal | Central | 200 | Live | 2025-11-12 | 2025-12-04 | 2025-12-05 | 2025-12-23 | 2025-12-26 | 1 | Met | Yatin Baral | 244231
ST01906 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-012 | Nagpur | Central | 100 | Live | 2025-11-20 | 2026-01-10 | 2026-01-11 | 2026-02-06 | 2026-02-18 | 1 | Met | Ikbal Kothari | 179209
ST01907 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-013 | Bhopal | Central | 10 | Live | 2025-11-10 | 2025-12-25 | 2025-12-29 | 2026-01-19 | 2026-01-30 | 4 | Met | Jai Kota | 69718
ST01908 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-014 | Bhopal | Central | 200 | Live | 2025-11-23 | 2025-12-13 | 2025-12-11 | 2026-01-03 | 2026-01-06 | 0 | Met | Tanay Rattan | 51079
ST01909 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-015 | Bhopal | Central | 20 | Testing | 2025-11-16 | 2025-12-14 | 2025-12-20 | 2026-01-01 |  | 12 | Marginal | Dominic Kakar | 113672
ST01910 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-016 | Bhopal | Central | 50 | Live | 2025-11-09 | 2025-12-13 | 2025-12-10 | 2026-01-11 | 2026-01-09 | 0 | Met | Mohammed Gupta | 166064
ST01911 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-017 | Bhopal | Central | 10 | Survey Pending | 2025-11-28 | 2026-01-04 |  | 2026-01-16 |  | 0 | Met | Wahab Raval | 225739
ST01912 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-018 | Nagpur | Central | 50 | Live | 2025-11-12 | 2025-12-08 | 2025-12-09 | 2025-12-23 | 2025-12-28 | 1 | Met | Devika Rastogi | 265250
ST01913 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-019 | Nagpur | Central | 10 | Live | 2025-11-05 | 2026-01-03 | 2026-01-13 | 2026-02-01 | 2026-02-07 | 10 | Marginal | Aarush Lall | 82800
ST01914 | PRJ024 | CL005 | HDFC Bank | Indore Site-020 | Indore | Central | 100 | Testing | 2025-11-18 | 2025-12-09 | 2025-12-19 | 2025-12-23 |  | 12 | Marginal | Jai Kota | 271898
ST01915 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-021 | Nagpur | Central | 100 | Installation Done | 2025-11-09 | 2025-12-10 | 2025-12-16 | 2025-12-22 |  | 12 | Marginal | Arya Sunder | 252998
ST01916 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-022 | Bhopal | Central | 20 | ROW In Progress | 2025-11-04 | 2025-12-10 |  | 2026-01-09 |  | 3 | Met | Tanay Rattan | 71130
ST01917 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-023 | Bhopal | Central | 50 | Testing | 2025-11-23 | 2025-12-16 | 2025-12-12 | 2026-01-01 |  | 12 | Marginal | Arya Shere | 182845
ST01918 | PRJ024 | CL005 | HDFC Bank | Indore Site-024 | Indore | Central | 10 | ROW In Progress | 2025-11-16 | 2025-12-19 |  | 2025-12-30 |  | 7 | Met | Yashica Cherian | 188171
ST01919 | PRJ024 | CL005 | HDFC Bank | Indore Site-025 | Indore | Central | 10 | Installation Done | 2025-11-24 | 2025-12-24 | 2025-12-20 | 2026-01-07 |  | 12 | Marginal | Diya Rattan | 200859
ST01920 | PRJ024 | CL005 | HDFC Bank | Indore Site-026 | Indore | Central | 200 | Live | 2025-11-11 | 2025-12-26 | 2026-01-03 | 2026-01-09 | 2026-01-08 | 8 | Marginal | Ranveer Yadav | 96535
ST01921 | PRJ024 | CL005 | HDFC Bank | Indore Site-027 | Indore | Central | 100 | Pending Acceptance | 2025-11-22 | 2025-12-13 | 2025-12-08 | 2026-01-02 | 2026-01-13 | 0 | Met | Urvashi Ray | 52870
ST01922 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-028 | Bhopal | Central | 10 | ROW In Progress | 2025-11-11 | 2025-12-09 |  | 2025-12-29 |  | 0 | Met | Dipta Bhandari | 101672
ST01923 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-029 | Nagpur | Central | 20 | Installation Done | 2025-11-10 | 2025-12-02 | 2025-12-11 | 2025-12-17 |  | 12 | Marginal | Gavin Batta | 73614
ST01924 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-030 | Bhopal | Central | 100 | Testing | 2025-11-16 | 2026-01-11 | 2026-01-07 | 2026-02-06 |  | 12 | Marginal | Priya Rastogi | 216726
ST01925 | PRJ024 | CL005 | HDFC Bank | Indore Site-031 | Indore | Central | 50 | Installation Done | 2025-11-09 | 2025-12-06 | 2025-12-01 | 2025-12-24 |  | 12 | Marginal | Ekavir Bhargava | 239899
ST01926 | PRJ024 | CL005 | HDFC Bank | Indore Site-032 | Indore | Central | 100 | Live | 2025-11-19 | 2025-12-16 | 2025-12-16 | 2026-01-12 | 2026-01-11 | 0 | Met | Ekbal Garg | 164219
ST01927 | PRJ024 | CL005 | HDFC Bank | Indore Site-033 | Indore | Central | 50 | Installation Scheduled | 2025-11-17 | 2025-12-10 | 2025-12-09 | 2025-12-27 |  | 4 | Met | Harini Choudhury | 93147
ST01928 | PRJ024 | CL005 | HDFC Bank | Indore Site-034 | Indore | Central | 50 | ROW In Progress | 2025-11-24 | 2026-01-08 |  | 2026-01-18 |  | 2 | Met | Isaac Patil | 101275
ST01929 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-035 | Nagpur | Central | 50 | Installation Scheduled | 2025-11-06 | 2025-12-05 | 2025-11-30 | 2026-01-02 |  | 4 | Met | Mohammed Gupta | 254147
ST01930 | PRJ024 | CL005 | HDFC Bank | Indore Site-036 | Indore | Central | 100 | Live | 2025-11-16 | 2026-01-14 | 2026-01-09 | 2026-01-30 | 2026-02-01 | 0 | Met | Ikbal Kothari | 127786
ST01931 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-037 | Bhopal | Central | 200 | Installation Scheduled | 2025-11-08 | 2025-12-28 | 2026-01-05 | 2026-01-09 |  | 7 | Met | Arya Sunder | 233796
ST01932 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-038 | Nagpur | Central | 50 | Survey Pending | 2025-11-25 | 2025-12-23 |  | 2026-01-10 |  | 5 | Met | Darsh Rau | 74346
ST01933 | PRJ024 | CL005 | HDFC Bank | Indore Site-039 | Indore | Central | 50 | Survey Pending | 2025-11-07 | 2025-12-03 |  | 2025-12-31 |  | 1 | Met | Gavin Batta | 89755
ST01934 | PRJ024 | CL005 | HDFC Bank | Indore Site-040 | Indore | Central | 100 | Testing | 2025-11-16 | 2025-12-24 | 2026-01-01 | 2026-01-11 |  | 12 | Marginal | Nitesh Raghavan | 252398
ST01935 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-041 | Nagpur | Central | 10 | Live | 2025-11-08 | 2025-12-11 | 2025-12-20 | 2026-01-02 | 2025-12-31 | 9 | Marginal | Yatin Baral | 182761
ST01936 | PRJ024 | CL005 | HDFC Bank | Indore Site-042 | Indore | Central | 10 | Installation Scheduled | 2025-11-12 | 2025-12-03 | 2025-12-05 | 2025-12-27 |  | 8 | Marginal | Upadhriti Wadhwa | 194916
ST01937 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-043 | Bhopal | Central | 100 | Installation Done | 2025-11-23 | 2026-01-18 | 2026-01-17 | 2026-01-30 |  | 12 | Marginal | Arya Sunder | 56432
ST01938 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-044 | Bhopal | Central | 200 | Installation Done | 2025-11-27 | 2026-01-19 | 2026-01-20 | 2026-02-10 |  | 12 | Marginal | Harini Choudhury | 263524
ST01939 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-045 | Bhopal | Central | 50 | Live | 2025-11-11 | 2025-12-18 | 2025-12-21 | 2026-01-13 | 2026-01-23 | 3 | Met | Mohammed Gupta | 55242
ST01940 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-046 | Nagpur | Central | 50 | ROW In Progress | 2025-11-11 | 2026-01-06 |  | 2026-02-01 |  | 6 | Met | Ekavir Bhargava | 158165
ST01941 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-047 | Bhopal | Central | 20 | ROW In Progress | 2025-11-04 | 2025-12-04 |  | 2025-12-16 |  | 2 | Met | Quincy Biswas | 224914
ST01942 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-048 | Nagpur | Central | 20 | ROW In Progress | 2025-11-04 | 2025-12-16 |  | 2026-01-05 |  | 0 | Met | Kabir Soman | 45518
ST01943 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-049 | Bhopal | Central | 50 | Survey Pending | 2025-11-21 | 2026-01-13 |  | 2026-02-04 |  | 3 | Met | Girik Khalsa | 163865
ST01944 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-050 | Bhopal | Central | 200 | Testing | 2025-11-23 | 2025-12-13 | 2025-12-08 | 2026-01-08 |  | 12 | Marginal | Gavin Batta | 76802
ST01945 | PRJ024 | CL005 | HDFC Bank | Indore Site-051 | Indore | Central | 100 | ROW In Progress | 2025-11-29 | 2025-12-19 |  | 2025-12-29 |  | 1 | Met | Yashica Cherian | 260062
ST01946 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-052 | Bhopal | Central | 200 | ROW In Progress | 2025-11-19 | 2025-12-21 |  | 2026-01-14 |  | 8 | Marginal | Teerth Bhardwaj | 238989
ST01947 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-053 | Nagpur | Central | 200 | Testing | 2025-11-16 | 2025-12-06 | 2025-12-11 | 2025-12-25 |  | 12 | Marginal | Theodore Devi | 269020
ST01948 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-054 | Nagpur | Central | 10 | Installation Done | 2025-11-12 | 2025-12-26 | 2025-12-28 | 2026-01-06 |  | 12 | Marginal | Anamika Kanda | 201427
ST01949 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-055 | Nagpur | Central | 10 | Installation Done | 2025-11-25 | 2025-12-29 | 2025-12-31 | 2026-01-21 |  | 12 | Marginal | Michael Dutta | 234533
ST01950 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-056 | Bhopal | Central | 200 | Pending Acceptance | 2025-11-06 | 2025-12-02 | 2025-11-29 | 2025-12-22 | 2025-12-21 | 0 | Met | Logan Sami | 227007
ST01951 | PRJ024 | CL005 | HDFC Bank | Indore Site-057 | Indore | Central | 20 | Installation Scheduled | 2025-11-08 | 2026-01-03 | 2026-01-07 | 2026-01-17 |  | 0 | Met | Devansh Nigam | 256004
ST01952 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-058 | Nagpur | Central | 50 | Survey Pending | 2025-11-15 | 2025-12-18 |  | 2026-01-07 |  | 3 | Met | Niharika Sunder | 152771
ST01953 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-059 | Bhopal | Central | 200 | Installation Done | 2025-11-16 | 2026-01-11 | 2026-01-14 | 2026-01-30 |  | 12 | Marginal | Victor Kannan | 271290
ST01954 | PRJ024 | CL005 | HDFC Bank | Indore Site-060 | Indore | Central | 200 | Installation Done | 2025-11-08 | 2025-12-01 | 2025-11-29 | 2025-12-12 |  | 12 | Marginal | Radhika Dugar | 114991
ST01955 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-061 | Nagpur | Central | 20 | Live | 2025-11-29 | 2025-12-27 | 2025-12-24 | 2026-01-22 | 2026-01-23 | 0 | Met | Alka Wable | 179568
ST01956 | PRJ024 | CL005 | HDFC Bank | Indore Site-062 | Indore | Central | 100 | Testing | 2025-11-28 | 2026-01-05 | 2025-12-31 | 2026-01-19 |  | 12 | Marginal | Aarush Lall | 53829
ST01957 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-063 | Nagpur | Central | 100 | Installation Scheduled | 2025-11-06 | 2025-12-27 | 2025-12-30 | 2026-01-16 |  | 2 | Met | Siddharth Zacharia | 252006
ST01958 | PRJ024 | CL005 | HDFC Bank | Indore Site-064 | Indore | Central | 50 | Live | 2025-11-10 | 2025-12-26 | 2025-12-30 | 2026-01-10 | 2026-01-14 | 4 | Met | Teerth Bhardwaj | 49560
ST01959 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-065 | Bhopal | Central | 200 | Installation Scheduled | 2025-11-09 | 2026-01-07 | 2026-01-05 | 2026-02-03 |  | 2 | Met | Irya Sampath | 73097
ST01960 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-066 | Nagpur | Central | 50 | ROW In Progress | 2025-11-17 | 2025-12-11 |  | 2026-01-10 |  | 2 | Met | Darsh Rau | 192970
ST01961 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-067 | Bhopal | Central | 200 | Installation Scheduled | 2025-11-16 | 2025-12-13 | 2025-12-09 | 2025-12-24 |  | 7 | Met | Ekiya Suresh | 102426
ST01962 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-068 | Bhopal | Central | 200 | Installation Scheduled | 2025-11-17 | 2025-12-08 | 2025-12-04 | 2025-12-20 |  | 2 | Met | Raksha Varughese | 181936
ST01963 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-069 | Bhopal | Central | 20 | Installation Done | 2025-11-04 | 2025-11-29 | 2025-11-29 | 2025-12-15 |  | 12 | Marginal | Nitesh Raghavan | 62994
ST01964 | PRJ024 | CL005 | HDFC Bank | Indore Site-070 | Indore | Central | 10 | ROW In Progress | 2025-11-04 | 2025-12-10 |  | 2026-01-06 |  | 5 | Met | Wahab Raval | 237788
ST01965 | PRJ024 | CL005 | HDFC Bank | Indore Site-071 | Indore | Central | 100 | Installation Done | 2025-11-14 | 2025-12-18 | 2025-12-21 | 2026-01-06 |  | 12 | Marginal | Dominic Kakar | 274459
ST01966 | PRJ024 | CL005 | HDFC Bank | Indore Site-072 | Indore | Central | 100 | Live | 2025-11-08 | 2025-12-26 | 2026-01-03 | 2026-01-12 | 2026-01-18 | 8 | Marginal | Daksh Karnik | 73068
ST01967 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-073 | Nagpur | Central | 20 | ROW In Progress | 2025-11-11 | 2025-12-01 |  | 2025-12-22 |  | 7 | Met | Kevin Solanki | 173927
ST01968 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-074 | Bhopal | Central | 100 | Installation Scheduled | 2025-11-15 | 2026-01-09 | 2026-01-17 | 2026-01-21 |  | 7 | Met | Kashvi Edwin | 87777
ST01969 | PRJ024 | CL005 | HDFC Bank | Indore Site-075 | Indore | Central | 100 | Live | 2025-11-27 | 2025-12-25 | 2026-01-03 | 2026-01-09 | 2026-01-18 | 9 | Marginal | Ekbal Garg | 178532
ST01970 | PRJ024 | CL005 | HDFC Bank | Indore Site-076 | Indore | Central | 20 | Live | 2025-11-26 | 2026-01-09 | 2026-01-15 | 2026-01-31 | 2026-02-01 | 6 | Met | Ekavir Bhargava | 65077
ST01971 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-077 | Nagpur | Central | 200 | Live | 2025-11-17 | 2026-01-10 | 2026-01-19 | 2026-02-05 | 2026-02-10 | 9 | Marginal | Ekavir Varkey | 169074
ST01972 | PRJ024 | CL005 | HDFC Bank | Indore Site-078 | Indore | Central | 50 | Live | 2025-11-25 | 2025-12-25 | 2025-12-21 | 2026-01-24 | 2026-01-27 | 0 | Met | Nihal Shere | 54568
ST01973 | PRJ024 | CL005 | HDFC Bank | Indore Site-079 | Indore | Central | 50 | Pending Acceptance | 2025-11-07 | 2025-12-29 | 2026-01-02 | 2026-01-24 | 2026-02-05 | 4 | Met | Aarush Lall | 77913
ST01974 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-080 | Bhopal | Central | 100 | Installation Scheduled | 2025-11-12 | 2025-12-15 | 2025-12-19 | 2025-12-26 |  | 4 | Met | Arya Shere | 188572
ST01975 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-081 | Bhopal | Central | 50 | Pending Acceptance | 2025-11-08 | 2025-12-03 | 2025-12-08 | 2026-01-02 | 2026-01-12 | 5 | Met | Ikbal Kothari | 87893
ST01976 | PRJ024 | CL005 | HDFC Bank | Indore Site-082 | Indore | Central | 50 | Installation Scheduled | 2025-11-29 | 2025-12-30 | 2025-12-25 | 2026-01-21 |  | 4 | Met | Gavin Batta | 245911
ST01977 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-083 | Bhopal | Central | 200 | ROW In Progress | 2025-11-26 | 2026-01-24 |  | 2026-02-18 |  | 3 | Met | Theodore Devi | 184249
ST01978 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-084 | Bhopal | Central | 20 | Installation Done | 2025-11-04 | 2025-12-21 | 2025-12-23 | 2026-01-09 |  | 12 | Marginal | Unni Bhagat | 222515
ST01979 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-085 | Nagpur | Central | 200 | Live | 2025-11-20 | 2026-01-11 | 2026-01-11 | 2026-01-23 | 2026-01-28 | 0 | Met | Tanay Rattan | 185729
ST01980 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-086 | Bhopal | Central | 10 | Pending Acceptance | 2025-11-16 | 2025-12-22 | 2025-12-17 | 2026-01-12 | 2026-01-12 | 0 | Met | Dominic Kakar | 92643
ST01981 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-087 | Bhopal | Central | 10 | ROW In Progress | 2025-11-15 | 2025-12-24 |  | 2026-01-09 |  | 4 | Met | Isaac Patil | 109784
ST01982 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-088 | Bhopal | Central | 100 | ROW In Progress | 2025-11-16 | 2025-12-09 |  | 2025-12-28 |  | 8 | Marginal | Ekbal Garg | 260953
ST01983 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-089 | Bhopal | Central | 10 | Installation Done | 2025-11-07 | 2025-12-29 | 2026-01-05 | 2026-01-09 |  | 12 | Marginal | Farhan Chada | 87770
ST01984 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-090 | Bhopal | Central | 10 | Pending Acceptance | 2025-11-10 | 2025-12-06 | 2025-12-15 | 2026-01-02 | 2025-12-31 | 9 | Marginal | Gavin Batta | 256704
ST01985 | PRJ024 | CL005 | HDFC Bank | Indore Site-091 | Indore | Central | 10 | Survey Pending | 2025-11-04 | 2025-12-07 |  | 2025-12-26 |  | 7 | Met | Devika Rastogi | 73033
ST01986 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-092 | Nagpur | Central | 200 | Installation Done | 2025-11-07 | 2026-01-03 | 2026-01-12 | 2026-02-02 |  | 12 | Marginal | Tanay Rattan | 56950
ST01987 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-093 | Nagpur | Central | 200 | ROW In Progress | 2025-11-24 | 2026-01-07 |  | 2026-01-21 |  | 5 | Met | Simon Tata | 234204
ST01988 | PRJ024 | CL005 | HDFC Bank | Nagpur Site-094 | Nagpur | Central | 50 | Installation Scheduled | 2025-11-22 | 2025-12-30 | 2026-01-08 | 2026-01-25 |  | 5 | Met | Nihal Shere | 209806
ST01989 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-095 | Bhopal | Central | 200 | Survey Pending | 2025-11-18 | 2025-12-29 |  | 2026-01-15 |  | 5 | Met | Kashvi Edwin | 230117
ST01990 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-096 | Bhopal | Central | 200 | Survey Pending | 2025-11-09 | 2026-01-03 |  | 2026-01-29 |  | 7 | Met | Ekbal Garg | 168646
ST01991 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-097 | Bhopal | Central | 100 | Live | 2025-11-23 | 2025-12-16 | 2025-12-18 | 2026-01-09 | 2026-01-09 | 2 | Met | Devansh Rajan | 156870
ST01992 | PRJ024 | CL005 | HDFC Bank | Bhopal Site-098 | Bhopal | Central | 20 | Testing | 2025-11-20 | 2025-12-17 | 2025-12-27 | 2025-12-31 |  | 12 | Marginal | Farhan Chada | 222431
ST01993 | PRJ025 | CL006 | ICICI Bank | Surat Site-001 | Surat | West | 20 | Live | 2025-09-28 | 2025-11-17 | 2025-11-19 | 2025-12-12 | 2025-12-10 | 2 | Met | Michael Dutta | 172579
ST01994 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-002 | Ahmedabad | West | 50 | Installation Scheduled | 2025-09-11 | 2025-11-03 | 2025-10-29 | 2025-11-18 |  | 7 | Met | Priya Rastogi | 265341
ST01995 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-003 | Ahmedabad | West | 10 | Installation Done | 2025-09-14 | 2025-11-02 | 2025-11-02 | 2025-11-24 |  | 12 | Marginal | Yashica Issac | 192488
ST01996 | PRJ025 | CL006 | ICICI Bank | Pune Site-004 | Pune | West | 20 | Installation Scheduled | 2025-09-28 | 2025-11-12 | 2025-11-19 | 2025-11-26 |  | 7 | Met | Arya Sunder | 56978
ST01997 | PRJ025 | CL006 | ICICI Bank | Surat Site-005 | Surat | West | 100 | Installation Done | 2025-09-12 | 2025-10-10 | 2025-10-05 | 2025-11-03 |  | 12 | Marginal | Ekapad Walia | 82700
ST01998 | PRJ025 | CL006 | ICICI Bank | Surat Site-006 | Surat | West | 100 | Pending Acceptance | 2025-09-26 | 2025-10-29 | 2025-11-03 | 2025-11-14 | 2025-11-23 | 5 | Met | Tanay Rattan | 226306
ST01999 | PRJ025 | CL006 | ICICI Bank | Pune Site-007 | Pune | West | 100 | Installation Done | 2025-09-08 | 2025-10-11 | 2025-10-19 | 2025-11-06 |  | 12 | Marginal | Simon Tata | 151545
ST02000 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-008 | Mumbai | West | 20 | Live | 2025-09-20 | 2025-11-12 | 2025-11-19 | 2025-12-10 | 2025-12-14 | 7 | Met | Tara Dhar | 226907
ST02001 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-009 | Ahmedabad | West | 10 | Live | 2025-09-28 | 2025-11-02 | 2025-11-05 | 2025-11-12 | 2025-11-20 | 3 | Met | Aarush Lall | 169325
ST02002 | PRJ025 | CL006 | ICICI Bank | Pune Site-010 | Pune | West | 100 | Testing | 2025-09-27 | 2025-10-22 | 2025-10-27 | 2025-11-20 |  | 12 | Marginal | Nitesh Raghavan | 112468
ST02003 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-011 | Mumbai | West | 100 | Installation Scheduled | 2025-09-25 | 2025-11-04 | 2025-11-12 | 2025-11-28 |  | 0 | Met | Yatin Baral | 201074
ST02004 | PRJ025 | CL006 | ICICI Bank | Surat Site-012 | Surat | West | 100 | Installation Done | 2025-09-14 | 2025-10-26 | 2025-10-29 | 2025-11-10 |  | 12 | Marginal | Priya Rastogi | 198798
ST02005 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-013 | Mumbai | West | 100 | Installation Scheduled | 2025-09-29 | 2025-11-21 | 2025-11-24 | 2025-12-05 |  | 2 | Met | Ekapad Walia | 270525
ST02006 | PRJ025 | CL006 | ICICI Bank | Surat Site-014 | Surat | West | 20 | Live | 2025-09-08 | 2025-10-27 | 2025-10-28 | 2025-11-11 | 2025-11-09 | 1 | Met | Ekiya Suresh | 213680
ST02007 | PRJ025 | CL006 | ICICI Bank | Pune Site-015 | Pune | West | 100 | Installation Done | 2025-09-07 | 2025-10-01 | 2025-10-10 | 2025-10-22 |  | 12 | Marginal | Nitesh Raghavan | 204055
ST02008 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-016 | Mumbai | West | 20 | Pending Acceptance | 2025-09-07 | 2025-10-24 | 2025-10-24 | 2025-11-04 | 2025-11-10 | 0 | Met | Logan Sami | 74889
ST02009 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-017 | Ahmedabad | West | 20 | Installation Scheduled | 2025-09-21 | 2025-11-05 | 2025-11-07 | 2025-11-16 |  | 5 | Met | Devansh Rajan | 264033
ST02010 | PRJ025 | CL006 | ICICI Bank | Surat Site-018 | Surat | West | 20 | Pending Acceptance | 2025-09-04 | 2025-10-07 | 2025-10-07 | 2025-10-22 | 2025-10-19 | 0 | Met | Niharika Sunder | 194065
ST02011 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-019 | Mumbai | West | 100 | ROW In Progress | 2025-09-12 | 2025-10-13 |  | 2025-11-04 |  | 4 | Met | Priya Rastogi | 60872
ST02012 | PRJ025 | CL006 | ICICI Bank | Surat Site-020 | Surat | West | 20 | Testing | 2025-09-06 | 2025-10-24 | 2025-11-02 | 2025-11-03 |  | 12 | Marginal | Theodore Devi | 149873
ST02013 | PRJ025 | CL006 | ICICI Bank | Pune Site-021 | Pune | West | 10 | Installation Done | 2025-09-28 | 2025-10-20 | 2025-10-25 | 2025-10-30 |  | 12 | Marginal | Ekavir Varkey | 197909
ST02014 | PRJ025 | CL006 | ICICI Bank | Pune Site-022 | Pune | West | 100 | Installation Scheduled | 2025-09-17 | 2025-11-05 | 2025-11-05 | 2025-11-23 |  | 4 | Met | Alka Wable | 268559
ST02015 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-023 | Mumbai | West | 20 | Live | 2025-09-18 | 2025-10-18 | 2025-10-21 | 2025-11-11 | 2025-11-21 | 3 | Met | Ekbal Garg | 186539
ST02016 | PRJ025 | CL006 | ICICI Bank | Pune Site-024 | Pune | West | 20 | Pending Acceptance | 2025-09-05 | 2025-10-20 | 2025-10-25 | 2025-11-07 | 2025-11-05 | 5 | Met | Darsh Rau | 206423
ST02017 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-025 | Ahmedabad | West | 20 | ROW In Progress | 2025-09-23 | 2025-10-27 |  | 2025-11-25 |  | 3 | Met | Dipta Bhandari | 228688
ST02018 | PRJ025 | CL006 | ICICI Bank | Pune Site-026 | Pune | West | 100 | Pending Acceptance | 2025-09-19 | 2025-10-20 | 2025-10-17 | 2025-11-04 | 2025-11-04 | 0 | Met | Alka Wable | 136242
ST02019 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-027 | Mumbai | West | 100 | Installation Scheduled | 2025-09-28 | 2025-11-23 | 2025-12-01 | 2025-12-04 |  | 2 | Met | Tanay Rattan | 163636
ST02020 | PRJ025 | CL006 | ICICI Bank | Surat Site-028 | Surat | West | 50 | Live | 2025-09-09 | 2025-10-28 | 2025-10-28 | 2025-11-24 | 2025-11-30 | 0 | Met | Ekapad Walia | 199170
ST02021 | PRJ025 | CL006 | ICICI Bank | Surat Site-029 | Surat | West | 10 | Installation Scheduled | 2025-09-27 | 2025-11-26 | 2025-12-02 | 2025-12-06 |  | 7 | Met | Yatin Baral | 270224
ST02022 | PRJ025 | CL006 | ICICI Bank | Surat Site-030 | Surat | West | 10 | Installation Scheduled | 2025-09-04 | 2025-10-20 | 2025-10-30 | 2025-11-10 |  | 6 | Met | Kashvi Edwin | 56690
ST02023 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-031 | Mumbai | West | 20 | Live | 2025-09-07 | 2025-11-02 | 2025-11-02 | 2025-12-01 | 2025-11-29 | 0 | Met | Isaac Patil | 247282
ST02024 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-032 | Mumbai | West | 50 | Live | 2025-09-28 | 2025-11-06 | 2025-11-08 | 2025-12-05 | 2025-12-03 | 2 | Met | Devansh Nigam | 187138
ST02025 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-033 | Mumbai | West | 20 | Testing | 2025-09-09 | 2025-10-09 | 2025-10-15 | 2025-10-25 |  | 12 | Marginal | Ekapad Walia | 90433
ST02026 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-034 | Mumbai | West | 50 | Pending Acceptance | 2025-09-11 | 2025-10-23 | 2025-10-20 | 2025-11-03 | 2025-11-04 | 0 | Met | Irya Sampath | 135191
ST02027 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-035 | Mumbai | West | 50 | ROW In Progress | 2025-09-27 | 2025-10-31 |  | 2025-11-20 |  | 4 | Met | Diya Rattan | 104254
ST02028 | PRJ025 | CL006 | ICICI Bank | Surat Site-036 | Surat | West | 200 | Testing | 2025-09-21 | 2025-11-15 | 2025-11-19 | 2025-12-01 |  | 12 | Marginal | Wriddhish Bhardwaj | 242932
ST02029 | PRJ025 | CL006 | ICICI Bank | Pune Site-037 | Pune | West | 20 | ROW In Progress | 2025-09-09 | 2025-10-17 |  | 2025-11-03 |  | 6 | Met | Nitesh Raghavan | 79671
ST02030 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-038 | Mumbai | West | 50 | Live | 2025-09-04 | 2025-10-16 | 2025-10-18 | 2025-10-29 | 2025-10-30 | 2 | Met | Victor Kannan | 68715
ST02031 | PRJ025 | CL006 | ICICI Bank | Pune Site-039 | Pune | West | 50 | Live | 2025-09-05 | 2025-10-23 | 2025-10-28 | 2025-11-21 | 2025-11-30 | 5 | Met | Radhika Dugar | 59795
ST02032 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-040 | Mumbai | West | 100 | ROW In Progress | 2025-09-19 | 2025-11-03 |  | 2025-11-19 |  | 1 | Met | Teerth Bhardwaj | 125999
ST02033 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-041 | Ahmedabad | West | 10 | Installation Scheduled | 2025-09-06 | 2025-09-26 | 2025-10-03 | 2025-10-11 |  | 4 | Met | Ekapad Walia | 162476
ST02034 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-042 | Ahmedabad | West | 100 | Testing | 2025-09-29 | 2025-10-25 | 2025-10-24 | 2025-11-09 |  | 12 | Marginal | Mohammed Gupta | 64926
ST02035 | PRJ025 | CL006 | ICICI Bank | Pune Site-043 | Pune | West | 100 | ROW In Progress | 2025-09-15 | 2025-10-19 |  | 2025-11-10 |  | 2 | Met | Ekavir Bhargava | 169112
ST02036 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-044 | Ahmedabad | West | 100 | ROW In Progress | 2025-09-20 | 2025-11-19 |  | 2025-12-11 |  | 4 | Met | Devansh Rajan | 82189
ST02037 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-045 | Mumbai | West | 10 | Live | 2025-09-17 | 2025-10-14 | 2025-10-23 | 2025-10-31 | 2025-10-28 | 9 | Marginal | Yashica Issac | 217974
ST02038 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-046 | Ahmedabad | West | 10 | Installation Scheduled | 2025-09-08 | 2025-10-15 | 2025-10-11 | 2025-10-31 |  | 2 | Met | Liam Koshy | 137755
ST02039 | PRJ025 | CL006 | ICICI Bank | Pune Site-047 | Pune | West | 20 | Live | 2025-09-15 | 2025-10-05 | 2025-10-10 | 2025-10-18 | 2025-10-23 | 5 | Met | Radhika Dugar | 71310
ST02040 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-048 | Mumbai | West | 20 | Installation Scheduled | 2025-09-25 | 2025-10-18 | 2025-10-27 | 2025-11-12 |  | 7 | Met | Devansh Nigam | 167195
ST02041 | PRJ025 | CL006 | ICICI Bank | Pune Site-049 | Pune | West | 10 | Installation Done | 2025-09-27 | 2025-11-02 | 2025-11-01 | 2025-11-16 |  | 12 | Marginal | Yatin Baral | 187935
ST02042 | PRJ025 | CL006 | ICICI Bank | Pune Site-050 | Pune | West | 200 | Live | 2025-09-12 | 2025-11-11 | 2025-11-16 | 2025-12-08 | 2025-12-08 | 5 | Met | Isaac Patil | 237925
ST02043 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-051 | Mumbai | West | 100 | Installation Scheduled | 2025-09-21 | 2025-11-10 | 2025-11-20 | 2025-11-21 |  | 6 | Met | Arya Shere | 262452
ST02044 | PRJ025 | CL006 | ICICI Bank | Pune Site-052 | Pune | West | 50 | Pending Acceptance | 2025-09-11 | 2025-10-11 | 2025-10-19 | 2025-11-01 | 2025-11-01 | 8 | Marginal | Tara Dhar | 88497
ST02045 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-053 | Ahmedabad | West | 10 | Installation Done | 2025-09-21 | 2025-10-29 | 2025-11-06 | 2025-11-16 |  | 12 | Marginal | Irya Sampath | 211865
ST02046 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-054 | Ahmedabad | West | 100 | Live | 2025-09-20 | 2025-10-22 | 2025-10-22 | 2025-11-11 | 2025-11-21 | 0 | Met | Radhika Dugar | 151045
ST02047 | PRJ025 | CL006 | ICICI Bank | Pune Site-055 | Pune | West | 20 | Survey Pending | 2025-09-20 | 2025-10-27 |  | 2025-11-18 |  | 7 | Met | Kashvi Edwin | 140004
ST02048 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-056 | Ahmedabad | West | 200 | Pending Acceptance | 2025-09-28 | 2025-11-27 | 2025-12-02 | 2025-12-18 | 2025-12-17 | 5 | Met | Chandresh Zachariah | 89242
ST02049 | PRJ025 | CL006 | ICICI Bank | Pune Site-057 | Pune | West | 20 | ROW In Progress | 2025-09-15 | 2025-10-05 |  | 2025-10-18 |  | 8 | Marginal | Ikbal Kothari | 236191
ST02050 | PRJ025 | CL006 | ICICI Bank | Surat Site-058 | Surat | West | 100 | ROW In Progress | 2025-09-13 | 2025-10-31 |  | 2025-11-15 |  | 8 | Marginal | Wriddhish Bhardwaj | 199398
ST02051 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-059 | Ahmedabad | West | 20 | Live | 2025-09-24 | 2025-10-14 | 2025-10-11 | 2025-10-29 | 2025-10-31 | 0 | Met | Ekavir Bhargava | 67856
ST02052 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-060 | Ahmedabad | West | 200 | Testing | 2025-09-09 | 2025-11-06 | 2025-11-01 | 2025-11-16 |  | 12 | Marginal | Tanay Rattan | 148394
ST02053 | PRJ025 | CL006 | ICICI Bank | Pune Site-061 | Pune | West | 10 | Live | 2025-09-18 | 2025-10-10 | 2025-10-09 | 2025-11-02 | 2025-11-11 | 0 | Met | Devansh Nigam | 262853
ST02054 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-062 | Ahmedabad | West | 20 | Live | 2025-09-05 | 2025-11-01 | 2025-11-07 | 2025-11-24 | 2025-11-27 | 6 | Met | Liam Koshy | 170098
ST02055 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-063 | Ahmedabad | West | 200 | Live | 2025-09-04 | 2025-10-08 | 2025-10-05 | 2025-10-19 | 2025-10-18 | 0 | Met | Alka Wable | 109385
ST02056 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-064 | Ahmedabad | West | 50 | Live | 2025-09-21 | 2025-11-19 | 2025-11-19 | 2025-12-03 | 2025-12-05 | 0 | Met | Dipta Bhandari | 69548
ST02057 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-065 | Mumbai | West | 10 | Pending Acceptance | 2025-09-11 | 2025-10-25 | 2025-10-20 | 2025-11-05 | 2025-11-15 | 0 | Met | Aarush Lall | 165954
ST02058 | PRJ025 | CL006 | ICICI Bank | Surat Site-066 | Surat | West | 100 | Live | 2025-09-14 | 2025-10-29 | 2025-11-01 | 2025-11-20 | 2025-11-20 | 3 | Met | Tara Dhar | 169256
ST02059 | PRJ025 | CL006 | ICICI Bank | Surat Site-067 | Surat | West | 10 | Live | 2025-09-16 | 2025-10-24 | 2025-10-25 | 2025-11-19 | 2025-11-27 | 1 | Met | Nihal Shere | 195062
ST02060 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-068 | Ahmedabad | West | 100 | Installation Scheduled | 2025-09-09 | 2025-10-11 | 2025-10-14 | 2025-11-03 |  | 1 | Met | Nitesh Raghavan | 217762
ST02061 | PRJ025 | CL006 | ICICI Bank | Pune Site-069 | Pune | West | 10 | Live | 2025-09-25 | 2025-10-22 | 2025-10-23 | 2025-11-07 | 2025-11-17 | 1 | Met | Nihal Shere | 213536
ST02062 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-070 | Ahmedabad | West | 10 | Installation Scheduled | 2025-09-06 | 2025-10-23 | 2025-10-27 | 2025-11-06 |  | 3 | Met | Faqid Savant | 136479
ST02063 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-071 | Ahmedabad | West | 100 | Live | 2025-09-13 | 2025-10-10 | 2025-10-11 | 2025-11-03 | 2025-11-05 | 1 | Met | Vansha Thakkar | 217619
ST02064 | PRJ025 | CL006 | ICICI Bank | Surat Site-072 | Surat | West | 20 | Installation Done | 2025-09-19 | 2025-11-04 | 2025-10-31 | 2025-11-27 |  | 12 | Marginal | Jai Kota | 203441
ST02065 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-073 | Ahmedabad | West | 100 | ROW In Progress | 2025-09-05 | 2025-10-12 |  | 2025-11-04 |  | 1 | Met | Girindra Chatterjee | 270010
ST02066 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-074 | Ahmedabad | West | 100 | ROW In Progress | 2025-09-21 | 2025-11-08 |  | 2025-11-18 |  | 1 | Met | Wriddhish Bhardwaj | 90202
ST02067 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-075 | Ahmedabad | West | 100 | Live | 2025-09-05 | 2025-10-05 | 2025-10-09 | 2025-11-01 | 2025-11-05 | 4 | Met | Kevin Solanki | 114889
ST02068 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-076 | Ahmedabad | West | 50 | Survey Pending | 2025-09-19 | 2025-10-19 |  | 2025-11-05 |  | 4 | Met | Nitesh Raghavan | 249709
ST02069 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-077 | Ahmedabad | West | 20 | Live | 2025-09-20 | 2025-11-03 | 2025-11-06 | 2025-11-27 | 2025-11-24 | 3 | Met | Ikbal Kothari | 274152
ST02070 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-078 | Ahmedabad | West | 200 | Live | 2025-09-15 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-12 | 7 | Met | Dominic Kakar | 118629
ST02071 | PRJ025 | CL006 | ICICI Bank | Surat Site-079 | Surat | West | 10 | ROW In Progress | 2025-09-20 | 2025-11-06 |  | 2025-11-24 |  | 1 | Met | Ekbal Garg | 201138
ST02072 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-080 | Ahmedabad | West | 20 | Installation Scheduled | 2025-09-14 | 2025-11-13 | 2025-11-18 | 2025-12-08 |  | 4 | Met | Gavin Batta | 147449
ST02073 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-081 | Ahmedabad | West | 100 | Installation Scheduled | 2025-09-28 | 2025-11-24 | 2025-11-19 | 2025-12-05 |  | 3 | Met | Priya Rastogi | 113642
ST02074 | PRJ025 | CL006 | ICICI Bank | Surat Site-082 | Surat | West | 50 | Survey Pending | 2025-09-19 | 2025-11-18 |  | 2025-12-11 |  | 1 | Met | Alka Wable | 164435
ST02075 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-083 | Ahmedabad | West | 200 | Installation Scheduled | 2025-09-18 | 2025-10-11 | 2025-10-18 | 2025-11-02 |  | 1 | Met | Mohammed Gupta | 266050
ST02076 | PRJ025 | CL006 | ICICI Bank | Ahmedabad Site-084 | Ahmedabad | West | 20 | Live | 2025-09-12 | 2025-10-28 | 2025-11-06 | 2025-11-11 | 2025-11-20 | 9 | Marginal | Girik Khalsa | 190084
ST02077 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-085 | Mumbai | West | 200 | Installation Done | 2025-09-13 | 2025-10-08 | 2025-10-14 | 2025-11-03 |  | 12 | Marginal | Diya Rattan | 60678
ST02078 | PRJ025 | CL006 | ICICI Bank | Pune Site-086 | Pune | West | 200 | Installation Done | 2025-09-26 | 2025-10-26 | 2025-10-24 | 2025-11-05 |  | 12 | Marginal | Kevin Solanki | 132692
ST02079 | PRJ025 | CL006 | ICICI Bank | Mumbai Site-087 | Mumbai | West | 20 | Live | 2025-09-24 | 2025-11-18 | 2025-11-25 | 2025-11-28 | 2025-12-04 | 7 | Met | Ranveer Yadav | 152976
ST02080 | PRJ025 | CL006 | ICICI Bank | Surat Site-088 | Surat | West | 50 | Survey Pending | 2025-09-05 | 2025-10-09 |  | 2025-10-26 |  | 7 | Met | Nitesh Raghavan | 200225
ST02081 | PRJ025 | CL006 | ICICI Bank | Pune Site-089 | Pune | West | 100 | Installation Scheduled | 2025-09-16 | 2025-11-05 | 2025-11-14 | 2025-11-21 |  | 0 | Met | Vansha Thakkar | 228721
ST02082 | PRJ026 | CL006 | ICICI Bank | Pune Site-001 | Pune | West | 10 | Live | 2025-07-08 | 2025-08-15 | 2025-08-19 | 2025-09-10 | 2025-09-17 | 4 | Met | Anamika Kanda | 164968
ST02083 | PRJ026 | CL006 | ICICI Bank | Pune Site-002 | Pune | West | 20 | Installation Done | 2025-07-05 | 2025-08-31 | 2025-09-05 | 2025-09-28 |  | 12 | Marginal | Dipta Bhandari | 210503
ST02084 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-003 | Ahmedabad | West | 200 | ROW In Progress | 2025-06-27 | 2025-08-20 |  | 2025-08-30 |  | 6 | Met | Upadhriti Wadhwa | 233542
ST02085 | PRJ026 | CL006 | ICICI Bank | Surat Site-004 | Surat | West | 10 | Live | 2025-06-19 | 2025-08-08 | 2025-08-15 | 2025-08-30 | 2025-08-31 | 7 | Met | Diya Rattan | 184036
ST02086 | PRJ026 | CL006 | ICICI Bank | Pune Site-005 | Pune | West | 20 | Live | 2025-06-21 | 2025-08-19 | 2025-08-17 | 2025-09-12 | 2025-09-10 | 0 | Met | Tanay Rattan | 96018
ST02087 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-006 | Ahmedabad | West | 50 | Installation Scheduled | 2025-06-20 | 2025-07-30 | 2025-08-06 | 2025-08-29 |  | 2 | Met | Irya Sampath | 181818
ST02088 | PRJ026 | CL006 | ICICI Bank | Surat Site-007 | Surat | West | 50 | Live | 2025-06-16 | 2025-07-17 | 2025-07-12 | 2025-08-05 | 2025-08-06 | 0 | Met | Yashica Issac | 217393
ST02089 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-008 | Ahmedabad | West | 100 | Installation Scheduled | 2025-07-03 | 2025-07-24 | 2025-07-21 | 2025-08-07 |  | 3 | Met | Ranveer Yadav | 110180
ST02090 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-009 | Mumbai | West | 10 | ROW In Progress | 2025-06-22 | 2025-08-17 |  | 2025-09-10 |  | 6 | Met | Raksha Varughese | 204919
ST02091 | PRJ026 | CL006 | ICICI Bank | Surat Site-010 | Surat | West | 100 | Live | 2025-06-28 | 2025-07-18 | 2025-07-17 | 2025-08-06 | 2025-08-10 | 0 | Met | Urvashi Ray | 79854
ST02092 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-011 | Ahmedabad | West | 200 | Survey Pending | 2025-06-25 | 2025-07-29 |  | 2025-08-21 |  | 4 | Met | Theodore Devi | 228477
ST02093 | PRJ026 | CL006 | ICICI Bank | Surat Site-012 | Surat | West | 50 | Live | 2025-07-08 | 2025-08-14 | 2025-08-09 | 2025-08-31 | 2025-09-09 | 0 | Met | Aarush Lall | 76157
ST02094 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-013 | Ahmedabad | West | 50 | Live | 2025-07-02 | 2025-08-19 | 2025-08-29 | 2025-09-05 | 2025-09-13 | 10 | Marginal | Girik Khalsa | 152771
ST02095 | PRJ026 | CL006 | ICICI Bank | Pune Site-014 | Pune | West | 100 | Pending Acceptance | 2025-06-18 | 2025-07-22 | 2025-07-30 | 2025-08-02 | 2025-08-11 | 8 | Marginal | Dipta Bhandari | 203418
ST02096 | PRJ026 | CL006 | ICICI Bank | Surat Site-015 | Surat | West | 200 | Installation Scheduled | 2025-06-16 | 2025-07-14 | 2025-07-20 | 2025-08-11 |  | 4 | Met | Quincy Biswas | 269216
ST02097 | PRJ026 | CL006 | ICICI Bank | Pune Site-016 | Pune | West | 100 | ROW In Progress | 2025-06-15 | 2025-07-21 |  | 2025-08-05 |  | 8 | Marginal | Isaac Patil | 88459
ST02098 | PRJ026 | CL006 | ICICI Bank | Surat Site-017 | Surat | West | 100 | Testing | 2025-06-18 | 2025-07-08 | 2025-07-15 | 2025-07-31 |  | 12 | Marginal | Priya Rastogi | 163936
ST02099 | PRJ026 | CL006 | ICICI Bank | Surat Site-018 | Surat | West | 200 | ROW In Progress | 2025-06-25 | 2025-08-08 |  | 2025-09-06 |  | 2 | Met | Raksha Varughese | 101449
ST02100 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-019 | Ahmedabad | West | 100 | Live | 2025-07-07 | 2025-08-26 | 2025-09-02 | 2025-09-22 | 2025-10-03 | 7 | Met | Mohammed Gupta | 205147
ST02101 | PRJ026 | CL006 | ICICI Bank | Pune Site-020 | Pune | West | 10 | Installation Done | 2025-07-08 | 2025-08-24 | 2025-08-19 | 2025-09-12 |  | 12 | Marginal | Raksha Varughese | 111796
ST02102 | PRJ026 | CL006 | ICICI Bank | Pune Site-021 | Pune | West | 10 | Survey Pending | 2025-07-09 | 2025-08-14 |  | 2025-09-12 |  | 3 | Met | Girindra Chatterjee | 97466
ST02103 | PRJ026 | CL006 | ICICI Bank | Pune Site-022 | Pune | West | 10 | Pending Acceptance | 2025-07-03 | 2025-07-28 | 2025-07-27 | 2025-08-11 | 2025-08-20 | 0 | Met | Daksh Karnik | 46158
ST02104 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-023 | Mumbai | West | 50 | Installation Scheduled | 2025-06-15 | 2025-08-03 | 2025-08-10 | 2025-08-17 |  | 1 | Met | Siddharth Zacharia | 268584
ST02105 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-024 | Mumbai | West | 10 | Live | 2025-07-07 | 2025-09-01 | 2025-08-29 | 2025-09-17 | 2025-09-23 | 0 | Met | Anamika Kanda | 98510
ST02106 | PRJ026 | CL006 | ICICI Bank | Surat Site-025 | Surat | West | 200 | Installation Scheduled | 2025-07-04 | 2025-08-27 | 2025-09-06 | 2025-09-10 |  | 0 | Met | Madhavi Lanka | 213932
ST02107 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-026 | Ahmedabad | West | 10 | Live | 2025-06-26 | 2025-08-04 | 2025-08-04 | 2025-08-18 | 2025-08-24 | 0 | Met | Irya Sampath | 207813
ST02108 | PRJ026 | CL006 | ICICI Bank | Pune Site-027 | Pune | West | 10 | Survey Pending | 2025-06-19 | 2025-07-23 |  | 2025-08-12 |  | 3 | Met | Quincy Biswas | 156837
ST02109 | PRJ026 | CL006 | ICICI Bank | Surat Site-028 | Surat | West | 200 | Testing | 2025-07-09 | 2025-08-04 | 2025-08-07 | 2025-08-31 |  | 12 | Marginal | Girik Khalsa | 77794
ST02110 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-029 | Mumbai | West | 100 | Live | 2025-06-25 | 2025-08-09 | 2025-08-08 | 2025-08-19 | 2025-08-18 | 0 | Met | Ranveer Yadav | 109488
ST02111 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-030 | Mumbai | West | 100 | Installation Done | 2025-06-27 | 2025-08-12 | 2025-08-10 | 2025-09-07 |  | 12 | Marginal | Irya Sampath | 170905
ST02112 | PRJ026 | CL006 | ICICI Bank | Pune Site-031 | Pune | West | 50 | Live | 2025-07-04 | 2025-08-11 | 2025-08-06 | 2025-08-30 | 2025-09-03 | 0 | Met | Quincy Biswas | 112535
ST02113 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-032 | Mumbai | West | 200 | Live | 2025-06-24 | 2025-07-28 | 2025-07-25 | 2025-08-13 | 2025-08-25 | 0 | Met | Urvashi Ray | 267932
ST02114 | PRJ026 | CL006 | ICICI Bank | Surat Site-033 | Surat | West | 20 | ROW In Progress | 2025-06-15 | 2025-08-05 |  | 2025-08-30 |  | 7 | Met | Kashvi Edwin | 64208
ST02115 | PRJ026 | CL006 | ICICI Bank | Surat Site-034 | Surat | West | 200 | Pending Acceptance | 2025-06-25 | 2025-07-18 | 2025-07-20 | 2025-08-10 | 2025-08-09 | 2 | Met | Ekiya Suresh | 56793
ST02116 | PRJ026 | CL006 | ICICI Bank | Pune Site-035 | Pune | West | 200 | Live | 2025-07-03 | 2025-08-29 | 2025-08-26 | 2025-09-26 | 2025-09-29 | 0 | Met | Dakshesh Trivedi | 95692
ST02117 | PRJ026 | CL006 | ICICI Bank | Pune Site-036 | Pune | West | 50 | Installation Done | 2025-06-20 | 2025-07-29 | 2025-07-29 | 2025-08-17 |  | 12 | Marginal | Ekavir Bhargava | 266938
ST02118 | PRJ026 | CL006 | ICICI Bank | Surat Site-037 | Surat | West | 10 | Installation Scheduled | 2025-07-03 | 2025-07-23 | 2025-07-26 | 2025-08-17 |  | 6 | Met | Bhavika Sampath | 241553
ST02119 | PRJ026 | CL006 | ICICI Bank | Surat Site-038 | Surat | West | 100 | Live | 2025-07-08 | 2025-08-11 | 2025-08-16 | 2025-08-23 | 2025-08-20 | 5 | Met | Niharika Sunder | 129240
ST02120 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-039 | Mumbai | West | 200 | Live | 2025-07-03 | 2025-07-27 | 2025-08-06 | 2025-08-26 | 2025-08-24 | 10 | Marginal | Ikbal Kothari | 68547
ST02121 | PRJ026 | CL006 | ICICI Bank | Surat Site-040 | Surat | West | 50 | Live | 2025-07-05 | 2025-08-04 | 2025-08-10 | 2025-08-16 | 2025-08-21 | 6 | Met | Faqid Savant | 95485
ST02122 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-041 | Ahmedabad | West | 10 | Survey Pending | 2025-06-16 | 2025-08-10 |  | 2025-08-31 |  | 8 | Marginal | Darsh Rau | 135784
ST02123 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-042 | Mumbai | West | 50 | Live | 2025-07-09 | 2025-08-04 | 2025-08-09 | 2025-08-28 | 2025-09-02 | 5 | Met | Chandresh Zachariah | 220394
ST02124 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-043 | Ahmedabad | West | 100 | Installation Scheduled | 2025-07-05 | 2025-08-01 | 2025-08-08 | 2025-08-12 |  | 7 | Met | Ekbal Garg | 58258
ST02125 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-044 | Ahmedabad | West | 50 | Survey Pending | 2025-06-21 | 2025-07-11 |  | 2025-07-30 |  | 5 | Met | Advay Contractor | 186446
ST02126 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-045 | Ahmedabad | West | 200 | Pending Acceptance | 2025-07-08 | 2025-08-12 | 2025-08-11 | 2025-08-27 | 2025-08-26 | 0 | Met | Daksh Karnik | 223512
ST02127 | PRJ026 | CL006 | ICICI Bank | Pune Site-046 | Pune | West | 200 | Testing | 2025-06-26 | 2025-07-26 | 2025-07-22 | 2025-08-12 |  | 12 | Marginal | Logan Sami | 260159
ST02128 | PRJ026 | CL006 | ICICI Bank | Surat Site-047 | Surat | West | 20 | Live | 2025-06-22 | 2025-08-21 | 2025-08-16 | 2025-09-14 | 2025-09-11 | 0 | Met | Chandresh Zachariah | 129330
ST02129 | PRJ026 | CL006 | ICICI Bank | Pune Site-048 | Pune | West | 100 | Testing | 2025-06-24 | 2025-07-19 | 2025-07-26 | 2025-08-07 |  | 12 | Marginal | Ekapad Walia | 272266
ST02130 | PRJ026 | CL006 | ICICI Bank | Pune Site-049 | Pune | West | 20 | Live | 2025-06-24 | 2025-08-09 | 2025-08-08 | 2025-08-25 | 2025-08-23 | 0 | Met | Dipta Bhandari | 123638
ST02131 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-050 | Ahmedabad | West | 10 | Live | 2025-06-30 | 2025-08-21 | 2025-08-17 | 2025-09-13 | 2025-09-25 | 0 | Met | Yatin Baral | 233700
ST02132 | PRJ026 | CL006 | ICICI Bank | Surat Site-051 | Surat | West | 200 | Pending Acceptance | 2025-06-15 | 2025-08-12 | 2025-08-12 | 2025-08-23 | 2025-08-23 | 0 | Met | Gavin Batta | 186780
ST02133 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-052 | Ahmedabad | West | 100 | Live | 2025-06-16 | 2025-07-11 | 2025-07-12 | 2025-07-25 | 2025-08-03 | 1 | Met | Michael Dutta | 70230
ST02134 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-053 | Ahmedabad | West | 20 | Testing | 2025-07-01 | 2025-08-11 | 2025-08-07 | 2025-08-31 |  | 12 | Marginal | Girik Khalsa | 108168
ST02135 | PRJ026 | CL006 | ICICI Bank | Pune Site-054 | Pune | West | 100 | Live | 2025-06-17 | 2025-08-14 | 2025-08-21 | 2025-08-25 | 2025-08-31 | 7 | Met | Yashica Issac | 83467
ST02136 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-055 | Mumbai | West | 50 | Installation Scheduled | 2025-07-03 | 2025-08-22 | 2025-08-17 | 2025-09-16 |  | 7 | Met | Ranveer Yadav | 231428
ST02137 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-056 | Ahmedabad | West | 10 | Installation Scheduled | 2025-07-07 | 2025-07-30 | 2025-07-29 | 2025-08-29 |  | 3 | Met | Bhavika Sampath | 241795
ST02138 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-057 | Mumbai | West | 100 | Installation Scheduled | 2025-07-07 | 2025-07-31 | 2025-08-05 | 2025-08-17 |  | 4 | Met | Quincy Biswas | 255739
ST02139 | PRJ026 | CL006 | ICICI Bank | Surat Site-058 | Surat | West | 200 | Pending Acceptance | 2025-06-18 | 2025-08-03 | 2025-08-03 | 2025-08-20 | 2025-08-27 | 0 | Met | Arya Shere | 45727
ST02140 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-059 | Ahmedabad | West | 50 | Installation Scheduled | 2025-06-14 | 2025-07-12 | 2025-07-19 | 2025-07-24 |  | 8 | Marginal | Anamika Kanda | 79010
ST02141 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-060 | Ahmedabad | West | 100 | Installation Done | 2025-07-01 | 2025-08-18 | 2025-08-13 | 2025-09-03 |  | 12 | Marginal | Girik Khalsa | 57692
ST02142 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-061 | Ahmedabad | West | 100 | Pending Acceptance | 2025-06-15 | 2025-07-30 | 2025-08-01 | 2025-08-10 | 2025-08-19 | 2 | Met | Devika Rastogi | 158763
ST02143 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-062 | Mumbai | West | 100 | Installation Done | 2025-06-18 | 2025-08-10 | 2025-08-07 | 2025-09-09 |  | 12 | Marginal | Victor Kannan | 264524
ST02144 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-063 | Mumbai | West | 200 | Testing | 2025-07-02 | 2025-07-29 | 2025-07-24 | 2025-08-14 |  | 12 | Marginal | Dominic Kakar | 200284
ST02145 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-064 | Mumbai | West | 20 | Pending Acceptance | 2025-06-15 | 2025-07-20 | 2025-07-15 | 2025-08-03 | 2025-08-11 | 0 | Met | Anamika Kanda | 204464
ST02146 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-065 | Ahmedabad | West | 200 | Installation Scheduled | 2025-07-06 | 2025-08-07 | 2025-08-16 | 2025-08-28 |  | 7 | Met | Ranveer Yadav | 105624
ST02147 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-066 | Mumbai | West | 200 | Testing | 2025-06-19 | 2025-08-03 | 2025-07-30 | 2025-08-14 |  | 12 | Marginal | Madhavi Lanka | 56271
ST02148 | PRJ026 | CL006 | ICICI Bank | Pune Site-067 | Pune | West | 50 | Live | 2025-06-28 | 2025-08-09 | 2025-08-19 | 2025-08-28 | 2025-09-04 | 10 | Marginal | Victor Kannan | 210193
ST02149 | PRJ026 | CL006 | ICICI Bank | Pune Site-068 | Pune | West | 50 | Survey Pending | 2025-06-23 | 2025-08-17 |  | 2025-09-15 |  | 4 | Met | Irya Sampath | 104016
ST02150 | PRJ026 | CL006 | ICICI Bank | Mumbai Site-069 | Mumbai | West | 200 | ROW In Progress | 2025-06-14 | 2025-08-13 |  | 2025-09-09 |  | 1 | Met | Faqid Savant | 136189
ST02151 | PRJ026 | CL006 | ICICI Bank | Ahmedabad Site-070 | Ahmedabad | West | 100 | Installation Done | 2025-06-23 | 2025-07-31 | 2025-08-05 | 2025-08-22 |  | 12 | Marginal | Yashica Issac | 272267
ST02152 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-001 | Bengaluru | South | 50 | Installation Scheduled | 2025-10-27 | 2025-11-23 | 2025-11-18 | 2025-12-03 |  | 6 | Met | Raksha Varughese | 100953
ST02153 | PRJ027 | CL006 | ICICI Bank | Chennai Site-002 | Chennai | South | 20 | ROW In Progress | 2025-11-13 | 2025-12-30 |  | 2026-01-29 |  | 2 | Met | Wahab Raval | 162807
ST02154 | PRJ027 | CL006 | ICICI Bank | Kochi Site-003 | Kochi | South | 10 | Installation Done | 2025-10-26 | 2025-11-19 | 2025-11-27 | 2025-12-15 |  | 12 | Marginal | Chandresh Zachariah | 150331
ST02155 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-004 | Hyderabad | South | 10 | Live | 2025-10-20 | 2025-12-07 | 2025-12-02 | 2025-12-23 | 2025-12-31 | 0 | Met | Devika Rastogi | 144208
ST02156 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-005 | Bengaluru | South | 10 | Installation Scheduled | 2025-10-30 | 2025-11-29 | 2025-12-03 | 2025-12-13 |  | 4 | Met | Diya Rattan | 212854
ST02157 | PRJ027 | CL006 | ICICI Bank | Kochi Site-006 | Kochi | South | 10 | Live | 2025-10-29 | 2025-11-21 | 2025-11-20 | 2025-12-16 | 2025-12-21 | 0 | Met | Madhavi Lanka | 169057
ST02158 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-007 | Hyderabad | South | 50 | Installation Done | 2025-11-02 | 2025-12-21 | 2025-12-29 | 2026-01-04 |  | 12 | Marginal | Ekbal Garg | 265687
ST02159 | PRJ027 | CL006 | ICICI Bank | Kochi Site-008 | Kochi | South | 200 | Live | 2025-10-20 | 2025-11-11 | 2025-11-13 | 2025-12-03 | 2025-12-06 | 2 | Met | Ikbal Kothari | 211276
ST02160 | PRJ027 | CL006 | ICICI Bank | Kochi Site-009 | Kochi | South | 200 | Live | 2025-11-14 | 2025-12-20 | 2025-12-28 | 2026-01-01 | 2026-01-07 | 8 | Marginal | Mohammed Gupta | 115062
ST02161 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-010 | Hyderabad | South | 200 | Testing | 2025-11-09 | 2026-01-05 | 2026-01-06 | 2026-01-18 |  | 12 | Marginal | Kabir Soman | 198898
ST02162 | PRJ027 | CL006 | ICICI Bank | Kochi Site-011 | Kochi | South | 10 | Live | 2025-11-06 | 2025-12-13 | 2025-12-10 | 2025-12-31 | 2026-01-10 | 0 | Met | Urvashi Ray | 258350
ST02163 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-012 | Hyderabad | South | 100 | Survey Pending | 2025-10-29 | 2025-12-26 |  | 2026-01-11 |  | 2 | Met | Madhavi Lanka | 122751
ST02164 | PRJ027 | CL006 | ICICI Bank | Chennai Site-013 | Chennai | South | 100 | ROW In Progress | 2025-11-12 | 2025-12-16 |  | 2026-01-13 |  | 4 | Met | Michael Dutta | 79278
ST02165 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-014 | Bengaluru | South | 10 | ROW In Progress | 2025-11-06 | 2026-01-02 |  | 2026-01-29 |  | 1 | Met | Irya Sampath | 206459
ST02166 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-015 | Hyderabad | South | 10 | Testing | 2025-10-30 | 2025-12-03 | 2025-12-06 | 2025-12-13 |  | 12 | Marginal | Priya Rastogi | 92828
ST02167 | PRJ027 | CL006 | ICICI Bank | Kochi Site-016 | Kochi | South | 200 | Installation Done | 2025-11-11 | 2025-12-11 | 2025-12-10 | 2025-12-27 |  | 12 | Marginal | Arya Sunder | 175471
ST02168 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-017 | Hyderabad | South | 100 | ROW In Progress | 2025-11-09 | 2025-12-09 |  | 2025-12-29 |  | 6 | Met | Yatin Baral | 227474
ST02169 | PRJ027 | CL006 | ICICI Bank | Kochi Site-018 | Kochi | South | 20 | Survey Pending | 2025-11-05 | 2025-12-27 |  | 2026-01-22 |  | 2 | Met | Ekapad Walia | 163030
ST02170 | PRJ027 | CL006 | ICICI Bank | Kochi Site-019 | Kochi | South | 100 | Survey Pending | 2025-11-10 | 2026-01-03 |  | 2026-01-22 |  | 1 | Met | Simon Tata | 145773
ST02171 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-020 | Bengaluru | South | 100 | Pending Acceptance | 2025-10-26 | 2025-12-01 | 2025-12-07 | 2025-12-23 | 2025-12-29 | 6 | Met | Victor Kannan | 147607
ST02172 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-021 | Bengaluru | South | 200 | Live | 2025-10-30 | 2025-12-21 | 2025-12-29 | 2026-01-14 | 2026-01-19 | 8 | Marginal | Faqid Savant | 95540
ST02173 | PRJ027 | CL006 | ICICI Bank | Chennai Site-022 | Chennai | South | 10 | Pending Acceptance | 2025-11-08 | 2025-12-26 | 2025-12-25 | 2026-01-11 | 2026-01-20 | 0 | Met | Simon Tata | 265046
ST02174 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-023 | Bengaluru | South | 100 | Testing | 2025-10-24 | 2025-12-09 | 2025-12-06 | 2025-12-31 |  | 12 | Marginal | Harini Choudhury | 46942
ST02175 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-024 | Bengaluru | South | 100 | Installation Done | 2025-10-31 | 2025-12-10 | 2025-12-19 | 2026-01-05 |  | 12 | Marginal | Ekavir Bhargava | 131650
ST02176 | PRJ027 | CL006 | ICICI Bank | Kochi Site-025 | Kochi | South | 100 | Live | 2025-11-05 | 2025-12-20 | 2025-12-25 | 2026-01-09 | 2026-01-17 | 5 | Met | Ikbal Kothari | 71181
ST02177 | PRJ027 | CL006 | ICICI Bank | Chennai Site-026 | Chennai | South | 100 | Installation Scheduled | 2025-11-02 | 2025-12-09 | 2025-12-04 | 2025-12-19 |  | 0 | Met | Mohammed Gupta | 133494
ST02178 | PRJ027 | CL006 | ICICI Bank | Kochi Site-027 | Kochi | South | 100 | Live | 2025-10-24 | 2025-12-01 | 2025-11-27 | 2025-12-22 | 2025-12-21 | 0 | Met | Arya Shere | 137510
ST02179 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-028 | Hyderabad | South | 10 | Installation Scheduled | 2025-10-24 | 2025-11-24 | 2025-11-27 | 2025-12-13 |  | 4 | Met | Vansha Thakkar | 122622
ST02180 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-029 | Bengaluru | South | 200 | ROW In Progress | 2025-10-26 | 2025-11-27 |  | 2025-12-23 |  | 6 | Met | Nitesh Raghavan | 49453
ST02181 | PRJ027 | CL006 | ICICI Bank | Chennai Site-030 | Chennai | South | 20 | Live | 2025-11-04 | 2025-11-26 | 2025-11-23 | 2025-12-20 | 2025-12-17 | 0 | Met | Niharika Sunder | 95852
ST02182 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-031 | Bengaluru | South | 10 | Live | 2025-10-29 | 2025-12-05 | 2025-12-04 | 2025-12-21 | 2025-12-31 | 0 | Met | Ekiya Suresh | 56854
ST02183 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-032 | Hyderabad | South | 10 | Live | 2025-11-06 | 2026-01-04 | 2026-01-06 | 2026-01-14 | 2026-01-19 | 2 | Met | Kabir Soman | 115546
ST02184 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-033 | Bengaluru | South | 100 | Testing | 2025-11-02 | 2026-01-01 | 2025-12-29 | 2026-01-30 |  | 12 | Marginal | Quincy Biswas | 272542
ST02185 | PRJ027 | CL006 | ICICI Bank | Kochi Site-034 | Kochi | South | 50 | ROW In Progress | 2025-10-28 | 2025-12-08 |  | 2025-12-22 |  | 8 | Marginal | Upadhriti Wadhwa | 99983
ST02186 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-035 | Hyderabad | South | 50 | Installation Done | 2025-10-28 | 2025-12-20 | 2025-12-15 | 2026-01-08 |  | 12 | Marginal | Dominic Kakar | 166644
ST02187 | PRJ027 | CL006 | ICICI Bank | Chennai Site-036 | Chennai | South | 200 | Installation Done | 2025-11-13 | 2025-12-27 | 2026-01-06 | 2026-01-15 |  | 12 | Marginal | Nihal Shere | 195218
ST02188 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-037 | Hyderabad | South | 50 | Installation Done | 2025-11-09 | 2025-12-13 | 2025-12-16 | 2025-12-23 |  | 12 | Marginal | Dominic Kakar | 81793
ST02189 | PRJ027 | CL006 | ICICI Bank | Kochi Site-038 | Kochi | South | 20 | Survey Pending | 2025-11-11 | 2026-01-09 |  | 2026-01-27 |  | 4 | Met | Dominic Kakar | 255090
ST02190 | PRJ027 | CL006 | ICICI Bank | Chennai Site-039 | Chennai | South | 200 | Pending Acceptance | 2025-10-31 | 2025-12-23 | 2025-12-22 | 2026-01-12 | 2026-01-17 | 0 | Met | Anamika Kanda | 167852
ST02191 | PRJ027 | CL006 | ICICI Bank | Chennai Site-040 | Chennai | South | 100 | Live | 2025-10-24 | 2025-11-15 | 2025-11-17 | 2025-11-28 | 2025-12-09 | 2 | Met | Vansha Thakkar | 119895
ST02192 | PRJ027 | CL006 | ICICI Bank | Kochi Site-041 | Kochi | South | 10 | Installation Done | 2025-11-08 | 2025-12-21 | 2025-12-19 | 2026-01-09 |  | 12 | Marginal | Nitesh Raghavan | 238413
ST02193 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-042 | Hyderabad | South | 200 | Pending Acceptance | 2025-11-10 | 2026-01-02 | 2026-01-02 | 2026-01-18 | 2026-01-15 | 0 | Met | Harini Choudhury | 264964
ST02194 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-043 | Hyderabad | South | 20 | Live | 2025-11-05 | 2025-12-20 | 2025-12-23 | 2026-01-02 | 2026-01-12 | 3 | Met | Raksha Varughese | 214529
ST02195 | PRJ027 | CL006 | ICICI Bank | Chennai Site-044 | Chennai | South | 200 | ROW In Progress | 2025-11-02 | 2025-11-23 |  | 2025-12-23 |  | 5 | Met | Arya Shere | 232808
ST02196 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-045 | Hyderabad | South | 20 | ROW In Progress | 2025-11-02 | 2025-12-22 |  | 2026-01-10 |  | 8 | Marginal | Michael Dutta | 267640
ST02197 | PRJ027 | CL006 | ICICI Bank | Kochi Site-046 | Kochi | South | 200 | ROW In Progress | 2025-10-20 | 2025-12-03 |  | 2025-12-25 |  | 2 | Met | Kabir Soman | 217281
ST02198 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-047 | Bengaluru | South | 200 | Installation Done | 2025-11-14 | 2026-01-06 | 2026-01-03 | 2026-01-30 |  | 12 | Marginal | Yatin Baral | 84211
ST02199 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-048 | Hyderabad | South | 100 | Live | 2025-11-01 | 2025-12-14 | 2025-12-19 | 2026-01-11 | 2026-01-17 | 5 | Met | Anamika Kanda | 155207
ST02200 | PRJ027 | CL006 | ICICI Bank | Chennai Site-049 | Chennai | South | 10 | Installation Scheduled | 2025-11-03 | 2025-12-02 | 2025-12-04 | 2026-01-01 |  | 7 | Met | Mohammed Gupta | 208754
ST02201 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-050 | Bengaluru | South | 10 | Pending Acceptance | 2025-10-25 | 2025-11-28 | 2025-12-08 | 2025-12-26 | 2025-12-24 | 10 | Marginal | Nitesh Raghavan | 127931
ST02202 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-051 | Hyderabad | South | 100 | Live | 2025-11-11 | 2026-01-04 | 2026-01-13 | 2026-01-15 | 2026-01-20 | 9 | Marginal | Mohammed Gupta | 197285
ST02203 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-052 | Hyderabad | South | 50 | Live | 2025-10-22 | 2025-12-21 | 2025-12-30 | 2026-01-13 | 2026-01-25 | 9 | Marginal | Urvashi Ray | 98090
ST02204 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-053 | Bengaluru | South | 100 | Pending Acceptance | 2025-11-06 | 2025-12-30 | 2025-12-26 | 2026-01-23 | 2026-01-26 | 0 | Met | Liam Koshy | 137469
ST02205 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-054 | Bengaluru | South | 200 | Installation Scheduled | 2025-11-08 | 2025-12-01 | 2025-12-05 | 2025-12-22 |  | 8 | Marginal | Faqid Savant | 88947
ST02206 | PRJ027 | CL006 | ICICI Bank | Kochi Site-055 | Kochi | South | 100 | Live | 2025-10-26 | 2025-12-17 | 2025-12-20 | 2026-01-13 | 2026-01-24 | 3 | Met | Ekapad Walia | 182658
ST02207 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-056 | Bengaluru | South | 20 | Live | 2025-10-20 | 2025-12-09 | 2025-12-16 | 2025-12-21 | 2025-12-22 | 7 | Met | Girik Khalsa | 223587
ST02208 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-057 | Bengaluru | South | 10 | ROW In Progress | 2025-11-09 | 2026-01-06 |  | 2026-01-16 |  | 5 | Met | Michael Dutta | 85550
ST02209 | PRJ027 | CL006 | ICICI Bank | Kochi Site-058 | Kochi | South | 10 | Live | 2025-11-14 | 2025-12-10 | 2025-12-09 | 2025-12-20 | 2026-01-01 | 0 | Met | Girik Khalsa | 146718
ST02210 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-059 | Bengaluru | South | 20 | Live | 2025-10-21 | 2025-12-09 | 2025-12-08 | 2025-12-26 | 2026-01-07 | 0 | Met | Aarush Lall | 146612
ST02211 | PRJ027 | CL006 | ICICI Bank | Chennai Site-060 | Chennai | South | 10 | Installation Scheduled | 2025-11-11 | 2026-01-02 | 2026-01-10 | 2026-01-21 |  | 7 | Met | Raksha Varughese | 232131
ST02212 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-061 | Hyderabad | South | 200 | Survey Pending | 2025-11-04 | 2025-12-14 |  | 2026-01-07 |  | 8 | Marginal | Niharika Sunder | 271034
ST02213 | PRJ027 | CL006 | ICICI Bank | Chennai Site-062 | Chennai | South | 100 | Pending Acceptance | 2025-10-26 | 2025-12-06 | 2025-12-12 | 2025-12-30 | 2025-12-27 | 6 | Met | Bhavika Sampath | 106898
ST02214 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-063 | Bengaluru | South | 50 | Live | 2025-11-14 | 2025-12-17 | 2025-12-15 | 2026-01-06 | 2026-01-13 | 0 | Met | Dominic Kakar | 223610
ST02215 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-064 | Hyderabad | South | 10 | Installation Done | 2025-10-21 | 2025-12-02 | 2025-12-01 | 2026-01-01 |  | 12 | Marginal | Dakshesh Trivedi | 206970
ST02216 | PRJ027 | CL006 | ICICI Bank | Chennai Site-065 | Chennai | South | 50 | Installation Done | 2025-11-11 | 2025-12-18 | 2025-12-21 | 2025-12-29 |  | 12 | Marginal | Logan Sami | 178457
ST02217 | PRJ027 | CL006 | ICICI Bank | Chennai Site-066 | Chennai | South | 100 | ROW In Progress | 2025-10-22 | 2025-11-30 |  | 2025-12-12 |  | 4 | Met | Simon Tata | 215760
ST02218 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-067 | Bengaluru | South | 200 | Live | 2025-10-27 | 2025-12-06 | 2025-12-02 | 2025-12-22 | 2025-12-31 | 0 | Met | Bhavika Sampath | 74840
ST02219 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-068 | Hyderabad | South | 200 | Testing | 2025-11-01 | 2025-12-25 | 2025-12-22 | 2026-01-05 |  | 12 | Marginal | Bhavika Sampath | 275251
ST02220 | PRJ027 | CL006 | ICICI Bank | Kochi Site-069 | Kochi | South | 50 | Testing | 2025-11-06 | 2025-11-29 | 2025-11-28 | 2025-12-16 |  | 12 | Marginal | Victor Kannan | 138627
ST02221 | PRJ027 | CL006 | ICICI Bank | Kochi Site-070 | Kochi | South | 50 | Installation Done | 2025-10-28 | 2025-12-13 | 2025-12-23 | 2026-01-10 |  | 12 | Marginal | Daksh Karnik | 244565
ST02222 | PRJ027 | CL006 | ICICI Bank | Chennai Site-071 | Chennai | South | 100 | Live | 2025-11-02 | 2025-12-19 | 2025-12-23 | 2025-12-29 | 2025-12-28 | 4 | Met | Kabir Soman | 80314
ST02223 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-072 | Hyderabad | South | 50 | Installation Done | 2025-11-13 | 2026-01-03 | 2026-01-04 | 2026-01-16 |  | 12 | Marginal | Wahab Raval | 140958
ST02224 | PRJ027 | CL006 | ICICI Bank | Kochi Site-073 | Kochi | South | 10 | Live | 2025-10-25 | 2025-12-22 | 2025-12-21 | 2026-01-15 | 2026-01-19 | 0 | Met | Chandresh Zachariah | 191685
ST02225 | PRJ027 | CL006 | ICICI Bank | Chennai Site-074 | Chennai | South | 50 | Live | 2025-10-24 | 2025-12-19 | 2025-12-16 | 2026-01-08 | 2026-01-16 | 0 | Met | Yashica Issac | 260389
ST02226 | PRJ027 | CL006 | ICICI Bank | Chennai Site-075 | Chennai | South | 200 | Installation Scheduled | 2025-10-29 | 2025-11-23 | 2025-11-30 | 2025-12-14 |  | 1 | Met | Darsh Rau | 209319
ST02227 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-076 | Hyderabad | South | 100 | Testing | 2025-11-07 | 2025-12-24 | 2025-12-31 | 2026-01-03 |  | 12 | Marginal | Ekapad Walia | 123614
ST02228 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-077 | Hyderabad | South | 50 | Live | 2025-11-04 | 2025-12-10 | 2025-12-17 | 2025-12-25 | 2025-12-25 | 7 | Met | Ikbal Kothari | 187808
ST02229 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-078 | Hyderabad | South | 100 | Live | 2025-11-09 | 2025-12-30 | 2026-01-02 | 2026-01-28 | 2026-01-28 | 3 | Met | Liam Koshy | 160855
ST02230 | PRJ027 | CL006 | ICICI Bank | Bengaluru Site-079 | Bengaluru | South | 100 | Installation Scheduled | 2025-10-25 | 2025-11-24 | 2025-11-21 | 2025-12-20 |  | 1 | Met | Priya Rastogi | 214221
ST02231 | PRJ027 | CL006 | ICICI Bank | Hyderabad Site-080 | Hyderabad | South | 100 | Live | 2025-10-23 | 2025-11-26 | 2025-11-30 | 2025-12-14 | 2025-12-26 | 4 | Met | Tara Dhar | 229872
ST02232 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-001 | Bhubaneswar | East | 100 | Testing | 2025-11-07 | 2026-01-06 | 2026-01-04 | 2026-01-16 |  | 12 | Marginal | Priya Rastogi | 188862
ST02233 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-002 | Bhubaneswar | East | 50 | ROW In Progress | 2025-11-21 | 2026-01-05 |  | 2026-02-04 |  | 8 | Marginal | Nitesh Raghavan | 123955
ST02234 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-003 | Kolkata | East | 10 | Installation Scheduled | 2025-11-16 | 2025-12-09 | 2025-12-17 | 2026-01-08 |  | 8 | Marginal | Aarush Lall | 271420
ST02235 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-004 | Bhubaneswar | East | 50 | Live | 2025-11-23 | 2025-12-25 | 2025-12-27 | 2026-01-06 | 2026-01-14 | 2 | Met | Ekiya Suresh | 230264
ST02236 | PRJ028 | CL006 | ICICI Bank | Patna Site-005 | Patna | East | 20 | ROW In Progress | 2025-11-14 | 2025-12-06 |  | 2025-12-17 |  | 2 | Met | Simon Tata | 93501
ST02237 | PRJ028 | CL006 | ICICI Bank | Patna Site-006 | Patna | East | 20 | Installation Done | 2025-11-12 | 2025-12-23 | 2025-12-18 | 2026-01-12 |  | 12 | Marginal | Kashvi Edwin | 120577
ST02238 | PRJ028 | CL006 | ICICI Bank | Patna Site-007 | Patna | East | 100 | ROW In Progress | 2025-11-11 | 2025-12-10 |  | 2025-12-20 |  | 6 | Met | Dakshesh Trivedi | 54612
ST02239 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-008 | Kolkata | East | 100 | Installation Scheduled | 2025-11-10 | 2025-12-20 | 2025-12-19 | 2025-12-30 |  | 1 | Met | Nitesh Raghavan | 279051
ST02240 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-009 | Kolkata | East | 20 | Installation Scheduled | 2025-11-25 | 2026-01-17 | 2026-01-16 | 2026-01-31 |  | 2 | Met | Ekavir Bhargava | 54793
ST02241 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-010 | Kolkata | East | 10 | Pending Acceptance | 2025-11-09 | 2026-01-05 | 2026-01-04 | 2026-01-20 | 2026-01-22 | 0 | Met | Logan Sami | 144032
ST02242 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-011 | Kolkata | East | 20 | Live | 2025-11-05 | 2026-01-03 | 2025-12-30 | 2026-01-15 | 2026-01-15 | 0 | Met | Jai Kota | 185033
ST02243 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-012 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-11-20 | 2025-12-16 | 2025-12-17 | 2026-01-02 |  | 2 | Met | Isaac Patil | 180534
ST02244 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-013 | Bhubaneswar | East | 50 | Pending Acceptance | 2025-11-05 | 2025-12-08 | 2025-12-08 | 2025-12-25 | 2025-12-30 | 0 | Met | Niharika Sunder | 223067
ST02245 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-014 | Bhubaneswar | East | 50 | Installation Scheduled | 2025-11-08 | 2025-12-17 | 2025-12-17 | 2026-01-12 |  | 6 | Met | Arya Sunder | 204753
ST02246 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-015 | Bhubaneswar | East | 200 | Installation Done | 2025-11-02 | 2025-12-03 | 2025-12-06 | 2025-12-31 |  | 12 | Marginal | Madhavi Lanka | 157564
ST02247 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-016 | Kolkata | East | 100 | Installation Scheduled | 2025-11-25 | 2025-12-18 | 2025-12-24 | 2026-01-04 |  | 6 | Met | Vansha Thakkar | 208866
ST02248 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-017 | Kolkata | East | 20 | Installation Scheduled | 2025-11-20 | 2026-01-14 | 2026-01-20 | 2026-01-29 |  | 7 | Met | Ikbal Kothari | 151106
ST02249 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-018 | Kolkata | East | 200 | Installation Scheduled | 2025-11-07 | 2025-12-21 | 2025-12-28 | 2026-01-11 |  | 5 | Met | Liam Koshy | 115126
ST02250 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-019 | Bhubaneswar | East | 200 | Live | 2025-11-14 | 2025-12-14 | 2025-12-20 | 2025-12-31 | 2025-12-29 | 6 | Met | Tanay Rattan | 154180
ST02251 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-020 | Bhubaneswar | East | 100 | ROW In Progress | 2025-11-17 | 2025-12-30 |  | 2026-01-16 |  | 3 | Met | Logan Sami | 86747
ST02252 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-021 | Bhubaneswar | East | 20 | Live | 2025-11-26 | 2026-01-02 | 2026-01-09 | 2026-01-25 | 2026-02-01 | 7 | Met | Unni Bhagat | 99625
ST02253 | PRJ028 | CL006 | ICICI Bank | Patna Site-022 | Patna | East | 200 | Testing | 2025-11-24 | 2026-01-09 | 2026-01-08 | 2026-02-08 |  | 12 | Marginal | Unni Bhagat | 241067
ST02254 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-023 | Kolkata | East | 50 | ROW In Progress | 2025-11-08 | 2025-12-22 |  | 2026-01-16 |  | 2 | Met | Devansh Rajan | 133802
ST02255 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-024 | Bhubaneswar | East | 20 | ROW In Progress | 2025-11-22 | 2026-01-10 |  | 2026-02-09 |  | 6 | Met | Alka Wable | 129929
ST02256 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-025 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-11-23 | 2025-12-31 | 2026-01-08 | 2026-01-27 |  | 5 | Met | Nitesh Raghavan | 109579
ST02257 | PRJ028 | CL006 | ICICI Bank | Patna Site-026 | Patna | East | 20 | Testing | 2025-11-15 | 2025-12-11 | 2025-12-18 | 2026-01-07 |  | 12 | Marginal | Ekavir Varkey | 193244
ST02258 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-027 | Bhubaneswar | East | 10 | Testing | 2025-11-09 | 2026-01-07 | 2026-01-04 | 2026-01-30 |  | 12 | Marginal | Ikbal Kothari | 270560
ST02259 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-028 | Kolkata | East | 100 | Live | 2025-11-18 | 2025-12-13 | 2025-12-11 | 2026-01-04 | 2026-01-07 | 0 | Met | Gavin Batta | 52661
ST02260 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-029 | Kolkata | East | 100 | Survey Pending | 2025-11-27 | 2025-12-30 |  | 2026-01-24 |  | 2 | Met | Tara Dhar | 168608
ST02261 | PRJ028 | CL006 | ICICI Bank | Patna Site-030 | Patna | East | 200 | ROW In Progress | 2025-11-26 | 2025-12-16 |  | 2025-12-29 |  | 4 | Met | Nitesh Raghavan | 258521
ST02262 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-031 | Bhubaneswar | East | 200 | Pending Acceptance | 2025-11-24 | 2025-12-15 | 2025-12-14 | 2026-01-06 | 2026-01-11 | 0 | Met | Ekapad Walia | 75887
ST02263 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-032 | Kolkata | East | 100 | Pending Acceptance | 2025-11-11 | 2025-12-26 | 2025-12-27 | 2026-01-23 | 2026-01-29 | 1 | Met | Chandresh Zachariah | 93219
ST02264 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-033 | Bhubaneswar | East | 50 | Live | 2025-11-06 | 2026-01-02 | 2026-01-02 | 2026-01-24 | 2026-01-30 | 0 | Met | Girik Khalsa | 98769
ST02265 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-034 | Kolkata | East | 20 | Testing | 2025-11-16 | 2025-12-14 | 2025-12-18 | 2025-12-24 |  | 12 | Marginal | Chandresh Zachariah | 260130
ST02266 | PRJ028 | CL006 | ICICI Bank | Patna Site-035 | Patna | East | 100 | Installation Scheduled | 2025-11-23 | 2025-12-18 | 2025-12-16 | 2026-01-02 |  | 6 | Met | Ekavir Varkey | 193676
ST02267 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-036 | Bhubaneswar | East | 200 | ROW In Progress | 2025-11-15 | 2026-01-02 |  | 2026-01-12 |  | 6 | Met | Alka Wable | 102265
ST02268 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-037 | Bhubaneswar | East | 20 | Installation Scheduled | 2025-11-05 | 2025-11-27 | 2025-11-25 | 2025-12-19 |  | 1 | Met | Darsh Rau | 250853
ST02269 | PRJ028 | CL006 | ICICI Bank | Patna Site-038 | Patna | East | 200 | Survey Pending | 2025-11-14 | 2025-12-19 |  | 2026-01-16 |  | 4 | Met | Diya Rattan | 244601
ST02270 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-039 | Kolkata | East | 100 | ROW In Progress | 2025-11-09 | 2025-12-16 |  | 2026-01-03 |  | 3 | Met | Tanay Rattan | 263426
ST02271 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-040 | Bhubaneswar | East | 200 | Live | 2025-11-08 | 2025-12-15 | 2025-12-13 | 2026-01-03 | 2026-01-01 | 0 | Met | Devansh Nigam | 68228
ST02272 | PRJ028 | CL006 | ICICI Bank | Patna Site-041 | Patna | East | 10 | Survey Pending | 2025-11-04 | 2025-12-21 |  | 2026-01-15 |  | 3 | Met | Priya Rastogi | 110810
ST02273 | PRJ028 | CL006 | ICICI Bank | Patna Site-042 | Patna | East | 10 | ROW In Progress | 2025-11-14 | 2025-12-04 |  | 2025-12-23 |  | 1 | Met | Simon Tata | 267408
ST02274 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-043 | Bhubaneswar | East | 100 | Live | 2025-11-07 | 2025-11-29 | 2025-11-28 | 2025-12-25 | 2026-01-04 | 0 | Met | Advay Contractor | 150958
ST02275 | PRJ028 | CL006 | ICICI Bank | Patna Site-044 | Patna | East | 20 | Pending Acceptance | 2025-11-25 | 2025-12-19 | 2025-12-15 | 2026-01-05 | 2026-01-11 | 0 | Met | Advay Contractor | 266677
ST02276 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-045 | Kolkata | East | 20 | Installation Scheduled | 2025-11-25 | 2026-01-05 | 2026-01-09 | 2026-02-01 |  | 4 | Met | Tara Dhar | 99926
ST02277 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-046 | Bhubaneswar | East | 100 | ROW In Progress | 2025-11-15 | 2025-12-08 |  | 2026-01-02 |  | 1 | Met | Michael Dutta | 98846
ST02278 | PRJ028 | CL006 | ICICI Bank | Patna Site-047 | Patna | East | 10 | Installation Done | 2025-11-04 | 2025-12-14 | 2025-12-24 | 2025-12-27 |  | 12 | Marginal | Wahab Raval | 75410
ST02279 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-048 | Kolkata | East | 50 | Live | 2025-11-27 | 2025-12-23 | 2025-12-27 | 2026-01-02 | 2026-01-03 | 4 | Met | Dipta Bhandari | 220376
ST02280 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-049 | Kolkata | East | 50 | ROW In Progress | 2025-11-18 | 2026-01-12 |  | 2026-02-11 |  | 1 | Met | Gavin Batta | 76255
ST02281 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-050 | Kolkata | East | 100 | Live | 2025-11-16 | 2026-01-15 | 2026-01-19 | 2026-02-04 | 2026-02-05 | 4 | Met | Priya Rastogi | 247534
ST02282 | PRJ028 | CL006 | ICICI Bank | Patna Site-051 | Patna | East | 50 | Installation Scheduled | 2025-11-15 | 2026-01-04 | 2026-01-10 | 2026-01-29 |  | 6 | Met | Nitesh Raghavan | 94157
ST02283 | PRJ028 | CL006 | ICICI Bank | Patna Site-052 | Patna | East | 50 | Survey Pending | 2025-11-19 | 2025-12-14 |  | 2025-12-25 |  | 7 | Met | Upadhriti Wadhwa | 217391
ST02284 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-053 | Bhubaneswar | East | 20 | ROW In Progress | 2025-11-20 | 2025-12-28 |  | 2026-01-12 |  | 3 | Met | Advay Contractor | 136318
ST02285 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-054 | Bhubaneswar | East | 50 | Live | 2025-11-04 | 2025-12-09 | 2025-12-06 | 2025-12-29 | 2026-01-01 | 0 | Met | Simon Tata | 152731
ST02286 | PRJ028 | CL006 | ICICI Bank | Patna Site-055 | Patna | East | 200 | Live | 2025-11-23 | 2025-12-24 | 2025-12-31 | 2026-01-05 | 2026-01-15 | 7 | Met | Jai Kota | 258424
ST02287 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-056 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-11-12 | 2025-12-13 | 2025-12-23 | 2026-01-01 |  | 1 | Met | Radhika Dugar | 210936
ST02288 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-057 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-11-25 | 2025-12-19 | 2025-12-28 | 2026-01-16 |  | 8 | Marginal | Ekavir Bhargava | 181471
ST02289 | PRJ028 | CL006 | ICICI Bank | Patna Site-058 | Patna | East | 200 | Pending Acceptance | 2025-11-13 | 2025-12-30 | 2026-01-06 | 2026-01-28 | 2026-02-03 | 7 | Met | Alka Wable | 60297
ST02290 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-059 | Kolkata | East | 100 | Installation Done | 2025-11-20 | 2026-01-19 | 2026-01-24 | 2026-02-11 |  | 12 | Marginal | Darsh Rau | 218908
ST02291 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-060 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-11-13 | 2026-01-04 | 2026-01-08 | 2026-01-18 |  | 2 | Met | Gavin Batta | 164455
ST02292 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-061 | Kolkata | East | 10 | Installation Done | 2025-11-06 | 2025-12-19 | 2025-12-26 | 2026-01-09 |  | 12 | Marginal | Devansh Nigam | 145343
ST02293 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-062 | Kolkata | East | 50 | Installation Done | 2025-11-23 | 2025-12-15 | 2025-12-12 | 2026-01-03 |  | 12 | Marginal | Upadhriti Wadhwa | 264894
ST02294 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-063 | Kolkata | East | 20 | Survey Pending | 2025-11-14 | 2026-01-05 |  | 2026-02-04 |  | 6 | Met | Devansh Nigam | 55623
ST02295 | PRJ028 | CL006 | ICICI Bank | Patna Site-064 | Patna | East | 100 | Installation Done | 2025-11-26 | 2025-12-22 | 2025-12-17 | 2026-01-01 |  | 12 | Marginal | Niharika Sunder | 186949
ST02296 | PRJ028 | CL006 | ICICI Bank | Patna Site-065 | Patna | East | 200 | Survey Pending | 2025-11-10 | 2025-12-06 |  | 2025-12-31 |  | 2 | Met | Aarush Lall | 47020
ST02297 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-066 | Bhubaneswar | East | 50 | Installation Done | 2025-11-08 | 2025-12-30 | 2025-12-28 | 2026-01-12 |  | 12 | Marginal | Yashica Issac | 81701
ST02298 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-067 | Kolkata | East | 20 | ROW In Progress | 2025-11-06 | 2025-12-07 |  | 2025-12-22 |  | 8 | Marginal | Ekansh Balay | 48452
ST02299 | PRJ028 | CL006 | ICICI Bank | Patna Site-068 | Patna | East | 10 | Installation Scheduled | 2025-11-12 | 2025-12-11 | 2025-12-12 | 2026-01-01 |  | 4 | Met | Ekbal Garg | 116544
ST02300 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-069 | Kolkata | East | 200 | Survey Pending | 2025-11-26 | 2026-01-20 |  | 2026-02-07 |  | 7 | Met | Upadhriti Wadhwa | 104814
ST02301 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-070 | Bhubaneswar | East | 50 | Live | 2025-11-05 | 2025-12-02 | 2025-12-04 | 2025-12-23 | 2025-12-20 | 2 | Met | Wriddhish Bhardwaj | 128541
ST02302 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-071 | Bhubaneswar | East | 50 | Pending Acceptance | 2025-11-07 | 2025-12-30 | 2025-12-29 | 2026-01-09 | 2026-01-19 | 0 | Met | Advay Contractor | 212655
ST02303 | PRJ028 | CL006 | ICICI Bank | Patna Site-072 | Patna | East | 200 | Pending Acceptance | 2025-11-13 | 2026-01-03 | 2025-12-30 | 2026-02-01 | 2026-02-12 | 0 | Met | Devika Rastogi | 52657
ST02304 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-073 | Kolkata | East | 200 | Pending Acceptance | 2025-11-02 | 2025-11-26 | 2025-11-21 | 2025-12-15 | 2025-12-15 | 0 | Met | Ekansh Balay | 272205
ST02305 | PRJ028 | CL006 | ICICI Bank | Patna Site-074 | Patna | East | 20 | Pending Acceptance | 2025-11-09 | 2025-12-18 | 2025-12-15 | 2026-01-16 | 2026-01-23 | 0 | Met | Michael Dutta | 216910
ST02306 | PRJ028 | CL006 | ICICI Bank | Bhubaneswar Site-075 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-11-19 | 2026-01-04 | 2026-01-13 | 2026-01-23 |  | 2 | Met | Diya Rattan | 90950
ST02307 | PRJ028 | CL006 | ICICI Bank | Kolkata Site-076 | Kolkata | East | 20 | Live | 2025-11-23 | 2026-01-17 | 2026-01-19 | 2026-01-27 | 2026-02-05 | 2 | Met | Darsh Rau | 175474
ST02308 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-001 | Bhopal | Central | 10 | Live | 2025-09-10 | 2025-10-23 | 2025-10-25 | 2025-11-17 | 2025-11-29 | 2 | Met | Tara Dhar | 45540
ST02309 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-002 | Bhopal | Central | 100 | Live | 2025-09-09 | 2025-11-05 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 5 | Met | Aarush Lall | 93288
ST02310 | PRJ029 | CL006 | ICICI Bank | Indore Site-003 | Indore | Central | 200 | Installation Done | 2025-09-26 | 2025-11-02 | 2025-11-12 | 2025-11-14 |  | 12 | Marginal | Logan Sami | 137772
ST02311 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-004 | Nagpur | Central | 50 | Installation Scheduled | 2025-09-27 | 2025-11-14 | 2025-11-13 | 2025-12-01 |  | 0 | Met | Darsh Rau | 235567
ST02312 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-005 | Bhopal | Central | 100 | ROW In Progress | 2025-09-11 | 2025-10-06 |  | 2025-10-28 |  | 7 | Met | Priya Rastogi | 119675
ST02313 | PRJ029 | CL006 | ICICI Bank | Indore Site-006 | Indore | Central | 10 | Installation Done | 2025-09-18 | 2025-10-26 | 2025-10-28 | 2025-11-19 |  | 12 | Marginal | Advay Contractor | 206202
ST02314 | PRJ029 | CL006 | ICICI Bank | Indore Site-007 | Indore | Central | 100 | Pending Acceptance | 2025-09-15 | 2025-10-17 | 2025-10-15 | 2025-10-29 | 2025-11-09 | 0 | Met | Nitesh Raghavan | 155289
ST02315 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-008 | Nagpur | Central | 100 | Installation Done | 2025-09-05 | 2025-10-17 | 2025-10-17 | 2025-11-11 |  | 12 | Marginal | Liam Koshy | 77773
ST02316 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-009 | Bhopal | Central | 100 | Live | 2025-09-09 | 2025-11-03 | 2025-10-31 | 2025-12-03 | 2025-12-10 | 0 | Met | Tara Dhar | 151634
ST02317 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-010 | Nagpur | Central | 20 | Survey Pending | 2025-09-27 | 2025-11-25 |  | 2025-12-06 |  | 2 | Met | Raksha Varughese | 63152
ST02318 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-011 | Nagpur | Central | 10 | ROW In Progress | 2025-09-19 | 2025-11-18 |  | 2025-12-15 |  | 7 | Met | Faqid Savant | 209940
ST02319 | PRJ029 | CL006 | ICICI Bank | Indore Site-012 | Indore | Central | 20 | Live | 2025-09-10 | 2025-10-21 | 2025-10-23 | 2025-11-04 | 2025-11-05 | 2 | Met | Quincy Biswas | 77271
ST02320 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-013 | Nagpur | Central | 200 | Installation Done | 2025-09-08 | 2025-10-02 | 2025-10-01 | 2025-10-24 |  | 12 | Marginal | Ekansh Balay | 214639
ST02321 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-014 | Nagpur | Central | 50 | Installation Done | 2025-09-11 | 2025-11-01 | 2025-10-29 | 2025-11-13 |  | 12 | Marginal | Yashica Cherian | 203931
ST02322 | PRJ029 | CL006 | ICICI Bank | Indore Site-015 | Indore | Central | 50 | ROW In Progress | 2025-09-05 | 2025-09-26 |  | 2025-10-13 |  | 7 | Met | Raksha Varughese | 194369
ST02323 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-016 | Nagpur | Central | 20 | Testing | 2025-09-26 | 2025-10-25 | 2025-10-27 | 2025-11-06 |  | 12 | Marginal | Aarush Lall | 113066
ST02324 | PRJ029 | CL006 | ICICI Bank | Indore Site-017 | Indore | Central | 20 | Installation Scheduled | 2025-09-25 | 2025-11-24 | 2025-12-01 | 2025-12-16 |  | 3 | Met | Dakshesh Trivedi | 242909
ST02325 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-018 | Nagpur | Central | 50 | Live | 2025-09-07 | 2025-10-28 | 2025-10-29 | 2025-11-22 | 2025-12-02 | 1 | Met | Priya Rastogi | 276311
ST02326 | PRJ029 | CL006 | ICICI Bank | Indore Site-019 | Indore | Central | 50 | Live | 2025-09-20 | 2025-10-18 | 2025-10-14 | 2025-10-31 | 2025-10-31 | 0 | Met | Daksh Karnik | 258522
ST02327 | PRJ029 | CL006 | ICICI Bank | Indore Site-020 | Indore | Central | 100 | Live | 2025-09-09 | 2025-10-26 | 2025-11-02 | 2025-11-14 | 2025-11-16 | 7 | Met | Bhavika Sampath | 271963
ST02328 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-021 | Bhopal | Central | 50 | Live | 2025-09-15 | 2025-10-09 | 2025-10-08 | 2025-11-03 | 2025-11-05 | 0 | Met | Urvashi Ray | 135551
ST02329 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-022 | Bhopal | Central | 100 | Pending Acceptance | 2025-09-11 | 2025-11-01 | 2025-11-07 | 2025-11-23 | 2025-11-30 | 6 | Met | Vansha Thakkar | 152671
ST02330 | PRJ029 | CL006 | ICICI Bank | Indore Site-023 | Indore | Central | 20 | Installation Done | 2025-09-20 | 2025-10-28 | 2025-11-05 | 2025-11-12 |  | 12 | Marginal | Ekavir Bhargava | 258423
ST02331 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-024 | Nagpur | Central | 20 | Installation Scheduled | 2025-09-15 | 2025-10-12 | 2025-10-07 | 2025-10-31 |  | 6 | Met | Urvashi Ray | 46523
ST02332 | PRJ029 | CL006 | ICICI Bank | Indore Site-025 | Indore | Central | 200 | Testing | 2025-09-22 | 2025-11-07 | 2025-11-12 | 2025-11-29 |  | 12 | Marginal | Irya Sampath | 270115
ST02333 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-026 | Bhopal | Central | 100 | ROW In Progress | 2025-09-25 | 2025-10-18 |  | 2025-11-10 |  | 2 | Met | Tanay Rattan | 231374
ST02334 | PRJ029 | CL006 | ICICI Bank | Indore Site-027 | Indore | Central | 200 | ROW In Progress | 2025-09-11 | 2025-10-21 |  | 2025-10-31 |  | 7 | Met | Kabir Soman | 112476
ST02335 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-028 | Nagpur | Central | 50 | Live | 2025-09-08 | 2025-10-02 | 2025-10-01 | 2025-10-30 | 2025-10-30 | 0 | Met | Madhavi Lanka | 272718
ST02336 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-029 | Nagpur | Central | 50 | Installation Done | 2025-09-04 | 2025-10-05 | 2025-10-04 | 2025-10-21 |  | 12 | Marginal | Wahab Raval | 165971
ST02337 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-030 | Nagpur | Central | 200 | Pending Acceptance | 2025-09-26 | 2025-10-16 | 2025-10-20 | 2025-11-06 | 2025-11-18 | 4 | Met | Dipta Bhandari | 269911
ST02338 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-031 | Bhopal | Central | 10 | Installation Done | 2025-09-20 | 2025-10-28 | 2025-10-24 | 2025-11-21 |  | 12 | Marginal | Ekapad Walia | 105339
ST02339 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-032 | Nagpur | Central | 200 | Testing | 2025-09-08 | 2025-10-03 | 2025-10-07 | 2025-10-27 |  | 12 | Marginal | Aarush Lall | 247944
ST02340 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-033 | Bhopal | Central | 50 | ROW In Progress | 2025-09-24 | 2025-10-23 |  | 2025-11-03 |  | 4 | Met | Liam Koshy | 233158
ST02341 | PRJ029 | CL006 | ICICI Bank | Indore Site-034 | Indore | Central | 20 | Installation Done | 2025-09-28 | 2025-11-15 | 2025-11-10 | 2025-12-07 |  | 12 | Marginal | Niharika Sunder | 210187
ST02342 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-035 | Bhopal | Central | 10 | Live | 2025-09-29 | 2025-11-21 | 2025-11-29 | 2025-12-07 | 2025-12-04 | 8 | Marginal | Liam Koshy | 81259
ST02343 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-036 | Bhopal | Central | 50 | Survey Pending | 2025-09-05 | 2025-10-28 |  | 2025-11-16 |  | 8 | Marginal | Harini Choudhury | 146632
ST02344 | PRJ029 | CL006 | ICICI Bank | Indore Site-037 | Indore | Central | 100 | Live | 2025-09-21 | 2025-10-24 | 2025-10-25 | 2025-11-09 | 2025-11-19 | 1 | Met | Arya Shere | 51013
ST02345 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-038 | Nagpur | Central | 100 | ROW In Progress | 2025-09-26 | 2025-11-19 |  | 2025-12-18 |  | 6 | Met | Theodore Devi | 227796
ST02346 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-039 | Bhopal | Central | 50 | Installation Done | 2025-09-14 | 2025-11-13 | 2025-11-16 | 2025-12-12 |  | 12 | Marginal | Madhavi Lanka | 274823
ST02347 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-040 | Nagpur | Central | 200 | ROW In Progress | 2025-09-21 | 2025-11-03 |  | 2025-11-26 |  | 4 | Met | Simon Tata | 74812
ST02348 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-041 | Bhopal | Central | 50 | ROW In Progress | 2025-09-23 | 2025-11-05 |  | 2025-11-17 |  | 3 | Met | Simon Tata | 261234
ST02349 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-042 | Nagpur | Central | 100 | Pending Acceptance | 2025-09-04 | 2025-09-28 | 2025-09-26 | 2025-10-18 | 2025-10-24 | 0 | Met | Upadhriti Wadhwa | 169569
ST02350 | PRJ029 | CL006 | ICICI Bank | Indore Site-043 | Indore | Central | 50 | Live | 2025-09-20 | 2025-10-13 | 2025-10-09 | 2025-10-29 | 2025-10-27 | 0 | Met | Jai Kota | 212262
ST02351 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-044 | Bhopal | Central | 50 | Survey Pending | 2025-09-05 | 2025-10-12 |  | 2025-10-29 |  | 1 | Met | Girik Khalsa | 145915
ST02352 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-045 | Nagpur | Central | 10 | Installation Scheduled | 2025-09-25 | 2025-10-28 | 2025-11-02 | 2025-11-13 |  | 8 | Marginal | Ekavir Bhargava | 180017
ST02353 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-046 | Nagpur | Central | 10 | Installation Scheduled | 2025-09-13 | 2025-11-01 | 2025-11-06 | 2025-11-22 |  | 8 | Marginal | Farhan Chada | 56026
ST02354 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-047 | Nagpur | Central | 100 | Live | 2025-09-07 | 2025-10-22 | 2025-10-27 | 2025-11-13 | 2025-11-19 | 5 | Met | Upadhriti Wadhwa | 172679
ST02355 | PRJ029 | CL006 | ICICI Bank | Indore Site-048 | Indore | Central | 100 | Testing | 2025-09-05 | 2025-09-30 | 2025-09-26 | 2025-10-14 |  | 12 | Marginal | Devansh Rajan | 151115
ST02356 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-049 | Nagpur | Central | 100 | Installation Done | 2025-09-21 | 2025-10-24 | 2025-11-03 | 2025-11-06 |  | 12 | Marginal | Gavin Batta | 72971
ST02357 | PRJ029 | CL006 | ICICI Bank | Indore Site-050 | Indore | Central | 10 | Installation Done | 2025-09-16 | 2025-11-02 | 2025-11-10 | 2025-11-15 |  | 12 | Marginal | Vansha Thakkar | 261688
ST02358 | PRJ029 | CL006 | ICICI Bank | Indore Site-051 | Indore | Central | 20 | Installation Done | 2025-09-22 | 2025-11-14 | 2025-11-15 | 2025-11-30 |  | 12 | Marginal | Niharika Sunder | 62215
ST02359 | PRJ029 | CL006 | ICICI Bank | Indore Site-052 | Indore | Central | 50 | Live | 2025-09-27 | 2025-11-06 | 2025-11-01 | 2025-11-26 | 2025-11-29 | 0 | Met | Wriddhish Bhardwaj | 111999
ST02360 | PRJ029 | CL006 | ICICI Bank | Indore Site-053 | Indore | Central | 100 | Live | 2025-09-06 | 2025-11-02 | 2025-11-08 | 2025-11-25 | 2025-12-02 | 6 | Met | Yashica Cherian | 187981
ST02361 | PRJ029 | CL006 | ICICI Bank | Indore Site-054 | Indore | Central | 100 | Installation Scheduled | 2025-09-11 | 2025-10-16 | 2025-10-16 | 2025-11-04 |  | 2 | Met | Girik Khalsa | 217872
ST02362 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-055 | Bhopal | Central | 10 | ROW In Progress | 2025-09-28 | 2025-11-17 |  | 2025-12-07 |  | 8 | Marginal | Liam Koshy | 223603
ST02363 | PRJ029 | CL006 | ICICI Bank | Indore Site-056 | Indore | Central | 100 | Testing | 2025-09-12 | 2025-10-29 | 2025-11-06 | 2025-11-25 |  | 12 | Marginal | Ekapad Walia | 46127
ST02364 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-057 | Bhopal | Central | 20 | Survey Pending | 2025-09-29 | 2025-11-20 |  | 2025-12-10 |  | 3 | Met | Dipta Bhandari | 91863
ST02365 | PRJ029 | CL006 | ICICI Bank | Indore Site-058 | Indore | Central | 10 | Live | 2025-09-17 | 2025-11-13 | 2025-11-15 | 2025-12-01 | 2025-12-08 | 2 | Met | Logan Sami | 257600
ST02366 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-059 | Nagpur | Central | 50 | Live | 2025-09-09 | 2025-10-19 | 2025-10-18 | 2025-11-14 | 2025-11-22 | 0 | Met | Nitesh Raghavan | 72917
ST02367 | PRJ029 | CL006 | ICICI Bank | Bhopal Site-060 | Bhopal | Central | 200 | Survey Pending | 2025-09-21 | 2025-11-09 |  | 2025-11-25 |  | 0 | Met | Vansha Thakkar | 77784
ST02368 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-061 | Nagpur | Central | 100 | Live | 2025-09-24 | 2025-11-12 | 2025-11-14 | 2025-12-09 | 2025-12-11 | 2 | Met | Vansha Thakkar | 167982
ST02369 | PRJ029 | CL006 | ICICI Bank | Indore Site-062 | Indore | Central | 20 | Pending Acceptance | 2025-09-28 | 2025-10-25 | 2025-10-23 | 2025-11-20 | 2025-11-26 | 0 | Met | Urvashi Ray | 78625
ST02370 | PRJ029 | CL006 | ICICI Bank | Nagpur Site-063 | Nagpur | Central | 200 | Live | 2025-09-24 | 2025-11-15 | 2025-11-22 | 2025-12-01 | 2025-11-28 | 7 | Met | Tara Dhar | 47259
ST02371 | PRJ030 | CL007 | Tata Motors | Nagpur Site-001 | Nagpur | Central | 20 | Installation Scheduled | 2026-02-23 | 2026-03-27 | 2026-03-29 | 2026-04-16 |  | 6 | Met | Arya Shere | 201833
ST02372 | PRJ030 | CL007 | Tata Motors | Nagpur Site-002 | Nagpur | Central | 10 | Live | 2026-02-28 | 2026-03-20 | 2026-03-17 | 2026-03-31 | 2026-03-29 | 0 | Met | Simon Tata | 182972
ST02373 | PRJ030 | CL007 | Tata Motors | Nagpur Site-003 | Nagpur | Central | 10 | Testing | 2026-02-24 | 2026-04-20 | 2026-04-29 | 2026-05-16 |  | 12 | Marginal | Ekbal Garg | 257216
ST02374 | PRJ030 | CL007 | Tata Motors | Indore Site-004 | Indore | Central | 50 | Live | 2026-03-11 | 2026-04-02 | 2026-04-02 | 2026-04-28 | 2026-05-02 | 0 | Met | Ekavir Bhargava | 61900
ST02375 | PRJ030 | CL007 | Tata Motors | Indore Site-005 | Indore | Central | 20 | Testing | 2026-03-13 | 2026-04-13 | 2026-04-09 | 2026-05-12 |  | 12 | Marginal | Simon Tata | 113815
ST02376 | PRJ030 | CL007 | Tata Motors | Nagpur Site-006 | Nagpur | Central | 100 | Installation Scheduled | 2026-03-08 | 2026-04-23 | 2026-05-01 | 2026-05-05 |  | 3 | Met | Chandresh Zachariah | 89667
ST02377 | PRJ030 | CL007 | Tata Motors | Nagpur Site-007 | Nagpur | Central | 100 | Pending Acceptance | 2026-02-22 | 2026-04-15 | 2026-04-12 | 2026-04-29 | 2026-04-30 | 0 | Met | Liam Koshy | 136433
ST02378 | PRJ030 | CL007 | Tata Motors | Nagpur Site-008 | Nagpur | Central | 20 | Installation Scheduled | 2026-03-08 | 2026-04-13 | 2026-04-22 | 2026-04-23 |  | 5 | Met | Priya Rastogi | 262109
ST02379 | PRJ030 | CL007 | Tata Motors | Bhopal Site-009 | Bhopal | Central | 10 | Survey Pending | 2026-03-05 | 2026-04-29 |  | 2026-05-15 |  | 3 | Met | Madhavi Lanka | 175336
ST02380 | PRJ030 | CL007 | Tata Motors | Bhopal Site-010 | Bhopal | Central | 10 | Testing | 2026-03-13 | 2026-05-04 | 2026-05-08 | 2026-05-18 |  | 12 | Marginal | Advay Contractor | 240820
ST02381 | PRJ030 | CL007 | Tata Motors | Indore Site-011 | Indore | Central | 100 | ROW In Progress | 2026-03-07 | 2026-05-04 |  | 2026-05-21 |  | 7 | Met | Ikbal Kothari | 214774
ST02382 | PRJ030 | CL007 | Tata Motors | Bhopal Site-012 | Bhopal | Central | 10 | Live | 2026-02-25 | 2026-04-11 | 2026-04-21 | 2026-05-04 | 2026-05-16 | 10 | Marginal | Wahab Raval | 170492
ST02383 | PRJ030 | CL007 | Tata Motors | Indore Site-013 | Indore | Central | 100 | Live | 2026-02-26 | 2026-04-20 | 2026-04-21 | 2026-05-13 | 2026-05-17 | 1 | Met | Ikbal Kothari | 51442
ST02384 | PRJ030 | CL007 | Tata Motors | Bhopal Site-014 | Bhopal | Central | 20 | Live | 2026-03-06 | 2026-05-05 | 2026-05-05 | 2026-05-29 | 2026-06-07 | 0 | Met | Yashica Issac | 93254
ST02385 | PRJ030 | CL007 | Tata Motors | Indore Site-015 | Indore | Central | 20 | Installation Done | 2026-03-08 | 2026-04-29 | 2026-04-24 | 2026-05-27 |  | 12 | Marginal | Mohammed Gupta | 213710
ST02386 | PRJ030 | CL007 | Tata Motors | Indore Site-016 | Indore | Central | 200 | ROW In Progress | 2026-03-06 | 2026-04-15 |  | 2026-04-30 |  | 2 | Met | Ekbal Garg | 166582
ST02387 | PRJ030 | CL007 | Tata Motors | Indore Site-017 | Indore | Central | 50 | Testing | 2026-03-01 | 2026-04-10 | 2026-04-08 | 2026-04-24 |  | 12 | Marginal | Unni Bhagat | 208181
ST02388 | PRJ030 | CL007 | Tata Motors | Indore Site-018 | Indore | Central | 100 | Installation Done | 2026-02-26 | 2026-04-14 | 2026-04-19 | 2026-05-13 |  | 12 | Marginal | Arya Shere | 122695
ST02389 | PRJ030 | CL007 | Tata Motors | Bhopal Site-019 | Bhopal | Central | 10 | Testing | 2026-02-28 | 2026-04-24 | 2026-04-30 | 2026-05-21 |  | 12 | Marginal | Urvashi Ray | 52687
ST02390 | PRJ030 | CL007 | Tata Motors | Bhopal Site-020 | Bhopal | Central | 50 | Pending Acceptance | 2026-03-03 | 2026-03-30 | 2026-04-08 | 2026-04-12 | 2026-04-21 | 9 | Marginal | Dakshesh Trivedi | 189555
ST02391 | PRJ030 | CL007 | Tata Motors | Nagpur Site-021 | Nagpur | Central | 100 | ROW In Progress | 2026-02-24 | 2026-03-24 |  | 2026-04-21 |  | 5 | Met | Darsh Rau | 255090
ST02392 | PRJ030 | CL007 | Tata Motors | Bhopal Site-022 | Bhopal | Central | 200 | Testing | 2026-03-08 | 2026-04-02 | 2026-03-31 | 2026-04-21 |  | 12 | Marginal | Nitesh Raghavan | 55322
ST02393 | PRJ030 | CL007 | Tata Motors | Bhopal Site-023 | Bhopal | Central | 50 | Live | 2026-03-05 | 2026-03-27 | 2026-03-22 | 2026-04-25 | 2026-04-27 | 0 | Met | Victor Kannan | 200809
ST02394 | PRJ030 | CL007 | Tata Motors | Nagpur Site-024 | Nagpur | Central | 10 | Live | 2026-03-10 | 2026-04-27 | 2026-05-07 | 2026-05-18 | 2026-05-29 | 10 | Marginal | Siddharth Zacharia | 213443
ST02395 | PRJ030 | CL007 | Tata Motors | Bhopal Site-025 | Bhopal | Central | 20 | Live | 2026-03-12 | 2026-04-13 | 2026-04-08 | 2026-04-26 | 2026-04-26 | 0 | Met | Unni Bhagat | 211099
ST02396 | PRJ030 | CL007 | Tata Motors | Bhopal Site-026 | Bhopal | Central | 100 | Survey Pending | 2026-03-10 | 2026-04-24 |  | 2026-05-24 |  | 0 | Met | Ekavir Bhargava | 89804
ST02397 | PRJ030 | CL007 | Tata Motors | Nagpur Site-027 | Nagpur | Central | 20 | Live | 2026-02-22 | 2026-04-08 | 2026-04-14 | 2026-04-22 | 2026-04-24 | 6 | Met | Siddharth Zacharia | 268079
ST02398 | PRJ030 | CL007 | Tata Motors | Bhopal Site-028 | Bhopal | Central | 20 | Installation Done | 2026-02-28 | 2026-03-27 | 2026-03-22 | 2026-04-18 |  | 12 | Marginal | Dominic Kakar | 48575
ST02399 | PRJ030 | CL007 | Tata Motors | Indore Site-029 | Indore | Central | 100 | Live | 2026-02-22 | 2026-03-22 | 2026-03-25 | 2026-04-06 | 2026-04-15 | 3 | Met | Radhika Dugar | 113042
ST02400 | PRJ030 | CL007 | Tata Motors | Nagpur Site-030 | Nagpur | Central | 10 | Live | 2026-03-08 | 2026-04-20 | 2026-04-22 | 2026-05-15 | 2026-05-21 | 2 | Met | Girindra Chatterjee | 174713
ST02401 | PRJ030 | CL007 | Tata Motors | Nagpur Site-031 | Nagpur | Central | 200 | ROW In Progress | 2026-03-14 | 2026-04-20 |  | 2026-05-09 |  | 6 | Met | Logan Sami | 151956
ST02402 | PRJ030 | CL007 | Tata Motors | Nagpur Site-032 | Nagpur | Central | 20 | Live | 2026-03-09 | 2026-04-14 | 2026-04-10 | 2026-05-06 | 2026-05-18 | 0 | Met | Ranveer Yadav | 214329
ST02403 | PRJ030 | CL007 | Tata Motors | Indore Site-033 | Indore | Central | 50 | Installation Scheduled | 2026-03-05 | 2026-04-08 | 2026-04-11 | 2026-04-28 |  | 1 | Met | Arya Shere | 216787
ST02404 | PRJ030 | CL007 | Tata Motors | Indore Site-034 | Indore | Central | 50 | Live | 2026-03-11 | 2026-04-26 | 2026-05-02 | 2026-05-22 | 2026-05-25 | 6 | Met | Yatin Baral | 96982
ST02405 | PRJ030 | CL007 | Tata Motors | Indore Site-035 | Indore | Central | 20 | Testing | 2026-03-01 | 2026-04-12 | 2026-04-20 | 2026-05-12 |  | 12 | Marginal | Tanay Rattan | 263136
ST02406 | PRJ030 | CL007 | Tata Motors | Indore Site-036 | Indore | Central | 10 | Installation Scheduled | 2026-03-06 | 2026-04-14 | 2026-04-19 | 2026-05-01 |  | 2 | Met | Teerth Bhardwaj | 168931
ST02407 | PRJ030 | CL007 | Tata Motors | Indore Site-037 | Indore | Central | 20 | Installation Done | 2026-02-22 | 2026-04-15 | 2026-04-19 | 2026-05-02 |  | 12 | Marginal | Niharika Sunder | 247231
ST02408 | PRJ030 | CL007 | Tata Motors | Nagpur Site-038 | Nagpur | Central | 100 | Testing | 2026-03-15 | 2026-04-20 | 2026-04-24 | 2026-05-07 |  | 12 | Marginal | Unni Bhagat | 272153
ST02409 | PRJ030 | CL007 | Tata Motors | Nagpur Site-039 | Nagpur | Central | 50 | Survey Pending | 2026-02-22 | 2026-04-02 |  | 2026-04-22 |  | 0 | Met | Diya Rattan | 201206
ST02410 | PRJ030 | CL007 | Tata Motors | Bhopal Site-040 | Bhopal | Central | 10 | Testing | 2026-03-06 | 2026-04-24 | 2026-04-24 | 2026-05-04 |  | 12 | Marginal | Teerth Bhardwaj | 96661
ST02411 | PRJ030 | CL007 | Tata Motors | Indore Site-041 | Indore | Central | 100 | ROW In Progress | 2026-03-18 | 2026-05-15 |  | 2026-05-31 |  | 0 | Met | Mohammed Gupta | 104579
ST02412 | PRJ030 | CL007 | Tata Motors | Nagpur Site-042 | Nagpur | Central | 50 | Installation Done | 2026-02-26 | 2026-04-24 | 2026-04-29 | 2026-05-12 |  | 12 | Marginal | Ekbal Garg | 108357
ST02413 | PRJ030 | CL007 | Tata Motors | Nagpur Site-043 | Nagpur | Central | 10 | Pending Acceptance | 2026-02-24 | 2026-04-11 | 2026-04-10 | 2026-05-01 | 2026-05-09 | 0 | Met | Ikbal Kothari | 55079
ST02414 | PRJ030 | CL007 | Tata Motors | Nagpur Site-044 | Nagpur | Central | 50 | ROW In Progress | 2026-03-16 | 2026-05-15 |  | 2026-05-25 |  | 4 | Met | Anamika Kanda | 217473
ST02415 | PRJ030 | CL007 | Tata Motors | Bhopal Site-045 | Bhopal | Central | 10 | Pending Acceptance | 2026-02-25 | 2026-04-05 | 2026-04-06 | 2026-04-25 | 2026-04-29 | 1 | Met | Radhika Dugar | 166633
ST02416 | PRJ030 | CL007 | Tata Motors | Nagpur Site-046 | Nagpur | Central | 20 | Installation Scheduled | 2026-03-15 | 2026-04-18 | 2026-04-20 | 2026-05-13 |  | 5 | Met | Theodore Devi | 254056
ST02417 | PRJ030 | CL007 | Tata Motors | Nagpur Site-047 | Nagpur | Central | 200 | Live | 2026-02-25 | 2026-03-24 | 2026-03-23 | 2026-04-10 | 2026-04-18 | 0 | Met | Daksh Karnik | 117029
ST02418 | PRJ030 | CL007 | Tata Motors | Bhopal Site-048 | Bhopal | Central | 200 | Installation Done | 2026-02-27 | 2026-04-17 | 2026-04-20 | 2026-05-01 |  | 12 | Marginal | Madhavi Lanka | 265330
ST02419 | PRJ030 | CL007 | Tata Motors | Nagpur Site-049 | Nagpur | Central | 200 | Installation Done | 2026-02-27 | 2026-04-10 | 2026-04-08 | 2026-04-21 |  | 12 | Marginal | Ranveer Yadav | 174999
ST02420 | PRJ030 | CL007 | Tata Motors | Bhopal Site-050 | Bhopal | Central | 50 | Installation Done | 2026-03-11 | 2026-04-22 | 2026-04-28 | 2026-05-11 |  | 12 | Marginal | Theodore Devi | 113037
ST02421 | PRJ030 | CL007 | Tata Motors | Nagpur Site-051 | Nagpur | Central | 50 | Live | 2026-02-23 | 2026-04-22 | 2026-04-19 | 2026-05-20 | 2026-05-24 | 0 | Met | Michael Dutta | 65550
ST02422 | PRJ030 | CL007 | Tata Motors | Indore Site-052 | Indore | Central | 100 | Live | 2026-03-03 | 2026-04-14 | 2026-04-20 | 2026-05-04 | 2026-05-08 | 6 | Met | Diya Rattan | 245505
ST02423 | PRJ030 | CL007 | Tata Motors | Indore Site-053 | Indore | Central | 100 | ROW In Progress | 2026-02-27 | 2026-04-22 |  | 2026-05-05 |  | 6 | Met | Farhan Chada | 109867
ST02424 | PRJ030 | CL007 | Tata Motors | Indore Site-054 | Indore | Central | 50 | Installation Scheduled | 2026-02-25 | 2026-03-25 | 2026-03-22 | 2026-04-14 |  | 7 | Met | Nitesh Raghavan | 233518
ST02425 | PRJ030 | CL007 | Tata Motors | Nagpur Site-055 | Nagpur | Central | 20 | Live | 2026-03-17 | 2026-04-16 | 2026-04-24 | 2026-05-04 | 2026-05-04 | 8 | Marginal | Nitesh Raghavan | 52535
ST02426 | PRJ030 | CL007 | Tata Motors | Nagpur Site-056 | Nagpur | Central | 10 | Installation Scheduled | 2026-02-25 | 2026-04-18 | 2026-04-27 | 2026-05-10 |  | 2 | Met | Tara Dhar | 156121
ST02427 | PRJ030 | CL007 | Tata Motors | Nagpur Site-057 | Nagpur | Central | 200 | Installation Scheduled | 2026-03-13 | 2026-04-29 | 2026-05-01 | 2026-05-09 |  | 3 | Met | Unni Bhagat | 64334
ST02428 | PRJ030 | CL007 | Tata Motors | Indore Site-058 | Indore | Central | 200 | Live | 2026-02-23 | 2026-04-03 | 2026-04-08 | 2026-04-14 | 2026-04-21 | 5 | Met | Aarush Lall | 260191
ST02429 | PRJ030 | CL007 | Tata Motors | Bhopal Site-059 | Bhopal | Central | 20 | Pending Acceptance | 2026-03-16 | 2026-05-01 | 2026-05-10 | 2026-05-18 | 2026-05-18 | 9 | Marginal | Kabir Soman | 118504
ST02430 | PRJ030 | CL007 | Tata Motors | Bhopal Site-060 | Bhopal | Central | 10 | Live | 2026-03-10 | 2026-05-04 | 2026-04-30 | 2026-05-23 | 2026-05-31 | 0 | Met | Ekavir Varkey | 215449
ST02431 | PRJ030 | CL007 | Tata Motors | Bhopal Site-061 | Bhopal | Central | 50 | Survey Pending | 2026-03-05 | 2026-05-02 |  | 2026-05-19 |  | 6 | Met | Ranveer Yadav | 57110
ST02432 | PRJ030 | CL007 | Tata Motors | Nagpur Site-062 | Nagpur | Central | 50 | ROW In Progress | 2026-02-27 | 2026-04-03 |  | 2026-04-16 |  | 3 | Met | Harini Choudhury | 168569
ST02433 | PRJ030 | CL007 | Tata Motors | Indore Site-063 | Indore | Central | 10 | Live | 2026-03-08 | 2026-04-21 | 2026-04-30 | 2026-05-06 | 2026-05-05 | 9 | Marginal | Irya Sampath | 121756
ST02434 | PRJ030 | CL007 | Tata Motors | Nagpur Site-064 | Nagpur | Central | 10 | Survey Pending | 2026-03-03 | 2026-05-02 |  | 2026-05-20 |  | 3 | Met | Farhan Chada | 214580
ST02435 | PRJ030 | CL007 | Tata Motors | Indore Site-065 | Indore | Central | 20 | Installation Scheduled | 2026-03-13 | 2026-04-25 | 2026-04-27 | 2026-05-07 |  | 0 | Met | Dakshesh Trivedi | 171784
ST02436 | PRJ030 | CL007 | Tata Motors | Bhopal Site-066 | Bhopal | Central | 200 | Live | 2026-02-25 | 2026-04-06 | 2026-04-01 | 2026-04-29 | 2026-04-30 | 0 | Met | Upadhriti Wadhwa | 221461
ST02437 | PRJ030 | CL007 | Tata Motors | Indore Site-067 | Indore | Central | 20 | Testing | 2026-03-06 | 2026-04-16 | 2026-04-13 | 2026-05-10 |  | 12 | Marginal | Yashica Issac | 178492
ST02438 | PRJ030 | CL007 | Tata Motors | Bhopal Site-068 | Bhopal | Central | 20 | Live | 2026-02-26 | 2026-04-26 | 2026-04-23 | 2026-05-07 | 2026-05-19 | 0 | Met | Yashica Cherian | 86086
ST02439 | PRJ030 | CL007 | Tata Motors | Bhopal Site-069 | Bhopal | Central | 100 | Testing | 2026-03-01 | 2026-04-15 | 2026-04-12 | 2026-05-05 |  | 12 | Marginal | Kabir Soman | 223099
ST02440 | PRJ030 | CL007 | Tata Motors | Indore Site-070 | Indore | Central | 20 | Installation Done | 2026-03-09 | 2026-04-05 | 2026-03-31 | 2026-04-26 |  | 12 | Marginal | Mohammed Gupta | 172749
ST02441 | PRJ030 | CL007 | Tata Motors | Bhopal Site-071 | Bhopal | Central | 20 | Installation Done | 2026-03-03 | 2026-04-14 | 2026-04-11 | 2026-05-05 |  | 12 | Marginal | Tara Dhar | 111662
ST02442 | PRJ030 | CL007 | Tata Motors | Indore Site-072 | Indore | Central | 200 | Installation Scheduled | 2026-02-22 | 2026-03-25 | 2026-03-20 | 2026-04-08 |  | 6 | Met | Raksha Varughese | 191921
ST02443 | PRJ030 | CL007 | Tata Motors | Indore Site-073 | Indore | Central | 50 | Testing | 2026-02-23 | 2026-03-28 | 2026-04-01 | 2026-04-27 |  | 12 | Marginal | Tara Dhar | 89590
ST02444 | PRJ030 | CL007 | Tata Motors | Nagpur Site-074 | Nagpur | Central | 10 | Installation Scheduled | 2026-03-06 | 2026-04-23 | 2026-04-30 | 2026-05-04 |  | 3 | Met | Victor Kannan | 47230
ST02445 | PRJ030 | CL007 | Tata Motors | Nagpur Site-075 | Nagpur | Central | 50 | Live | 2026-03-19 | 2026-04-21 | 2026-04-24 | 2026-05-14 | 2026-05-25 | 3 | Met | Arya Sunder | 208953
ST02446 | PRJ030 | CL007 | Tata Motors | Bhopal Site-076 | Bhopal | Central | 200 | Testing | 2026-03-17 | 2026-04-15 | 2026-04-17 | 2026-05-08 |  | 12 | Marginal | Yatin Baral | 70233
ST02447 | PRJ030 | CL007 | Tata Motors | Bhopal Site-077 | Bhopal | Central | 20 | Survey Pending | 2026-03-01 | 2026-04-25 |  | 2026-05-09 |  | 7 | Met | Priya Rastogi | 57705
ST02448 | PRJ030 | CL007 | Tata Motors | Indore Site-078 | Indore | Central | 10 | ROW In Progress | 2026-03-01 | 2026-04-07 |  | 2026-04-29 |  | 0 | Met | Kevin Solanki | 86859
ST02449 | PRJ030 | CL007 | Tata Motors | Bhopal Site-079 | Bhopal | Central | 50 | Survey Pending | 2026-03-01 | 2026-04-24 |  | 2026-05-21 |  | 2 | Met | Devika Rastogi | 90563
ST02450 | PRJ030 | CL007 | Tata Motors | Bhopal Site-080 | Bhopal | Central | 100 | Live | 2026-03-17 | 2026-04-18 | 2026-04-15 | 2026-05-10 | 2026-05-10 | 0 | Met | Alka Wable | 153877
ST02451 | PRJ030 | CL007 | Tata Motors | Bhopal Site-081 | Bhopal | Central | 200 | Installation Scheduled | 2026-03-12 | 2026-04-06 | 2026-04-16 | 2026-04-23 |  | 6 | Met | Nihal Shere | 167121
ST02452 | PRJ030 | CL007 | Tata Motors | Nagpur Site-082 | Nagpur | Central | 100 | Installation Done | 2026-03-16 | 2026-04-24 | 2026-05-04 | 2026-05-17 |  | 12 | Marginal | Isaac Patil | 57103
ST02453 | PRJ030 | CL007 | Tata Motors | Bhopal Site-083 | Bhopal | Central | 10 | Survey Pending | 2026-02-26 | 2026-03-23 |  | 2026-04-10 |  | 1 | Met | Vansha Thakkar | 47316
ST02454 | PRJ030 | CL007 | Tata Motors | Indore Site-084 | Indore | Central | 10 | ROW In Progress | 2026-03-01 | 2026-04-07 |  | 2026-05-04 |  | 5 | Met | Girindra Chatterjee | 72315
ST02455 | PRJ030 | CL007 | Tata Motors | Bhopal Site-085 | Bhopal | Central | 200 | Installation Scheduled | 2026-02-22 | 2026-04-16 | 2026-04-22 | 2026-04-28 |  | 1 | Met | Theodore Devi | 208110
ST02456 | PRJ030 | CL007 | Tata Motors | Indore Site-086 | Indore | Central | 200 | Live | 2026-03-03 | 2026-04-15 | 2026-04-18 | 2026-05-06 | 2026-05-16 | 3 | Met | Vansha Thakkar | 82163
ST02457 | PRJ030 | CL007 | Tata Motors | Nagpur Site-087 | Nagpur | Central | 20 | Installation Done | 2026-03-04 | 2026-04-17 | 2026-04-15 | 2026-05-16 |  | 12 | Marginal | Teerth Bhardwaj | 157141
ST02458 | PRJ030 | CL007 | Tata Motors | Indore Site-088 | Indore | Central | 200 | Survey Pending | 2026-03-08 | 2026-04-25 |  | 2026-05-08 |  | 8 | Marginal | Tanay Rattan | 241629
ST02459 | PRJ030 | CL007 | Tata Motors | Bhopal Site-089 | Bhopal | Central | 20 | Live | 2026-03-01 | 2026-04-27 | 2026-05-03 | 2026-05-19 | 2026-05-19 | 6 | Met | Girik Khalsa | 245517
ST02460 | PRJ030 | CL007 | Tata Motors | Indore Site-090 | Indore | Central | 50 | Pending Acceptance | 2026-03-08 | 2026-05-01 | 2026-05-03 | 2026-05-11 | 2026-05-19 | 2 | Met | Wahab Raval | 99387
ST02461 | PRJ030 | CL007 | Tata Motors | Indore Site-091 | Indore | Central | 10 | ROW In Progress | 2026-03-11 | 2026-05-03 |  | 2026-05-28 |  | 4 | Met | Kashvi Edwin | 236217
ST02462 | PRJ030 | CL007 | Tata Motors | Bhopal Site-092 | Bhopal | Central | 50 | Installation Scheduled | 2026-03-14 | 2026-04-21 | 2026-04-28 | 2026-05-03 |  | 4 | Met | Chandresh Zachariah | 277193
ST02463 | PRJ030 | CL007 | Tata Motors | Indore Site-093 | Indore | Central | 50 | ROW In Progress | 2026-03-07 | 2026-04-09 |  | 2026-04-25 |  | 0 | Met | Upadhriti Wadhwa | 63774
ST02464 | PRJ030 | CL007 | Tata Motors | Indore Site-094 | Indore | Central | 10 | Installation Done | 2026-02-25 | 2026-04-05 | 2026-04-05 | 2026-05-05 |  | 12 | Marginal | Logan Sami | 93645
ST02465 | PRJ030 | CL007 | Tata Motors | Indore Site-095 | Indore | Central | 100 | Installation Done | 2026-02-25 | 2026-04-24 | 2026-05-01 | 2026-05-21 |  | 12 | Marginal | Ekapad Walia | 277567
ST02466 | PRJ030 | CL007 | Tata Motors | Indore Site-096 | Indore | Central | 200 | Installation Scheduled | 2026-02-22 | 2026-03-30 | 2026-04-06 | 2026-04-19 |  | 6 | Met | Faqid Savant | 200492
ST02467 | PRJ030 | CL007 | Tata Motors | Nagpur Site-097 | Nagpur | Central | 10 | Live | 2026-02-22 | 2026-03-27 | 2026-04-03 | 2026-04-23 | 2026-04-27 | 7 | Met | Daksh Karnik | 117955
ST02468 | PRJ030 | CL007 | Tata Motors | Nagpur Site-098 | Nagpur | Central | 10 | Installation Scheduled | 2026-03-15 | 2026-05-12 | 2026-05-14 | 2026-06-03 |  | 3 | Met | Darsh Rau | 196166
ST02469 | PRJ030 | CL007 | Tata Motors | Bhopal Site-099 | Bhopal | Central | 100 | Live | 2026-02-26 | 2026-04-25 | 2026-04-23 | 2026-05-25 | 2026-05-27 | 0 | Met | Tara Dhar | 145480
ST02470 | PRJ030 | CL007 | Tata Motors | Indore Site-100 | Indore | Central | 10 | Testing | 2026-03-02 | 2026-03-26 | 2026-03-22 | 2026-04-13 |  | 12 | Marginal | Arya Shere | 239727
ST02471 | PRJ030 | CL007 | Tata Motors | Nagpur Site-101 | Nagpur | Central | 20 | ROW In Progress | 2026-02-25 | 2026-03-22 |  | 2026-04-18 |  | 7 | Met | Harini Choudhury | 179627
ST02472 | PRJ030 | CL007 | Tata Motors | Bhopal Site-102 | Bhopal | Central | 200 | Installation Scheduled | 2026-02-25 | 2026-04-19 | 2026-04-20 | 2026-04-29 |  | 1 | Met | Upadhriti Wadhwa | 162007
ST02473 | PRJ030 | CL007 | Tata Motors | Nagpur Site-103 | Nagpur | Central | 100 | Testing | 2026-03-06 | 2026-03-29 | 2026-04-08 | 2026-04-18 |  | 12 | Marginal | Jai Kota | 263269
ST02474 | PRJ030 | CL007 | Tata Motors | Nagpur Site-104 | Nagpur | Central | 200 | Installation Done | 2026-03-03 | 2026-04-29 | 2026-05-08 | 2026-05-28 |  | 12 | Marginal | Tara Dhar | 127765
ST02475 | PRJ030 | CL007 | Tata Motors | Bhopal Site-105 | Bhopal | Central | 50 | Pending Acceptance | 2026-02-26 | 2026-03-24 | 2026-04-03 | 2026-04-06 | 2026-04-06 | 10 | Marginal | Niharika Sunder | 252232
ST02476 | PRJ030 | CL007 | Tata Motors | Indore Site-106 | Indore | Central | 10 | Pending Acceptance | 2026-03-05 | 2026-04-27 | 2026-04-25 | 2026-05-24 | 2026-05-24 | 0 | Met | Madhavi Lanka | 65177
ST02477 | PRJ030 | CL007 | Tata Motors | Indore Site-107 | Indore | Central | 100 | Installation Scheduled | 2026-03-19 | 2026-04-28 | 2026-05-06 | 2026-05-15 |  | 1 | Met | Farhan Chada | 262341
ST02478 | PRJ030 | CL007 | Tata Motors | Bhopal Site-108 | Bhopal | Central | 20 | ROW In Progress | 2026-03-08 | 2026-04-20 |  | 2026-05-11 |  | 7 | Met | Tanay Rattan | 72094
ST02479 | PRJ030 | CL007 | Tata Motors | Indore Site-109 | Indore | Central | 200 | Testing | 2026-03-13 | 2026-04-28 | 2026-04-29 | 2026-05-23 |  | 12 | Marginal | Yatin Baral | 63620
ST02480 | PRJ030 | CL007 | Tata Motors | Bhopal Site-110 | Bhopal | Central | 200 | Testing | 2026-02-28 | 2026-04-22 | 2026-04-18 | 2026-05-14 |  | 12 | Marginal | Kashvi Edwin | 227897
ST02481 | PRJ030 | CL007 | Tata Motors | Bhopal Site-111 | Bhopal | Central | 100 | ROW In Progress | 2026-02-28 | 2026-03-20 |  | 2026-04-14 |  | 1 | Met | Wahab Raval | 136241
ST02482 | PRJ030 | CL007 | Tata Motors | Bhopal Site-112 | Bhopal | Central | 20 | Live | 2026-03-16 | 2026-04-15 | 2026-04-13 | 2026-05-07 | 2026-05-11 | 0 | Met | Tanay Rattan | 76597
ST02483 | PRJ030 | CL007 | Tata Motors | Bhopal Site-113 | Bhopal | Central | 200 | Survey Pending | 2026-03-13 | 2026-05-05 |  | 2026-05-25 |  | 4 | Met | Diya Rattan | 242738
ST02484 | PRJ030 | CL007 | Tata Motors | Bhopal Site-114 | Bhopal | Central | 200 | Installation Scheduled | 2026-03-13 | 2026-04-05 | 2026-04-07 | 2026-04-30 |  | 2 | Met | Ikbal Kothari | 241538
ST02485 | PRJ030 | CL007 | Tata Motors | Indore Site-115 | Indore | Central | 100 | Installation Done | 2026-03-18 | 2026-04-28 | 2026-04-30 | 2026-05-18 |  | 12 | Marginal | Devika Rastogi | 223279
ST02486 | PRJ030 | CL007 | Tata Motors | Nagpur Site-116 | Nagpur | Central | 20 | Pending Acceptance | 2026-03-11 | 2026-04-07 | 2026-04-06 | 2026-05-02 | 2026-05-07 | 0 | Met | Yashica Cherian | 83141
ST02487 | PRJ031 | CL007 | Tata Motors | Bhopal Site-001 | Bhopal | Central | 10 | Live | 2025-12-25 | 2026-02-05 | 2026-02-07 | 2026-02-22 | 2026-03-03 | 2 | Met | Jai Kota | 69344
ST02488 | PRJ031 | CL007 | Tata Motors | Bhopal Site-002 | Bhopal | Central | 20 | Testing | 2025-12-24 | 2026-01-25 | 2026-01-20 | 2026-02-23 |  | 12 | Marginal | Kevin Solanki | 78244
ST02489 | PRJ031 | CL007 | Tata Motors | Indore Site-003 | Indore | Central | 20 | Live | 2025-12-11 | 2026-01-18 | 2026-01-13 | 2026-02-09 | 2026-02-19 | 0 | Met | Wriddhish Bhardwaj | 115820
ST02490 | PRJ031 | CL007 | Tata Motors | Indore Site-004 | Indore | Central | 200 | ROW In Progress | 2026-01-01 | 2026-02-09 |  | 2026-03-07 |  | 8 | Marginal | Siddharth Zacharia | 107424
ST02491 | PRJ031 | CL007 | Tata Motors | Indore Site-005 | Indore | Central | 10 | Installation Scheduled | 2025-12-18 | 2026-01-13 | 2026-01-20 | 2026-02-05 |  | 4 | Met | Yatin Baral | 158942
ST02492 | PRJ031 | CL007 | Tata Motors | Indore Site-006 | Indore | Central | 100 | Live | 2025-12-12 | 2026-01-19 | 2026-01-21 | 2026-02-15 | 2026-02-17 | 2 | Met | Radhika Dugar | 190354
ST02493 | PRJ031 | CL007 | Tata Motors | Indore Site-007 | Indore | Central | 200 | Installation Scheduled | 2025-12-21 | 2026-01-27 | 2026-01-28 | 2026-02-16 |  | 0 | Met | Darsh Rau | 87752
ST02494 | PRJ031 | CL007 | Tata Motors | Nagpur Site-008 | Nagpur | Central | 100 | Live | 2025-12-23 | 2026-02-20 | 2026-02-26 | 2026-03-21 | 2026-03-26 | 6 | Met | Nihal Shere | 110205
ST02495 | PRJ031 | CL007 | Tata Motors | Nagpur Site-009 | Nagpur | Central | 20 | Installation Done | 2025-12-26 | 2026-02-11 | 2026-02-15 | 2026-03-03 |  | 12 | Marginal | Girindra Chatterjee | 202532
ST02496 | PRJ031 | CL007 | Tata Motors | Bhopal Site-010 | Bhopal | Central | 100 | Live | 2025-12-22 | 2026-02-05 | 2026-02-10 | 2026-02-16 | 2026-02-21 | 5 | Met | Advay Contractor | 255388
ST02497 | PRJ031 | CL007 | Tata Motors | Nagpur Site-011 | Nagpur | Central | 20 | Installation Done | 2025-12-07 | 2025-12-29 | 2026-01-03 | 2026-01-16 |  | 12 | Marginal | Teerth Bhardwaj | 100644
ST02498 | PRJ031 | CL007 | Tata Motors | Indore Site-012 | Indore | Central | 100 | Pending Acceptance | 2025-12-30 | 2026-02-27 | 2026-03-06 | 2026-03-21 | 2026-03-31 | 7 | Met | Mohammed Gupta | 199414
ST02499 | PRJ031 | CL007 | Tata Motors | Nagpur Site-013 | Nagpur | Central | 10 | Testing | 2025-12-15 | 2026-02-02 | 2026-01-28 | 2026-02-25 |  | 12 | Marginal | Teerth Bhardwaj | 228574
ST02500 | PRJ031 | CL007 | Tata Motors | Nagpur Site-014 | Nagpur | Central | 50 | Survey Pending | 2025-12-20 | 2026-02-15 |  | 2026-02-26 |  | 1 | Met | Bhavika Sampath | 66505
ST02501 | PRJ031 | CL007 | Tata Motors | Bhopal Site-015 | Bhopal | Central | 100 | Survey Pending | 2025-12-31 | 2026-02-02 |  | 2026-02-28 |  | 4 | Met | Devansh Rajan | 133269
ST02502 | PRJ031 | CL007 | Tata Motors | Indore Site-016 | Indore | Central | 10 | Installation Done | 2025-12-18 | 2026-02-02 | 2026-02-10 | 2026-02-22 |  | 12 | Marginal | Unni Bhagat | 65073
ST02503 | PRJ031 | CL007 | Tata Motors | Nagpur Site-017 | Nagpur | Central | 50 | Live | 2025-12-20 | 2026-01-10 | 2026-01-08 | 2026-02-01 | 2026-02-13 | 0 | Met | Devansh Nigam | 192580
ST02504 | PRJ031 | CL007 | Tata Motors | Nagpur Site-018 | Nagpur | Central | 200 | Live | 2025-12-13 | 2026-01-20 | 2026-01-21 | 2026-02-10 | 2026-02-20 | 1 | Met | Girindra Chatterjee | 49888
ST02505 | PRJ031 | CL007 | Tata Motors | Indore Site-019 | Indore | Central | 100 | Installation Scheduled | 2025-12-07 | 2026-01-17 | 2026-01-25 | 2026-02-09 |  | 3 | Met | Unni Bhagat | 126491
ST02506 | PRJ031 | CL007 | Tata Motors | Bhopal Site-020 | Bhopal | Central | 100 | ROW In Progress | 2025-12-29 | 2026-02-03 |  | 2026-02-18 |  | 8 | Marginal | Priya Rastogi | 168634
ST02507 | PRJ031 | CL007 | Tata Motors | Nagpur Site-021 | Nagpur | Central | 50 | Testing | 2025-12-12 | 2026-01-22 | 2026-01-31 | 2026-02-04 |  | 12 | Marginal | Diya Rattan | 266376
ST02508 | PRJ031 | CL007 | Tata Motors | Bhopal Site-022 | Bhopal | Central | 20 | Installation Scheduled | 2025-12-28 | 2026-02-01 | 2026-02-06 | 2026-02-26 |  | 6 | Met | Arya Shere | 274256
ST02509 | PRJ031 | CL007 | Tata Motors | Indore Site-023 | Indore | Central | 200 | Installation Done | 2026-01-01 | 2026-01-25 | 2026-02-02 | 2026-02-11 |  | 12 | Marginal | Ekansh Balay | 195200
ST02510 | PRJ031 | CL007 | Tata Motors | Bhopal Site-024 | Bhopal | Central | 50 | Live | 2025-12-20 | 2026-02-13 | 2026-02-09 | 2026-03-07 | 2026-03-10 | 0 | Met | Darsh Rau | 102864
ST02511 | PRJ031 | CL007 | Tata Motors | Bhopal Site-025 | Bhopal | Central | 200 | Live | 2025-12-09 | 2025-12-30 | 2025-12-27 | 2026-01-13 | 2026-01-24 | 0 | Met | Arya Shere | 202570
ST02512 | PRJ031 | CL007 | Tata Motors | Indore Site-026 | Indore | Central | 10 | ROW In Progress | 2026-01-01 | 2026-03-01 |  | 2026-03-31 |  | 3 | Met | Ekavir Varkey | 213480
ST02513 | PRJ031 | CL007 | Tata Motors | Nagpur Site-027 | Nagpur | Central | 100 | Live | 2025-12-11 | 2026-01-31 | 2026-02-09 | 2026-02-21 | 2026-03-02 | 9 | Marginal | Simon Tata | 278710
ST02514 | PRJ031 | CL007 | Tata Motors | Bhopal Site-028 | Bhopal | Central | 100 | Installation Done | 2025-12-20 | 2026-01-18 | 2026-01-14 | 2026-02-03 |  | 12 | Marginal | Kabir Soman | 111513
ST02515 | PRJ031 | CL007 | Tata Motors | Indore Site-029 | Indore | Central | 20 | Live | 2025-12-13 | 2026-02-11 | 2026-02-14 | 2026-03-05 | 2026-03-14 | 3 | Met | Siddharth Zacharia | 72512
ST02516 | PRJ031 | CL007 | Tata Motors | Nagpur Site-030 | Nagpur | Central | 100 | Survey Pending | 2025-12-11 | 2026-01-12 |  | 2026-01-29 |  | 5 | Met | Tanay Rattan | 68272
ST02517 | PRJ031 | CL007 | Tata Motors | Indore Site-031 | Indore | Central | 100 | Live | 2025-12-30 | 2026-01-22 | 2026-01-31 | 2026-02-08 | 2026-02-08 | 9 | Marginal | Arya Sunder | 118384
ST02518 | PRJ031 | CL007 | Tata Motors | Indore Site-032 | Indore | Central | 100 | Installation Done | 2025-12-20 | 2026-01-20 | 2026-01-28 | 2026-02-03 |  | 12 | Marginal | Raksha Varughese | 147868
ST02519 | PRJ031 | CL007 | Tata Motors | Indore Site-033 | Indore | Central | 50 | Testing | 2025-12-29 | 2026-01-20 | 2026-01-30 | 2026-02-14 |  | 12 | Marginal | Wahab Raval | 247737
ST02520 | PRJ031 | CL007 | Tata Motors | Indore Site-034 | Indore | Central | 200 | Testing | 2025-12-28 | 2026-02-04 | 2026-02-06 | 2026-02-23 |  | 12 | Marginal | Irya Sampath | 81264
ST02521 | PRJ031 | CL007 | Tata Motors | Nagpur Site-035 | Nagpur | Central | 10 | Installation Done | 2025-12-13 | 2026-01-30 | 2026-02-08 | 2026-02-17 |  | 12 | Marginal | Devika Rastogi | 169832
ST02522 | PRJ031 | CL007 | Tata Motors | Indore Site-036 | Indore | Central | 50 | Installation Done | 2025-12-24 | 2026-02-12 | 2026-02-16 | 2026-02-22 |  | 12 | Marginal | Yashica Cherian | 50905
ST02523 | PRJ031 | CL007 | Tata Motors | Indore Site-037 | Indore | Central | 100 | Installation Done | 2025-12-18 | 2026-01-12 | 2026-01-16 | 2026-02-10 |  | 12 | Marginal | Darsh Rau | 97355
ST02524 | PRJ031 | CL007 | Tata Motors | Indore Site-038 | Indore | Central | 10 | ROW In Progress | 2025-12-17 | 2026-02-05 |  | 2026-02-21 |  | 3 | Met | Tara Dhar | 251770
ST02525 | PRJ031 | CL007 | Tata Motors | Bhopal Site-039 | Bhopal | Central | 50 | Live | 2025-12-08 | 2026-02-02 | 2026-02-05 | 2026-02-13 | 2026-02-23 | 3 | Met | Chandresh Zachariah | 138603
ST02526 | PRJ031 | CL007 | Tata Motors | Nagpur Site-040 | Nagpur | Central | 20 | Installation Done | 2025-12-14 | 2026-01-21 | 2026-01-24 | 2026-02-10 |  | 12 | Marginal | Irya Sampath | 216624
ST02527 | PRJ031 | CL007 | Tata Motors | Nagpur Site-041 | Nagpur | Central | 20 | Installation Done | 2025-12-14 | 2026-01-24 | 2026-01-24 | 2026-02-09 |  | 12 | Marginal | Niharika Sunder | 157679
ST02528 | PRJ031 | CL007 | Tata Motors | Bhopal Site-042 | Bhopal | Central | 10 | Live | 2025-12-28 | 2026-01-17 | 2026-01-13 | 2026-02-04 | 2026-02-15 | 0 | Met | Theodore Devi | 63386
ST02529 | PRJ031 | CL007 | Tata Motors | Bhopal Site-043 | Bhopal | Central | 10 | Live | 2025-12-16 | 2026-02-11 | 2026-02-17 | 2026-03-06 | 2026-03-05 | 6 | Met | Yatin Baral | 193818
ST02530 | PRJ031 | CL007 | Tata Motors | Nagpur Site-044 | Nagpur | Central | 50 | Live | 2025-12-17 | 2026-01-11 | 2026-01-08 | 2026-02-07 | 2026-02-07 | 0 | Met | Yatin Baral | 101370
ST02531 | PRJ031 | CL007 | Tata Motors | Nagpur Site-045 | Nagpur | Central | 50 | Pending Acceptance | 2026-01-01 | 2026-02-07 | 2026-02-14 | 2026-03-02 | 2026-03-01 | 7 | Met | Kevin Solanki | 168308
ST02532 | PRJ031 | CL007 | Tata Motors | Indore Site-046 | Indore | Central | 100 | Installation Done | 2025-12-09 | 2026-01-30 | 2026-02-07 | 2026-02-25 |  | 12 | Marginal | Ekbal Garg | 118574
ST02533 | PRJ031 | CL007 | Tata Motors | Nagpur Site-047 | Nagpur | Central | 100 | Installation Done | 2025-12-25 | 2026-02-09 | 2026-02-16 | 2026-03-11 |  | 12 | Marginal | Aarush Lall | 230642
ST02534 | PRJ031 | CL007 | Tata Motors | Nagpur Site-048 | Nagpur | Central | 50 | Survey Pending | 2025-12-18 | 2026-01-15 |  | 2026-02-05 |  | 6 | Met | Logan Sami | 49397
ST02535 | PRJ031 | CL007 | Tata Motors | Nagpur Site-049 | Nagpur | Central | 10 | Live | 2025-12-09 | 2026-01-15 | 2026-01-15 | 2026-02-01 | 2026-02-05 | 0 | Met | Isaac Patil | 195536
ST02536 | PRJ031 | CL007 | Tata Motors | Nagpur Site-050 | Nagpur | Central | 50 | ROW In Progress | 2025-12-20 | 2026-01-27 |  | 2026-02-06 |  | 5 | Met | Dakshesh Trivedi | 223365
ST02537 | PRJ031 | CL007 | Tata Motors | Bhopal Site-051 | Bhopal | Central | 50 | Testing | 2025-12-20 | 2026-01-20 | 2026-01-19 | 2026-02-01 |  | 12 | Marginal | Tara Dhar | 137944
ST02538 | PRJ031 | CL007 | Tata Motors | Bhopal Site-052 | Bhopal | Central | 50 | Installation Scheduled | 2025-12-09 | 2026-02-01 | 2026-02-08 | 2026-02-23 |  | 0 | Met | Quincy Biswas | 125616
ST02539 | PRJ031 | CL007 | Tata Motors | Indore Site-053 | Indore | Central | 200 | Live | 2025-12-13 | 2026-02-06 | 2026-02-03 | 2026-02-24 | 2026-03-07 | 0 | Met | Unni Bhagat | 88950
ST02540 | PRJ031 | CL007 | Tata Motors | Indore Site-054 | Indore | Central | 50 | Installation Done | 2025-12-16 | 2026-01-13 | 2026-01-08 | 2026-01-29 |  | 12 | Marginal | Devansh Nigam | 118931
ST02541 | PRJ031 | CL007 | Tata Motors | Bhopal Site-055 | Bhopal | Central | 100 | Survey Pending | 2025-12-30 | 2026-01-29 |  | 2026-02-15 |  | 8 | Marginal | Alka Wable | 264756
ST02542 | PRJ031 | CL007 | Tata Motors | Indore Site-056 | Indore | Central | 100 | Pending Acceptance | 2025-12-24 | 2026-02-08 | 2026-02-16 | 2026-02-27 | 2026-03-11 | 8 | Marginal | Arya Sunder | 70037
ST02543 | PRJ031 | CL007 | Tata Motors | Bhopal Site-057 | Bhopal | Central | 20 | ROW In Progress | 2025-12-13 | 2026-01-25 |  | 2026-02-06 |  | 8 | Marginal | Nihal Shere | 82055
ST02544 | PRJ031 | CL007 | Tata Motors | Indore Site-058 | Indore | Central | 200 | Installation Done | 2025-12-13 | 2026-01-19 | 2026-01-27 | 2026-02-08 |  | 12 | Marginal | Theodore Devi | 136556
ST02545 | PRJ031 | CL007 | Tata Motors | Bhopal Site-059 | Bhopal | Central | 10 | Pending Acceptance | 2025-12-23 | 2026-02-15 | 2026-02-21 | 2026-03-17 | 2026-03-19 | 6 | Met | Quincy Biswas | 189278
ST02546 | PRJ031 | CL007 | Tata Motors | Nagpur Site-060 | Nagpur | Central | 50 | Installation Scheduled | 2025-12-26 | 2026-02-23 | 2026-02-19 | 2026-03-23 |  | 8 | Marginal | Priya Rastogi | 89776
ST02547 | PRJ031 | CL007 | Tata Motors | Nagpur Site-061 | Nagpur | Central | 50 | Pending Acceptance | 2025-12-17 | 2026-01-29 | 2026-01-27 | 2026-02-20 | 2026-03-03 | 0 | Met | Ekiya Suresh | 101395
ST02548 | PRJ031 | CL007 | Tata Motors | Nagpur Site-062 | Nagpur | Central | 200 | Installation Scheduled | 2025-12-10 | 2026-02-05 | 2026-02-07 | 2026-02-24 |  | 8 | Marginal | Gavin Batta | 188584
ST02549 | PRJ031 | CL007 | Tata Motors | Nagpur Site-063 | Nagpur | Central | 50 | Live | 2025-12-30 | 2026-01-22 | 2026-01-23 | 2026-02-18 | 2026-02-17 | 1 | Met | Faqid Savant | 94565
ST02550 | PRJ031 | CL007 | Tata Motors | Indore Site-064 | Indore | Central | 10 | ROW In Progress | 2025-12-26 | 2026-01-26 |  | 2026-02-14 |  | 2 | Met | Logan Sami | 195531
ST02551 | PRJ031 | CL007 | Tata Motors | Indore Site-065 | Indore | Central | 200 | Live | 2025-12-14 | 2026-01-06 | 2026-01-04 | 2026-01-21 | 2026-01-20 | 0 | Met | Urvashi Ray | 85563
ST02552 | PRJ031 | CL007 | Tata Motors | Indore Site-066 | Indore | Central | 10 | Live | 2025-12-16 | 2026-01-10 | 2026-01-07 | 2026-01-29 | 2026-02-07 | 0 | Met | Farhan Chada | 110394
ST02553 | PRJ031 | CL007 | Tata Motors | Bhopal Site-067 | Bhopal | Central | 10 | Installation Scheduled | 2025-12-27 | 2026-02-07 | 2026-02-13 | 2026-02-23 |  | 0 | Met | Girindra Chatterjee | 103577
ST02554 | PRJ031 | CL007 | Tata Motors | Bhopal Site-068 | Bhopal | Central | 100 | ROW In Progress | 2026-01-01 | 2026-02-09 |  | 2026-02-28 |  | 0 | Met | Bhavika Sampath | 184676
ST02555 | PRJ031 | CL007 | Tata Motors | Bhopal Site-069 | Bhopal | Central | 50 | Live | 2025-12-10 | 2026-01-02 | 2026-01-10 | 2026-01-23 | 2026-01-29 | 8 | Marginal | Urvashi Ray | 164699
ST02556 | PRJ031 | CL007 | Tata Motors | Indore Site-070 | Indore | Central | 50 | Live | 2025-12-29 | 2026-02-14 | 2026-02-16 | 2026-03-05 | 2026-03-12 | 2 | Met | Advay Contractor | 250281
ST02557 | PRJ031 | CL007 | Tata Motors | Nagpur Site-071 | Nagpur | Central | 200 | Live | 2025-12-12 | 2026-02-08 | 2026-02-06 | 2026-02-22 | 2026-03-04 | 0 | Met | Victor Kannan | 134454
ST02558 | PRJ031 | CL007 | Tata Motors | Bhopal Site-072 | Bhopal | Central | 10 | Survey Pending | 2025-12-16 | 2026-01-10 |  | 2026-02-08 |  | 1 | Met | Tanay Rattan | 72431
ST02559 | PRJ031 | CL007 | Tata Motors | Nagpur Site-073 | Nagpur | Central | 200 | Live | 2025-12-27 | 2026-02-09 | 2026-02-06 | 2026-02-19 | 2026-02-17 | 0 | Met | Harini Choudhury | 86952
ST02560 | PRJ031 | CL007 | Tata Motors | Nagpur Site-074 | Nagpur | Central | 100 | Installation Scheduled | 2026-01-01 | 2026-01-28 | 2026-02-04 | 2026-02-24 |  | 2 | Met | Yatin Baral | 78015
ST02561 | PRJ031 | CL007 | Tata Motors | Bhopal Site-075 | Bhopal | Central | 20 | Live | 2025-12-27 | 2026-02-16 | 2026-02-22 | 2026-03-18 | 2026-03-27 | 6 | Met | Arya Shere | 264062
ST02562 | PRJ031 | CL007 | Tata Motors | Nagpur Site-076 | Nagpur | Central | 20 | Testing | 2025-12-19 | 2026-01-17 | 2026-01-12 | 2026-02-12 |  | 12 | Marginal | Victor Kannan | 175172
ST02563 | PRJ031 | CL007 | Tata Motors | Nagpur Site-077 | Nagpur | Central | 200 | Live | 2025-12-29 | 2026-01-23 | 2026-01-18 | 2026-02-02 | 2026-02-10 | 0 | Met | Siddharth Zacharia | 81477
ST02564 | PRJ031 | CL007 | Tata Motors | Nagpur Site-078 | Nagpur | Central | 20 | Live | 2025-12-27 | 2026-02-25 | 2026-03-03 | 2026-03-22 | 2026-03-23 | 6 | Met | Teerth Bhardwaj | 57886
ST02565 | PRJ031 | CL007 | Tata Motors | Nagpur Site-079 | Nagpur | Central | 50 | Installation Scheduled | 2025-12-11 | 2026-01-01 | 2025-12-28 | 2026-01-31 |  | 7 | Met | Unni Bhagat | 206398
ST02566 | PRJ031 | CL007 | Tata Motors | Indore Site-080 | Indore | Central | 200 | Live | 2025-12-15 | 2026-01-16 | 2026-01-25 | 2026-01-29 | 2026-01-30 | 9 | Marginal | Darsh Rau | 68166
ST02567 | PRJ031 | CL007 | Tata Motors | Indore Site-081 | Indore | Central | 20 | Installation Scheduled | 2025-12-29 | 2026-01-20 | 2026-01-25 | 2026-02-15 |  | 0 | Met | Girik Khalsa | 49177
ST02568 | PRJ031 | CL007 | Tata Motors | Indore Site-082 | Indore | Central | 50 | Survey Pending | 2025-12-24 | 2026-01-14 |  | 2026-01-29 |  | 2 | Met | Nihal Shere | 154709
ST02569 | PRJ031 | CL007 | Tata Motors | Indore Site-083 | Indore | Central | 10 | Live | 2025-12-22 | 2026-01-27 | 2026-02-05 | 2026-02-18 | 2026-02-25 | 9 | Marginal | Anamika Kanda | 112417
ST02570 | PRJ031 | CL007 | Tata Motors | Bhopal Site-084 | Bhopal | Central | 50 | Live | 2025-12-30 | 2026-02-25 | 2026-03-02 | 2026-03-20 | 2026-03-29 | 5 | Met | Ekapad Walia | 54247
ST02571 | PRJ031 | CL007 | Tata Motors | Bhopal Site-085 | Bhopal | Central | 20 | Live | 2025-12-17 | 2026-02-15 | 2026-02-21 | 2026-03-10 | 2026-03-11 | 6 | Met | Quincy Biswas | 184157
ST02572 | PRJ031 | CL007 | Tata Motors | Nagpur Site-086 | Nagpur | Central | 10 | Pending Acceptance | 2025-12-21 | 2026-02-03 | 2026-02-09 | 2026-02-26 | 2026-03-02 | 6 | Met | Ekapad Walia | 147066
ST02573 | PRJ031 | CL007 | Tata Motors | Nagpur Site-087 | Nagpur | Central | 10 | Pending Acceptance | 2025-12-20 | 2026-01-17 | 2026-01-16 | 2026-02-14 | 2026-02-11 | 0 | Met | Michael Dutta | 254548
ST02574 | PRJ032 | CL007 | Tata Motors | Bhopal Site-001 | Bhopal | Central | 50 | ROW In Progress | 2025-06-22 | 2025-08-16 |  | 2025-08-26 |  | 1 | Met | Alka Wable | 159985
ST02575 | PRJ032 | CL007 | Tata Motors | Nagpur Site-002 | Nagpur | Central | 10 | Installation Scheduled | 2025-07-08 | 2025-08-30 | 2025-09-06 | 2025-09-21 |  | 7 | Met | Darsh Rau | 130536
ST02576 | PRJ032 | CL007 | Tata Motors | Indore Site-003 | Indore | Central | 100 | Installation Scheduled | 2025-06-13 | 2025-07-25 | 2025-07-27 | 2025-08-22 |  | 2 | Met | Dominic Kakar | 206232
ST02577 | PRJ032 | CL007 | Tata Motors | Indore Site-004 | Indore | Central | 20 | Installation Done | 2025-06-21 | 2025-08-05 | 2025-08-04 | 2025-08-30 |  | 12 | Marginal | Simon Tata | 209921
ST02578 | PRJ032 | CL007 | Tata Motors | Indore Site-005 | Indore | Central | 200 | Live | 2025-06-25 | 2025-08-03 | 2025-07-31 | 2025-08-16 | 2025-08-17 | 0 | Met | Darsh Rau | 152156
ST02579 | PRJ032 | CL007 | Tata Motors | Indore Site-006 | Indore | Central | 10 | Live | 2025-07-04 | 2025-08-02 | 2025-08-08 | 2025-08-13 | 2025-08-15 | 6 | Met | Ikbal Kothari | 129143
ST02580 | PRJ032 | CL007 | Tata Motors | Nagpur Site-007 | Nagpur | Central | 100 | Live | 2025-07-08 | 2025-08-10 | 2025-08-12 | 2025-08-20 | 2025-09-01 | 2 | Met | Unni Bhagat | 274310
ST02581 | PRJ032 | CL007 | Tata Motors | Indore Site-008 | Indore | Central | 100 | Testing | 2025-06-15 | 2025-07-15 | 2025-07-22 | 2025-07-30 |  | 12 | Marginal | Devansh Nigam | 102027
ST02582 | PRJ032 | CL007 | Tata Motors | Nagpur Site-009 | Nagpur | Central | 100 | Installation Done | 2025-06-28 | 2025-08-19 | 2025-08-22 | 2025-09-07 |  | 12 | Marginal | Ekbal Garg | 161866
ST02583 | PRJ032 | CL007 | Tata Motors | Nagpur Site-010 | Nagpur | Central | 200 | Testing | 2025-06-13 | 2025-08-02 | 2025-08-07 | 2025-08-14 |  | 12 | Marginal | Michael Dutta | 204160
ST02584 | PRJ032 | CL007 | Tata Motors | Nagpur Site-011 | Nagpur | Central | 20 | Survey Pending | 2025-06-28 | 2025-08-10 |  | 2025-08-31 |  | 1 | Met | Ekavir Bhargava | 123364
ST02585 | PRJ032 | CL007 | Tata Motors | Bhopal Site-012 | Bhopal | Central | 100 | Live | 2025-07-02 | 2025-08-01 | 2025-08-06 | 2025-08-17 | 2025-08-17 | 5 | Met | Ekavir Bhargava | 207506
ST02586 | PRJ032 | CL007 | Tata Motors | Nagpur Site-013 | Nagpur | Central | 200 | ROW In Progress | 2025-07-07 | 2025-08-11 |  | 2025-09-06 |  | 5 | Met | Vansha Thakkar | 116332
ST02587 | PRJ032 | CL007 | Tata Motors | Indore Site-014 | Indore | Central | 10 | Installation Done | 2025-06-24 | 2025-08-07 | 2025-08-12 | 2025-09-04 |  | 12 | Marginal | Dakshesh Trivedi | 49913
ST02588 | PRJ032 | CL007 | Tata Motors | Indore Site-015 | Indore | Central | 50 | Installation Scheduled | 2025-07-06 | 2025-09-03 | 2025-09-06 | 2025-10-03 |  | 3 | Met | Alka Wable | 245759
ST02589 | PRJ032 | CL007 | Tata Motors | Indore Site-016 | Indore | Central | 100 | Testing | 2025-07-04 | 2025-08-24 | 2025-08-22 | 2025-09-13 |  | 12 | Marginal | Ekiya Suresh | 81926
ST02590 | PRJ032 | CL007 | Tata Motors | Nagpur Site-017 | Nagpur | Central | 100 | Survey Pending | 2025-07-01 | 2025-08-07 |  | 2025-09-05 |  | 0 | Met | Girik Khalsa | 226910
ST02591 | PRJ032 | CL007 | Tata Motors | Bhopal Site-018 | Bhopal | Central | 100 | Installation Scheduled | 2025-06-16 | 2025-07-28 | 2025-07-29 | 2025-08-18 |  | 7 | Met | Advay Contractor | 58357
ST02592 | PRJ032 | CL007 | Tata Motors | Nagpur Site-019 | Nagpur | Central | 100 | Survey Pending | 2025-06-16 | 2025-07-27 |  | 2025-08-26 |  | 4 | Met | Teerth Bhardwaj | 270131
ST02593 | PRJ032 | CL007 | Tata Motors | Bhopal Site-020 | Bhopal | Central | 200 | Live | 2025-07-02 | 2025-08-07 | 2025-08-09 | 2025-08-19 | 2025-08-24 | 2 | Met | Dakshesh Trivedi | 79994
ST02594 | PRJ032 | CL007 | Tata Motors | Bhopal Site-021 | Bhopal | Central | 50 | Installation Done | 2025-06-24 | 2025-08-12 | 2025-08-17 | 2025-09-03 |  | 12 | Marginal | Devansh Rajan | 103523
ST02595 | PRJ032 | CL007 | Tata Motors | Indore Site-022 | Indore | Central | 100 | Installation Scheduled | 2025-07-06 | 2025-09-04 | 2025-09-14 | 2025-09-23 |  | 1 | Met | Irya Sampath | 274516
ST02596 | PRJ032 | CL007 | Tata Motors | Nagpur Site-023 | Nagpur | Central | 20 | Installation Done | 2025-06-19 | 2025-08-17 | 2025-08-22 | 2025-08-31 |  | 12 | Marginal | Aarush Lall | 185615
ST02597 | PRJ032 | CL007 | Tata Motors | Indore Site-024 | Indore | Central | 100 | Pending Acceptance | 2025-06-24 | 2025-08-18 | 2025-08-13 | 2025-09-15 | 2025-09-23 | 0 | Met | Arya Sunder | 263330
ST02598 | PRJ032 | CL007 | Tata Motors | Indore Site-025 | Indore | Central | 10 | Installation Done | 2025-06-29 | 2025-07-25 | 2025-08-02 | 2025-08-16 |  | 12 | Marginal | Yashica Cherian | 251416
ST02599 | PRJ032 | CL007 | Tata Motors | Nagpur Site-026 | Nagpur | Central | 20 | Live | 2025-06-21 | 2025-08-20 | 2025-08-18 | 2025-09-05 | 2025-09-15 | 0 | Met | Devika Rastogi | 100942
ST02600 | PRJ032 | CL007 | Tata Motors | Nagpur Site-027 | Nagpur | Central | 50 | Live | 2025-07-08 | 2025-09-06 | 2025-09-10 | 2025-09-30 | 2025-09-27 | 4 | Met | Anamika Kanda | 166900
ST02601 | PRJ032 | CL007 | Tata Motors | Bhopal Site-028 | Bhopal | Central | 50 | Installation Scheduled | 2025-07-08 | 2025-09-03 | 2025-09-12 | 2025-10-03 |  | 1 | Met | Wahab Raval | 220489
ST02602 | PRJ032 | CL007 | Tata Motors | Nagpur Site-029 | Nagpur | Central | 200 | Installation Done | 2025-07-08 | 2025-08-12 | 2025-08-16 | 2025-08-25 |  | 12 | Marginal | Darsh Rau | 232077
ST02603 | PRJ032 | CL007 | Tata Motors | Indore Site-030 | Indore | Central | 50 | Testing | 2025-06-14 | 2025-08-06 | 2025-08-07 | 2025-08-31 |  | 12 | Marginal | Logan Sami | 232140
ST02604 | PRJ032 | CL007 | Tata Motors | Indore Site-031 | Indore | Central | 10 | Survey Pending | 2025-06-27 | 2025-07-18 |  | 2025-08-03 |  | 6 | Met | Anamika Kanda | 65403
ST02605 | PRJ032 | CL007 | Tata Motors | Indore Site-032 | Indore | Central | 10 | Installation Scheduled | 2025-07-04 | 2025-07-25 | 2025-07-21 | 2025-08-07 |  | 7 | Met | Faqid Savant | 165589
ST02606 | PRJ032 | CL007 | Tata Motors | Nagpur Site-033 | Nagpur | Central | 200 | Live | 2025-06-21 | 2025-08-16 | 2025-08-12 | 2025-09-10 | 2025-09-20 | 0 | Met | Ekiya Suresh | 183674
ST02607 | PRJ032 | CL007 | Tata Motors | Indore Site-034 | Indore | Central | 200 | Installation Scheduled | 2025-06-16 | 2025-07-31 | 2025-07-30 | 2025-08-13 |  | 5 | Met | Devika Rastogi | 219216
ST02608 | PRJ032 | CL007 | Tata Motors | Nagpur Site-035 | Nagpur | Central | 50 | Live | 2025-07-01 | 2025-08-17 | 2025-08-26 | 2025-09-08 | 2025-09-12 | 9 | Marginal | Farhan Chada | 252247
ST02609 | PRJ032 | CL007 | Tata Motors | Indore Site-036 | Indore | Central | 200 | Installation Done | 2025-06-20 | 2025-08-02 | 2025-08-08 | 2025-08-28 |  | 12 | Marginal | Niharika Sunder | 56921
ST02610 | PRJ032 | CL007 | Tata Motors | Indore Site-037 | Indore | Central | 20 | Survey Pending | 2025-06-17 | 2025-07-15 |  | 2025-08-11 |  | 8 | Marginal | Victor Kannan | 249233
ST02611 | PRJ032 | CL007 | Tata Motors | Bhopal Site-038 | Bhopal | Central | 10 | Pending Acceptance | 2025-06-20 | 2025-08-01 | 2025-07-30 | 2025-08-17 | 2025-08-14 | 0 | Met | Victor Kannan | 94692
ST02612 | PRJ032 | CL007 | Tata Motors | Bhopal Site-039 | Bhopal | Central | 50 | Testing | 2025-06-22 | 2025-07-22 | 2025-08-01 | 2025-08-21 |  | 12 | Marginal | Siddharth Zacharia | 158302
ST02613 | PRJ032 | CL007 | Tata Motors | Indore Site-040 | Indore | Central | 100 | Live | 2025-06-20 | 2025-07-30 | 2025-08-09 | 2025-08-27 | 2025-09-06 | 10 | Marginal | Liam Koshy | 227060
ST02614 | PRJ032 | CL007 | Tata Motors | Indore Site-041 | Indore | Central | 100 | Installation Done | 2025-06-13 | 2025-07-15 | 2025-07-10 | 2025-07-26 |  | 12 | Marginal | Siddharth Zacharia | 255919
ST02615 | PRJ032 | CL007 | Tata Motors | Indore Site-042 | Indore | Central | 200 | Live | 2025-06-26 | 2025-08-08 | 2025-08-07 | 2025-08-30 | 2025-08-27 | 0 | Met | Ekiya Suresh | 267770
ST02616 | PRJ032 | CL007 | Tata Motors | Indore Site-043 | Indore | Central | 200 | ROW In Progress | 2025-07-04 | 2025-08-19 |  | 2025-09-05 |  | 7 | Met | Devansh Nigam | 230477
ST02617 | PRJ032 | CL007 | Tata Motors | Bhopal Site-044 | Bhopal | Central | 200 | ROW In Progress | 2025-06-29 | 2025-08-21 |  | 2025-09-12 |  | 6 | Met | Devansh Rajan | 68189
ST02618 | PRJ032 | CL007 | Tata Motors | Bhopal Site-045 | Bhopal | Central | 50 | Live | 2025-06-19 | 2025-07-19 | 2025-07-16 | 2025-08-06 | 2025-08-08 | 0 | Met | Yashica Issac | 256053
ST02619 | PRJ032 | CL007 | Tata Motors | Indore Site-046 | Indore | Central | 200 | ROW In Progress | 2025-06-16 | 2025-08-12 |  | 2025-09-06 |  | 8 | Marginal | Aarush Lall | 265961
ST02620 | PRJ032 | CL007 | Tata Motors | Indore Site-047 | Indore | Central | 50 | Live | 2025-06-22 | 2025-08-06 | 2025-08-11 | 2025-08-30 | 2025-09-04 | 5 | Met | Arya Shere | 142596
ST02621 | PRJ032 | CL007 | Tata Motors | Nagpur Site-048 | Nagpur | Central | 10 | Installation Scheduled | 2025-06-24 | 2025-08-03 | 2025-08-06 | 2025-08-22 |  | 1 | Met | Michael Dutta | 254005
ST02622 | PRJ032 | CL007 | Tata Motors | Nagpur Site-049 | Nagpur | Central | 100 | Testing | 2025-07-07 | 2025-08-17 | 2025-08-14 | 2025-09-02 |  | 12 | Marginal | Mohammed Gupta | 94173
ST02623 | PRJ032 | CL007 | Tata Motors | Nagpur Site-050 | Nagpur | Central | 200 | Pending Acceptance | 2025-07-04 | 2025-08-14 | 2025-08-13 | 2025-08-25 | 2025-08-28 | 0 | Met | Michael Dutta | 225883
ST02624 | PRJ032 | CL007 | Tata Motors | Nagpur Site-051 | Nagpur | Central | 50 | Installation Scheduled | 2025-07-06 | 2025-08-22 | 2025-08-26 | 2025-09-04 |  | 8 | Marginal | Wahab Raval | 66042
ST02625 | PRJ032 | CL007 | Tata Motors | Indore Site-052 | Indore | Central | 50 | Installation Done | 2025-06-17 | 2025-07-17 | 2025-07-12 | 2025-07-29 |  | 12 | Marginal | Raksha Varughese | 96990
ST02626 | PRJ032 | CL007 | Tata Motors | Bhopal Site-053 | Bhopal | Central | 20 | Installation Scheduled | 2025-06-14 | 2025-07-10 | 2025-07-08 | 2025-07-25 |  | 7 | Met | Ekapad Walia | 147017
ST02627 | PRJ032 | CL007 | Tata Motors | Bhopal Site-054 | Bhopal | Central | 100 | ROW In Progress | 2025-06-29 | 2025-08-18 |  | 2025-09-09 |  | 4 | Met | Dakshesh Trivedi | 57113
ST02628 | PRJ032 | CL007 | Tata Motors | Nagpur Site-055 | Nagpur | Central | 200 | Testing | 2025-06-26 | 2025-08-15 | 2025-08-23 | 2025-08-28 |  | 12 | Marginal | Devika Rastogi | 248287
ST02629 | PRJ032 | CL007 | Tata Motors | Indore Site-056 | Indore | Central | 100 | Installation Done | 2025-07-06 | 2025-09-02 | 2025-09-08 | 2025-09-12 |  | 12 | Marginal | Tanay Rattan | 216496
ST02630 | PRJ032 | CL007 | Tata Motors | Indore Site-057 | Indore | Central | 100 | Live | 2025-06-15 | 2025-08-14 | 2025-08-22 | 2025-08-29 | 2025-08-29 | 8 | Marginal | Aarush Lall | 55956
ST02631 | PRJ032 | CL007 | Tata Motors | Indore Site-058 | Indore | Central | 10 | Testing | 2025-06-29 | 2025-08-13 | 2025-08-09 | 2025-09-01 |  | 12 | Marginal | Yatin Baral | 147218
ST02632 | PRJ032 | CL007 | Tata Motors | Nagpur Site-059 | Nagpur | Central | 100 | Installation Scheduled | 2025-06-20 | 2025-07-20 | 2025-07-27 | 2025-08-08 |  | 5 | Met | Jai Kota | 206155
ST02633 | PRJ032 | CL007 | Tata Motors | Indore Site-060 | Indore | Central | 10 | Installation Done | 2025-06-16 | 2025-08-12 | 2025-08-09 | 2025-09-03 |  | 12 | Marginal | Girindra Chatterjee | 233199
ST02634 | PRJ032 | CL007 | Tata Motors | Nagpur Site-061 | Nagpur | Central | 200 | Live | 2025-07-02 | 2025-07-23 | 2025-07-30 | 2025-08-10 | 2025-08-08 | 7 | Met | Quincy Biswas | 214128
ST02635 | PRJ032 | CL007 | Tata Motors | Bhopal Site-062 | Bhopal | Central | 10 | Installation Scheduled | 2025-06-17 | 2025-07-28 | 2025-07-26 | 2025-08-26 |  | 7 | Met | Advay Contractor | 189785
ST02636 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-001 | Hyderabad | South | 200 | Installation Scheduled | 2025-08-03 | 2025-08-24 | 2025-08-25 | 2025-09-21 |  | 0 | Met | Yatin Baral | 112586
ST02637 | PRJ033 | CL007 | Tata Motors | Kochi Site-002 | Kochi | South | 100 | Installation Done | 2025-07-24 | 2025-09-08 | 2025-09-03 | 2025-10-01 |  | 12 | Marginal | Isaac Patil | 271886
ST02638 | PRJ033 | CL007 | Tata Motors | Kochi Site-003 | Kochi | South | 100 | Survey Pending | 2025-07-29 | 2025-08-26 |  | 2025-09-18 |  | 8 | Marginal | Diya Rattan | 208786
ST02639 | PRJ033 | CL007 | Tata Motors | Kochi Site-004 | Kochi | South | 20 | Live | 2025-07-27 | 2025-09-13 | 2025-09-19 | 2025-10-07 | 2025-10-05 | 6 | Met | Niharika Sunder | 82831
ST02640 | PRJ033 | CL007 | Tata Motors | Kochi Site-005 | Kochi | South | 10 | Installation Scheduled | 2025-07-27 | 2025-09-22 | 2025-09-22 | 2025-10-16 |  | 1 | Met | Tara Dhar | 159767
ST02641 | PRJ033 | CL007 | Tata Motors | Chennai Site-006 | Chennai | South | 10 | Pending Acceptance | 2025-07-16 | 2025-08-13 | 2025-08-21 | 2025-08-28 | 2025-08-30 | 8 | Marginal | Niharika Sunder | 186463
ST02642 | PRJ033 | CL007 | Tata Motors | Chennai Site-007 | Chennai | South | 20 | Installation Scheduled | 2025-07-18 | 2025-08-21 | 2025-08-22 | 2025-09-07 |  | 0 | Met | Kabir Soman | 206685
ST02643 | PRJ033 | CL007 | Tata Motors | Chennai Site-008 | Chennai | South | 200 | Installation Scheduled | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-25 |  | 6 | Met | Devansh Nigam | 230524
ST02644 | PRJ033 | CL007 | Tata Motors | Chennai Site-009 | Chennai | South | 20 | Live | 2025-07-13 | 2025-08-27 | 2025-09-02 | 2025-09-26 | 2025-09-27 | 6 | Met | Unni Bhagat | 159726
ST02645 | PRJ033 | CL007 | Tata Motors | Kochi Site-010 | Kochi | South | 200 | Installation Scheduled | 2025-07-17 | 2025-09-13 | 2025-09-17 | 2025-09-25 |  | 2 | Met | Unni Bhagat | 108554
ST02646 | PRJ033 | CL007 | Tata Motors | Kochi Site-011 | Kochi | South | 200 | Live | 2025-07-14 | 2025-08-05 | 2025-08-12 | 2025-08-23 | 2025-08-28 | 7 | Met | Unni Bhagat | 120305
ST02647 | PRJ033 | CL007 | Tata Motors | Kochi Site-012 | Kochi | South | 50 | Live | 2025-07-23 | 2025-08-27 | 2025-08-25 | 2025-09-09 | 2025-09-06 | 0 | Met | Kashvi Edwin | 139924
ST02648 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-013 | Hyderabad | South | 100 | Pending Acceptance | 2025-07-17 | 2025-09-08 | 2025-09-03 | 2025-09-28 | 2025-10-02 | 0 | Met | Niharika Sunder | 244264
ST02649 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-014 | Hyderabad | South | 200 | Pending Acceptance | 2025-07-24 | 2025-09-03 | 2025-08-29 | 2025-09-28 | 2025-10-08 | 0 | Met | Mohammed Gupta | 187699
ST02650 | PRJ033 | CL007 | Tata Motors | Kochi Site-015 | Kochi | South | 20 | Survey Pending | 2025-07-18 | 2025-08-09 |  | 2025-08-26 |  | 2 | Met | Advay Contractor | 110301
ST02651 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-016 | Bengaluru | South | 100 | Pending Acceptance | 2025-07-14 | 2025-08-08 | 2025-08-13 | 2025-09-04 | 2025-09-13 | 5 | Met | Ekapad Walia | 200154
ST02652 | PRJ033 | CL007 | Tata Motors | Chennai Site-017 | Chennai | South | 200 | Testing | 2025-07-28 | 2025-09-22 | 2025-10-02 | 2025-10-07 |  | 12 | Marginal | Wahab Raval | 98210
ST02653 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-018 | Bengaluru | South | 200 | Installation Scheduled | 2025-07-18 | 2025-08-26 | 2025-09-01 | 2025-09-18 |  | 2 | Met | Upadhriti Wadhwa | 169227
ST02654 | PRJ033 | CL007 | Tata Motors | Kochi Site-019 | Kochi | South | 20 | Installation Scheduled | 2025-07-16 | 2025-09-01 | 2025-08-27 | 2025-09-18 |  | 3 | Met | Yatin Baral | 46737
ST02655 | PRJ033 | CL007 | Tata Motors | Kochi Site-020 | Kochi | South | 200 | Survey Pending | 2025-07-23 | 2025-08-17 |  | 2025-08-28 |  | 2 | Met | Quincy Biswas | 126846
ST02656 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-021 | Hyderabad | South | 10 | Live | 2025-07-17 | 2025-08-07 | 2025-08-06 | 2025-08-22 | 2025-08-19 | 0 | Met | Quincy Biswas | 139595
ST02657 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-022 | Hyderabad | South | 200 | Installation Done | 2025-07-21 | 2025-08-14 | 2025-08-21 | 2025-09-01 |  | 12 | Marginal | Wahab Raval | 207401
ST02658 | PRJ033 | CL007 | Tata Motors | Chennai Site-023 | Chennai | South | 100 | Live | 2025-08-04 | 2025-08-28 | 2025-08-24 | 2025-09-15 | 2025-09-24 | 0 | Met | Harini Choudhury | 274230
ST02659 | PRJ033 | CL007 | Tata Motors | Kochi Site-024 | Kochi | South | 100 | Installation Scheduled | 2025-08-05 | 2025-08-26 | 2025-08-24 | 2025-09-16 |  | 2 | Met | Mohammed Gupta | 111286
ST02660 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-025 | Hyderabad | South | 100 | ROW In Progress | 2025-07-14 | 2025-08-17 |  | 2025-09-08 |  | 0 | Met | Unni Bhagat | 121639
ST02661 | PRJ033 | CL007 | Tata Motors | Chennai Site-026 | Chennai | South | 200 | Installation Scheduled | 2025-07-31 | 2025-09-12 | 2025-09-22 | 2025-09-26 |  | 3 | Met | Kabir Soman | 149306
ST02662 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-027 | Bengaluru | South | 100 | Installation Done | 2025-08-07 | 2025-09-01 | 2025-09-04 | 2025-09-21 |  | 12 | Marginal | Yashica Cherian | 105062
ST02663 | PRJ033 | CL007 | Tata Motors | Chennai Site-028 | Chennai | South | 10 | Installation Done | 2025-07-15 | 2025-08-21 | 2025-08-26 | 2025-09-16 |  | 12 | Marginal | Teerth Bhardwaj | 46826
ST02664 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-029 | Bengaluru | South | 200 | Installation Done | 2025-08-05 | 2025-08-31 | 2025-09-08 | 2025-09-25 |  | 12 | Marginal | Dakshesh Trivedi | 220455
ST02665 | PRJ033 | CL007 | Tata Motors | Chennai Site-030 | Chennai | South | 10 | Survey Pending | 2025-07-17 | 2025-08-28 |  | 2025-09-09 |  | 2 | Met | Advay Contractor | 267399
ST02666 | PRJ033 | CL007 | Tata Motors | Chennai Site-031 | Chennai | South | 20 | Testing | 2025-08-05 | 2025-09-16 | 2025-09-15 | 2025-10-03 |  | 12 | Marginal | Yashica Cherian | 193138
ST02667 | PRJ033 | CL007 | Tata Motors | Kochi Site-032 | Kochi | South | 200 | Live | 2025-07-21 | 2025-09-15 | 2025-09-16 | 2025-10-10 | 2025-10-17 | 1 | Met | Yashica Issac | 200553
ST02668 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-033 | Bengaluru | South | 100 | Installation Scheduled | 2025-08-02 | 2025-09-14 | 2025-09-19 | 2025-09-27 |  | 1 | Met | Kabir Soman | 255258
ST02669 | PRJ033 | CL007 | Tata Motors | Kochi Site-034 | Kochi | South | 50 | ROW In Progress | 2025-08-01 | 2025-08-31 |  | 2025-09-10 |  | 7 | Met | Teerth Bhardwaj | 124352
ST02670 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-035 | Bengaluru | South | 20 | Pending Acceptance | 2025-07-22 | 2025-08-22 | 2025-08-26 | 2025-09-18 | 2025-09-29 | 4 | Met | Niharika Sunder | 86537
ST02671 | PRJ033 | CL007 | Tata Motors | Kochi Site-036 | Kochi | South | 20 | ROW In Progress | 2025-08-01 | 2025-08-26 |  | 2025-09-21 |  | 8 | Marginal | Liam Koshy | 91613
ST02672 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-037 | Hyderabad | South | 100 | Live | 2025-08-07 | 2025-09-26 | 2025-10-05 | 2025-10-13 | 2025-10-23 | 9 | Marginal | Dakshesh Trivedi | 90049
ST02673 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-038 | Hyderabad | South | 50 | Installation Scheduled | 2025-08-02 | 2025-09-10 | 2025-09-11 | 2025-10-10 |  | 5 | Met | Dipta Bhandari | 181024
ST02674 | PRJ033 | CL007 | Tata Motors | Kochi Site-039 | Kochi | South | 50 | ROW In Progress | 2025-07-25 | 2025-09-06 |  | 2025-10-01 |  | 1 | Met | Girik Khalsa | 242311
ST02675 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-040 | Hyderabad | South | 20 | Installation Scheduled | 2025-07-29 | 2025-08-20 | 2025-08-20 | 2025-09-18 |  | 0 | Met | Victor Kannan | 184969
ST02676 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-041 | Bengaluru | South | 10 | Live | 2025-07-17 | 2025-08-24 | 2025-09-03 | 2025-09-21 | 2025-10-01 | 10 | Marginal | Daksh Karnik | 234004
ST02677 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-042 | Bengaluru | South | 50 | Testing | 2025-07-13 | 2025-09-09 | 2025-09-06 | 2025-10-02 |  | 12 | Marginal | Dakshesh Trivedi | 104783
ST02678 | PRJ033 | CL007 | Tata Motors | Kochi Site-043 | Kochi | South | 20 | Installation Done | 2025-07-22 | 2025-08-21 | 2025-08-28 | 2025-09-12 |  | 12 | Marginal | Harini Choudhury | 140936
ST02679 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-044 | Hyderabad | South | 20 | Testing | 2025-07-14 | 2025-08-17 | 2025-08-25 | 2025-09-15 |  | 12 | Marginal | Simon Tata | 201089
ST02680 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-045 | Bengaluru | South | 20 | Live | 2025-07-21 | 2025-09-19 | 2025-09-15 | 2025-10-02 | 2025-10-09 | 0 | Met | Dipta Bhandari | 108367
ST02681 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-046 | Bengaluru | South | 50 | Pending Acceptance | 2025-07-16 | 2025-09-03 | 2025-09-03 | 2025-09-18 | 2025-09-27 | 0 | Met | Liam Koshy | 112796
ST02682 | PRJ033 | CL007 | Tata Motors | Kochi Site-047 | Kochi | South | 200 | Pending Acceptance | 2025-07-23 | 2025-09-07 | 2025-09-02 | 2025-09-17 | 2025-09-16 | 0 | Met | Victor Kannan | 77997
ST02683 | PRJ033 | CL007 | Tata Motors | Chennai Site-048 | Chennai | South | 20 | Installation Scheduled | 2025-07-23 | 2025-09-20 | 2025-09-23 | 2025-10-14 |  | 4 | Met | Yashica Issac | 195787
ST02684 | PRJ033 | CL007 | Tata Motors | Chennai Site-049 | Chennai | South | 100 | Live | 2025-08-06 | 2025-09-15 | 2025-09-23 | 2025-10-08 | 2025-10-20 | 8 | Marginal | Theodore Devi | 137513
ST02685 | PRJ033 | CL007 | Tata Motors | Chennai Site-050 | Chennai | South | 50 | Live | 2025-07-13 | 2025-08-12 | 2025-08-12 | 2025-09-04 | 2025-09-06 | 0 | Met | Dipta Bhandari | 235996
ST02686 | PRJ033 | CL007 | Tata Motors | Chennai Site-051 | Chennai | South | 200 | Installation Done | 2025-07-13 | 2025-08-04 | 2025-08-05 | 2025-08-18 |  | 12 | Marginal | Anamika Kanda | 195640
ST02687 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-052 | Bengaluru | South | 100 | Live | 2025-08-02 | 2025-08-25 | 2025-09-02 | 2025-09-13 | 2025-09-24 | 8 | Marginal | Liam Koshy | 271666
ST02688 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-053 | Hyderabad | South | 50 | Installation Scheduled | 2025-07-27 | 2025-09-17 | 2025-09-27 | 2025-10-04 |  | 5 | Met | Devansh Nigam | 217663
ST02689 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-054 | Bengaluru | South | 200 | Live | 2025-07-22 | 2025-08-22 | 2025-08-24 | 2025-09-04 | 2025-09-13 | 2 | Met | Wahab Raval | 201943
ST02690 | PRJ033 | CL007 | Tata Motors | Chennai Site-055 | Chennai | South | 50 | Live | 2025-08-05 | 2025-08-28 | 2025-09-05 | 2025-09-21 | 2025-09-29 | 8 | Marginal | Alka Wable | 208046
ST02691 | PRJ033 | CL007 | Tata Motors | Chennai Site-056 | Chennai | South | 50 | Installation Scheduled | 2025-07-20 | 2025-09-14 | 2025-09-21 | 2025-10-12 |  | 0 | Met | Urvashi Ray | 268784
ST02692 | PRJ033 | CL007 | Tata Motors | Chennai Site-057 | Chennai | South | 200 | Live | 2025-08-03 | 2025-09-29 | 2025-09-29 | 2025-10-20 | 2025-10-22 | 0 | Met | Vansha Thakkar | 191259
ST02693 | PRJ033 | CL007 | Tata Motors | Chennai Site-058 | Chennai | South | 10 | Installation Scheduled | 2025-07-19 | 2025-08-23 | 2025-08-21 | 2025-09-09 |  | 3 | Met | Dakshesh Trivedi | 105933
ST02694 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-059 | Hyderabad | South | 100 | Installation Scheduled | 2025-08-02 | 2025-09-04 | 2025-08-31 | 2025-09-19 |  | 3 | Met | Kevin Solanki | 71599
ST02695 | PRJ033 | CL007 | Tata Motors | Chennai Site-060 | Chennai | South | 200 | ROW In Progress | 2025-08-06 | 2025-09-25 |  | 2025-10-13 |  | 0 | Met | Logan Sami | 95037
ST02696 | PRJ033 | CL007 | Tata Motors | Kochi Site-061 | Kochi | South | 50 | ROW In Progress | 2025-07-20 | 2025-08-23 |  | 2025-09-13 |  | 0 | Met | Priya Rastogi | 149794
ST02697 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-062 | Bengaluru | South | 100 | ROW In Progress | 2025-07-17 | 2025-08-26 |  | 2025-09-08 |  | 0 | Met | Gavin Batta | 140849
ST02698 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-063 | Hyderabad | South | 50 | Installation Scheduled | 2025-07-28 | 2025-08-20 | 2025-08-23 | 2025-09-19 |  | 0 | Met | Yashica Cherian | 84927
ST02699 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-064 | Hyderabad | South | 50 | Pending Acceptance | 2025-07-25 | 2025-09-02 | 2025-08-30 | 2025-09-14 | 2025-09-16 | 0 | Met | Logan Sami | 269356
ST02700 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-065 | Bengaluru | South | 200 | ROW In Progress | 2025-07-20 | 2025-09-10 |  | 2025-09-21 |  | 7 | Met | Priya Rastogi | 198716
ST02701 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-066 | Bengaluru | South | 50 | Live | 2025-08-05 | 2025-09-16 | 2025-09-11 | 2025-10-07 | 2025-10-11 | 0 | Met | Jai Kota | 244777
ST02702 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-067 | Bengaluru | South | 50 | Testing | 2025-07-28 | 2025-08-24 | 2025-08-29 | 2025-09-18 |  | 12 | Marginal | Ikbal Kothari | 175069
ST02703 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-068 | Bengaluru | South | 50 | Live | 2025-07-25 | 2025-09-10 | 2025-09-12 | 2025-09-25 | 2025-09-26 | 2 | Met | Niharika Sunder | 109495
ST02704 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-069 | Bengaluru | South | 200 | Live | 2025-07-26 | 2025-08-22 | 2025-08-30 | 2025-09-05 | 2025-09-04 | 8 | Marginal | Ranveer Yadav | 278774
ST02705 | PRJ033 | CL007 | Tata Motors | Kochi Site-070 | Kochi | South | 10 | Installation Scheduled | 2025-07-17 | 2025-08-06 | 2025-08-01 | 2025-08-30 |  | 6 | Met | Urvashi Ray | 55888
ST02706 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-071 | Hyderabad | South | 200 | ROW In Progress | 2025-07-23 | 2025-09-19 |  | 2025-10-16 |  | 6 | Met | Ikbal Kothari | 220019
ST02707 | PRJ033 | CL007 | Tata Motors | Kochi Site-072 | Kochi | South | 20 | Testing | 2025-07-27 | 2025-08-20 | 2025-08-24 | 2025-09-05 |  | 12 | Marginal | Nitesh Raghavan | 51285
ST02708 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-073 | Bengaluru | South | 50 | Live | 2025-07-31 | 2025-08-22 | 2025-08-20 | 2025-09-02 | 2025-09-01 | 0 | Met | Tanay Rattan | 237081
ST02709 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-074 | Bengaluru | South | 200 | Live | 2025-08-05 | 2025-09-07 | 2025-09-06 | 2025-10-02 | 2025-10-02 | 0 | Met | Ekapad Walia | 55030
ST02710 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-075 | Hyderabad | South | 100 | Live | 2025-07-25 | 2025-08-21 | 2025-08-28 | 2025-09-07 | 2025-09-07 | 7 | Met | Vansha Thakkar | 230524
ST02711 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-076 | Hyderabad | South | 50 | ROW In Progress | 2025-08-03 | 2025-09-14 |  | 2025-10-07 |  | 0 | Met | Diya Rattan | 218234
ST02712 | PRJ033 | CL007 | Tata Motors | Kochi Site-077 | Kochi | South | 20 | Installation Scheduled | 2025-07-25 | 2025-09-18 | 2025-09-18 | 2025-10-10 |  | 7 | Met | Diya Rattan | 48153
ST02713 | PRJ033 | CL007 | Tata Motors | Kochi Site-078 | Kochi | South | 50 | Pending Acceptance | 2025-08-04 | 2025-09-24 | 2025-09-24 | 2025-10-04 | 2025-10-04 | 0 | Met | Mohammed Gupta | 85458
ST02714 | PRJ033 | CL007 | Tata Motors | Chennai Site-079 | Chennai | South | 100 | Installation Done | 2025-07-24 | 2025-09-08 | 2025-09-12 | 2025-09-18 |  | 12 | Marginal | Alka Wable | 235618
ST02715 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-080 | Bengaluru | South | 200 | Pending Acceptance | 2025-07-20 | 2025-08-12 | 2025-08-19 | 2025-09-10 | 2025-09-21 | 7 | Met | Logan Sami | 72063
ST02716 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-081 | Hyderabad | South | 10 | Installation Scheduled | 2025-07-22 | 2025-09-18 | 2025-09-19 | 2025-10-11 |  | 7 | Met | Devansh Nigam | 146588
ST02717 | PRJ033 | CL007 | Tata Motors | Kochi Site-082 | Kochi | South | 100 | Installation Scheduled | 2025-07-14 | 2025-08-30 | 2025-09-06 | 2025-09-25 |  | 8 | Marginal | Mohammed Gupta | 142668
ST02718 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-083 | Bengaluru | South | 50 | Live | 2025-07-23 | 2025-09-12 | 2025-09-10 | 2025-09-24 | 2025-10-04 | 0 | Met | Ikbal Kothari | 158012
ST02719 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-084 | Bengaluru | South | 50 | Installation Done | 2025-08-01 | 2025-09-13 | 2025-09-20 | 2025-09-29 |  | 12 | Marginal | Raksha Varughese | 241737
ST02720 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-085 | Bengaluru | South | 20 | Installation Done | 2025-08-02 | 2025-09-19 | 2025-09-20 | 2025-10-17 |  | 12 | Marginal | Anamika Kanda | 233680
ST02721 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-086 | Bengaluru | South | 20 | ROW In Progress | 2025-07-29 | 2025-09-09 |  | 2025-10-02 |  | 5 | Met | Devika Rastogi | 246989
ST02722 | PRJ033 | CL007 | Tata Motors | Kochi Site-087 | Kochi | South | 100 | Live | 2025-07-28 | 2025-09-01 | 2025-08-27 | 2025-09-17 | 2025-09-17 | 0 | Met | Wahab Raval | 225227
ST02723 | PRJ033 | CL007 | Tata Motors | Kochi Site-088 | Kochi | South | 50 | ROW In Progress | 2025-08-07 | 2025-09-06 |  | 2025-09-29 |  | 1 | Met | Ekansh Balay | 188525
ST02724 | PRJ033 | CL007 | Tata Motors | Kochi Site-089 | Kochi | South | 20 | Live | 2025-07-13 | 2025-08-08 | 2025-08-07 | 2025-08-26 | 2025-08-24 | 0 | Met | Logan Sami | 259450
ST02725 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-090 | Hyderabad | South | 200 | Installation Scheduled | 2025-07-13 | 2025-08-05 | 2025-08-10 | 2025-08-24 |  | 0 | Met | Diya Rattan | 219537
ST02726 | PRJ033 | CL007 | Tata Motors | Chennai Site-091 | Chennai | South | 200 | Testing | 2025-07-28 | 2025-09-11 | 2025-09-20 | 2025-09-28 |  | 12 | Marginal | Dakshesh Trivedi | 80416
ST02727 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-092 | Hyderabad | South | 50 | Installation Done | 2025-07-25 | 2025-08-27 | 2025-08-22 | 2025-09-12 |  | 12 | Marginal | Raksha Varughese | 182927
ST02728 | PRJ033 | CL007 | Tata Motors | Chennai Site-093 | Chennai | South | 50 | Live | 2025-07-14 | 2025-08-04 | 2025-07-30 | 2025-09-01 | 2025-08-31 | 0 | Met | Alka Wable | 127017
ST02729 | PRJ033 | CL007 | Tata Motors | Chennai Site-094 | Chennai | South | 50 | Testing | 2025-08-01 | 2025-09-04 | 2025-08-30 | 2025-09-29 |  | 12 | Marginal | Devansh Rajan | 159735
ST02730 | PRJ033 | CL007 | Tata Motors | Kochi Site-095 | Kochi | South | 200 | Installation Scheduled | 2025-07-21 | 2025-09-05 | 2025-09-12 | 2025-09-19 |  | 8 | Marginal | Wahab Raval | 226714
ST02731 | PRJ033 | CL007 | Tata Motors | Chennai Site-096 | Chennai | South | 20 | Installation Done | 2025-07-29 | 2025-09-25 | 2025-10-02 | 2025-10-10 |  | 12 | Marginal | Unni Bhagat | 85685
ST02732 | PRJ033 | CL007 | Tata Motors | Kochi Site-097 | Kochi | South | 20 | Live | 2025-08-02 | 2025-09-16 | 2025-09-12 | 2025-09-26 | 2025-09-28 | 0 | Met | Raksha Varughese | 54792
ST02733 | PRJ033 | CL007 | Tata Motors | Chennai Site-098 | Chennai | South | 100 | Installation Scheduled | 2025-07-22 | 2025-08-13 | 2025-08-19 | 2025-09-04 |  | 7 | Met | Devansh Rajan | 93353
ST02734 | PRJ033 | CL007 | Tata Motors | Hyderabad Site-099 | Hyderabad | South | 50 | Survey Pending | 2025-07-24 | 2025-09-15 |  | 2025-10-13 |  | 0 | Met | Devansh Rajan | 180419
ST02735 | PRJ033 | CL007 | Tata Motors | Chennai Site-100 | Chennai | South | 100 | Live | 2025-07-29 | 2025-08-18 | 2025-08-23 | 2025-08-30 | 2025-09-09 | 5 | Met | Madhavi Lanka | 56388
ST02736 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-101 | Bengaluru | South | 50 | Live | 2025-07-19 | 2025-09-14 | 2025-09-13 | 2025-10-09 | 2025-10-15 | 0 | Met | Quincy Biswas | 211431
ST02737 | PRJ033 | CL007 | Tata Motors | Bengaluru Site-102 | Bengaluru | South | 50 | Testing | 2025-07-25 | 2025-08-26 | 2025-09-03 | 2025-09-07 |  | 12 | Marginal | Radhika Dugar | 169160
ST02738 | PRJ033 | CL007 | Tata Motors | Kochi Site-103 | Kochi | South | 20 | Testing | 2025-07-30 | 2025-09-06 | 2025-09-10 | 2025-09-25 |  | 12 | Marginal | Nihal Shere | 82944
ST02739 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-001 | Ahmedabad | West | 20 | Installation Done | 2025-10-30 | 2025-11-23 | 2025-12-02 | 2025-12-03 |  | 12 | Marginal | Girik Khalsa | 256844
ST02740 | PRJ034 | CL007 | Tata Motors | Mumbai Site-002 | Mumbai | West | 10 | Survey Pending | 2025-10-15 | 2025-12-03 |  | 2025-12-27 |  | 0 | Met | Bhavika Sampath | 172477
ST02741 | PRJ034 | CL007 | Tata Motors | Pune Site-003 | Pune | West | 20 | Live | 2025-10-24 | 2025-12-19 | 2025-12-23 | 2026-01-17 | 2026-01-20 | 4 | Met | Diya Rattan | 161431
ST02742 | PRJ034 | CL007 | Tata Motors | Mumbai Site-004 | Mumbai | West | 10 | ROW In Progress | 2025-10-16 | 2025-12-03 |  | 2025-12-16 |  | 6 | Met | Diya Rattan | 117884
ST02743 | PRJ034 | CL007 | Tata Motors | Mumbai Site-005 | Mumbai | West | 10 | ROW In Progress | 2025-10-16 | 2025-11-22 |  | 2025-12-11 |  | 4 | Met | Ikbal Kothari | 132605
ST02744 | PRJ034 | CL007 | Tata Motors | Surat Site-006 | Surat | West | 50 | Installation Done | 2025-10-21 | 2025-11-24 | 2025-11-26 | 2025-12-20 |  | 12 | Marginal | Niharika Sunder | 228849
ST02745 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-007 | Ahmedabad | West | 10 | Installation Done | 2025-10-19 | 2025-11-22 | 2025-11-20 | 2025-12-17 |  | 12 | Marginal | Kabir Soman | 235550
ST02746 | PRJ034 | CL007 | Tata Motors | Pune Site-008 | Pune | West | 200 | Installation Done | 2025-10-14 | 2025-11-06 | 2025-11-10 | 2025-12-05 |  | 12 | Marginal | Isaac Patil | 145853
ST02747 | PRJ034 | CL007 | Tata Motors | Surat Site-009 | Surat | West | 100 | Pending Acceptance | 2025-10-20 | 2025-12-03 | 2025-12-01 | 2026-01-01 | 2026-01-13 | 0 | Met | Devika Rastogi | 72201
ST02748 | PRJ034 | CL007 | Tata Motors | Surat Site-010 | Surat | West | 200 | Installation Scheduled | 2025-11-01 | 2025-12-10 | 2025-12-18 | 2025-12-24 |  | 4 | Met | Wahab Raval | 233129
ST02749 | PRJ034 | CL007 | Tata Motors | Pune Site-011 | Pune | West | 50 | Pending Acceptance | 2025-10-20 | 2025-12-14 | 2025-12-20 | 2026-01-09 | 2026-01-18 | 6 | Met | Raksha Varughese | 264045
ST02750 | PRJ034 | CL007 | Tata Motors | Pune Site-012 | Pune | West | 10 | Live | 2025-11-04 | 2025-12-18 | 2025-12-27 | 2025-12-30 | 2026-01-04 | 9 | Marginal | Devika Rastogi | 116691
ST02751 | PRJ034 | CL007 | Tata Motors | Pune Site-013 | Pune | West | 100 | Live | 2025-11-07 | 2025-12-27 | 2026-01-03 | 2026-01-20 | 2026-01-18 | 7 | Met | Ekbal Garg | 140758
ST02752 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-014 | Ahmedabad | West | 100 | Testing | 2025-10-17 | 2025-12-06 | 2025-12-08 | 2025-12-26 |  | 12 | Marginal | Harini Choudhury | 76048
ST02753 | PRJ034 | CL007 | Tata Motors | Mumbai Site-015 | Mumbai | West | 200 | Installation Done | 2025-10-24 | 2025-11-14 | 2025-11-21 | 2025-12-12 |  | 12 | Marginal | Wriddhish Bhardwaj | 274876
ST02754 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-016 | Ahmedabad | West | 10 | Live | 2025-10-26 | 2025-12-04 | 2025-12-11 | 2025-12-20 | 2025-12-31 | 7 | Met | Devansh Rajan | 122586
ST02755 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-017 | Ahmedabad | West | 20 | Installation Done | 2025-10-14 | 2025-11-17 | 2025-11-19 | 2025-12-05 |  | 12 | Marginal | Vansha Thakkar | 227350
ST02756 | PRJ034 | CL007 | Tata Motors | Mumbai Site-018 | Mumbai | West | 20 | Live | 2025-10-26 | 2025-12-10 | 2025-12-09 | 2025-12-31 | 2026-01-07 | 0 | Met | Tara Dhar | 131315
ST02757 | PRJ034 | CL007 | Tata Motors | Mumbai Site-019 | Mumbai | West | 10 | Testing | 2025-10-19 | 2025-12-02 | 2025-11-28 | 2025-12-12 |  | 12 | Marginal | Theodore Devi | 250461
ST02758 | PRJ034 | CL007 | Tata Motors | Mumbai Site-020 | Mumbai | West | 10 | Live | 2025-11-06 | 2025-11-29 | 2025-11-26 | 2025-12-19 | 2025-12-29 | 0 | Met | Tanay Rattan | 63458
ST02759 | PRJ034 | CL007 | Tata Motors | Surat Site-021 | Surat | West | 10 | ROW In Progress | 2025-10-22 | 2025-11-27 |  | 2025-12-26 |  | 8 | Marginal | Radhika Dugar | 67995
ST02760 | PRJ034 | CL007 | Tata Motors | Pune Site-022 | Pune | West | 20 | Survey Pending | 2025-11-04 | 2025-12-29 |  | 2026-01-24 |  | 2 | Met | Arya Sunder | 219590
ST02761 | PRJ034 | CL007 | Tata Motors | Surat Site-023 | Surat | West | 20 | Live | 2025-11-02 | 2025-11-25 | 2025-12-02 | 2025-12-20 | 2025-12-21 | 7 | Met | Kabir Soman | 64287
ST02762 | PRJ034 | CL007 | Tata Motors | Mumbai Site-024 | Mumbai | West | 20 | Installation Scheduled | 2025-10-22 | 2025-12-14 | 2025-12-12 | 2026-01-08 |  | 7 | Met | Niharika Sunder | 269415
ST02763 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-025 | Ahmedabad | West | 20 | Pending Acceptance | 2025-11-06 | 2025-12-22 | 2025-12-19 | 2026-01-20 | 2026-01-21 | 0 | Met | Priya Rastogi | 247401
ST02764 | PRJ034 | CL007 | Tata Motors | Pune Site-026 | Pune | West | 50 | Live | 2025-10-14 | 2025-11-29 | 2025-11-30 | 2025-12-11 | 2025-12-20 | 1 | Met | Advay Contractor | 171010
ST02765 | PRJ034 | CL007 | Tata Motors | Surat Site-027 | Surat | West | 20 | Survey Pending | 2025-11-03 | 2026-01-02 |  | 2026-01-19 |  | 0 | Met | Wriddhish Bhardwaj | 153386
ST02766 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-028 | Ahmedabad | West | 100 | Live | 2025-11-05 | 2026-01-04 | 2026-01-12 | 2026-02-02 | 2026-02-06 | 8 | Marginal | Yatin Baral | 94617
ST02767 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-029 | Ahmedabad | West | 100 | Pending Acceptance | 2025-11-02 | 2025-12-29 | 2025-12-26 | 2026-01-21 | 2026-02-01 | 0 | Met | Ekavir Bhargava | 48919
ST02768 | PRJ034 | CL007 | Tata Motors | Pune Site-030 | Pune | West | 20 | ROW In Progress | 2025-11-08 | 2026-01-03 |  | 2026-01-15 |  | 3 | Met | Unni Bhagat | 81677
ST02769 | PRJ034 | CL007 | Tata Motors | Pune Site-031 | Pune | West | 100 | Live | 2025-11-03 | 2025-12-18 | 2025-12-27 | 2025-12-31 | 2026-01-02 | 9 | Marginal | Devika Rastogi | 165873
ST02770 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-032 | Ahmedabad | West | 20 | Testing | 2025-11-02 | 2025-12-28 | 2026-01-02 | 2026-01-12 |  | 12 | Marginal | Urvashi Ray | 93499
ST02771 | PRJ034 | CL007 | Tata Motors | Surat Site-033 | Surat | West | 200 | Live | 2025-10-22 | 2025-11-30 | 2025-12-03 | 2025-12-17 | 2025-12-27 | 3 | Met | Madhavi Lanka | 177984
ST02772 | PRJ034 | CL007 | Tata Motors | Mumbai Site-034 | Mumbai | West | 10 | Live | 2025-10-17 | 2025-11-10 | 2025-11-14 | 2025-11-27 | 2025-12-01 | 4 | Met | Nitesh Raghavan | 112503
ST02773 | PRJ034 | CL007 | Tata Motors | Mumbai Site-035 | Mumbai | West | 100 | Testing | 2025-10-30 | 2025-11-20 | 2025-11-25 | 2025-12-17 |  | 12 | Marginal | Dakshesh Trivedi | 67327
ST02774 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-036 | Ahmedabad | West | 20 | Installation Scheduled | 2025-10-25 | 2025-12-22 | 2025-12-18 | 2026-01-21 |  | 6 | Met | Dakshesh Trivedi | 184105
ST02775 | PRJ034 | CL007 | Tata Motors | Surat Site-037 | Surat | West | 20 | Pending Acceptance | 2025-10-15 | 2025-11-14 | 2025-11-20 | 2025-12-12 | 2025-12-12 | 6 | Met | Anamika Kanda | 231971
ST02776 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-038 | Ahmedabad | West | 20 | Pending Acceptance | 2025-10-21 | 2025-12-09 | 2025-12-09 | 2025-12-22 | 2026-01-01 | 0 | Met | Chandresh Zachariah | 148617
ST02777 | PRJ034 | CL007 | Tata Motors | Mumbai Site-039 | Mumbai | West | 10 | Installation Scheduled | 2025-10-20 | 2025-11-29 | 2025-12-03 | 2025-12-11 |  | 8 | Marginal | Ekiya Suresh | 208181
ST02778 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-040 | Ahmedabad | West | 100 | Installation Scheduled | 2025-11-02 | 2025-12-29 | 2026-01-08 | 2026-01-22 |  | 3 | Met | Farhan Chada | 202717
ST02779 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-041 | Ahmedabad | West | 50 | Pending Acceptance | 2025-11-01 | 2025-12-11 | 2025-12-17 | 2025-12-23 | 2025-12-24 | 6 | Met | Mohammed Gupta | 115630
ST02780 | PRJ034 | CL007 | Tata Motors | Mumbai Site-042 | Mumbai | West | 10 | Survey Pending | 2025-10-29 | 2025-12-01 |  | 2025-12-23 |  | 7 | Met | Kabir Soman | 231249
ST02781 | PRJ034 | CL007 | Tata Motors | Surat Site-043 | Surat | West | 100 | ROW In Progress | 2025-10-25 | 2025-12-09 |  | 2026-01-08 |  | 7 | Met | Devansh Rajan | 72108
ST02782 | PRJ034 | CL007 | Tata Motors | Pune Site-044 | Pune | West | 20 | Installation Done | 2025-10-31 | 2025-12-08 | 2025-12-08 | 2025-12-24 |  | 12 | Marginal | Daksh Karnik | 253793
ST02783 | PRJ034 | CL007 | Tata Motors | Mumbai Site-045 | Mumbai | West | 200 | Testing | 2025-10-25 | 2025-12-09 | 2025-12-11 | 2025-12-20 |  | 12 | Marginal | Aarush Lall | 196528
ST02784 | PRJ034 | CL007 | Tata Motors | Pune Site-046 | Pune | West | 100 | Testing | 2025-11-03 | 2025-12-28 | 2025-12-27 | 2026-01-23 |  | 12 | Marginal | Alka Wable | 264823
ST02785 | PRJ034 | CL007 | Tata Motors | Pune Site-047 | Pune | West | 100 | Live | 2025-10-15 | 2025-12-04 | 2025-12-05 | 2025-12-16 | 2025-12-18 | 1 | Met | Siddharth Zacharia | 232765
ST02786 | PRJ034 | CL007 | Tata Motors | Surat Site-048 | Surat | West | 10 | Pending Acceptance | 2025-11-07 | 2025-12-15 | 2025-12-21 | 2025-12-29 | 2025-12-31 | 6 | Met | Vansha Thakkar | 80057
ST02787 | PRJ034 | CL007 | Tata Motors | Mumbai Site-049 | Mumbai | West | 20 | Survey Pending | 2025-10-28 | 2025-11-18 |  | 2025-12-15 |  | 4 | Met | Vansha Thakkar | 111423
ST02788 | PRJ034 | CL007 | Tata Motors | Mumbai Site-050 | Mumbai | West | 100 | Installation Done | 2025-11-05 | 2025-12-05 | 2025-12-15 | 2026-01-03 |  | 12 | Marginal | Ekapad Walia | 209949
ST02789 | PRJ034 | CL007 | Tata Motors | Surat Site-051 | Surat | West | 10 | Installation Scheduled | 2025-10-19 | 2025-12-17 | 2025-12-22 | 2026-01-07 |  | 5 | Met | Anamika Kanda | 49802
ST02790 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-052 | Ahmedabad | West | 200 | Live | 2025-10-15 | 2025-12-06 | 2025-12-04 | 2026-01-04 | 2026-01-10 | 0 | Met | Jai Kota | 231123
ST02791 | PRJ034 | CL007 | Tata Motors | Pune Site-053 | Pune | West | 20 | ROW In Progress | 2025-10-19 | 2025-11-21 |  | 2025-12-02 |  | 0 | Met | Tanay Rattan | 47814
ST02792 | PRJ034 | CL007 | Tata Motors | Surat Site-054 | Surat | West | 200 | ROW In Progress | 2025-10-21 | 2025-11-30 |  | 2025-12-11 |  | 2 | Met | Siddharth Zacharia | 45739
ST02793 | PRJ034 | CL007 | Tata Motors | Pune Site-055 | Pune | West | 50 | Live | 2025-11-04 | 2025-12-03 | 2025-12-06 | 2025-12-19 | 2025-12-30 | 3 | Met | Ekapad Walia | 195553
ST02794 | PRJ034 | CL007 | Tata Motors | Mumbai Site-056 | Mumbai | West | 200 | Pending Acceptance | 2025-11-07 | 2026-01-02 | 2026-01-01 | 2026-01-29 | 2026-01-26 | 0 | Met | Upadhriti Wadhwa | 273379
ST02795 | PRJ034 | CL007 | Tata Motors | Surat Site-057 | Surat | West | 200 | Live | 2025-10-21 | 2025-11-17 | 2025-11-25 | 2025-12-10 | 2025-12-19 | 8 | Marginal | Vansha Thakkar | 235548
ST02796 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-058 | Ahmedabad | West | 50 | Survey Pending | 2025-10-20 | 2025-11-09 |  | 2025-11-27 |  | 5 | Met | Jai Kota | 61849
ST02797 | PRJ034 | CL007 | Tata Motors | Mumbai Site-059 | Mumbai | West | 100 | Installation Done | 2025-10-27 | 2025-12-11 | 2025-12-14 | 2026-01-08 |  | 12 | Marginal | Ekbal Garg | 53028
ST02798 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-060 | Ahmedabad | West | 10 | Installation Scheduled | 2025-11-06 | 2025-12-17 | 2025-12-12 | 2025-12-30 |  | 5 | Met | Quincy Biswas | 151749
ST02799 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-061 | Ahmedabad | West | 200 | ROW In Progress | 2025-10-27 | 2025-11-26 |  | 2025-12-22 |  | 0 | Met | Harini Choudhury | 122520
ST02800 | PRJ034 | CL007 | Tata Motors | Mumbai Site-062 | Mumbai | West | 200 | ROW In Progress | 2025-10-14 | 2025-11-23 |  | 2025-12-03 |  | 6 | Met | Tanay Rattan | 70877
ST02801 | PRJ034 | CL007 | Tata Motors | Pune Site-063 | Pune | West | 20 | ROW In Progress | 2025-10-19 | 2025-11-29 |  | 2025-12-20 |  | 2 | Met | Yashica Issac | 79906
ST02802 | PRJ034 | CL007 | Tata Motors | Mumbai Site-064 | Mumbai | West | 50 | Installation Scheduled | 2025-10-31 | 2025-12-02 | 2025-12-11 | 2026-01-01 |  | 7 | Met | Devika Rastogi | 136708
ST02803 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-065 | Ahmedabad | West | 50 | Live | 2025-11-05 | 2025-12-14 | 2025-12-24 | 2026-01-05 | 2026-01-07 | 10 | Marginal | Farhan Chada | 201189
ST02804 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-066 | Ahmedabad | West | 20 | Survey Pending | 2025-10-17 | 2025-11-11 |  | 2025-11-24 |  | 5 | Met | Girindra Chatterjee | 128713
ST02805 | PRJ034 | CL007 | Tata Motors | Surat Site-067 | Surat | West | 20 | Live | 2025-10-28 | 2025-12-15 | 2025-12-15 | 2026-01-06 | 2026-01-04 | 0 | Met | Theodore Devi | 161691
ST02806 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-068 | Ahmedabad | West | 50 | Testing | 2025-10-14 | 2025-11-18 | 2025-11-13 | 2025-12-06 |  | 12 | Marginal | Yatin Baral | 46833
ST02807 | PRJ034 | CL007 | Tata Motors | Surat Site-069 | Surat | West | 20 | ROW In Progress | 2025-10-31 | 2025-12-17 |  | 2025-12-29 |  | 4 | Met | Ekiya Suresh | 204685
ST02808 | PRJ034 | CL007 | Tata Motors | Pune Site-070 | Pune | West | 200 | Installation Done | 2025-11-05 | 2025-12-16 | 2025-12-20 | 2026-01-06 |  | 12 | Marginal | Isaac Patil | 56847
ST02809 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-071 | Ahmedabad | West | 100 | Live | 2025-10-25 | 2025-12-20 | 2025-12-28 | 2026-01-13 | 2026-01-20 | 8 | Marginal | Wahab Raval | 202177
ST02810 | PRJ034 | CL007 | Tata Motors | Mumbai Site-072 | Mumbai | West | 20 | ROW In Progress | 2025-10-20 | 2025-12-07 |  | 2026-01-04 |  | 8 | Marginal | Anamika Kanda | 230766
ST02811 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-073 | Ahmedabad | West | 50 | Live | 2025-10-28 | 2025-12-13 | 2025-12-12 | 2026-01-06 | 2026-01-11 | 0 | Met | Devansh Rajan | 68006
ST02812 | PRJ034 | CL007 | Tata Motors | Surat Site-074 | Surat | West | 10 | Survey Pending | 2025-11-01 | 2025-12-13 |  | 2026-01-08 |  | 7 | Met | Devansh Rajan | 275213
ST02813 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-075 | Ahmedabad | West | 100 | Live | 2025-10-19 | 2025-11-19 | 2025-11-17 | 2025-12-05 | 2025-12-08 | 0 | Met | Arya Shere | 60935
ST02814 | PRJ034 | CL007 | Tata Motors | Mumbai Site-076 | Mumbai | West | 20 | Pending Acceptance | 2025-10-20 | 2025-11-26 | 2025-12-05 | 2025-12-19 | 2025-12-18 | 9 | Marginal | Yatin Baral | 211623
ST02815 | PRJ034 | CL007 | Tata Motors | Pune Site-077 | Pune | West | 10 | Survey Pending | 2025-10-29 | 2025-12-05 |  | 2025-12-27 |  | 1 | Met | Raksha Varughese | 236502
ST02816 | PRJ034 | CL007 | Tata Motors | Surat Site-078 | Surat | West | 50 | Testing | 2025-11-02 | 2025-11-30 | 2025-12-09 | 2025-12-13 |  | 12 | Marginal | Chandresh Zachariah | 57750
ST02817 | PRJ034 | CL007 | Tata Motors | Pune Site-079 | Pune | West | 50 | Installation Scheduled | 2025-11-04 | 2025-12-25 | 2025-12-31 | 2026-01-08 |  | 8 | Marginal | Chandresh Zachariah | 179356
ST02818 | PRJ034 | CL007 | Tata Motors | Mumbai Site-080 | Mumbai | West | 100 | Testing | 2025-11-07 | 2025-12-13 | 2025-12-15 | 2026-01-10 |  | 12 | Marginal | Chandresh Zachariah | 227629
ST02819 | PRJ034 | CL007 | Tata Motors | Pune Site-081 | Pune | West | 100 | Survey Pending | 2025-11-01 | 2025-11-21 |  | 2025-12-21 |  | 0 | Met | Devika Rastogi | 175139
ST02820 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-082 | Ahmedabad | West | 100 | Testing | 2025-11-02 | 2025-12-11 | 2025-12-14 | 2025-12-31 |  | 12 | Marginal | Jai Kota | 272946
ST02821 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-083 | Ahmedabad | West | 100 | Installation Scheduled | 2025-10-15 | 2025-12-02 | 2025-12-09 | 2025-12-30 |  | 2 | Met | Radhika Dugar | 146083
ST02822 | PRJ034 | CL007 | Tata Motors | Ahmedabad Site-084 | Ahmedabad | West | 100 | Installation Scheduled | 2025-10-21 | 2025-11-29 | 2025-12-08 | 2025-12-20 |  | 1 | Met | Daksh Karnik | 254802
ST02823 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-001 | Kolkata | East | 100 | Installation Done | 2026-03-12 | 2026-05-09 | 2026-05-05 | 2026-06-01 |  | 12 | Marginal | Daksh Karnik | 234085
ST02824 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-002 | Kolkata | East | 20 | Pending Acceptance | 2026-03-19 | 2026-04-14 | 2026-04-14 | 2026-04-25 | 2026-04-23 | 0 | Met | Ekapad Walia | 111283
ST02825 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-003 | Bhubaneswar | East | 10 | Testing | 2026-03-12 | 2026-04-28 | 2026-05-08 | 2026-05-13 |  | 12 | Marginal | Arya Shere | 92794
ST02826 | PRJ035 | CL008 | Reliance Retail | Patna Site-004 | Patna | East | 200 | Survey Pending | 2026-03-18 | 2026-04-19 |  | 2026-05-06 |  | 3 | Met | Priya Rastogi | 239152
ST02827 | PRJ035 | CL008 | Reliance Retail | Patna Site-005 | Patna | East | 10 | ROW In Progress | 2026-03-10 | 2026-05-08 |  | 2026-05-22 |  | 1 | Met | Unni Bhagat | 103807
ST02828 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-006 | Kolkata | East | 10 | Installation Done | 2026-03-03 | 2026-04-03 | 2026-04-11 | 2026-04-14 |  | 12 | Marginal | Harini Choudhury | 276856
ST02829 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-007 | Kolkata | East | 20 | Installation Done | 2026-03-18 | 2026-05-06 | 2026-05-15 | 2026-05-24 |  | 12 | Marginal | Teerth Bhardwaj | 249316
ST02830 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-008 | Kolkata | East | 200 | Installation Scheduled | 2026-03-17 | 2026-05-11 | 2026-05-16 | 2026-06-05 |  | 8 | Marginal | Bhavika Sampath | 251906
ST02831 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-009 | Kolkata | East | 20 | Live | 2026-03-02 | 2026-03-25 | 2026-04-01 | 2026-04-10 | 2026-04-11 | 7 | Met | Daksh Karnik | 65748
ST02832 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-010 | Kolkata | East | 50 | Installation Done | 2026-03-16 | 2026-05-10 | 2026-05-06 | 2026-05-29 |  | 12 | Marginal | Tanay Rattan | 229467
ST02833 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-011 | Bhubaneswar | East | 100 | Installation Done | 2026-03-16 | 2026-04-25 | 2026-04-24 | 2026-05-13 |  | 12 | Marginal | Niharika Sunder | 48444
ST02834 | PRJ035 | CL008 | Reliance Retail | Patna Site-012 | Patna | East | 100 | Installation Done | 2026-03-20 | 2026-04-10 | 2026-04-18 | 2026-04-28 |  | 12 | Marginal | Yashica Cherian | 227130
ST02835 | PRJ035 | CL008 | Reliance Retail | Patna Site-013 | Patna | East | 100 | Installation Scheduled | 2026-03-08 | 2026-04-08 | 2026-04-14 | 2026-05-02 |  | 3 | Met | Dipta Bhandari | 227157
ST02836 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-014 | Bhubaneswar | East | 100 | Installation Done | 2026-03-15 | 2026-05-08 | 2026-05-11 | 2026-05-18 |  | 12 | Marginal | Ekbal Garg | 257458
ST02837 | PRJ035 | CL008 | Reliance Retail | Patna Site-015 | Patna | East | 100 | Live | 2026-03-06 | 2026-04-21 | 2026-04-26 | 2026-05-16 | 2026-05-27 | 5 | Met | Simon Tata | 158764
ST02838 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-016 | Kolkata | East | 20 | ROW In Progress | 2026-03-17 | 2026-05-08 |  | 2026-06-03 |  | 7 | Met | Kevin Solanki | 85648
ST02839 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-017 | Bhubaneswar | East | 20 | Installation Done | 2026-03-23 | 2026-05-20 | 2026-05-19 | 2026-06-15 |  | 12 | Marginal | Girik Khalsa | 225097
ST02840 | PRJ035 | CL008 | Reliance Retail | Patna Site-018 | Patna | East | 100 | Survey Pending | 2026-03-18 | 2026-05-01 |  | 2026-05-19 |  | 1 | Met | Daksh Karnik | 45343
ST02841 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-019 | Bhubaneswar | East | 100 | ROW In Progress | 2026-03-13 | 2026-04-06 |  | 2026-05-06 |  | 8 | Marginal | Diya Rattan | 132736
ST02842 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-020 | Bhubaneswar | East | 100 | Live | 2026-03-10 | 2026-05-03 | 2026-04-28 | 2026-05-19 | 2026-05-18 | 0 | Met | Arya Shere | 125114
ST02843 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-021 | Bhubaneswar | East | 200 | Pending Acceptance | 2026-03-16 | 2026-04-28 | 2026-04-25 | 2026-05-12 | 2026-05-23 | 0 | Met | Wriddhish Bhardwaj | 77298
ST02844 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-022 | Kolkata | East | 50 | Live | 2026-03-06 | 2026-04-03 | 2026-04-09 | 2026-04-20 | 2026-04-28 | 6 | Met | Theodore Devi | 264795
ST02845 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-023 | Bhubaneswar | East | 200 | Live | 2026-02-28 | 2026-04-25 | 2026-04-22 | 2026-05-24 | 2026-05-29 | 0 | Met | Anamika Kanda | 181917
ST02846 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-024 | Bhubaneswar | East | 200 | Survey Pending | 2026-03-20 | 2026-04-16 |  | 2026-05-11 |  | 0 | Met | Girik Khalsa | 172375
ST02847 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-025 | Kolkata | East | 10 | Installation Done | 2026-02-27 | 2026-04-18 | 2026-04-27 | 2026-05-18 |  | 12 | Marginal | Tara Dhar | 168547
ST02848 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-026 | Bhubaneswar | East | 200 | Survey Pending | 2026-03-05 | 2026-04-08 |  | 2026-05-01 |  | 8 | Marginal | Logan Sami | 236891
ST02849 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-027 | Bhubaneswar | East | 10 | Testing | 2026-03-12 | 2026-04-10 | 2026-04-14 | 2026-05-03 |  | 12 | Marginal | Simon Tata | 130858
ST02850 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-028 | Kolkata | East | 10 | ROW In Progress | 2026-03-16 | 2026-04-05 |  | 2026-04-16 |  | 7 | Met | Devansh Rajan | 175118
ST02851 | PRJ035 | CL008 | Reliance Retail | Patna Site-029 | Patna | East | 20 | Live | 2026-02-26 | 2026-03-29 | 2026-03-24 | 2026-04-19 | 2026-04-17 | 0 | Met | Darsh Rau | 219358
ST02852 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-030 | Bhubaneswar | East | 20 | Testing | 2026-03-03 | 2026-05-02 | 2026-05-04 | 2026-05-31 |  | 12 | Marginal | Diya Rattan | 66471
ST02853 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-031 | Kolkata | East | 50 | Pending Acceptance | 2026-03-03 | 2026-05-01 | 2026-05-11 | 2026-05-22 | 2026-06-03 | 10 | Marginal | Teerth Bhardwaj | 221800
ST02854 | PRJ035 | CL008 | Reliance Retail | Patna Site-032 | Patna | East | 50 | Live | 2026-03-08 | 2026-05-07 | 2026-05-09 | 2026-06-05 | 2026-06-15 | 2 | Met | Mohammed Gupta | 241127
ST02855 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-033 | Bhubaneswar | East | 200 | Installation Scheduled | 2026-03-22 | 2026-04-21 | 2026-04-27 | 2026-05-05 |  | 6 | Met | Devansh Nigam | 220360
ST02856 | PRJ035 | CL008 | Reliance Retail | Patna Site-034 | Patna | East | 10 | ROW In Progress | 2026-03-07 | 2026-04-01 |  | 2026-04-23 |  | 4 | Met | Darsh Rau | 249094
ST02857 | PRJ035 | CL008 | Reliance Retail | Patna Site-035 | Patna | East | 20 | Installation Scheduled | 2026-03-07 | 2026-03-29 | 2026-04-04 | 2026-04-10 |  | 3 | Met | Teerth Bhardwaj | 249728
ST02858 | PRJ035 | CL008 | Reliance Retail | Patna Site-036 | Patna | East | 100 | Live | 2026-03-12 | 2026-04-28 | 2026-05-05 | 2026-05-26 | 2026-06-06 | 7 | Met | Upadhriti Wadhwa | 239915
ST02859 | PRJ035 | CL008 | Reliance Retail | Patna Site-037 | Patna | East | 10 | Live | 2026-03-22 | 2026-04-11 | 2026-04-16 | 2026-05-01 | 2026-05-13 | 5 | Met | Teerth Bhardwaj | 123952
ST02860 | PRJ035 | CL008 | Reliance Retail | Patna Site-038 | Patna | East | 200 | Live | 2026-03-23 | 2026-05-05 | 2026-05-09 | 2026-06-03 | 2026-06-12 | 4 | Met | Theodore Devi | 117098
ST02861 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-039 | Bhubaneswar | East | 50 | Testing | 2026-02-27 | 2026-04-20 | 2026-04-16 | 2026-05-06 |  | 12 | Marginal | Yatin Baral | 150058
ST02862 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-040 | Kolkata | East | 50 | Installation Scheduled | 2026-02-27 | 2026-04-10 | 2026-04-19 | 2026-04-28 |  | 4 | Met | Daksh Karnik | 193094
ST02863 | PRJ035 | CL008 | Reliance Retail | Patna Site-041 | Patna | East | 50 | Testing | 2026-03-11 | 2026-04-13 | 2026-04-13 | 2026-05-01 |  | 12 | Marginal | Raksha Varughese | 128188
ST02864 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-042 | Kolkata | East | 10 | Pending Acceptance | 2026-03-21 | 2026-05-17 | 2026-05-15 | 2026-05-30 | 2026-05-30 | 0 | Met | Tara Dhar | 228798
ST02865 | PRJ035 | CL008 | Reliance Retail | Patna Site-043 | Patna | East | 100 | Installation Done | 2026-03-20 | 2026-04-13 | 2026-04-16 | 2026-05-06 |  | 12 | Marginal | Girindra Chatterjee | 201356
ST02866 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-044 | Kolkata | East | 10 | Live | 2026-02-28 | 2026-04-04 | 2026-04-10 | 2026-05-02 | 2026-05-12 | 6 | Met | Yatin Baral | 219590
ST02867 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-045 | Kolkata | East | 200 | Survey Pending | 2026-03-19 | 2026-05-07 |  | 2026-05-23 |  | 4 | Met | Nihal Shere | 275053
ST02868 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-046 | Kolkata | East | 200 | Live | 2026-03-02 | 2026-04-17 | 2026-04-20 | 2026-05-01 | 2026-05-09 | 3 | Met | Wahab Raval | 218722
ST02869 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-047 | Kolkata | East | 200 | Survey Pending | 2026-03-08 | 2026-04-15 |  | 2026-05-12 |  | 2 | Met | Dakshesh Trivedi | 252535
ST02870 | PRJ035 | CL008 | Reliance Retail | Patna Site-048 | Patna | East | 100 | Live | 2026-03-20 | 2026-05-18 | 2026-05-17 | 2026-05-30 | 2026-06-05 | 0 | Met | Jai Kota | 204606
ST02871 | PRJ035 | CL008 | Reliance Retail | Patna Site-049 | Patna | East | 50 | Testing | 2026-03-12 | 2026-04-20 | 2026-04-27 | 2026-04-30 |  | 12 | Marginal | Ekiya Suresh | 198059
ST02872 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-050 | Kolkata | East | 10 | Pending Acceptance | 2026-03-01 | 2026-04-20 | 2026-04-23 | 2026-05-15 | 2026-05-17 | 3 | Met | Devansh Nigam | 157664
ST02873 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-051 | Kolkata | East | 50 | Installation Done | 2026-03-13 | 2026-04-23 | 2026-04-19 | 2026-05-11 |  | 12 | Marginal | Aarush Lall | 207921
ST02874 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-052 | Kolkata | East | 200 | Installation Done | 2026-03-11 | 2026-05-09 | 2026-05-18 | 2026-06-06 |  | 12 | Marginal | Dipta Bhandari | 168374
ST02875 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-053 | Bhubaneswar | East | 10 | Installation Scheduled | 2026-03-08 | 2026-04-29 | 2026-05-02 | 2026-05-23 |  | 4 | Met | Devika Rastogi | 117780
ST02876 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-054 | Kolkata | East | 100 | ROW In Progress | 2026-03-17 | 2026-04-14 |  | 2026-05-12 |  | 3 | Met | Ekbal Garg | 226208
ST02877 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-055 | Bhubaneswar | East | 200 | Pending Acceptance | 2026-03-11 | 2026-04-11 | 2026-04-20 | 2026-05-01 | 2026-04-30 | 9 | Marginal | Ekapad Walia | 110842
ST02878 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-056 | Bhubaneswar | East | 50 | Live | 2026-03-14 | 2026-05-11 | 2026-05-06 | 2026-05-24 | 2026-05-25 | 0 | Met | Ekansh Balay | 251471
ST02879 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-057 | Bhubaneswar | East | 10 | Installation Done | 2026-03-05 | 2026-04-21 | 2026-04-27 | 2026-05-14 |  | 12 | Marginal | Liam Koshy | 139408
ST02880 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-058 | Bhubaneswar | East | 10 | Testing | 2026-03-10 | 2026-04-07 | 2026-04-06 | 2026-04-24 |  | 12 | Marginal | Dipta Bhandari | 52398
ST02881 | PRJ035 | CL008 | Reliance Retail | Patna Site-059 | Patna | East | 20 | Installation Done | 2026-03-17 | 2026-04-22 | 2026-04-17 | 2026-05-12 |  | 12 | Marginal | Devansh Rajan | 144291
ST02882 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-060 | Kolkata | East | 20 | ROW In Progress | 2026-03-02 | 2026-04-19 |  | 2026-05-19 |  | 4 | Met | Raksha Varughese | 58856
ST02883 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-061 | Kolkata | East | 20 | Live | 2026-03-19 | 2026-04-19 | 2026-04-29 | 2026-05-01 | 2026-05-11 | 10 | Marginal | Ekansh Balay | 123184
ST02884 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-062 | Bhubaneswar | East | 20 | Live | 2026-03-09 | 2026-04-24 | 2026-04-25 | 2026-05-06 | 2026-05-06 | 1 | Met | Priya Rastogi | 99973
ST02885 | PRJ035 | CL008 | Reliance Retail | Patna Site-063 | Patna | East | 200 | Live | 2026-03-13 | 2026-05-06 | 2026-05-06 | 2026-06-02 | 2026-06-14 | 0 | Met | Simon Tata | 148571
ST02886 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-064 | Bhubaneswar | East | 50 | Survey Pending | 2026-03-20 | 2026-04-28 |  | 2026-05-19 |  | 8 | Marginal | Girik Khalsa | 143751
ST02887 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-065 | Kolkata | East | 10 | Installation Done | 2026-03-08 | 2026-04-15 | 2026-04-12 | 2026-05-11 |  | 12 | Marginal | Kashvi Edwin | 209751
ST02888 | PRJ035 | CL008 | Reliance Retail | Patna Site-066 | Patna | East | 200 | Live | 2026-03-03 | 2026-04-13 | 2026-04-12 | 2026-04-25 | 2026-04-27 | 0 | Met | Arya Shere | 158453
ST02889 | PRJ035 | CL008 | Reliance Retail | Patna Site-067 | Patna | East | 200 | Survey Pending | 2026-03-08 | 2026-05-06 |  | 2026-05-24 |  | 6 | Met | Kevin Solanki | 91033
ST02890 | PRJ035 | CL008 | Reliance Retail | Patna Site-068 | Patna | East | 10 | Installation Done | 2026-03-03 | 2026-04-26 | 2026-04-30 | 2026-05-20 |  | 12 | Marginal | Irya Sampath | 85400
ST02891 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-069 | Kolkata | East | 200 | Installation Scheduled | 2026-03-19 | 2026-04-22 | 2026-04-22 | 2026-05-21 |  | 8 | Marginal | Teerth Bhardwaj | 68899
ST02892 | PRJ035 | CL008 | Reliance Retail | Patna Site-070 | Patna | East | 100 | Live | 2026-03-03 | 2026-04-05 | 2026-04-05 | 2026-04-15 | 2026-04-18 | 0 | Met | Arya Shere | 182089
ST02893 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-071 | Bhubaneswar | East | 20 | Pending Acceptance | 2026-03-02 | 2026-04-19 | 2026-04-29 | 2026-05-16 | 2026-05-25 | 10 | Marginal | Nitesh Raghavan | 186971
ST02894 | PRJ035 | CL008 | Reliance Retail | Patna Site-072 | Patna | East | 100 | Live | 2026-03-08 | 2026-04-08 | 2026-04-18 | 2026-04-22 | 2026-05-03 | 10 | Marginal | Daksh Karnik | 234366
ST02895 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-073 | Kolkata | East | 20 | ROW In Progress | 2026-03-14 | 2026-05-03 |  | 2026-05-27 |  | 8 | Marginal | Victor Kannan | 159722
ST02896 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-074 | Kolkata | East | 20 | Pending Acceptance | 2026-02-26 | 2026-04-13 | 2026-04-13 | 2026-05-10 | 2026-05-14 | 0 | Met | Victor Kannan | 212176
ST02897 | PRJ035 | CL008 | Reliance Retail | Patna Site-075 | Patna | East | 50 | Installation Scheduled | 2026-03-22 | 2026-05-21 | 2026-05-27 | 2026-06-15 |  | 3 | Met | Nitesh Raghavan | 90477
ST02898 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-076 | Kolkata | East | 10 | Pending Acceptance | 2026-03-02 | 2026-04-19 | 2026-04-29 | 2026-05-19 | 2026-05-17 | 10 | Marginal | Jai Kota | 131662
ST02899 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-077 | Kolkata | East | 20 | Installation Scheduled | 2026-03-09 | 2026-05-05 | 2026-05-15 | 2026-05-21 |  | 0 | Met | Dipta Bhandari | 102835
ST02900 | PRJ035 | CL008 | Reliance Retail | Patna Site-078 | Patna | East | 50 | Live | 2026-03-02 | 2026-04-01 | 2026-04-07 | 2026-04-25 | 2026-04-22 | 6 | Met | Yashica Issac | 251742
ST02901 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-079 | Bhubaneswar | East | 50 | Survey Pending | 2026-03-21 | 2026-04-19 |  | 2026-05-09 |  | 5 | Met | Ekavir Varkey | 152621
ST02902 | PRJ035 | CL008 | Reliance Retail | Patna Site-080 | Patna | East | 10 | Testing | 2026-03-23 | 2026-04-26 | 2026-05-05 | 2026-05-20 |  | 12 | Marginal | Ekavir Varkey | 72331
ST02903 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-081 | Kolkata | East | 200 | Installation Done | 2026-03-15 | 2026-05-08 | 2026-05-05 | 2026-05-29 |  | 12 | Marginal | Tanay Rattan | 212151
ST02904 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-082 | Bhubaneswar | East | 100 | Installation Done | 2026-03-18 | 2026-05-06 | 2026-05-08 | 2026-06-01 |  | 12 | Marginal | Unni Bhagat | 144644
ST02905 | PRJ035 | CL008 | Reliance Retail | Patna Site-083 | Patna | East | 100 | Survey Pending | 2026-03-06 | 2026-04-27 |  | 2026-05-15 |  | 6 | Met | Siddharth Zacharia | 99323
ST02906 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-084 | Kolkata | East | 50 | Live | 2026-03-17 | 2026-04-10 | 2026-04-10 | 2026-04-29 | 2026-05-06 | 0 | Met | Dipta Bhandari | 225740
ST02907 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-085 | Bhubaneswar | East | 200 | Survey Pending | 2026-03-19 | 2026-05-05 |  | 2026-05-20 |  | 3 | Met | Devansh Nigam | 126994
ST02908 | PRJ035 | CL008 | Reliance Retail | Patna Site-086 | Patna | East | 10 | Live | 2026-03-19 | 2026-04-25 | 2026-04-25 | 2026-05-18 | 2026-05-23 | 0 | Met | Quincy Biswas | 153155
ST02909 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-087 | Kolkata | East | 20 | Live | 2026-03-17 | 2026-04-26 | 2026-04-27 | 2026-05-07 | 2026-05-06 | 1 | Met | Simon Tata | 104084
ST02910 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-088 | Kolkata | East | 100 | Testing | 2026-02-26 | 2026-03-25 | 2026-03-27 | 2026-04-20 |  | 12 | Marginal | Gavin Batta | 272316
ST02911 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-089 | Bhubaneswar | East | 200 | ROW In Progress | 2026-03-05 | 2026-04-09 |  | 2026-04-30 |  | 6 | Met | Simon Tata | 129008
ST02912 | PRJ035 | CL008 | Reliance Retail | Patna Site-090 | Patna | East | 20 | Live | 2026-02-28 | 2026-03-22 | 2026-03-17 | 2026-04-04 | 2026-04-12 | 0 | Met | Ekapad Walia | 164808
ST02913 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-091 | Bhubaneswar | East | 20 | Live | 2026-03-04 | 2026-04-13 | 2026-04-20 | 2026-05-07 | 2026-05-04 | 7 | Met | Mohammed Gupta | 173713
ST02914 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-092 | Kolkata | East | 50 | Installation Done | 2026-03-12 | 2026-04-05 | 2026-04-10 | 2026-04-27 |  | 12 | Marginal | Madhavi Lanka | 218028
ST02915 | PRJ035 | CL008 | Reliance Retail | Patna Site-093 | Patna | East | 100 | Installation Done | 2026-03-20 | 2026-05-16 | 2026-05-20 | 2026-06-06 |  | 12 | Marginal | Unni Bhagat | 193988
ST02916 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-094 | Bhubaneswar | East | 50 | Testing | 2026-03-09 | 2026-04-21 | 2026-04-16 | 2026-05-11 |  | 12 | Marginal | Devika Rastogi | 225441
ST02917 | PRJ035 | CL008 | Reliance Retail | Patna Site-095 | Patna | East | 10 | Installation Done | 2026-03-16 | 2026-05-15 | 2026-05-12 | 2026-06-08 |  | 12 | Marginal | Arya Sunder | 179727
ST02918 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-096 | Bhubaneswar | East | 20 | Live | 2026-03-07 | 2026-03-31 | 2026-04-02 | 2026-04-29 | 2026-05-07 | 2 | Met | Urvashi Ray | 79336
ST02919 | PRJ035 | CL008 | Reliance Retail | Patna Site-097 | Patna | East | 10 | Live | 2026-03-09 | 2026-04-07 | 2026-04-03 | 2026-05-01 | 2026-05-03 | 0 | Met | Chandresh Zachariah | 215422
ST02920 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-098 | Bhubaneswar | East | 10 | ROW In Progress | 2026-02-28 | 2026-04-28 |  | 2026-05-28 |  | 2 | Met | Arya Sunder | 263164
ST02921 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-099 | Bhubaneswar | East | 10 | Installation Done | 2026-03-20 | 2026-04-27 | 2026-05-02 | 2026-05-11 |  | 12 | Marginal | Ekapad Walia | 55580
ST02922 | PRJ035 | CL008 | Reliance Retail | Patna Site-100 | Patna | East | 100 | ROW In Progress | 2026-03-18 | 2026-05-01 |  | 2026-05-30 |  | 4 | Met | Farhan Chada | 51742
ST02923 | PRJ035 | CL008 | Reliance Retail | Patna Site-101 | Patna | East | 50 | Live | 2026-03-15 | 2026-04-13 | 2026-04-17 | 2026-04-24 | 2026-04-27 | 4 | Met | Devika Rastogi | 90168
ST02924 | PRJ035 | CL008 | Reliance Retail | Patna Site-102 | Patna | East | 20 | Pending Acceptance | 2026-03-23 | 2026-04-22 | 2026-04-26 | 2026-05-11 | 2026-05-08 | 4 | Met | Farhan Chada | 247612
ST02925 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-103 | Bhubaneswar | East | 10 | Installation Scheduled | 2026-03-18 | 2026-04-08 | 2026-04-11 | 2026-04-20 |  | 2 | Met | Diya Rattan | 139816
ST02926 | PRJ035 | CL008 | Reliance Retail | Patna Site-104 | Patna | East | 200 | Live | 2026-03-03 | 2026-04-14 | 2026-04-24 | 2026-05-12 | 2026-05-19 | 10 | Marginal | Tara Dhar | 230441
ST02927 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-105 | Kolkata | East | 20 | Installation Scheduled | 2026-03-13 | 2026-05-10 | 2026-05-13 | 2026-05-22 |  | 2 | Met | Yashica Cherian | 130175
ST02928 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-106 | Bhubaneswar | East | 20 | Installation Done | 2026-02-28 | 2026-04-24 | 2026-04-21 | 2026-05-07 |  | 12 | Marginal | Arya Sunder | 239252
ST02929 | PRJ035 | CL008 | Reliance Retail | Patna Site-107 | Patna | East | 20 | Pending Acceptance | 2026-03-06 | 2026-04-27 | 2026-05-03 | 2026-05-22 | 2026-05-21 | 6 | Met | Kabir Soman | 202503
ST02930 | PRJ035 | CL008 | Reliance Retail | Patna Site-108 | Patna | East | 200 | Testing | 2026-03-20 | 2026-04-20 | 2026-04-29 | 2026-05-13 |  | 12 | Marginal | Tanay Rattan | 67854
ST02931 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-109 | Kolkata | East | 20 | Installation Done | 2026-03-07 | 2026-04-04 | 2026-04-02 | 2026-04-17 |  | 12 | Marginal | Daksh Karnik | 247708
ST02932 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-110 | Kolkata | East | 10 | Testing | 2026-03-20 | 2026-04-22 | 2026-04-19 | 2026-05-09 |  | 12 | Marginal | Gavin Batta | 121021
ST02933 | PRJ035 | CL008 | Reliance Retail | Patna Site-111 | Patna | East | 200 | Live | 2026-03-15 | 2026-04-06 | 2026-04-06 | 2026-05-05 | 2026-05-03 | 0 | Met | Liam Koshy | 196622
ST02934 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-112 | Bhubaneswar | East | 200 | Live | 2026-03-07 | 2026-04-19 | 2026-04-19 | 2026-05-05 | 2026-05-05 | 0 | Met | Devansh Rajan | 222235
ST02935 | PRJ035 | CL008 | Reliance Retail | Patna Site-113 | Patna | East | 20 | Live | 2026-02-27 | 2026-04-20 | 2026-04-19 | 2026-05-02 | 2026-05-05 | 0 | Met | Girindra Chatterjee | 147905
ST02936 | PRJ035 | CL008 | Reliance Retail | Patna Site-114 | Patna | East | 20 | Live | 2026-03-20 | 2026-04-22 | 2026-04-20 | 2026-05-16 | 2026-05-17 | 0 | Met | Madhavi Lanka | 275949
ST02937 | PRJ035 | CL008 | Reliance Retail | Patna Site-115 | Patna | East | 10 | Installation Done | 2026-02-27 | 2026-04-07 | 2026-04-04 | 2026-05-02 |  | 12 | Marginal | Nihal Shere | 269987
ST02938 | PRJ035 | CL008 | Reliance Retail | Patna Site-116 | Patna | East | 200 | Installation Scheduled | 2026-03-15 | 2026-05-10 | 2026-05-07 | 2026-06-08 |  | 1 | Met | Dakshesh Trivedi | 121169
ST02939 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-117 | Kolkata | East | 10 | Installation Scheduled | 2026-02-26 | 2026-03-25 | 2026-03-27 | 2026-04-10 |  | 2 | Met | Raksha Varughese | 116416
ST02940 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-118 | Bhubaneswar | East | 50 | Testing | 2026-03-11 | 2026-04-01 | 2026-04-11 | 2026-04-13 |  | 12 | Marginal | Vansha Thakkar | 246836
ST02941 | PRJ035 | CL008 | Reliance Retail | Bhubaneswar Site-119 | Bhubaneswar | East | 50 | Installation Scheduled | 2026-03-20 | 2026-05-10 | 2026-05-19 | 2026-05-31 |  | 2 | Met | Teerth Bhardwaj | 84852
ST02942 | PRJ035 | CL008 | Reliance Retail | Kolkata Site-120 | Kolkata | East | 10 | Survey Pending | 2026-03-10 | 2026-04-12 |  | 2026-04-25 |  | 6 | Met | Farhan Chada | 218575
ST02943 | PRJ036 | CL008 | Reliance Retail | Delhi Site-001 | Delhi | North | 20 | Survey Pending | 2025-10-09 | 2025-11-03 |  | 2025-11-15 |  | 6 | Met | Yashica Cherian | 175165
ST02944 | PRJ036 | CL008 | Reliance Retail | Noida Site-002 | Noida | North | 10 | Pending Acceptance | 2025-10-25 | 2025-12-08 | 2025-12-18 | 2025-12-26 | 2025-12-27 | 10 | Marginal | Bhavika Sampath | 239968
ST02945 | PRJ036 | CL008 | Reliance Retail | Noida Site-003 | Noida | North | 200 | Installation Done | 2025-10-25 | 2025-11-28 | 2025-12-04 | 2025-12-09 |  | 12 | Marginal | Girindra Chatterjee | 264606
ST02946 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-004 | Jaipur | North | 10 | Survey Pending | 2025-11-03 | 2025-12-30 |  | 2026-01-15 |  | 4 | Met | Theodore Devi | 151532
ST02947 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-005 | Gurgaon | North | 50 | Survey Pending | 2025-10-12 | 2025-11-05 |  | 2025-11-21 |  | 6 | Met | Anamika Kanda | 108058
ST02948 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-006 | Gurgaon | North | 100 | Live | 2025-10-29 | 2025-12-04 | 2025-12-07 | 2025-12-20 | 2026-01-01 | 3 | Met | Diya Rattan | 49088
ST02949 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-007 | Jaipur | North | 10 | ROW In Progress | 2025-10-24 | 2025-12-19 |  | 2026-01-08 |  | 5 | Met | Kevin Solanki | 257677
ST02950 | PRJ036 | CL008 | Reliance Retail | Noida Site-008 | Noida | North | 100 | Testing | 2025-10-20 | 2025-11-25 | 2025-11-29 | 2025-12-24 |  | 12 | Marginal | Nitesh Raghavan | 196015
ST02951 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-009 | Gurgaon | North | 100 | Installation Scheduled | 2025-10-11 | 2025-11-30 | 2025-12-06 | 2025-12-23 |  | 2 | Met | Unni Bhagat | 89185
ST02952 | PRJ036 | CL008 | Reliance Retail | Delhi Site-010 | Delhi | North | 20 | Pending Acceptance | 2025-10-12 | 2025-11-27 | 2025-11-24 | 2025-12-27 | 2026-01-07 | 0 | Met | Victor Kannan | 125224
ST02953 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-011 | Jaipur | North | 20 | Testing | 2025-11-03 | 2025-12-11 | 2025-12-16 | 2026-01-08 |  | 12 | Marginal | Siddharth Zacharia | 127062
ST02954 | PRJ036 | CL008 | Reliance Retail | Delhi Site-012 | Delhi | North | 50 | Live | 2025-10-31 | 2025-12-03 | 2025-12-05 | 2025-12-18 | 2025-12-28 | 2 | Met | Quincy Biswas | 233332
ST02955 | PRJ036 | CL008 | Reliance Retail | Delhi Site-013 | Delhi | North | 10 | Live | 2025-10-30 | 2025-11-21 | 2025-11-17 | 2025-12-03 | 2025-12-14 | 0 | Met | Dipta Bhandari | 190800
ST02956 | PRJ036 | CL008 | Reliance Retail | Delhi Site-014 | Delhi | North | 100 | ROW In Progress | 2025-10-31 | 2025-12-29 |  | 2026-01-17 |  | 5 | Met | Girik Khalsa | 64632
ST02957 | PRJ036 | CL008 | Reliance Retail | Noida Site-015 | Noida | North | 50 | Survey Pending | 2025-10-17 | 2025-12-12 |  | 2025-12-31 |  | 8 | Marginal | Gavin Batta | 228199
ST02958 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-016 | Gurgaon | North | 50 | ROW In Progress | 2025-10-31 | 2025-12-30 |  | 2026-01-16 |  | 5 | Met | Yashica Cherian | 251353
ST02959 | PRJ036 | CL008 | Reliance Retail | Noida Site-017 | Noida | North | 100 | Live | 2025-10-24 | 2025-11-23 | 2025-12-03 | 2025-12-14 | 2025-12-23 | 10 | Marginal | Advay Contractor | 217895
ST02960 | PRJ036 | CL008 | Reliance Retail | Noida Site-018 | Noida | North | 50 | Survey Pending | 2025-10-13 | 2025-11-28 |  | 2025-12-18 |  | 6 | Met | Teerth Bhardwaj | 231377
ST02961 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-019 | Jaipur | North | 20 | ROW In Progress | 2025-10-11 | 2025-11-21 |  | 2025-12-17 |  | 8 | Marginal | Liam Koshy | 264097
ST02962 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-020 | Jaipur | North | 100 | Pending Acceptance | 2025-10-30 | 2025-12-22 | 2025-12-25 | 2026-01-03 | 2025-12-31 | 3 | Met | Advay Contractor | 75407
ST02963 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-021 | Jaipur | North | 100 | ROW In Progress | 2025-10-18 | 2025-12-02 |  | 2025-12-20 |  | 4 | Met | Theodore Devi | 72019
ST02964 | PRJ036 | CL008 | Reliance Retail | Noida Site-022 | Noida | North | 20 | Survey Pending | 2025-10-27 | 2025-12-15 |  | 2026-01-05 |  | 4 | Met | Arya Sunder | 273894
ST02965 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-023 | Jaipur | North | 100 | Installation Scheduled | 2025-11-01 | 2025-12-24 | 2025-12-29 | 2026-01-08 |  | 3 | Met | Dakshesh Trivedi | 121648
ST02966 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-024 | Jaipur | North | 20 | Installation Done | 2025-10-10 | 2025-11-29 | 2025-11-27 | 2025-12-29 |  | 12 | Marginal | Unni Bhagat | 108504
ST02967 | PRJ036 | CL008 | Reliance Retail | Noida Site-025 | Noida | North | 10 | Installation Scheduled | 2025-10-12 | 2025-11-11 | 2025-11-08 | 2025-12-11 |  | 8 | Marginal | Yashica Issac | 242906
ST02968 | PRJ036 | CL008 | Reliance Retail | Noida Site-026 | Noida | North | 100 | Installation Done | 2025-10-27 | 2025-12-23 | 2025-12-19 | 2026-01-21 |  | 12 | Marginal | Girik Khalsa | 152986
ST02969 | PRJ036 | CL008 | Reliance Retail | Delhi Site-027 | Delhi | North | 20 | ROW In Progress | 2025-10-22 | 2025-12-04 |  | 2025-12-20 |  | 8 | Marginal | Ranveer Yadav | 165422
ST02970 | PRJ036 | CL008 | Reliance Retail | Delhi Site-028 | Delhi | North | 10 | Installation Done | 2025-10-21 | 2025-12-13 | 2025-12-12 | 2025-12-26 |  | 12 | Marginal | Nihal Shere | 94522
ST02971 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-029 | Jaipur | North | 10 | Survey Pending | 2025-11-02 | 2025-12-29 |  | 2026-01-08 |  | 7 | Met | Raksha Varughese | 172773
ST02972 | PRJ036 | CL008 | Reliance Retail | Delhi Site-030 | Delhi | North | 20 | Installation Done | 2025-10-25 | 2025-12-10 | 2025-12-18 | 2026-01-07 |  | 12 | Marginal | Kashvi Edwin | 54590
ST02973 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-031 | Jaipur | North | 200 | Live | 2025-11-03 | 2025-11-25 | 2025-11-27 | 2025-12-13 | 2025-12-18 | 2 | Met | Yashica Cherian | 221262
ST02974 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-032 | Jaipur | North | 20 | Installation Done | 2025-10-18 | 2025-12-11 | 2025-12-20 | 2026-01-03 |  | 12 | Marginal | Niharika Sunder | 136124
ST02975 | PRJ036 | CL008 | Reliance Retail | Delhi Site-033 | Delhi | North | 50 | Live | 2025-11-03 | 2025-12-11 | 2025-12-14 | 2025-12-31 | 2026-01-09 | 3 | Met | Bhavika Sampath | 79925
ST02976 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-034 | Jaipur | North | 200 | Installation Done | 2025-10-20 | 2025-11-26 | 2025-11-23 | 2025-12-25 |  | 12 | Marginal | Yashica Issac | 176634
ST02977 | PRJ036 | CL008 | Reliance Retail | Delhi Site-035 | Delhi | North | 200 | Installation Done | 2025-10-27 | 2025-12-03 | 2025-12-13 | 2025-12-28 |  | 12 | Marginal | Darsh Rau | 45915
ST02978 | PRJ036 | CL008 | Reliance Retail | Delhi Site-036 | Delhi | North | 20 | ROW In Progress | 2025-10-19 | 2025-11-16 |  | 2025-11-30 |  | 0 | Met | Madhavi Lanka | 92068
ST02979 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-037 | Jaipur | North | 100 | Testing | 2025-10-16 | 2025-11-08 | 2025-11-09 | 2025-11-22 |  | 12 | Marginal | Jai Kota | 135521
ST02980 | PRJ036 | CL008 | Reliance Retail | Noida Site-038 | Noida | North | 200 | Pending Acceptance | 2025-10-20 | 2025-12-07 | 2025-12-09 | 2025-12-24 | 2025-12-21 | 2 | Met | Diya Rattan | 165965
ST02981 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-039 | Gurgaon | North | 100 | Live | 2025-10-10 | 2025-11-23 | 2025-11-25 | 2025-12-13 | 2025-12-12 | 2 | Met | Unni Bhagat | 83440
ST02982 | PRJ036 | CL008 | Reliance Retail | Noida Site-040 | Noida | North | 50 | Installation Scheduled | 2025-10-21 | 2025-12-10 | 2025-12-16 | 2025-12-23 |  | 2 | Met | Farhan Chada | 171402
ST02983 | PRJ036 | CL008 | Reliance Retail | Delhi Site-041 | Delhi | North | 100 | Survey Pending | 2025-11-03 | 2025-12-15 |  | 2025-12-31 |  | 6 | Met | Ekapad Walia | 95888
ST02984 | PRJ036 | CL008 | Reliance Retail | Noida Site-042 | Noida | North | 20 | Installation Done | 2025-10-16 | 2025-11-18 | 2025-11-21 | 2025-12-02 |  | 12 | Marginal | Ikbal Kothari | 227754
ST02985 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-043 | Jaipur | North | 20 | ROW In Progress | 2025-11-02 | 2025-12-25 |  | 2026-01-11 |  | 7 | Met | Alka Wable | 175362
ST02986 | PRJ036 | CL008 | Reliance Retail | Noida Site-044 | Noida | North | 10 | ROW In Progress | 2025-11-02 | 2025-12-29 |  | 2026-01-14 |  | 1 | Met | Siddharth Zacharia | 257313
ST02987 | PRJ036 | CL008 | Reliance Retail | Noida Site-045 | Noida | North | 20 | Live | 2025-11-02 | 2025-11-25 | 2025-11-20 | 2025-12-22 | 2025-12-28 | 0 | Met | Ekapad Walia | 110793
ST02988 | PRJ036 | CL008 | Reliance Retail | Delhi Site-046 | Delhi | North | 20 | Installation Scheduled | 2025-10-23 | 2025-11-12 | 2025-11-15 | 2025-11-28 |  | 3 | Met | Farhan Chada | 223991
ST02989 | PRJ036 | CL008 | Reliance Retail | Delhi Site-047 | Delhi | North | 50 | Live | 2025-10-26 | 2025-12-17 | 2025-12-18 | 2026-01-13 | 2026-01-18 | 1 | Met | Girik Khalsa | 211361
ST02990 | PRJ036 | CL008 | Reliance Retail | Delhi Site-048 | Delhi | North | 50 | ROW In Progress | 2025-10-29 | 2025-12-19 |  | 2026-01-15 |  | 0 | Met | Dipta Bhandari | 102441
ST02991 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-049 | Jaipur | North | 100 | ROW In Progress | 2025-10-25 | 2025-12-24 |  | 2026-01-14 |  | 1 | Met | Tanay Rattan | 194780
ST02992 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-050 | Jaipur | North | 50 | Testing | 2025-10-29 | 2025-12-28 | 2026-01-04 | 2026-01-16 |  | 12 | Marginal | Ikbal Kothari | 125520
ST02993 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-051 | Gurgaon | North | 200 | Live | 2025-10-31 | 2025-11-29 | 2025-11-27 | 2025-12-20 | 2026-01-01 | 0 | Met | Alka Wable | 166521
ST02994 | PRJ036 | CL008 | Reliance Retail | Noida Site-052 | Noida | North | 100 | Installation Done | 2025-10-09 | 2025-11-18 | 2025-11-19 | 2025-12-02 |  | 12 | Marginal | Farhan Chada | 214788
ST02995 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-053 | Jaipur | North | 20 | Installation Done | 2025-10-20 | 2025-12-18 | 2025-12-19 | 2026-01-05 |  | 12 | Marginal | Kabir Soman | 211634
ST02996 | PRJ036 | CL008 | Reliance Retail | Delhi Site-054 | Delhi | North | 20 | Installation Scheduled | 2025-10-23 | 2025-12-21 | 2025-12-30 | 2026-01-16 |  | 3 | Met | Theodore Devi | 226766
ST02997 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-055 | Gurgaon | North | 50 | Survey Pending | 2025-10-14 | 2025-11-09 |  | 2025-12-08 |  | 8 | Marginal | Tanay Rattan | 135556
ST02998 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-056 | Gurgaon | North | 100 | Live | 2025-10-30 | 2025-11-20 | 2025-11-19 | 2025-12-10 | 2025-12-07 | 0 | Met | Madhavi Lanka | 158875
ST02999 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-057 | Jaipur | North | 20 | Live | 2025-11-02 | 2025-11-24 | 2025-12-01 | 2025-12-24 | 2026-01-04 | 7 | Met | Arya Sunder | 174554
ST03000 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-058 | Jaipur | North | 20 | Installation Done | 2025-10-18 | 2025-12-13 | 2025-12-21 | 2025-12-30 |  | 12 | Marginal | Ikbal Kothari | 234833
ST03001 | PRJ036 | CL008 | Reliance Retail | Delhi Site-059 | Delhi | North | 20 | Live | 2025-10-09 | 2025-11-12 | 2025-11-17 | 2025-11-27 | 2025-12-03 | 5 | Met | Vansha Thakkar | 144911
ST03002 | PRJ036 | CL008 | Reliance Retail | Noida Site-060 | Noida | North | 20 | ROW In Progress | 2025-10-19 | 2025-11-30 |  | 2025-12-28 |  | 6 | Met | Bhavika Sampath | 122321
ST03003 | PRJ036 | CL008 | Reliance Retail | Noida Site-061 | Noida | North | 50 | Testing | 2025-10-22 | 2025-11-25 | 2025-11-28 | 2025-12-24 |  | 12 | Marginal | Ekansh Balay | 46893
ST03004 | PRJ036 | CL008 | Reliance Retail | Noida Site-062 | Noida | North | 50 | Testing | 2025-10-20 | 2025-11-29 | 2025-12-03 | 2025-12-22 |  | 12 | Marginal | Madhavi Lanka | 249130
ST03005 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-063 | Gurgaon | North | 20 | ROW In Progress | 2025-10-24 | 2025-11-16 |  | 2025-12-12 |  | 7 | Met | Diya Rattan | 59044
ST03006 | PRJ036 | CL008 | Reliance Retail | Noida Site-064 | Noida | North | 100 | Live | 2025-10-11 | 2025-11-01 | 2025-10-31 | 2025-11-25 | 2025-11-28 | 0 | Met | Arya Shere | 103051
ST03007 | PRJ036 | CL008 | Reliance Retail | Noida Site-065 | Noida | North | 20 | Installation Done | 2025-10-21 | 2025-12-09 | 2025-12-10 | 2025-12-24 |  | 12 | Marginal | Ekapad Walia | 119732
ST03008 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-066 | Jaipur | North | 10 | Installation Scheduled | 2025-10-15 | 2025-12-12 | 2025-12-09 | 2026-01-04 |  | 6 | Met | Michael Dutta | 197111
ST03009 | PRJ036 | CL008 | Reliance Retail | Delhi Site-067 | Delhi | North | 100 | Survey Pending | 2025-10-09 | 2025-11-17 |  | 2025-12-14 |  | 8 | Marginal | Chandresh Zachariah | 233743
ST03010 | PRJ036 | CL008 | Reliance Retail | Delhi Site-068 | Delhi | North | 100 | Live | 2025-10-15 | 2025-11-13 | 2025-11-21 | 2025-12-02 | 2025-12-08 | 8 | Marginal | Farhan Chada | 219187
ST03011 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-069 | Jaipur | North | 100 | Installation Done | 2025-10-28 | 2025-12-10 | 2025-12-13 | 2025-12-22 |  | 12 | Marginal | Madhavi Lanka | 253393
ST03012 | PRJ036 | CL008 | Reliance Retail | Delhi Site-070 | Delhi | North | 100 | Live | 2025-10-28 | 2025-11-18 | 2025-11-19 | 2025-12-13 | 2025-12-13 | 1 | Met | Ekavir Varkey | 247155
ST03013 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-071 | Gurgaon | North | 100 | Live | 2025-10-26 | 2025-11-21 | 2025-11-16 | 2025-12-10 | 2025-12-18 | 0 | Met | Raksha Varughese | 232635
ST03014 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-072 | Gurgaon | North | 20 | Installation Done | 2025-10-27 | 2025-12-05 | 2025-12-08 | 2025-12-30 |  | 12 | Marginal | Siddharth Zacharia | 186442
ST03015 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-073 | Jaipur | North | 50 | Live | 2025-10-10 | 2025-11-19 | 2025-11-18 | 2025-12-15 | 2025-12-12 | 0 | Met | Faqid Savant | 159489
ST03016 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-074 | Gurgaon | North | 100 | Pending Acceptance | 2025-10-11 | 2025-12-05 | 2025-12-06 | 2025-12-29 | 2026-01-04 | 1 | Met | Bhavika Sampath | 68742
ST03017 | PRJ036 | CL008 | Reliance Retail | Noida Site-075 | Noida | North | 200 | Pending Acceptance | 2025-10-17 | 2025-11-21 | 2025-11-24 | 2025-12-12 | 2025-12-10 | 3 | Met | Girik Khalsa | 178198
ST03018 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-076 | Gurgaon | North | 50 | Testing | 2025-10-25 | 2025-11-16 | 2025-11-23 | 2025-12-01 |  | 12 | Marginal | Tara Dhar | 84268
ST03019 | PRJ036 | CL008 | Reliance Retail | Noida Site-077 | Noida | North | 100 | Survey Pending | 2025-10-27 | 2025-12-23 |  | 2026-01-14 |  | 4 | Met | Kashvi Edwin | 114525
ST03020 | PRJ036 | CL008 | Reliance Retail | Noida Site-078 | Noida | North | 200 | Installation Scheduled | 2025-10-16 | 2025-11-27 | 2025-11-30 | 2025-12-23 |  | 6 | Met | Irya Sampath | 91348
ST03021 | PRJ036 | CL008 | Reliance Retail | Delhi Site-079 | Delhi | North | 20 | ROW In Progress | 2025-10-12 | 2025-11-23 |  | 2025-12-15 |  | 0 | Met | Yatin Baral | 163455
ST03022 | PRJ036 | CL008 | Reliance Retail | Delhi Site-080 | Delhi | North | 50 | Survey Pending | 2025-10-26 | 2025-11-17 |  | 2025-12-03 |  | 5 | Met | Tanay Rattan | 208026
ST03023 | PRJ036 | CL008 | Reliance Retail | Gurgaon Site-081 | Gurgaon | North | 100 | Installation Done | 2025-10-09 | 2025-11-17 | 2025-11-13 | 2025-12-03 |  | 12 | Marginal | Girik Khalsa | 113041
ST03024 | PRJ036 | CL008 | Reliance Retail | Jaipur Site-082 | Jaipur | North | 10 | Installation Scheduled | 2025-10-22 | 2025-12-18 | 2025-12-16 | 2025-12-30 |  | 6 | Met | Isaac Patil | 91509
ST03025 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-001 | Bhubaneswar | East | 200 | Survey Pending | 2025-06-02 | 2025-07-17 |  | 2025-08-04 |  | 1 | Met | Nihal Shere | 111367
ST03026 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-002 | Bhubaneswar | East | 200 | Live | 2025-06-24 | 2025-08-09 | 2025-08-05 | 2025-09-05 | 2025-09-04 | 0 | Met | Wahab Raval | 71792
ST03027 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-003 | Bhubaneswar | East | 100 | Survey Pending | 2025-06-23 | 2025-08-17 |  | 2025-09-03 |  | 4 | Met | Girindra Chatterjee | 114104
ST03028 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-004 | Bhubaneswar | East | 200 | Testing | 2025-06-10 | 2025-07-01 | 2025-07-08 | 2025-07-11 |  | 12 | Marginal | Irya Sampath | 262221
ST03029 | PRJ037 | CL008 | Reliance Retail | Patna Site-005 | Patna | East | 100 | Survey Pending | 2025-06-03 | 2025-07-22 |  | 2025-08-09 |  | 5 | Met | Madhavi Lanka | 200745
ST03030 | PRJ037 | CL008 | Reliance Retail | Patna Site-006 | Patna | East | 100 | Installation Scheduled | 2025-06-18 | 2025-08-17 | 2025-08-23 | 2025-09-14 |  | 0 | Met | Devansh Nigam | 82135
ST03031 | PRJ037 | CL008 | Reliance Retail | Patna Site-007 | Patna | East | 50 | Pending Acceptance | 2025-06-01 | 2025-07-10 | 2025-07-09 | 2025-08-08 | 2025-08-05 | 0 | Met | Ikbal Kothari | 164092
ST03032 | PRJ037 | CL008 | Reliance Retail | Patna Site-008 | Patna | East | 200 | Installation Done | 2025-06-12 | 2025-07-13 | 2025-07-18 | 2025-07-29 |  | 12 | Marginal | Ekansh Balay | 164049
ST03033 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-009 | Bhubaneswar | East | 10 | Live | 2025-06-18 | 2025-07-13 | 2025-07-19 | 2025-07-29 | 2025-07-27 | 6 | Met | Chandresh Zachariah | 269573
ST03034 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-010 | Bhubaneswar | East | 100 | Installation Done | 2025-06-15 | 2025-08-14 | 2025-08-21 | 2025-08-27 |  | 12 | Marginal | Ekavir Varkey | 221238
ST03035 | PRJ037 | CL008 | Reliance Retail | Patna Site-011 | Patna | East | 100 | Installation Done | 2025-06-15 | 2025-07-25 | 2025-07-20 | 2025-08-08 |  | 12 | Marginal | Harini Choudhury | 204580
ST03036 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-012 | Bhubaneswar | East | 200 | Pending Acceptance | 2025-06-01 | 2025-06-28 | 2025-07-05 | 2025-07-20 | 2025-07-21 | 7 | Met | Girik Khalsa | 159133
ST03037 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-013 | Kolkata | East | 200 | Live | 2025-06-08 | 2025-08-05 | 2025-08-04 | 2025-08-23 | 2025-09-01 | 0 | Met | Niharika Sunder | 171646
ST03038 | PRJ037 | CL008 | Reliance Retail | Patna Site-014 | Patna | East | 100 | Survey Pending | 2025-06-11 | 2025-07-24 |  | 2025-08-15 |  | 2 | Met | Quincy Biswas | 260356
ST03039 | PRJ037 | CL008 | Reliance Retail | Patna Site-015 | Patna | East | 20 | Installation Scheduled | 2025-06-04 | 2025-06-28 | 2025-07-04 | 2025-07-23 |  | 2 | Met | Gavin Batta | 232904
ST03040 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-016 | Kolkata | East | 50 | Installation Scheduled | 2025-06-07 | 2025-07-08 | 2025-07-09 | 2025-07-28 |  | 2 | Met | Faqid Savant | 262878
ST03041 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-017 | Kolkata | East | 200 | Survey Pending | 2025-06-09 | 2025-08-01 |  | 2025-08-30 |  | 4 | Met | Faqid Savant | 275311
ST03042 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-018 | Kolkata | East | 20 | Installation Done | 2025-06-02 | 2025-07-15 | 2025-07-11 | 2025-08-04 |  | 12 | Marginal | Nihal Shere | 209085
ST03043 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-019 | Bhubaneswar | East | 10 | Live | 2025-06-06 | 2025-07-17 | 2025-07-18 | 2025-07-29 | 2025-08-01 | 1 | Met | Victor Kannan | 142377
ST03044 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-020 | Bhubaneswar | East | 20 | Survey Pending | 2025-06-18 | 2025-08-16 |  | 2025-09-02 |  | 4 | Met | Raksha Varughese | 84170
ST03045 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-021 | Kolkata | East | 20 | Live | 2025-06-21 | 2025-07-18 | 2025-07-13 | 2025-08-16 | 2025-08-15 | 0 | Met | Victor Kannan | 112670
ST03046 | PRJ037 | CL008 | Reliance Retail | Patna Site-022 | Patna | East | 200 | Installation Scheduled | 2025-06-02 | 2025-07-09 | 2025-07-06 | 2025-07-27 |  | 0 | Met | Quincy Biswas | 179216
ST03047 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-023 | Kolkata | East | 20 | Installation Scheduled | 2025-06-24 | 2025-07-26 | 2025-08-04 | 2025-08-20 |  | 8 | Marginal | Arya Sunder | 56831
ST03048 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-024 | Kolkata | East | 20 | ROW In Progress | 2025-06-02 | 2025-07-19 |  | 2025-08-14 |  | 2 | Met | Gavin Batta | 101888
ST03049 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-025 | Bhubaneswar | East | 10 | Testing | 2025-06-17 | 2025-08-09 | 2025-08-06 | 2025-09-04 |  | 12 | Marginal | Nihal Shere | 56176
ST03050 | PRJ037 | CL008 | Reliance Retail | Patna Site-026 | Patna | East | 50 | Testing | 2025-06-03 | 2025-07-12 | 2025-07-12 | 2025-08-04 |  | 12 | Marginal | Dipta Bhandari | 181136
ST03051 | PRJ037 | CL008 | Reliance Retail | Patna Site-027 | Patna | East | 100 | Live | 2025-06-12 | 2025-07-15 | 2025-07-20 | 2025-08-05 | 2025-08-17 | 5 | Met | Ekansh Balay | 248502
ST03052 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-028 | Bhubaneswar | East | 20 | Live | 2025-06-12 | 2025-07-15 | 2025-07-19 | 2025-08-10 | 2025-08-11 | 4 | Met | Wahab Raval | 260997
ST03053 | PRJ037 | CL008 | Reliance Retail | Patna Site-029 | Patna | East | 50 | ROW In Progress | 2025-06-08 | 2025-07-16 |  | 2025-07-31 |  | 2 | Met | Farhan Chada | 130704
ST03054 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-030 | Kolkata | East | 200 | Survey Pending | 2025-06-13 | 2025-08-05 |  | 2025-09-01 |  | 2 | Met | Daksh Karnik | 131800
ST03055 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-031 | Kolkata | East | 200 | Pending Acceptance | 2025-06-07 | 2025-07-18 | 2025-07-24 | 2025-08-04 | 2025-08-06 | 6 | Met | Vansha Thakkar | 86638
ST03056 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-032 | Kolkata | East | 100 | Pending Acceptance | 2025-06-13 | 2025-07-28 | 2025-08-07 | 2025-08-20 | 2025-08-29 | 10 | Marginal | Dominic Kakar | 184533
ST03057 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-033 | Kolkata | East | 100 | Testing | 2025-06-14 | 2025-07-23 | 2025-07-28 | 2025-08-18 |  | 12 | Marginal | Theodore Devi | 234519
ST03058 | PRJ037 | CL008 | Reliance Retail | Patna Site-034 | Patna | East | 10 | ROW In Progress | 2025-06-19 | 2025-08-08 |  | 2025-08-28 |  | 3 | Met | Kabir Soman | 232900
ST03059 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-035 | Bhubaneswar | East | 20 | Testing | 2025-06-18 | 2025-07-20 | 2025-07-18 | 2025-08-10 |  | 12 | Marginal | Chandresh Zachariah | 78657
ST03060 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-036 | Kolkata | East | 50 | Live | 2025-05-31 | 2025-07-20 | 2025-07-24 | 2025-08-01 | 2025-08-06 | 4 | Met | Alka Wable | 45994
ST03061 | PRJ037 | CL008 | Reliance Retail | Patna Site-037 | Patna | East | 50 | Live | 2025-05-30 | 2025-07-13 | 2025-07-10 | 2025-07-31 | 2025-08-06 | 0 | Met | Aarush Lall | 199895
ST03062 | PRJ037 | CL008 | Reliance Retail | Patna Site-038 | Patna | East | 50 | Installation Done | 2025-06-08 | 2025-07-20 | 2025-07-29 | 2025-08-08 |  | 12 | Marginal | Ekapad Walia | 100976
ST03063 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-039 | Kolkata | East | 50 | Testing | 2025-06-18 | 2025-08-07 | 2025-08-05 | 2025-08-20 |  | 12 | Marginal | Siddharth Zacharia | 104528
ST03064 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-040 | Kolkata | East | 200 | Live | 2025-06-24 | 2025-08-20 | 2025-08-29 | 2025-09-04 | 2025-09-14 | 9 | Marginal | Dipta Bhandari | 52468
ST03065 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-041 | Kolkata | East | 20 | Survey Pending | 2025-05-31 | 2025-07-03 |  | 2025-08-02 |  | 4 | Met | Ekavir Varkey | 124043
ST03066 | PRJ037 | CL008 | Reliance Retail | Patna Site-042 | Patna | East | 100 | Testing | 2025-06-10 | 2025-08-03 | 2025-08-09 | 2025-08-30 |  | 12 | Marginal | Liam Koshy | 237325
ST03067 | PRJ037 | CL008 | Reliance Retail | Patna Site-043 | Patna | East | 20 | Installation Done | 2025-06-01 | 2025-07-21 | 2025-07-28 | 2025-08-01 |  | 12 | Marginal | Upadhriti Wadhwa | 141038
ST03068 | PRJ037 | CL008 | Reliance Retail | Patna Site-044 | Patna | East | 100 | Testing | 2025-06-14 | 2025-08-11 | 2025-08-14 | 2025-08-27 |  | 12 | Marginal | Madhavi Lanka | 102564
ST03069 | PRJ037 | CL008 | Reliance Retail | Patna Site-045 | Patna | East | 20 | ROW In Progress | 2025-06-08 | 2025-08-04 |  | 2025-08-15 |  | 3 | Met | Advay Contractor | 86989
ST03070 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-046 | Kolkata | East | 10 | ROW In Progress | 2025-06-18 | 2025-07-28 |  | 2025-08-15 |  | 8 | Marginal | Bhavika Sampath | 48612
ST03071 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-047 | Bhubaneswar | East | 20 | Installation Done | 2025-06-20 | 2025-07-17 | 2025-07-21 | 2025-08-12 |  | 12 | Marginal | Chandresh Zachariah | 190640
ST03072 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-048 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-06-14 | 2025-08-04 | 2025-08-07 | 2025-08-14 |  | 7 | Met | Alka Wable | 150562
ST03073 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-049 | Bhubaneswar | East | 10 | Installation Done | 2025-06-23 | 2025-08-04 | 2025-08-11 | 2025-08-14 |  | 12 | Marginal | Mohammed Gupta | 143992
ST03074 | PRJ037 | CL008 | Reliance Retail | Patna Site-050 | Patna | East | 200 | ROW In Progress | 2025-06-16 | 2025-07-15 |  | 2025-07-28 |  | 2 | Met | Harini Choudhury | 76699
ST03075 | PRJ037 | CL008 | Reliance Retail | Patna Site-051 | Patna | East | 100 | Live | 2025-06-05 | 2025-07-27 | 2025-08-04 | 2025-08-23 | 2025-08-25 | 8 | Marginal | Devansh Nigam | 244899
ST03076 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-052 | Bhubaneswar | East | 20 | ROW In Progress | 2025-06-07 | 2025-07-10 |  | 2025-08-08 |  | 3 | Met | Nihal Shere | 123476
ST03077 | PRJ037 | CL008 | Reliance Retail | Patna Site-053 | Patna | East | 10 | Live | 2025-06-19 | 2025-08-15 | 2025-08-23 | 2025-09-12 | 2025-09-14 | 8 | Marginal | Girik Khalsa | 150090
ST03078 | PRJ037 | CL008 | Reliance Retail | Patna Site-054 | Patna | East | 20 | Pending Acceptance | 2025-05-31 | 2025-07-07 | 2025-07-13 | 2025-07-24 | 2025-07-24 | 6 | Met | Farhan Chada | 111158
ST03079 | PRJ037 | CL008 | Reliance Retail | Patna Site-055 | Patna | East | 10 | Pending Acceptance | 2025-06-05 | 2025-07-16 | 2025-07-19 | 2025-08-13 | 2025-08-12 | 3 | Met | Kevin Solanki | 270499
ST03080 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-056 | Bhubaneswar | East | 10 | Installation Done | 2025-06-03 | 2025-07-09 | 2025-07-09 | 2025-07-22 |  | 12 | Marginal | Faqid Savant | 241440
ST03081 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-057 | Kolkata | East | 50 | Installation Done | 2025-06-20 | 2025-07-15 | 2025-07-25 | 2025-07-25 |  | 12 | Marginal | Alka Wable | 251906
ST03082 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-058 | Bhubaneswar | East | 200 | Installation Scheduled | 2025-06-15 | 2025-07-11 | 2025-07-08 | 2025-08-03 |  | 5 | Met | Darsh Rau | 139746
ST03083 | PRJ037 | CL008 | Reliance Retail | Patna Site-059 | Patna | East | 20 | Pending Acceptance | 2025-06-16 | 2025-08-15 | 2025-08-21 | 2025-09-12 | 2025-09-17 | 6 | Met | Priya Rastogi | 208227
ST03084 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-060 | Kolkata | East | 100 | Installation Done | 2025-06-23 | 2025-07-25 | 2025-07-23 | 2025-08-10 |  | 12 | Marginal | Wriddhish Bhardwaj | 225708
ST03085 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-061 | Bhubaneswar | East | 100 | Installation Scheduled | 2025-06-14 | 2025-07-15 | 2025-07-25 | 2025-08-06 |  | 7 | Met | Wahab Raval | 169843
ST03086 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-062 | Bhubaneswar | East | 20 | Installation Done | 2025-06-05 | 2025-07-18 | 2025-07-26 | 2025-07-30 |  | 12 | Marginal | Kevin Solanki | 68409
ST03087 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-063 | Bhubaneswar | East | 10 | Installation Scheduled | 2025-06-18 | 2025-07-12 | 2025-07-18 | 2025-07-29 |  | 8 | Marginal | Arya Sunder | 91964
ST03088 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-064 | Bhubaneswar | East | 100 | Live | 2025-06-03 | 2025-07-05 | 2025-07-06 | 2025-08-03 | 2025-07-31 | 1 | Met | Girik Khalsa | 75141
ST03089 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-065 | Bhubaneswar | East | 200 | Live | 2025-05-31 | 2025-06-26 | 2025-06-23 | 2025-07-08 | 2025-07-12 | 0 | Met | Devansh Rajan | 132637
ST03090 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-066 | Bhubaneswar | East | 20 | Installation Done | 2025-05-30 | 2025-07-08 | 2025-07-12 | 2025-07-23 |  | 12 | Marginal | Niharika Sunder | 110828
ST03091 | PRJ037 | CL008 | Reliance Retail | Bhubaneswar Site-067 | Bhubaneswar | East | 200 | Testing | 2025-06-23 | 2025-07-17 | 2025-07-20 | 2025-08-14 |  | 12 | Marginal | Nihal Shere | 67814
ST03092 | PRJ037 | CL008 | Reliance Retail | Kolkata Site-068 | Kolkata | East | 100 | Live | 2025-06-15 | 2025-07-30 | 2025-07-28 | 2025-08-21 | 2025-08-26 | 0 | Met | Anamika Kanda | 126753
ST03093 | PRJ037 | CL008 | Reliance Retail | Patna Site-069 | Patna | East | 20 | Pending Acceptance | 2025-06-20 | 2025-08-17 | 2025-08-14 | 2025-09-06 | 2025-09-18 | 0 | Met | Daksh Karnik | 144987
ST03094 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-001 | Gurgaon | North | 10 | Testing | 2025-12-10 | 2026-01-02 | 2026-01-06 | 2026-01-14 |  | 12 | Marginal | Gavin Batta | 50543
ST03095 | PRJ038 | CL008 | Reliance Retail | Noida Site-002 | Noida | North | 10 | Testing | 2025-11-28 | 2025-12-20 | 2025-12-30 | 2026-01-16 |  | 12 | Marginal | Girindra Chatterjee | 75142
ST03096 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-003 | Jaipur | North | 20 | Installation Scheduled | 2025-12-01 | 2026-01-06 | 2026-01-15 | 2026-01-31 |  | 7 | Met | Farhan Chada | 106881
ST03097 | PRJ038 | CL008 | Reliance Retail | Delhi Site-004 | Delhi | North | 100 | Installation Done | 2025-11-23 | 2025-12-29 | 2025-12-30 | 2026-01-18 |  | 12 | Marginal | Logan Sami | 115671
ST03098 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-005 | Jaipur | North | 20 | Installation Done | 2025-11-21 | 2026-01-01 | 2025-12-27 | 2026-01-22 |  | 12 | Marginal | Niharika Sunder | 53311
ST03099 | PRJ038 | CL008 | Reliance Retail | Noida Site-006 | Noida | North | 100 | Live | 2025-11-15 | 2025-12-30 | 2026-01-09 | 2026-01-19 | 2026-01-29 | 10 | Marginal | Tara Dhar | 171061
ST03100 | PRJ038 | CL008 | Reliance Retail | Delhi Site-007 | Delhi | North | 20 | Live | 2025-12-07 | 2026-01-30 | 2026-01-28 | 2026-02-14 | 2026-02-16 | 0 | Met | Girik Khalsa | 69865
ST03101 | PRJ038 | CL008 | Reliance Retail | Noida Site-008 | Noida | North | 50 | Testing | 2025-11-19 | 2025-12-21 | 2025-12-31 | 2026-01-14 |  | 12 | Marginal | Ranveer Yadav | 201820
ST03102 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-009 | Gurgaon | North | 200 | Pending Acceptance | 2025-11-18 | 2025-12-21 | 2025-12-23 | 2026-01-15 | 2026-01-25 | 2 | Met | Mohammed Gupta | 47354
ST03103 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-010 | Gurgaon | North | 10 | Pending Acceptance | 2025-12-01 | 2025-12-21 | 2025-12-31 | 2026-01-18 | 2026-01-17 | 10 | Marginal | Girik Khalsa | 266517
ST03104 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-011 | Gurgaon | North | 100 | ROW In Progress | 2025-11-15 | 2026-01-01 |  | 2026-01-19 |  | 0 | Met | Diya Rattan | 164293
ST03105 | PRJ038 | CL008 | Reliance Retail | Noida Site-012 | Noida | North | 200 | Live | 2025-12-06 | 2026-01-14 | 2026-01-23 | 2026-02-09 | 2026-02-14 | 9 | Marginal | Farhan Chada | 256165
ST03106 | PRJ038 | CL008 | Reliance Retail | Delhi Site-013 | Delhi | North | 50 | Installation Scheduled | 2025-12-01 | 2026-01-12 | 2026-01-21 | 2026-01-28 |  | 6 | Met | Ekansh Balay | 225905
ST03107 | PRJ038 | CL008 | Reliance Retail | Delhi Site-014 | Delhi | North | 200 | Live | 2025-11-23 | 2026-01-21 | 2026-01-20 | 2026-02-15 | 2026-02-17 | 0 | Met | Tara Dhar | 206045
ST03108 | PRJ038 | CL008 | Reliance Retail | Delhi Site-015 | Delhi | North | 100 | ROW In Progress | 2025-11-29 | 2026-01-23 |  | 2026-02-18 |  | 3 | Met | Jai Kota | 109409
ST03109 | PRJ038 | CL008 | Reliance Retail | Delhi Site-016 | Delhi | North | 200 | Installation Done | 2025-12-08 | 2026-01-30 | 2026-02-04 | 2026-02-28 |  | 12 | Marginal | Victor Kannan | 113443
ST03110 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-017 | Gurgaon | North | 10 | Live | 2025-12-02 | 2026-01-26 | 2026-01-31 | 2026-02-23 | 2026-02-26 | 5 | Met | Farhan Chada | 93808
ST03111 | PRJ038 | CL008 | Reliance Retail | Delhi Site-018 | Delhi | North | 20 | Installation Done | 2025-11-26 | 2026-01-12 | 2026-01-07 | 2026-02-01 |  | 12 | Marginal | Nitesh Raghavan | 207349
ST03112 | PRJ038 | CL008 | Reliance Retail | Delhi Site-019 | Delhi | North | 20 | ROW In Progress | 2025-11-26 | 2025-12-26 |  | 2026-01-11 |  | 0 | Met | Girik Khalsa | 144902
ST03113 | PRJ038 | CL008 | Reliance Retail | Noida Site-020 | Noida | North | 50 | Installation Scheduled | 2025-12-04 | 2026-01-03 | 2026-01-05 | 2026-01-24 |  | 6 | Met | Devansh Nigam | 45843
ST03114 | PRJ038 | CL008 | Reliance Retail | Noida Site-021 | Noida | North | 50 | Survey Pending | 2025-12-04 | 2026-01-30 |  | 2026-02-12 |  | 5 | Met | Tara Dhar | 255845
ST03115 | PRJ038 | CL008 | Reliance Retail | Noida Site-022 | Noida | North | 200 | Live | 2025-11-21 | 2025-12-21 | 2025-12-16 | 2026-01-03 | 2026-01-04 | 0 | Met | Ikbal Kothari | 101361
ST03116 | PRJ038 | CL008 | Reliance Retail | Delhi Site-023 | Delhi | North | 20 | Testing | 2025-11-25 | 2025-12-15 | 2025-12-10 | 2026-01-03 |  | 12 | Marginal | Farhan Chada | 65548
ST03117 | PRJ038 | CL008 | Reliance Retail | Noida Site-024 | Noida | North | 200 | Live | 2025-12-09 | 2026-01-22 | 2026-01-21 | 2026-02-02 | 2026-02-08 | 0 | Met | Advay Contractor | 249934
ST03118 | PRJ038 | CL008 | Reliance Retail | Delhi Site-025 | Delhi | North | 50 | Testing | 2025-11-16 | 2025-12-28 | 2026-01-01 | 2026-01-23 |  | 12 | Marginal | Mohammed Gupta | 102020
ST03119 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-026 | Gurgaon | North | 200 | Installation Done | 2025-11-30 | 2026-01-27 | 2026-02-05 | 2026-02-12 |  | 12 | Marginal | Yashica Cherian | 116013
ST03120 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-027 | Gurgaon | North | 200 | Live | 2025-11-25 | 2025-12-30 | 2025-12-28 | 2026-01-20 | 2026-01-19 | 0 | Met | Yashica Issac | 172407
ST03121 | PRJ038 | CL008 | Reliance Retail | Noida Site-028 | Noida | North | 20 | Live | 2025-11-21 | 2026-01-12 | 2026-01-11 | 2026-02-04 | 2026-02-09 | 0 | Met | Ikbal Kothari | 272560
ST03122 | PRJ038 | CL008 | Reliance Retail | Delhi Site-029 | Delhi | North | 100 | Installation Done | 2025-11-20 | 2026-01-02 | 2026-01-08 | 2026-02-01 |  | 12 | Marginal | Tanay Rattan | 247900
ST03123 | PRJ038 | CL008 | Reliance Retail | Delhi Site-030 | Delhi | North | 200 | Installation Scheduled | 2025-11-25 | 2026-01-21 | 2026-01-17 | 2026-02-07 |  | 0 | Met | Advay Contractor | 195781
ST03124 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-031 | Jaipur | North | 100 | Live | 2025-12-04 | 2026-01-14 | 2026-01-18 | 2026-02-01 | 2026-02-12 | 4 | Met | Devansh Rajan | 222001
ST03125 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-032 | Gurgaon | North | 50 | Survey Pending | 2025-12-07 | 2026-01-14 |  | 2026-02-09 |  | 8 | Marginal | Upadhriti Wadhwa | 276938
ST03126 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-033 | Gurgaon | North | 50 | Live | 2025-12-01 | 2026-01-26 | 2026-01-25 | 2026-02-25 | 2026-03-02 | 0 | Met | Niharika Sunder | 231605
ST03127 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-034 | Gurgaon | North | 200 | Survey Pending | 2025-11-25 | 2025-12-16 |  | 2026-01-09 |  | 6 | Met | Ranveer Yadav | 135877
ST03128 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-035 | Gurgaon | North | 200 | Testing | 2025-12-10 | 2026-01-12 | 2026-01-18 | 2026-02-01 |  | 12 | Marginal | Priya Rastogi | 270130
ST03129 | PRJ038 | CL008 | Reliance Retail | Delhi Site-036 | Delhi | North | 100 | Installation Done | 2025-12-07 | 2026-01-04 | 2026-01-03 | 2026-01-28 |  | 12 | Marginal | Irya Sampath | 123649
ST03130 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-037 | Jaipur | North | 50 | Live | 2025-11-29 | 2026-01-28 | 2026-02-07 | 2026-02-22 | 2026-02-27 | 10 | Marginal | Isaac Patil | 141976
ST03131 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-038 | Gurgaon | North | 20 | Live | 2025-11-18 | 2025-12-16 | 2025-12-17 | 2026-01-11 | 2026-01-22 | 1 | Met | Ekansh Balay | 238111
ST03132 | PRJ038 | CL008 | Reliance Retail | Noida Site-039 | Noida | North | 100 | Installation Done | 2025-11-30 | 2026-01-28 | 2026-01-24 | 2026-02-07 |  | 12 | Marginal | Tara Dhar | 231304
ST03133 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-040 | Gurgaon | North | 200 | Live | 2025-11-26 | 2026-01-23 | 2026-01-27 | 2026-02-19 | 2026-02-25 | 4 | Met | Tanay Rattan | 166069
ST03134 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-041 | Gurgaon | North | 200 | Pending Acceptance | 2025-11-18 | 2026-01-04 | 2026-01-12 | 2026-01-18 | 2026-01-21 | 8 | Marginal | Unni Bhagat | 251593
ST03135 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-042 | Jaipur | North | 200 | Live | 2025-11-30 | 2025-12-27 | 2025-12-26 | 2026-01-16 | 2026-01-24 | 0 | Met | Alka Wable | 135048
ST03136 | PRJ038 | CL008 | Reliance Retail | Delhi Site-043 | Delhi | North | 200 | Pending Acceptance | 2025-12-09 | 2026-01-26 | 2026-02-03 | 2026-02-19 | 2026-02-24 | 8 | Marginal | Anamika Kanda | 143462
ST03137 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-044 | Gurgaon | North | 100 | ROW In Progress | 2025-11-19 | 2025-12-18 |  | 2026-01-12 |  | 2 | Met | Chandresh Zachariah | 139488
ST03138 | PRJ038 | CL008 | Reliance Retail | Noida Site-045 | Noida | North | 50 | Live | 2025-11-24 | 2026-01-06 | 2026-01-04 | 2026-02-05 | 2026-02-08 | 0 | Met | Devansh Rajan | 175137
ST03139 | PRJ038 | CL008 | Reliance Retail | Delhi Site-046 | Delhi | North | 20 | Survey Pending | 2025-11-24 | 2026-01-06 |  | 2026-01-26 |  | 8 | Marginal | Ekavir Varkey | 137587
ST03140 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-047 | Gurgaon | North | 10 | Testing | 2025-11-25 | 2026-01-07 | 2026-01-15 | 2026-01-22 |  | 12 | Marginal | Nitesh Raghavan | 191340
ST03141 | PRJ038 | CL008 | Reliance Retail | Noida Site-048 | Noida | North | 10 | Installation Scheduled | 2025-12-10 | 2026-01-29 | 2026-02-06 | 2026-02-21 |  | 8 | Marginal | Ikbal Kothari | 243869
ST03142 | PRJ038 | CL008 | Reliance Retail | Delhi Site-049 | Delhi | North | 100 | Installation Scheduled | 2025-12-10 | 2026-02-05 | 2026-02-02 | 2026-02-15 |  | 8 | Marginal | Simon Tata | 121992
ST03143 | PRJ038 | CL008 | Reliance Retail | Noida Site-050 | Noida | North | 200 | Survey Pending | 2025-11-17 | 2025-12-30 |  | 2026-01-19 |  | 7 | Met | Girindra Chatterjee | 245791
ST03144 | PRJ038 | CL008 | Reliance Retail | Noida Site-051 | Noida | North | 20 | ROW In Progress | 2025-12-07 | 2026-02-02 |  | 2026-02-26 |  | 3 | Met | Chandresh Zachariah | 190748
ST03145 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-052 | Jaipur | North | 10 | Live | 2025-12-09 | 2026-02-06 | 2026-02-08 | 2026-02-18 | 2026-02-28 | 2 | Met | Yatin Baral | 188214
ST03146 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-053 | Gurgaon | North | 200 | Live | 2025-11-15 | 2025-12-10 | 2025-12-06 | 2025-12-31 | 2026-01-08 | 0 | Met | Farhan Chada | 201556
ST03147 | PRJ038 | CL008 | Reliance Retail | Delhi Site-054 | Delhi | North | 20 | ROW In Progress | 2025-11-26 | 2025-12-29 |  | 2026-01-13 |  | 0 | Met | Girik Khalsa | 119720
ST03148 | PRJ038 | CL008 | Reliance Retail | Delhi Site-055 | Delhi | North | 200 | Survey Pending | 2025-12-07 | 2026-01-08 |  | 2026-01-25 |  | 3 | Met | Madhavi Lanka | 108699
ST03149 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-056 | Jaipur | North | 200 | Testing | 2025-11-20 | 2025-12-10 | 2025-12-12 | 2026-01-06 |  | 12 | Marginal | Mohammed Gupta | 180989
ST03150 | PRJ038 | CL008 | Reliance Retail | Noida Site-057 | Noida | North | 50 | Pending Acceptance | 2025-11-17 | 2026-01-11 | 2026-01-12 | 2026-02-06 | 2026-02-12 | 1 | Met | Mohammed Gupta | 181244
ST03151 | PRJ038 | CL008 | Reliance Retail | Delhi Site-058 | Delhi | North | 50 | Live | 2025-11-28 | 2026-01-15 | 2026-01-23 | 2026-02-06 | 2026-02-10 | 8 | Marginal | Radhika Dugar | 238763
ST03152 | PRJ038 | CL008 | Reliance Retail | Delhi Site-059 | Delhi | North | 50 | Testing | 2025-11-24 | 2026-01-15 | 2026-01-12 | 2026-01-30 |  | 12 | Marginal | Isaac Patil | 239735
ST03153 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-060 | Jaipur | North | 50 | Installation Done | 2025-11-30 | 2026-01-06 | 2026-01-05 | 2026-01-29 |  | 12 | Marginal | Ekavir Bhargava | 267357
ST03154 | PRJ038 | CL008 | Reliance Retail | Delhi Site-061 | Delhi | North | 200 | Installation Scheduled | 2025-12-05 | 2026-01-29 | 2026-01-30 | 2026-02-13 |  | 7 | Met | Madhavi Lanka | 151552
ST03155 | PRJ038 | CL008 | Reliance Retail | Noida Site-062 | Noida | North | 100 | Installation Done | 2025-12-10 | 2026-01-19 | 2026-01-16 | 2026-02-15 |  | 12 | Marginal | Bhavika Sampath | 261213
ST03156 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-063 | Gurgaon | North | 100 | Installation Scheduled | 2025-12-03 | 2026-01-02 | 2026-01-06 | 2026-01-24 |  | 8 | Marginal | Gavin Batta | 125204
ST03157 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-064 | Gurgaon | North | 10 | Installation Done | 2025-12-04 | 2026-01-06 | 2026-01-11 | 2026-01-23 |  | 12 | Marginal | Girindra Chatterjee | 131581
ST03158 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-065 | Jaipur | North | 50 | Installation Done | 2025-12-05 | 2026-01-03 | 2026-01-04 | 2026-02-01 |  | 12 | Marginal | Nihal Shere | 85002
ST03159 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-066 | Jaipur | North | 100 | Live | 2025-12-03 | 2025-12-23 | 2025-12-30 | 2026-01-10 | 2026-01-19 | 7 | Met | Tanay Rattan | 220026
ST03160 | PRJ038 | CL008 | Reliance Retail | Delhi Site-067 | Delhi | North | 20 | Pending Acceptance | 2025-11-18 | 2026-01-11 | 2026-01-11 | 2026-01-25 | 2026-01-26 | 0 | Met | Radhika Dugar | 114806
ST03161 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-068 | Jaipur | North | 100 | Testing | 2025-11-19 | 2025-12-20 | 2025-12-16 | 2026-01-06 |  | 12 | Marginal | Ekapad Walia | 105398
ST03162 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-069 | Jaipur | North | 20 | Live | 2025-12-09 | 2026-01-15 | 2026-01-11 | 2026-02-06 | 2026-02-05 | 0 | Met | Niharika Sunder | 173959
ST03163 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-070 | Gurgaon | North | 10 | Live | 2025-12-01 | 2026-01-10 | 2026-01-20 | 2026-02-05 | 2026-02-09 | 10 | Marginal | Devansh Nigam | 251365
ST03164 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-071 | Gurgaon | North | 100 | Installation Scheduled | 2025-11-27 | 2026-01-06 | 2026-01-15 | 2026-01-28 |  | 5 | Met | Yatin Baral | 146023
ST03165 | PRJ038 | CL008 | Reliance Retail | Delhi Site-072 | Delhi | North | 100 | Survey Pending | 2025-11-26 | 2026-01-06 |  | 2026-01-18 |  | 2 | Met | Dakshesh Trivedi | 215828
ST03166 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-073 | Jaipur | North | 20 | Installation Scheduled | 2025-11-23 | 2026-01-20 | 2026-01-23 | 2026-02-05 |  | 6 | Met | Kashvi Edwin | 167392
ST03167 | PRJ038 | CL008 | Reliance Retail | Delhi Site-074 | Delhi | North | 20 | Installation Done | 2025-11-18 | 2025-12-24 | 2026-01-01 | 2026-01-14 |  | 12 | Marginal | Jai Kota | 254619
ST03168 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-075 | Gurgaon | North | 200 | ROW In Progress | 2025-11-16 | 2025-12-24 |  | 2026-01-07 |  | 1 | Met | Madhavi Lanka | 161149
ST03169 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-076 | Gurgaon | North | 20 | Installation Done | 2025-11-18 | 2025-12-31 | 2025-12-30 | 2026-01-11 |  | 12 | Marginal | Girindra Chatterjee | 66711
ST03170 | PRJ038 | CL008 | Reliance Retail | Delhi Site-077 | Delhi | North | 100 | Testing | 2025-12-01 | 2026-01-12 | 2026-01-07 | 2026-02-01 |  | 12 | Marginal | Logan Sami | 209455
ST03171 | PRJ038 | CL008 | Reliance Retail | Delhi Site-078 | Delhi | North | 10 | Installation Scheduled | 2025-11-25 | 2026-01-19 | 2026-01-24 | 2026-01-30 |  | 8 | Marginal | Devansh Nigam | 94161
ST03172 | PRJ038 | CL008 | Reliance Retail | Noida Site-079 | Noida | North | 20 | Live | 2025-12-07 | 2026-02-01 | 2026-02-11 | 2026-02-24 | 2026-03-06 | 10 | Marginal | Isaac Patil | 268925
ST03173 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-080 | Jaipur | North | 20 | Live | 2025-12-07 | 2025-12-30 | 2026-01-02 | 2026-01-13 | 2026-01-16 | 3 | Met | Michael Dutta | 45409
ST03174 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-081 | Jaipur | North | 100 | Survey Pending | 2025-12-08 | 2026-01-29 |  | 2026-02-27 |  | 1 | Met | Dominic Kakar | 55003
ST03175 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-082 | Gurgaon | North | 50 | ROW In Progress | 2025-12-04 | 2025-12-29 |  | 2026-01-24 |  | 4 | Met | Teerth Bhardwaj | 264832
ST03176 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-083 | Gurgaon | North | 200 | Testing | 2025-12-09 | 2026-01-24 | 2026-01-30 | 2026-02-22 |  | 12 | Marginal | Anamika Kanda | 132491
ST03177 | PRJ038 | CL008 | Reliance Retail | Noida Site-084 | Noida | North | 200 | Installation Done | 2025-12-07 | 2026-01-07 | 2026-01-13 | 2026-02-05 |  | 12 | Marginal | Nitesh Raghavan | 70082
ST03178 | PRJ038 | CL008 | Reliance Retail | Delhi Site-085 | Delhi | North | 10 | Live | 2025-11-21 | 2025-12-31 | 2026-01-01 | 2026-01-11 | 2026-01-17 | 1 | Met | Dakshesh Trivedi | 170602
ST03179 | PRJ038 | CL008 | Reliance Retail | Gurgaon Site-086 | Gurgaon | North | 200 | ROW In Progress | 2025-11-16 | 2026-01-02 |  | 2026-01-14 |  | 0 | Met | Yashica Cherian | 278162
ST03180 | PRJ038 | CL008 | Reliance Retail | Noida Site-087 | Noida | North | 50 | ROW In Progress | 2025-12-02 | 2026-01-28 |  | 2026-02-21 |  | 4 | Met | Farhan Chada | 260772
ST03181 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-088 | Jaipur | North | 50 | ROW In Progress | 2025-11-29 | 2026-01-03 |  | 2026-01-17 |  | 0 | Met | Raksha Varughese | 66675
ST03182 | PRJ038 | CL008 | Reliance Retail | Noida Site-089 | Noida | North | 100 | Installation Done | 2025-11-22 | 2025-12-17 | 2025-12-17 | 2026-01-09 |  | 12 | Marginal | Niharika Sunder | 137114
ST03183 | PRJ038 | CL008 | Reliance Retail | Jaipur Site-090 | Jaipur | North | 100 | Live | 2025-11-20 | 2025-12-24 | 2025-12-25 | 2026-01-15 | 2026-01-14 | 1 | Met | Ikbal Kothari | 134064
ST03184 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-001 | Hyderabad | South | 100 | Testing | 2025-10-15 | 2025-12-03 | 2025-11-28 | 2025-12-28 |  | 12 | Marginal | Logan Sami | 46758
ST03185 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-002 | Hyderabad | South | 20 | Installation Done | 2025-10-04 | 2025-11-23 | 2025-11-28 | 2025-12-16 |  | 12 | Marginal | Isaac Patil | 163008
ST03186 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-003 | Bengaluru | South | 100 | Testing | 2025-10-09 | 2025-11-24 | 2025-11-19 | 2025-12-08 |  | 12 | Marginal | Liam Koshy | 76793
ST03187 | PRJ039 | CL008 | Reliance Retail | Kochi Site-004 | Kochi | South | 20 | Installation Done | 2025-10-04 | 2025-10-31 | 2025-10-26 | 2025-11-29 |  | 12 | Marginal | Madhavi Lanka | 264791
ST03188 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-005 | Bengaluru | South | 10 | Testing | 2025-10-06 | 2025-12-02 | 2025-12-05 | 2025-12-30 |  | 12 | Marginal | Liam Koshy | 216358
ST03189 | PRJ039 | CL008 | Reliance Retail | Kochi Site-006 | Kochi | South | 20 | Survey Pending | 2025-10-10 | 2025-11-07 |  | 2025-12-02 |  | 6 | Met | Daksh Karnik | 135367
ST03190 | PRJ039 | CL008 | Reliance Retail | Kochi Site-007 | Kochi | South | 50 | Installation Done | 2025-10-19 | 2025-12-09 | 2025-12-05 | 2025-12-21 |  | 12 | Marginal | Dipta Bhandari | 80161
ST03191 | PRJ039 | CL008 | Reliance Retail | Kochi Site-008 | Kochi | South | 200 | Installation Done | 2025-10-07 | 2025-11-02 | 2025-11-07 | 2025-11-25 |  | 12 | Marginal | Girik Khalsa | 125192
ST03192 | PRJ039 | CL008 | Reliance Retail | Kochi Site-009 | Kochi | South | 200 | Survey Pending | 2025-10-19 | 2025-12-06 |  | 2025-12-22 |  | 5 | Met | Ranveer Yadav | 147326
ST03193 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-010 | Bengaluru | South | 20 | Pending Acceptance | 2025-10-09 | 2025-11-07 | 2025-11-03 | 2025-11-28 | 2025-11-28 | 0 | Met | Logan Sami | 150190
ST03194 | PRJ039 | CL008 | Reliance Retail | Chennai Site-011 | Chennai | South | 50 | Live | 2025-10-27 | 2025-12-22 | 2025-12-31 | 2026-01-10 | 2026-01-12 | 9 | Marginal | Dominic Kakar | 57768
ST03195 | PRJ039 | CL008 | Reliance Retail | Kochi Site-012 | Kochi | South | 100 | Installation Done | 2025-10-17 | 2025-12-05 | 2025-12-08 | 2025-12-31 |  | 12 | Marginal | Vansha Thakkar | 94581
ST03196 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-013 | Hyderabad | South | 100 | Testing | 2025-10-21 | 2025-11-18 | 2025-11-16 | 2025-12-13 |  | 12 | Marginal | Devansh Nigam | 178586
ST03197 | PRJ039 | CL008 | Reliance Retail | Kochi Site-014 | Kochi | South | 50 | Pending Acceptance | 2025-10-13 | 2025-12-03 | 2025-12-12 | 2026-01-01 | 2026-01-05 | 9 | Marginal | Irya Sampath | 216600
ST03198 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-015 | Hyderabad | South | 10 | Installation Scheduled | 2025-10-11 | 2025-11-23 | 2025-11-30 | 2025-12-22 |  | 7 | Met | Ekiya Suresh | 136925
ST03199 | PRJ039 | CL008 | Reliance Retail | Chennai Site-016 | Chennai | South | 50 | Live | 2025-10-06 | 2025-12-04 | 2025-12-05 | 2025-12-15 | 2025-12-24 | 1 | Met | Nitesh Raghavan | 212880
ST03200 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-017 | Bengaluru | South | 200 | ROW In Progress | 2025-10-29 | 2025-12-19 |  | 2026-01-01 |  | 1 | Met | Tanay Rattan | 198424
ST03201 | PRJ039 | CL008 | Reliance Retail | Chennai Site-018 | Chennai | South | 20 | Installation Scheduled | 2025-10-11 | 2025-11-02 | 2025-11-03 | 2025-12-02 |  | 1 | Met | Dakshesh Trivedi | 190964
ST03202 | PRJ039 | CL008 | Reliance Retail | Chennai Site-019 | Chennai | South | 200 | Survey Pending | 2025-10-24 | 2025-12-08 |  | 2026-01-03 |  | 2 | Met | Dakshesh Trivedi | 143018
ST03203 | PRJ039 | CL008 | Reliance Retail | Chennai Site-020 | Chennai | South | 20 | Installation Scheduled | 2025-10-14 | 2025-11-14 | 2025-11-22 | 2025-11-29 |  | 0 | Met | Ekavir Bhargava | 248306
ST03204 | PRJ039 | CL008 | Reliance Retail | Kochi Site-021 | Kochi | South | 20 | Installation Scheduled | 2025-10-20 | 2025-11-16 | 2025-11-14 | 2025-12-01 |  | 8 | Marginal | Girik Khalsa | 199898
ST03205 | PRJ039 | CL008 | Reliance Retail | Chennai Site-022 | Chennai | South | 20 | Installation Scheduled | 2025-10-15 | 2025-11-11 | 2025-11-20 | 2025-11-28 |  | 2 | Met | Radhika Dugar | 196783
ST03206 | PRJ039 | CL008 | Reliance Retail | Chennai Site-023 | Chennai | South | 50 | ROW In Progress | 2025-10-24 | 2025-12-12 |  | 2026-01-07 |  | 6 | Met | Nihal Shere | 252936
ST03207 | PRJ039 | CL008 | Reliance Retail | Chennai Site-024 | Chennai | South | 10 | Testing | 2025-10-12 | 2025-11-29 | 2025-12-05 | 2025-12-29 |  | 12 | Marginal | Urvashi Ray | 130368
ST03208 | PRJ039 | CL008 | Reliance Retail | Kochi Site-025 | Kochi | South | 20 | Live | 2025-10-19 | 2025-12-08 | 2025-12-05 | 2026-01-01 | 2026-01-07 | 0 | Met | Priya Rastogi | 77909
ST03209 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-026 | Hyderabad | South | 200 | Installation Scheduled | 2025-10-24 | 2025-12-03 | 2025-12-04 | 2025-12-24 |  | 3 | Met | Priya Rastogi | 63011
ST03210 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-027 | Hyderabad | South | 20 | Installation Done | 2025-10-05 | 2025-12-01 | 2025-11-30 | 2025-12-25 |  | 12 | Marginal | Simon Tata | 207241
ST03211 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-028 | Hyderabad | South | 50 | Installation Done | 2025-10-27 | 2025-11-28 | 2025-12-05 | 2025-12-26 |  | 12 | Marginal | Mohammed Gupta | 213729
ST03212 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-029 | Hyderabad | South | 200 | Pending Acceptance | 2025-10-09 | 2025-12-07 | 2025-12-10 | 2025-12-23 | 2025-12-26 | 3 | Met | Michael Dutta | 151676
ST03213 | PRJ039 | CL008 | Reliance Retail | Kochi Site-030 | Kochi | South | 50 | Live | 2025-10-29 | 2025-12-17 | 2025-12-12 | 2026-01-12 | 2026-01-19 | 0 | Met | Anamika Kanda | 149788
ST03214 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-031 | Hyderabad | South | 10 | Installation Scheduled | 2025-10-22 | 2025-11-28 | 2025-12-01 | 2025-12-11 |  | 0 | Met | Anamika Kanda | 123601
ST03215 | PRJ039 | CL008 | Reliance Retail | Chennai Site-032 | Chennai | South | 50 | Live | 2025-10-28 | 2025-12-24 | 2026-01-03 | 2026-01-11 | 2026-01-14 | 10 | Marginal | Ekavir Bhargava | 265592
ST03216 | PRJ039 | CL008 | Reliance Retail | Chennai Site-033 | Chennai | South | 200 | ROW In Progress | 2025-10-04 | 2025-10-30 |  | 2025-11-25 |  | 1 | Met | Tanay Rattan | 205247
ST03217 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-034 | Bengaluru | South | 50 | Installation Scheduled | 2025-10-08 | 2025-12-07 | 2025-12-09 | 2025-12-28 |  | 7 | Met | Ekapad Walia | 183587
ST03218 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-035 | Hyderabad | South | 100 | Live | 2025-10-24 | 2025-11-17 | 2025-11-15 | 2025-11-29 | 2025-12-06 | 0 | Met | Diya Rattan | 269157
ST03219 | PRJ039 | CL008 | Reliance Retail | Chennai Site-036 | Chennai | South | 100 | Installation Scheduled | 2025-10-15 | 2025-11-29 | 2025-11-25 | 2025-12-29 |  | 1 | Met | Ekansh Balay | 265610
ST03220 | PRJ039 | CL008 | Reliance Retail | Chennai Site-037 | Chennai | South | 100 | Installation Done | 2025-10-13 | 2025-11-23 | 2025-11-28 | 2025-12-12 |  | 12 | Marginal | Yashica Issac | 45851
ST03221 | PRJ039 | CL008 | Reliance Retail | Chennai Site-038 | Chennai | South | 20 | Pending Acceptance | 2025-10-11 | 2025-11-21 | 2025-11-24 | 2025-12-13 | 2025-12-15 | 3 | Met | Raksha Varughese | 194321
ST03222 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-039 | Hyderabad | South | 20 | Survey Pending | 2025-10-06 | 2025-11-23 |  | 2025-12-10 |  | 4 | Met | Ekavir Bhargava | 145904
ST03223 | PRJ039 | CL008 | Reliance Retail | Kochi Site-040 | Kochi | South | 10 | Pending Acceptance | 2025-10-29 | 2025-12-27 | 2026-01-01 | 2026-01-14 | 2026-01-26 | 5 | Met | Simon Tata | 154345
ST03224 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-041 | Bengaluru | South | 200 | Live | 2025-10-11 | 2025-12-06 | 2025-12-03 | 2025-12-17 | 2025-12-28 | 0 | Met | Ikbal Kothari | 73404
ST03225 | PRJ039 | CL008 | Reliance Retail | Kochi Site-042 | Kochi | South | 20 | ROW In Progress | 2025-10-08 | 2025-11-01 |  | 2025-11-19 |  | 1 | Met | Ekbal Garg | 89684
ST03226 | PRJ039 | CL008 | Reliance Retail | Chennai Site-043 | Chennai | South | 100 | Installation Scheduled | 2025-10-07 | 2025-11-27 | 2025-12-02 | 2025-12-19 |  | 1 | Met | Dominic Kakar | 204219
ST03227 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-044 | Hyderabad | South | 10 | Installation Done | 2025-10-25 | 2025-11-19 | 2025-11-24 | 2025-12-07 |  | 12 | Marginal | Wriddhish Bhardwaj | 102234
ST03228 | PRJ039 | CL008 | Reliance Retail | Chennai Site-045 | Chennai | South | 50 | Installation Done | 2025-10-15 | 2025-11-04 | 2025-11-03 | 2025-11-30 |  | 12 | Marginal | Liam Koshy | 131177
ST03229 | PRJ039 | CL008 | Reliance Retail | Kochi Site-046 | Kochi | South | 50 | Live | 2025-10-14 | 2025-12-08 | 2025-12-06 | 2026-01-01 | 2026-01-01 | 0 | Met | Vansha Thakkar | 188865
ST03230 | PRJ039 | CL008 | Reliance Retail | Chennai Site-047 | Chennai | South | 200 | Testing | 2025-10-26 | 2025-12-06 | 2025-12-06 | 2025-12-25 |  | 12 | Marginal | Ekiya Suresh | 89612
ST03231 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-048 | Bengaluru | South | 200 | Live | 2025-10-07 | 2025-11-02 | 2025-11-06 | 2025-11-17 | 2025-11-22 | 4 | Met | Upadhriti Wadhwa | 121072
ST03232 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-049 | Bengaluru | South | 100 | Installation Scheduled | 2025-10-28 | 2025-11-22 | 2025-11-23 | 2025-12-18 |  | 5 | Met | Wriddhish Bhardwaj | 197171
ST03233 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-050 | Bengaluru | South | 10 | Installation Scheduled | 2025-10-09 | 2025-11-24 | 2025-11-29 | 2025-12-08 |  | 0 | Met | Yashica Issac | 260165
ST03234 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-051 | Bengaluru | South | 200 | ROW In Progress | 2025-10-13 | 2025-11-04 |  | 2025-11-18 |  | 0 | Met | Yatin Baral | 214502
ST03235 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-052 | Hyderabad | South | 200 | Live | 2025-10-17 | 2025-12-15 | 2025-12-22 | 2026-01-06 | 2026-01-14 | 7 | Met | Arya Sunder | 187543
ST03236 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-053 | Bengaluru | South | 20 | Live | 2025-10-08 | 2025-11-26 | 2025-11-26 | 2025-12-25 | 2025-12-25 | 0 | Met | Faqid Savant | 164816
ST03237 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-054 | Hyderabad | South | 50 | Pending Acceptance | 2025-10-07 | 2025-11-22 | 2025-11-26 | 2025-12-10 | 2025-12-10 | 4 | Met | Wriddhish Bhardwaj | 253639
ST03238 | PRJ039 | CL008 | Reliance Retail | Chennai Site-055 | Chennai | South | 10 | Live | 2025-10-21 | 2025-11-11 | 2025-11-09 | 2025-11-24 | 2025-11-27 | 0 | Met | Urvashi Ray | 276386
ST03239 | PRJ039 | CL008 | Reliance Retail | Chennai Site-056 | Chennai | South | 20 | Installation Scheduled | 2025-10-15 | 2025-11-29 | 2025-11-29 | 2025-12-16 |  | 4 | Met | Jai Kota | 232502
ST03240 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-057 | Bengaluru | South | 100 | Live | 2025-10-08 | 2025-11-13 | 2025-11-20 | 2025-11-28 | 2025-12-07 | 7 | Met | Theodore Devi | 210080
ST03241 | PRJ039 | CL008 | Reliance Retail | Chennai Site-058 | Chennai | South | 50 | Pending Acceptance | 2025-10-09 | 2025-10-29 | 2025-10-28 | 2025-11-18 | 2025-11-22 | 0 | Met | Yashica Issac | 108371
ST03242 | PRJ039 | CL008 | Reliance Retail | Kochi Site-059 | Kochi | South | 10 | Installation Done | 2025-10-05 | 2025-11-22 | 2025-12-02 | 2025-12-14 |  | 12 | Marginal | Kevin Solanki | 247573
ST03243 | PRJ039 | CL008 | Reliance Retail | Chennai Site-060 | Chennai | South | 100 | Testing | 2025-10-27 | 2025-11-28 | 2025-12-08 | 2025-12-28 |  | 12 | Marginal | Chandresh Zachariah | 168146
ST03244 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-061 | Hyderabad | South | 10 | Survey Pending | 2025-10-21 | 2025-12-11 |  | 2026-01-05 |  | 2 | Met | Dominic Kakar | 162655
ST03245 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-062 | Hyderabad | South | 20 | ROW In Progress | 2025-10-13 | 2025-11-05 |  | 2025-11-15 |  | 3 | Met | Diya Rattan | 276334
ST03246 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-063 | Hyderabad | South | 100 | Live | 2025-10-04 | 2025-12-01 | 2025-12-11 | 2025-12-15 | 2025-12-21 | 10 | Marginal | Radhika Dugar | 135351
ST03247 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-064 | Hyderabad | South | 200 | ROW In Progress | 2025-10-15 | 2025-11-22 |  | 2025-12-04 |  | 6 | Met | Ekapad Walia | 200589
ST03248 | PRJ039 | CL008 | Reliance Retail | Chennai Site-065 | Chennai | South | 20 | Installation Done | 2025-10-17 | 2025-11-20 | 2025-11-25 | 2025-12-05 |  | 12 | Marginal | Devansh Rajan | 256009
ST03249 | PRJ039 | CL008 | Reliance Retail | Chennai Site-066 | Chennai | South | 20 | Live | 2025-10-20 | 2025-12-15 | 2025-12-16 | 2026-01-06 | 2026-01-09 | 1 | Met | Teerth Bhardwaj | 188990
ST03250 | PRJ039 | CL008 | Reliance Retail | Kochi Site-067 | Kochi | South | 20 | Installation Done | 2025-10-19 | 2025-11-10 | 2025-11-13 | 2025-11-25 |  | 12 | Marginal | Ikbal Kothari | 164697
ST03251 | PRJ039 | CL008 | Reliance Retail | Chennai Site-068 | Chennai | South | 10 | Survey Pending | 2025-10-23 | 2025-12-20 |  | 2026-01-10 |  | 3 | Met | Theodore Devi | 235176
ST03252 | PRJ039 | CL008 | Reliance Retail | Kochi Site-069 | Kochi | South | 50 | Live | 2025-10-22 | 2025-11-22 | 2025-11-19 | 2025-12-22 | 2025-12-25 | 0 | Met | Raksha Varughese | 126909
ST03253 | PRJ039 | CL008 | Reliance Retail | Kochi Site-070 | Kochi | South | 100 | Live | 2025-10-15 | 2025-11-04 | 2025-11-14 | 2025-12-04 | 2025-12-01 | 10 | Marginal | Dakshesh Trivedi | 143292
ST03254 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-071 | Bengaluru | South | 20 | Live | 2025-10-21 | 2025-11-29 | 2025-12-03 | 2025-12-27 | 2026-01-05 | 4 | Met | Darsh Rau | 164555
ST03255 | PRJ039 | CL008 | Reliance Retail | Kochi Site-072 | Kochi | South | 20 | Installation Done | 2025-10-26 | 2025-12-11 | 2025-12-10 | 2025-12-23 |  | 12 | Marginal | Nihal Shere | 257825
ST03256 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-073 | Hyderabad | South | 50 | Pending Acceptance | 2025-10-15 | 2025-11-08 | 2025-11-11 | 2025-12-05 | 2025-12-10 | 3 | Met | Ekavir Bhargava | 241149
ST03257 | PRJ039 | CL008 | Reliance Retail | Chennai Site-074 | Chennai | South | 10 | ROW In Progress | 2025-10-15 | 2025-12-11 |  | 2025-12-31 |  | 5 | Met | Farhan Chada | 259206
ST03258 | PRJ039 | CL008 | Reliance Retail | Chennai Site-075 | Chennai | South | 10 | Live | 2025-10-27 | 2025-12-06 | 2025-12-03 | 2025-12-27 | 2026-01-02 | 0 | Met | Niharika Sunder | 99570
ST03259 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-076 | Hyderabad | South | 100 | ROW In Progress | 2025-10-27 | 2025-11-22 |  | 2025-12-02 |  | 6 | Met | Kevin Solanki | 134817
ST03260 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-077 | Bengaluru | South | 200 | Live | 2025-10-29 | 2025-12-15 | 2025-12-17 | 2026-01-06 | 2026-01-14 | 2 | Met | Nihal Shere | 268740
ST03261 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-078 | Hyderabad | South | 20 | Live | 2025-10-12 | 2025-11-05 | 2025-11-15 | 2025-11-22 | 2025-12-04 | 10 | Marginal | Aarush Lall | 107195
ST03262 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-079 | Hyderabad | South | 10 | ROW In Progress | 2025-10-26 | 2025-12-16 |  | 2026-01-11 |  | 7 | Met | Farhan Chada | 276609
ST03263 | PRJ039 | CL008 | Reliance Retail | Chennai Site-080 | Chennai | South | 100 | Installation Scheduled | 2025-10-21 | 2025-11-17 | 2025-11-16 | 2025-12-13 |  | 1 | Met | Liam Koshy | 277480
ST03264 | PRJ039 | CL008 | Reliance Retail | Chennai Site-081 | Chennai | South | 10 | Installation Done | 2025-10-13 | 2025-11-30 | 2025-12-05 | 2025-12-14 |  | 12 | Marginal | Priya Rastogi | 87265
ST03265 | PRJ039 | CL008 | Reliance Retail | Kochi Site-082 | Kochi | South | 10 | Live | 2025-10-22 | 2025-12-08 | 2025-12-10 | 2026-01-02 | 2026-01-05 | 2 | Met | Gavin Batta | 125167
ST03266 | PRJ039 | CL008 | Reliance Retail | Chennai Site-083 | Chennai | South | 10 | Installation Scheduled | 2025-10-07 | 2025-10-28 | 2025-11-04 | 2025-11-12 |  | 3 | Met | Madhavi Lanka | 236890
ST03267 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-084 | Hyderabad | South | 200 | Live | 2025-10-22 | 2025-11-27 | 2025-11-22 | 2025-12-07 | 2025-12-11 | 0 | Met | Michael Dutta | 178544
ST03268 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-085 | Bengaluru | South | 10 | Installation Scheduled | 2025-10-17 | 2025-11-25 | 2025-12-01 | 2025-12-07 |  | 0 | Met | Harini Choudhury | 62752
ST03269 | PRJ039 | CL008 | Reliance Retail | Chennai Site-086 | Chennai | South | 100 | Installation Scheduled | 2025-10-26 | 2025-12-01 | 2025-11-26 | 2025-12-28 |  | 1 | Met | Dominic Kakar | 80314
ST03270 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-087 | Hyderabad | South | 20 | Pending Acceptance | 2025-10-06 | 2025-11-22 | 2025-12-02 | 2025-12-19 | 2025-12-30 | 10 | Marginal | Isaac Patil | 244095
ST03271 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-088 | Bengaluru | South | 20 | Installation Scheduled | 2025-10-23 | 2025-12-18 | 2025-12-28 | 2025-12-28 |  | 3 | Met | Anamika Kanda | 118427
ST03272 | PRJ039 | CL008 | Reliance Retail | Chennai Site-089 | Chennai | South | 50 | Live | 2025-10-25 | 2025-12-15 | 2025-12-18 | 2025-12-31 | 2026-01-03 | 3 | Met | Kevin Solanki | 79002
ST03273 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-090 | Bengaluru | South | 50 | Survey Pending | 2025-10-15 | 2025-11-08 |  | 2025-11-19 |  | 0 | Met | Chandresh Zachariah | 45509
ST03274 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-091 | Bengaluru | South | 20 | Survey Pending | 2025-10-13 | 2025-11-09 |  | 2025-11-25 |  | 1 | Met | Unni Bhagat | 141046
ST03275 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-092 | Hyderabad | South | 100 | Pending Acceptance | 2025-10-18 | 2025-12-13 | 2025-12-17 | 2025-12-27 | 2025-12-25 | 4 | Met | Aarush Lall | 224472
ST03276 | PRJ039 | CL008 | Reliance Retail | Chennai Site-093 | Chennai | South | 10 | Live | 2025-10-23 | 2025-12-04 | 2025-12-12 | 2025-12-28 | 2025-12-29 | 8 | Marginal | Quincy Biswas | 144030
ST03277 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-094 | Bengaluru | South | 100 | Live | 2025-10-29 | 2025-12-26 | 2026-01-05 | 2026-01-22 | 2026-02-02 | 10 | Marginal | Nitesh Raghavan | 169812
ST03278 | PRJ039 | CL008 | Reliance Retail | Kochi Site-095 | Kochi | South | 20 | Pending Acceptance | 2025-10-06 | 2025-11-08 | 2025-11-18 | 2025-12-02 | 2025-12-01 | 10 | Marginal | Kabir Soman | 203982
ST03279 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-096 | Bengaluru | South | 20 | Testing | 2025-10-22 | 2025-11-25 | 2025-12-04 | 2025-12-25 |  | 12 | Marginal | Dominic Kakar | 117806
ST03280 | PRJ039 | CL008 | Reliance Retail | Kochi Site-097 | Kochi | South | 50 | Installation Scheduled | 2025-10-12 | 2025-11-24 | 2025-11-22 | 2025-12-22 |  | 4 | Met | Unni Bhagat | 238793
ST03281 | PRJ039 | CL008 | Reliance Retail | Kochi Site-098 | Kochi | South | 10 | Pending Acceptance | 2025-10-29 | 2025-11-23 | 2025-12-02 | 2025-12-10 | 2025-12-15 | 9 | Marginal | Daksh Karnik | 175713
ST03282 | PRJ039 | CL008 | Reliance Retail | Kochi Site-099 | Kochi | South | 50 | Live | 2025-10-27 | 2025-11-18 | 2025-11-20 | 2025-12-18 | 2025-12-18 | 2 | Met | Quincy Biswas | 255988
ST03283 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-100 | Hyderabad | South | 50 | Installation Done | 2025-10-23 | 2025-11-24 | 2025-11-22 | 2025-12-21 |  | 12 | Marginal | Devika Rastogi | 218454
ST03284 | PRJ039 | CL008 | Reliance Retail | Kochi Site-101 | Kochi | South | 20 | Live | 2025-10-05 | 2025-11-17 | 2025-11-20 | 2025-12-06 | 2025-12-09 | 3 | Met | Isaac Patil | 162455
ST03285 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-102 | Bengaluru | South | 200 | Live | 2025-10-14 | 2025-11-19 | 2025-11-14 | 2025-12-12 | 2025-12-16 | 0 | Met | Urvashi Ray | 267151
ST03286 | PRJ039 | CL008 | Reliance Retail | Kochi Site-103 | Kochi | South | 50 | Live | 2025-10-04 | 2025-11-01 | 2025-10-28 | 2025-11-25 | 2025-11-24 | 0 | Met | Farhan Chada | 165228
ST03287 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-104 | Hyderabad | South | 50 | ROW In Progress | 2025-10-25 | 2025-12-06 |  | 2025-12-27 |  | 5 | Met | Alka Wable | 221624
ST03288 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-105 | Hyderabad | South | 100 | Installation Scheduled | 2025-10-28 | 2025-11-19 | 2025-11-28 | 2025-12-15 |  | 6 | Met | Dipta Bhandari | 228119
ST03289 | PRJ039 | CL008 | Reliance Retail | Chennai Site-106 | Chennai | South | 100 | Live | 2025-10-27 | 2025-11-24 | 2025-11-22 | 2025-12-05 | 2025-12-03 | 0 | Met | Radhika Dugar | 223031
ST03290 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-107 | Bengaluru | South | 10 | Pending Acceptance | 2025-10-04 | 2025-12-02 | 2025-12-06 | 2025-12-27 | 2025-12-26 | 4 | Met | Ekiya Suresh | 122344
ST03291 | PRJ039 | CL008 | Reliance Retail | Kochi Site-108 | Kochi | South | 10 | ROW In Progress | 2025-10-18 | 2025-11-30 |  | 2025-12-25 |  | 8 | Marginal | Ekavir Bhargava | 69845
ST03292 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-109 | Bengaluru | South | 10 | Pending Acceptance | 2025-10-13 | 2025-12-07 | 2025-12-15 | 2025-12-30 | 2026-01-11 | 8 | Marginal | Tanay Rattan | 112400
ST03293 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-110 | Hyderabad | South | 100 | ROW In Progress | 2025-10-17 | 2025-11-14 |  | 2025-12-03 |  | 4 | Met | Tara Dhar | 227374
ST03294 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-111 | Hyderabad | South | 10 | Testing | 2025-10-17 | 2025-12-06 | 2025-12-03 | 2025-12-19 |  | 12 | Marginal | Advay Contractor | 176617
ST03295 | PRJ039 | CL008 | Reliance Retail | Kochi Site-112 | Kochi | South | 50 | Installation Done | 2025-10-04 | 2025-11-07 | 2025-11-09 | 2025-11-22 |  | 12 | Marginal | Dipta Bhandari | 248570
ST03296 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-113 | Bengaluru | South | 20 | Live | 2025-10-25 | 2025-12-02 | 2025-12-04 | 2025-12-12 | 2025-12-23 | 2 | Met | Radhika Dugar | 125729
ST03297 | PRJ039 | CL008 | Reliance Retail | Kochi Site-114 | Kochi | South | 20 | Live | 2025-10-28 | 2025-12-20 | 2025-12-30 | 2026-01-07 | 2026-01-05 | 10 | Marginal | Tara Dhar | 113362
ST03298 | PRJ039 | CL008 | Reliance Retail | Chennai Site-115 | Chennai | South | 200 | Installation Done | 2025-10-07 | 2025-11-25 | 2025-12-04 | 2025-12-24 |  | 12 | Marginal | Yatin Baral | 199635
ST03299 | PRJ039 | CL008 | Reliance Retail | Chennai Site-116 | Chennai | South | 50 | Installation Scheduled | 2025-10-22 | 2025-11-21 | 2025-11-25 | 2025-12-15 |  | 0 | Met | Advay Contractor | 72599
ST03300 | PRJ039 | CL008 | Reliance Retail | Chennai Site-117 | Chennai | South | 20 | Survey Pending | 2025-10-20 | 2025-12-06 |  | 2025-12-25 |  | 3 | Met | Raksha Varughese | 66951
ST03301 | PRJ039 | CL008 | Reliance Retail | Hyderabad Site-118 | Hyderabad | South | 20 | Pending Acceptance | 2025-10-26 | 2025-12-09 | 2025-12-15 | 2025-12-22 | 2025-12-22 | 6 | Met | Dipta Bhandari | 141260
ST03302 | PRJ039 | CL008 | Reliance Retail | Bengaluru Site-119 | Bengaluru | South | 20 | Live | 2025-10-19 | 2025-11-11 | 2025-11-06 | 2025-11-28 | 2025-12-03 | 0 | Met | Teerth Bhardwaj | 115991
ST03303 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-001 | Bhopal | Central | 50 | ROW In Progress | 2026-01-04 | 2026-01-27 |  | 2026-02-12 |  | 2 | Met | Tara Dhar | 215153
ST03304 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-002 | Bhopal | Central | 50 | Live | 2026-01-14 | 2026-03-12 | 2026-03-16 | 2026-03-29 | 2026-04-03 | 4 | Met | Yashica Cherian | 165567
ST03305 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-003 | Nagpur | Central | 100 | Testing | 2025-12-27 | 2026-01-31 | 2026-02-08 | 2026-02-12 |  | 12 | Marginal | Devansh Nigam | 194398
ST03306 | PRJ040 | CL008 | Reliance Retail | Indore Site-004 | Indore | Central | 100 | Live | 2026-01-02 | 2026-02-10 | 2026-02-16 | 2026-03-11 | 2026-03-19 | 6 | Met | Yatin Baral | 274597
ST03307 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-005 | Bhopal | Central | 50 | ROW In Progress | 2026-01-15 | 2026-02-16 |  | 2026-03-01 |  | 7 | Met | Aarush Lall | 160198
ST03308 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-006 | Nagpur | Central | 10 | ROW In Progress | 2025-12-30 | 2026-01-27 |  | 2026-02-10 |  | 4 | Met | Yashica Issac | 100909
ST03309 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-007 | Nagpur | Central | 100 | Pending Acceptance | 2026-01-04 | 2026-02-01 | 2026-02-11 | 2026-02-23 | 2026-02-23 | 10 | Marginal | Niharika Sunder | 258831
ST03310 | PRJ040 | CL008 | Reliance Retail | Indore Site-008 | Indore | Central | 50 | Live | 2026-01-16 | 2026-02-22 | 2026-02-18 | 2026-03-12 | 2026-03-21 | 0 | Met | Ranveer Yadav | 71030
ST03311 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-009 | Bhopal | Central | 10 | ROW In Progress | 2026-01-04 | 2026-02-07 |  | 2026-03-05 |  | 1 | Met | Anamika Kanda | 136806
ST03312 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-010 | Bhopal | Central | 50 | Pending Acceptance | 2026-01-14 | 2026-02-11 | 2026-02-11 | 2026-02-22 | 2026-03-06 | 0 | Met | Unni Bhagat | 199052
ST03313 | PRJ040 | CL008 | Reliance Retail | Indore Site-011 | Indore | Central | 100 | ROW In Progress | 2026-01-08 | 2026-02-05 |  | 2026-03-01 |  | 6 | Met | Dakshesh Trivedi | 253296
ST03314 | PRJ040 | CL008 | Reliance Retail | Indore Site-012 | Indore | Central | 20 | ROW In Progress | 2026-01-11 | 2026-02-13 |  | 2026-03-05 |  | 4 | Met | Siddharth Zacharia | 259936
ST03315 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-013 | Nagpur | Central | 200 | Pending Acceptance | 2026-01-06 | 2026-02-07 | 2026-02-06 | 2026-03-03 | 2026-03-06 | 0 | Met | Tanay Rattan | 246781
ST03316 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-014 | Nagpur | Central | 10 | Testing | 2025-12-25 | 2026-02-05 | 2026-02-03 | 2026-02-16 |  | 12 | Marginal | Radhika Dugar | 144445
ST03317 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-015 | Bhopal | Central | 20 | Installation Done | 2026-01-16 | 2026-02-15 | 2026-02-12 | 2026-03-05 |  | 12 | Marginal | Jai Kota | 227690
ST03318 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-016 | Nagpur | Central | 100 | Installation Done | 2026-01-10 | 2026-02-23 | 2026-02-28 | 2026-03-11 |  | 12 | Marginal | Liam Koshy | 139684
ST03319 | PRJ040 | CL008 | Reliance Retail | Indore Site-017 | Indore | Central | 10 | Installation Done | 2025-12-26 | 2026-01-16 | 2026-01-22 | 2026-01-31 |  | 12 | Marginal | Wriddhish Bhardwaj | 62168
ST03320 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-018 | Nagpur | Central | 100 | Installation Done | 2025-12-23 | 2026-02-17 | 2026-02-23 | 2026-02-28 |  | 12 | Marginal | Ekapad Walia | 265540
ST03321 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-019 | Bhopal | Central | 100 | Installation Done | 2025-12-30 | 2026-01-25 | 2026-01-24 | 2026-02-23 |  | 12 | Marginal | Wriddhish Bhardwaj | 278069
ST03322 | PRJ040 | CL008 | Reliance Retail | Indore Site-020 | Indore | Central | 100 | Pending Acceptance | 2026-01-15 | 2026-02-23 | 2026-02-28 | 2026-03-06 | 2026-03-08 | 5 | Met | Logan Sami | 204000
ST03323 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-021 | Nagpur | Central | 10 | Live | 2026-01-14 | 2026-02-04 | 2026-02-03 | 2026-02-27 | 2026-02-24 | 0 | Met | Tara Dhar | 168750
ST03324 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-022 | Bhopal | Central | 20 | ROW In Progress | 2026-01-09 | 2026-03-10 |  | 2026-04-04 |  | 1 | Met | Advay Contractor | 181956
ST03325 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-023 | Nagpur | Central | 200 | Live | 2025-12-31 | 2026-02-11 | 2026-02-11 | 2026-02-28 | 2026-03-07 | 0 | Met | Niharika Sunder | 247486
ST03326 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-024 | Bhopal | Central | 100 | ROW In Progress | 2025-12-29 | 2026-01-22 |  | 2026-02-11 |  | 8 | Marginal | Darsh Rau | 75143
ST03327 | PRJ040 | CL008 | Reliance Retail | Indore Site-025 | Indore | Central | 20 | Installation Done | 2026-01-17 | 2026-03-17 | 2026-03-12 | 2026-04-02 |  | 12 | Marginal | Farhan Chada | 48607
ST03328 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-026 | Nagpur | Central | 50 | Installation Done | 2025-12-24 | 2026-02-09 | 2026-02-04 | 2026-03-10 |  | 12 | Marginal | Liam Koshy | 166859
ST03329 | PRJ040 | CL008 | Reliance Retail | Indore Site-027 | Indore | Central | 10 | Survey Pending | 2026-01-17 | 2026-02-23 |  | 2026-03-08 |  | 3 | Met | Simon Tata | 161313
ST03330 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-028 | Nagpur | Central | 100 | Testing | 2026-01-05 | 2026-02-25 | 2026-03-03 | 2026-03-23 |  | 12 | Marginal | Girindra Chatterjee | 134305
ST03331 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-029 | Nagpur | Central | 10 | Testing | 2025-12-23 | 2026-02-18 | 2026-02-23 | 2026-03-18 |  | 12 | Marginal | Arya Sunder | 132885
ST03332 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-030 | Bhopal | Central | 200 | Installation Scheduled | 2026-01-06 | 2026-02-06 | 2026-02-08 | 2026-02-28 |  | 6 | Met | Ekavir Varkey | 222512
ST03333 | PRJ040 | CL008 | Reliance Retail | Indore Site-031 | Indore | Central | 10 | ROW In Progress | 2025-12-28 | 2026-02-18 |  | 2026-03-13 |  | 5 | Met | Advay Contractor | 120506
ST03334 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-032 | Nagpur | Central | 50 | ROW In Progress | 2026-01-01 | 2026-02-04 |  | 2026-03-06 |  | 8 | Marginal | Girindra Chatterjee | 57054
ST03335 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-033 | Nagpur | Central | 100 | Pending Acceptance | 2025-12-31 | 2026-02-14 | 2026-02-13 | 2026-02-27 | 2026-03-11 | 0 | Met | Devansh Nigam | 218643
ST03336 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-034 | Bhopal | Central | 100 | Pending Acceptance | 2026-01-11 | 2026-02-12 | 2026-02-16 | 2026-02-25 | 2026-03-07 | 4 | Met | Mohammed Gupta | 112216
ST03337 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-035 | Bhopal | Central | 200 | Installation Done | 2026-01-13 | 2026-03-09 | 2026-03-17 | 2026-04-06 |  | 12 | Marginal | Ranveer Yadav | 184696
ST03338 | PRJ040 | CL008 | Reliance Retail | Indore Site-036 | Indore | Central | 100 | Installation Done | 2026-01-11 | 2026-02-04 | 2026-02-01 | 2026-02-15 |  | 12 | Marginal | Madhavi Lanka | 164991
ST03339 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-037 | Nagpur | Central | 100 | ROW In Progress | 2026-01-05 | 2026-02-12 |  | 2026-02-24 |  | 8 | Marginal | Devika Rastogi | 216211
ST03340 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-038 | Nagpur | Central | 100 | Installation Done | 2026-01-11 | 2026-02-20 | 2026-02-21 | 2026-03-16 |  | 12 | Marginal | Simon Tata | 64000
ST03341 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-039 | Bhopal | Central | 200 | Installation Scheduled | 2025-12-29 | 2026-01-25 | 2026-02-02 | 2026-02-12 |  | 5 | Met | Aarush Lall | 279318
ST03342 | PRJ040 | CL008 | Reliance Retail | Indore Site-040 | Indore | Central | 10 | Pending Acceptance | 2026-01-06 | 2026-03-01 | 2026-02-24 | 2026-03-19 | 2026-03-30 | 0 | Met | Ekavir Varkey | 55296
ST03343 | PRJ040 | CL008 | Reliance Retail | Indore Site-041 | Indore | Central | 200 | Testing | 2025-12-29 | 2026-02-11 | 2026-02-17 | 2026-02-23 |  | 12 | Marginal | Mohammed Gupta | 142850
ST03344 | PRJ040 | CL008 | Reliance Retail | Indore Site-042 | Indore | Central | 20 | Live | 2025-12-28 | 2026-02-13 | 2026-02-12 | 2026-02-24 | 2026-02-28 | 0 | Met | Vansha Thakkar | 99615
ST03345 | PRJ040 | CL008 | Reliance Retail | Indore Site-043 | Indore | Central | 20 | Live | 2025-12-26 | 2026-01-24 | 2026-01-30 | 2026-02-15 | 2026-02-27 | 6 | Met | Priya Rastogi | 85448
ST03346 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-044 | Bhopal | Central | 200 | Survey Pending | 2026-01-09 | 2026-02-19 |  | 2026-03-15 |  | 8 | Marginal | Darsh Rau | 251483
ST03347 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-045 | Nagpur | Central | 50 | ROW In Progress | 2025-12-30 | 2026-01-28 |  | 2026-02-16 |  | 2 | Met | Faqid Savant | 144787
ST03348 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-046 | Bhopal | Central | 200 | Survey Pending | 2026-01-09 | 2026-01-29 |  | 2026-02-18 |  | 7 | Met | Kabir Soman | 151761
ST03349 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-047 | Nagpur | Central | 50 | Testing | 2026-01-14 | 2026-02-16 | 2026-02-11 | 2026-03-04 |  | 12 | Marginal | Priya Rastogi | 260260
ST03350 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-048 | Bhopal | Central | 100 | Live | 2026-01-04 | 2026-02-14 | 2026-02-15 | 2026-02-28 | 2026-03-07 | 1 | Met | Victor Kannan | 206620
ST03351 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-049 | Nagpur | Central | 10 | Testing | 2026-01-06 | 2026-02-23 | 2026-02-18 | 2026-03-20 |  | 12 | Marginal | Nitesh Raghavan | 56528
ST03352 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-050 | Bhopal | Central | 20 | Installation Done | 2026-01-04 | 2026-01-30 | 2026-02-02 | 2026-02-16 |  | 12 | Marginal | Bhavika Sampath | 53227
ST03353 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-051 | Bhopal | Central | 50 | Live | 2026-01-15 | 2026-03-13 | 2026-03-10 | 2026-04-07 | 2026-04-13 | 0 | Met | Farhan Chada | 146585
ST03354 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-052 | Nagpur | Central | 200 | Installation Done | 2026-01-13 | 2026-03-14 | 2026-03-21 | 2026-03-31 |  | 12 | Marginal | Teerth Bhardwaj | 159468
ST03355 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-053 | Bhopal | Central | 50 | Live | 2026-01-03 | 2026-02-22 | 2026-03-04 | 2026-03-13 | 2026-03-10 | 10 | Marginal | Jai Kota | 143213
ST03356 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-054 | Nagpur | Central | 200 | Installation Done | 2025-12-26 | 2026-02-17 | 2026-02-16 | 2026-03-08 |  | 12 | Marginal | Wahab Raval | 125637
ST03357 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-055 | Bhopal | Central | 50 | Installation Scheduled | 2026-01-07 | 2026-02-28 | 2026-03-06 | 2026-03-17 |  | 1 | Met | Devansh Rajan | 235262
ST03358 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-056 | Nagpur | Central | 20 | Testing | 2026-01-08 | 2026-02-27 | 2026-02-27 | 2026-03-22 |  | 12 | Marginal | Devansh Nigam | 224843
ST03359 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-057 | Nagpur | Central | 20 | ROW In Progress | 2026-01-12 | 2026-02-11 |  | 2026-02-25 |  | 3 | Met | Yashica Issac | 77157
ST03360 | PRJ040 | CL008 | Reliance Retail | Indore Site-058 | Indore | Central | 20 | Testing | 2025-12-23 | 2026-01-12 | 2026-01-21 | 2026-01-25 |  | 12 | Marginal | Radhika Dugar | 218491
ST03361 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-059 | Nagpur | Central | 50 | Survey Pending | 2026-01-14 | 2026-02-20 |  | 2026-03-18 |  | 4 | Met | Tanay Rattan | 163850
ST03362 | PRJ040 | CL008 | Reliance Retail | Indore Site-060 | Indore | Central | 100 | Survey Pending | 2026-01-13 | 2026-02-19 |  | 2026-03-04 |  | 7 | Met | Faqid Savant | 46852
ST03363 | PRJ040 | CL008 | Reliance Retail | Indore Site-061 | Indore | Central | 10 | Installation Scheduled | 2026-01-09 | 2026-03-07 | 2026-03-09 | 2026-04-04 |  | 1 | Met | Girik Khalsa | 224731
ST03364 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-062 | Nagpur | Central | 50 | Installation Scheduled | 2026-01-06 | 2026-02-20 | 2026-03-02 | 2026-03-16 |  | 6 | Met | Vansha Thakkar | 233632
ST03365 | PRJ040 | CL008 | Reliance Retail | Indore Site-063 | Indore | Central | 200 | Installation Done | 2025-12-31 | 2026-02-19 | 2026-02-26 | 2026-03-02 |  | 12 | Marginal | Ikbal Kothari | 77957
ST03366 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-064 | Bhopal | Central | 100 | Installation Done | 2026-01-15 | 2026-02-25 | 2026-02-24 | 2026-03-25 |  | 12 | Marginal | Kevin Solanki | 131384
ST03367 | PRJ040 | CL008 | Reliance Retail | Indore Site-065 | Indore | Central | 200 | Pending Acceptance | 2025-12-25 | 2026-02-14 | 2026-02-20 | 2026-02-25 | 2026-03-03 | 6 | Met | Wahab Raval | 183731
ST03368 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-066 | Bhopal | Central | 50 | Testing | 2026-01-08 | 2026-02-28 | 2026-02-27 | 2026-03-24 |  | 12 | Marginal | Arya Sunder | 239091
ST03369 | PRJ040 | CL008 | Reliance Retail | Indore Site-067 | Indore | Central | 50 | ROW In Progress | 2025-12-23 | 2026-02-08 |  | 2026-02-20 |  | 8 | Marginal | Dominic Kakar | 153568
ST03370 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-068 | Nagpur | Central | 100 | ROW In Progress | 2026-01-09 | 2026-02-27 |  | 2026-03-16 |  | 8 | Marginal | Ekavir Bhargava | 54096
ST03371 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-069 | Bhopal | Central | 100 | Installation Done | 2026-01-07 | 2026-02-04 | 2026-02-08 | 2026-02-27 |  | 12 | Marginal | Farhan Chada | 198133
ST03372 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-070 | Bhopal | Central | 20 | Installation Scheduled | 2026-01-17 | 2026-02-11 | 2026-02-14 | 2026-02-28 |  | 0 | Met | Gavin Batta | 187602
ST03373 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-071 | Nagpur | Central | 10 | ROW In Progress | 2026-01-10 | 2026-02-14 |  | 2026-03-03 |  | 0 | Met | Devansh Rajan | 74370
ST03374 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-072 | Nagpur | Central | 200 | Installation Scheduled | 2025-12-23 | 2026-02-06 | 2026-02-12 | 2026-02-24 |  | 8 | Marginal | Girindra Chatterjee | 134951
ST03375 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-073 | Nagpur | Central | 20 | Installation Done | 2026-01-03 | 2026-01-31 | 2026-02-04 | 2026-02-21 |  | 12 | Marginal | Chandresh Zachariah | 72352
ST03376 | PRJ040 | CL008 | Reliance Retail | Indore Site-074 | Indore | Central | 50 | Survey Pending | 2025-12-29 | 2026-02-13 |  | 2026-03-14 |  | 7 | Met | Darsh Rau | 164229
ST03377 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-075 | Nagpur | Central | 200 | Pending Acceptance | 2025-12-29 | 2026-02-07 | 2026-02-04 | 2026-03-03 | 2026-03-06 | 0 | Met | Teerth Bhardwaj | 231808
ST03378 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-076 | Bhopal | Central | 20 | Live | 2026-01-02 | 2026-02-13 | 2026-02-20 | 2026-03-08 | 2026-03-18 | 7 | Met | Ekapad Walia | 256782
ST03379 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-077 | Nagpur | Central | 100 | Live | 2026-01-10 | 2026-02-21 | 2026-03-01 | 2026-03-11 | 2026-03-10 | 8 | Marginal | Aarush Lall | 130726
ST03380 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-078 | Nagpur | Central | 20 | Installation Done | 2025-12-24 | 2026-01-20 | 2026-01-18 | 2026-02-12 |  | 12 | Marginal | Devansh Nigam | 270630
ST03381 | PRJ040 | CL008 | Reliance Retail | Indore Site-079 | Indore | Central | 200 | Pending Acceptance | 2026-01-01 | 2026-03-02 | 2026-03-12 | 2026-03-25 | 2026-03-27 | 10 | Marginal | Farhan Chada | 148110
ST03382 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-080 | Nagpur | Central | 10 | Pending Acceptance | 2026-01-01 | 2026-01-29 | 2026-02-06 | 2026-02-24 | 2026-03-04 | 8 | Marginal | Quincy Biswas | 199626
ST03383 | PRJ040 | CL008 | Reliance Retail | Indore Site-081 | Indore | Central | 10 | ROW In Progress | 2026-01-07 | 2026-03-04 |  | 2026-04-02 |  | 0 | Met | Ekbal Garg | 79371
ST03384 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-082 | Nagpur | Central | 20 | Pending Acceptance | 2026-01-07 | 2026-01-31 | 2026-01-27 | 2026-03-01 | 2026-03-08 | 0 | Met | Nihal Shere | 94249
ST03385 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-083 | Nagpur | Central | 50 | Pending Acceptance | 2026-01-06 | 2026-02-05 | 2026-02-03 | 2026-02-19 | 2026-02-19 | 0 | Met | Priya Rastogi | 194980
ST03386 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-084 | Bhopal | Central | 100 | Live | 2026-01-03 | 2026-02-16 | 2026-02-16 | 2026-03-07 | 2026-03-12 | 0 | Met | Isaac Patil | 84453
ST03387 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-085 | Bhopal | Central | 20 | ROW In Progress | 2026-01-02 | 2026-02-18 |  | 2026-03-13 |  | 3 | Met | Kabir Soman | 222763
ST03388 | PRJ040 | CL008 | Reliance Retail | Indore Site-086 | Indore | Central | 100 | Survey Pending | 2025-12-27 | 2026-02-03 |  | 2026-02-19 |  | 2 | Met | Harini Choudhury | 129681
ST03389 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-087 | Bhopal | Central | 100 | Live | 2025-12-25 | 2026-01-31 | 2026-01-26 | 2026-02-17 | 2026-02-15 | 0 | Met | Urvashi Ray | 127147
ST03390 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-088 | Nagpur | Central | 20 | Live | 2026-01-01 | 2026-01-25 | 2026-01-28 | 2026-02-09 | 2026-02-07 | 3 | Met | Ekansh Balay | 183731
ST03391 | PRJ040 | CL008 | Reliance Retail | Indore Site-089 | Indore | Central | 50 | ROW In Progress | 2026-01-03 | 2026-01-26 |  | 2026-02-20 |  | 4 | Met | Nihal Shere | 244220
ST03392 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-090 | Nagpur | Central | 10 | Testing | 2026-01-15 | 2026-02-19 | 2026-02-19 | 2026-03-17 |  | 12 | Marginal | Dipta Bhandari | 51407
ST03393 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-091 | Bhopal | Central | 200 | Installation Scheduled | 2025-12-23 | 2026-01-31 | 2026-02-01 | 2026-02-12 |  | 0 | Met | Nihal Shere | 167698
ST03394 | PRJ040 | CL008 | Reliance Retail | Indore Site-092 | Indore | Central | 20 | ROW In Progress | 2026-01-09 | 2026-02-09 |  | 2026-02-26 |  | 5 | Met | Harini Choudhury | 243309
ST03395 | PRJ040 | CL008 | Reliance Retail | Indore Site-093 | Indore | Central | 50 | Installation Done | 2026-01-12 | 2026-02-15 | 2026-02-25 | 2026-03-10 |  | 12 | Marginal | Unni Bhagat | 112437
ST03396 | PRJ040 | CL008 | Reliance Retail | Indore Site-094 | Indore | Central | 100 | Installation Done | 2026-01-06 | 2026-02-03 | 2026-02-12 | 2026-02-24 |  | 12 | Marginal | Alka Wable | 133487
ST03397 | PRJ040 | CL008 | Reliance Retail | Indore Site-095 | Indore | Central | 100 | Installation Scheduled | 2025-12-26 | 2026-02-02 | 2026-02-11 | 2026-02-15 |  | 2 | Met | Niharika Sunder | 157195
ST03398 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-096 | Bhopal | Central | 200 | Installation Scheduled | 2026-01-13 | 2026-02-17 | 2026-02-18 | 2026-03-17 |  | 2 | Met | Victor Kannan | 91984
ST03399 | PRJ040 | CL008 | Reliance Retail | Indore Site-097 | Indore | Central | 20 | Live | 2025-12-27 | 2026-01-20 | 2026-01-26 | 2026-01-31 | 2026-01-31 | 6 | Met | Jai Kota | 262712
ST03400 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-098 | Bhopal | Central | 200 | Live | 2026-01-10 | 2026-02-02 | 2026-02-10 | 2026-02-17 | 2026-03-01 | 8 | Marginal | Irya Sampath | 177185
ST03401 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-099 | Bhopal | Central | 200 | Live | 2026-01-17 | 2026-03-06 | 2026-03-16 | 2026-03-22 | 2026-03-25 | 10 | Marginal | Liam Koshy | 262932
ST03402 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-100 | Bhopal | Central | 10 | Testing | 2026-01-11 | 2026-02-02 | 2026-02-04 | 2026-02-26 |  | 12 | Marginal | Upadhriti Wadhwa | 83807
ST03403 | PRJ040 | CL008 | Reliance Retail | Indore Site-101 | Indore | Central | 10 | Installation Scheduled | 2025-12-30 | 2026-02-24 | 2026-03-02 | 2026-03-16 |  | 7 | Met | Ekansh Balay | 255250
ST03404 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-102 | Bhopal | Central | 20 | ROW In Progress | 2026-01-15 | 2026-02-09 |  | 2026-03-04 |  | 2 | Met | Diya Rattan | 263427
ST03405 | PRJ040 | CL008 | Reliance Retail | Nagpur Site-103 | Nagpur | Central | 10 | Installation Done | 2026-01-12 | 2026-02-21 | 2026-02-18 | 2026-03-04 |  | 12 | Marginal | Ekavir Bhargava | 263670
ST03406 | PRJ040 | CL008 | Reliance Retail | Indore Site-104 | Indore | Central | 50 | ROW In Progress | 2025-12-31 | 2026-02-02 |  | 2026-02-24 |  | 4 | Met | Jai Kota | 100119
ST03407 | PRJ040 | CL008 | Reliance Retail | Bhopal Site-105 | Bhopal | Central | 20 | Live | 2026-01-10 | 2026-02-25 | 2026-02-22 | 2026-03-15 | 2026-03-16 | 0 | Met | Ekbal Garg | 210554

## Tasks_WBS
TaskID | ProjectID | ClientID | WBSPhase | TaskName | Owner | PlannedStart | PlannedEnd | PctComplete | Status | DelayDays
TSK0001 | PRJ001 | CL001 | Initiation | Initiation - SD-WAN Rollout | Gayathri Chaudry | 2025-07-22 | 2025-08-16 | 84 | Not Started | 0
TSK0002 | PRJ001 | CL001 | Survey | Survey - SD-WAN Rollout | Alka Wable | 2025-08-16 | 2025-09-10 | 80 | Delayed | 9
TSK0003 | PRJ001 | CL001 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Arya Sunder | 2025-09-10 | 2025-10-05 | 67 | Delayed | 7
TSK0004 | PRJ001 | CL001 | Procurement | Procurement - SD-WAN Rollout | Tara Dhar | 2025-10-05 | 2025-10-30 | 86 | Not Started | 0
TSK0005 | PRJ001 | CL001 | Installation | Installation - SD-WAN Rollout | Nitesh Raghavan | 2025-10-30 | 2025-11-24 | 81 | Completed | 0
TSK0006 | PRJ001 | CL001 | Testing | Testing - SD-WAN Rollout | Quincy Biswas | 2025-11-24 | 2025-12-19 | 87 | Not Started | 0
TSK0007 | PRJ001 | CL001 | Go-Live | Go-Live - SD-WAN Rollout | Gayathri Chaudry | 2025-12-19 | 2026-01-13 | 88 | Completed | 0
TSK0008 | PRJ001 | CL001 | Hypercare | Hypercare - SD-WAN Rollout | Girindra Chatterjee | 2026-01-13 | 2026-02-07 | 68 | Not Started | 0
TSK0009 | PRJ002 | CL001 | Initiation | Initiation - MPLS Backbone | Hemangini Lalla | 2025-08-08 | 2025-09-02 | 55 | In Progress | 0
TSK0010 | PRJ002 | CL001 | Survey | Survey - MPLS Backbone | Dipta Bhandari | 2025-09-02 | 2025-09-27 | 52 | Delayed | 4
TSK0011 | PRJ002 | CL001 | ROW/Permits | ROW/Permits - MPLS Backbone | Irya Sampath | 2025-09-27 | 2025-10-22 | 31 | Not Started | 0
TSK0012 | PRJ002 | CL001 | Procurement | Procurement - MPLS Backbone | Jai Kota | 2025-10-22 | 2025-11-16 | 30 | Completed | 0
TSK0013 | PRJ002 | CL001 | Installation | Installation - MPLS Backbone | Nihal Shere | 2025-11-16 | 2025-12-11 | 47 | In Progress | 0
TSK0014 | PRJ002 | CL001 | Testing | Testing - MPLS Backbone | Ekavir Varkey | 2025-12-11 | 2026-01-05 | 48 | Blocked | 0
TSK0015 | PRJ002 | CL001 | Go-Live | Go-Live - MPLS Backbone | Hemangini Lalla | 2026-01-05 | 2026-01-30 | 43 | In Progress | 0
TSK0016 | PRJ002 | CL001 | Hypercare | Hypercare - MPLS Backbone | Girik Khalsa | 2026-01-30 | 2026-02-24 | 30 | Delayed | 6
TSK0017 | PRJ003 | CL001 | Initiation | Initiation - ATM Connectivity | Janaki Handa | 2025-06-21 | 2025-07-16 | 49 | Not Started | 0
TSK0018 | PRJ003 | CL001 | Survey | Survey - ATM Connectivity | Upadhriti Wadhwa | 2025-07-16 | 2025-08-10 | 71 | Completed | 0
TSK0019 | PRJ003 | CL001 | ROW/Permits | ROW/Permits - ATM Connectivity | Tara Dhar | 2025-08-10 | 2025-09-04 | 56 | Delayed | 4
TSK0020 | PRJ003 | CL001 | Procurement | Procurement - ATM Connectivity | Advay Contractor | 2025-09-04 | 2025-09-29 | 63 | In Progress | 0
TSK0021 | PRJ003 | CL001 | Installation | Installation - ATM Connectivity | Nihal Shere | 2025-09-29 | 2025-10-24 | 42 | In Progress | 0
TSK0022 | PRJ003 | CL001 | Testing | Testing - ATM Connectivity | Darsh Rau | 2025-10-24 | 2025-11-18 | 47 | Completed | 0
TSK0023 | PRJ003 | CL001 | Go-Live | Go-Live - ATM Connectivity | Janaki Handa | 2025-11-18 | 2025-12-13 | 58 | Delayed | 12
TSK0024 | PRJ003 | CL001 | Hypercare | Hypercare - ATM Connectivity | Kashvi Edwin | 2025-12-13 | 2026-01-07 | 68 | Blocked | 0
TSK0025 | PRJ004 | CL001 | Initiation | Initiation - SD-WAN Rollout | Lajita Chatterjee | 2025-07-13 | 2025-08-07 | 90 | Delayed | 9
TSK0026 | PRJ004 | CL001 | Survey | Survey - SD-WAN Rollout | Madhavi Lanka | 2025-08-07 | 2025-09-01 | 83 | Blocked | 0
TSK0027 | PRJ004 | CL001 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Unni Bhagat | 2025-09-01 | 2025-09-26 | 95 | In Progress | 0
TSK0028 | PRJ004 | CL001 | Procurement | Procurement - SD-WAN Rollout | Ikbal Kothari | 2025-09-26 | 2025-10-21 | 95 | Completed | 0
TSK0029 | PRJ004 | CL001 | Installation | Installation - SD-WAN Rollout | Kashvi Edwin | 2025-10-21 | 2025-11-15 | 91 | In Progress | 0
TSK0030 | PRJ004 | CL001 | Testing | Testing - SD-WAN Rollout | Anamika Kanda | 2025-11-15 | 2025-12-10 | 97 | Completed | 0
TSK0031 | PRJ004 | CL001 | Go-Live | Go-Live - SD-WAN Rollout | Lajita Chatterjee | 2025-12-10 | 2026-01-04 | 74 | In Progress | 0
TSK0032 | PRJ004 | CL001 | Hypercare | Hypercare - SD-WAN Rollout | Kabir Soman | 2026-01-04 | 2026-01-29 | 90 | In Progress | 0
TSK0033 | PRJ005 | CL001 | Initiation | Initiation - MPLS Backbone | Hemangini Lalla | 2025-06-23 | 2025-07-18 | 40 | Blocked | 0
TSK0034 | PRJ005 | CL001 | Survey | Survey - MPLS Backbone | Girik Khalsa | 2025-07-18 | 2025-08-12 | 48 | Delayed | 1
TSK0035 | PRJ005 | CL001 | ROW/Permits | ROW/Permits - MPLS Backbone | Unni Bhagat | 2025-08-12 | 2025-09-06 | 37 | In Progress | 0
TSK0036 | PRJ005 | CL001 | Procurement | Procurement - MPLS Backbone | Urvashi Ray | 2025-09-06 | 2025-10-01 | 42 | Blocked | 0
TSK0037 | PRJ005 | CL001 | Installation | Installation - MPLS Backbone | Victor Kannan | 2025-10-01 | 2025-10-26 | 55 | Blocked | 0
TSK0038 | PRJ005 | CL001 | Testing | Testing - MPLS Backbone | Victor Kannan | 2025-10-26 | 2025-11-20 | 54 | Completed | 0
TSK0039 | PRJ005 | CL001 | Go-Live | Go-Live - MPLS Backbone | Hemangini Lalla | 2025-11-20 | 2025-12-15 | 63 | Completed | 0
TSK0040 | PRJ005 | CL001 | Hypercare | Hypercare - MPLS Backbone | Mohammed Gupta | 2025-12-15 | 2026-01-09 | 59 | Blocked | 0
TSK0041 | PRJ006 | CL002 | Initiation | Initiation - VSAT Backup | Janaki Handa | 2025-08-29 | 2025-09-23 | 81 | Not Started | 0
TSK0042 | PRJ006 | CL002 | Survey | Survey - VSAT Backup | Daksh Karnik | 2025-09-23 | 2025-10-18 | 89 | Delayed | 12
TSK0043 | PRJ006 | CL002 | ROW/Permits | ROW/Permits - VSAT Backup | Yashica Cherian | 2025-10-18 | 2025-11-12 | 90 | Delayed | 3
TSK0044 | PRJ006 | CL002 | Procurement | Procurement - VSAT Backup | Kevin Solanki | 2025-11-12 | 2025-12-07 | 85 | Completed | 0
TSK0045 | PRJ006 | CL002 | Installation | Installation - VSAT Backup | Aarush Lall | 2025-12-07 | 2026-01-01 | 99 | Blocked | 0
TSK0046 | PRJ006 | CL002 | Testing | Testing - VSAT Backup | Harini Choudhury | 2026-01-01 | 2026-01-26 | 99 | Not Started | 0
TSK0047 | PRJ006 | CL002 | Go-Live | Go-Live - VSAT Backup | Janaki Handa | 2026-01-26 | 2026-02-20 | 81 | Not Started | 0
TSK0048 | PRJ006 | CL002 | Hypercare | Hypercare - VSAT Backup | Upadhriti Wadhwa | 2026-02-20 | 2026-03-17 | 89 | Completed | 0
TSK0049 | PRJ007 | CL002 | Initiation | Initiation - VSAT Backup | Lajita Mall | 2025-09-27 | 2025-10-22 | 94 | Delayed | 12
TSK0050 | PRJ007 | CL002 | Survey | Survey - VSAT Backup | Ekbal Garg | 2025-10-22 | 2025-11-16 | 77 | Not Started | 0
TSK0051 | PRJ007 | CL002 | ROW/Permits | ROW/Permits - VSAT Backup | Tanay Rattan | 2025-11-16 | 2025-12-11 | 78 | Blocked | 0
TSK0052 | PRJ007 | CL002 | Procurement | Procurement - VSAT Backup | Dipta Bhandari | 2025-12-11 | 2026-01-05 | 70 | Delayed | 11
TSK0053 | PRJ007 | CL002 | Installation | Installation - VSAT Backup | Farhan Chada | 2026-01-05 | 2026-01-30 | 83 | In Progress | 0
TSK0054 | PRJ007 | CL002 | Testing | Testing - VSAT Backup | Ekavir Varkey | 2026-01-30 | 2026-02-24 | 70 | Completed | 0
TSK0055 | PRJ007 | CL002 | Go-Live | Go-Live - VSAT Backup | Lajita Mall | 2026-02-24 | 2026-03-21 | 82 | Completed | 0
TSK0056 | PRJ007 | CL002 | Hypercare | Hypercare - VSAT Backup | Arya Sunder | 2026-03-21 | 2026-04-15 | 66 | Blocked | 0
TSK0057 | PRJ008 | CL002 | Initiation | Initiation - ATM Connectivity | Gayathri Chaudry | 2025-11-29 | 2025-12-24 | 60 | Delayed | 3
TSK0058 | PRJ008 | CL002 | Survey | Survey - ATM Connectivity | Teerth Bhardwaj | 2025-12-24 | 2026-01-18 | 70 | Blocked | 0
TSK0059 | PRJ008 | CL002 | ROW/Permits | ROW/Permits - ATM Connectivity | Nitesh Raghavan | 2026-01-18 | 2026-02-12 | 47 | In Progress | 0
TSK0060 | PRJ008 | CL002 | Procurement | Procurement - ATM Connectivity | Theodore Devi | 2026-02-12 | 2026-03-09 | 70 | Completed | 0
TSK0061 | PRJ008 | CL002 | Installation | Installation - ATM Connectivity | Nitesh Raghavan | 2026-03-09 | 2026-04-03 | 46 | Not Started | 0
TSK0062 | PRJ008 | CL002 | Testing | Testing - ATM Connectivity | Vansha Thakkar | 2026-04-03 | 2026-04-28 | 72 | In Progress | 0
TSK0063 | PRJ008 | CL002 | Go-Live | Go-Live - ATM Connectivity | Gayathri Chaudry | 2026-04-28 | 2026-05-23 | 50 | Completed | 0
TSK0064 | PRJ008 | CL002 | Hypercare | Hypercare - ATM Connectivity | Girik Khalsa | 2026-05-23 | 2026-06-17 | 46 | Blocked | 0
TSK0065 | PRJ009 | CL002 | Initiation | Initiation - Branch Link Upgrade | Lajita Mall | 2026-01-09 | 2026-02-03 | 90 | Not Started | 0
TSK0066 | PRJ009 | CL002 | Survey | Survey - Branch Link Upgrade | Advay Contractor | 2026-02-03 | 2026-02-28 | 75 | Not Started | 0
TSK0067 | PRJ009 | CL002 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Nitesh Raghavan | 2026-02-28 | 2026-03-25 | 77 | In Progress | 0
TSK0068 | PRJ009 | CL002 | Procurement | Procurement - Branch Link Upgrade | Theodore Devi | 2026-03-25 | 2026-04-19 | 92 | In Progress | 0
TSK0069 | PRJ009 | CL002 | Installation | Installation - Branch Link Upgrade | Logan Sami | 2026-04-19 | 2026-05-14 | 69 | In Progress | 0
TSK0070 | PRJ009 | CL002 | Testing | Testing - Branch Link Upgrade | Farhan Chada | 2026-05-14 | 2026-06-08 | 83 | Blocked | 0
TSK0071 | PRJ009 | CL002 | Go-Live | Go-Live - Branch Link Upgrade | Lajita Mall | 2026-06-08 | 2026-07-03 | 72 | Completed | 0
TSK0072 | PRJ009 | CL002 | Hypercare | Hypercare - Branch Link Upgrade | Devika Rastogi | 2026-07-03 | 2026-07-28 | 74 | Not Started | 0
TSK0073 | PRJ010 | CL002 | Initiation | Initiation - ATM Connectivity | Isha Kadakia | 2025-07-31 | 2025-08-25 | 41 | Not Started | 0
TSK0074 | PRJ010 | CL002 | Survey | Survey - ATM Connectivity | Harini Choudhury | 2025-08-25 | 2025-09-19 | 63 | Not Started | 0
TSK0075 | PRJ010 | CL002 | ROW/Permits | ROW/Permits - ATM Connectivity | Yatin Baral | 2025-09-19 | 2025-10-14 | 42 | Blocked | 0
TSK0076 | PRJ010 | CL002 | Procurement | Procurement - ATM Connectivity | Simon Tata | 2025-10-14 | 2025-11-08 | 38 | In Progress | 0
TSK0077 | PRJ010 | CL002 | Installation | Installation - ATM Connectivity | Nitesh Raghavan | 2025-11-08 | 2025-12-03 | 59 | Blocked | 0
TSK0078 | PRJ010 | CL002 | Testing | Testing - ATM Connectivity | Madhavi Lanka | 2025-12-03 | 2025-12-28 | 57 | Not Started | 0
TSK0079 | PRJ010 | CL002 | Go-Live | Go-Live - ATM Connectivity | Isha Kadakia | 2025-12-28 | 2026-01-22 | 53 | Blocked | 0
TSK0080 | PRJ010 | CL002 | Hypercare | Hypercare - ATM Connectivity | Theodore Devi | 2026-01-22 | 2026-02-16 | 47 | Completed | 0
TSK0081 | PRJ011 | CL002 | Initiation | Initiation - Branch Link Upgrade | Fariq Kaul | 2026-03-01 | 2026-03-26 | 52 | Completed | 0
TSK0082 | PRJ011 | CL002 | Survey | Survey - Branch Link Upgrade | Isaac Patil | 2026-03-26 | 2026-04-20 | 67 | In Progress | 0
TSK0083 | PRJ011 | CL002 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Ekiya Suresh | 2026-04-20 | 2026-05-15 | 51 | Not Started | 0
TSK0084 | PRJ011 | CL002 | Procurement | Procurement - Branch Link Upgrade | Diya Rattan | 2026-05-15 | 2026-06-09 | 63 | Delayed | 1
TSK0085 | PRJ011 | CL002 | Installation | Installation - Branch Link Upgrade | Dakshesh Trivedi | 2026-06-09 | 2026-07-04 | 52 | Blocked | 0
TSK0086 | PRJ011 | CL002 | Testing | Testing - Branch Link Upgrade | Ekbal Garg | 2026-07-04 | 2026-07-29 | 61 | Delayed | 2
TSK0087 | PRJ011 | CL002 | Go-Live | Go-Live - Branch Link Upgrade | Fariq Kaul | 2026-07-29 | 2026-08-23 | 58 | Blocked | 0
TSK0088 | PRJ011 | CL002 | Hypercare | Hypercare - Branch Link Upgrade | Wriddhish Bhardwaj | 2026-08-23 | 2026-09-17 | 71 | Not Started | 0
TSK0089 | PRJ012 | CL003 | Initiation | Initiation - MPLS Backbone | Gayathri Chaudry | 2025-05-30 | 2025-06-24 | 97 | In Progress | 0
TSK0090 | PRJ012 | CL003 | Survey | Survey - MPLS Backbone | Yatin Baral | 2025-06-24 | 2025-07-19 | 100 | Completed | 0
TSK0091 | PRJ012 | CL003 | ROW/Permits | ROW/Permits - MPLS Backbone | Tara Dhar | 2025-07-19 | 2025-08-13 | 88 | Completed | 0
TSK0092 | PRJ012 | CL003 | Procurement | Procurement - MPLS Backbone | Vansha Thakkar | 2025-08-13 | 2025-09-07 | 96 | Not Started | 0
TSK0093 | PRJ012 | CL003 | Installation | Installation - MPLS Backbone | Devansh Nigam | 2025-09-07 | 2025-10-02 | 100 | Completed | 0
TSK0094 | PRJ012 | CL003 | Testing | Testing - MPLS Backbone | Diya Rattan | 2025-10-02 | 2025-10-27 | 99 | Not Started | 0
TSK0095 | PRJ012 | CL003 | Go-Live | Go-Live - MPLS Backbone | Gayathri Chaudry | 2025-10-27 | 2025-11-21 | 89 | Completed | 0
TSK0096 | PRJ012 | CL003 | Hypercare | Hypercare - MPLS Backbone | Irya Sampath | 2025-11-21 | 2025-12-16 | 87 | In Progress | 0
TSK0097 | PRJ013 | CL003 | Initiation | Initiation - MPLS Backbone | Fariq Kaul | 2025-11-27 | 2025-12-22 | 47 | In Progress | 0
TSK0098 | PRJ013 | CL003 | Survey | Survey - MPLS Backbone | Arya Sunder | 2025-12-22 | 2026-01-16 | 63 | In Progress | 0
TSK0099 | PRJ013 | CL003 | ROW/Permits | ROW/Permits - MPLS Backbone | Farhan Chada | 2026-01-16 | 2026-02-10 | 75 | Delayed | 9
TSK0100 | PRJ013 | CL003 | Procurement | Procurement - MPLS Backbone | Harini Choudhury | 2026-02-10 | 2026-03-07 | 71 | In Progress | 0
TSK0101 | PRJ013 | CL003 | Installation | Installation - MPLS Backbone | Simon Tata | 2026-03-07 | 2026-04-01 | 68 | Blocked | 0
TSK0102 | PRJ013 | CL003 | Testing | Testing - MPLS Backbone | Aarush Lall | 2026-04-01 | 2026-04-26 | 49 | Blocked | 0
TSK0103 | PRJ013 | CL003 | Go-Live | Go-Live - MPLS Backbone | Fariq Kaul | 2026-04-26 | 2026-05-21 | 72 | Blocked | 0
TSK0104 | PRJ013 | CL003 | Hypercare | Hypercare - MPLS Backbone | Kashvi Edwin | 2026-05-21 | 2026-06-15 | 61 | Completed | 0
TSK0105 | PRJ014 | CL003 | Initiation | Initiation - Branch Link Upgrade | Tripti Yadav | 2025-08-18 | 2025-09-12 | 77 | In Progress | 0
TSK0106 | PRJ014 | CL003 | Survey | Survey - Branch Link Upgrade | Faqid Savant | 2025-09-12 | 2025-10-07 | 84 | Not Started | 0
TSK0107 | PRJ014 | CL003 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Farhan Chada | 2025-10-07 | 2025-11-01 | 86 | Not Started | 0
TSK0108 | PRJ014 | CL003 | Procurement | Procurement - Branch Link Upgrade | Aarush Lall | 2025-11-01 | 2025-11-26 | 71 | Not Started | 0
TSK0109 | PRJ014 | CL003 | Installation | Installation - Branch Link Upgrade | Devika Rastogi | 2025-11-26 | 2025-12-21 | 86 | Not Started | 0
TSK0110 | PRJ014 | CL003 | Testing | Testing - Branch Link Upgrade | Girindra Chatterjee | 2025-12-21 | 2026-01-15 | 71 | Completed | 0
TSK0111 | PRJ014 | CL003 | Go-Live | Go-Live - Branch Link Upgrade | Tripti Yadav | 2026-01-15 | 2026-02-09 | 66 | Delayed | 7
TSK0112 | PRJ014 | CL003 | Hypercare | Hypercare - Branch Link Upgrade | Wriddhish Bhardwaj | 2026-02-09 | 2026-03-06 | 81 | Blocked | 0
TSK0113 | PRJ015 | CL003 | Initiation | Initiation - SD-WAN Rollout | Tripti Yadav | 2025-10-11 | 2025-11-05 | 61 | In Progress | 0
TSK0114 | PRJ015 | CL003 | Survey | Survey - SD-WAN Rollout | Devansh Nigam | 2025-11-05 | 2025-11-30 | 82 | Blocked | 0
TSK0115 | PRJ015 | CL003 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Unni Bhagat | 2025-11-30 | 2025-12-25 | 74 | Completed | 0
TSK0116 | PRJ015 | CL003 | Procurement | Procurement - SD-WAN Rollout | Teerth Bhardwaj | 2025-12-25 | 2026-01-19 | 61 | Blocked | 0
TSK0117 | PRJ015 | CL003 | Installation | Installation - SD-WAN Rollout | Irya Sampath | 2026-01-19 | 2026-02-13 | 81 | Not Started | 0
TSK0118 | PRJ015 | CL003 | Testing | Testing - SD-WAN Rollout | Harini Choudhury | 2026-02-13 | 2026-03-10 | 77 | Not Started | 0
TSK0119 | PRJ015 | CL003 | Go-Live | Go-Live - SD-WAN Rollout | Tripti Yadav | 2026-03-10 | 2026-04-04 | 87 | Delayed | 0
TSK0120 | PRJ015 | CL003 | Hypercare | Hypercare - SD-WAN Rollout | Anamika Kanda | 2026-04-04 | 2026-04-29 | 83 | Delayed | 4
TSK0121 | PRJ016 | CL004 | Initiation | Initiation - VSAT Backup | Hemangini Lalla | 2025-07-22 | 2025-08-16 | 99 | Completed | 0
TSK0122 | PRJ016 | CL004 | Survey | Survey - VSAT Backup | Upadhriti Wadhwa | 2025-08-16 | 2025-09-10 | 100 | Completed | 0
TSK0123 | PRJ016 | CL004 | ROW/Permits | ROW/Permits - VSAT Backup | Radhika Dugar | 2025-09-10 | 2025-10-05 | 80 | In Progress | 0
TSK0124 | PRJ016 | CL004 | Procurement | Procurement - VSAT Backup | Daksh Karnik | 2025-10-05 | 2025-10-30 | 81 | Delayed | 7
TSK0125 | PRJ016 | CL004 | Installation | Installation - VSAT Backup | Madhavi Lanka | 2025-10-30 | 2025-11-24 | 92 | Blocked | 0
TSK0126 | PRJ016 | CL004 | Testing | Testing - VSAT Backup | Logan Sami | 2025-11-24 | 2025-12-19 | 77 | Delayed | 10
TSK0127 | PRJ016 | CL004 | Go-Live | Go-Live - VSAT Backup | Hemangini Lalla | 2025-12-19 | 2026-01-13 | 94 | Not Started | 0
TSK0128 | PRJ016 | CL004 | Hypercare | Hypercare - VSAT Backup | Diya Rattan | 2026-01-13 | 2026-02-07 | 90 | Completed | 0
TSK0129 | PRJ017 | CL004 | Initiation | Initiation - Branch Link Upgrade | Isha Kadakia | 2025-09-18 | 2025-10-13 | 98 | Not Started | 0
TSK0130 | PRJ017 | CL004 | Survey | Survey - Branch Link Upgrade | Jai Kota | 2025-10-13 | 2025-11-07 | 93 | Completed | 0
TSK0131 | PRJ017 | CL004 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Wahab Raval | 2025-11-07 | 2025-12-02 | 91 | Delayed | 0
TSK0132 | PRJ017 | CL004 | Procurement | Procurement - Branch Link Upgrade | Wriddhish Bhardwaj | 2025-12-02 | 2025-12-27 | 74 | Completed | 0
TSK0133 | PRJ017 | CL004 | Installation | Installation - Branch Link Upgrade | Harini Choudhury | 2025-12-27 | 2026-01-21 | 94 | Blocked | 0
TSK0134 | PRJ017 | CL004 | Testing | Testing - Branch Link Upgrade | Advay Contractor | 2026-01-21 | 2026-02-15 | 89 | In Progress | 0
TSK0135 | PRJ017 | CL004 | Go-Live | Go-Live - Branch Link Upgrade | Isha Kadakia | 2026-02-15 | 2026-03-12 | 100 | Completed | 0
TSK0136 | PRJ017 | CL004 | Hypercare | Hypercare - Branch Link Upgrade | Harini Choudhury | 2026-03-12 | 2026-04-06 | 92 | In Progress | 0
TSK0137 | PRJ018 | CL004 | Initiation | Initiation - SD-WAN Rollout | Isha Kadakia | 2025-12-21 | 2026-01-15 | 72 | Not Started | 0
TSK0138 | PRJ018 | CL004 | Survey | Survey - SD-WAN Rollout | Liam Koshy | 2026-01-15 | 2026-02-09 | 62 | Blocked | 0
TSK0139 | PRJ018 | CL004 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Ekansh Balay | 2026-02-09 | 2026-03-06 | 71 | Blocked | 0
TSK0140 | PRJ018 | CL004 | Procurement | Procurement - SD-WAN Rollout | Anamika Kanda | 2026-03-06 | 2026-03-31 | 64 | In Progress | 0
TSK0141 | PRJ018 | CL004 | Installation | Installation - SD-WAN Rollout | Jai Kota | 2026-03-31 | 2026-04-25 | 68 | Completed | 0
TSK0142 | PRJ018 | CL004 | Testing | Testing - SD-WAN Rollout | Girik Khalsa | 2026-04-25 | 2026-05-20 | 64 | In Progress | 0
TSK0143 | PRJ018 | CL004 | Go-Live | Go-Live - SD-WAN Rollout | Isha Kadakia | 2026-05-20 | 2026-06-14 | 70 | Delayed | 11
TSK0144 | PRJ018 | CL004 | Hypercare | Hypercare - SD-WAN Rollout | Tanay Rattan | 2026-06-14 | 2026-07-09 | 64 | Delayed | 12
TSK0145 | PRJ019 | CL004 | Initiation | Initiation - SD-WAN Rollout | Kritika Brar | 2025-12-20 | 2026-01-14 | 82 | In Progress | 0
TSK0146 | PRJ019 | CL004 | Survey | Survey - SD-WAN Rollout | Darsh Rau | 2026-01-14 | 2026-02-08 | 93 | In Progress | 0
TSK0147 | PRJ019 | CL004 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Girindra Chatterjee | 2026-02-08 | 2026-03-05 | 83 | Completed | 0
TSK0148 | PRJ019 | CL004 | Procurement | Procurement - SD-WAN Rollout | Victor Kannan | 2026-03-05 | 2026-03-30 | 76 | Blocked | 0
TSK0149 | PRJ019 | CL004 | Installation | Installation - SD-WAN Rollout | Arya Shere | 2026-03-30 | 2026-04-24 | 83 | In Progress | 0
TSK0150 | PRJ019 | CL004 | Testing | Testing - SD-WAN Rollout | Diya Rattan | 2026-04-24 | 2026-05-19 | 72 | Delayed | 5
TSK0151 | PRJ019 | CL004 | Go-Live | Go-Live - SD-WAN Rollout | Kritika Brar | 2026-05-19 | 2026-06-13 | 72 | Delayed | 1
TSK0152 | PRJ019 | CL004 | Hypercare | Hypercare - SD-WAN Rollout | Arya Shere | 2026-06-13 | 2026-07-08 | 84 | Completed | 0
TSK0153 | PRJ020 | CL004 | Initiation | Initiation - ATM Connectivity | Gayathri Chaudry | 2025-12-20 | 2026-01-14 | 34 | Completed | 0
TSK0154 | PRJ020 | CL004 | Survey | Survey - ATM Connectivity | Darsh Rau | 2026-01-14 | 2026-02-08 | 55 | Not Started | 0
TSK0155 | PRJ020 | CL004 | ROW/Permits | ROW/Permits - ATM Connectivity | Vansha Thakkar | 2026-02-08 | 2026-03-05 | 30 | Not Started | 0
TSK0156 | PRJ020 | CL004 | Procurement | Procurement - ATM Connectivity | Tara Dhar | 2026-03-05 | 2026-03-30 | 29 | Completed | 0
TSK0157 | PRJ020 | CL004 | Installation | Installation - ATM Connectivity | Chandresh Zachariah | 2026-03-30 | 2026-04-24 | 34 | Delayed | 3
TSK0158 | PRJ020 | CL004 | Testing | Testing - ATM Connectivity | Raksha Varughese | 2026-04-24 | 2026-05-19 | 40 | Blocked | 0
TSK0159 | PRJ020 | CL004 | Go-Live | Go-Live - ATM Connectivity | Gayathri Chaudry | 2026-05-19 | 2026-06-13 | 40 | In Progress | 0
TSK0160 | PRJ020 | CL004 | Hypercare | Hypercare - ATM Connectivity | Devansh Nigam | 2026-06-13 | 2026-07-08 | 30 | Delayed | 5
TSK0161 | PRJ021 | CL005 | Initiation | Initiation - SD-WAN Rollout | Isha Kadakia | 2025-10-22 | 2025-11-16 | 69 | Blocked | 0
TSK0162 | PRJ021 | CL005 | Survey | Survey - SD-WAN Rollout | Kabir Soman | 2025-11-16 | 2025-12-11 | 65 | Not Started | 0
TSK0163 | PRJ021 | CL005 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Yatin Baral | 2025-12-11 | 2026-01-05 | 74 | Not Started | 0
TSK0164 | PRJ021 | CL005 | Procurement | Procurement - SD-WAN Rollout | Liam Koshy | 2026-01-05 | 2026-01-30 | 80 | Blocked | 0
TSK0165 | PRJ021 | CL005 | Installation | Installation - SD-WAN Rollout | Arya Sunder | 2026-01-30 | 2026-02-24 | 63 | Delayed | 10
TSK0166 | PRJ021 | CL005 | Testing | Testing - SD-WAN Rollout | Alka Wable | 2026-02-24 | 2026-03-21 | 80 | Not Started | 0
TSK0167 | PRJ021 | CL005 | Go-Live | Go-Live - SD-WAN Rollout | Isha Kadakia | 2026-03-21 | 2026-04-15 | 81 | Blocked | 0
TSK0168 | PRJ021 | CL005 | Hypercare | Hypercare - SD-WAN Rollout | Ekiya Suresh | 2026-04-15 | 2026-05-10 | 89 | Delayed | 8
TSK0169 | PRJ022 | CL005 | Initiation | Initiation - VSAT Backup | Kritika Brar | 2026-01-12 | 2026-02-06 | 44 | Completed | 0
TSK0170 | PRJ022 | CL005 | Survey | Survey - VSAT Backup | Kevin Solanki | 2026-02-06 | 2026-03-03 | 44 | Completed | 0
TSK0171 | PRJ022 | CL005 | ROW/Permits | ROW/Permits - VSAT Backup | Tanay Rattan | 2026-03-03 | 2026-03-28 | 54 | Not Started | 0
TSK0172 | PRJ022 | CL005 | Procurement | Procurement - VSAT Backup | Faqid Savant | 2026-03-28 | 2026-04-22 | 52 | In Progress | 0
TSK0173 | PRJ022 | CL005 | Installation | Installation - VSAT Backup | Nitesh Raghavan | 2026-04-22 | 2026-05-17 | 54 | Blocked | 0
TSK0174 | PRJ022 | CL005 | Testing | Testing - VSAT Backup | Jai Kota | 2026-05-17 | 2026-06-11 | 48 | Not Started | 0
TSK0175 | PRJ022 | CL005 | Go-Live | Go-Live - VSAT Backup | Kritika Brar | 2026-06-11 | 2026-07-06 | 53 | Blocked | 0
TSK0176 | PRJ022 | CL005 | Hypercare | Hypercare - VSAT Backup | Niharika Sunder | 2026-07-06 | 2026-07-31 | 27 | Not Started | 0
TSK0177 | PRJ023 | CL005 | Initiation | Initiation - ATM Connectivity | Arunima Dugal | 2025-11-08 | 2025-12-03 | 29 | Delayed | 5
TSK0178 | PRJ023 | CL005 | Survey | Survey - ATM Connectivity | Irya Sampath | 2025-12-03 | 2025-12-28 | 50 | Completed | 0
TSK0179 | PRJ023 | CL005 | ROW/Permits | ROW/Permits - ATM Connectivity | Darsh Rau | 2025-12-28 | 2026-01-22 | 44 | Delayed | 12
TSK0180 | PRJ023 | CL005 | Procurement | Procurement - ATM Connectivity | Upadhriti Wadhwa | 2026-01-22 | 2026-02-16 | 40 | In Progress | 0
TSK0181 | PRJ023 | CL005 | Installation | Installation - ATM Connectivity | Simon Tata | 2026-02-16 | 2026-03-13 | 50 | Delayed | 2
TSK0182 | PRJ023 | CL005 | Testing | Testing - ATM Connectivity | Bhavika Sampath | 2026-03-13 | 2026-04-07 | 28 | Not Started | 0
TSK0183 | PRJ023 | CL005 | Go-Live | Go-Live - ATM Connectivity | Arunima Dugal | 2026-04-07 | 2026-05-02 | 47 | Delayed | 7
TSK0184 | PRJ023 | CL005 | Hypercare | Hypercare - ATM Connectivity | Priya Rastogi | 2026-05-02 | 2026-05-27 | 47 | Delayed | 2
TSK0185 | PRJ024 | CL005 | Initiation | Initiation - MPLS Backbone | Fariq Kaul | 2025-10-30 | 2025-11-24 | 70 | Delayed | 10
TSK0186 | PRJ024 | CL005 | Survey | Survey - MPLS Backbone | Dakshesh Trivedi | 2025-11-24 | 2025-12-19 | 63 | Blocked | 0
TSK0187 | PRJ024 | CL005 | ROW/Permits | ROW/Permits - MPLS Backbone | Farhan Chada | 2025-12-19 | 2026-01-13 | 66 | Not Started | 0
TSK0188 | PRJ024 | CL005 | Procurement | Procurement - MPLS Backbone | Siddharth Zacharia | 2026-01-13 | 2026-02-07 | 66 | Blocked | 0
TSK0189 | PRJ024 | CL005 | Installation | Installation - MPLS Backbone | Tanay Rattan | 2026-02-07 | 2026-03-04 | 52 | Completed | 0
TSK0190 | PRJ024 | CL005 | Testing | Testing - MPLS Backbone | Ekbal Garg | 2026-03-04 | 2026-03-29 | 68 | Not Started | 0
TSK0191 | PRJ024 | CL005 | Go-Live | Go-Live - MPLS Backbone | Fariq Kaul | 2026-03-29 | 2026-04-23 | 56 | Blocked | 0
TSK0192 | PRJ024 | CL005 | Hypercare | Hypercare - MPLS Backbone | Ranveer Yadav | 2026-04-23 | 2026-05-18 | 68 | Not Started | 0
TSK0193 | PRJ025 | CL006 | Initiation | Initiation - MPLS Backbone | Fariq Kaul | 2025-08-30 | 2025-09-24 | 73 | Not Started | 0
TSK0194 | PRJ025 | CL006 | Survey | Survey - MPLS Backbone | Isaac Patil | 2025-09-24 | 2025-10-19 | 65 | In Progress | 0
TSK0195 | PRJ025 | CL006 | ROW/Permits | ROW/Permits - MPLS Backbone | Tanay Rattan | 2025-10-19 | 2025-11-13 | 71 | In Progress | 0
TSK0196 | PRJ025 | CL006 | Procurement | Procurement - MPLS Backbone | Ekavir Bhargava | 2025-11-13 | 2025-12-08 | 61 | Completed | 0
TSK0197 | PRJ025 | CL006 | Installation | Installation - MPLS Backbone | Anamika Kanda | 2025-12-08 | 2026-01-02 | 72 | Not Started | 0
TSK0198 | PRJ025 | CL006 | Testing | Testing - MPLS Backbone | Mohammed Gupta | 2026-01-02 | 2026-01-27 | 72 | Delayed | 8
TSK0199 | PRJ025 | CL006 | Go-Live | Go-Live - MPLS Backbone | Fariq Kaul | 2026-01-27 | 2026-02-21 | 68 | Delayed | 6
TSK0200 | PRJ025 | CL006 | Hypercare | Hypercare - MPLS Backbone | Yatin Baral | 2026-02-21 | 2026-03-18 | 58 | In Progress | 0
TSK0201 | PRJ026 | CL006 | Initiation | Initiation - Branch Link Upgrade | Fariq Kaul | 2025-06-09 | 2025-07-04 | 82 | Delayed | 12
TSK0202 | PRJ026 | CL006 | Survey | Survey - Branch Link Upgrade | Yashica Cherian | 2025-07-04 | 2025-07-29 | 98 | Blocked | 0
TSK0203 | PRJ026 | CL006 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Wahab Raval | 2025-07-29 | 2025-08-23 | 80 | Completed | 0
TSK0204 | PRJ026 | CL006 | Procurement | Procurement - Branch Link Upgrade | Niharika Sunder | 2025-08-23 | 2025-09-17 | 78 | Blocked | 0
TSK0205 | PRJ026 | CL006 | Installation | Installation - Branch Link Upgrade | Devika Rastogi | 2025-09-17 | 2025-10-12 | 89 | Not Started | 0
TSK0206 | PRJ026 | CL006 | Testing | Testing - Branch Link Upgrade | Niharika Sunder | 2025-10-12 | 2025-11-06 | 100 | Completed | 0
TSK0207 | PRJ026 | CL006 | Go-Live | Go-Live - Branch Link Upgrade | Fariq Kaul | 2025-11-06 | 2025-12-01 | 80 | Completed | 0
TSK0208 | PRJ026 | CL006 | Hypercare | Hypercare - Branch Link Upgrade | Radhika Dugar | 2025-12-01 | 2025-12-26 | 100 | Completed | 0
TSK0209 | PRJ027 | CL006 | Initiation | Initiation - SD-WAN Rollout | Chakradev Kari | 2025-10-15 | 2025-11-09 | 59 | Blocked | 0
TSK0210 | PRJ027 | CL006 | Survey | Survey - SD-WAN Rollout | Ekapad Walia | 2025-11-09 | 2025-12-04 | 67 | Delayed | 11
TSK0211 | PRJ027 | CL006 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Ekansh Balay | 2025-12-04 | 2025-12-29 | 56 | Completed | 0
TSK0212 | PRJ027 | CL006 | Procurement | Procurement - SD-WAN Rollout | Harini Choudhury | 2025-12-29 | 2026-01-23 | 41 | In Progress | 0
TSK0213 | PRJ027 | CL006 | Installation | Installation - SD-WAN Rollout | Ekansh Balay | 2026-01-23 | 2026-02-17 | 58 | Completed | 0
TSK0214 | PRJ027 | CL006 | Testing | Testing - SD-WAN Rollout | Farhan Chada | 2026-02-17 | 2026-03-14 | 62 | In Progress | 0
TSK0215 | PRJ027 | CL006 | Go-Live | Go-Live - SD-WAN Rollout | Chakradev Kari | 2026-03-14 | 2026-04-08 | 65 | Not Started | 0
TSK0216 | PRJ027 | CL006 | Hypercare | Hypercare - SD-WAN Rollout | Nitesh Raghavan | 2026-04-08 | 2026-05-03 | 66 | In Progress | 0
TSK0217 | PRJ028 | CL006 | Initiation | Initiation - Branch Link Upgrade | Gayathri Chaudry | 2025-10-28 | 2025-11-22 | 68 | Delayed | 10
TSK0218 | PRJ028 | CL006 | Survey | Survey - Branch Link Upgrade | Siddharth Zacharia | 2025-11-22 | 2025-12-17 | 61 | Not Started | 0
TSK0219 | PRJ028 | CL006 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Upadhriti Wadhwa | 2025-12-17 | 2026-01-11 | 53 | Delayed | 10
TSK0220 | PRJ028 | CL006 | Procurement | Procurement - Branch Link Upgrade | Alka Wable | 2026-01-11 | 2026-02-05 | 43 | Not Started | 0
TSK0221 | PRJ028 | CL006 | Installation | Installation - Branch Link Upgrade | Bhavika Sampath | 2026-02-05 | 2026-03-02 | 65 | Delayed | 4
TSK0222 | PRJ028 | CL006 | Testing | Testing - Branch Link Upgrade | Girik Khalsa | 2026-03-02 | 2026-03-27 | 68 | In Progress | 0
TSK0223 | PRJ028 | CL006 | Go-Live | Go-Live - Branch Link Upgrade | Gayathri Chaudry | 2026-03-27 | 2026-04-21 | 58 | Delayed | 0
TSK0224 | PRJ028 | CL006 | Hypercare | Hypercare - Branch Link Upgrade | Girindra Chatterjee | 2026-04-21 | 2026-05-16 | 49 | Blocked | 0
TSK0225 | PRJ029 | CL006 | Initiation | Initiation - VSAT Backup | Lajita Mall | 2025-08-30 | 2025-09-24 | 45 | Not Started | 0
TSK0226 | PRJ029 | CL006 | Survey | Survey - VSAT Backup | Simon Tata | 2025-09-24 | 2025-10-19 | 35 | Not Started | 0
TSK0227 | PRJ029 | CL006 | ROW/Permits | ROW/Permits - VSAT Backup | Ekavir Bhargava | 2025-10-19 | 2025-11-13 | 57 | In Progress | 0
TSK0228 | PRJ029 | CL006 | Procurement | Procurement - VSAT Backup | Ekavir Varkey | 2025-11-13 | 2025-12-08 | 35 | In Progress | 0
TSK0229 | PRJ029 | CL006 | Installation | Installation - VSAT Backup | Quincy Biswas | 2025-12-08 | 2026-01-02 | 52 | Blocked | 0
TSK0230 | PRJ029 | CL006 | Testing | Testing - VSAT Backup | Darsh Rau | 2026-01-02 | 2026-01-27 | 37 | Not Started | 0
TSK0231 | PRJ029 | CL006 | Go-Live | Go-Live - VSAT Backup | Lajita Mall | 2026-01-27 | 2026-02-21 | 54 | Completed | 0
TSK0232 | PRJ029 | CL006 | Hypercare | Hypercare - VSAT Backup | Vansha Thakkar | 2026-02-21 | 2026-03-18 | 58 | Completed | 0
TSK0233 | PRJ030 | CL007 | Initiation | Initiation - SD-WAN Rollout | Chakradev Kari | 2026-02-17 | 2026-03-14 | 98 | Blocked | 0
TSK0234 | PRJ030 | CL007 | Survey | Survey - SD-WAN Rollout | Devansh Rajan | 2026-03-14 | 2026-04-08 | 93 | Blocked | 0
TSK0235 | PRJ030 | CL007 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Liam Koshy | 2026-04-08 | 2026-05-03 | 83 | Blocked | 0
TSK0236 | PRJ030 | CL007 | Procurement | Procurement - SD-WAN Rollout | Isaac Patil | 2026-05-03 | 2026-05-28 | 95 | Delayed | 5
TSK0237 | PRJ030 | CL007 | Installation | Installation - SD-WAN Rollout | Jai Kota | 2026-05-28 | 2026-06-22 | 86 | Not Started | 0
TSK0238 | PRJ030 | CL007 | Testing | Testing - SD-WAN Rollout | Tanay Rattan | 2026-06-22 | 2026-07-17 | 95 | Completed | 0
TSK0239 | PRJ030 | CL007 | Go-Live | Go-Live - SD-WAN Rollout | Chakradev Kari | 2026-07-17 | 2026-08-11 | 97 | In Progress | 0
TSK0240 | PRJ030 | CL007 | Hypercare | Hypercare - SD-WAN Rollout | Isaac Patil | 2026-08-11 | 2026-09-05 | 97 | Not Started | 0
TSK0241 | PRJ031 | CL007 | Initiation | Initiation - MPLS Backbone | Janaki Handa | 2025-12-02 | 2025-12-27 | 83 | In Progress | 0
TSK0242 | PRJ031 | CL007 | Survey | Survey - MPLS Backbone | Nihal Shere | 2025-12-27 | 2026-01-21 | 77 | Completed | 0
TSK0243 | PRJ031 | CL007 | ROW/Permits | ROW/Permits - MPLS Backbone | Dakshesh Trivedi | 2026-01-21 | 2026-02-15 | 89 | Blocked | 0
TSK0244 | PRJ031 | CL007 | Procurement | Procurement - MPLS Backbone | Ekavir Bhargava | 2026-02-15 | 2026-03-12 | 86 | Delayed | 10
TSK0245 | PRJ031 | CL007 | Installation | Installation - MPLS Backbone | Theodore Devi | 2026-03-12 | 2026-04-06 | 84 | Completed | 0
TSK0246 | PRJ031 | CL007 | Testing | Testing - MPLS Backbone | Nihal Shere | 2026-04-06 | 2026-05-01 | 84 | Delayed | 3
TSK0247 | PRJ031 | CL007 | Go-Live | Go-Live - MPLS Backbone | Janaki Handa | 2026-05-01 | 2026-05-26 | 76 | Not Started | 0
TSK0248 | PRJ031 | CL007 | Hypercare | Hypercare - MPLS Backbone | Advay Contractor | 2026-05-26 | 2026-06-20 | 66 | Blocked | 0
TSK0249 | PRJ032 | CL007 | Initiation | Initiation - SD-WAN Rollout | Fariq Kaul | 2025-06-08 | 2025-07-03 | 49 | Blocked | 0
TSK0250 | PRJ032 | CL007 | Survey | Survey - SD-WAN Rollout | Michael Dutta | 2025-07-03 | 2025-07-28 | 64 | Delayed | 3
TSK0251 | PRJ032 | CL007 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Aarush Lall | 2025-07-28 | 2025-08-22 | 59 | Delayed | 9
TSK0252 | PRJ032 | CL007 | Procurement | Procurement - SD-WAN Rollout | Nihal Shere | 2025-08-22 | 2025-09-16 | 59 | Completed | 0
TSK0253 | PRJ032 | CL007 | Installation | Installation - SD-WAN Rollout | Ekiya Suresh | 2025-09-16 | 2025-10-11 | 61 | Blocked | 0
TSK0254 | PRJ032 | CL007 | Testing | Testing - SD-WAN Rollout | Raksha Varughese | 2025-10-11 | 2025-11-05 | 50 | Blocked | 0
TSK0255 | PRJ032 | CL007 | Go-Live | Go-Live - SD-WAN Rollout | Fariq Kaul | 2025-11-05 | 2025-11-30 | 49 | Delayed | 3
TSK0256 | PRJ032 | CL007 | Hypercare | Hypercare - SD-WAN Rollout | Radhika Dugar | 2025-11-30 | 2025-12-25 | 67 | Completed | 0
TSK0257 | PRJ033 | CL007 | Initiation | Initiation - ATM Connectivity | Janaki Handa | 2025-07-08 | 2025-08-02 | 57 | Blocked | 0
TSK0258 | PRJ033 | CL007 | Survey | Survey - ATM Connectivity | Yashica Cherian | 2025-08-02 | 2025-08-27 | 74 | Delayed | 4
TSK0259 | PRJ033 | CL007 | ROW/Permits | ROW/Permits - ATM Connectivity | Chandresh Zachariah | 2025-08-27 | 2025-09-21 | 69 | Delayed | 3
TSK0260 | PRJ033 | CL007 | Procurement | Procurement - ATM Connectivity | Raksha Varughese | 2025-09-21 | 2025-10-16 | 75 | Not Started | 0
TSK0261 | PRJ033 | CL007 | Installation | Installation - ATM Connectivity | Devika Rastogi | 2025-10-16 | 2025-11-10 | 79 | Completed | 0
TSK0262 | PRJ033 | CL007 | Testing | Testing - ATM Connectivity | Arya Sunder | 2025-11-10 | 2025-12-05 | 66 | Not Started | 0
TSK0263 | PRJ033 | CL007 | Go-Live | Go-Live - ATM Connectivity | Janaki Handa | 2025-12-05 | 2025-12-30 | 63 | Not Started | 0
TSK0264 | PRJ033 | CL007 | Hypercare | Hypercare - ATM Connectivity | Upadhriti Wadhwa | 2025-12-30 | 2026-01-24 | 59 | Not Started | 0
TSK0265 | PRJ034 | CL007 | Initiation | Initiation - SD-WAN Rollout | Fariq Kaul | 2025-10-09 | 2025-11-03 | 61 | Blocked | 0
TSK0266 | PRJ034 | CL007 | Survey | Survey - SD-WAN Rollout | Ekapad Walia | 2025-11-03 | 2025-11-28 | 45 | Blocked | 0
TSK0267 | PRJ034 | CL007 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Irya Sampath | 2025-11-28 | 2025-12-23 | 67 | Delayed | 10
TSK0268 | PRJ034 | CL007 | Procurement | Procurement - SD-WAN Rollout | Simon Tata | 2025-12-23 | 2026-01-17 | 58 | Delayed | 7
TSK0269 | PRJ034 | CL007 | Installation | Installation - SD-WAN Rollout | Nitesh Raghavan | 2026-01-17 | 2026-02-11 | 63 | Delayed | 5
TSK0270 | PRJ034 | CL007 | Testing | Testing - SD-WAN Rollout | Mohammed Gupta | 2026-02-11 | 2026-03-08 | 54 | Blocked | 0
TSK0271 | PRJ034 | CL007 | Go-Live | Go-Live - SD-WAN Rollout | Fariq Kaul | 2026-03-08 | 2026-04-02 | 54 | In Progress | 0
TSK0272 | PRJ034 | CL007 | Hypercare | Hypercare - SD-WAN Rollout | Irya Sampath | 2026-04-02 | 2026-04-27 | 67 | Completed | 0
TSK0273 | PRJ035 | CL008 | Initiation | Initiation - MPLS Backbone | Kritika Brar | 2026-02-21 | 2026-03-18 | 95 | Delayed | 11
TSK0274 | PRJ035 | CL008 | Survey | Survey - MPLS Backbone | Tara Dhar | 2026-03-18 | 2026-04-12 | 82 | Not Started | 0
TSK0275 | PRJ035 | CL008 | ROW/Permits | ROW/Permits - MPLS Backbone | Daksh Karnik | 2026-04-12 | 2026-05-07 | 90 | Completed | 0
TSK0276 | PRJ035 | CL008 | Procurement | Procurement - MPLS Backbone | Wriddhish Bhardwaj | 2026-05-07 | 2026-06-01 | 100 | Completed | 0
TSK0277 | PRJ035 | CL008 | Installation | Installation - MPLS Backbone | Arya Shere | 2026-06-01 | 2026-06-26 | 100 | Completed | 0
TSK0278 | PRJ035 | CL008 | Testing | Testing - MPLS Backbone | Ekapad Walia | 2026-06-26 | 2026-07-21 | 100 | Completed | 0
TSK0279 | PRJ035 | CL008 | Go-Live | Go-Live - MPLS Backbone | Kritika Brar | 2026-07-21 | 2026-08-15 | 81 | Completed | 0
TSK0280 | PRJ035 | CL008 | Hypercare | Hypercare - MPLS Backbone | Anamika Kanda | 2026-08-15 | 2026-09-09 | 92 | Completed | 0
TSK0281 | PRJ036 | CL008 | Initiation | Initiation - SD-WAN Rollout | Lajita Mall | 2025-10-04 | 2025-10-29 | 40 | Blocked | 0
TSK0282 | PRJ036 | CL008 | Survey | Survey - SD-WAN Rollout | Girik Khalsa | 2025-10-29 | 2025-11-23 | 38 | In Progress | 0
TSK0283 | PRJ036 | CL008 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Darsh Rau | 2025-11-23 | 2025-12-18 | 59 | Blocked | 0
TSK0284 | PRJ036 | CL008 | Procurement | Procurement - SD-WAN Rollout | Yatin Baral | 2025-12-18 | 2026-01-12 | 54 | Completed | 0
TSK0285 | PRJ036 | CL008 | Installation | Installation - SD-WAN Rollout | Dominic Kakar | 2026-01-12 | 2026-02-06 | 59 | Not Started | 0
TSK0286 | PRJ036 | CL008 | Testing | Testing - SD-WAN Rollout | Advay Contractor | 2026-02-06 | 2026-03-03 | 38 | Blocked | 0
TSK0287 | PRJ036 | CL008 | Go-Live | Go-Live - SD-WAN Rollout | Lajita Mall | 2026-03-03 | 2026-03-28 | 47 | Delayed | 9
TSK0288 | PRJ036 | CL008 | Hypercare | Hypercare - SD-WAN Rollout | Kabir Soman | 2026-03-28 | 2026-04-22 | 44 | In Progress | 0
TSK0289 | PRJ037 | CL008 | Initiation | Initiation - Branch Link Upgrade | Gayathri Chaudry | 2025-05-25 | 2025-06-19 | 52 | Delayed | 9
TSK0290 | PRJ037 | CL008 | Survey | Survey - Branch Link Upgrade | Siddharth Zacharia | 2025-06-19 | 2025-07-14 | 50 | Completed | 0
TSK0291 | PRJ037 | CL008 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Isaac Patil | 2025-07-14 | 2025-08-08 | 50 | Completed | 0
TSK0292 | PRJ037 | CL008 | Procurement | Procurement - Branch Link Upgrade | Chandresh Zachariah | 2025-08-08 | 2025-09-02 | 39 | Delayed | 1
TSK0293 | PRJ037 | CL008 | Installation | Installation - Branch Link Upgrade | Wriddhish Bhardwaj | 2025-09-02 | 2025-09-27 | 39 | In Progress | 0
TSK0294 | PRJ037 | CL008 | Testing | Testing - Branch Link Upgrade | Madhavi Lanka | 2025-09-27 | 2025-10-22 | 52 | In Progress | 0
TSK0295 | PRJ037 | CL008 | Go-Live | Go-Live - Branch Link Upgrade | Gayathri Chaudry | 2025-10-22 | 2025-11-16 | 47 | In Progress | 0
TSK0296 | PRJ037 | CL008 | Hypercare | Hypercare - Branch Link Upgrade | Tara Dhar | 2025-11-16 | 2025-12-11 | 59 | In Progress | 0
TSK0297 | PRJ038 | CL008 | Initiation | Initiation - SD-WAN Rollout | Lajita Mall | 2025-11-10 | 2025-12-05 | 93 | Not Started | 0
TSK0298 | PRJ038 | CL008 | Survey | Survey - SD-WAN Rollout | Jai Kota | 2025-12-05 | 2025-12-30 | 90 | In Progress | 0
TSK0299 | PRJ038 | CL008 | ROW/Permits | ROW/Permits - SD-WAN Rollout | Irya Sampath | 2025-12-30 | 2026-01-24 | 91 | Blocked | 0
TSK0300 | PRJ038 | CL008 | Procurement | Procurement - SD-WAN Rollout | Tanay Rattan | 2026-01-24 | 2026-02-18 | 87 | In Progress | 0
TSK0301 | PRJ038 | CL008 | Installation | Installation - SD-WAN Rollout | Simon Tata | 2026-02-18 | 2026-03-15 | 91 | In Progress | 0
TSK0302 | PRJ038 | CL008 | Testing | Testing - SD-WAN Rollout | Girik Khalsa | 2026-03-15 | 2026-04-09 | 98 | In Progress | 0
TSK0303 | PRJ038 | CL008 | Go-Live | Go-Live - SD-WAN Rollout | Lajita Mall | 2026-04-09 | 2026-05-04 | 97 | Completed | 0
TSK0304 | PRJ038 | CL008 | Hypercare | Hypercare - SD-WAN Rollout | Tara Dhar | 2026-05-04 | 2026-05-29 | 100 | Completed | 0
TSK0305 | PRJ039 | CL008 | Initiation | Initiation - Branch Link Upgrade | Tripti Yadav | 2025-09-29 | 2025-10-24 | 50 | In Progress | 0
TSK0306 | PRJ039 | CL008 | Survey | Survey - Branch Link Upgrade | Vansha Thakkar | 2025-10-24 | 2025-11-18 | 55 | Completed | 0
TSK0307 | PRJ039 | CL008 | ROW/Permits | ROW/Permits - Branch Link Upgrade | Irya Sampath | 2025-11-18 | 2025-12-13 | 53 | Not Started | 0
TSK0308 | PRJ039 | CL008 | Procurement | Procurement - Branch Link Upgrade | Radhika Dugar | 2025-12-13 | 2026-01-07 | 50 | Completed | 0
TSK0309 | PRJ039 | CL008 | Installation | Installation - Branch Link Upgrade | Yashica Cherian | 2026-01-07 | 2026-02-01 | 54 | Not Started | 0
TSK0310 | PRJ039 | CL008 | Testing | Testing - Branch Link Upgrade | Priya Rastogi | 2026-02-01 | 2026-02-26 | 50 | Not Started | 0
TSK0311 | PRJ039 | CL008 | Go-Live | Go-Live - Branch Link Upgrade | Tripti Yadav | 2026-02-26 | 2026-03-23 | 70 | Blocked | 0
TSK0312 | PRJ039 | CL008 | Hypercare | Hypercare - Branch Link Upgrade | Liam Koshy | 2026-03-23 | 2026-04-17 | 52 | Not Started | 0
TSK0313 | PRJ040 | CL008 | Initiation | Initiation - ATM Connectivity | Gayathri Chaudry | 2025-12-18 | 2026-01-12 | 81 | Completed | 0
TSK0314 | PRJ040 | CL008 | Survey | Survey - ATM Connectivity | Yashica Cherian | 2026-01-12 | 2026-02-06 | 100 | Completed | 0
TSK0315 | PRJ040 | CL008 | ROW/Permits | ROW/Permits - ATM Connectivity | Chandresh Zachariah | 2026-02-06 | 2026-03-03 | 85 | Completed | 0
TSK0316 | PRJ040 | CL008 | Procurement | Procurement - ATM Connectivity | Yatin Baral | 2026-03-03 | 2026-03-28 | 100 | Completed | 0
TSK0317 | PRJ040 | CL008 | Installation | Installation - ATM Connectivity | Yashica Issac | 2026-03-28 | 2026-04-22 | 87 | Blocked | 0
TSK0318 | PRJ040 | CL008 | Testing | Testing - ATM Connectivity | Simon Tata | 2026-04-22 | 2026-05-17 | 94 | Delayed | 10
TSK0319 | PRJ040 | CL008 | Go-Live | Go-Live - ATM Connectivity | Gayathri Chaudry | 2026-05-17 | 2026-06-11 | 96 | Completed | 0
TSK0320 | PRJ040 | CL008 | Hypercare | Hypercare - ATM Connectivity | Urvashi Ray | 2026-06-11 | 2026-07-06 | 100 | Completed | 0

## RAID_Log
RAIDID | ProjectID | ClientID | Type | Title | Severity | Owner | Status | Impact | DueDate | DaysOpen
RD001 | PRJ001 | CL001 | Risk | Aspernatur omnis natus et ea pariatur et eaque | Medium | Tripti Yadav | Closed | Scope | 2026-07-27 | 34
RD002 | PRJ001 | CL001 | Assumption | Perferendis error et quibusdam | Critical | Fariq Kaul | Escalated | Schedule | 2026-08-08 | 45
RD003 | PRJ001 | CL001 | Risk | Ab numquam natus aut | Medium | Janaki Handa | Escalated | Cost | 2026-07-15 | 22
RD004 | PRJ001 | CL001 | Dependency | Distinctio eaque ut sunt sunt fuga culpa | Critical | Janaki Handa | Open | Quality | 2026-07-16 | 21
RD005 | PRJ002 | CL001 | Risk | Autem ipsa quas | Critical | Janya Gaba | Open | Cost | 2026-06-27 | 31
RD006 | PRJ002 | CL001 | Assumption | Ipsa voluptates blanditiis tempore deleniti aliquid | Medium | Arunima Dugal | Closed | Scope | 2026-07-04 | 29
RD007 | PRJ002 | CL001 | Assumption | A unde modi quaerat quia perferendis | High | Tripti Yadav | Open | Quality | 2026-07-30 | 24
RD008 | PRJ002 | CL001 | Issue | Inventore veniam ullam numquam optio commodi | Low | Janya Gaba | Open | Scope | 2026-07-08 | 11
RD009 | PRJ002 | CL001 | Dependency | Magni pariatur eveniet possimus mollitia | High | Isha Kadakia | Open | Quality | 2026-07-12 | 40
RD010 | PRJ003 | CL001 | Issue | Ad hic natus ad odit consequatur iure | High | Isha Kadakia | Open | Schedule | 2026-07-10 | 52
RD011 | PRJ003 | CL001 | Dependency | Ea eveniet iste | High | Fariq Kaul | Open | Quality | 2026-08-03 | 37
RD012 | PRJ003 | CL001 | Risk | Quis fugit quibusdam rerum dolorum aspernatur | Critical | Chakradev Kari | Closed | Schedule | 2026-07-20 | 55
RD013 | PRJ003 | CL001 | Issue | Quibusdam amet veritatis | High | Lajita Chatterjee | Closed | Schedule | 2026-07-25 | 44
RD014 | PRJ003 | CL001 | Risk | Officiis quos officiis quidem veniam | Medium | Isha Kadakia | Open | Schedule | 2026-08-12 | 56
RD015 | PRJ004 | CL001 | Issue | Voluptate mollitia possimus | Low | Kritika Brar | Open | Scope | 2026-07-29 | 17
RD016 | PRJ004 | CL001 | Risk | Odit quidem aut accusamus | Low | Janya Gaba | Open | Schedule | 2026-06-22 | 45
RD017 | PRJ004 | CL001 | Risk | Iusto ipsam delectus amet velit | Critical | Chakradev Kari | Escalated | Schedule | 2026-07-24 | 17
RD018 | PRJ005 | CL001 | Issue | Est accusamus illum dolore | Medium | Arunima Dugal | Mitigated | Cost | 2026-07-31 | 17
RD019 | PRJ005 | CL001 | Risk | Itaque blanditiis rerum libero | Medium | Lajita Chatterjee | Escalated | Schedule | 2026-06-25 | 5
RD020 | PRJ005 | CL001 | Dependency | Magni earum rerum voluptatem doloribus | Low | Arunima Dugal | Escalated | Schedule | 2026-06-25 | 17
RD021 | PRJ005 | CL001 | Issue | Corporis deleniti nobis quia consequatur architecto quo | Low | Janya Gaba | Escalated | Quality | 2026-07-03 | 16
RD022 | PRJ005 | CL001 | Assumption | Excepturi ratione eaque a quas saepe | Critical | Janya Gaba | Mitigated | Cost | 2026-07-22 | 54
RD023 | PRJ005 | CL001 | Issue | Voluptatum laudantium corrupti molestiae exercitationem mollitia molestiae iste | Low | Arunima Dugal | Closed | Quality | 2026-08-13 | 31
RD024 | PRJ006 | CL002 | Assumption | Alias facilis consectetur tenetur eveniet impedit | Low | Janya Gaba | Open | Quality | 2026-07-18 | 57
RD025 | PRJ006 | CL002 | Risk | Consequatur molestiae voluptas minus totam | Low | Fariq Kaul | Closed | Schedule | 2026-07-25 | 49
RD026 | PRJ006 | CL002 | Assumption | Ducimus repudiandae laboriosam rem | Medium | Kritika Brar | Mitigated | Cost | 2026-07-07 | 18
RD027 | PRJ007 | CL002 | Dependency | Error officia adipisci voluptatum sed incidunt autem | Medium | Arunima Dugal | Open | Cost | 2026-07-05 | 20
RD028 | PRJ007 | CL002 | Dependency | Asperiores aspernatur non aperiam eius odio | Low | Janya Gaba | Closed | Scope | 2026-06-30 | 32
RD029 | PRJ007 | CL002 | Issue | Quae fugit nisi eos magni inventore recusandae | Low | Gayathri Chaudry | Closed | Scope | 2026-06-23 | 39
RD030 | PRJ007 | CL002 | Assumption | Sequi officiis quisquam quam | Critical | Lajita Mall | Escalated | Quality | 2026-07-29 | 44
RD031 | PRJ007 | CL002 | Dependency | Inventore suscipit impedit repudiandae id | Low | Kritika Brar | Open | Quality | 2026-06-29 | 38
RD032 | PRJ007 | CL002 | Risk | Est est ducimus veritatis | Medium | Kritika Brar | Escalated | Cost | 2026-07-11 | 11
RD033 | PRJ008 | CL002 | Assumption | Officia voluptates eum voluptas et ipsam iusto | Critical | Janya Gaba | Escalated | Scope | 2026-08-02 | 60
RD034 | PRJ008 | CL002 | Dependency | Esse earum animi magni est iste animi rerum | Critical | Lajita Chatterjee | Mitigated | Cost | 2026-07-20 | 46
RD035 | PRJ008 | CL002 | Dependency | Officia voluptate at nisi | Medium | Isha Kadakia | Open | Cost | 2026-07-18 | 31
RD036 | PRJ008 | CL002 | Risk | Iure mollitia recusandae tempore ipsum repellat | Medium | Fariq Kaul | Closed | Schedule | 2026-07-27 | 55
RD037 | PRJ008 | CL002 | Dependency | Eum labore corrupti aperiam aut | Low | Gayathri Chaudry | Closed | Quality | 2026-06-21 | 34
RD038 | PRJ008 | CL002 | Issue | Voluptatem assumenda officia aliquam provident voluptatibus | Low | Kritika Brar | Closed | Quality | 2026-07-08 | 19
RD039 | PRJ009 | CL002 | Assumption | Ipsum a aspernatur ducimus rerum molestias quas | Medium | Tripti Yadav | Closed | Schedule | 2026-07-22 | 51
RD040 | PRJ009 | CL002 | Dependency | Incidunt quod dolores commodi dolores odit numquam | High | Arunima Dugal | Mitigated | Quality | 2026-07-10 | 16
RD041 | PRJ009 | CL002 | Issue | Beatae temporibus nisi accusamus | Low | Janya Gaba | Mitigated | Cost | 2026-07-27 | 56
RD042 | PRJ009 | CL002 | Dependency | Nemo quaerat eos a explicabo necessitatibus deleniti | High | Lajita Chatterjee | Escalated | Schedule | 2026-06-23 | 56
RD043 | PRJ009 | CL002 | Dependency | Minima facere veritatis molestias | Low | Hemangini Lalla | Open | Cost | 2026-07-02 | 9
RD044 | PRJ009 | CL002 | Risk | Mollitia hic iusto odio voluptatem ducimus accusamus | Medium | Lajita Mall | Mitigated | Cost | 2026-07-21 | 6
RD045 | PRJ010 | CL002 | Issue | Dolore voluptates recusandae dolores laudantium facere nemo | Medium | Isha Kadakia | Mitigated | Cost | 2026-07-06 | 50
RD046 | PRJ010 | CL002 | Risk | Rem mollitia nostrum assumenda est voluptatum quaerat | High | Isha Kadakia | Mitigated | Scope | 2026-07-01 | 31
RD047 | PRJ010 | CL002 | Risk | Illum illum nemo commodi et asperiores iure | Medium | Hemangini Lalla | Mitigated | Cost | 2026-06-26 | 9
RD048 | PRJ010 | CL002 | Dependency | Exercitationem soluta quos odit delectus vitae inventore | Low | Tripti Yadav | Mitigated | Cost | 2026-07-16 | 2
RD049 | PRJ010 | CL002 | Issue | Rerum maxime esse cum | Low | Arunima Dugal | Escalated | Scope | 2026-07-22 | 20
RD050 | PRJ010 | CL002 | Issue | Exercitationem velit tempora sapiente dolorum | Medium | Kritika Brar | Escalated | Scope | 2026-06-22 | 33
RD051 | PRJ011 | CL002 | Risk | Neque quam nesciunt cupiditate occaecati nulla sapiente corporis | Medium | Hemangini Lalla | Closed | Schedule | 2026-07-02 | 2
RD052 | PRJ011 | CL002 | Assumption | Adipisci veniam beatae accusantium et | Medium | Hemangini Lalla | Open | Cost | 2026-07-06 | 18
RD053 | PRJ011 | CL002 | Dependency | Impedit dignissimos magnam nostrum | Medium | Gayathri Chaudry | Closed | Quality | 2026-07-18 | 48
RD054 | PRJ012 | CL003 | Issue | Error quam accusamus officiis possimus aperiam | Medium | Fariq Kaul | Closed | Schedule | 2026-07-04 | 32
RD055 | PRJ012 | CL003 | Risk | Iure cum placeat unde | Low | Kritika Brar | Open | Scope | 2026-07-27 | 48
RD056 | PRJ012 | CL003 | Risk | Porro odit velit facilis dolore | Critical | Lajita Chatterjee | Closed | Schedule | 2026-06-25 | 3
RD057 | PRJ013 | CL003 | Risk | Neque quo repellendus dolores soluta voluptates | Medium | Hemangini Lalla | Mitigated | Quality | 2026-07-08 | 6
RD058 | PRJ013 | CL003 | Issue | Dolore error aperiam veniam sunt tenetur numquam | Medium | Hemangini Lalla | Escalated | Schedule | 2026-08-04 | 16
RD059 | PRJ013 | CL003 | Issue | Nam aliquid exercitationem officia fugit minima | High | Arunima Dugal | Escalated | Cost | 2026-07-11 | 7
RD060 | PRJ013 | CL003 | Dependency | Illum error delectus modi dolores dolorem | Critical | Isha Kadakia | Mitigated | Scope | 2026-07-31 | 25
RD061 | PRJ013 | CL003 | Dependency | Rem totam natus voluptas | Medium | Gayathri Chaudry | Escalated | Cost | 2026-07-09 | 49
RD062 | PRJ013 | CL003 | Issue | Minus harum ducimus ex aspernatur ipsum fuga | Critical | Kritika Brar | Closed | Scope | 2026-07-27 | 26
RD063 | PRJ014 | CL003 | Dependency | Natus similique atque minus aliquam distinctio | Medium | Chakradev Kari | Closed | Scope | 2026-06-26 | 48
RD064 | PRJ014 | CL003 | Assumption | Labore aliquid asperiores unde tempore natus adipisci | High | Kritika Brar | Mitigated | Quality | 2026-07-10 | 52
RD065 | PRJ014 | CL003 | Dependency | Accusamus dignissimos corporis reprehenderit reprehenderit ut | Critical | Janya Gaba | Open | Quality | 2026-08-06 | 34
RD066 | PRJ014 | CL003 | Assumption | Cum dolores rerum harum tempore | Low | Kritika Brar | Escalated | Schedule | 2026-07-23 | 9
RD067 | PRJ014 | CL003 | Risk | Fugit qui ratione porro aspernatur quia | Medium | Chakradev Kari | Open | Schedule | 2026-07-24 | 46
RD068 | PRJ014 | CL003 | Assumption | Amet ipsa saepe excepturi quisquam veritatis | Medium | Kritika Brar | Closed | Scope | 2026-07-16 | 36
RD069 | PRJ015 | CL003 | Issue | Nam porro dolore fugiat iure perspiciatis porro | Critical | Janaki Handa | Escalated | Schedule | 2026-08-02 | 44
RD070 | PRJ015 | CL003 | Assumption | Exercitationem ad autem impedit | Critical | Kritika Brar | Closed | Scope | 2026-07-15 | 46
RD071 | PRJ015 | CL003 | Assumption | Blanditiis velit consequuntur est | Medium | Kritika Brar | Closed | Cost | 2026-07-20 | 19
RD072 | PRJ015 | CL003 | Assumption | Quos maxime expedita atque quam iste architecto | Low | Chakradev Kari | Open | Quality | 2026-08-13 | 33
RD073 | PRJ015 | CL003 | Risk | Repellat beatae sed | Low | Lajita Chatterjee | Open | Cost | 2026-06-23 | 12
RD074 | PRJ015 | CL003 | Assumption | Perspiciatis cum voluptates doloribus | Low | Lajita Chatterjee | Mitigated | Schedule | 2026-08-13 | 5
RD075 | PRJ016 | CL004 | Dependency | Vitae quos ullam voluptatibus | Critical | Gayathri Chaudry | Open | Schedule | 2026-07-05 | 57
RD076 | PRJ016 | CL004 | Assumption | Praesentium consequatur corporis eum | Critical | Janaki Handa | Mitigated | Cost | 2026-06-26 | 2
RD077 | PRJ016 | CL004 | Issue | Quis perspiciatis laudantium neque eaque | Low | Lajita Mall | Mitigated | Cost | 2026-07-17 | 43
RD078 | PRJ016 | CL004 | Assumption | Fugiat asperiores recusandae quisquam illo quibusdam | High | Chakradev Kari | Open | Cost | 2026-07-26 | 27
RD079 | PRJ016 | CL004 | Risk | Iste laborum neque sit sed at | Low | Hemangini Lalla | Mitigated | Cost | 2026-07-08 | 9
RD080 | PRJ017 | CL004 | Issue | Magni occaecati magnam impedit praesentium assumenda | Medium | Isha Kadakia | Open | Schedule | 2026-08-01 | 26
RD081 | PRJ017 | CL004 | Issue | Modi corrupti assumenda aspernatur ullam voluptate culpa | Medium | Tripti Yadav | Open | Schedule | 2026-07-30 | 14
RD082 | PRJ017 | CL004 | Risk | Hic odio rerum perspiciatis architecto praesentium | Low | Janaki Handa | Open | Quality | 2026-07-02 | 29
RD083 | PRJ018 | CL004 | Assumption | Veritatis a omnis | Critical | Gayathri Chaudry | Closed | Cost | 2026-07-23 | 51
RD084 | PRJ018 | CL004 | Assumption | Aut minus dolores laudantium animi | Critical | Janya Gaba | Mitigated | Cost | 2026-07-10 | 37
RD085 | PRJ018 | CL004 | Risk | Quae at ullam tempore | High | Arunima Dugal | Closed | Cost | 2026-06-30 | 57
RD086 | PRJ018 | CL004 | Issue | Impedit tempora itaque quibusdam neque magnam odio | Low | Lajita Chatterjee | Mitigated | Quality | 2026-08-07 | 10
RD087 | PRJ018 | CL004 | Dependency | Asperiores necessitatibus ipsa vitae dolores ea | Critical | Lajita Mall | Open | Scope | 2026-07-28 | 45
RD088 | PRJ018 | CL004 | Risk | Unde hic rerum eveniet iste doloremque | Critical | Lajita Chatterjee | Escalated | Schedule | 2026-07-18 | 49
RD089 | PRJ019 | CL004 | Risk | Debitis nihil rem possimus | Critical | Arunima Dugal | Mitigated | Scope | 2026-06-26 | 42
RD090 | PRJ019 | CL004 | Dependency | Adipisci praesentium veniam natus natus deleniti voluptates sunt | Medium | Gayathri Chaudry | Escalated | Cost | 2026-07-01 | 29
RD091 | PRJ019 | CL004 | Issue | Molestiae cupiditate alias animi nobis accusantium labore | Medium | Arunima Dugal | Closed | Cost | 2026-06-30 | 10
RD092 | PRJ019 | CL004 | Issue | Ullam dicta consectetur quaerat ullam sapiente | Critical | Lajita Chatterjee | Open | Scope | 2026-08-09 | 21
RD093 | PRJ020 | CL004 | Risk | Iusto tempora eaque odit harum fuga | Critical | Chakradev Kari | Open | Schedule | 2026-06-20 | 39
RD094 | PRJ020 | CL004 | Assumption | Fuga ipsum ea iure dolorem eaque | Medium | Tripti Yadav | Closed | Cost | 2026-06-22 | 19
RD095 | PRJ020 | CL004 | Dependency | Corrupti possimus atque pariatur | Critical | Janya Gaba | Closed | Scope | 2026-07-16 | 32
RD096 | PRJ020 | CL004 | Dependency | Impedit quidem dolorem aperiam harum minima vitae | Low | Kritika Brar | Escalated | Quality | 2026-06-29 | 1
RD097 | PRJ020 | CL004 | Assumption | Nemo doloremque error hic sequi alias necessitatibus | High | Janaki Handa | Closed | Scope | 2026-08-06 | 29
RD098 | PRJ021 | CL005 | Assumption | Incidunt fugiat expedita dolorum iure | Medium | Kritika Brar | Closed | Cost | 2026-06-21 | 24
RD099 | PRJ021 | CL005 | Dependency | Repudiandae id aut maiores optio sapiente fugiat | Low | Arunima Dugal | Open | Scope | 2026-07-20 | 37
RD100 | PRJ021 | CL005 | Risk | Non error autem aperiam voluptates odit similique ea | Low | Janaki Handa | Escalated | Schedule | 2026-06-23 | 35
RD101 | PRJ021 | CL005 | Dependency | Deleniti maxime dolores animi similique | Critical | Chakradev Kari | Closed | Schedule | 2026-08-07 | 45
RD102 | PRJ021 | CL005 | Issue | Illo eum consequuntur ad libero eos tenetur illo | Critical | Fariq Kaul | Closed | Cost | 2026-08-03 | 57
RD103 | PRJ022 | CL005 | Assumption | Voluptatum optio officiis accusantium porro impedit fugit molestias | High | Isha Kadakia | Mitigated | Scope | 2026-07-01 | 3
RD104 | PRJ022 | CL005 | Dependency | Praesentium dignissimos placeat ab in aut maxime | High | Lajita Mall | Escalated | Cost | 2026-07-18 | 29
RD105 | PRJ022 | CL005 | Risk | Non consequatur rerum autem quaerat blanditiis beatae autem | Low | Janya Gaba | Closed | Cost | 2026-07-25 | 45
RD106 | PRJ022 | CL005 | Dependency | Non quod rerum voluptate facere | Medium | Kritika Brar | Mitigated | Schedule | 2026-08-02 | 24
RD107 | PRJ023 | CL005 | Issue | Vitae odit tempora natus omnis itaque exercitationem repudiandae | Critical | Gayathri Chaudry | Escalated | Schedule | 2026-07-10 | 49
RD108 | PRJ023 | CL005 | Assumption | Sapiente ex quisquam nobis quaerat | High | Kritika Brar | Open | Quality | 2026-08-08 | 60
RD109 | PRJ023 | CL005 | Issue | Quaerat beatae quis dolore exercitationem rerum | Critical | Chakradev Kari | Mitigated | Scope | 2026-07-22 | 7
RD110 | PRJ023 | CL005 | Risk | Molestias fugiat autem tempore laudantium | Medium | Isha Kadakia | Mitigated | Schedule | 2026-07-02 | 34
RD111 | PRJ023 | CL005 | Assumption | Autem nostrum deleniti ut hic itaque | Critical | Fariq Kaul | Open | Schedule | 2026-07-25 | 16
RD112 | PRJ024 | CL005 | Dependency | Aliquam ut nisi quo | Low | Arunima Dugal | Mitigated | Quality | 2026-07-31 | 56
RD113 | PRJ024 | CL005 | Assumption | Nulla optio laudantium nemo facere quos et dolore | Medium | Lajita Chatterjee | Mitigated | Scope | 2026-06-30 | 11
RD114 | PRJ024 | CL005 | Risk | Maxime ratione cum molestiae | Critical | Lajita Mall | Open | Scope | 2026-07-27 | 43
RD115 | PRJ024 | CL005 | Dependency | At dolore distinctio ex facere dolor | High | Chakradev Kari | Closed | Scope | 2026-07-31 | 31
RD116 | PRJ024 | CL005 | Risk | Minus voluptatum reprehenderit voluptatem ab pariatur ipsum temporibus | Critical | Chakradev Kari | Closed | Schedule | 2026-07-16 | 40
RD117 | PRJ025 | CL006 | Risk | Eius facere perspiciatis ex laboriosam ipsum | Critical | Chakradev Kari | Mitigated | Scope | 2026-07-02 | 20
RD118 | PRJ025 | CL006 | Issue | Laborum autem officia aspernatur eligendi | Critical | Janaki Handa | Open | Quality | 2026-08-09 | 41
RD119 | PRJ025 | CL006 | Assumption | Tempora deserunt quasi occaecati | Low | Janya Gaba | Closed | Cost | 2026-06-27 | 54
RD120 | PRJ025 | CL006 | Risk | Tempora sed occaecati repellat | Critical | Arunima Dugal | Closed | Scope | 2026-08-06 | 45
RD121 | PRJ025 | CL006 | Risk | Illo nihil temporibus mollitia molestiae voluptatum iusto quod | Critical | Janya Gaba | Escalated | Schedule | 2026-07-15 | 26
RD122 | PRJ026 | CL006 | Dependency | Ducimus a quia ab minima maxime | Low | Chakradev Kari | Open | Quality | 2026-07-17 | 56
RD123 | PRJ026 | CL006 | Issue | Omnis porro et facere culpa officiis | Critical | Janaki Handa | Open | Cost | 2026-07-01 | 23
RD124 | PRJ026 | CL006 | Risk | Ea modi natus nostrum voluptatibus | High | Fariq Kaul | Closed | Schedule | 2026-06-23 | 24
RD125 | PRJ026 | CL006 | Issue | Quidem impedit quos laboriosam fuga mollitia | Low | Gayathri Chaudry | Escalated | Cost | 2026-08-01 | 47
RD126 | PRJ026 | CL006 | Risk | Voluptates neque quo id consequuntur | Critical | Chakradev Kari | Open | Quality | 2026-07-16 | 4
RD127 | PRJ027 | CL006 | Risk | Sit laudantium voluptates totam eligendi dolore nemo | Critical | Isha Kadakia | Mitigated | Schedule | 2026-07-24 | 58
RD128 | PRJ027 | CL006 | Issue | Minima incidunt velit | Critical | Janaki Handa | Escalated | Scope | 2026-06-26 | 39
RD129 | PRJ027 | CL006 | Dependency | Magnam hic placeat | Critical | Janaki Handa | Escalated | Schedule | 2026-06-19 | 9
RD130 | PRJ027 | CL006 | Assumption | Itaque blanditiis maxime et | Critical | Hemangini Lalla | Closed | Cost | 2026-08-09 | 59
RD131 | PRJ027 | CL006 | Risk | Accusamus distinctio neque | Medium | Lajita Chatterjee | Mitigated | Cost | 2026-07-06 | 40
RD132 | PRJ028 | CL006 | Dependency | Minima quis consequatur | High | Lajita Mall | Closed | Schedule | 2026-07-23 | 49
RD133 | PRJ028 | CL006 | Assumption | Iusto ab ullam veniam labore | Medium | Lajita Mall | Open | Scope | 2026-07-27 | 28
RD134 | PRJ028 | CL006 | Risk | Quisquam reiciendis nisi | High | Kritika Brar | Mitigated | Scope | 2026-06-19 | 25
RD135 | PRJ028 | CL006 | Risk | Molestias deleniti sunt | Low | Janaki Handa | Closed | Scope | 2026-07-18 | 16
RD136 | PRJ028 | CL006 | Issue | Hic cum qui harum fugiat ea | Critical | Tripti Yadav | Closed | Scope | 2026-06-21 | 6
RD137 | PRJ029 | CL006 | Dependency | Necessitatibus saepe omnis | Low | Janya Gaba | Escalated | Schedule | 2026-07-13 | 24
RD138 | PRJ029 | CL006 | Dependency | Numquam nihil aliquid dolore quaerat accusamus ullam | High | Janaki Handa | Escalated | Scope | 2026-07-15 | 19
RD139 | PRJ029 | CL006 | Risk | Unde rerum iusto odit facere quia tempora | Critical | Fariq Kaul | Mitigated | Cost | 2026-07-07 | 50
RD140 | PRJ030 | CL007 | Dependency | Nemo at inventore ratione corporis excepturi labore quia | Low | Gayathri Chaudry | Escalated | Cost | 2026-07-25 | 39
RD141 | PRJ030 | CL007 | Assumption | Id assumenda magnam quo consectetur consequatur nam | High | Tripti Yadav | Open | Cost | 2026-08-04 | 50
RD142 | PRJ030 | CL007 | Assumption | Hic necessitatibus natus voluptatum minima doloribus eaque | High | Hemangini Lalla | Open | Quality | 2026-07-13 | 14
RD143 | PRJ030 | CL007 | Risk | Eum unde at perferendis incidunt expedita | Medium | Arunima Dugal | Escalated | Scope | 2026-07-22 | 43
RD144 | PRJ031 | CL007 | Assumption | Quisquam sunt impedit | Medium | Fariq Kaul | Mitigated | Quality | 2026-07-08 | 5
RD145 | PRJ031 | CL007 | Risk | Esse quia reprehenderit odio qui corrupti | High | Chakradev Kari | Open | Quality | 2026-07-03 | 20
RD146 | PRJ031 | CL007 | Dependency | Autem delectus quis nostrum eaque | Medium | Fariq Kaul | Mitigated | Quality | 2026-06-24 | 48
RD147 | PRJ031 | CL007 | Dependency | Nostrum nisi doloremque ad aspernatur quod consequatur | Critical | Hemangini Lalla | Open | Quality | 2026-08-04 | 15
RD148 | PRJ031 | CL007 | Issue | Iusto officiis delectus harum labore cum dolorem illum | Critical | Chakradev Kari | Open | Quality | 2026-08-13 | 33
RD149 | PRJ032 | CL007 | Issue | Molestiae ab sunt dolores nihil labore illum | Critical | Arunima Dugal | Mitigated | Cost | 2026-06-26 | 28
RD150 | PRJ032 | CL007 | Risk | Nobis ab sunt eius | Critical | Kritika Brar | Closed | Schedule | 2026-06-28 | 56
RD151 | PRJ032 | CL007 | Issue | Nam repudiandae aliquid corporis officiis alias sequi pariatur | Medium | Kritika Brar | Mitigated | Quality | 2026-07-01 | 44
RD152 | PRJ032 | CL007 | Risk | Error ullam aliquid impedit debitis perferendis nostrum porro | Low | Janaki Handa | Closed | Scope | 2026-07-04 | 57
RD153 | PRJ032 | CL007 | Assumption | Nemo natus vitae quibusdam facere alias quisquam eum | Low | Chakradev Kari | Closed | Quality | 2026-07-05 | 25
RD154 | PRJ033 | CL007 | Issue | Ad laboriosam magnam deleniti unde quasi minima | Critical | Janya Gaba | Escalated | Schedule | 2026-07-05 | 51
RD155 | PRJ033 | CL007 | Risk | Corporis sit reprehenderit vel perspiciatis consequatur | Medium | Janya Gaba | Escalated | Schedule | 2026-07-13 | 6
RD156 | PRJ033 | CL007 | Risk | Itaque quae minima | High | Chakradev Kari | Open | Schedule | 2026-08-11 | 7
RD157 | PRJ034 | CL007 | Risk | Recusandae perspiciatis ullam vel quaerat totam voluptatibus | Critical | Chakradev Kari | Closed | Cost | 2026-07-08 | 44
RD158 | PRJ034 | CL007 | Risk | Ab voluptates illo consectetur eos fuga molestias amet | Critical | Isha Kadakia | Mitigated | Schedule | 2026-07-17 | 42
RD159 | PRJ034 | CL007 | Risk | Reprehenderit facere similique sint doloremque praesentium hic | Critical | Chakradev Kari | Escalated | Schedule | 2026-08-01 | 41
RD160 | PRJ034 | CL007 | Issue | Quae illo ipsa distinctio cupiditate consequuntur | High | Janya Gaba | Open | Schedule | 2026-07-20 | 33
RD161 | PRJ034 | CL007 | Issue | Fugit unde saepe culpa voluptatum pariatur consequatur | Critical | Lajita Mall | Mitigated | Cost | 2026-07-01 | 13
RD162 | PRJ034 | CL007 | Assumption | Officiis corporis suscipit omnis | High | Arunima Dugal | Mitigated | Cost | 2026-07-15 | 38
RD163 | PRJ035 | CL008 | Assumption | Et ab ab architecto | High | Janaki Handa | Escalated | Scope | 2026-08-01 | 39
RD164 | PRJ035 | CL008 | Issue | Atque aut ipsum dolor eligendi deserunt | Medium | Hemangini Lalla | Mitigated | Scope | 2026-06-22 | 2
RD165 | PRJ035 | CL008 | Dependency | Nulla animi nisi | Low | Isha Kadakia | Closed | Schedule | 2026-08-08 | 2
RD166 | PRJ036 | CL008 | Issue | Qui doloremque asperiores quasi | Critical | Isha Kadakia | Escalated | Schedule | 2026-06-25 | 53
RD167 | PRJ036 | CL008 | Issue | Officiis iusto ullam aliquid praesentium consectetur cupiditate | High | Kritika Brar | Open | Schedule | 2026-06-29 | 38
RD168 | PRJ036 | CL008 | Assumption | Temporibus reprehenderit atque | Critical | Hemangini Lalla | Open | Schedule | 2026-06-20 | 5
RD169 | PRJ036 | CL008 | Issue | Cupiditate nihil repellendus autem libero reiciendis dolore rem | High | Kritika Brar | Escalated | Schedule | 2026-07-23 | 6
RD170 | PRJ036 | CL008 | Assumption | Excepturi saepe qui illo blanditiis placeat | Low | Janaki Handa | Open | Quality | 2026-07-27 | 37
RD171 | PRJ037 | CL008 | Dependency | Quidem possimus illum dolor facere dolores voluptatum | Critical | Lajita Chatterjee | Closed | Quality | 2026-07-28 | 31
RD172 | PRJ037 | CL008 | Risk | Laboriosam esse provident | High | Kritika Brar | Escalated | Cost | 2026-06-29 | 50
RD173 | PRJ037 | CL008 | Dependency | Quibusdam ad iste quo soluta illo ratione | Critical | Arunima Dugal | Open | Schedule | 2026-08-01 | 22
RD174 | PRJ037 | CL008 | Assumption | Occaecati provident a occaecati harum porro | Low | Chakradev Kari | Escalated | Cost | 2026-07-29 | 52
RD175 | PRJ037 | CL008 | Issue | Adipisci incidunt earum veniam molestiae recusandae ratione | Critical | Arunima Dugal | Escalated | Quality | 2026-07-15 | 33
RD176 | PRJ038 | CL008 | Dependency | Illo libero corporis | High | Gayathri Chaudry | Open | Schedule | 2026-07-11 | 58
RD177 | PRJ038 | CL008 | Dependency | Unde culpa voluptas molestias magni officia eos | Critical | Arunima Dugal | Escalated | Schedule | 2026-07-09 | 30
RD178 | PRJ038 | CL008 | Risk | Voluptas quidem voluptatibus pariatur reiciendis | Low | Lajita Chatterjee | Open | Schedule | 2026-08-12 | 25
RD179 | PRJ038 | CL008 | Dependency | Excepturi beatae laboriosam aliquam perspiciatis blanditiis | Medium | Lajita Chatterjee | Mitigated | Quality | 2026-08-09 | 51
RD180 | PRJ039 | CL008 | Risk | Aut culpa dolore deleniti | Medium | Arunima Dugal | Escalated | Schedule | 2026-07-20 | 7
RD181 | PRJ039 | CL008 | Issue | Nostrum rerum minima minus mollitia quidem beatae | Critical | Janya Gaba | Mitigated | Schedule | 2026-08-08 | 3
RD182 | PRJ039 | CL008 | Assumption | Totam blanditiis consectetur accusantium expedita porro consequuntur | Medium | Lajita Chatterjee | Open | Quality | 2026-07-05 | 11
RD183 | PRJ040 | CL008 | Risk | Eius quisquam autem dolorum libero occaecati consequatur | Low | Lajita Mall | Mitigated | Cost | 2026-07-23 | 49
RD184 | PRJ040 | CL008 | Assumption | Qui rerum libero ad | Medium | Arunima Dugal | Open | Schedule | 2026-07-26 | 3
RD185 | PRJ040 | CL008 | Risk | Fugit perspiciatis corrupti numquam | Critical | Hemangini Lalla | Mitigated | Quality | 2026-07-21 | 47
RD186 | PRJ040 | CL008 | Dependency | Quis optio maxime laudantium | Critical | Chakradev Kari | Closed | Quality | 2026-07-14 | 24
RD187 | PRJ040 | CL008 | Dependency | Dicta optio laudantium ea exercitationem similique molestias | Low | Chakradev Kari | Mitigated | Quality | 2026-07-18 | 42
RD188 | PRJ040 | CL008 | Risk | Voluptatibus sunt blanditiis | Medium | Tripti Yadav | Closed | Scope | 2026-07-29 | 14

## Resources
ResourceID | Name | Role | Region | BillRate_INR | Utilization_Pct | Certification | Experience_Yrs | Status
RES001 | Ekbal Garg | ROW Coordinator | West | 2500 | 60 | PRINCE2 | 10 | On Leave
RES002 | Nihal Shere | QA Lead | West | 6800 | 67 | ITIL | 16 | Allocated
RES003 | Anamika Kanda | ROW Coordinator | Central | 4500 | 55 | PRINCE2 | 16 | Bench
RES004 | Daksh Karnik | Network Engineer | North | 3200 | 76 | PMP | 5 | Bench
RES005 | Diya Rattan | Project Manager | South | 4500 | 93 | CCNA | 4 | On Leave
RES006 | Dominic Kakar | ROW Coordinator | Central | 2500 | 79 | PMP | 12 | On Leave
RES007 | Simon Tata | QA Lead | South | 6800 | 67 | ITIL | 5 | Allocated
RES008 | Tara Dhar | Delivery Manager | North | 4500 | 60 | PRINCE2 | 6 | Bench
RES009 | Liam Koshy | Network Engineer | East | 4500 | 65 | CCNA | 14 | Allocated
RES010 | Priya Rastogi | Delivery Manager | South | 2500 | 93 | ITIL | 8 | On Leave
RES011 | Theodore Devi | Delivery Manager | North | 3200 | 84 | CCNP | 11 | On Leave
RES012 | Gavin Batta | Delivery Manager | Central | 3200 | 98 | CCNA | 4 | Allocated
RES013 | Michael Dutta | Project Manager | South | 5500 | 72 | PMP | 9 | On Leave
RES014 | Devansh Rajan | Delivery Manager | South | 3200 | 96 | CCNP | 15 | On Leave
RES015 | Upadhriti Wadhwa | ROW Coordinator | North | 4500 | 63 | PRINCE2 | 11 | On Leave
RES016 | Advay Contractor | QA Lead | East | 6800 | 80 | CCNA | 10 | Allocated
RES017 | Harini Choudhury | QA Lead | East | 2500 | 58 | PMP | 7 | On Leave
RES018 | Radhika Dugar | Site Engineer | East | 6800 | 59 | CCNP | 15 | On Leave
RES019 | Aarush Lall | ROW Coordinator | Central | 4500 | 90 | PMP | 6 | On Leave
RES020 | Yashica Cherian | QA Lead | South | 4500 | 62 | CCNA | 16 | Allocated
RES021 | Yashica Issac | ROW Coordinator | West | 4500 | 87 | PRINCE2 | 6 | On Leave
RES022 | Kashvi Edwin | Network Engineer | Central | 6800 | 67 | PRINCE2 | 14 | Allocated
RES023 | Ekiya Suresh | QA Lead | Central | 2500 | 93 | CCNA | 18 | Allocated
RES024 | Isaac Patil | Project Manager | South | 4500 | 70 | PMP | 10 | On Leave
RES025 | Wriddhish Bhardwaj | Project Manager | West | 5500 | 59 | CSM | 7 | Allocated
RES026 | Farhan Chada | Delivery Manager | East | 6800 | 65 | CCNA | 16 | Allocated
RES027 | Ekapad Walia | QA Lead | North | 4500 | 80 | ITIL | 14 | Bench
RES028 | Kabir Soman | QA Lead | East | 2500 | 70 | PRINCE2 | 5 | Bench
RES029 | Alka Wable | Project Manager | Central | 6800 | 69 | CSM | 10 | Allocated
RES030 | Siddharth Zacharia | Project Manager | West | 3200 | 59 | PMP | 13 | Allocated
RES031 | Devika Rastogi | QA Lead | North | 4500 | 97 | CCNP | 9 | On Leave
RES032 | Raksha Varughese | Site Engineer | Central | 6800 | 85 | PRINCE2 | 18 | Bench
RES033 | Jai Kota | Site Engineer | West | 2500 | 97 | CCNP | 14 | Bench
RES034 | Devansh Nigam | ROW Coordinator | East | 2500 | 98 | ITIL | 6 | Allocated
RES035 | Victor Kannan | ROW Coordinator | South | 2500 | 70 | PRINCE2 | 9 | On Leave
RES036 | Ekavir Bhargava | ROW Coordinator | North | 5500 | 66 | CCNA | 17 | Allocated
RES037 | Ekansh Balay | Project Manager | East | 6800 | 61 | PMP | 3 | Allocated
RES038 | Ekavir Varkey | Site Engineer | North | 5500 | 86 | CCNP | 9 | Bench
RES039 | Arya Sunder | Project Manager | North | 5500 | 55 | CCNP | 11 | Bench
RES040 | Kevin Solanki | Network Engineer | East | 6800 | 97 | ITIL | 18 | Allocated
RES041 | Urvashi Ray | Site Engineer | South | 3200 | 58 | CSM | 4 | On Leave
RES042 | Girindra Chatterjee | Network Engineer | West | 2500 | 92 | CCNP | 8 | Allocated
RES043 | Irya Sampath | QA Lead | West | 3200 | 59 | CSM | 5 | On Leave
RES044 | Unni Bhagat | Site Engineer | East | 2500 | 91 | PRINCE2 | 4 | On Leave
RES045 | Darsh Rau | Project Manager | East | 6800 | 91 | CSM | 13 | Bench
RES046 | Ikbal Kothari | Site Engineer | South | 3200 | 71 | CCNP | 7 | On Leave
RES047 | Ranveer Yadav | Delivery Manager | South | 5500 | 75 | PMP | 3 | Bench
RES048 | Logan Sami | QA Lead | Central | 2500 | 59 | CSM | 9 | On Leave
RES049 | Arya Shere | Network Engineer | North | 4500 | 59 | PRINCE2 | 14 | Bench
RES050 | Faqid Savant | Site Engineer | East | 6800 | 74 | CSM | 3 | On Leave
RES051 | Chandresh Zachariah | QA Lead | South | 2500 | 63 | CCNA | 6 | Allocated
RES052 | Girik Khalsa | Delivery Manager | Central | 3200 | 72 | CCNA | 9 | On Leave
RES053 | Niharika Sunder | Network Engineer | North | 4500 | 87 | CCNP | 11 | Allocated
RES054 | Tanay Rattan | Project Manager | East | 4500 | 57 | PMP | 13 | Allocated
RES055 | Nitesh Raghavan | Delivery Manager | South | 3200 | 83 | CSM | 16 | On Leave
RES056 | Madhavi Lanka | Project Manager | West | 2500 | 64 | CSM | 4 | Bench
RES057 | Bhavika Sampath | QA Lead | Central | 3200 | 82 | PRINCE2 | 4 | Bench
RES058 | Mohammed Gupta | Network Engineer | West | 4500 | 68 | ITIL | 10 | On Leave
RES059 | Teerth Bhardwaj | Project Manager | South | 6800 | 81 | CSM | 7 | Allocated
RES060 | Dipta Bhandari | Site Engineer | North | 5500 | 56 | PRINCE2 | 13 | Bench
RES061 | Vansha Thakkar | Delivery Manager | North | 4500 | 65 | ITIL | 6 | Bench
RES062 | Dakshesh Trivedi | Project Manager | East | 3200 | 67 | CCNP | 14 | Bench
RES063 | Quincy Biswas | Site Engineer | North | 2500 | 97 | PRINCE2 | 15 | Bench
RES064 | Wahab Raval | Network Engineer | West | 4500 | 77 | ITIL | 15 | On Leave
RES065 | Yatin Baral | QA Lead | South | 2500 | 62 | CCNA | 8 | On Leave

## Budget_Costs
BudgetID | ProjectID | ClientID | Month | Category | Planned_INR | Actual_INR | Variance_Pct
BG0001 | PRJ001 | CL001 | 2026-06 | Labor | 1081577 | 916493 | -15.3
BG0002 | PRJ001 | CL001 | 2026-06 | PMO Overhead | 1158044 | 981985 | -15.2
BG0003 | PRJ001 | CL001 | 2026-06 | Last Mile | 1205020 | 1257289 | 4.3
BG0004 | PRJ001 | CL001 | 2026-06 | Logistics | 2362994 | 2513116 | 6.4
BG0005 | PRJ001 | CL001 | 2026-06 | ROW Charges | 3133588 | 2625928 | -16.2
BG0006 | PRJ001 | CL001 | 2026-05 | Logistics | 4464174 | 4551681 | 2
BG0007 | PRJ001 | CL001 | 2026-05 | Labor | 3946920 | 3737263 | -5.3
BG0008 | PRJ001 | CL001 | 2026-05 | CapEx Hardware | 3824347 | 3194988 | -16.5
BG0009 | PRJ001 | CL001 | 2026-05 | Last Mile | 2006405 | 2006651 | 0
BG0010 | PRJ001 | CL001 | 2026-05 | PMO Overhead | 2274911 | 1936131 | -14.9
BG0011 | PRJ001 | CL001 | 2026-04 | Last Mile | 2268484 | 2435471 | 7.4
BG0012 | PRJ001 | CL001 | 2026-04 | PMO Overhead | 2341662 | 2000869 | -14.6
BG0013 | PRJ001 | CL001 | 2026-04 | ROW Charges | 1968399 | 1953104 | -0.8
BG0014 | PRJ001 | CL001 | 2026-04 | CapEx Hardware | 4185731 | 3971144 | -5.1
BG0015 | PRJ001 | CL001 | 2026-04 | Labor | 3152860 | 3507127 | 11.2
BG0016 | PRJ001 | CL001 | 2026-03 | Logistics | 921438 | 805451 | -12.6
BG0017 | PRJ001 | CL001 | 2026-03 | PMO Overhead | 3747332 | 3929912 | 4.9
BG0018 | PRJ001 | CL001 | 2026-03 | CapEx Hardware | 2225327 | 2059110 | -7.5
BG0019 | PRJ001 | CL001 | 2026-03 | Labor | 1560870 | 1687236 | 8.1
BG0020 | PRJ001 | CL001 | 2026-03 | Last Mile | 3175322 | 3229948 | 1.7
BG0021 | PRJ001 | CL001 | 2026-02 | Last Mile | 3929419 | 3847470 | -2.1
BG0022 | PRJ001 | CL001 | 2026-02 | CapEx Hardware | 2377873 | 2249348 | -5.4
BG0023 | PRJ001 | CL001 | 2026-02 | Logistics | 2229821 | 1933751 | -13.3
BG0024 | PRJ001 | CL001 | 2026-01 | PMO Overhead | 1452549 | 1259683 | -13.3
BG0025 | PRJ001 | CL001 | 2026-01 | Labor | 3391401 | 2831578 | -16.5
BG0026 | PRJ001 | CL001 | 2026-01 | CapEx Hardware | 1142177 | 1029822 | -9.8
BG0027 | PRJ001 | CL001 | 2026-01 | ROW Charges | 3576372 | 3387555 | -5.3
BG0028 | PRJ002 | CL001 | 2026-06 | Last Mile | 1442506 | 1379747 | -4.4
BG0029 | PRJ002 | CL001 | 2026-06 | PMO Overhead | 3340653 | 3113780 | -6.8
BG0030 | PRJ002 | CL001 | 2026-06 | ROW Charges | 3744152 | 3687129 | -1.5
BG0031 | PRJ002 | CL001 | 2026-05 | Logistics | 3965607 | 3960627 | -0.1
BG0032 | PRJ002 | CL001 | 2026-05 | Last Mile | 4102472 | 3464788 | -15.5
BG0033 | PRJ002 | CL001 | 2026-05 | PMO Overhead | 2673796 | 2616180 | -2.2
BG0034 | PRJ002 | CL001 | 2026-05 | Labor | 2317435 | 1954596 | -15.7
BG0035 | PRJ002 | CL001 | 2026-04 | CapEx Hardware | 1490118 | 1368576 | -8.2
BG0036 | PRJ002 | CL001 | 2026-04 | PMO Overhead | 2982470 | 2840958 | -4.7
BG0037 | PRJ002 | CL001 | 2026-04 | Last Mile | 3653365 | 3220881 | -11.8
BG0038 | PRJ002 | CL001 | 2026-04 | Labor | 3245898 | 3137642 | -3.3
BG0039 | PRJ002 | CL001 | 2026-04 | Logistics | 2940669 | 2804353 | -4.6
BG0040 | PRJ002 | CL001 | 2026-03 | ROW Charges | 2715951 | 2686546 | -1.1
BG0041 | PRJ002 | CL001 | 2026-03 | Last Mile | 3143765 | 3013969 | -4.1
BG0042 | PRJ002 | CL001 | 2026-03 | PMO Overhead | 4184448 | 3818103 | -8.8
BG0043 | PRJ002 | CL001 | 2026-02 | ROW Charges | 3928130 | 3477850 | -11.5
BG0044 | PRJ002 | CL001 | 2026-02 | Labor | 1106308 | 922203 | -16.6
BG0045 | PRJ002 | CL001 | 2026-02 | CapEx Hardware | 2245058 | 2312668 | 3
BG0046 | PRJ002 | CL001 | 2026-01 | CapEx Hardware | 2514912 | 2198018 | -12.6
BG0047 | PRJ002 | CL001 | 2026-01 | PMO Overhead | 1368029 | 1436086 | 5
BG0048 | PRJ002 | CL001 | 2026-01 | ROW Charges | 3858861 | 3911975 | 1.4
BG0049 | PRJ002 | CL001 | 2026-01 | Logistics | 2563125 | 2389699 | -6.8
BG0050 | PRJ002 | CL001 | 2026-01 | Last Mile | 2404235 | 2294989 | -4.5
BG0051 | PRJ003 | CL001 | 2026-06 | Last Mile | 2326628 | 2175150 | -6.5
BG0052 | PRJ003 | CL001 | 2026-06 | CapEx Hardware | 1429500 | 1248937 | -12.6
BG0053 | PRJ003 | CL001 | 2026-06 | ROW Charges | 4396553 | 3651816 | -16.9
BG0054 | PRJ003 | CL001 | 2026-05 | PMO Overhead | 2545906 | 2787146 | 9.5
BG0055 | PRJ003 | CL001 | 2026-05 | ROW Charges | 2141905 | 1930664 | -9.9
BG0056 | PRJ003 | CL001 | 2026-05 | Last Mile | 1126682 | 1117061 | -0.9
BG0057 | PRJ003 | CL001 | 2026-05 | Logistics | 1300803 | 1262575 | -2.9
BG0058 | PRJ003 | CL001 | 2026-05 | CapEx Hardware | 1020923 | 892085 | -12.6
BG0059 | PRJ003 | CL001 | 2026-04 | CapEx Hardware | 4044409 | 4341486 | 7.3
BG0060 | PRJ003 | CL001 | 2026-04 | ROW Charges | 2172799 | 1838004 | -15.4
BG0061 | PRJ003 | CL001 | 2026-04 | PMO Overhead | 2715732 | 2233392 | -17.8
BG0062 | PRJ003 | CL001 | 2026-04 | Last Mile | 1641675 | 1489784 | -9.3
BG0063 | PRJ003 | CL001 | 2026-04 | Labor | 4090461 | 3727116 | -8.9
BG0064 | PRJ003 | CL001 | 2026-03 | Last Mile | 4040574 | 4253778 | 5.3
BG0065 | PRJ003 | CL001 | 2026-03 | ROW Charges | 3872173 | 4221183 | 9
BG0066 | PRJ003 | CL001 | 2026-03 | Labor | 3989693 | 4224255 | 5.9
BG0067 | PRJ003 | CL001 | 2026-03 | Logistics | 1431521 | 1176586 | -17.8
BG0068 | PRJ003 | CL001 | 2026-03 | PMO Overhead | 2519816 | 2084323 | -17.3
BG0069 | PRJ003 | CL001 | 2026-02 | Labor | 4360989 | 4541642 | 4.1
BG0070 | PRJ003 | CL001 | 2026-02 | CapEx Hardware | 2089793 | 1778799 | -14.9
BG0071 | PRJ003 | CL001 | 2026-02 | PMO Overhead | 3022203 | 3369559 | 11.5
BG0072 | PRJ003 | CL001 | 2026-02 | Logistics | 2560835 | 2477886 | -3.2
BG0073 | PRJ003 | CL001 | 2026-02 | Last Mile | 1051218 | 1168710 | 11.2
BG0074 | PRJ003 | CL001 | 2026-01 | PMO Overhead | 984131 | 1078983 | 9.6
BG0075 | PRJ003 | CL001 | 2026-01 | Labor | 4346301 | 4241675 | -2.4
BG0076 | PRJ003 | CL001 | 2026-01 | CapEx Hardware | 3739564 | 4071163 | 8.9
BG0077 | PRJ004 | CL001 | 2026-06 | PMO Overhead | 3676202 | 3709631 | 0.9
BG0078 | PRJ004 | CL001 | 2026-06 | Last Mile | 2062973 | 1952111 | -5.4
BG0079 | PRJ004 | CL001 | 2026-06 | Logistics | 1223540 | 1246475 | 1.9
BG0080 | PRJ004 | CL001 | 2026-06 | Labor | 1932366 | 1945582 | 0.7
BG0081 | PRJ004 | CL001 | 2026-05 | Last Mile | 1985758 | 1696241 | -14.6
BG0082 | PRJ004 | CL001 | 2026-05 | ROW Charges | 1245702 | 1207486 | -3.1
BG0083 | PRJ004 | CL001 | 2026-05 | CapEx Hardware | 3354338 | 2951565 | -12
BG0084 | PRJ004 | CL001 | 2026-05 | Labor | 1903076 | 2035243 | 6.9
BG0085 | PRJ004 | CL001 | 2026-05 | Logistics | 1645878 | 1526348 | -7.3
BG0086 | PRJ004 | CL001 | 2026-04 | Labor | 2881862 | 3150183 | 9.3
BG0087 | PRJ004 | CL001 | 2026-04 | Last Mile | 3686536 | 4054958 | 10
BG0088 | PRJ004 | CL001 | 2026-04 | CapEx Hardware | 2186652 | 1946889 | -11
BG0089 | PRJ004 | CL001 | 2026-04 | PMO Overhead | 853474 | 871815 | 2.1
BG0090 | PRJ004 | CL001 | 2026-03 | Logistics | 1177834 | 1241269 | 5.4
BG0091 | PRJ004 | CL001 | 2026-03 | ROW Charges | 1114775 | 1156098 | 3.7
BG0092 | PRJ004 | CL001 | 2026-03 | Last Mile | 1224843 | 1336835 | 9.1
BG0093 | PRJ004 | CL001 | 2026-02 | Last Mile | 1010051 | 858485 | -15
BG0094 | PRJ004 | CL001 | 2026-02 | ROW Charges | 1532752 | 1658808 | 8.2
BG0095 | PRJ004 | CL001 | 2026-02 | Labor | 4374590 | 3968497 | -9.3
BG0096 | PRJ004 | CL001 | 2026-02 | PMO Overhead | 4162137 | 4257990 | 2.3
BG0097 | PRJ004 | CL001 | 2026-02 | Logistics | 2586753 | 2694263 | 4.2
BG0098 | PRJ004 | CL001 | 2026-01 | CapEx Hardware | 3582312 | 3633036 | 1.4
BG0099 | PRJ004 | CL001 | 2026-01 | PMO Overhead | 2178503 | 2020034 | -7.3
BG0100 | PRJ004 | CL001 | 2026-01 | Last Mile | 2635907 | 2916701 | 10.7
BG0101 | PRJ005 | CL001 | 2026-06 | Logistics | 3726042 | 3658176 | -1.8
BG0102 | PRJ005 | CL001 | 2026-06 | Labor | 3278124 | 3275748 | -0.1
BG0103 | PRJ005 | CL001 | 2026-06 | ROW Charges | 3446805 | 3600785 | 4.5
BG0104 | PRJ005 | CL001 | 2026-06 | CapEx Hardware | 4479636 | 4431235 | -1.1
BG0105 | PRJ005 | CL001 | 2026-05 | PMO Overhead | 3063532 | 2720840 | -11.2
BG0106 | PRJ005 | CL001 | 2026-05 | Logistics | 1175616 | 1119842 | -4.7
BG0107 | PRJ005 | CL001 | 2026-05 | Labor | 2334206 | 2202699 | -5.6
BG0108 | PRJ005 | CL001 | 2026-05 | Last Mile | 1453126 | 1323902 | -8.9
BG0109 | PRJ005 | CL001 | 2026-05 | ROW Charges | 800387 | 781973 | -2.3
BG0110 | PRJ005 | CL001 | 2026-04 | Labor | 3044367 | 2503977 | -17.8
BG0111 | PRJ005 | CL001 | 2026-04 | PMO Overhead | 2863310 | 3161344 | 10.4
BG0112 | PRJ005 | CL001 | 2026-04 | ROW Charges | 2800964 | 2548549 | -9
BG0113 | PRJ005 | CL001 | 2026-03 | Labor | 3099368 | 2888899 | -6.8
BG0114 | PRJ005 | CL001 | 2026-03 | Logistics | 2526945 | 2740847 | 8.5
BG0115 | PRJ005 | CL001 | 2026-03 | Last Mile | 2633356 | 2471208 | -6.2
BG0116 | PRJ005 | CL001 | 2026-03 | CapEx Hardware | 1484801 | 1535999 | 3.4
BG0117 | PRJ005 | CL001 | 2026-02 | ROW Charges | 2571000 | 2590531 | 0.8
BG0118 | PRJ005 | CL001 | 2026-02 | PMO Overhead | 2966819 | 3113265 | 4.9
BG0119 | PRJ005 | CL001 | 2026-02 | Last Mile | 3372015 | 3581998 | 6.2
BG0120 | PRJ005 | CL001 | 2026-02 | Logistics | 3671589 | 3310156 | -9.8
BG0121 | PRJ005 | CL001 | 2026-02 | CapEx Hardware | 3519825 | 3670748 | 4.3
BG0122 | PRJ005 | CL001 | 2026-01 | ROW Charges | 1373042 | 1245182 | -9.3
BG0123 | PRJ005 | CL001 | 2026-01 | Last Mile | 3471321 | 3320675 | -4.3
BG0124 | PRJ005 | CL001 | 2026-01 | CapEx Hardware | 2699043 | 2433565 | -9.8
BG0125 | PRJ005 | CL001 | 2026-01 | PMO Overhead | 3412018 | 3301464 | -3.2
BG0126 | PRJ006 | CL002 | 2026-06 | Labor | 1460586 | 1317581 | -9.8
BG0127 | PRJ006 | CL002 | 2026-06 | ROW Charges | 863991 | 956860 | 10.7
BG0128 | PRJ006 | CL002 | 2026-06 | CapEx Hardware | 3147240 | 3066098 | -2.6
BG0129 | PRJ006 | CL002 | 2026-06 | Last Mile | 1666448 | 1637716 | -1.7
BG0130 | PRJ006 | CL002 | 2026-06 | Logistics | 3104206 | 2842041 | -8.4
BG0131 | PRJ006 | CL002 | 2026-05 | PMO Overhead | 1518379 | 1277522 | -15.9
BG0132 | PRJ006 | CL002 | 2026-05 | Labor | 3372210 | 3667861 | 8.8
BG0133 | PRJ006 | CL002 | 2026-05 | Last Mile | 3067344 | 2923468 | -4.7
BG0134 | PRJ006 | CL002 | 2026-04 | CapEx Hardware | 1244289 | 1163509 | -6.5
BG0135 | PRJ006 | CL002 | 2026-04 | ROW Charges | 1161211 | 1100758 | -5.2
BG0136 | PRJ006 | CL002 | 2026-04 | PMO Overhead | 1550709 | 1599406 | 3.1
BG0137 | PRJ006 | CL002 | 2026-03 | PMO Overhead | 4228600 | 3718817 | -12.1
BG0138 | PRJ006 | CL002 | 2026-03 | ROW Charges | 3980970 | 4065609 | 2.1
BG0139 | PRJ006 | CL002 | 2026-03 | Labor | 3037597 | 2562406 | -15.6
BG0140 | PRJ006 | CL002 | 2026-03 | Last Mile | 3969815 | 4165639 | 4.9
BG0141 | PRJ006 | CL002 | 2026-03 | Logistics | 3181480 | 2734604 | -14
BG0142 | PRJ006 | CL002 | 2026-02 | ROW Charges | 2773612 | 2467150 | -11
BG0143 | PRJ006 | CL002 | 2026-02 | CapEx Hardware | 1738661 | 1500667 | -13.7
BG0144 | PRJ006 | CL002 | 2026-02 | PMO Overhead | 3387642 | 3040123 | -10.3
BG0145 | PRJ006 | CL002 | 2026-02 | Last Mile | 2324417 | 2179427 | -6.2
BG0146 | PRJ006 | CL002 | 2026-02 | Labor | 3734396 | 4089833 | 9.5
BG0147 | PRJ006 | CL002 | 2026-01 | Labor | 1074161 | 1033987 | -3.7
BG0148 | PRJ006 | CL002 | 2026-01 | ROW Charges | 2274049 | 2191263 | -3.6
BG0149 | PRJ006 | CL002 | 2026-01 | Logistics | 4347400 | 3787630 | -12.9
BG0150 | PRJ006 | CL002 | 2026-01 | CapEx Hardware | 4020980 | 3717736 | -7.5
BG0151 | PRJ007 | CL002 | 2026-06 | Labor | 3468613 | 3793384 | 9.4
BG0152 | PRJ007 | CL002 | 2026-06 | PMO Overhead | 2293106 | 1913859 | -16.5
BG0153 | PRJ007 | CL002 | 2026-06 | ROW Charges | 2023327 | 1980601 | -2.1
BG0154 | PRJ007 | CL002 | 2026-05 | Logistics | 4007339 | 3399636 | -15.2
BG0155 | PRJ007 | CL002 | 2026-05 | Last Mile | 3956752 | 3442931 | -13
BG0156 | PRJ007 | CL002 | 2026-05 | PMO Overhead | 2153111 | 2329091 | 8.2
BG0157 | PRJ007 | CL002 | 2026-04 | Labor | 4253232 | 3671029 | -13.7
BG0158 | PRJ007 | CL002 | 2026-04 | PMO Overhead | 1374407 | 1340666 | -2.5
BG0159 | PRJ007 | CL002 | 2026-04 | Logistics | 2364534 | 2491373 | 5.4
BG0160 | PRJ007 | CL002 | 2026-04 | CapEx Hardware | 2528030 | 2331081 | -7.8
BG0161 | PRJ007 | CL002 | 2026-04 | Last Mile | 1483793 | 1262300 | -14.9
BG0162 | PRJ007 | CL002 | 2026-03 | Logistics | 4134919 | 4503410 | 8.9
BG0163 | PRJ007 | CL002 | 2026-03 | Last Mile | 3372905 | 3463622 | 2.7
BG0164 | PRJ007 | CL002 | 2026-03 | PMO Overhead | 3004747 | 3226560 | 7.4
BG0165 | PRJ007 | CL002 | 2026-02 | Logistics | 1288911 | 1373532 | 6.6
BG0166 | PRJ007 | CL002 | 2026-02 | CapEx Hardware | 872894 | 841343 | -3.6
BG0167 | PRJ007 | CL002 | 2026-02 | ROW Charges | 2106833 | 2164381 | 2.7
BG0168 | PRJ007 | CL002 | 2026-02 | Last Mile | 1383066 | 1473119 | 6.5
BG0169 | PRJ007 | CL002 | 2026-02 | PMO Overhead | 3306720 | 3230454 | -2.3
BG0170 | PRJ007 | CL002 | 2026-01 | Last Mile | 4216571 | 3607609 | -14.4
BG0171 | PRJ007 | CL002 | 2026-01 | Labor | 1339867 | 1443096 | 7.7
BG0172 | PRJ007 | CL002 | 2026-01 | CapEx Hardware | 1397098 | 1434001 | 2.6
BG0173 | PRJ007 | CL002 | 2026-01 | Logistics | 2089447 | 1791916 | -14.2
BG0174 | PRJ008 | CL002 | 2026-06 | CapEx Hardware | 2568976 | 2144055 | -16.5
BG0175 | PRJ008 | CL002 | 2026-06 | Last Mile | 2079950 | 2260317 | 8.7
BG0176 | PRJ008 | CL002 | 2026-06 | Logistics | 1704214 | 1491056 | -12.5
BG0177 | PRJ008 | CL002 | 2026-06 | Labor | 3902360 | 3772169 | -3.3
BG0178 | PRJ008 | CL002 | 2026-05 | Logistics | 4450833 | 3709345 | -16.7
BG0179 | PRJ008 | CL002 | 2026-05 | Labor | 2818200 | 2795422 | -0.8
BG0180 | PRJ008 | CL002 | 2026-05 | CapEx Hardware | 3172986 | 3032461 | -4.4
BG0181 | PRJ008 | CL002 | 2026-04 | ROW Charges | 2917133 | 2949040 | 1.1
BG0182 | PRJ008 | CL002 | 2026-04 | PMO Overhead | 3994712 | 3814865 | -4.5
BG0183 | PRJ008 | CL002 | 2026-04 | Last Mile | 2683555 | 2320455 | -13.5
BG0184 | PRJ008 | CL002 | 2026-04 | CapEx Hardware | 3852883 | 3535270 | -8.2
BG0185 | PRJ008 | CL002 | 2026-03 | PMO Overhead | 2458415 | 2265919 | -7.8
BG0186 | PRJ008 | CL002 | 2026-03 | Logistics | 992181 | 1098764 | 10.7
BG0187 | PRJ008 | CL002 | 2026-03 | ROW Charges | 2658480 | 2766876 | 4.1
BG0188 | PRJ008 | CL002 | 2026-03 | Last Mile | 3509170 | 2970719 | -15.3
BG0189 | PRJ008 | CL002 | 2026-03 | CapEx Hardware | 1494638 | 1542709 | 3.2
BG0190 | PRJ008 | CL002 | 2026-02 | PMO Overhead | 1607096 | 1778332 | 10.7
BG0191 | PRJ008 | CL002 | 2026-02 | Labor | 3072617 | 3051282 | -0.7
BG0192 | PRJ008 | CL002 | 2026-02 | CapEx Hardware | 1021771 | 1131292 | 10.7
BG0193 | PRJ008 | CL002 | 2026-02 | Logistics | 2988394 | 2620279 | -12.3
BG0194 | PRJ008 | CL002 | 2026-02 | ROW Charges | 2795799 | 2714138 | -2.9
BG0195 | PRJ008 | CL002 | 2026-01 | CapEx Hardware | 879580 | 793811 | -9.8
BG0196 | PRJ008 | CL002 | 2026-01 | Logistics | 1663208 | 1486219 | -10.6
BG0197 | PRJ008 | CL002 | 2026-01 | Last Mile | 3759575 | 4029043 | 7.2
BG0198 | PRJ009 | CL002 | 2026-06 | PMO Overhead | 3826919 | 3364860 | -12.1
BG0199 | PRJ009 | CL002 | 2026-06 | ROW Charges | 2578455 | 2250812 | -12.7
BG0200 | PRJ009 | CL002 | 2026-06 | Labor | 1844253 | 1679985 | -8.9
BG0201 | PRJ009 | CL002 | 2026-06 | CapEx Hardware | 3217688 | 3071223 | -4.6
BG0202 | PRJ009 | CL002 | 2026-05 | Last Mile | 2470358 | 2305622 | -6.7
BG0203 | PRJ009 | CL002 | 2026-05 | Labor | 2774315 | 2642293 | -4.8
BG0204 | PRJ009 | CL002 | 2026-05 | ROW Charges | 2919350 | 2927577 | 0.3
BG0205 | PRJ009 | CL002 | 2026-05 | CapEx Hardware | 2617939 | 2743854 | 4.8
BG0206 | PRJ009 | CL002 | 2026-05 | PMO Overhead | 4237667 | 4687398 | 10.6
BG0207 | PRJ009 | CL002 | 2026-04 | CapEx Hardware | 3982882 | 4349056 | 9.2
BG0208 | PRJ009 | CL002 | 2026-04 | ROW Charges | 2059262 | 2056286 | -0.1
BG0209 | PRJ009 | CL002 | 2026-04 | Logistics | 1440884 | 1420503 | -1.4
BG0210 | PRJ009 | CL002 | 2026-04 | PMO Overhead | 1536936 | 1378919 | -10.3
BG0211 | PRJ009 | CL002 | 2026-03 | Labor | 3157794 | 3163502 | 0.2
BG0212 | PRJ009 | CL002 | 2026-03 | ROW Charges | 1101736 | 1013564 | -8
BG0213 | PRJ009 | CL002 | 2026-03 | PMO Overhead | 3798354 | 3649373 | -3.9
BG0214 | PRJ009 | CL002 | 2026-03 | Last Mile | 1448961 | 1586379 | 9.5
BG0215 | PRJ009 | CL002 | 2026-02 | CapEx Hardware | 2861306 | 2693537 | -5.9
BG0216 | PRJ009 | CL002 | 2026-02 | Logistics | 2544076 | 2803789 | 10.2
BG0217 | PRJ009 | CL002 | 2026-02 | Labor | 3912987 | 3646682 | -6.8
BG0218 | PRJ009 | CL002 | 2026-01 | Labor | 962851 | 1076218 | 11.8
BG0219 | PRJ009 | CL002 | 2026-01 | Logistics | 1322096 | 1236751 | -6.5
BG0220 | PRJ009 | CL002 | 2026-01 | CapEx Hardware | 3172334 | 2755834 | -13.1
BG0221 | PRJ009 | CL002 | 2026-01 | Last Mile | 4000047 | 3803602 | -4.9
BG0222 | PRJ010 | CL002 | 2026-06 | PMO Overhead | 1929299 | 1792459 | -7.1
BG0223 | PRJ010 | CL002 | 2026-06 | CapEx Hardware | 2272303 | 2348369 | 3.3
BG0224 | PRJ010 | CL002 | 2026-06 | Labor | 1835861 | 1681561 | -8.4
BG0225 | PRJ010 | CL002 | 2026-06 | Logistics | 999465 | 874057 | -12.5
BG0226 | PRJ010 | CL002 | 2026-05 | CapEx Hardware | 1996706 | 1920067 | -3.8
BG0227 | PRJ010 | CL002 | 2026-05 | Labor | 3343936 | 2843109 | -15
BG0228 | PRJ010 | CL002 | 2026-05 | Last Mile | 1575275 | 1410940 | -10.4
BG0229 | PRJ010 | CL002 | 2026-04 | Labor | 1206374 | 1231326 | 2.1
BG0230 | PRJ010 | CL002 | 2026-04 | PMO Overhead | 3664548 | 3611523 | -1.4
BG0231 | PRJ010 | CL002 | 2026-04 | Logistics | 4415382 | 3793221 | -14.1
BG0232 | PRJ010 | CL002 | 2026-04 | CapEx Hardware | 2312334 | 2410348 | 4.2
BG0233 | PRJ010 | CL002 | 2026-03 | PMO Overhead | 3527339 | 3184425 | -9.7
BG0234 | PRJ010 | CL002 | 2026-03 | Logistics | 3250845 | 3040238 | -6.5
BG0235 | PRJ010 | CL002 | 2026-03 | Labor | 1246129 | 1070606 | -14.1
BG0236 | PRJ010 | CL002 | 2026-03 | CapEx Hardware | 3914637 | 3916792 | 0.1
BG0237 | PRJ010 | CL002 | 2026-02 | Logistics | 3755558 | 3581791 | -4.6
BG0238 | PRJ010 | CL002 | 2026-02 | Last Mile | 1213715 | 1022511 | -15.8
BG0239 | PRJ010 | CL002 | 2026-02 | PMO Overhead | 3092518 | 3110154 | 0.6
BG0240 | PRJ010 | CL002 | 2026-01 | PMO Overhead | 3823126 | 3311215 | -13.4
BG0241 | PRJ010 | CL002 | 2026-01 | ROW Charges | 1336166 | 1172501 | -12.2
BG0242 | PRJ010 | CL002 | 2026-01 | Last Mile | 3108946 | 3213036 | 3.3
BG0243 | PRJ010 | CL002 | 2026-01 | Labor | 4478720 | 4692832 | 4.8
BG0244 | PRJ011 | CL002 | 2026-06 | ROW Charges | 1848966 | 1612090 | -12.8
BG0245 | PRJ011 | CL002 | 2026-06 | Logistics | 3681727 | 3953477 | 7.4
BG0246 | PRJ011 | CL002 | 2026-06 | PMO Overhead | 3808977 | 3444552 | -9.6
BG0247 | PRJ011 | CL002 | 2026-06 | CapEx Hardware | 2447631 | 2082611 | -14.9
BG0248 | PRJ011 | CL002 | 2026-05 | Labor | 2618111 | 2840276 | 8.5
BG0249 | PRJ011 | CL002 | 2026-05 | Last Mile | 2577283 | 2574445 | -0.1
BG0250 | PRJ011 | CL002 | 2026-05 | Logistics | 1939483 | 2065098 | 6.5
BG0251 | PRJ011 | CL002 | 2026-05 | PMO Overhead | 3412677 | 2908514 | -14.8
BG0252 | PRJ011 | CL002 | 2026-05 | ROW Charges | 2406610 | 2283376 | -5.1
BG0253 | PRJ011 | CL002 | 2026-04 | Labor | 941599 | 1042754 | 10.7
BG0254 | PRJ011 | CL002 | 2026-04 | PMO Overhead | 1861425 | 1854092 | -0.4
BG0255 | PRJ011 | CL002 | 2026-04 | CapEx Hardware | 2030917 | 2033282 | 0.1
BG0256 | PRJ011 | CL002 | 2026-04 | Last Mile | 4479461 | 4540065 | 1.4
BG0257 | PRJ011 | CL002 | 2026-04 | ROW Charges | 3025070 | 2800234 | -7.4
BG0258 | PRJ011 | CL002 | 2026-03 | CapEx Hardware | 2600978 | 2749933 | 5.7
BG0259 | PRJ011 | CL002 | 2026-03 | Last Mile | 2300489 | 2055706 | -10.6
BG0260 | PRJ011 | CL002 | 2026-03 | Labor | 1702547 | 1731637 | 1.7
BG0261 | PRJ011 | CL002 | 2026-02 | Last Mile | 2136259 | 2192843 | 2.6
BG0262 | PRJ011 | CL002 | 2026-02 | Labor | 3806488 | 3496871 | -8.1
BG0263 | PRJ011 | CL002 | 2026-02 | CapEx Hardware | 2751931 | 2725074 | -1
BG0264 | PRJ011 | CL002 | 2026-02 | ROW Charges | 2148725 | 2341300 | 9
BG0265 | PRJ011 | CL002 | 2026-01 | CapEx Hardware | 3011498 | 2665895 | -11.5
BG0266 | PRJ011 | CL002 | 2026-01 | ROW Charges | 3152831 | 2848313 | -9.7
BG0267 | PRJ011 | CL002 | 2026-01 | Labor | 3349735 | 3697709 | 10.4
BG0268 | PRJ011 | CL002 | 2026-01 | Logistics | 4186592 | 4513036 | 7.8
BG0269 | PRJ011 | CL002 | 2026-01 | PMO Overhead | 1113835 | 1105129 | -0.8
BG0270 | PRJ012 | CL003 | 2026-06 | Logistics | 2803168 | 2553757 | -8.9
BG0271 | PRJ012 | CL003 | 2026-06 | Last Mile | 4364460 | 4726426 | 8.3
BG0272 | PRJ012 | CL003 | 2026-06 | Labor | 1755274 | 1450616 | -17.4
BG0273 | PRJ012 | CL003 | 2026-06 | PMO Overhead | 1032182 | 854549 | -17.2
BG0274 | PRJ012 | CL003 | 2026-05 | Logistics | 3660268 | 3752062 | 2.5
BG0275 | PRJ012 | CL003 | 2026-05 | PMO Overhead | 875895 | 863412 | -1.4
BG0276 | PRJ012 | CL003 | 2026-05 | ROW Charges | 1018692 | 953635 | -6.4
BG0277 | PRJ012 | CL003 | 2026-04 | PMO Overhead | 2590269 | 2551061 | -1.5
BG0278 | PRJ012 | CL003 | 2026-04 | Last Mile | 1284791 | 1222331 | -4.9
BG0279 | PRJ012 | CL003 | 2026-04 | ROW Charges | 3382236 | 3770382 | 11.5
BG0280 | PRJ012 | CL003 | 2026-04 | Labor | 2342281 | 2167867 | -7.4
BG0281 | PRJ012 | CL003 | 2026-03 | ROW Charges | 1185837 | 1181787 | -0.3
BG0282 | PRJ012 | CL003 | 2026-03 | CapEx Hardware | 1752635 | 1654346 | -5.6
BG0283 | PRJ012 | CL003 | 2026-03 | Last Mile | 3956503 | 4298742 | 8.7
BG0284 | PRJ012 | CL003 | 2026-03 | Logistics | 4126841 | 4047875 | -1.9
BG0285 | PRJ012 | CL003 | 2026-02 | CapEx Hardware | 1121332 | 938550 | -16.3
BG0286 | PRJ012 | CL003 | 2026-02 | Last Mile | 2639436 | 2307336 | -12.6
BG0287 | PRJ012 | CL003 | 2026-02 | PMO Overhead | 983372 | 899035 | -8.6
BG0288 | PRJ012 | CL003 | 2026-01 | PMO Overhead | 2807819 | 2856323 | 1.7
BG0289 | PRJ012 | CL003 | 2026-01 | Last Mile | 3553939 | 2996116 | -15.7
BG0290 | PRJ012 | CL003 | 2026-01 | Labor | 1849410 | 2037145 | 10.2
BG0291 | PRJ012 | CL003 | 2026-01 | CapEx Hardware | 1663443 | 1611009 | -3.2
BG0292 | PRJ012 | CL003 | 2026-01 | Logistics | 3883730 | 4132395 | 6.4
BG0293 | PRJ013 | CL003 | 2026-06 | CapEx Hardware | 1729852 | 1878059 | 8.6
BG0294 | PRJ013 | CL003 | 2026-06 | Labor | 1547257 | 1625166 | 5
BG0295 | PRJ013 | CL003 | 2026-06 | ROW Charges | 2348254 | 2180786 | -7.1
BG0296 | PRJ013 | CL003 | 2026-06 | Logistics | 2903258 | 3097693 | 6.7
BG0297 | PRJ013 | CL003 | 2026-06 | PMO Overhead | 3360901 | 3360064 | 0
BG0298 | PRJ013 | CL003 | 2026-05 | CapEx Hardware | 1588405 | 1323577 | -16.7
BG0299 | PRJ013 | CL003 | 2026-05 | Last Mile | 2066419 | 1964379 | -4.9
BG0300 | PRJ013 | CL003 | 2026-05 | Logistics | 2224329 | 2080236 | -6.5
BG0301 | PRJ013 | CL003 | 2026-05 | ROW Charges | 1554453 | 1473175 | -5.2
BG0302 | PRJ013 | CL003 | 2026-04 | Labor | 1894795 | 2098587 | 10.8
BG0303 | PRJ013 | CL003 | 2026-04 | ROW Charges | 2568892 | 2244840 | -12.6
BG0304 | PRJ013 | CL003 | 2026-04 | Logistics | 2470239 | 2531258 | 2.5
BG0305 | PRJ013 | CL003 | 2026-04 | CapEx Hardware | 4299024 | 3662463 | -14.8
BG0306 | PRJ013 | CL003 | 2026-03 | Labor | 4170334 | 4429206 | 6.2
BG0307 | PRJ013 | CL003 | 2026-03 | CapEx Hardware | 1474795 | 1350481 | -8.4
BG0308 | PRJ013 | CL003 | 2026-03 | ROW Charges | 3210391 | 3120792 | -2.8
BG0309 | PRJ013 | CL003 | 2026-02 | ROW Charges | 2571913 | 2704129 | 5.1
BG0310 | PRJ013 | CL003 | 2026-02 | CapEx Hardware | 2070683 | 1961960 | -5.3
BG0311 | PRJ013 | CL003 | 2026-02 | PMO Overhead | 3912446 | 3952490 | 1
BG0312 | PRJ013 | CL003 | 2026-02 | Labor | 3331833 | 3538864 | 6.2
BG0313 | PRJ013 | CL003 | 2026-02 | Last Mile | 2688569 | 2609574 | -2.9
BG0314 | PRJ013 | CL003 | 2026-01 | PMO Overhead | 4094603 | 3577257 | -12.6
BG0315 | PRJ013 | CL003 | 2026-01 | Labor | 2578658 | 2525830 | -2
BG0316 | PRJ013 | CL003 | 2026-01 | Logistics | 2408397 | 2603704 | 8.1
BG0317 | PRJ013 | CL003 | 2026-01 | CapEx Hardware | 1135582 | 982410 | -13.5
BG0318 | PRJ014 | CL003 | 2026-06 | Logistics | 4239440 | 4673452 | 10.2
BG0319 | PRJ014 | CL003 | 2026-06 | Last Mile | 2942889 | 2585220 | -12.2
BG0320 | PRJ014 | CL003 | 2026-06 | ROW Charges | 4323269 | 4427772 | 2.4
BG0321 | PRJ014 | CL003 | 2026-05 | Last Mile | 3160902 | 3407382 | 7.8
BG0322 | PRJ014 | CL003 | 2026-05 | Labor | 3002199 | 2504129 | -16.6
BG0323 | PRJ014 | CL003 | 2026-05 | PMO Overhead | 3036219 | 2820030 | -7.1
BG0324 | PRJ014 | CL003 | 2026-04 | PMO Overhead | 2370649 | 2056834 | -13.2
BG0325 | PRJ014 | CL003 | 2026-04 | Logistics | 3653791 | 3177667 | -13
BG0326 | PRJ014 | CL003 | 2026-04 | Last Mile | 3460499 | 3729318 | 7.8
BG0327 | PRJ014 | CL003 | 2026-03 | PMO Overhead | 4399950 | 3874854 | -11.9
BG0328 | PRJ014 | CL003 | 2026-03 | Last Mile | 1005152 | 1113423 | 10.8
BG0329 | PRJ014 | CL003 | 2026-03 | ROW Charges | 2481382 | 2255449 | -9.1
BG0330 | PRJ014 | CL003 | 2026-02 | ROW Charges | 3826390 | 4214550 | 10.1
BG0331 | PRJ014 | CL003 | 2026-02 | PMO Overhead | 801483 | 675218 | -15.8
BG0332 | PRJ014 | CL003 | 2026-02 | Logistics | 3770997 | 3720945 | -1.3
BG0333 | PRJ014 | CL003 | 2026-02 | Last Mile | 2106967 | 1859664 | -11.7
BG0334 | PRJ014 | CL003 | 2026-02 | CapEx Hardware | 3876356 | 3891610 | 0.4
BG0335 | PRJ014 | CL003 | 2026-01 | CapEx Hardware | 1403105 | 1352985 | -3.6
BG0336 | PRJ014 | CL003 | 2026-01 | ROW Charges | 1472149 | 1544840 | 4.9
BG0337 | PRJ014 | CL003 | 2026-01 | Last Mile | 4184754 | 4657365 | 11.3
BG0338 | PRJ015 | CL003 | 2026-06 | PMO Overhead | 4449713 | 4862083 | 9.3
BG0339 | PRJ015 | CL003 | 2026-06 | CapEx Hardware | 1095206 | 949404 | -13.3
BG0340 | PRJ015 | CL003 | 2026-06 | Labor | 3426164 | 3801991 | 11
BG0341 | PRJ015 | CL003 | 2026-05 | PMO Overhead | 1311614 | 1097624 | -16.3
BG0342 | PRJ015 | CL003 | 2026-05 | Labor | 1381812 | 1215796 | -12
BG0343 | PRJ015 | CL003 | 2026-05 | CapEx Hardware | 3929219 | 4314159 | 9.8
BG0344 | PRJ015 | CL003 | 2026-05 | Logistics | 1578357 | 1337675 | -15.2
BG0345 | PRJ015 | CL003 | 2026-04 | CapEx Hardware | 1681722 | 1404237 | -16.5
BG0346 | PRJ015 | CL003 | 2026-04 | ROW Charges | 1133077 | 1060639 | -6.4
BG0347 | PRJ015 | CL003 | 2026-04 | Last Mile | 3423334 | 3350759 | -2.1
BG0348 | PRJ015 | CL003 | 2026-03 | Last Mile | 2008225 | 2087488 | 3.9
BG0349 | PRJ015 | CL003 | 2026-03 | ROW Charges | 3282239 | 3543185 | 8
BG0350 | PRJ015 | CL003 | 2026-03 | PMO Overhead | 1056969 | 1007032 | -4.7
BG0351 | PRJ015 | CL003 | 2026-03 | Logistics | 2928963 | 2407297 | -17.8
BG0352 | PRJ015 | CL003 | 2026-02 | Last Mile | 4483339 | 4405326 | -1.7
BG0353 | PRJ015 | CL003 | 2026-02 | Labor | 1594172 | 1641981 | 3
BG0354 | PRJ015 | CL003 | 2026-02 | PMO Overhead | 3748042 | 3929821 | 4.8
BG0355 | PRJ015 | CL003 | 2026-01 | Last Mile | 1481253 | 1390008 | -6.2
BG0356 | PRJ015 | CL003 | 2026-01 | Labor | 4306607 | 4296669 | -0.2
BG0357 | PRJ015 | CL003 | 2026-01 | PMO Overhead | 3323100 | 3135958 | -5.6
BG0358 | PRJ016 | CL004 | 2026-06 | PMO Overhead | 2939917 | 3105805 | 5.6
BG0359 | PRJ016 | CL004 | 2026-06 | ROW Charges | 1272918 | 1244110 | -2.3
BG0360 | PRJ016 | CL004 | 2026-06 | CapEx Hardware | 1915213 | 1906923 | -0.4
BG0361 | PRJ016 | CL004 | 2026-06 | Last Mile | 837151 | 762647 | -8.9
BG0362 | PRJ016 | CL004 | 2026-06 | Logistics | 4203517 | 3619726 | -13.9
BG0363 | PRJ016 | CL004 | 2026-05 | ROW Charges | 3585170 | 3450467 | -3.8
BG0364 | PRJ016 | CL004 | 2026-05 | Last Mile | 2807957 | 2482898 | -11.6
BG0365 | PRJ016 | CL004 | 2026-05 | Logistics | 1523173 | 1426234 | -6.4
BG0366 | PRJ016 | CL004 | 2026-04 | PMO Overhead | 4398065 | 4279142 | -2.7
BG0367 | PRJ016 | CL004 | 2026-04 | Logistics | 4412073 | 4624538 | 4.8
BG0368 | PRJ016 | CL004 | 2026-04 | CapEx Hardware | 2803570 | 2730720 | -2.6
BG0369 | PRJ016 | CL004 | 2026-04 | ROW Charges | 1104464 | 1093250 | -1
BG0370 | PRJ016 | CL004 | 2026-04 | Labor | 1836277 | 1851118 | 0.8
BG0371 | PRJ016 | CL004 | 2026-03 | PMO Overhead | 2504529 | 2098549 | -16.2
BG0372 | PRJ016 | CL004 | 2026-03 | Labor | 2611398 | 2174962 | -16.7
BG0373 | PRJ016 | CL004 | 2026-03 | Last Mile | 2144222 | 2260416 | 5.4
BG0374 | PRJ016 | CL004 | 2026-03 | ROW Charges | 916036 | 804079 | -12.2
BG0375 | PRJ016 | CL004 | 2026-02 | Labor | 3939891 | 4303355 | 9.2
BG0376 | PRJ016 | CL004 | 2026-02 | ROW Charges | 2810605 | 2823164 | 0.4
BG0377 | PRJ016 | CL004 | 2026-02 | Logistics | 4115461 | 4003784 | -2.7
BG0378 | PRJ016 | CL004 | 2026-02 | PMO Overhead | 2505118 | 2539719 | 1.4
BG0379 | PRJ016 | CL004 | 2026-02 | CapEx Hardware | 3968503 | 4010582 | 1.1
BG0380 | PRJ016 | CL004 | 2026-01 | Logistics | 2885128 | 3034951 | 5.2
BG0381 | PRJ016 | CL004 | 2026-01 | PMO Overhead | 2615049 | 2614909 | 0
BG0382 | PRJ016 | CL004 | 2026-01 | Labor | 2550352 | 2142041 | -16
BG0383 | PRJ017 | CL004 | 2026-06 | Last Mile | 2163616 | 2408483 | 11.3
BG0384 | PRJ017 | CL004 | 2026-06 | CapEx Hardware | 2388486 | 2431134 | 1.8
BG0385 | PRJ017 | CL004 | 2026-06 | Labor | 3653445 | 3297304 | -9.7
BG0386 | PRJ017 | CL004 | 2026-05 | Last Mile | 1588532 | 1717179 | 8.1
BG0387 | PRJ017 | CL004 | 2026-05 | PMO Overhead | 4399189 | 4856834 | 10.4
BG0388 | PRJ017 | CL004 | 2026-05 | Logistics | 1818244 | 1758194 | -3.3
BG0389 | PRJ017 | CL004 | 2026-05 | ROW Charges | 1948809 | 1853775 | -4.9
BG0390 | PRJ017 | CL004 | 2026-05 | Labor | 1857431 | 1524797 | -17.9
BG0391 | PRJ017 | CL004 | 2026-04 | Last Mile | 2724126 | 2662246 | -2.3
BG0392 | PRJ017 | CL004 | 2026-04 | CapEx Hardware | 1654966 | 1562323 | -5.6
BG0393 | PRJ017 | CL004 | 2026-04 | Logistics | 4496467 | 4074531 | -9.4
BG0394 | PRJ017 | CL004 | 2026-04 | Labor | 1988859 | 1797527 | -9.6
BG0395 | PRJ017 | CL004 | 2026-03 | CapEx Hardware | 2706013 | 2501310 | -7.6
BG0396 | PRJ017 | CL004 | 2026-03 | ROW Charges | 3502180 | 3107465 | -11.3
BG0397 | PRJ017 | CL004 | 2026-03 | PMO Overhead | 1642736 | 1686316 | 2.7
BG0398 | PRJ017 | CL004 | 2026-03 | Labor | 1956015 | 2096535 | 7.2
BG0399 | PRJ017 | CL004 | 2026-02 | Labor | 2637647 | 2878838 | 9.1
BG0400 | PRJ017 | CL004 | 2026-02 | Last Mile | 871914 | 919260 | 5.4
BG0401 | PRJ017 | CL004 | 2026-02 | ROW Charges | 3506250 | 3386233 | -3.4
BG0402 | PRJ017 | CL004 | 2026-02 | CapEx Hardware | 1718019 | 1917219 | 11.6
BG0403 | PRJ017 | CL004 | 2026-01 | Logistics | 2989545 | 2679957 | -10.4
BG0404 | PRJ017 | CL004 | 2026-01 | Last Mile | 1214542 | 1094962 | -9.8
BG0405 | PRJ017 | CL004 | 2026-01 | CapEx Hardware | 3561084 | 3471858 | -2.5
BG0406 | PRJ017 | CL004 | 2026-01 | PMO Overhead | 2101145 | 2193429 | 4.4
BG0407 | PRJ017 | CL004 | 2026-01 | Labor | 885142 | 742537 | -16.1
BG0408 | PRJ018 | CL004 | 2026-06 | CapEx Hardware | 1705578 | 1556937 | -8.7
BG0409 | PRJ018 | CL004 | 2026-06 | ROW Charges | 3838359 | 3410125 | -11.2
BG0410 | PRJ018 | CL004 | 2026-06 | Last Mile | 3344814 | 2963903 | -11.4
BG0411 | PRJ018 | CL004 | 2026-06 | Labor | 3610798 | 3678547 | 1.9
BG0412 | PRJ018 | CL004 | 2026-05 | PMO Overhead | 3153647 | 3302195 | 4.7
BG0413 | PRJ018 | CL004 | 2026-05 | Last Mile | 4306317 | 4588948 | 6.6
BG0414 | PRJ018 | CL004 | 2026-05 | Logistics | 1994124 | 2130530 | 6.8
BG0415 | PRJ018 | CL004 | 2026-05 | Labor | 2245704 | 2488253 | 10.8
BG0416 | PRJ018 | CL004 | 2026-04 | CapEx Hardware | 3103730 | 3294223 | 6.1
BG0417 | PRJ018 | CL004 | 2026-04 | Last Mile | 4088653 | 3533302 | -13.6
BG0418 | PRJ018 | CL004 | 2026-04 | ROW Charges | 3276787 | 3437125 | 4.9
BG0419 | PRJ018 | CL004 | 2026-04 | Logistics | 3083800 | 3154623 | 2.3
BG0420 | PRJ018 | CL004 | 2026-04 | PMO Overhead | 2620938 | 2668837 | 1.8
BG0421 | PRJ018 | CL004 | 2026-03 | Logistics | 2245849 | 2115763 | -5.8
BG0422 | PRJ018 | CL004 | 2026-03 | ROW Charges | 1105362 | 1212624 | 9.7
BG0423 | PRJ018 | CL004 | 2026-03 | PMO Overhead | 1708620 | 1408722 | -17.6
BG0424 | PRJ018 | CL004 | 2026-02 | ROW Charges | 4185778 | 4095998 | -2.1
BG0425 | PRJ018 | CL004 | 2026-02 | CapEx Hardware | 3197074 | 2944683 | -7.9
BG0426 | PRJ018 | CL004 | 2026-02 | Last Mile | 3947497 | 3379277 | -14.4
BG0427 | PRJ018 | CL004 | 2026-02 | Logistics | 4337089 | 3806282 | -12.2
BG0428 | PRJ018 | CL004 | 2026-01 | ROW Charges | 3264620 | 3456857 | 5.9
BG0429 | PRJ018 | CL004 | 2026-01 | Logistics | 2103349 | 2260950 | 7.5
BG0430 | PRJ018 | CL004 | 2026-01 | Last Mile | 1940437 | 1955596 | 0.8
BG0431 | PRJ018 | CL004 | 2026-01 | CapEx Hardware | 970129 | 1044238 | 7.6
BG0432 | PRJ019 | CL004 | 2026-06 | Logistics | 1791762 | 1951250 | 8.9
BG0433 | PRJ019 | CL004 | 2026-06 | CapEx Hardware | 2163578 | 2198186 | 1.6
BG0434 | PRJ019 | CL004 | 2026-06 | Labor | 3746373 | 4155647 | 10.9
BG0435 | PRJ019 | CL004 | 2026-06 | PMO Overhead | 4110780 | 4083161 | -0.7
BG0436 | PRJ019 | CL004 | 2026-06 | ROW Charges | 3065610 | 2700667 | -11.9
BG0437 | PRJ019 | CL004 | 2026-05 | Labor | 3839973 | 3891359 | 1.3
BG0438 | PRJ019 | CL004 | 2026-05 | PMO Overhead | 3891684 | 4059407 | 4.3
BG0439 | PRJ019 | CL004 | 2026-05 | ROW Charges | 2868218 | 2540265 | -11.4
BG0440 | PRJ019 | CL004 | 2026-05 | CapEx Hardware | 4190011 | 3929914 | -6.2
BG0441 | PRJ019 | CL004 | 2026-05 | Last Mile | 1836560 | 2024935 | 10.3
BG0442 | PRJ019 | CL004 | 2026-04 | Labor | 3363612 | 3480151 | 3.5
BG0443 | PRJ019 | CL004 | 2026-04 | PMO Overhead | 1288547 | 1126368 | -12.6
BG0444 | PRJ019 | CL004 | 2026-04 | Logistics | 2674127 | 2677021 | 0.1
BG0445 | PRJ019 | CL004 | 2026-04 | ROW Charges | 4356534 | 4697146 | 7.8
BG0446 | PRJ019 | CL004 | 2026-04 | Last Mile | 2640443 | 2167292 | -17.9
BG0447 | PRJ019 | CL004 | 2026-03 | Last Mile | 2188774 | 1956647 | -10.6
BG0448 | PRJ019 | CL004 | 2026-03 | ROW Charges | 3299368 | 3169218 | -3.9
BG0449 | PRJ019 | CL004 | 2026-03 | CapEx Hardware | 3010398 | 3290964 | 9.3
BG0450 | PRJ019 | CL004 | 2026-03 | Logistics | 3814717 | 3256829 | -14.6
BG0451 | PRJ019 | CL004 | 2026-03 | Labor | 2856582 | 2949065 | 3.2
BG0452 | PRJ019 | CL004 | 2026-02 | Last Mile | 1425956 | 1181295 | -17.2
BG0453 | PRJ019 | CL004 | 2026-02 | Logistics | 3632080 | 3798518 | 4.6
BG0454 | PRJ019 | CL004 | 2026-02 | PMO Overhead | 1213375 | 1044005 | -14
BG0455 | PRJ019 | CL004 | 2026-02 | CapEx Hardware | 2328015 | 2186330 | -6.1
BG0456 | PRJ019 | CL004 | 2026-01 | CapEx Hardware | 986502 | 887450 | -10
BG0457 | PRJ019 | CL004 | 2026-01 | Logistics | 3124525 | 3020427 | -3.3
BG0458 | PRJ019 | CL004 | 2026-01 | Last Mile | 4200879 | 4629024 | 10.2
BG0459 | PRJ019 | CL004 | 2026-01 | PMO Overhead | 2752876 | 2685670 | -2.4
BG0460 | PRJ019 | CL004 | 2026-01 | Labor | 2921962 | 3153050 | 7.9
BG0461 | PRJ020 | CL004 | 2026-06 | Logistics | 4021248 | 3682175 | -8.4
BG0462 | PRJ020 | CL004 | 2026-06 | CapEx Hardware | 1725819 | 1514727 | -12.2
BG0463 | PRJ020 | CL004 | 2026-06 | ROW Charges | 2924087 | 3104150 | 6.2
BG0464 | PRJ020 | CL004 | 2026-06 | Last Mile | 921179 | 872858 | -5.2
BG0465 | PRJ020 | CL004 | 2026-05 | Labor | 4473730 | 4180155 | -6.6
BG0466 | PRJ020 | CL004 | 2026-05 | PMO Overhead | 1348640 | 1451522 | 7.6
BG0467 | PRJ020 | CL004 | 2026-05 | ROW Charges | 1573116 | 1653545 | 5.1
BG0468 | PRJ020 | CL004 | 2026-04 | PMO Overhead | 2463001 | 2487106 | 1
BG0469 | PRJ020 | CL004 | 2026-04 | Labor | 3331893 | 3340129 | 0.2
BG0470 | PRJ020 | CL004 | 2026-04 | CapEx Hardware | 1760085 | 1931879 | 9.8
BG0471 | PRJ020 | CL004 | 2026-04 | ROW Charges | 838403 | 862245 | 2.8
BG0472 | PRJ020 | CL004 | 2026-03 | ROW Charges | 1438187 | 1306209 | -9.2
BG0473 | PRJ020 | CL004 | 2026-03 | Last Mile | 3996213 | 4233818 | 5.9
BG0474 | PRJ020 | CL004 | 2026-03 | Logistics | 2595925 | 2879660 | 10.9
BG0475 | PRJ020 | CL004 | 2026-03 | CapEx Hardware | 2806407 | 2885505 | 2.8
BG0476 | PRJ020 | CL004 | 2026-03 | Labor | 2787883 | 2545852 | -8.7
BG0477 | PRJ020 | CL004 | 2026-02 | Labor | 2436380 | 2018113 | -17.2
BG0478 | PRJ020 | CL004 | 2026-02 | Logistics | 1131622 | 987977 | -12.7
BG0479 | PRJ020 | CL004 | 2026-02 | CapEx Hardware | 3774352 | 4208584 | 11.5
BG0480 | PRJ020 | CL004 | 2026-01 | Labor | 3037279 | 3216674 | 5.9
BG0481 | PRJ020 | CL004 | 2026-01 | Logistics | 3481912 | 3260718 | -6.4
BG0482 | PRJ020 | CL004 | 2026-01 | PMO Overhead | 1051526 | 864181 | -17.8
BG0483 | PRJ021 | CL005 | 2026-06 | PMO Overhead | 2086631 | 2074770 | -0.6
BG0484 | PRJ021 | CL005 | 2026-06 | Last Mile | 2372732 | 2559149 | 7.9
BG0485 | PRJ021 | CL005 | 2026-06 | Labor | 886030 | 727283 | -17.9
BG0486 | PRJ021 | CL005 | 2026-05 | ROW Charges | 2176116 | 1789670 | -17.8
BG0487 | PRJ021 | CL005 | 2026-05 | PMO Overhead | 1473941 | 1488481 | 1
BG0488 | PRJ021 | CL005 | 2026-05 | Last Mile | 4274738 | 3519461 | -17.7
BG0489 | PRJ021 | CL005 | 2026-05 | Logistics | 2868757 | 2535278 | -11.6
BG0490 | PRJ021 | CL005 | 2026-04 | Labor | 1570262 | 1422281 | -9.4
BG0491 | PRJ021 | CL005 | 2026-04 | PMO Overhead | 2726773 | 2675432 | -1.9
BG0492 | PRJ021 | CL005 | 2026-04 | Last Mile | 1570788 | 1562358 | -0.5
BG0493 | PRJ021 | CL005 | 2026-04 | ROW Charges | 3432917 | 3007341 | -12.4
BG0494 | PRJ021 | CL005 | 2026-03 | PMO Overhead | 2188440 | 2356519 | 7.7
BG0495 | PRJ021 | CL005 | 2026-03 | Last Mile | 1092527 | 900864 | -17.5
BG0496 | PRJ021 | CL005 | 2026-03 | Logistics | 4102825 | 3403639 | -17
BG0497 | PRJ021 | CL005 | 2026-03 | CapEx Hardware | 967075 | 979594 | 1.3
BG0498 | PRJ021 | CL005 | 2026-03 | ROW Charges | 2568968 | 2753109 | 7.2
BG0499 | PRJ021 | CL005 | 2026-02 | Labor | 3472638 | 3643809 | 4.9
BG0500 | PRJ021 | CL005 | 2026-02 | Last Mile | 3069176 | 3028465 | -1.3
BG0501 | PRJ021 | CL005 | 2026-02 | CapEx Hardware | 2536460 | 2468307 | -2.7
BG0502 | PRJ021 | CL005 | 2026-01 | CapEx Hardware | 1170718 | 1094864 | -6.5
BG0503 | PRJ021 | CL005 | 2026-01 | Last Mile | 2662572 | 2358994 | -11.4
BG0504 | PRJ021 | CL005 | 2026-01 | PMO Overhead | 1370765 | 1377454 | 0.5
BG0505 | PRJ022 | CL005 | 2026-06 | ROW Charges | 1261884 | 1095887 | -13.2
BG0506 | PRJ022 | CL005 | 2026-06 | CapEx Hardware | 1475711 | 1414914 | -4.1
BG0507 | PRJ022 | CL005 | 2026-06 | Last Mile | 3628727 | 3200214 | -11.8
BG0508 | PRJ022 | CL005 | 2026-06 | PMO Overhead | 2057073 | 1831682 | -11
BG0509 | PRJ022 | CL005 | 2026-06 | Labor | 1128678 | 1214454 | 7.6
BG0510 | PRJ022 | CL005 | 2026-05 | Labor | 2262473 | 2481437 | 9.7
BG0511 | PRJ022 | CL005 | 2026-05 | Logistics | 2536221 | 2579939 | 1.7
BG0512 | PRJ022 | CL005 | 2026-05 | PMO Overhead | 1840244 | 1673814 | -9
BG0513 | PRJ022 | CL005 | 2026-05 | ROW Charges | 2185829 | 2286630 | 4.6
BG0514 | PRJ022 | CL005 | 2026-05 | Last Mile | 4468585 | 4872267 | 9
BG0515 | PRJ022 | CL005 | 2026-04 | PMO Overhead | 1879604 | 1984240 | 5.6
BG0516 | PRJ022 | CL005 | 2026-04 | Last Mile | 4120660 | 4487424 | 8.9
BG0517 | PRJ022 | CL005 | 2026-04 | Labor | 3366858 | 2883355 | -14.4
BG0518 | PRJ022 | CL005 | 2026-04 | ROW Charges | 3188175 | 3501894 | 9.8
BG0519 | PRJ022 | CL005 | 2026-03 | Last Mile | 1956738 | 1944010 | -0.7
BG0520 | PRJ022 | CL005 | 2026-03 | Logistics | 1995749 | 1772074 | -11.2
BG0521 | PRJ022 | CL005 | 2026-03 | PMO Overhead | 4494835 | 4049359 | -9.9
BG0522 | PRJ022 | CL005 | 2026-03 | Labor | 2519320 | 2265217 | -10.1
BG0523 | PRJ022 | CL005 | 2026-03 | ROW Charges | 3005467 | 3148891 | 4.8
BG0524 | PRJ022 | CL005 | 2026-02 | PMO Overhead | 1000253 | 998248 | -0.2
BG0525 | PRJ022 | CL005 | 2026-02 | Logistics | 2899267 | 2742818 | -5.4
BG0526 | PRJ022 | CL005 | 2026-02 | Last Mile | 3339394 | 3462567 | 3.7
BG0527 | PRJ022 | CL005 | 2026-02 | CapEx Hardware | 3834772 | 4220372 | 10.1
BG0528 | PRJ022 | CL005 | 2026-02 | Labor | 3214323 | 3280867 | 2.1
BG0529 | PRJ022 | CL005 | 2026-01 | PMO Overhead | 1461413 | 1243784 | -14.9
BG0530 | PRJ022 | CL005 | 2026-01 | Logistics | 833454 | 932894 | 11.9
BG0531 | PRJ022 | CL005 | 2026-01 | Labor | 3988714 | 3954020 | -0.9
BG0532 | PRJ022 | CL005 | 2026-01 | CapEx Hardware | 1341437 | 1124608 | -16.2
BG0533 | PRJ022 | CL005 | 2026-01 | ROW Charges | 1527028 | 1304911 | -14.5
BG0534 | PRJ023 | CL005 | 2026-06 | ROW Charges | 3217755 | 2649521 | -17.7
BG0535 | PRJ023 | CL005 | 2026-06 | Logistics | 4243801 | 3508771 | -17.3
BG0536 | PRJ023 | CL005 | 2026-06 | CapEx Hardware | 4134164 | 4155490 | 0.5
BG0537 | PRJ023 | CL005 | 2026-06 | Last Mile | 4434223 | 4921195 | 11
BG0538 | PRJ023 | CL005 | 2026-06 | Labor | 3820466 | 3789358 | -0.8
BG0539 | PRJ023 | CL005 | 2026-05 | CapEx Hardware | 3220500 | 2686213 | -16.6
BG0540 | PRJ023 | CL005 | 2026-05 | ROW Charges | 2123818 | 1835705 | -13.6
BG0541 | PRJ023 | CL005 | 2026-05 | Logistics | 4413154 | 4181761 | -5.2
BG0542 | PRJ023 | CL005 | 2026-04 | Logistics | 1175097 | 1184969 | 0.8
BG0543 | PRJ023 | CL005 | 2026-04 | Last Mile | 3555628 | 3249574 | -8.6
BG0544 | PRJ023 | CL005 | 2026-04 | PMO Overhead | 2916414 | 2862572 | -1.8
BG0545 | PRJ023 | CL005 | 2026-04 | ROW Charges | 886685 | 927794 | 4.6
BG0546 | PRJ023 | CL005 | 2026-03 | PMO Overhead | 1330732 | 1360008 | 2.2
BG0547 | PRJ023 | CL005 | 2026-03 | CapEx Hardware | 883782 | 922525 | 4.4
BG0548 | PRJ023 | CL005 | 2026-03 | Labor | 1309766 | 1121890 | -14.3
BG0549 | PRJ023 | CL005 | 2026-03 | Logistics | 1811377 | 1913139 | 5.6
BG0550 | PRJ023 | CL005 | 2026-02 | CapEx Hardware | 4377033 | 4342242 | -0.8
BG0551 | PRJ023 | CL005 | 2026-02 | Last Mile | 2789402 | 2544526 | -8.8
BG0552 | PRJ023 | CL005 | 2026-02 | Logistics | 3510855 | 3791168 | 8
BG0553 | PRJ023 | CL005 | 2026-01 | CapEx Hardware | 3207395 | 2686902 | -16.2
BG0554 | PRJ023 | CL005 | 2026-01 | Last Mile | 3027673 | 2780696 | -8.2
BG0555 | PRJ023 | CL005 | 2026-01 | ROW Charges | 3044000 | 3224449 | 5.9
BG0556 | PRJ023 | CL005 | 2026-01 | PMO Overhead | 4388584 | 4259939 | -2.9
BG0557 | PRJ024 | CL005 | 2026-06 | CapEx Hardware | 1175149 | 1077090 | -8.3
BG0558 | PRJ024 | CL005 | 2026-06 | Last Mile | 3886168 | 3321243 | -14.5
BG0559 | PRJ024 | CL005 | 2026-06 | Labor | 2505287 | 2726741 | 8.8
BG0560 | PRJ024 | CL005 | 2026-06 | ROW Charges | 4253805 | 3673405 | -13.6
BG0561 | PRJ024 | CL005 | 2026-06 | PMO Overhead | 1104924 | 907500 | -17.9
BG0562 | PRJ024 | CL005 | 2026-05 | Last Mile | 994702 | 1107866 | 11.4
BG0563 | PRJ024 | CL005 | 2026-05 | PMO Overhead | 4211521 | 4273149 | 1.5
BG0564 | PRJ024 | CL005 | 2026-05 | Labor | 4016375 | 3604328 | -10.3
BG0565 | PRJ024 | CL005 | 2026-04 | Labor | 3400480 | 3337428 | -1.9
BG0566 | PRJ024 | CL005 | 2026-04 | Last Mile | 1731686 | 1720198 | -0.7
BG0567 | PRJ024 | CL005 | 2026-04 | CapEx Hardware | 2010301 | 1975218 | -1.7
BG0568 | PRJ024 | CL005 | 2026-03 | Logistics | 842861 | 767364 | -9
BG0569 | PRJ024 | CL005 | 2026-03 | CapEx Hardware | 1249364 | 1301308 | 4.2
BG0570 | PRJ024 | CL005 | 2026-03 | Last Mile | 3319463 | 3527960 | 6.3
BG0571 | PRJ024 | CL005 | 2026-03 | PMO Overhead | 1112870 | 1184332 | 6.4
BG0572 | PRJ024 | CL005 | 2026-02 | Last Mile | 2344766 | 2563949 | 9.3
BG0573 | PRJ024 | CL005 | 2026-02 | CapEx Hardware | 2381491 | 2293093 | -3.7
BG0574 | PRJ024 | CL005 | 2026-02 | PMO Overhead | 2329781 | 2444162 | 4.9
BG0575 | PRJ024 | CL005 | 2026-02 | Logistics | 3796020 | 3739136 | -1.5
BG0576 | PRJ024 | CL005 | 2026-01 | PMO Overhead | 4131065 | 3691190 | -10.6
BG0577 | PRJ024 | CL005 | 2026-01 | Labor | 3600732 | 3889945 | 8
BG0578 | PRJ024 | CL005 | 2026-01 | ROW Charges | 3377250 | 3643210 | 7.9
BG0579 | PRJ024 | CL005 | 2026-01 | Logistics | 1775899 | 1621320 | -8.7
BG0580 | PRJ025 | CL006 | 2026-06 | Last Mile | 2487029 | 2608649 | 4.9
BG0581 | PRJ025 | CL006 | 2026-06 | CapEx Hardware | 3223806 | 3543864 | 9.9
BG0582 | PRJ025 | CL006 | 2026-06 | Logistics | 3636045 | 3959267 | 8.9
BG0583 | PRJ025 | CL006 | 2026-05 | ROW Charges | 4015930 | 4301435 | 7.1
BG0584 | PRJ025 | CL006 | 2026-05 | Last Mile | 4320302 | 4340663 | 0.5
BG0585 | PRJ025 | CL006 | 2026-05 | Logistics | 3622363 | 4051826 | 11.9
BG0586 | PRJ025 | CL006 | 2026-04 | Last Mile | 2556069 | 2634612 | 3.1
BG0587 | PRJ025 | CL006 | 2026-04 | ROW Charges | 4027367 | 3549004 | -11.9
BG0588 | PRJ025 | CL006 | 2026-04 | CapEx Hardware | 4173406 | 3714390 | -11
BG0589 | PRJ025 | CL006 | 2026-04 | Labor | 1179320 | 1128918 | -4.3
BG0590 | PRJ025 | CL006 | 2026-04 | Logistics | 825483 | 809112 | -2
BG0591 | PRJ025 | CL006 | 2026-03 | Logistics | 3263366 | 2961769 | -9.2
BG0592 | PRJ025 | CL006 | 2026-03 | Labor | 926697 | 817230 | -11.8
BG0593 | PRJ025 | CL006 | 2026-03 | Last Mile | 3716954 | 3707317 | -0.3
BG0594 | PRJ025 | CL006 | 2026-03 | ROW Charges | 3681332 | 4071936 | 10.6
BG0595 | PRJ025 | CL006 | 2026-02 | CapEx Hardware | 2068721 | 2122769 | 2.6
BG0596 | PRJ025 | CL006 | 2026-02 | Last Mile | 3483237 | 3484808 | 0
BG0597 | PRJ025 | CL006 | 2026-02 | Labor | 880856 | 752150 | -14.6
BG0598 | PRJ025 | CL006 | 2026-01 | Logistics | 912340 | 1020146 | 11.8
BG0599 | PRJ025 | CL006 | 2026-01 | PMO Overhead | 3311609 | 2893980 | -12.6
BG0600 | PRJ025 | CL006 | 2026-01 | ROW Charges | 3387592 | 3123338 | -7.8
BG0601 | PRJ025 | CL006 | 2026-01 | Last Mile | 3059086 | 2911505 | -4.8
BG0602 | PRJ026 | CL006 | 2026-06 | Logistics | 1340849 | 1171597 | -12.6
BG0603 | PRJ026 | CL006 | 2026-06 | ROW Charges | 2067611 | 1741995 | -15.7
BG0604 | PRJ026 | CL006 | 2026-06 | CapEx Hardware | 1828841 | 1823755 | -0.3
BG0605 | PRJ026 | CL006 | 2026-06 | Last Mile | 2090129 | 1991268 | -4.7
BG0606 | PRJ026 | CL006 | 2026-05 | CapEx Hardware | 3926172 | 3649808 | -7
BG0607 | PRJ026 | CL006 | 2026-05 | ROW Charges | 1207157 | 1236132 | 2.4
BG0608 | PRJ026 | CL006 | 2026-05 | Labor | 2141648 | 2202297 | 2.8
BG0609 | PRJ026 | CL006 | 2026-05 | Logistics | 2760997 | 2747350 | -0.5
BG0610 | PRJ026 | CL006 | 2026-04 | PMO Overhead | 3884238 | 3278240 | -15.6
BG0611 | PRJ026 | CL006 | 2026-04 | ROW Charges | 3496877 | 3845591 | 10
BG0612 | PRJ026 | CL006 | 2026-04 | CapEx Hardware | 3472715 | 3447272 | -0.7
BG0613 | PRJ026 | CL006 | 2026-04 | Labor | 2468744 | 2346339 | -5
BG0614 | PRJ026 | CL006 | 2026-03 | Labor | 2428829 | 2636621 | 8.6
BG0615 | PRJ026 | CL006 | 2026-03 | ROW Charges | 3122507 | 2780640 | -10.9
BG0616 | PRJ026 | CL006 | 2026-03 | Last Mile | 4495629 | 4121056 | -8.3
BG0617 | PRJ026 | CL006 | 2026-03 | Logistics | 3347088 | 3241550 | -3.2
BG0618 | PRJ026 | CL006 | 2026-03 | PMO Overhead | 3430672 | 3503284 | 2.1
BG0619 | PRJ026 | CL006 | 2026-02 | ROW Charges | 3680080 | 3535129 | -3.9
BG0620 | PRJ026 | CL006 | 2026-02 | Logistics | 4037989 | 3536150 | -12.4
BG0621 | PRJ026 | CL006 | 2026-02 | CapEx Hardware | 1818743 | 2033620 | 11.8
BG0622 | PRJ026 | CL006 | 2026-02 | Last Mile | 3711119 | 3575591 | -3.7
BG0623 | PRJ026 | CL006 | 2026-01 | PMO Overhead | 4388389 | 3606350 | -17.8
BG0624 | PRJ026 | CL006 | 2026-01 | CapEx Hardware | 3494374 | 2970492 | -15
BG0625 | PRJ026 | CL006 | 2026-01 | Labor | 1578498 | 1372003 | -13.1
BG0626 | PRJ026 | CL006 | 2026-01 | Logistics | 3331136 | 3091174 | -7.2
BG0627 | PRJ027 | CL006 | 2026-06 | Logistics | 2575770 | 2540013 | -1.4
BG0628 | PRJ027 | CL006 | 2026-06 | CapEx Hardware | 2565701 | 2479664 | -3.4
BG0629 | PRJ027 | CL006 | 2026-06 | PMO Overhead | 3388711 | 3531412 | 4.2
BG0630 | PRJ027 | CL006 | 2026-06 | ROW Charges | 1193372 | 1148388 | -3.8
BG0631 | PRJ027 | CL006 | 2026-06 | Last Mile | 2697249 | 2708794 | 0.4
BG0632 | PRJ027 | CL006 | 2026-05 | Last Mile | 1304564 | 1177113 | -9.8
BG0633 | PRJ027 | CL006 | 2026-05 | Labor | 912834 | 917429 | 0.5
BG0634 | PRJ027 | CL006 | 2026-05 | Logistics | 1686209 | 1506786 | -10.6
BG0635 | PRJ027 | CL006 | 2026-05 | PMO Overhead | 4400167 | 4070764 | -7.5
BG0636 | PRJ027 | CL006 | 2026-04 | Labor | 4498042 | 4102893 | -8.8
BG0637 | PRJ027 | CL006 | 2026-04 | ROW Charges | 4442978 | 4721557 | 6.3
BG0638 | PRJ027 | CL006 | 2026-04 | PMO Overhead | 4212301 | 3520489 | -16.4
BG0639 | PRJ027 | CL006 | 2026-04 | Last Mile | 3105128 | 2903664 | -6.5
BG0640 | PRJ027 | CL006 | 2026-03 | Last Mile | 3180735 | 3165998 | -0.5
BG0641 | PRJ027 | CL006 | 2026-03 | ROW Charges | 3947565 | 3659437 | -7.3
BG0642 | PRJ027 | CL006 | 2026-03 | PMO Overhead | 3496290 | 3266995 | -6.6
BG0643 | PRJ027 | CL006 | 2026-03 | CapEx Hardware | 3368342 | 3402401 | 1
BG0644 | PRJ027 | CL006 | 2026-02 | Logistics | 3674394 | 3496558 | -4.8
BG0645 | PRJ027 | CL006 | 2026-02 | Last Mile | 4368546 | 4736550 | 8.4
BG0646 | PRJ027 | CL006 | 2026-02 | PMO Overhead | 4205325 | 3565293 | -15.2
BG0647 | PRJ027 | CL006 | 2026-02 | ROW Charges | 3349532 | 2791816 | -16.7
BG0648 | PRJ027 | CL006 | 2026-01 | Logistics | 1550363 | 1616850 | 4.3
BG0649 | PRJ027 | CL006 | 2026-01 | Labor | 2203089 | 2033412 | -7.7
BG0650 | PRJ027 | CL006 | 2026-01 | CapEx Hardware | 3856000 | 3997136 | 3.7
BG0651 | PRJ028 | CL006 | 2026-06 | Labor | 1191049 | 1307692 | 9.8
BG0652 | PRJ028 | CL006 | 2026-06 | Last Mile | 2554287 | 2603239 | 1.9
BG0653 | PRJ028 | CL006 | 2026-06 | ROW Charges | 1089877 | 991409 | -9
BG0654 | PRJ028 | CL006 | 2026-06 | Logistics | 3114572 | 2608690 | -16.2
BG0655 | PRJ028 | CL006 | 2026-05 | Last Mile | 2808696 | 2912240 | 3.7
BG0656 | PRJ028 | CL006 | 2026-05 | CapEx Hardware | 3383545 | 3397533 | 0.4
BG0657 | PRJ028 | CL006 | 2026-05 | Labor | 3484974 | 3498429 | 0.4
BG0658 | PRJ028 | CL006 | 2026-05 | Logistics | 2468366 | 2243074 | -9.1
BG0659 | PRJ028 | CL006 | 2026-04 | ROW Charges | 4166798 | 4512358 | 8.3
BG0660 | PRJ028 | CL006 | 2026-04 | PMO Overhead | 838379 | 821151 | -2.1
BG0661 | PRJ028 | CL006 | 2026-04 | Last Mile | 3632464 | 3179334 | -12.5
BG0662 | PRJ028 | CL006 | 2026-04 | Logistics | 3920338 | 3380317 | -13.8
BG0663 | PRJ028 | CL006 | 2026-03 | Last Mile | 819996 | 861026 | 5
BG0664 | PRJ028 | CL006 | 2026-03 | PMO Overhead | 1948847 | 1644836 | -15.6
BG0665 | PRJ028 | CL006 | 2026-03 | Labor | 3775598 | 3238729 | -14.2
BG0666 | PRJ028 | CL006 | 2026-03 | ROW Charges | 1263935 | 1309492 | 3.6
BG0667 | PRJ028 | CL006 | 2026-02 | Last Mile | 3042179 | 2803097 | -7.9
BG0668 | PRJ028 | CL006 | 2026-02 | ROW Charges | 2723238 | 2463268 | -9.5
BG0669 | PRJ028 | CL006 | 2026-02 | CapEx Hardware | 3253496 | 3573802 | 9.8
BG0670 | PRJ028 | CL006 | 2026-02 | PMO Overhead | 2411337 | 2103252 | -12.8
BG0671 | PRJ028 | CL006 | 2026-01 | Logistics | 1964130 | 1707541 | -13.1
BG0672 | PRJ028 | CL006 | 2026-01 | ROW Charges | 2696573 | 2260888 | -16.2
BG0673 | PRJ028 | CL006 | 2026-01 | CapEx Hardware | 3999787 | 3535285 | -11.6
BG0674 | PRJ028 | CL006 | 2026-01 | PMO Overhead | 3556324 | 3070244 | -13.7
BG0675 | PRJ029 | CL006 | 2026-06 | CapEx Hardware | 1477283 | 1626268 | 10.1
BG0676 | PRJ029 | CL006 | 2026-06 | PMO Overhead | 4321646 | 3908776 | -9.6
BG0677 | PRJ029 | CL006 | 2026-06 | Labor | 1380532 | 1540568 | 11.6
BG0678 | PRJ029 | CL006 | 2026-06 | Logistics | 2393256 | 2452238 | 2.5
BG0679 | PRJ029 | CL006 | 2026-05 | Last Mile | 1564617 | 1342684 | -14.2
BG0680 | PRJ029 | CL006 | 2026-05 | ROW Charges | 1170120 | 1162908 | -0.6
BG0681 | PRJ029 | CL006 | 2026-05 | PMO Overhead | 3988673 | 3579881 | -10.2
BG0682 | PRJ029 | CL006 | 2026-05 | Labor | 3416268 | 3522261 | 3.1
BG0683 | PRJ029 | CL006 | 2026-04 | CapEx Hardware | 3617573 | 3230398 | -10.7
BG0684 | PRJ029 | CL006 | 2026-04 | Labor | 1010003 | 1059168 | 4.9
BG0685 | PRJ029 | CL006 | 2026-04 | Logistics | 2203308 | 2132477 | -3.2
BG0686 | PRJ029 | CL006 | 2026-04 | Last Mile | 3486618 | 3472752 | -0.4
BG0687 | PRJ029 | CL006 | 2026-03 | Labor | 983946 | 827275 | -15.9
BG0688 | PRJ029 | CL006 | 2026-03 | CapEx Hardware | 3773087 | 4032076 | 6.9
BG0689 | PRJ029 | CL006 | 2026-03 | Logistics | 1434984 | 1357089 | -5.4
BG0690 | PRJ029 | CL006 | 2026-02 | Logistics | 2483282 | 2296029 | -7.5
BG0691 | PRJ029 | CL006 | 2026-02 | CapEx Hardware | 3198389 | 3311389 | 3.5
BG0692 | PRJ029 | CL006 | 2026-02 | Last Mile | 3607770 | 3241567 | -10.2
BG0693 | PRJ029 | CL006 | 2026-01 | Labor | 4381477 | 3860048 | -11.9
BG0694 | PRJ029 | CL006 | 2026-01 | Logistics | 2136491 | 1937170 | -9.3
BG0695 | PRJ029 | CL006 | 2026-01 | ROW Charges | 2898803 | 2997707 | 3.4
BG0696 | PRJ029 | CL006 | 2026-01 | PMO Overhead | 2302217 | 2227622 | -3.2
BG0697 | PRJ030 | CL007 | 2026-06 | Labor | 3718243 | 3786958 | 1.8
BG0698 | PRJ030 | CL007 | 2026-06 | Logistics | 2319858 | 2516068 | 8.5
BG0699 | PRJ030 | CL007 | 2026-06 | CapEx Hardware | 3229738 | 3170032 | -1.8
BG0700 | PRJ030 | CL007 | 2026-06 | PMO Overhead | 1368795 | 1380965 | 0.9
BG0701 | PRJ030 | CL007 | 2026-06 | Last Mile | 3859240 | 3201753 | -17
BG0702 | PRJ030 | CL007 | 2026-05 | Logistics | 2733164 | 2637603 | -3.5
BG0703 | PRJ030 | CL007 | 2026-05 | PMO Overhead | 4056456 | 4411844 | 8.8
BG0704 | PRJ030 | CL007 | 2026-05 | Last Mile | 2178340 | 2211570 | 1.5
BG0705 | PRJ030 | CL007 | 2026-05 | Labor | 3989494 | 4379342 | 9.8
BG0706 | PRJ030 | CL007 | 2026-05 | CapEx Hardware | 2555471 | 2402495 | -6
BG0707 | PRJ030 | CL007 | 2026-04 | CapEx Hardware | 3407599 | 3275181 | -3.9
BG0708 | PRJ030 | CL007 | 2026-04 | Last Mile | 2598485 | 2483752 | -4.4
BG0709 | PRJ030 | CL007 | 2026-04 | Logistics | 2805796 | 2883581 | 2.8
BG0710 | PRJ030 | CL007 | 2026-03 | ROW Charges | 846997 | 874019 | 3.2
BG0711 | PRJ030 | CL007 | 2026-03 | Last Mile | 1556063 | 1418645 | -8.8
BG0712 | PRJ030 | CL007 | 2026-03 | Labor | 3528211 | 3074819 | -12.9
BG0713 | PRJ030 | CL007 | 2026-02 | PMO Overhead | 3687130 | 3705635 | 0.5
BG0714 | PRJ030 | CL007 | 2026-02 | Labor | 4489138 | 4747594 | 5.8
BG0715 | PRJ030 | CL007 | 2026-02 | CapEx Hardware | 3827633 | 3402230 | -11.1
BG0716 | PRJ030 | CL007 | 2026-01 | ROW Charges | 3876604 | 3451753 | -11
BG0717 | PRJ030 | CL007 | 2026-01 | Last Mile | 2111438 | 1926818 | -8.7
BG0718 | PRJ030 | CL007 | 2026-01 | Logistics | 860465 | 729883 | -15.2
BG0719 | PRJ031 | CL007 | 2026-06 | ROW Charges | 3688896 | 3756214 | 1.8
BG0720 | PRJ031 | CL007 | 2026-06 | Logistics | 3287227 | 3574121 | 8.7
BG0721 | PRJ031 | CL007 | 2026-06 | PMO Overhead | 2341658 | 2464102 | 5.2
BG0722 | PRJ031 | CL007 | 2026-06 | Last Mile | 3578423 | 3508424 | -2
BG0723 | PRJ031 | CL007 | 2026-06 | Labor | 1578342 | 1707436 | 8.2
BG0724 | PRJ031 | CL007 | 2026-05 | Logistics | 3988243 | 4184394 | 4.9
BG0725 | PRJ031 | CL007 | 2026-05 | Last Mile | 3010156 | 2665493 | -11.5
BG0726 | PRJ031 | CL007 | 2026-05 | CapEx Hardware | 1829573 | 1705262 | -6.8
BG0727 | PRJ031 | CL007 | 2026-04 | ROW Charges | 2591361 | 2540967 | -1.9
BG0728 | PRJ031 | CL007 | 2026-04 | Logistics | 2050011 | 2100138 | 2.4
BG0729 | PRJ031 | CL007 | 2026-04 | Labor | 4288835 | 4060332 | -5.3
BG0730 | PRJ031 | CL007 | 2026-03 | PMO Overhead | 2474465 | 2235833 | -9.6
BG0731 | PRJ031 | CL007 | 2026-03 | ROW Charges | 4162616 | 4102254 | -1.5
BG0732 | PRJ031 | CL007 | 2026-03 | CapEx Hardware | 2811714 | 3126822 | 11.2
BG0733 | PRJ031 | CL007 | 2026-03 | Labor | 3878896 | 3507367 | -9.6
BG0734 | PRJ031 | CL007 | 2026-02 | Logistics | 1132815 | 1007429 | -11.1
BG0735 | PRJ031 | CL007 | 2026-02 | ROW Charges | 3468325 | 3052819 | -12
BG0736 | PRJ031 | CL007 | 2026-02 | Labor | 2803098 | 2569636 | -8.3
BG0737 | PRJ031 | CL007 | 2026-02 | CapEx Hardware | 2245411 | 2301779 | 2.5
BG0738 | PRJ031 | CL007 | 2026-01 | Labor | 1951495 | 1914874 | -1.9
BG0739 | PRJ031 | CL007 | 2026-01 | Logistics | 2718281 | 3016232 | 11
BG0740 | PRJ031 | CL007 | 2026-01 | Last Mile | 1164844 | 1293082 | 11
BG0741 | PRJ031 | CL007 | 2026-01 | PMO Overhead | 1069987 | 1103933 | 3.2
BG0742 | PRJ031 | CL007 | 2026-01 | ROW Charges | 2021098 | 2245884 | 11.1
BG0743 | PRJ032 | CL007 | 2026-06 | Last Mile | 3880316 | 3276718 | -15.6
BG0744 | PRJ032 | CL007 | 2026-06 | Labor | 997488 | 1089460 | 9.2
BG0745 | PRJ032 | CL007 | 2026-06 | CapEx Hardware | 4009302 | 3393986 | -15.3
BG0746 | PRJ032 | CL007 | 2026-06 | ROW Charges | 3077841 | 2749629 | -10.7
BG0747 | PRJ032 | CL007 | 2026-06 | Logistics | 1163984 | 1153981 | -0.9
BG0748 | PRJ032 | CL007 | 2026-05 | Logistics | 3225098 | 2656127 | -17.6
BG0749 | PRJ032 | CL007 | 2026-05 | PMO Overhead | 1725041 | 1589905 | -7.8
BG0750 | PRJ032 | CL007 | 2026-05 | ROW Charges | 3980821 | 4294099 | 7.9
BG0751 | PRJ032 | CL007 | 2026-05 | Labor | 2703357 | 2297826 | -15
BG0752 | PRJ032 | CL007 | 2026-04 | CapEx Hardware | 936978 | 865411 | -7.6
BG0753 | PRJ032 | CL007 | 2026-04 | ROW Charges | 2898481 | 2769702 | -4.4
BG0754 | PRJ032 | CL007 | 2026-04 | PMO Overhead | 1039007 | 1130414 | 8.8
BG0755 | PRJ032 | CL007 | 2026-04 | Logistics | 2072823 | 1745553 | -15.8
BG0756 | PRJ032 | CL007 | 2026-03 | PMO Overhead | 1191004 | 1320767 | 10.9
BG0757 | PRJ032 | CL007 | 2026-03 | ROW Charges | 1862710 | 1829667 | -1.8
BG0758 | PRJ032 | CL007 | 2026-03 | CapEx Hardware | 1772487 | 1857973 | 4.8
BG0759 | PRJ032 | CL007 | 2026-03 | Last Mile | 3447431 | 3401180 | -1.3
BG0760 | PRJ032 | CL007 | 2026-02 | Last Mile | 3143003 | 2821348 | -10.2
BG0761 | PRJ032 | CL007 | 2026-02 | PMO Overhead | 3971121 | 3920313 | -1.3
BG0762 | PRJ032 | CL007 | 2026-02 | ROW Charges | 4004297 | 4283871 | 7
BG0763 | PRJ032 | CL007 | 2026-02 | Logistics | 2718915 | 2608626 | -4.1
BG0764 | PRJ032 | CL007 | 2026-01 | ROW Charges | 1741372 | 1589958 | -8.7
BG0765 | PRJ032 | CL007 | 2026-01 | CapEx Hardware | 3551694 | 3810390 | 7.3
BG0766 | PRJ032 | CL007 | 2026-01 | Logistics | 3262569 | 3457381 | 6
BG0767 | PRJ032 | CL007 | 2026-01 | Last Mile | 2708603 | 2770621 | 2.3
BG0768 | PRJ032 | CL007 | 2026-01 | Labor | 3603038 | 3864656 | 7.3
BG0769 | PRJ033 | CL007 | 2026-06 | Logistics | 2074119 | 2152695 | 3.8
BG0770 | PRJ033 | CL007 | 2026-06 | Last Mile | 2516338 | 2486292 | -1.2
BG0771 | PRJ033 | CL007 | 2026-06 | Labor | 3606327 | 3797890 | 5.3
BG0772 | PRJ033 | CL007 | 2026-06 | PMO Overhead | 2014108 | 1689871 | -16.1
BG0773 | PRJ033 | CL007 | 2026-06 | CapEx Hardware | 989861 | 877148 | -11.4
BG0774 | PRJ033 | CL007 | 2026-05 | Labor | 3969293 | 3337890 | -15.9
BG0775 | PRJ033 | CL007 | 2026-05 | CapEx Hardware | 1234716 | 1053532 | -14.7
BG0776 | PRJ033 | CL007 | 2026-05 | Last Mile | 4398148 | 4925161 | 12
BG0777 | PRJ033 | CL007 | 2026-04 | PMO Overhead | 1160390 | 1194299 | 2.9
BG0778 | PRJ033 | CL007 | 2026-04 | CapEx Hardware | 1770796 | 1535230 | -13.3
BG0779 | PRJ033 | CL007 | 2026-04 | Labor | 3468336 | 2964571 | -14.5
BG0780 | PRJ033 | CL007 | 2026-04 | Logistics | 4465294 | 4448209 | -0.4
BG0781 | PRJ033 | CL007 | 2026-04 | Last Mile | 809338 | 738857 | -8.7
BG0782 | PRJ033 | CL007 | 2026-03 | CapEx Hardware | 805719 | 799077 | -0.8
BG0783 | PRJ033 | CL007 | 2026-03 | Logistics | 1952974 | 2065690 | 5.8
BG0784 | PRJ033 | CL007 | 2026-03 | Labor | 4183428 | 4684590 | 12
BG0785 | PRJ033 | CL007 | 2026-03 | Last Mile | 2420645 | 2314065 | -4.4
BG0786 | PRJ033 | CL007 | 2026-02 | PMO Overhead | 1692045 | 1422608 | -15.9
BG0787 | PRJ033 | CL007 | 2026-02 | Logistics | 1630189 | 1387893 | -14.9
BG0788 | PRJ033 | CL007 | 2026-02 | ROW Charges | 4194551 | 4455334 | 6.2
BG0789 | PRJ033 | CL007 | 2026-02 | Labor | 3999949 | 4372454 | 9.3
BG0790 | PRJ033 | CL007 | 2026-01 | Labor | 2719836 | 2497997 | -8.2
BG0791 | PRJ033 | CL007 | 2026-01 | ROW Charges | 2781374 | 2781076 | 0
BG0792 | PRJ033 | CL007 | 2026-01 | Last Mile | 4115846 | 3442476 | -16.4
BG0793 | PRJ033 | CL007 | 2026-01 | CapEx Hardware | 3843571 | 3460438 | -10
BG0794 | PRJ034 | CL007 | 2026-06 | Logistics | 3661009 | 3843137 | 5
BG0795 | PRJ034 | CL007 | 2026-06 | Labor | 3853643 | 3376508 | -12.4
BG0796 | PRJ034 | CL007 | 2026-06 | Last Mile | 1164897 | 1222552 | 4.9
BG0797 | PRJ034 | CL007 | 2026-06 | PMO Overhead | 1379839 | 1516317 | 9.9
BG0798 | PRJ034 | CL007 | 2026-06 | ROW Charges | 3666289 | 3887545 | 6
BG0799 | PRJ034 | CL007 | 2026-05 | Last Mile | 2115174 | 2175047 | 2.8
BG0800 | PRJ034 | CL007 | 2026-05 | PMO Overhead | 3781878 | 3476696 | -8.1
BG0801 | PRJ034 | CL007 | 2026-05 | ROW Charges | 1298623 | 1175803 | -9.5
BG0802 | PRJ034 | CL007 | 2026-05 | CapEx Hardware | 2689493 | 2331151 | -13.3
BG0803 | PRJ034 | CL007 | 2026-04 | PMO Overhead | 1830402 | 1648005 | -10
BG0804 | PRJ034 | CL007 | 2026-04 | CapEx Hardware | 2843879 | 2395828 | -15.8
BG0805 | PRJ034 | CL007 | 2026-04 | Last Mile | 2577885 | 2726534 | 5.8
BG0806 | PRJ034 | CL007 | 2026-04 | Logistics | 2183026 | 2370480 | 8.6
BG0807 | PRJ034 | CL007 | 2026-04 | Labor | 3254339 | 2905824 | -10.7
BG0808 | PRJ034 | CL007 | 2026-03 | Labor | 2693663 | 3006150 | 11.6
BG0809 | PRJ034 | CL007 | 2026-03 | PMO Overhead | 975748 | 1067443 | 9.4
BG0810 | PRJ034 | CL007 | 2026-03 | Logistics | 1424097 | 1183459 | -16.9
BG0811 | PRJ034 | CL007 | 2026-03 | ROW Charges | 2524166 | 2155798 | -14.6
BG0812 | PRJ034 | CL007 | 2026-02 | CapEx Hardware | 1913457 | 2106917 | 10.1
BG0813 | PRJ034 | CL007 | 2026-02 | Last Mile | 4125944 | 3829434 | -7.2
BG0814 | PRJ034 | CL007 | 2026-02 | ROW Charges | 1949636 | 2066216 | 6
BG0815 | PRJ034 | CL007 | 2026-02 | Logistics | 4152068 | 3892515 | -6.3
BG0816 | PRJ034 | CL007 | 2026-01 | CapEx Hardware | 3579447 | 3576295 | -0.1
BG0817 | PRJ034 | CL007 | 2026-01 | Logistics | 3462827 | 2992722 | -13.6
BG0818 | PRJ034 | CL007 | 2026-01 | Last Mile | 3639547 | 3784130 | 4
BG0819 | PRJ035 | CL008 | 2026-06 | ROW Charges | 3146432 | 2977332 | -5.4
BG0820 | PRJ035 | CL008 | 2026-06 | CapEx Hardware | 1847096 | 1615805 | -12.5
BG0821 | PRJ035 | CL008 | 2026-06 | Labor | 2050928 | 1814348 | -11.5
BG0822 | PRJ035 | CL008 | 2026-06 | PMO Overhead | 928432 | 983882 | 6
BG0823 | PRJ035 | CL008 | 2026-06 | Logistics | 2503813 | 2306746 | -7.9
BG0824 | PRJ035 | CL008 | 2026-05 | ROW Charges | 3413266 | 3695138 | 8.3
BG0825 | PRJ035 | CL008 | 2026-05 | Labor | 1517643 | 1355288 | -10.7
BG0826 | PRJ035 | CL008 | 2026-05 | Logistics | 2205317 | 2205170 | 0
BG0827 | PRJ035 | CL008 | 2026-05 | PMO Overhead | 821827 | 881178 | 7.2
BG0828 | PRJ035 | CL008 | 2026-05 | CapEx Hardware | 2867320 | 2511632 | -12.4
BG0829 | PRJ035 | CL008 | 2026-04 | Labor | 3108585 | 3430836 | 10.4
BG0830 | PRJ035 | CL008 | 2026-04 | Logistics | 3915086 | 3532598 | -9.8
BG0831 | PRJ035 | CL008 | 2026-04 | Last Mile | 2126930 | 2381482 | 12
BG0832 | PRJ035 | CL008 | 2026-04 | PMO Overhead | 1272151 | 1123909 | -11.7
BG0833 | PRJ035 | CL008 | 2026-04 | ROW Charges | 4026661 | 3439970 | -14.6
BG0834 | PRJ035 | CL008 | 2026-03 | ROW Charges | 4064365 | 4248469 | 4.5
BG0835 | PRJ035 | CL008 | 2026-03 | CapEx Hardware | 2596695 | 2515373 | -3.1
BG0836 | PRJ035 | CL008 | 2026-03 | Last Mile | 3152139 | 3444224 | 9.3
BG0837 | PRJ035 | CL008 | 2026-03 | PMO Overhead | 3097657 | 3200283 | 3.3
BG0838 | PRJ035 | CL008 | 2026-03 | Logistics | 1619785 | 1520838 | -6.1
BG0839 | PRJ035 | CL008 | 2026-02 | PMO Overhead | 936489 | 840432 | -10.3
BG0840 | PRJ035 | CL008 | 2026-02 | Last Mile | 1787279 | 1686044 | -5.7
BG0841 | PRJ035 | CL008 | 2026-02 | Logistics | 2641197 | 2454273 | -7.1
BG0842 | PRJ035 | CL008 | 2026-02 | CapEx Hardware | 2105271 | 1987351 | -5.6
BG0843 | PRJ035 | CL008 | 2026-02 | Labor | 4153611 | 3746727 | -9.8
BG0844 | PRJ035 | CL008 | 2026-01 | PMO Overhead | 2447920 | 2176853 | -11.1
BG0845 | PRJ035 | CL008 | 2026-01 | ROW Charges | 4015873 | 3399440 | -15.3
BG0846 | PRJ035 | CL008 | 2026-01 | Labor | 961862 | 904243 | -6
BG0847 | PRJ035 | CL008 | 2026-01 | CapEx Hardware | 1243124 | 1189931 | -4.3
BG0848 | PRJ036 | CL008 | 2026-06 | CapEx Hardware | 951758 | 1030873 | 8.3
BG0849 | PRJ036 | CL008 | 2026-06 | Last Mile | 2209466 | 1891842 | -14.4
BG0850 | PRJ036 | CL008 | 2026-06 | ROW Charges | 1197992 | 1223812 | 2.2
BG0851 | PRJ036 | CL008 | 2026-06 | Labor | 3902505 | 4149017 | 6.3
BG0852 | PRJ036 | CL008 | 2026-06 | Logistics | 1733699 | 1855047 | 7
BG0853 | PRJ036 | CL008 | 2026-05 | ROW Charges | 4134276 | 4209020 | 1.8
BG0854 | PRJ036 | CL008 | 2026-05 | Logistics | 1122134 | 1082756 | -3.5
BG0855 | PRJ036 | CL008 | 2026-05 | PMO Overhead | 3049270 | 2510892 | -17.7
BG0856 | PRJ036 | CL008 | 2026-05 | CapEx Hardware | 2105220 | 2111737 | 0.3
BG0857 | PRJ036 | CL008 | 2026-05 | Last Mile | 1419092 | 1418004 | -0.1
BG0858 | PRJ036 | CL008 | 2026-04 | PMO Overhead | 872446 | 843758 | -3.3
BG0859 | PRJ036 | CL008 | 2026-04 | Last Mile | 3744379 | 3184309 | -15
BG0860 | PRJ036 | CL008 | 2026-04 | Labor | 2572363 | 2173952 | -15.5
BG0861 | PRJ036 | CL008 | 2026-03 | Last Mile | 1972092 | 1958181 | -0.7
BG0862 | PRJ036 | CL008 | 2026-03 | PMO Overhead | 1484482 | 1645572 | 10.9
BG0863 | PRJ036 | CL008 | 2026-03 | Logistics | 976543 | 965567 | -1.1
BG0864 | PRJ036 | CL008 | 2026-03 | CapEx Hardware | 4405444 | 4632327 | 5.2
BG0865 | PRJ036 | CL008 | 2026-03 | Labor | 1912272 | 1591783 | -16.8
BG0866 | PRJ036 | CL008 | 2026-02 | Last Mile | 2776291 | 2689692 | -3.1
BG0867 | PRJ036 | CL008 | 2026-02 | ROW Charges | 2990057 | 2950293 | -1.3
BG0868 | PRJ036 | CL008 | 2026-02 | CapEx Hardware | 2416303 | 2093363 | -13.4
BG0869 | PRJ036 | CL008 | 2026-01 | Labor | 2475316 | 2108635 | -14.8
BG0870 | PRJ036 | CL008 | 2026-01 | Logistics | 3696191 | 4048961 | 9.5
BG0871 | PRJ036 | CL008 | 2026-01 | CapEx Hardware | 1560482 | 1703320 | 9.2
BG0872 | PRJ036 | CL008 | 2026-01 | Last Mile | 4109277 | 4573219 | 11.3
BG0873 | PRJ037 | CL008 | 2026-06 | PMO Overhead | 3971681 | 3880823 | -2.3
BG0874 | PRJ037 | CL008 | 2026-06 | Logistics | 3625074 | 3630457 | 0.1
BG0875 | PRJ037 | CL008 | 2026-06 | ROW Charges | 1640817 | 1809048 | 10.3
BG0876 | PRJ037 | CL008 | 2026-06 | CapEx Hardware | 2901155 | 2708375 | -6.6
BG0877 | PRJ037 | CL008 | 2026-06 | Labor | 2808439 | 3029175 | 7.9
BG0878 | PRJ037 | CL008 | 2026-05 | Labor | 1938929 | 2103955 | 8.5
BG0879 | PRJ037 | CL008 | 2026-05 | Last Mile | 1014162 | 882792 | -13
BG0880 | PRJ037 | CL008 | 2026-05 | Logistics | 1642067 | 1420575 | -13.5
BG0881 | PRJ037 | CL008 | 2026-05 | ROW Charges | 2459322 | 2636140 | 7.2
BG0882 | PRJ037 | CL008 | 2026-05 | PMO Overhead | 3559235 | 3371624 | -5.3
BG0883 | PRJ037 | CL008 | 2026-04 | Logistics | 2204163 | 2150101 | -2.5
BG0884 | PRJ037 | CL008 | 2026-04 | ROW Charges | 3550719 | 3701358 | 4.2
BG0885 | PRJ037 | CL008 | 2026-04 | Labor | 2414852 | 2428631 | 0.6
BG0886 | PRJ037 | CL008 | 2026-04 | PMO Overhead | 4236245 | 4215107 | -0.5
BG0887 | PRJ037 | CL008 | 2026-03 | ROW Charges | 4331433 | 4368281 | 0.9
BG0888 | PRJ037 | CL008 | 2026-03 | CapEx Hardware | 3896556 | 3474107 | -10.8
BG0889 | PRJ037 | CL008 | 2026-03 | Labor | 4380546 | 4174685 | -4.7
BG0890 | PRJ037 | CL008 | 2026-03 | Last Mile | 1860075 | 2007133 | 7.9
BG0891 | PRJ037 | CL008 | 2026-02 | CapEx Hardware | 1812242 | 1726713 | -4.7
BG0892 | PRJ037 | CL008 | 2026-02 | Last Mile | 1511576 | 1511809 | 0
BG0893 | PRJ037 | CL008 | 2026-02 | Labor | 823320 | 813232 | -1.2
BG0894 | PRJ037 | CL008 | 2026-02 | PMO Overhead | 1944598 | 1990816 | 2.4
BG0895 | PRJ037 | CL008 | 2026-02 | Logistics | 3937495 | 3847977 | -2.3
BG0896 | PRJ037 | CL008 | 2026-01 | Labor | 4480624 | 3710385 | -17.2
BG0897 | PRJ037 | CL008 | 2026-01 | Last Mile | 2649378 | 2812099 | 6.1
BG0898 | PRJ037 | CL008 | 2026-01 | PMO Overhead | 2265479 | 2047760 | -9.6
BG0899 | PRJ037 | CL008 | 2026-01 | Logistics | 4436040 | 4890976 | 10.3
BG0900 | PRJ038 | CL008 | 2026-06 | Logistics | 870036 | 877773 | 0.9
BG0901 | PRJ038 | CL008 | 2026-06 | Last Mile | 2354305 | 2123095 | -9.8
BG0902 | PRJ038 | CL008 | 2026-06 | PMO Overhead | 1982274 | 2062006 | 4
BG0903 | PRJ038 | CL008 | 2026-05 | Labor | 4229680 | 3539478 | -16.3
BG0904 | PRJ038 | CL008 | 2026-05 | CapEx Hardware | 2655396 | 2640803 | -0.5
BG0905 | PRJ038 | CL008 | 2026-05 | ROW Charges | 1589978 | 1373079 | -13.6
BG0906 | PRJ038 | CL008 | 2026-05 | Last Mile | 1254129 | 1294109 | 3.2
BG0907 | PRJ038 | CL008 | 2026-05 | PMO Overhead | 1752954 | 1454285 | -17
BG0908 | PRJ038 | CL008 | 2026-04 | Last Mile | 3945208 | 3860370 | -2.2
BG0909 | PRJ038 | CL008 | 2026-04 | ROW Charges | 2202273 | 2220824 | 0.8
BG0910 | PRJ038 | CL008 | 2026-04 | Labor | 3669360 | 3373151 | -8.1
BG0911 | PRJ038 | CL008 | 2026-04 | PMO Overhead | 1262920 | 1252893 | -0.8
BG0912 | PRJ038 | CL008 | 2026-03 | PMO Overhead | 1088668 | 1172341 | 7.7
BG0913 | PRJ038 | CL008 | 2026-03 | CapEx Hardware | 3536555 | 3861124 | 9.2
BG0914 | PRJ038 | CL008 | 2026-03 | Labor | 2154734 | 2225901 | 3.3
BG0915 | PRJ038 | CL008 | 2026-02 | Logistics | 3345068 | 2965092 | -11.4
BG0916 | PRJ038 | CL008 | 2026-02 | CapEx Hardware | 1992999 | 1868247 | -6.3
BG0917 | PRJ038 | CL008 | 2026-02 | Labor | 2331024 | 2417321 | 3.7
BG0918 | PRJ038 | CL008 | 2026-02 | PMO Overhead | 1740658 | 1939365 | 11.4
BG0919 | PRJ038 | CL008 | 2026-02 | ROW Charges | 1651790 | 1733034 | 4.9
BG0920 | PRJ038 | CL008 | 2026-01 | Labor | 3735604 | 3402375 | -8.9
BG0921 | PRJ038 | CL008 | 2026-01 | ROW Charges | 2752290 | 2835318 | 3
BG0922 | PRJ038 | CL008 | 2026-01 | PMO Overhead | 1022026 | 838949 | -17.9
BG0923 | PRJ039 | CL008 | 2026-06 | ROW Charges | 4223819 | 3717171 | -12
BG0924 | PRJ039 | CL008 | 2026-06 | PMO Overhead | 1913647 | 1953704 | 2.1
BG0925 | PRJ039 | CL008 | 2026-06 | Last Mile | 2125244 | 2236790 | 5.2
BG0926 | PRJ039 | CL008 | 2026-06 | Labor | 1302977 | 1116792 | -14.3
BG0927 | PRJ039 | CL008 | 2026-06 | Logistics | 2516968 | 2145967 | -14.7
BG0928 | PRJ039 | CL008 | 2026-05 | Labor | 2532612 | 2678571 | 5.8
BG0929 | PRJ039 | CL008 | 2026-05 | Logistics | 1157653 | 1134710 | -2
BG0930 | PRJ039 | CL008 | 2026-05 | PMO Overhead | 4369430 | 4667028 | 6.8
BG0931 | PRJ039 | CL008 | 2026-05 | Last Mile | 2119459 | 1871262 | -11.7
BG0932 | PRJ039 | CL008 | 2026-05 | CapEx Hardware | 4001045 | 4209874 | 5.2
BG0933 | PRJ039 | CL008 | 2026-04 | Logistics | 1333735 | 1381684 | 3.6
BG0934 | PRJ039 | CL008 | 2026-04 | Last Mile | 3420878 | 3183548 | -6.9
BG0935 | PRJ039 | CL008 | 2026-04 | ROW Charges | 3039160 | 2589181 | -14.8
BG0936 | PRJ039 | CL008 | 2026-04 | Labor | 4371510 | 4387300 | 0.4
BG0937 | PRJ039 | CL008 | 2026-03 | Labor | 1617275 | 1494687 | -7.6
BG0938 | PRJ039 | CL008 | 2026-03 | CapEx Hardware | 2353730 | 2348901 | -0.2
BG0939 | PRJ039 | CL008 | 2026-03 | Last Mile | 4262302 | 3939832 | -7.6
BG0940 | PRJ039 | CL008 | 2026-03 | Logistics | 1034727 | 1063802 | 2.8
BG0941 | PRJ039 | CL008 | 2026-03 | PMO Overhead | 3608770 | 3756884 | 4.1
BG0942 | PRJ039 | CL008 | 2026-02 | Labor | 4180042 | 4049420 | -3.1
BG0943 | PRJ039 | CL008 | 2026-02 | Last Mile | 991139 | 1072271 | 8.2
BG0944 | PRJ039 | CL008 | 2026-02 | CapEx Hardware | 3803421 | 3878332 | 2
BG0945 | PRJ039 | CL008 | 2026-02 | Logistics | 1169224 | 1164281 | -0.4
BG0946 | PRJ039 | CL008 | 2026-02 | ROW Charges | 3444307 | 3672953 | 6.6
BG0947 | PRJ039 | CL008 | 2026-01 | Labor | 1351592 | 1253518 | -7.3
BG0948 | PRJ039 | CL008 | 2026-01 | PMO Overhead | 1976497 | 2038012 | 3.1
BG0949 | PRJ039 | CL008 | 2026-01 | Logistics | 2785420 | 2695457 | -3.2
BG0950 | PRJ040 | CL008 | 2026-06 | Last Mile | 2283554 | 2316784 | 1.5
BG0951 | PRJ040 | CL008 | 2026-06 | Labor | 3990676 | 4074663 | 2.1
BG0952 | PRJ040 | CL008 | 2026-06 | ROW Charges | 4388942 | 4736366 | 7.9
BG0953 | PRJ040 | CL008 | 2026-05 | CapEx Hardware | 2523097 | 2625166 | 4
BG0954 | PRJ040 | CL008 | 2026-05 | Labor | 2196270 | 1880723 | -14.4
BG0955 | PRJ040 | CL008 | 2026-05 | Logistics | 2111175 | 2044723 | -3.1
BG0956 | PRJ040 | CL008 | 2026-05 | ROW Charges | 2115258 | 2351871 | 11.2
BG0957 | PRJ040 | CL008 | 2026-04 | Logistics | 4103467 | 4262380 | 3.9
BG0958 | PRJ040 | CL008 | 2026-04 | Labor | 2895883 | 2718553 | -6.1
BG0959 | PRJ040 | CL008 | 2026-04 | CapEx Hardware | 3629558 | 3397198 | -6.4
BG0960 | PRJ040 | CL008 | 2026-03 | Logistics | 852877 | 710047 | -16.7
BG0961 | PRJ040 | CL008 | 2026-03 | Labor | 3486726 | 3823070 | 9.6
BG0962 | PRJ040 | CL008 | 2026-03 | ROW Charges | 1759095 | 1814685 | 3.2
BG0963 | PRJ040 | CL008 | 2026-03 | Last Mile | 2677803 | 2793448 | 4.3
BG0964 | PRJ040 | CL008 | 2026-03 | PMO Overhead | 1443600 | 1262719 | -12.5
BG0965 | PRJ040 | CL008 | 2026-02 | PMO Overhead | 1385825 | 1173076 | -15.4
BG0966 | PRJ040 | CL008 | 2026-02 | Labor | 3165393 | 2747329 | -13.2
BG0967 | PRJ040 | CL008 | 2026-02 | Logistics | 1336376 | 1226553 | -8.2
BG0968 | PRJ040 | CL008 | 2026-02 | ROW Charges | 3871709 | 3483258 | -10
BG0969 | PRJ040 | CL008 | 2026-01 | ROW Charges | 1630304 | 1558485 | -4.4
BG0970 | PRJ040 | CL008 | 2026-01 | Logistics | 1347196 | 1197597 | -11.1
BG0971 | PRJ040 | CL008 | 2026-01 | Labor | 2463036 | 2325016 | -5.6
BG0972 | PRJ040 | CL008 | 2026-01 | PMO Overhead | 1945111 | 1635888 | -15.9

## SLA_Governance
SLAID | ProjectID | ClientID | Metric | Target_Pct | Achieved_Pct | Status | Penalty_INR | ReviewPeriod
SL001 | PRJ001 | CL001 | Go-Live TAT | 97 | 95.4 | Marginal | 198502 | Q2 FY26
SL002 | PRJ001 | CL001 | Uptime SLA | 99 | 97.7 | Marginal | 399769 | Q2 FY26
SL003 | PRJ001 | CL001 | Installation TAT | 97 | 93.2 | Breached | 257231 | Q2 FY26
SL004 | PRJ001 | CL001 | Site Survey TAT | 99 | 95.3 | Breached | 157176 | Q2 FY26
SL005 | PRJ001 | CL001 | Fault Resolution | 97 | 98.2 | Met | 0 | Q2 FY26
SL006 | PRJ002 | CL001 | Go-Live TAT | 97 | 93.7 | Breached | 331678 | Q2 FY26
SL007 | PRJ002 | CL001 | Site Survey TAT | 98 | 96.9 | Marginal | 431607 | Q2 FY26
SL008 | PRJ002 | CL001 | ROW Clearance TAT | 96 | 96.6 | Met | 0 | Q2 FY26
SL009 | PRJ002 | CL001 | Installation TAT | 95 | 96.4 | Met | 0 | Q2 FY26
SL010 | PRJ003 | CL001 | Uptime SLA | 96 | 95.5 | Marginal | 256753 | Q2 FY26
SL011 | PRJ003 | CL001 | Site Survey TAT | 95 | 94.3 | Marginal | 82654 | Q2 FY26
SL012 | PRJ003 | CL001 | Fault Resolution | 98 | 97.6 | Marginal | 118528 | Q2 FY26
SL013 | PRJ003 | CL001 | Installation TAT | 96 | 93.6 | Breached | 496123 | Q2 FY26
SL014 | PRJ004 | CL001 | Uptime SLA | 96 | 92.6 | Breached | 259846 | Q2 FY26
SL015 | PRJ004 | CL001 | Site Survey TAT | 98 | 95.5 | Breached | 252226 | Q2 FY26
SL016 | PRJ004 | CL001 | Installation TAT | 98 | 98.4 | Met | 0 | Q2 FY26
SL017 | PRJ004 | CL001 | ROW Clearance TAT | 96 | 92.6 | Breached | 414993 | Q2 FY26
SL018 | PRJ005 | CL001 | Site Survey TAT | 95 | 92 | Breached | 103620 | Q2 FY26
SL019 | PRJ005 | CL001 | ROW Clearance TAT | 97 | 94.5 | Breached | 424968 | Q2 FY26
SL020 | PRJ005 | CL001 | Uptime SLA | 98 | 98 | Met | 0 | Q2 FY26
SL021 | PRJ005 | CL001 | Installation TAT | 96 | 92.5 | Breached | 57720 | Q2 FY26
SL022 | PRJ006 | CL002 | ROW Clearance TAT | 97 | 96.1 | Marginal | 87184 | Q2 FY26
SL023 | PRJ006 | CL002 | Fault Resolution | 97 | 95.9 | Marginal | 260143 | Q2 FY26
SL024 | PRJ006 | CL002 | Site Survey TAT | 99 | 97.3 | Marginal | 375517 | Q2 FY26
SL025 | PRJ006 | CL002 | Uptime SLA | 96 | 95 | Marginal | 302903 | Q2 FY26
SL026 | PRJ006 | CL002 | Go-Live TAT | 98 | 94.4 | Breached | 159176 | Q2 FY26
SL027 | PRJ007 | CL002 | Site Survey TAT | 95 | 91.1 | Breached | 303889 | Q2 FY26
SL028 | PRJ007 | CL002 | Go-Live TAT | 98 | 94.2 | Breached | 106527 | Q2 FY26
SL029 | PRJ007 | CL002 | Uptime SLA | 95 | 95.4 | Met | 0 | Q2 FY26
SL030 | PRJ008 | CL002 | Go-Live TAT | 98 | 98.7 | Met | 0 | Q2 FY26
SL031 | PRJ008 | CL002 | Site Survey TAT | 95 | 92.9 | Breached | 144638 | Q2 FY26
SL032 | PRJ008 | CL002 | Installation TAT | 98 | 94.1 | Breached | 326772 | Q2 FY26
SL033 | PRJ008 | CL002 | ROW Clearance TAT | 97 | 95.1 | Marginal | 97723 | Q2 FY26
SL034 | PRJ008 | CL002 | Fault Resolution | 95 | 96.4 | Met | 0 | Q2 FY26
SL035 | PRJ009 | CL002 | Uptime SLA | 97 | 96.8 | Marginal | 391262 | Q2 FY26
SL036 | PRJ009 | CL002 | Installation TAT | 98 | 99.1 | Met | 0 | Q2 FY26
SL037 | PRJ009 | CL002 | Go-Live TAT | 96 | 93.3 | Breached | 68091 | Q2 FY26
SL038 | PRJ009 | CL002 | Fault Resolution | 97 | 96.5 | Marginal | 404641 | Q2 FY26
SL039 | PRJ010 | CL002 | Installation TAT | 98 | 94.4 | Breached | 269678 | Q2 FY26
SL040 | PRJ010 | CL002 | Uptime SLA | 99 | 100.1 | Met | 0 | Q2 FY26
SL041 | PRJ010 | CL002 | Go-Live TAT | 99 | 99.3 | Met | 0 | Q2 FY26
SL042 | PRJ010 | CL002 | Fault Resolution | 96 | 95.3 | Marginal | 415274 | Q2 FY26
SL043 | PRJ010 | CL002 | Site Survey TAT | 96 | 93.6 | Breached | 346838 | Q2 FY26
SL044 | PRJ011 | CL002 | Go-Live TAT | 96 | 92.3 | Breached | 308963 | Q2 FY26
SL045 | PRJ011 | CL002 | Uptime SLA | 98 | 94.3 | Breached | 193872 | Q2 FY26
SL046 | PRJ011 | CL002 | Installation TAT | 98 | 94.7 | Breached | 287389 | Q2 FY26
SL047 | PRJ011 | CL002 | ROW Clearance TAT | 96 | 95.3 | Marginal | 359943 | Q2 FY26
SL048 | PRJ011 | CL002 | Site Survey TAT | 98 | 95.3 | Breached | 61150 | Q2 FY26
SL049 | PRJ012 | CL003 | Go-Live TAT | 99 | 96.6 | Breached | 392697 | Q2 FY26
SL050 | PRJ012 | CL003 | Installation TAT | 96 | 94.9 | Marginal | 190265 | Q2 FY26
SL051 | PRJ012 | CL003 | Fault Resolution | 97 | 96.8 | Marginal | 313950 | Q2 FY26
SL052 | PRJ013 | CL003 | Uptime SLA | 99 | 99.5 | Met | 0 | Q2 FY26
SL053 | PRJ013 | CL003 | Fault Resolution | 98 | 96.4 | Marginal | 293669 | Q2 FY26
SL054 | PRJ013 | CL003 | Installation TAT | 97 | 93.2 | Breached | 306702 | Q2 FY26
SL055 | PRJ013 | CL003 | Site Survey TAT | 98 | 96 | Marginal | 364220 | Q2 FY26
SL056 | PRJ014 | CL003 | Go-Live TAT | 98 | 97.3 | Marginal | 180323 | Q2 FY26
SL057 | PRJ014 | CL003 | ROW Clearance TAT | 97 | 93.4 | Breached | 194817 | Q2 FY26
SL058 | PRJ014 | CL003 | Uptime SLA | 96 | 96.9 | Met | 0 | Q2 FY26
SL059 | PRJ015 | CL003 | Installation TAT | 96 | 94.9 | Marginal | 393325 | Q2 FY26
SL060 | PRJ015 | CL003 | ROW Clearance TAT | 97 | 94.5 | Breached | 134548 | Q2 FY26
SL061 | PRJ015 | CL003 | Go-Live TAT | 95 | 91.3 | Breached | 308957 | Q2 FY26
SL062 | PRJ015 | CL003 | Fault Resolution | 97 | 98 | Met | 0 | Q2 FY26
SL063 | PRJ015 | CL003 | Uptime SLA | 95 | 94.4 | Marginal | 478712 | Q2 FY26
SL064 | PRJ016 | CL004 | Uptime SLA | 97 | 94.5 | Breached | 197237 | Q2 FY26
SL065 | PRJ016 | CL004 | ROW Clearance TAT | 98 | 97.6 | Marginal | 229035 | Q2 FY26
SL066 | PRJ016 | CL004 | Site Survey TAT | 97 | 97.6 | Met | 0 | Q2 FY26
SL067 | PRJ017 | CL004 | ROW Clearance TAT | 96 | 96.2 | Met | 0 | Q2 FY26
SL068 | PRJ017 | CL004 | Installation TAT | 99 | 99.7 | Met | 0 | Q2 FY26
SL069 | PRJ017 | CL004 | Fault Resolution | 99 | 99.4 | Met | 0 | Q2 FY26
SL070 | PRJ018 | CL004 | Go-Live TAT | 95 | 94.7 | Marginal | 319430 | Q2 FY26
SL071 | PRJ018 | CL004 | ROW Clearance TAT | 98 | 97.3 | Marginal | 254098 | Q2 FY26
SL072 | PRJ018 | CL004 | Site Survey TAT | 95 | 96.5 | Met | 0 | Q2 FY26
SL073 | PRJ019 | CL004 | Installation TAT | 99 | 97 | Marginal | 174149 | Q2 FY26
SL074 | PRJ019 | CL004 | ROW Clearance TAT | 99 | 97.2 | Marginal | 81919 | Q2 FY26
SL075 | PRJ019 | CL004 | Uptime SLA | 95 | 92.1 | Breached | 195820 | Q2 FY26
SL076 | PRJ019 | CL004 | Go-Live TAT | 97 | 94.3 | Breached | 253345 | Q2 FY26
SL077 | PRJ020 | CL004 | Site Survey TAT | 98 | 97.9 | Marginal | 342987 | Q2 FY26
SL078 | PRJ020 | CL004 | Uptime SLA | 96 | 93.1 | Breached | 91488 | Q2 FY26
SL079 | PRJ020 | CL004 | Go-Live TAT | 96 | 95.2 | Marginal | 237886 | Q2 FY26
SL080 | PRJ020 | CL004 | Installation TAT | 98 | 99.1 | Met | 0 | Q2 FY26
SL081 | PRJ020 | CL004 | ROW Clearance TAT | 95 | 96.1 | Met | 0 | Q2 FY26
SL082 | PRJ021 | CL005 | Installation TAT | 97 | 97.1 | Met | 0 | Q2 FY26
SL083 | PRJ021 | CL005 | Uptime SLA | 99 | 98.1 | Marginal | 334704 | Q2 FY26
SL084 | PRJ021 | CL005 | Go-Live TAT | 98 | 95.8 | Breached | 346533 | Q2 FY26
SL085 | PRJ022 | CL005 | Site Survey TAT | 99 | 96.9 | Breached | 200504 | Q2 FY26
SL086 | PRJ022 | CL005 | Go-Live TAT | 98 | 96 | Marginal | 297787 | Q2 FY26
SL087 | PRJ022 | CL005 | Installation TAT | 99 | 95.7 | Breached | 457762 | Q2 FY26
SL088 | PRJ022 | CL005 | ROW Clearance TAT | 96 | 92.2 | Breached | 55327 | Q2 FY26
SL089 | PRJ023 | CL005 | Site Survey TAT | 95 | 95.8 | Met | 0 | Q2 FY26
SL090 | PRJ023 | CL005 | Installation TAT | 97 | 94.2 | Breached | 291716 | Q2 FY26
SL091 | PRJ023 | CL005 | Fault Resolution | 96 | 94.2 | Marginal | 229962 | Q2 FY26
SL092 | PRJ024 | CL005 | Site Survey TAT | 95 | 95.5 | Met | 0 | Q2 FY26
SL093 | PRJ024 | CL005 | Uptime SLA | 97 | 98 | Met | 0 | Q2 FY26
SL094 | PRJ024 | CL005 | Installation TAT | 98 | 95.4 | Breached | 131510 | Q2 FY26
SL095 | PRJ025 | CL006 | Installation TAT | 97 | 94.3 | Breached | 318765 | Q2 FY26
SL096 | PRJ025 | CL006 | Uptime SLA | 97 | 96.6 | Marginal | 178638 | Q2 FY26
SL097 | PRJ025 | CL006 | ROW Clearance TAT | 95 | 94.8 | Marginal | 460417 | Q2 FY26
SL098 | PRJ026 | CL006 | ROW Clearance TAT | 99 | 98.8 | Marginal | 161516 | Q2 FY26
SL099 | PRJ026 | CL006 | Uptime SLA | 96 | 93.2 | Breached | 262269 | Q2 FY26
SL100 | PRJ026 | CL006 | Fault Resolution | 97 | 94.4 | Breached | 147540 | Q2 FY26
SL101 | PRJ026 | CL006 | Site Survey TAT | 99 | 100.1 | Met | 0 | Q2 FY26
SL102 | PRJ027 | CL006 | Installation TAT | 99 | 97.2 | Marginal | 123757 | Q2 FY26
SL103 | PRJ027 | CL006 | Uptime SLA | 96 | 94.9 | Marginal | 330988 | Q2 FY26
SL104 | PRJ027 | CL006 | Fault Resolution | 96 | 95.1 | Marginal | 207648 | Q2 FY26
SL105 | PRJ028 | CL006 | Uptime SLA | 96 | 97.1 | Met | 0 | Q2 FY26
SL106 | PRJ028 | CL006 | Fault Resolution | 95 | 92.8 | Breached | 331972 | Q2 FY26
SL107 | PRJ028 | CL006 | Installation TAT | 96 | 94.9 | Marginal | 168677 | Q2 FY26
SL108 | PRJ028 | CL006 | ROW Clearance TAT | 95 | 92.5 | Breached | 484183 | Q2 FY26
SL109 | PRJ029 | CL006 | Fault Resolution | 97 | 96.1 | Marginal | 297460 | Q2 FY26
SL110 | PRJ029 | CL006 | ROW Clearance TAT | 99 | 95.5 | Breached | 182198 | Q2 FY26
SL111 | PRJ029 | CL006 | Site Survey TAT | 98 | 95.3 | Breached | 422706 | Q2 FY26
SL112 | PRJ030 | CL007 | Site Survey TAT | 97 | 97.2 | Met | 0 | Q2 FY26
SL113 | PRJ030 | CL007 | Installation TAT | 99 | 99.8 | Met | 0 | Q2 FY26
SL114 | PRJ030 | CL007 | Fault Resolution | 97 | 93.9 | Breached | 400304 | Q2 FY26
SL115 | PRJ030 | CL007 | ROW Clearance TAT | 95 | 91.9 | Breached | 196544 | Q2 FY26
SL116 | PRJ030 | CL007 | Uptime SLA | 96 | 96.4 | Met | 0 | Q2 FY26
SL117 | PRJ031 | CL007 | Uptime SLA | 97 | 97.2 | Met | 0 | Q2 FY26
SL118 | PRJ031 | CL007 | ROW Clearance TAT | 95 | 95.3 | Met | 0 | Q2 FY26
SL119 | PRJ031 | CL007 | Go-Live TAT | 99 | 97.7 | Marginal | 184832 | Q2 FY26
SL120 | PRJ031 | CL007 | Fault Resolution | 97 | 94.2 | Breached | 371455 | Q2 FY26
SL121 | PRJ032 | CL007 | Uptime SLA | 95 | 92.3 | Breached | 142823 | Q2 FY26
SL122 | PRJ032 | CL007 | Go-Live TAT | 97 | 96.2 | Marginal | 270305 | Q2 FY26
SL123 | PRJ032 | CL007 | ROW Clearance TAT | 98 | 95.8 | Breached | 445800 | Q2 FY26
SL124 | PRJ033 | CL007 | ROW Clearance TAT | 97 | 96.4 | Marginal | 354414 | Q2 FY26
SL125 | PRJ033 | CL007 | Go-Live TAT | 99 | 100.1 | Met | 0 | Q2 FY26
SL126 | PRJ033 | CL007 | Installation TAT | 99 | 97.5 | Marginal | 366810 | Q2 FY26
SL127 | PRJ034 | CL007 | Go-Live TAT | 98 | 98 | Met | 0 | Q2 FY26
SL128 | PRJ034 | CL007 | Installation TAT | 95 | 96 | Met | 0 | Q2 FY26
SL129 | PRJ034 | CL007 | Site Survey TAT | 96 | 96.8 | Met | 0 | Q2 FY26
SL130 | PRJ035 | CL008 | ROW Clearance TAT | 98 | 94.2 | Breached | 186392 | Q2 FY26
SL131 | PRJ035 | CL008 | Fault Resolution | 97 | 95.8 | Marginal | 52553 | Q2 FY26
SL132 | PRJ035 | CL008 | Go-Live TAT | 99 | 95.6 | Breached | 442847 | Q2 FY26
SL133 | PRJ035 | CL008 | Uptime SLA | 97 | 94.4 | Breached | 91665 | Q2 FY26
SL134 | PRJ036 | CL008 | Uptime SLA | 95 | 96.5 | Met | 0 | Q2 FY26
SL135 | PRJ036 | CL008 | Site Survey TAT | 99 | 100.5 | Met | 0 | Q2 FY26
SL136 | PRJ036 | CL008 | ROW Clearance TAT | 97 | 98.2 | Met | 0 | Q2 FY26
SL137 | PRJ037 | CL008 | Fault Resolution | 99 | 96.2 | Breached | 432414 | Q2 FY26
SL138 | PRJ037 | CL008 | Site Survey TAT | 99 | 97 | Marginal | 261242 | Q2 FY26
SL139 | PRJ037 | CL008 | Installation TAT | 99 | 96 | Breached | 428334 | Q2 FY26
SL140 | PRJ037 | CL008 | Uptime SLA | 99 | 95.7 | Breached | 263428 | Q2 FY26
SL141 | PRJ038 | CL008 | Installation TAT | 98 | 99.1 | Met | 0 | Q2 FY26
SL142 | PRJ038 | CL008 | Site Survey TAT | 95 | 94.5 | Marginal | 126924 | Q2 FY26
SL143 | PRJ038 | CL008 | Go-Live TAT | 95 | 95.3 | Met | 0 | Q2 FY26
SL144 | PRJ038 | CL008 | ROW Clearance TAT | 95 | 95.6 | Met | 0 | Q2 FY26
SL145 | PRJ038 | CL008 | Fault Resolution | 97 | 95.4 | Marginal | 108363 | Q2 FY26
SL146 | PRJ039 | CL008 | Installation TAT | 98 | 95.5 | Breached | 357914 | Q2 FY26
SL147 | PRJ039 | CL008 | Uptime SLA | 96 | 92.2 | Breached | 273943 | Q2 FY26
SL148 | PRJ039 | CL008 | Fault Resolution | 97 | 97.4 | Met | 0 | Q2 FY26
SL149 | PRJ039 | CL008 | Go-Live TAT | 95 | 93.4 | Marginal | 252654 | Q2 FY26
SL150 | PRJ040 | CL008 | Go-Live TAT | 95 | 92 | Breached | 493680 | Q2 FY26
SL151 | PRJ040 | CL008 | Installation TAT | 98 | 94.3 | Breached | 90621 | Q2 FY26
SL152 | PRJ040 | CL008 | ROW Clearance TAT | 96 | 96.3 | Met | 0 | Q2 FY26

## Weekly_Status_Log
LogID | ProjectID | ClientID | WeekEnding | RAGStatus | PctComplete | Narrative | OpenIssues | SitesLive_Week
WL0001 | PRJ001 | CL001 | 2026-06-29 | Green | 81 | Nostrum voluptates omnis ab repellendus. Ut aut soluta eaque suscipit. | 2 | 5
WL0002 | PRJ001 | CL001 | 2026-06-22 | Green | 80 | Earum non quaerat dignissimos. Magnam dolorum tenetur amet odio. | 3 | 6
WL0003 | PRJ001 | CL001 | 2026-06-15 | Green | 77 | A quo odio. | 3 | 8
WL0004 | PRJ001 | CL001 | 2026-06-08 | Red | 75 | Qui mollitia incidunt ab. | 4 | 8
WL0005 | PRJ001 | CL001 | 2026-06-01 | Red | 69 | Molestias rerum nesciunt corporis. | 0 | 6
WL0006 | PRJ001 | CL001 | 2026-05-25 | Red | 76 | Est tempore recusandae. | 3 | 0
WL0007 | PRJ001 | CL001 | 2026-05-18 | Amber | 75 | Distinctio dolorum aut quod sunt illo. | 6 | 5
WL0008 | PRJ001 | CL001 | 2026-05-11 | Red | 53 | Unde dolores cum reiciendis. Sunt ad qui ex. | 4 | 6
WL0009 | PRJ001 | CL001 | 2026-05-04 | Red | 49 | Eaque ratione autem sit similique. Dicta ullam expedita reprehenderit sit. | 2 | 1
WL0010 | PRJ001 | CL001 | 2026-04-27 | Amber | 72 | Optio id eius. | 2 | 2
WL0011 | PRJ001 | CL001 | 2026-04-20 | Red | 41 | Expedita magni perspiciatis sapiente ex. | 6 | 5
WL0012 | PRJ001 | CL001 | 2026-04-13 | Green | 37 | Soluta ea neque voluptates. | 6 | 1
WL0013 | PRJ002 | CL001 | 2026-06-29 | Amber | 40 | Pariatur fugit quibusdam cupiditate necessitatibus illo. | 4 | 6
WL0014 | PRJ002 | CL001 | 2026-06-22 | Green | 38 | Enim inventore neque omnis iure. | 3 | 5
WL0015 | PRJ002 | CL001 | 2026-06-15 | Green | 34 | Maiores recusandae vero quasi omnis. Maiores odio excepturi repellendus quibusdam. | 1 | 1
WL0016 | PRJ002 | CL001 | 2026-06-08 | Green | 28 | Rem corporis aliquid voluptates nostrum. | 4 | 0
WL0017 | PRJ002 | CL001 | 2026-06-01 | Green | 32 | Impedit occaecati deserunt possimus laudantium doloribus omnis. | 0 | 1
WL0018 | PRJ002 | CL001 | 2026-05-25 | Red | 35 | Quod dolor rem possimus. | 3 | 0
WL0019 | PRJ002 | CL001 | 2026-05-18 | Green | 34 | Nam totam commodi. Reiciendis pariatur voluptates nisi. | 3 | 7
WL0020 | PRJ002 | CL001 | 2026-05-11 | Green | 26 | Repellendus tempora incidunt tenetur ipsum culpa similique ipsum. Saepe eius quod laborum dolores. | 6 | 0
WL0021 | PRJ002 | CL001 | 2026-05-04 | Green | 16 | Quae doloremque excepturi tempora. Consequuntur doloremque possimus provident. | 1 | 5
WL0022 | PRJ002 | CL001 | 2026-04-27 | Red | 13 | Illum molestiae impedit dignissimos in temporibus. | 1 | 4
WL0023 | PRJ002 | CL001 | 2026-04-20 | Green | 20 | Sequi quisquam fugit. Velit error harum. | 3 | 4
WL0024 | PRJ002 | CL001 | 2026-04-13 | Amber | 29 | Quibusdam molestias nobis dolore dolor ipsa adipisci. Pariatur reiciendis quam saepe ullam voluptatem. | 4 | 2
WL0025 | PRJ003 | CL001 | 2026-06-29 | Amber | 57 | Numquam dolores labore. | 5 | 5
WL0026 | PRJ003 | CL001 | 2026-06-22 | Amber | 53 | Veniam iure ducimus fuga non vitae quaerat. | 2 | 3
WL0027 | PRJ003 | CL001 | 2026-06-15 | Green | 53 | Autem ad est perspiciatis vero. | 1 | 1
WL0028 | PRJ003 | CL001 | 2026-06-08 | Green | 54 | Asperiores porro occaecati aut quo. Rem recusandae natus aliquam minus optio architecto officia. | 1 | 7
WL0029 | PRJ003 | CL001 | 2026-06-01 | Amber | 45 | Reprehenderit autem vero odio repudiandae provident. | 3 | 1
WL0030 | PRJ003 | CL001 | 2026-05-25 | Red | 42 | Quasi vitae earum repellat. Quo iure repudiandae nihil eum doloribus vel. | 6 | 3
WL0031 | PRJ003 | CL001 | 2026-05-18 | Amber | 39 | Doloribus iure nostrum fugiat adipisci sed delectus. | 3 | 4
WL0032 | PRJ003 | CL001 | 2026-05-11 | Green | 50 | Reiciendis excepturi sunt praesentium eius ab. | 1 | 4
WL0033 | PRJ003 | CL001 | 2026-05-04 | Red | 49 | Dolores illo nam dolores. | 1 | 5
WL0034 | PRJ003 | CL001 | 2026-04-27 | Green | 48 | Ipsum accusantium eos illo doloribus optio fuga. Minus incidunt quia ex praesentium earum dolorum. | 5 | 3
WL0035 | PRJ003 | CL001 | 2026-04-20 | Amber | 17 | Et quia veritatis porro deleniti. | 4 | 0
WL0036 | PRJ003 | CL001 | 2026-04-13 | Red | 24 | Quam voluptate minima eligendi aut. Eos facere esse provident consectetur. | 2 | 2
WL0037 | PRJ004 | CL001 | 2026-06-29 | Red | 82 | Reprehenderit id asperiores occaecati. Corrupti repellat veniam. | 6 | 2
WL0038 | PRJ004 | CL001 | 2026-06-22 | Green | 78 | Blanditiis quisquam non ratione dolorem. | 4 | 7
WL0039 | PRJ004 | CL001 | 2026-06-15 | Red | 74 | Ipsum ipsam similique voluptatibus esse numquam. Vero aut quis numquam eaque aspernatur dolores mollitia. | 1 | 6
WL0040 | PRJ004 | CL001 | 2026-06-08 | Amber | 79 | Illum porro iusto. | 6 | 2
WL0041 | PRJ004 | CL001 | 2026-06-01 | Amber | 66 | Enim eligendi similique architecto doloremque. | 0 | 6
WL0042 | PRJ004 | CL001 | 2026-05-25 | Amber | 77 | Nihil rem dicta beatae dolore corrupti eaque consequuntur. | 0 | 4
WL0043 | PRJ004 | CL001 | 2026-05-18 | Red | 64 | Recusandae nisi repudiandae ullam. | 0 | 8
WL0044 | PRJ004 | CL001 | 2026-05-11 | Red | 68 | Iusto esse illo earum. Laudantium aspernatur aliquam inventore eum dolorum at. | 5 | 5
WL0045 | PRJ004 | CL001 | 2026-05-04 | Red | 74 | Veritatis voluptatum perferendis earum aliquam quidem iusto officiis. Delectus nesciunt odio laudantium at. | 3 | 3
WL0046 | PRJ004 | CL001 | 2026-04-27 | Amber | 55 | Ex pariatur similique ex possimus enim. Repellendus mollitia iste et eum voluptas. | 5 | 6
WL0047 | PRJ004 | CL001 | 2026-04-20 | Green | 72 | Repudiandae a sit iure amet maxime numquam. Numquam quis dignissimos molestias unde ipsa praesentium. | 0 | 2
WL0048 | PRJ004 | CL001 | 2026-04-13 | Red | 38 | Voluptate non dolores. | 6 | 7
WL0049 | PRJ005 | CL001 | 2026-06-29 | Amber | 50 | Voluptatem dolores fugit sequi illum. Quia provident repellat harum optio reprehenderit. | 2 | 6
WL0050 | PRJ005 | CL001 | 2026-06-22 | Amber | 46 | Vitae commodi vitae ex aut sapiente aut. | 2 | 7
WL0051 | PRJ005 | CL001 | 2026-06-15 | Red | 48 | Quam illum omnis. Asperiores quos eaque numquam. | 2 | 1
WL0052 | PRJ005 | CL001 | 2026-06-08 | Green | 47 | Sequi sequi similique fugit. Occaecati suscipit laborum molestiae nulla doloremque. | 2 | 6
WL0053 | PRJ005 | CL001 | 2026-06-01 | Green | 34 | Quia inventore atque odio sit. | 1 | 3
WL0054 | PRJ005 | CL001 | 2026-05-25 | Amber | 30 | Possimus temporibus aliquid recusandae. Facere inventore doloribus illum placeat. | 6 | 0
WL0055 | PRJ005 | CL001 | 2026-05-18 | Green | 38 | Cupiditate non fugit placeat. | 3 | 7
WL0056 | PRJ005 | CL001 | 2026-05-11 | Green | 43 | Corporis itaque ducimus ducimus ab rem temporibus perspiciatis. Asperiores veniam voluptates error. | 1 | 7
WL0057 | PRJ005 | CL001 | 2026-05-04 | Red | 42 | Itaque error voluptatum sequi autem. Nemo nemo voluptatibus eos voluptate omnis. | 4 | 3
WL0058 | PRJ005 | CL001 | 2026-04-27 | Amber | 14 | Natus placeat quia. | 5 | 4
WL0059 | PRJ005 | CL001 | 2026-04-20 | Amber | 30 | Quia rerum temporibus quod dolorem reiciendis dolor deleniti. | 5 | 0
WL0060 | PRJ005 | CL001 | 2026-04-13 | Red | 39 | Occaecati temporibus officia est. | 2 | 7
WL0061 | PRJ006 | CL002 | 2026-06-29 | Red | 90 | Iusto asperiores quidem dolorem. Voluptas rem facilis ratione accusamus modi. | 6 | 6
WL0062 | PRJ006 | CL002 | 2026-06-22 | Red | 87 | Perferendis perferendis nesciunt reprehenderit velit autem. Iusto nulla velit eveniet nostrum. | 4 | 3
WL0063 | PRJ006 | CL002 | 2026-06-15 | Green | 88 | Tenetur error illum consequuntur veniam esse laudantium. | 5 | 7
WL0064 | PRJ006 | CL002 | 2026-06-08 | Green | 78 | Suscipit consequatur iste perferendis quia. | 2 | 8
WL0065 | PRJ006 | CL002 | 2026-06-01 | Green | 74 | Nesciunt quas suscipit omnis rerum nulla. Adipisci fuga ipsam veritatis sequi. | 1 | 4
WL0066 | PRJ006 | CL002 | 2026-05-25 | Amber | 85 | Molestias voluptate facere id deleniti commodi. | 4 | 1
WL0067 | PRJ006 | CL002 | 2026-05-18 | Red | 66 | Optio odit nisi accusantium. Doloribus commodi natus architecto quisquam dignissimos. | 2 | 7
WL0068 | PRJ006 | CL002 | 2026-05-11 | Red | 83 | Eveniet corporis tempore a similique. | 0 | 3
WL0069 | PRJ006 | CL002 | 2026-05-04 | Green | 82 | Molestiae reiciendis beatae sint. | 6 | 2
WL0070 | PRJ006 | CL002 | 2026-04-27 | Red | 72 | Facere ratione nihil. | 3 | 8
WL0071 | PRJ006 | CL002 | 2026-04-20 | Amber | 50 | Eaque consectetur in beatae. | 4 | 7
WL0072 | PRJ006 | CL002 | 2026-04-13 | Green | 68 | Ipsum facere nisi iste dolore nostrum quas. | 5 | 5
WL0073 | PRJ007 | CL002 | 2026-06-29 | Red | 80 | At assumenda inventore quia. Repellat nam nesciunt natus eveniet commodi. | 3 | 1
WL0074 | PRJ007 | CL002 | 2026-06-22 | Amber | 79 | Sint quam voluptas nobis expedita neque. Culpa laboriosam sed expedita nam. | 0 | 4
WL0075 | PRJ007 | CL002 | 2026-06-15 | Red | 78 | Nemo rem sapiente voluptate repellendus. | 6 | 1
WL0076 | PRJ007 | CL002 | 2026-06-08 | Green | 74 | Ad ut repudiandae eaque debitis praesentium est. Expedita delectus corporis omnis architecto qui. | 4 | 3
WL0077 | PRJ007 | CL002 | 2026-06-01 | Green | 68 | Quia dolor in exercitationem. | 0 | 1
WL0078 | PRJ007 | CL002 | 2026-05-25 | Green | 65 | Quam quod necessitatibus assumenda amet. Quidem amet aspernatur ipsam. | 4 | 5
WL0079 | PRJ007 | CL002 | 2026-05-18 | Amber | 68 | Non impedit dolor maiores exercitationem beatae perspiciatis. Laborum pariatur aliquid hic nobis ab error distinctio. | 6 | 8
WL0080 | PRJ007 | CL002 | 2026-05-11 | Red | 66 | Enim blanditiis libero inventore consectetur. | 4 | 1
WL0081 | PRJ007 | CL002 | 2026-05-04 | Green | 72 | Magnam rerum rem asperiores similique. Ipsa itaque aspernatur. | 4 | 3
WL0082 | PRJ007 | CL002 | 2026-04-27 | Red | 62 | Inventore illo odit enim illo vitae cupiditate. Itaque porro facere ipsa autem ipsa id aspernatur. | 2 | 2
WL0083 | PRJ007 | CL002 | 2026-04-20 | Red | 70 | Dolore quod asperiores odio minus deserunt. | 5 | 1
WL0084 | PRJ007 | CL002 | 2026-04-13 | Green | 36 | Quas reprehenderit repellendus dolores corporis deserunt. Corrupti quis asperiores veritatis occaecati iure natus neque. | 2 | 2
WL0085 | PRJ008 | CL002 | 2026-06-29 | Red | 59 | Non facilis ullam harum quo perspiciatis amet. Officia aperiam atque perspiciatis eligendi quam omnis temporibus. | 2 | 2
WL0086 | PRJ008 | CL002 | 2026-06-22 | Green | 56 | Aspernatur optio totam est omnis optio. | 6 | 1
WL0087 | PRJ008 | CL002 | 2026-06-15 | Green | 53 | Quae assumenda nam officia eveniet consectetur praesentium veniam. | 3 | 2
WL0088 | PRJ008 | CL002 | 2026-06-08 | Green | 50 | Officia incidunt facere facere. Veritatis exercitationem quisquam deleniti. | 1 | 0
WL0089 | PRJ008 | CL002 | 2026-06-01 | Red | 55 | Aspernatur sapiente aut quo. | 2 | 6
WL0090 | PRJ008 | CL002 | 2026-05-25 | Green | 44 | Optio soluta nulla. Fugiat cum rerum quo repellat cumque ipsa illum. | 1 | 6
WL0091 | PRJ008 | CL002 | 2026-05-18 | Amber | 41 | Nostrum quibusdam quos doloremque dolores vitae. | 3 | 1
WL0092 | PRJ008 | CL002 | 2026-05-11 | Green | 45 | Facilis veniam voluptates iure eligendi. Magnam in cum dicta non sit. | 1 | 3
WL0093 | PRJ008 | CL002 | 2026-05-04 | Amber | 27 | Soluta mollitia aut sapiente sed eligendi quis. | 0 | 4
WL0094 | PRJ008 | CL002 | 2026-04-27 | Green | 32 | Temporibus corporis ipsa veniam dolore iste expedita. | 3 | 8
WL0095 | PRJ008 | CL002 | 2026-04-20 | Amber | 49 | Amet magnam doloremque voluptatum fugiat adipisci. | 3 | 0
WL0096 | PRJ008 | CL002 | 2026-04-13 | Amber | 37 | Recusandae consequuntur enim rerum possimus consequuntur. | 0 | 4
WL0097 | PRJ009 | CL002 | 2026-06-29 | Green | 83 | Dolores omnis aut neque quidem consequatur. | 2 | 7
WL0098 | PRJ009 | CL002 | 2026-06-22 | Red | 81 | Excepturi odit rerum placeat voluptatem laboriosam delectus. Aperiam quod itaque eos. | 2 | 3
WL0099 | PRJ009 | CL002 | 2026-06-15 | Red | 79 | Suscipit et est id repellendus. | 0 | 1
WL0100 | PRJ009 | CL002 | 2026-06-08 | Green | 71 | Alias officia enim similique aliquid. Earum reiciendis ipsa id ipsam vero. | 3 | 1
WL0101 | PRJ009 | CL002 | 2026-06-01 | Red | 75 | Libero libero unde maxime. Quas aspernatur nobis reprehenderit. | 3 | 2
WL0102 | PRJ009 | CL002 | 2026-05-25 | Amber | 68 | Eum aspernatur optio esse nobis. Cumque ipsam ipsum quas tenetur nostrum. | 5 | 4
WL0103 | PRJ009 | CL002 | 2026-05-18 | Red | 59 | Odit recusandae animi perferendis illo. Reiciendis perspiciatis veritatis consequuntur non quos alias. | 4 | 4
WL0104 | PRJ009 | CL002 | 2026-05-11 | Red | 55 | Quod facilis fugit necessitatibus non. | 6 | 1
WL0105 | PRJ009 | CL002 | 2026-05-04 | Green | 59 | Fuga quis nemo minus id officiis. Vero ad delectus maxime totam. | 6 | 2
WL0106 | PRJ009 | CL002 | 2026-04-27 | Amber | 65 | Quod provident dolor nostrum possimus. | 5 | 6
WL0107 | PRJ009 | CL002 | 2026-04-20 | Red | 53 | Commodi sequi iste tempore ipsum. Repellat voluptas voluptates pariatur. | 0 | 2
WL0108 | PRJ009 | CL002 | 2026-04-13 | Amber | 72 | Molestiae tempora sed quae unde odit recusandae. | 0 | 1
WL0109 | PRJ010 | CL002 | 2026-06-29 | Green | 53 | Commodi esse modi magnam cumque. Culpa omnis quam non sapiente natus repudiandae adipisci. | 5 | 6
WL0110 | PRJ010 | CL002 | 2026-06-22 | Amber | 52 | Eaque distinctio nemo nulla adipisci suscipit molestias. | 1 | 7
WL0111 | PRJ010 | CL002 | 2026-06-15 | Red | 45 | Doloribus rem illo iste porro culpa impedit. | 4 | 6
WL0112 | PRJ010 | CL002 | 2026-06-08 | Amber | 44 | Excepturi corporis similique eum voluptates. Voluptate consectetur fuga natus eum iure. | 1 | 2
WL0113 | PRJ010 | CL002 | 2026-06-01 | Green | 45 | Dolorum atque enim fugit nostrum dolorum sint. | 4 | 3
WL0114 | PRJ010 | CL002 | 2026-05-25 | Red | 48 | Ut quam deleniti cum voluptatum iure. | 6 | 8
WL0115 | PRJ010 | CL002 | 2026-05-18 | Amber | 35 | Ad veniam magnam vitae dolor explicabo amet. | 2 | 3
WL0116 | PRJ010 | CL002 | 2026-05-11 | Amber | 32 | Sunt omnis iusto modi sed inventore sunt quas. Facilis id necessitatibus deserunt mollitia asperiores. | 4 | 1
WL0117 | PRJ010 | CL002 | 2026-05-04 | Green | 37 | Quisquam eius voluptatibus perspiciatis blanditiis voluptate hic. Nam facilis corporis nobis illo aliquam. | 0 | 8
WL0118 | PRJ010 | CL002 | 2026-04-27 | Green | 26 | Quae rem maxime corrupti. | 0 | 2
WL0119 | PRJ010 | CL002 | 2026-04-20 | Amber | 33 | Eveniet nostrum cum voluptatibus. Nisi magni magni laudantium natus. | 2 | 0
WL0120 | PRJ010 | CL002 | 2026-04-13 | Red | 31 | Fuga perferendis voluptatem. Esse tempore sit occaecati nisi eaque omnis voluptas. | 6 | 3
WL0121 | PRJ011 | CL002 | 2026-06-29 | Amber | 57 | Provident maxime natus voluptatum. Minima et cupiditate totam exercitationem explicabo quo. | 5 | 0
WL0122 | PRJ011 | CL002 | 2026-06-22 | Amber | 54 | Laborum vero eius error velit voluptatem quo provident. | 1 | 6
WL0123 | PRJ011 | CL002 | 2026-06-15 | Green | 55 | Laboriosam natus vel quam enim nemo. Fugit voluptatem repellendus veritatis rem enim enim. | 2 | 0
WL0124 | PRJ011 | CL002 | 2026-06-08 | Green | 45 | Unde omnis quibusdam distinctio repudiandae earum. | 0 | 6
WL0125 | PRJ011 | CL002 | 2026-06-01 | Red | 45 | Consequatur nulla nesciunt doloribus pariatur. Dolorem doloremque aut ex iusto perspiciatis consequuntur. | 2 | 5
WL0126 | PRJ011 | CL002 | 2026-05-25 | Amber | 37 | Illum vel soluta labore. Quidem enim eligendi animi quisquam. | 0 | 8
WL0127 | PRJ011 | CL002 | 2026-05-18 | Amber | 33 | Modi quam vel totam cupiditate. Ut alias saepe ratione. | 4 | 0
WL0128 | PRJ011 | CL002 | 2026-05-11 | Amber | 36 | Soluta ab necessitatibus autem voluptatem. | 5 | 7
WL0129 | PRJ011 | CL002 | 2026-05-04 | Amber | 49 | Voluptatibus molestiae laudantium vel sed iusto deserunt. | 6 | 5
WL0130 | PRJ011 | CL002 | 2026-04-27 | Red | 48 | Cum itaque ducimus delectus qui ratione. | 0 | 3
WL0131 | PRJ011 | CL002 | 2026-04-20 | Green | 47 | Cupiditate sequi tempore repudiandae maiores. Id atque voluptatem labore. | 1 | 1
WL0132 | PRJ011 | CL002 | 2026-04-13 | Amber | 13 | Ea doloremque quidem. | 1 | 2
WL0133 | PRJ012 | CL003 | 2026-06-29 | Green | 94 | Corrupti quibusdam non impedit molestias iusto modi. | 2 | 6
WL0134 | PRJ012 | CL003 | 2026-06-22 | Red | 90 | Perspiciatis nisi ratione minima minus. | 2 | 1
WL0135 | PRJ012 | CL003 | 2026-06-15 | Green | 90 | Totam beatae repudiandae temporibus. Nemo corrupti eveniet maxime blanditiis. | 6 | 8
WL0136 | PRJ012 | CL003 | 2026-06-08 | Green | 85 | Laborum tempore ipsum animi consequatur impedit natus nam. | 5 | 8
WL0137 | PRJ012 | CL003 | 2026-06-01 | Green | 90 | Id repellendus quia. | 2 | 2
WL0138 | PRJ012 | CL003 | 2026-05-25 | Green | 84 | Aliquid exercitationem aperiam voluptatibus. Voluptates iusto enim debitis. | 5 | 7
WL0139 | PRJ012 | CL003 | 2026-05-18 | Red | 70 | Fugiat tempora ipsum totam fugiat aspernatur. | 0 | 0
WL0140 | PRJ012 | CL003 | 2026-05-11 | Amber | 87 | Officiis expedita debitis modi. Consectetur voluptatem rerum quidem voluptatem iure quaerat. | 2 | 4
WL0141 | PRJ012 | CL003 | 2026-05-04 | Red | 62 | Fugit dolorem itaque culpa deleniti soluta quisquam. Repellat in quisquam. | 2 | 1
WL0142 | PRJ012 | CL003 | 2026-04-27 | Green | 67 | Dignissimos aut alias nisi praesentium. | 6 | 6
WL0143 | PRJ012 | CL003 | 2026-04-20 | Amber | 84 | Qui illo doloremque dolor sint. | 6 | 6
WL0144 | PRJ012 | CL003 | 2026-04-13 | Amber | 50 | Magnam enim repellendus quasi. | 0 | 3
WL0145 | PRJ013 | CL003 | 2026-06-29 | Red | 62 | Amet fugiat non aliquam asperiores. Quam nam laboriosam sit ex vero accusamus vel. | 2 | 6
WL0146 | PRJ013 | CL003 | 2026-06-22 | Amber | 59 | Totam possimus provident id dolores eum eligendi. | 6 | 0
WL0147 | PRJ013 | CL003 | 2026-06-15 | Red | 56 | Officiis est facere sunt iure rem quam. Totam fuga impedit natus dolore corporis. | 1 | 4
WL0148 | PRJ013 | CL003 | 2026-06-08 | Amber | 50 | Vel neque impedit corrupti ex fugit rerum. | 0 | 7
WL0149 | PRJ013 | CL003 | 2026-06-01 | Amber | 50 | Omnis placeat ducimus reprehenderit vitae odit laudantium. Quasi explicabo consequuntur molestias. | 5 | 0
WL0150 | PRJ013 | CL003 | 2026-05-25 | Red | 57 | Voluptatibus vero minima saepe asperiores repellendus aliquid. | 2 | 0
WL0151 | PRJ013 | CL003 | 2026-05-18 | Red | 38 | Consequuntur occaecati architecto corrupti dolor iste. | 1 | 2
WL0152 | PRJ013 | CL003 | 2026-05-11 | Green | 55 | Odit ut totam omnis accusamus minus illum accusantium. | 1 | 2
WL0153 | PRJ013 | CL003 | 2026-05-04 | Red | 30 | Voluptate accusantium repellat perferendis rem tenetur autem. | 3 | 4
WL0154 | PRJ013 | CL003 | 2026-04-27 | Amber | 26 | Corrupti deleniti minima repellendus eaque id fuga. | 5 | 3
WL0155 | PRJ013 | CL003 | 2026-04-20 | Red | 22 | Natus voluptatibus dolorem placeat sed officiis similique. Atque fugit mollitia. | 0 | 1
WL0156 | PRJ013 | CL003 | 2026-04-13 | Amber | 29 | Praesentium assumenda sapiente. | 0 | 2
WL0157 | PRJ014 | CL003 | 2026-06-29 | Green | 81 | Adipisci earum voluptatibus laudantium explicabo velit. Delectus nesciunt fugit quo eos doloribus. | 1 | 7
WL0158 | PRJ014 | CL003 | 2026-06-22 | Green | 78 | Eaque fugit quos culpa. | 6 | 5
WL0159 | PRJ014 | CL003 | 2026-06-15 | Green | 79 | Facere at velit ipsam quis aut. Deleniti ipsum mollitia illum. | 4 | 4
WL0160 | PRJ014 | CL003 | 2026-06-08 | Red | 78 | Explicabo at nisi eveniet. | 6 | 7
WL0161 | PRJ014 | CL003 | 2026-06-01 | Green | 65 | Eos harum assumenda. Temporibus voluptatem nemo cumque fugit consequuntur error. | 2 | 1
WL0162 | PRJ014 | CL003 | 2026-05-25 | Red | 61 | Aperiam ipsa in laborum. Facere velit quam libero. | 1 | 1
WL0163 | PRJ014 | CL003 | 2026-05-18 | Red | 63 | Itaque consequatur ab id sapiente. Rem eveniet ex repellendus similique voluptate. | 2 | 0
WL0164 | PRJ014 | CL003 | 2026-05-11 | Amber | 60 | Eum veniam dicta et vitae. | 0 | 7
WL0165 | PRJ014 | CL003 | 2026-05-04 | Amber | 65 | Quasi odio voluptas quos eveniet. Repellendus hic beatae natus nihil. | 5 | 7
WL0166 | PRJ014 | CL003 | 2026-04-27 | Amber | 63 | Placeat mollitia veritatis iure. Ipsa eos possimus reprehenderit recusandae. | 4 | 1
WL0167 | PRJ014 | CL003 | 2026-04-20 | Green | 51 | Consequuntur esse dolorum culpa incidunt fugiat ipsum. Laboriosam id magni ullam porro molestiae ratione facere. | 1 | 7
WL0168 | PRJ014 | CL003 | 2026-04-13 | Red | 37 | Odit assumenda quisquam omnis explicabo officia aliquid voluptates. Vitae ex recusandae autem atque dolore. | 3 | 0
WL0169 | PRJ015 | CL003 | 2026-06-29 | Amber | 75 | Cum nam vero doloremque illo delectus odit. | 5 | 7
WL0170 | PRJ015 | CL003 | 2026-06-22 | Green | 74 | Adipisci nostrum deserunt nihil harum provident. Eius provident recusandae neque reiciendis. | 2 | 5
WL0171 | PRJ015 | CL003 | 2026-06-15 | Red | 73 | Facilis deserunt beatae perferendis. Minus odit nisi nostrum nesciunt expedita sapiente. | 4 | 4
WL0172 | PRJ015 | CL003 | 2026-06-08 | Red | 66 | Repellendus provident error nostrum. Perferendis est dolores blanditiis. | 3 | 5
WL0173 | PRJ015 | CL003 | 2026-06-01 | Red | 59 | Magni in consequuntur fugit. Laborum modi ullam ut. | 2 | 7
WL0174 | PRJ015 | CL003 | 2026-05-25 | Amber | 55 | Cumque enim deleniti sapiente nulla sint veritatis. | 2 | 8
WL0175 | PRJ015 | CL003 | 2026-05-18 | Red | 63 | Deserunt fugit natus officiis. Placeat impedit saepe laborum assumenda adipisci. | 1 | 2
WL0176 | PRJ015 | CL003 | 2026-05-11 | Green | 54 | Adipisci dolore enim quos natus. | 3 | 7
WL0177 | PRJ015 | CL003 | 2026-05-04 | Amber | 51 | Magni nemo eaque molestiae voluptatibus molestiae quidem. Molestias voluptatibus aut rerum quibusdam error. | 6 | 6
WL0178 | PRJ015 | CL003 | 2026-04-27 | Amber | 39 | Ea similique assumenda sint blanditiis repellat distinctio. | 3 | 2
WL0179 | PRJ015 | CL003 | 2026-04-20 | Green | 35 | Similique nostrum incidunt nulla quos repellendus. Necessitatibus minus nisi cumque. | 3 | 0
WL0180 | PRJ015 | CL003 | 2026-04-13 | Green | 42 | Nemo veritatis maiores tempore repellendus. | 3 | 2
WL0181 | PRJ016 | CL004 | 2026-06-29 | Red | 92 | Sed recusandae id voluptas repudiandae libero. Repudiandae excepturi neque necessitatibus laborum exercitationem. | 2 | 7
WL0182 | PRJ016 | CL004 | 2026-06-22 | Red | 88 | Aut quos itaque. | 3 | 8
WL0183 | PRJ016 | CL004 | 2026-06-15 | Red | 88 | Ipsam a vero dicta. | 3 | 5
WL0184 | PRJ016 | CL004 | 2026-06-08 | Green | 80 | Culpa ut earum omnis dolorum. | 2 | 8
WL0185 | PRJ016 | CL004 | 2026-06-01 | Red | 88 | Amet numquam quas quidem. Omnis provident a labore consequatur dolorem. | 2 | 4
WL0186 | PRJ016 | CL004 | 2026-05-25 | Amber | 77 | Ab exercitationem blanditiis. Possimus labore dolorem at rem aut. | 4 | 8
WL0187 | PRJ016 | CL004 | 2026-05-18 | Green | 74 | Consequatur quo quidem consequatur voluptatibus. Architecto natus nostrum cum. | 2 | 3
WL0188 | PRJ016 | CL004 | 2026-05-11 | Red | 78 | Occaecati corrupti illum placeat similique. Tempore consequuntur commodi quas. | 2 | 4
WL0189 | PRJ016 | CL004 | 2026-05-04 | Green | 68 | Et consequuntur eius assumenda mollitia nobis. Eligendi velit ad sed soluta dignissimos non deleniti. | 4 | 6
WL0190 | PRJ016 | CL004 | 2026-04-27 | Amber | 65 | Officia quos recusandae dolores harum. Libero nisi minus voluptate voluptates. | 4 | 6
WL0191 | PRJ016 | CL004 | 2026-04-20 | Red | 72 | Harum saepe in molestias. Quis veritatis quo accusantium. | 6 | 2
WL0192 | PRJ016 | CL004 | 2026-04-13 | Red | 59 | Ea aliquam aperiam. | 1 | 5
WL0193 | PRJ017 | CL004 | 2026-06-29 | Red | 86 | Doloribus unde blanditiis nostrum. | 5 | 7
WL0194 | PRJ017 | CL004 | 2026-06-22 | Red | 85 | Pariatur omnis cupiditate accusamus consequatur. | 1 | 0
WL0195 | PRJ017 | CL004 | 2026-06-15 | Amber | 78 | Libero expedita maxime reprehenderit. | 4 | 5
WL0196 | PRJ017 | CL004 | 2026-06-08 | Green | 74 | Fuga quibusdam sit quasi. | 1 | 2
WL0197 | PRJ017 | CL004 | 2026-06-01 | Green | 74 | Ex inventore minima. | 5 | 6
WL0198 | PRJ017 | CL004 | 2026-05-25 | Amber | 71 | Occaecati libero magni animi similique cumque culpa. | 4 | 3
WL0199 | PRJ017 | CL004 | 2026-05-18 | Red | 62 | Perferendis beatae qui a similique accusamus aliquid. | 5 | 5
WL0200 | PRJ017 | CL004 | 2026-05-11 | Green | 58 | Ullam debitis vero alias rem quae. Dolore dolorum totam eum repudiandae nemo. | 3 | 3
WL0201 | PRJ017 | CL004 | 2026-05-04 | Green | 62 | Perferendis amet dolore maiores aliquid id soluta. | 0 | 5
WL0202 | PRJ017 | CL004 | 2026-04-27 | Amber | 50 | Eveniet mollitia ab dicta natus. | 6 | 3
WL0203 | PRJ017 | CL004 | 2026-04-20 | Red | 56 | Doloribus fuga voluptas voluptatum quod quasi molestias recusandae. | 3 | 3
WL0204 | PRJ017 | CL004 | 2026-04-13 | Amber | 75 | Ut ad molestiae. | 5 | 1
WL0205 | PRJ018 | CL004 | 2026-06-29 | Green | 61 | Quod nesciunt culpa cum. | 4 | 3
WL0206 | PRJ018 | CL004 | 2026-06-22 | Green | 60 | Illo modi vitae dignissimos est eaque. At rem esse provident. | 5 | 3
WL0207 | PRJ018 | CL004 | 2026-06-15 | Red | 55 | Dolor sequi corporis. Voluptas id aliquid error reprehenderit. | 6 | 0
WL0208 | PRJ018 | CL004 | 2026-06-08 | Green | 58 | Veritatis sequi nam. | 3 | 8
WL0209 | PRJ018 | CL004 | 2026-06-01 | Green | 49 | Atque aut recusandae commodi aperiam. Consectetur reprehenderit fuga occaecati officia. | 0 | 4
WL0210 | PRJ018 | CL004 | 2026-05-25 | Red | 56 | Ea repellat accusantium aperiam temporibus ipsam consectetur temporibus. Commodi velit amet unde inventore quam. | 6 | 5
WL0211 | PRJ018 | CL004 | 2026-05-18 | Green | 37 | Fugit incidunt explicabo. Eius ipsum corrupti nostrum. | 3 | 2
WL0212 | PRJ018 | CL004 | 2026-05-11 | Red | 47 | Officia libero sunt laboriosam assumenda. Consequatur dicta suscipit minima occaecati reiciendis. | 6 | 7
WL0213 | PRJ018 | CL004 | 2026-05-04 | Red | 29 | Quos facere molestias laborum totam magnam. | 5 | 2
WL0214 | PRJ018 | CL004 | 2026-04-27 | Green | 34 | Debitis eum dolor tempore quod. Repellat iusto facere nesciunt. | 1 | 4
WL0215 | PRJ018 | CL004 | 2026-04-20 | Amber | 51 | Aut omnis eaque repellendus. | 3 | 7
WL0216 | PRJ018 | CL004 | 2026-04-13 | Amber | 28 | Nemo voluptatem harum vel voluptatibus. | 3 | 2
WL0217 | PRJ019 | CL004 | 2026-06-29 | Red | 83 | Accusantium nesciunt totam quo. Similique vero fuga velit hic aut error. | 6 | 5
WL0218 | PRJ019 | CL004 | 2026-06-22 | Green | 79 | Quasi ipsa odit laborum. | 0 | 5
WL0219 | PRJ019 | CL004 | 2026-06-15 | Green | 79 | Provident natus suscipit nostrum. Dolore nihil cupiditate esse porro consectetur. | 6 | 1
WL0220 | PRJ019 | CL004 | 2026-06-08 | Green | 77 | Hic voluptatibus vitae adipisci nobis ullam voluptas. | 5 | 2
WL0221 | PRJ019 | CL004 | 2026-06-01 | Red | 71 | Aut libero ex aspernatur expedita eum odio. | 5 | 0
WL0222 | PRJ019 | CL004 | 2026-05-25 | Green | 68 | Ipsum eaque dolorum architecto ducimus autem. | 1 | 7
WL0223 | PRJ019 | CL004 | 2026-05-18 | Amber | 71 | Harum quasi voluptas. | 0 | 3
WL0224 | PRJ019 | CL004 | 2026-05-11 | Green | 55 | Sunt expedita fugiat repudiandae ratione neque quis. Cum asperiores sapiente eos eum. | 3 | 1
WL0225 | PRJ019 | CL004 | 2026-05-04 | Green | 51 | Exercitationem suscipit cum asperiores. | 0 | 1
WL0226 | PRJ019 | CL004 | 2026-04-27 | Green | 47 | Nisi nostrum laboriosam adipisci velit cumque. | 0 | 2
WL0227 | PRJ019 | CL004 | 2026-04-20 | Red | 63 | Amet ex voluptate illum. Quam quas eaque eligendi dolores amet nemo. | 0 | 3
WL0228 | PRJ019 | CL004 | 2026-04-13 | Green | 72 | Amet a assumenda reprehenderit. Nobis dicta ad cupiditate eos aspernatur sapiente est. | 6 | 7
WL0229 | PRJ020 | CL004 | 2026-06-29 | Amber | 42 | Perspiciatis nulla blanditiis quidem cupiditate voluptates voluptas. Commodi incidunt voluptates ipsa voluptatum. | 1 | 6
WL0230 | PRJ020 | CL004 | 2026-06-22 | Amber | 40 | Rerum ducimus tenetur totam. Assumenda nam mollitia sequi. | 5 | 6
WL0231 | PRJ020 | CL004 | 2026-06-15 | Green | 38 | Totam accusamus praesentium nesciunt quos beatae corrupti. Nihil quis velit unde natus aut enim. | 5 | 1
WL0232 | PRJ020 | CL004 | 2026-06-08 | Green | 39 | Soluta eaque omnis nemo labore cupiditate. Corporis non possimus aliquam suscipit ex. | 1 | 8
WL0233 | PRJ020 | CL004 | 2026-06-01 | Amber | 34 | Quia ullam tempore. | 5 | 7
WL0234 | PRJ020 | CL004 | 2026-05-25 | Amber | 32 | Repellendus esse eligendi laudantium possimus atque. | 3 | 5
WL0235 | PRJ020 | CL004 | 2026-05-18 | Red | 18 | Error quia quo eum. | 6 | 8
WL0236 | PRJ020 | CL004 | 2026-05-11 | Green | 14 | Officia deleniti distinctio reprehenderit qui quis sint reprehenderit. Recusandae aperiam quae illo quos minima necessitatibus. | 4 | 5
WL0237 | PRJ020 | CL004 | 2026-05-04 | Red | 26 | Soluta dicta animi alias amet. | 2 | 4
WL0238 | PRJ020 | CL004 | 2026-04-27 | Red | 24 | Earum reprehenderit magnam odio commodi. Doloribus laborum ipsum. | 2 | 2
WL0239 | PRJ020 | CL004 | 2026-04-20 | Green | 22 | Mollitia exercitationem saepe ea rerum at ad amet. Quod dolor dolore dolore dignissimos officiis maiores. | 4 | 5
WL0240 | PRJ020 | CL004 | 2026-04-13 | Amber | 10 | Tenetur officia nobis ab dolorum rem esse. | 6 | 4
WL0241 | PRJ021 | CL005 | 2026-06-29 | Green | 76 | Provident nemo deleniti quas dolore modi quos temporibus. | 1 | 6
WL0242 | PRJ021 | CL005 | 2026-06-22 | Amber | 74 | Error cumque omnis nam eos iusto qui. Quis delectus perspiciatis excepturi at explicabo quia. | 3 | 0
WL0243 | PRJ021 | CL005 | 2026-06-15 | Green | 72 | Ratione ex ea eos sed iusto. | 3 | 2
WL0244 | PRJ021 | CL005 | 2026-06-08 | Green | 70 | Velit architecto suscipit magnam sint fugit error amet. Consequuntur dicta illum necessitatibus. | 3 | 5
WL0245 | PRJ021 | CL005 | 2026-06-01 | Amber | 68 | Et quaerat quod laborum. Voluptates et animi iste distinctio quo nemo culpa. | 0 | 4
WL0246 | PRJ021 | CL005 | 2026-05-25 | Amber | 56 | Nostrum odio illo vitae. | 0 | 2
WL0247 | PRJ021 | CL005 | 2026-05-18 | Green | 52 | Alias dicta fuga. Tempora quidem minus. | 0 | 1
WL0248 | PRJ021 | CL005 | 2026-05-11 | Amber | 62 | Occaecati dolorum possimus. | 1 | 8
WL0249 | PRJ021 | CL005 | 2026-05-04 | Green | 60 | Consectetur fugit nihil cumque reprehenderit. Veniam iste maxime minima inventore. | 1 | 6
WL0250 | PRJ021 | CL005 | 2026-04-27 | Red | 58 | Voluptatum laudantium quibusdam cumque tenetur repellat. | 0 | 2
WL0251 | PRJ021 | CL005 | 2026-04-20 | Green | 46 | Dolore voluptates distinctio accusantium magnam. | 4 | 1
WL0252 | PRJ021 | CL005 | 2026-04-13 | Red | 32 | Quae recusandae fugiat odit quo numquam. | 5 | 0
WL0253 | PRJ022 | CL005 | 2026-06-29 | Green | 41 | Cum molestias tenetur porro laboriosam. A perferendis tenetur saepe pariatur. | 2 | 6
WL0254 | PRJ022 | CL005 | 2026-06-22 | Amber | 37 | Quod asperiores quam temporibus. | 0 | 2
WL0255 | PRJ022 | CL005 | 2026-06-15 | Red | 37 | Voluptates eos iure aut cupiditate aliquam enim. | 4 | 0
WL0256 | PRJ022 | CL005 | 2026-06-08 | Green | 35 | Qui atque quidem aliquid sequi optio. Eveniet tempora veritatis eaque. | 5 | 5
WL0257 | PRJ022 | CL005 | 2026-06-01 | Green | 33 | Repellendus delectus id vitae earum harum. | 6 | 1
WL0258 | PRJ022 | CL005 | 2026-05-25 | Green | 21 | Officiis reiciendis beatae possimus animi velit. Aut tenetur laboriosam necessitatibus. | 2 | 6
WL0259 | PRJ022 | CL005 | 2026-05-18 | Amber | 17 | Nostrum quod nostrum similique. Laboriosam laborum suscipit ipsam. | 1 | 5
WL0260 | PRJ022 | CL005 | 2026-05-11 | Red | 20 | Omnis accusamus sit minima quia. | 5 | 7
WL0261 | PRJ022 | CL005 | 2026-05-04 | Green | 10 | Voluptate pariatur excepturi minima praesentium. Inventore quas laboriosam optio. | 6 | 1
WL0262 | PRJ022 | CL005 | 2026-04-27 | Red | 23 | Saepe nam voluptates amet. Magni iusto libero cumque. | 0 | 4
WL0263 | PRJ022 | CL005 | 2026-04-20 | Red | 11 | Dolores voluptas amet dolore officia illo. Aspernatur ipsam nemo at libero. | 4 | 4
WL0264 | PRJ022 | CL005 | 2026-04-13 | Green | 10 | Voluptatem quia accusantium illo. Nam a at. | 5 | 5
WL0265 | PRJ023 | CL005 | 2026-06-29 | Red | 39 | Autem impedit unde saepe nihil quo. | 1 | 6
WL0266 | PRJ023 | CL005 | 2026-06-22 | Amber | 37 | Omnis vero consequatur libero minus aliquid vel. Laboriosam magni ullam debitis neque quas consectetur harum. | 3 | 1
WL0267 | PRJ023 | CL005 | 2026-06-15 | Green | 33 | Sunt magnam harum voluptatem totam quis earum vitae. Iste consequatur impedit praesentium quibusdam. | 4 | 6
WL0268 | PRJ023 | CL005 | 2026-06-08 | Red | 33 | Similique quae vel odio dicta numquam enim. | 1 | 5
WL0269 | PRJ023 | CL005 | 2026-06-01 | Green | 35 | Voluptatem officiis vero magnam. Quae quis natus nesciunt velit quae. | 5 | 0
WL0270 | PRJ023 | CL005 | 2026-05-25 | Red | 24 | Soluta in accusamus autem fugit. Pariatur dicta quibusdam. | 4 | 5
WL0271 | PRJ023 | CL005 | 2026-05-18 | Amber | 33 | Placeat corporis aperiam quos dignissimos. | 2 | 4
WL0272 | PRJ023 | CL005 | 2026-05-11 | Amber | 25 | Facere iste nulla. Sint quia natus dolores quos reiciendis enim. | 0 | 5
WL0273 | PRJ023 | CL005 | 2026-05-04 | Amber | 10 | Harum vero voluptate est mollitia accusamus. | 1 | 7
WL0274 | PRJ023 | CL005 | 2026-04-27 | Red | 21 | Nulla quos sit rerum tenetur. | 2 | 5
WL0275 | PRJ023 | CL005 | 2026-04-20 | Green | 29 | Molestias nobis quod vitae eos debitis placeat deleniti. Quasi blanditiis aliquam eius. | 3 | 4
WL0276 | PRJ023 | CL005 | 2026-04-13 | Green | 10 | Cum sapiente ab iure. | 5 | 0
WL0277 | PRJ024 | CL005 | 2026-06-29 | Amber | 66 | Doloribus aliquam suscipit fugit recusandae beatae ducimus quam. Tenetur reprehenderit fugiat. | 6 | 1
WL0278 | PRJ024 | CL005 | 2026-06-22 | Amber | 62 | Laborum eos officiis eum aspernatur atque voluptas. Modi occaecati distinctio occaecati distinctio placeat saepe. | 1 | 8
WL0279 | PRJ024 | CL005 | 2026-06-15 | Amber | 60 | Repudiandae soluta qui ipsa repellendus asperiores placeat. | 5 | 1
WL0280 | PRJ024 | CL005 | 2026-06-08 | Green | 63 | Quaerat alias asperiores debitis dolorum architecto reprehenderit. | 3 | 7
WL0281 | PRJ024 | CL005 | 2026-06-01 | Amber | 62 | Harum occaecati inventore accusantium perferendis modi. | 1 | 3
WL0282 | PRJ024 | CL005 | 2026-05-25 | Red | 51 | Quidem nesciunt praesentium asperiores. Autem ratione error assumenda quisquam ipsa hic. | 6 | 7
WL0283 | PRJ024 | CL005 | 2026-05-18 | Red | 60 | Culpa dolore quia reiciendis sed eos odio. | 2 | 5
WL0284 | PRJ024 | CL005 | 2026-05-11 | Amber | 52 | Vero accusamus soluta consequuntur aliquam nemo. | 3 | 0
WL0285 | PRJ024 | CL005 | 2026-05-04 | Red | 34 | Molestias assumenda distinctio qui quas distinctio temporibus. Consequuntur delectus nulla dolorum beatae perferendis necessitatibus. | 1 | 3
WL0286 | PRJ024 | CL005 | 2026-04-27 | Red | 30 | Itaque mollitia enim architecto atque quas laborum. | 0 | 2
WL0287 | PRJ024 | CL005 | 2026-04-20 | Amber | 36 | Consectetur omnis aut nulla tempore et. Eveniet optio possimus corrupti necessitatibus repellat vero. | 3 | 5
WL0288 | PRJ024 | CL005 | 2026-04-13 | Amber | 22 | Et quos quae. | 6 | 7
WL0289 | PRJ025 | CL006 | 2026-06-29 | Red | 63 | Dolore quo quasi enim iure magni. Facilis ab dolores vitae voluptatem placeat. | 3 | 8
WL0290 | PRJ025 | CL006 | 2026-06-22 | Green | 59 | Ipsum debitis veniam optio. Quasi laboriosam facere dolor. | 3 | 8
WL0291 | PRJ025 | CL006 | 2026-06-15 | Green | 55 | Aperiam fuga aliquam dignissimos tenetur. Harum ullam sunt aliquam officiis aut. | 5 | 6
WL0292 | PRJ025 | CL006 | 2026-06-08 | Red | 54 | Rerum ea molestias cupiditate officiis. Nesciunt tempore aspernatur dolorum voluptate dolore. | 5 | 3
WL0293 | PRJ025 | CL006 | 2026-06-01 | Red | 59 | Repellendus exercitationem recusandae suscipit ab sunt. Cumque aspernatur officia distinctio deleniti facere. | 2 | 8
WL0294 | PRJ025 | CL006 | 2026-05-25 | Red | 58 | Impedit ex beatae perferendis laboriosam. | 0 | 6
WL0295 | PRJ025 | CL006 | 2026-05-18 | Red | 45 | Officia illum doloribus consectetur. Cum occaecati aliquam nemo animi ea debitis vero. | 6 | 2
WL0296 | PRJ025 | CL006 | 2026-05-11 | Red | 56 | Odit soluta quas reprehenderit veniam dolor non. Sint cupiditate rerum nobis recusandae reprehenderit delectus. | 2 | 0
WL0297 | PRJ025 | CL006 | 2026-05-04 | Green | 31 | Cumque placeat ullam nisi architecto. Harum autem dicta similique magnam in. | 6 | 0
WL0298 | PRJ025 | CL006 | 2026-04-27 | Green | 27 | Atque labore nostrum aliquam quos magnam blanditiis laboriosam. | 0 | 2
WL0299 | PRJ025 | CL006 | 2026-04-20 | Amber | 33 | Molestiae a vel perspiciatis inventore in soluta possimus. | 0 | 7
WL0300 | PRJ025 | CL006 | 2026-04-13 | Green | 41 | Vel laboriosam quisquam expedita rem. Atque consequatur labore doloremque similique eligendi soluta. | 0 | 8
WL0301 | PRJ026 | CL006 | 2026-06-29 | Amber | 92 | Ipsum praesentium cum dolor id. | 6 | 2
WL0302 | PRJ026 | CL006 | 2026-06-22 | Amber | 88 | Nostrum placeat amet harum odio rem reprehenderit. Unde ipsa aperiam dolore aspernatur alias fugit. | 3 | 2
WL0303 | PRJ026 | CL006 | 2026-06-15 | Amber | 88 | Omnis enim vitae animi quo cupiditate laudantium ab. Enim alias nobis maiores doloremque cumque alias. | 3 | 7
WL0304 | PRJ026 | CL006 | 2026-06-08 | Green | 86 | Voluptate assumenda eius. | 1 | 8
WL0305 | PRJ026 | CL006 | 2026-06-01 | Amber | 84 | Pariatur illo dicta accusamus provident ullam. Eligendi rerum totam expedita vitae eius non. | 0 | 2
WL0306 | PRJ026 | CL006 | 2026-05-25 | Green | 82 | Ut nemo ea illum autem asperiores eos. | 0 | 1
WL0307 | PRJ026 | CL006 | 2026-05-18 | Amber | 86 | Vero soluta repellat nemo possimus vitae natus. | 0 | 6
WL0308 | PRJ026 | CL006 | 2026-05-11 | Red | 78 | Vero itaque itaque nesciunt ad blanditiis. | 1 | 2
WL0309 | PRJ026 | CL006 | 2026-05-04 | Red | 68 | Odio voluptatibus perspiciatis dolorem et veritatis. | 2 | 2
WL0310 | PRJ026 | CL006 | 2026-04-27 | Green | 65 | Ab rerum dolorum at perferendis reprehenderit asperiores. Labore explicabo tempora eaque. | 3 | 1
WL0311 | PRJ026 | CL006 | 2026-04-20 | Red | 72 | Qui doloremque doloribus eaque dolorem rerum saepe. | 4 | 0
WL0312 | PRJ026 | CL006 | 2026-04-13 | Red | 48 | Quod blanditiis aspernatur veritatis. Nostrum quisquam molestiae aliquam laboriosam nulla laudantium. | 2 | 5
WL0313 | PRJ027 | CL006 | 2026-06-29 | Amber | 56 | Nostrum ea molestias dolores iusto nostrum. Delectus incidunt in quibusdam facilis id. | 1 | 1
WL0314 | PRJ027 | CL006 | 2026-06-22 | Amber | 53 | Necessitatibus voluptatem placeat repellendus. Rem nam sequi deserunt reiciendis. | 2 | 6
WL0315 | PRJ027 | CL006 | 2026-06-15 | Red | 54 | Rem debitis libero voluptatum sed maxime quam. | 2 | 7
WL0316 | PRJ027 | CL006 | 2026-06-08 | Amber | 50 | Dolorum similique aliquid aut cum. Repellendus labore occaecati ipsum ex. | 1 | 5
WL0317 | PRJ027 | CL006 | 2026-06-01 | Green | 52 | Nam ut ducimus accusantium commodi sint. Dicta nemo officiis cupiditate quos explicabo perferendis laborum. | 2 | 7
WL0318 | PRJ027 | CL006 | 2026-05-25 | Red | 36 | Fugit enim occaecati corporis. Odit unde in nostrum. | 4 | 5
WL0319 | PRJ027 | CL006 | 2026-05-18 | Green | 50 | Aspernatur exercitationem et officiis. Non hic suscipit quos vel. | 1 | 0
WL0320 | PRJ027 | CL006 | 2026-05-11 | Amber | 49 | Vitae impedit delectus ad quas optio velit. Distinctio id atque vel. | 4 | 5
WL0321 | PRJ027 | CL006 | 2026-05-04 | Amber | 40 | Amet quo minima voluptatum aut nulla assumenda. Est dolorum eligendi occaecati consectetur saepe. | 3 | 7
WL0322 | PRJ027 | CL006 | 2026-04-27 | Red | 20 | Optio similique eveniet. | 3 | 1
WL0323 | PRJ027 | CL006 | 2026-04-20 | Red | 36 | Voluptate molestiae earum ipsam voluptas possimus debitis. Itaque quibusdam soluta ipsa odit modi tenetur laboriosam. | 0 | 8
WL0324 | PRJ027 | CL006 | 2026-04-13 | Amber | 45 | Ipsam facilis ea esse. | 0 | 1
WL0325 | PRJ028 | CL006 | 2026-06-29 | Green | 54 | Dolores quisquam tenetur rem placeat eligendi quia repellat. Deleniti architecto consequatur beatae iste iste. | 3 | 2
WL0326 | PRJ028 | CL006 | 2026-06-22 | Red | 53 | Deleniti accusantium amet modi delectus aut eaque. Quas doloremque corrupti laudantium exercitationem est. | 3 | 2
WL0327 | PRJ028 | CL006 | 2026-06-15 | Green | 46 | Iure recusandae ex sapiente veritatis animi. Architecto iusto deleniti sapiente repellendus repudiandae. | 2 | 2
WL0328 | PRJ028 | CL006 | 2026-06-08 | Red | 48 | Harum voluptate doloribus voluptatum dicta. | 6 | 2
WL0329 | PRJ028 | CL006 | 2026-06-01 | Green | 42 | Pariatur dignissimos harum vero vel culpa quas. | 0 | 6
WL0330 | PRJ028 | CL006 | 2026-05-25 | Amber | 44 | Commodi laboriosam error facere amet pariatur voluptate. Odio eveniet cumque eius blanditiis. | 0 | 5
WL0331 | PRJ028 | CL006 | 2026-05-18 | Red | 42 | Voluptas neque porro. | 4 | 2
WL0332 | PRJ028 | CL006 | 2026-05-11 | Amber | 26 | Fuga at culpa at. Excepturi voluptas quis animi explicabo culpa modi autem. | 4 | 3
WL0333 | PRJ028 | CL006 | 2026-05-04 | Amber | 46 | Et nam officia expedita tempora. Accusantium fugiat quam dolorum aliquam. | 3 | 3
WL0334 | PRJ028 | CL006 | 2026-04-27 | Green | 27 | Eos possimus deleniti delectus expedita quasi eius. Totam mollitia architecto culpa eos ea facilis a. | 6 | 0
WL0335 | PRJ028 | CL006 | 2026-04-20 | Green | 44 | Quasi sunt nulla facilis nulla eum. Omnis molestiae harum minima. | 6 | 3
WL0336 | PRJ028 | CL006 | 2026-04-13 | Red | 32 | Culpa eligendi illum eum atque omnis aliquam. Debitis adipisci autem deleniti. | 4 | 0
WL0337 | PRJ029 | CL006 | 2026-06-29 | Red | 46 | Reprehenderit eaque aliquam architecto. Aspernatur dolor maxime aut doloremque. | 5 | 6
WL0338 | PRJ029 | CL006 | 2026-06-22 | Amber | 44 | Deserunt omnis necessitatibus veniam nam. Impedit autem odit facere itaque pariatur sunt. | 6 | 2
WL0339 | PRJ029 | CL006 | 2026-06-15 | Green | 42 | Mollitia magnam omnis modi. | 0 | 7
WL0340 | PRJ029 | CL006 | 2026-06-08 | Red | 40 | Ut temporibus mollitia voluptatum sapiente impedit. Repudiandae eum dolores molestias fugiat mollitia. | 6 | 6
WL0341 | PRJ029 | CL006 | 2026-06-01 | Amber | 34 | Vitae ipsum id quas voluptatem nisi. | 1 | 8
WL0342 | PRJ029 | CL006 | 2026-05-25 | Green | 31 | Voluptatibus error error dolore. Accusantium reprehenderit porro eius mollitia nam. | 3 | 8
WL0343 | PRJ029 | CL006 | 2026-05-18 | Amber | 28 | Atque itaque culpa eaque. Dolorum ducimus error necessitatibus necessitatibus dolor aspernatur eveniet. | 6 | 2
WL0344 | PRJ029 | CL006 | 2026-05-11 | Red | 18 | Laborum tempore praesentium reprehenderit. Nisi error quasi nemo. | 5 | 2
WL0345 | PRJ029 | CL006 | 2026-05-04 | Amber | 38 | Ullam ex sunt ipsa. | 0 | 0
WL0346 | PRJ029 | CL006 | 2026-04-27 | Red | 28 | Quibusdam sed ut odio odio. | 0 | 8
WL0347 | PRJ029 | CL006 | 2026-04-20 | Amber | 36 | Minima eum natus eveniet possimus. | 0 | 4
WL0348 | PRJ029 | CL006 | 2026-04-13 | Red | 10 | Perferendis voluptatum voluptas. | 6 | 0
WL0349 | PRJ030 | CL007 | 2026-06-29 | Amber | 84 | Nisi ad esse voluptates nulla voluptatibus. Numquam ipsam unde doloremque placeat culpa. | 5 | 4
WL0350 | PRJ030 | CL007 | 2026-06-22 | Amber | 80 | Qui doloribus numquam corporis. | 2 | 1
WL0351 | PRJ030 | CL007 | 2026-06-15 | Green | 76 | Exercitationem rem esse. | 5 | 1
WL0352 | PRJ030 | CL007 | 2026-06-08 | Amber | 72 | Ex qui distinctio. Minima ea laboriosam quas consequuntur praesentium accusantium. | 2 | 0
WL0353 | PRJ030 | CL007 | 2026-06-01 | Red | 72 | Aliquam cumque eligendi ratione nulla amet omnis. Architecto optio optio. | 0 | 4
WL0354 | PRJ030 | CL007 | 2026-05-25 | Amber | 69 | Accusantium sint officiis doloremque. Magni quae temporibus laborum nisi at. | 1 | 8
WL0355 | PRJ030 | CL007 | 2026-05-18 | Red | 78 | Vitae natus quae aliquam ullam esse laudantium. | 1 | 7
WL0356 | PRJ030 | CL007 | 2026-05-11 | Green | 63 | Expedita explicabo numquam. | 2 | 2
WL0357 | PRJ030 | CL007 | 2026-05-04 | Amber | 60 | Eius aperiam ducimus harum voluptatum voluptatibus velit. | 0 | 0
WL0358 | PRJ030 | CL007 | 2026-04-27 | Red | 66 | Corrupti tempore omnis assumenda fugit. | 3 | 1
WL0359 | PRJ030 | CL007 | 2026-04-20 | Red | 74 | Placeat impedit nemo incidunt est non ipsum consectetur. Neque placeat dicta consequuntur. | 0 | 3
WL0360 | PRJ030 | CL007 | 2026-04-13 | Amber | 40 | Inventore tenetur quo omnis. Totam et nam veniam blanditiis et sunt. | 2 | 4
WL0361 | PRJ031 | CL007 | 2026-06-29 | Amber | 75 | Veniam dolore perferendis dicta dignissimos. | 6 | 5
WL0362 | PRJ031 | CL007 | 2026-06-22 | Green | 72 | Sint laudantium eveniet itaque doloribus illo. | 6 | 6
WL0363 | PRJ031 | CL007 | 2026-06-15 | Amber | 73 | Quasi fugit est nostrum quia nisi minima soluta. | 4 | 6
WL0364 | PRJ031 | CL007 | 2026-06-08 | Amber | 63 | Autem itaque soluta soluta doloribus modi voluptates. | 1 | 0
WL0365 | PRJ031 | CL007 | 2026-06-01 | Green | 67 | Harum quisquam vitae deleniti ipsa sunt quo. | 2 | 8
WL0366 | PRJ031 | CL007 | 2026-05-25 | Green | 70 | Cumque eos ullam porro temporibus iure officia. | 6 | 1
WL0367 | PRJ031 | CL007 | 2026-05-18 | Amber | 63 | Beatae quod vel possimus consequatur impedit iste. | 6 | 0
WL0368 | PRJ031 | CL007 | 2026-05-11 | Green | 54 | Nihil quae dicta iste dolorum porro tenetur. | 4 | 7
WL0369 | PRJ031 | CL007 | 2026-05-04 | Red | 59 | At provident odio assumenda. | 1 | 4
WL0370 | PRJ031 | CL007 | 2026-04-27 | Green | 57 | Nostrum cum mollitia aliquam cupiditate excepturi sit. Cum corporis quisquam amet. | 4 | 4
WL0371 | PRJ031 | CL007 | 2026-04-20 | Red | 55 | Quas vero enim debitis tempore. | 2 | 2
WL0372 | PRJ031 | CL007 | 2026-04-13 | Amber | 31 | Numquam ducimus itaque. | 3 | 8
WL0373 | PRJ032 | CL007 | 2026-06-29 | Amber | 62 | Quis sapiente aperiam iusto. Possimus earum minima minima. | 6 | 5
WL0374 | PRJ032 | CL007 | 2026-06-22 | Green | 61 | Animi necessitatibus voluptatem minus assumenda quam non ratione. | 2 | 8
WL0375 | PRJ032 | CL007 | 2026-06-15 | Amber | 60 | Non et minima voluptatum explicabo consectetur. | 4 | 4
WL0376 | PRJ032 | CL007 | 2026-06-08 | Red | 50 | Maxime occaecati laudantium debitis non provident voluptatem. Blanditiis iure reiciendis. | 5 | 3
WL0377 | PRJ032 | CL007 | 2026-06-01 | Green | 58 | Voluptatum impedit ex nam odit accusamus dicta eligendi. | 2 | 6
WL0378 | PRJ032 | CL007 | 2026-05-25 | Green | 47 | Error mollitia quisquam beatae ex. | 6 | 4
WL0379 | PRJ032 | CL007 | 2026-05-18 | Green | 38 | Nulla adipisci cupiditate ex excepturi perferendis totam. Officia laboriosam occaecati. | 0 | 7
WL0380 | PRJ032 | CL007 | 2026-05-11 | Red | 41 | Iure repellendus unde animi maxime natus. Nam accusantium neque ex totam recusandae. | 6 | 4
WL0381 | PRJ032 | CL007 | 2026-05-04 | Amber | 30 | Eligendi adipisci voluptates occaecati. | 6 | 1
WL0382 | PRJ032 | CL007 | 2026-04-27 | Green | 53 | Non deleniti blanditiis quos est similique quae. | 0 | 7
WL0383 | PRJ032 | CL007 | 2026-04-20 | Red | 22 | Assumenda soluta fuga repudiandae esse minima. | 3 | 4
WL0384 | PRJ032 | CL007 | 2026-04-13 | Amber | 29 | Fugiat alias dicta at. | 2 | 5
WL0385 | PRJ033 | CL007 | 2026-06-29 | Green | 67 | Ut porro nisi assumenda iure. | 4 | 1
WL0386 | PRJ033 | CL007 | 2026-06-22 | Red | 65 | Maxime omnis est neque. | 3 | 4
WL0387 | PRJ033 | CL007 | 2026-06-15 | Green | 63 | Eum deserunt eius eum ipsam. | 6 | 6
WL0388 | PRJ033 | CL007 | 2026-06-08 | Amber | 64 | Corrupti earum accusamus numquam maiores. | 0 | 6
WL0389 | PRJ033 | CL007 | 2026-06-01 | Green | 59 | Expedita et consequuntur provident eligendi doloribus architecto. | 1 | 6
WL0390 | PRJ033 | CL007 | 2026-05-25 | Amber | 52 | Molestiae amet adipisci temporibus amet fugit. Incidunt debitis nisi nihil. | 1 | 1
WL0391 | PRJ033 | CL007 | 2026-05-18 | Red | 61 | Explicabo ex dicta quis repellat aspernatur ullam quisquam. Consectetur repellat ullam iusto iste placeat quae. | 2 | 7
WL0392 | PRJ033 | CL007 | 2026-05-11 | Amber | 53 | Doloremque dolore similique nulla totam hic praesentium. Ratione sunt iste adipisci labore expedita. | 0 | 0
WL0393 | PRJ033 | CL007 | 2026-05-04 | Green | 59 | Eligendi expedita nemo magni. Repellendus reiciendis eveniet officiis recusandae minus. | 4 | 6
WL0394 | PRJ033 | CL007 | 2026-04-27 | Red | 40 | Impedit nulla molestias voluptate fugit exercitationem repellendus nihil. Necessitatibus exercitationem possimus cupiditate pariatur qui. | 2 | 6
WL0395 | PRJ033 | CL007 | 2026-04-20 | Green | 47 | Beatae nisi eveniet atque ipsum est illo. Autem repellendus quo fugiat laudantium optio at repellendus. | 2 | 3
WL0396 | PRJ033 | CL007 | 2026-04-13 | Amber | 56 | Quidem optio iste. Harum neque deserunt placeat et. | 3 | 4
WL0397 | PRJ034 | CL007 | 2026-06-29 | Red | 53 | Consequatur rem similique tempora. | 5 | 0
WL0398 | PRJ034 | CL007 | 2026-06-22 | Amber | 49 | Numquam iste incidunt reprehenderit harum dolorem. Non neque sed dolores magnam illum. | 2 | 4
WL0399 | PRJ034 | CL007 | 2026-06-15 | Amber | 47 | Facilis voluptatem necessitatibus provident beatae laboriosam porro. Quas minima similique quibusdam. | 1 | 0
WL0400 | PRJ034 | CL007 | 2026-06-08 | Amber | 44 | Maxime minima nostrum doloribus occaecati optio pariatur. | 2 | 5
WL0401 | PRJ034 | CL007 | 2026-06-01 | Amber | 41 | Est amet exercitationem quod iusto maiores iusto quasi. Explicabo voluptate eos cumque possimus nisi. | 0 | 2
WL0402 | PRJ034 | CL007 | 2026-05-25 | Amber | 43 | Ea occaecati neque nemo omnis eos qui. | 5 | 5
WL0403 | PRJ034 | CL007 | 2026-05-18 | Amber | 47 | Laborum consectetur asperiores quos dolorum. | 3 | 7
WL0404 | PRJ034 | CL007 | 2026-05-11 | Amber | 32 | Eius ducimus qui nobis tenetur. Omnis fuga cupiditate quos. | 6 | 3
WL0405 | PRJ034 | CL007 | 2026-05-04 | Green | 37 | Debitis minima alias voluptates voluptas nisi reprehenderit. | 3 | 6
WL0406 | PRJ034 | CL007 | 2026-04-27 | Green | 44 | Quo dolores ipsam odit distinctio quasi. Amet eaque reprehenderit amet iure labore. | 2 | 6
WL0407 | PRJ034 | CL007 | 2026-04-20 | Green | 43 | Doloremque placeat harum ea minus ipsa enim. Fugit et minus veritatis atque minus explicabo. | 4 | 2
WL0408 | PRJ034 | CL007 | 2026-04-13 | Red | 31 | Ullam similique ex eaque atque omnis hic quo. Quasi nihil deserunt excepturi porro. | 3 | 6
WL0409 | PRJ035 | CL008 | 2026-06-29 | Amber | 95 | Odit provident blanditiis sequi consectetur omnis tempore necessitatibus. | 1 | 8
WL0410 | PRJ035 | CL008 | 2026-06-22 | Green | 92 | Possimus ducimus iure vel. | 5 | 3
WL0411 | PRJ035 | CL008 | 2026-06-15 | Red | 87 | Quo porro pariatur quo ducimus. Eius aperiam harum voluptatum. | 0 | 1
WL0412 | PRJ035 | CL008 | 2026-06-08 | Amber | 83 | Debitis architecto voluptatem dicta hic. | 0 | 1
WL0413 | PRJ035 | CL008 | 2026-06-01 | Amber | 79 | Corporis quisquam dolor officia. Quaerat aut asperiores necessitatibus dolorum ipsum. | 0 | 3
WL0414 | PRJ035 | CL008 | 2026-05-25 | Amber | 90 | Officiis a alias hic. Praesentium temporibus nemo maiores. | 0 | 8
WL0415 | PRJ035 | CL008 | 2026-05-18 | Red | 83 | Ipsa sapiente quos quos molestiae a veritatis. Commodi modi voluptatibus ex esse animi voluptatum. | 3 | 0
WL0416 | PRJ035 | CL008 | 2026-05-11 | Amber | 74 | Modi vero aspernatur itaque quisquam officia. | 2 | 4
WL0417 | PRJ035 | CL008 | 2026-05-04 | Amber | 71 | Aliquam fugit deleniti possimus tempore occaecati facere. | 2 | 2
WL0418 | PRJ035 | CL008 | 2026-04-27 | Red | 59 | Ipsa deleniti alias ad voluptatum dolores harum recusandae. | 4 | 3
WL0419 | PRJ035 | CL008 | 2026-04-20 | Amber | 65 | Modi rerum ipsum voluptatum alias animi ratione. | 6 | 3
WL0420 | PRJ035 | CL008 | 2026-04-13 | Amber | 51 | Blanditiis rem pariatur itaque perspiciatis soluta. | 0 | 4
WL0421 | PRJ036 | CL008 | 2026-06-29 | Amber | 52 | Eum vitae distinctio aliquid. Excepturi blanditiis consequuntur impedit. | 3 | 1
WL0422 | PRJ036 | CL008 | 2026-06-22 | Green | 51 | Cumque doloribus neque consequatur ratione odio fugiat. Accusamus laborum ab debitis. | 0 | 8
WL0423 | PRJ036 | CL008 | 2026-06-15 | Amber | 50 | Suscipit impedit rem quo possimus dignissimos odit minima. | 6 | 1
WL0424 | PRJ036 | CL008 | 2026-06-08 | Red | 49 | Vel nostrum alias debitis libero. Occaecati quos expedita a. | 0 | 2
WL0425 | PRJ036 | CL008 | 2026-06-01 | Red | 44 | Blanditiis minus atque facere quis. | 6 | 3
WL0426 | PRJ036 | CL008 | 2026-05-25 | Green | 47 | Dolor quo omnis eius deserunt recusandae placeat. Libero cum ullam amet facilis distinctio dolorum. | 1 | 5
WL0427 | PRJ036 | CL008 | 2026-05-18 | Amber | 28 | Aliquam qui unde debitis quos laborum blanditiis. Quam nihil eveniet dicta perspiciatis. | 4 | 2
WL0428 | PRJ036 | CL008 | 2026-05-11 | Green | 24 | Quod eveniet atque qui sit. Tempora asperiores nesciunt amet ipsa dolor. | 6 | 2
WL0429 | PRJ036 | CL008 | 2026-05-04 | Green | 44 | Debitis fuga itaque deserunt facere earum excepturi. Porro animi consequatur. | 6 | 4
WL0430 | PRJ036 | CL008 | 2026-04-27 | Red | 25 | In quis dolore eos culpa recusandae veritatis. Neque mollitia dolorem illum. | 4 | 6
WL0431 | PRJ036 | CL008 | 2026-04-20 | Red | 42 | Similique dolor labore iure accusamus incidunt sit. Eveniet neque tempora nihil corrupti. | 6 | 0
WL0432 | PRJ036 | CL008 | 2026-04-13 | Red | 10 | In aliquid voluptatibus. Alias minus laboriosam reiciendis reprehenderit iste dolores. | 5 | 1
WL0433 | PRJ037 | CL008 | 2026-06-29 | Red | 53 | Sunt quasi amet veniam perferendis suscipit beatae facilis. | 2 | 8
WL0434 | PRJ037 | CL008 | 2026-06-22 | Green | 50 | Facilis cupiditate nam. Natus quo consequuntur ex. | 6 | 0
WL0435 | PRJ037 | CL008 | 2026-06-15 | Amber | 49 | Officiis qui quibusdam sit. Quidem quis eum tempore magnam. | 3 | 3
WL0436 | PRJ037 | CL008 | 2026-06-08 | Green | 44 | Amet fuga iste magnam repudiandae. Quae perspiciatis minus eos numquam reiciendis veniam. | 0 | 5
WL0437 | PRJ037 | CL008 | 2026-06-01 | Green | 37 | Tempora itaque aspernatur tempore enim. | 1 | 2
WL0438 | PRJ037 | CL008 | 2026-05-25 | Red | 38 | Cum beatae corporis corrupti. | 6 | 0
WL0439 | PRJ037 | CL008 | 2026-05-18 | Amber | 47 | Veritatis ad impedit placeat ut labore in. | 0 | 2
WL0440 | PRJ037 | CL008 | 2026-05-11 | Amber | 32 | Deleniti ad reiciendis rerum maxime. | 4 | 3
WL0441 | PRJ037 | CL008 | 2026-05-04 | Red | 21 | Neque omnis ratione laborum pariatur minus. Ipsum esse consequatur ratione cupiditate ea laborum. | 5 | 6
WL0442 | PRJ037 | CL008 | 2026-04-27 | Green | 35 | Corporis eligendi vero. | 2 | 6
WL0443 | PRJ037 | CL008 | 2026-04-20 | Amber | 23 | Quae eligendi voluptate saepe. Cum blanditiis voluptatibus nemo. | 5 | 6
WL0444 | PRJ037 | CL008 | 2026-04-13 | Amber | 10 | Fuga dignissimos provident pariatur voluptatem. Fuga molestiae cum error. | 6 | 6
WL0445 | PRJ038 | CL008 | 2026-06-29 | Green | 92 | Nulla dolore facere eveniet non deserunt. | 5 | 2
WL0446 | PRJ038 | CL008 | 2026-06-22 | Red | 90 | Quos quisquam deserunt assumenda sed. Voluptate hic laudantium nobis. | 6 | 3
WL0447 | PRJ038 | CL008 | 2026-06-15 | Red | 84 | Tenetur facere corporis sequi. Harum accusamus exercitationem est ipsum natus. | 0 | 7
WL0448 | PRJ038 | CL008 | 2026-06-08 | Red | 83 | Qui impedit ipsam cum quas tempore. | 3 | 8
WL0449 | PRJ038 | CL008 | 2026-06-01 | Green | 76 | Saepe nisi corporis esse. Voluptates architecto vero quidem at illum totam. | 3 | 7
WL0450 | PRJ038 | CL008 | 2026-05-25 | Amber | 87 | Nam quae quidem consequatur. Rerum enim laudantium reprehenderit. | 2 | 1
WL0451 | PRJ038 | CL008 | 2026-05-18 | Amber | 80 | Esse nam iure ad a ea veritatis rerum. | 5 | 3
WL0452 | PRJ038 | CL008 | 2026-05-11 | Green | 85 | Officiis tempora impedit laudantium. Adipisci quisquam laudantium voluptas nisi. | 0 | 5
WL0453 | PRJ038 | CL008 | 2026-05-04 | Red | 68 | Laboriosam ipsa ducimus placeat voluptate repellendus fuga quasi. Sapiente cum animi. | 6 | 1
WL0454 | PRJ038 | CL008 | 2026-04-27 | Amber | 74 | Soluta consequatur cum earum in totam explicabo. Eos odit asperiores deserunt occaecati. | 1 | 1
WL0455 | PRJ038 | CL008 | 2026-04-20 | Amber | 72 | Quibusdam molestiae sit repudiandae placeat error placeat porro. | 3 | 4
WL0456 | PRJ038 | CL008 | 2026-04-13 | Red | 48 | Neque reprehenderit accusamus maxime fuga laborum excepturi. | 0 | 8
WL0457 | PRJ039 | CL008 | 2026-06-29 | Red | 59 | Minima voluptas cupiditate esse quia blanditiis consectetur possimus. Esse distinctio voluptatem incidunt quis. | 3 | 4
WL0458 | PRJ039 | CL008 | 2026-06-22 | Red | 55 | Accusantium laborum inventore deserunt. | 1 | 7
WL0459 | PRJ039 | CL008 | 2026-06-15 | Amber | 53 | Nihil iusto tenetur aliquam error ab atque. | 6 | 3
WL0460 | PRJ039 | CL008 | 2026-06-08 | Amber | 47 | Dignissimos temporibus delectus expedita at sapiente velit veniam. | 4 | 3
WL0461 | PRJ039 | CL008 | 2026-06-01 | Red | 47 | Cum magnam quas doloribus necessitatibus aut. Quis minus quaerat vitae cupiditate quidem a quas. | 5 | 4
WL0462 | PRJ039 | CL008 | 2026-05-25 | Red | 39 | Sed labore praesentium delectus perferendis autem rerum. | 0 | 1
WL0463 | PRJ039 | CL008 | 2026-05-18 | Green | 53 | Distinctio dolorem beatae voluptates commodi beatae. Libero facere enim quam. | 0 | 4
WL0464 | PRJ039 | CL008 | 2026-05-11 | Green | 31 | Laudantium harum itaque quasi porro sapiente. | 1 | 5
WL0465 | PRJ039 | CL008 | 2026-05-04 | Amber | 35 | Illum voluptates incidunt sequi tempora rem vel. | 5 | 3
WL0466 | PRJ039 | CL008 | 2026-04-27 | Red | 23 | Accusamus perferendis perferendis id. Omnis assumenda corporis id nihil aut unde. | 0 | 1
WL0467 | PRJ039 | CL008 | 2026-04-20 | Amber | 49 | Facilis dicta dicta sapiente. | 4 | 3
WL0468 | PRJ039 | CL008 | 2026-04-13 | Green | 26 | Doloremque incidunt libero quisquam. Nisi quidem reiciendis velit explicabo pariatur veniam voluptates. | 3 | 0
WL0469 | PRJ040 | CL008 | 2026-06-29 | Green | 95 | Sequi ipsam alias debitis optio quod. Laudantium consequatur quaerat laborum. | 4 | 8
WL0470 | PRJ040 | CL008 | 2026-06-22 | Green | 94 | Perferendis optio placeat nemo labore sequi magni. | 0 | 3
WL0471 | PRJ040 | CL008 | 2026-06-15 | Amber | 91 | Libero voluptas nulla explicabo voluptate. Aperiam nihil consectetur facilis repellat nesciunt. | 2 | 3
WL0472 | PRJ040 | CL008 | 2026-06-08 | Red | 89 | Fugit incidunt voluptatibus illum animi doloribus. Officia nihil tenetur aperiam esse. | 1 | 5
WL0473 | PRJ040 | CL008 | 2026-06-01 | Green | 91 | Accusantium eveniet itaque sint. Maiores in accusantium iusto ad et necessitatibus. | 5 | 4
WL0474 | PRJ040 | CL008 | 2026-05-25 | Red | 75 | Atque laborum porro dignissimos libero repellat pariatur. Nostrum facilis ipsa libero. | 1 | 8
WL0475 | PRJ040 | CL008 | 2026-05-18 | Amber | 89 | Distinctio eaque error nemo rem numquam vero. | 3 | 6
WL0476 | PRJ040 | CL008 | 2026-05-11 | Red | 74 | Nihil earum necessitatibus minus. Distinctio recusandae officiis error rem inventore. | 1 | 0
WL0477 | PRJ040 | CL008 | 2026-05-04 | Red | 63 | Dicta illo numquam iste quis debitis. Occaecati maiores delectus. | 4 | 3
WL0478 | PRJ040 | CL008 | 2026-04-27 | Red | 68 | Optio reprehenderit vel eaque odit. Sequi tenetur vel quas animi dicta iure dolores. | 6 | 7
WL0479 | PRJ040 | CL008 | 2026-04-20 | Amber | 55 | Illum similique tenetur odio sapiente eaque. | 5 | 0
WL0480 | PRJ040 | CL008 | 2026-04-13 | Green | 51 | Ducimus nobis illo beatae. | 4 | 2

## Date_Dimension
Date | Year | Month | MonthName | Quarter | FY | WeekNum | IsWeekend
2024-01-01 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | FALSE
2024-01-02 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | FALSE
2024-01-03 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | FALSE
2024-01-04 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | FALSE
2024-01-05 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | FALSE
2024-01-06 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | TRUE
2024-01-07 | 2024 | 1 | January | Q1 | FY2023-24 | 1 | TRUE
2024-01-08 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | FALSE
2024-01-09 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | FALSE
2024-01-10 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | FALSE
2024-01-11 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | FALSE
2024-01-12 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | FALSE
2024-01-13 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | TRUE
2024-01-14 | 2024 | 1 | January | Q1 | FY2023-24 | 2 | TRUE
2024-01-15 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | FALSE
2024-01-16 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | FALSE
2024-01-17 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | FALSE
2024-01-18 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | FALSE
2024-01-19 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | FALSE
2024-01-20 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | TRUE
2024-01-21 | 2024 | 1 | January | Q1 | FY2023-24 | 3 | TRUE
2024-01-22 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | FALSE
2024-01-23 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | FALSE
2024-01-24 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | FALSE
2024-01-25 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | FALSE
2024-01-26 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | FALSE
2024-01-27 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | TRUE
2024-01-28 | 2024 | 1 | January | Q1 | FY2023-24 | 4 | TRUE
2024-01-29 | 2024 | 1 | January | Q1 | FY2023-24 | 5 | FALSE
2024-01-30 | 2024 | 1 | January | Q1 | FY2023-24 | 5 | FALSE
2024-01-31 | 2024 | 1 | January | Q1 | FY2023-24 | 5 | FALSE
2024-02-01 | 2024 | 2 | February | Q1 | FY2023-24 | 5 | FALSE
2024-02-02 | 2024 | 2 | February | Q1 | FY2023-24 | 5 | FALSE
2024-02-03 | 2024 | 2 | February | Q1 | FY2023-24 | 5 | TRUE
2024-02-04 | 2024 | 2 | February | Q1 | FY2023-24 | 5 | TRUE
2024-02-05 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | FALSE
2024-02-06 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | FALSE
2024-02-07 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | FALSE
2024-02-08 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | FALSE
2024-02-09 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | FALSE
2024-02-10 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | TRUE
2024-02-11 | 2024 | 2 | February | Q1 | FY2023-24 | 6 | TRUE
2024-02-12 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | FALSE
2024-02-13 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | FALSE
2024-02-14 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | FALSE
2024-02-15 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | FALSE
2024-02-16 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | FALSE
2024-02-17 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | TRUE
2024-02-18 | 2024 | 2 | February | Q1 | FY2023-24 | 7 | TRUE
2024-02-19 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | FALSE
2024-02-20 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | FALSE
2024-02-21 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | FALSE
2024-02-22 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | FALSE
2024-02-23 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | FALSE
2024-02-24 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | TRUE
2024-02-25 | 2024 | 2 | February | Q1 | FY2023-24 | 8 | TRUE
2024-02-26 | 2024 | 2 | February | Q1 | FY2023-24 | 9 | FALSE
2024-02-27 | 2024 | 2 | February | Q1 | FY2023-24 | 9 | FALSE
2024-02-28 | 2024 | 2 | February | Q1 | FY2023-24 | 9 | FALSE
2024-02-29 | 2024 | 2 | February | Q1 | FY2023-24 | 9 | FALSE
2024-03-01 | 2024 | 3 | March | Q1 | FY2023-24 | 9 | FALSE
2024-03-02 | 2024 | 3 | March | Q1 | FY2023-24 | 9 | TRUE
2024-03-03 | 2024 | 3 | March | Q1 | FY2023-24 | 9 | TRUE
2024-03-04 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | FALSE
2024-03-05 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | FALSE
2024-03-06 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | FALSE
2024-03-07 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | FALSE
2024-03-08 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | FALSE
2024-03-09 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | TRUE
2024-03-10 | 2024 | 3 | March | Q1 | FY2023-24 | 10 | TRUE
2024-03-11 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | FALSE
2024-03-12 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | FALSE
2024-03-13 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | FALSE
2024-03-14 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | FALSE
2024-03-15 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | FALSE
2024-03-16 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | TRUE
2024-03-17 | 2024 | 3 | March | Q1 | FY2023-24 | 11 | TRUE
2024-03-18 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | FALSE
2024-03-19 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | FALSE
2024-03-20 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | FALSE
2024-03-21 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | FALSE
2024-03-22 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | FALSE
2024-03-23 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | TRUE
2024-03-24 | 2024 | 3 | March | Q1 | FY2023-24 | 12 | TRUE
2024-03-25 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | FALSE
2024-03-26 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | FALSE
2024-03-27 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | FALSE
2024-03-28 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | FALSE
2024-03-29 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | FALSE
2024-03-30 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | TRUE
2024-03-31 | 2024 | 3 | March | Q1 | FY2023-24 | 13 | TRUE
2024-04-01 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | FALSE
2024-04-02 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | FALSE
2024-04-03 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | FALSE
2024-04-04 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | FALSE
2024-04-05 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | FALSE
2024-04-06 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | TRUE
2024-04-07 | 2024 | 4 | April | Q2 | FY2024-25 | 14 | TRUE
2024-04-08 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | FALSE
2024-04-09 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | FALSE
2024-04-10 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | FALSE
2024-04-11 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | FALSE
2024-04-12 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | FALSE
2024-04-13 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | TRUE
2024-04-14 | 2024 | 4 | April | Q2 | FY2024-25 | 15 | TRUE
2024-04-15 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | FALSE
2024-04-16 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | FALSE
2024-04-17 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | FALSE
2024-04-18 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | FALSE
2024-04-19 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | FALSE
2024-04-20 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | TRUE
2024-04-21 | 2024 | 4 | April | Q2 | FY2024-25 | 16 | TRUE
2024-04-22 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | FALSE
2024-04-23 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | FALSE
2024-04-24 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | FALSE
2024-04-25 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | FALSE
2024-04-26 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | FALSE
2024-04-27 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | TRUE
2024-04-28 | 2024 | 4 | April | Q2 | FY2024-25 | 17 | TRUE
2024-04-29 | 2024 | 4 | April | Q2 | FY2024-25 | 18 | FALSE
2024-04-30 | 2024 | 4 | April | Q2 | FY2024-25 | 18 | FALSE
2024-05-01 | 2024 | 5 | May | Q2 | FY2024-25 | 18 | FALSE
2024-05-02 | 2024 | 5 | May | Q2 | FY2024-25 | 18 | FALSE
2024-05-03 | 2024 | 5 | May | Q2 | FY2024-25 | 18 | FALSE
2024-05-04 | 2024 | 5 | May | Q2 | FY2024-25 | 18 | TRUE
2024-05-05 | 2024 | 5 | May | Q2 | FY2024-25 | 18 | TRUE
2024-05-06 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | FALSE
2024-05-07 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | FALSE
2024-05-08 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | FALSE
2024-05-09 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | FALSE
2024-05-10 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | FALSE
2024-05-11 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | TRUE
2024-05-12 | 2024 | 5 | May | Q2 | FY2024-25 | 19 | TRUE
2024-05-13 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | FALSE
2024-05-14 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | FALSE
2024-05-15 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | FALSE
2024-05-16 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | FALSE
2024-05-17 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | FALSE
2024-05-18 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | TRUE
2024-05-19 | 2024 | 5 | May | Q2 | FY2024-25 | 20 | TRUE
2024-05-20 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | FALSE
2024-05-21 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | FALSE
2024-05-22 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | FALSE
2024-05-23 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | FALSE
2024-05-24 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | FALSE
2024-05-25 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | TRUE
2024-05-26 | 2024 | 5 | May | Q2 | FY2024-25 | 21 | TRUE
2024-05-27 | 2024 | 5 | May | Q2 | FY2024-25 | 22 | FALSE
2024-05-28 | 2024 | 5 | May | Q2 | FY2024-25 | 22 | FALSE
2024-05-29 | 2024 | 5 | May | Q2 | FY2024-25 | 22 | FALSE
2024-05-30 | 2024 | 5 | May | Q2 | FY2024-25 | 22 | FALSE
2024-05-31 | 2024 | 5 | May | Q2 | FY2024-25 | 22 | FALSE
2024-06-01 | 2024 | 6 | June | Q2 | FY2024-25 | 22 | TRUE
2024-06-02 | 2024 | 6 | June | Q2 | FY2024-25 | 22 | TRUE
2024-06-03 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | FALSE
2024-06-04 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | FALSE
2024-06-05 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | FALSE
2024-06-06 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | FALSE
2024-06-07 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | FALSE
2024-06-08 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | TRUE
2024-06-09 | 2024 | 6 | June | Q2 | FY2024-25 | 23 | TRUE
2024-06-10 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | FALSE
2024-06-11 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | FALSE
2024-06-12 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | FALSE
2024-06-13 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | FALSE
2024-06-14 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | FALSE
2024-06-15 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | TRUE
2024-06-16 | 2024 | 6 | June | Q2 | FY2024-25 | 24 | TRUE
2024-06-17 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | FALSE
2024-06-18 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | FALSE
2024-06-19 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | FALSE
2024-06-20 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | FALSE
2024-06-21 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | FALSE
2024-06-22 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | TRUE
2024-06-23 | 2024 | 6 | June | Q2 | FY2024-25 | 25 | TRUE
2024-06-24 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | FALSE
2024-06-25 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | FALSE
2024-06-26 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | FALSE
2024-06-27 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | FALSE
2024-06-28 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | FALSE
2024-06-29 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | TRUE
2024-06-30 | 2024 | 6 | June | Q2 | FY2024-25 | 26 | TRUE
2024-07-01 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | FALSE
2024-07-02 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | FALSE
2024-07-03 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | FALSE
2024-07-04 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | FALSE
2024-07-05 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | FALSE
2024-07-06 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | TRUE
2024-07-07 | 2024 | 7 | July | Q3 | FY2024-25 | 27 | TRUE
2024-07-08 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | FALSE
2024-07-09 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | FALSE
2024-07-10 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | FALSE
2024-07-11 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | FALSE
2024-07-12 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | FALSE
2024-07-13 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | TRUE
2024-07-14 | 2024 | 7 | July | Q3 | FY2024-25 | 28 | TRUE
2024-07-15 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | FALSE
2024-07-16 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | FALSE
2024-07-17 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | FALSE
2024-07-18 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | FALSE
2024-07-19 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | FALSE
2024-07-20 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | TRUE
2024-07-21 | 2024 | 7 | July | Q3 | FY2024-25 | 29 | TRUE
2024-07-22 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | FALSE
2024-07-23 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | FALSE
2024-07-24 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | FALSE
2024-07-25 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | FALSE
2024-07-26 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | FALSE
2024-07-27 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | TRUE
2024-07-28 | 2024 | 7 | July | Q3 | FY2024-25 | 30 | TRUE
2024-07-29 | 2024 | 7 | July | Q3 | FY2024-25 | 31 | FALSE
2024-07-30 | 2024 | 7 | July | Q3 | FY2024-25 | 31 | FALSE
2024-07-31 | 2024 | 7 | July | Q3 | FY2024-25 | 31 | FALSE
2024-08-01 | 2024 | 8 | August | Q3 | FY2024-25 | 31 | FALSE
2024-08-02 | 2024 | 8 | August | Q3 | FY2024-25 | 31 | FALSE
2024-08-03 | 2024 | 8 | August | Q3 | FY2024-25 | 31 | TRUE
2024-08-04 | 2024 | 8 | August | Q3 | FY2024-25 | 31 | TRUE
2024-08-05 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | FALSE
2024-08-06 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | FALSE
2024-08-07 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | FALSE
2024-08-08 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | FALSE
2024-08-09 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | FALSE
2024-08-10 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | TRUE
2024-08-11 | 2024 | 8 | August | Q3 | FY2024-25 | 32 | TRUE
2024-08-12 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | FALSE
2024-08-13 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | FALSE
2024-08-14 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | FALSE
2024-08-15 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | FALSE
2024-08-16 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | FALSE
2024-08-17 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | TRUE
2024-08-18 | 2024 | 8 | August | Q3 | FY2024-25 | 33 | TRUE
2024-08-19 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | FALSE
2024-08-20 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | FALSE
2024-08-21 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | FALSE
2024-08-22 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | FALSE
2024-08-23 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | FALSE
2024-08-24 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | TRUE
2024-08-25 | 2024 | 8 | August | Q3 | FY2024-25 | 34 | TRUE
2024-08-26 | 2024 | 8 | August | Q3 | FY2024-25 | 35 | FALSE
2024-08-27 | 2024 | 8 | August | Q3 | FY2024-25 | 35 | FALSE
2024-08-28 | 2024 | 8 | August | Q3 | FY2024-25 | 35 | FALSE
2024-08-29 | 2024 | 8 | August | Q3 | FY2024-25 | 35 | FALSE
2024-08-30 | 2024 | 8 | August | Q3 | FY2024-25 | 35 | FALSE
2024-08-31 | 2024 | 8 | August | Q3 | FY2024-25 | 35 | TRUE
2024-09-01 | 2024 | 9 | September | Q3 | FY2024-25 | 35 | TRUE
2024-09-02 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | FALSE
2024-09-03 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | FALSE
2024-09-04 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | FALSE
2024-09-05 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | FALSE
2024-09-06 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | FALSE
2024-09-07 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | TRUE
2024-09-08 | 2024 | 9 | September | Q3 | FY2024-25 | 36 | TRUE
2024-09-09 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | FALSE
2024-09-10 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | FALSE
2024-09-11 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | FALSE
2024-09-12 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | FALSE
2024-09-13 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | FALSE
2024-09-14 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | TRUE
2024-09-15 | 2024 | 9 | September | Q3 | FY2024-25 | 37 | TRUE
2024-09-16 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | FALSE
2024-09-17 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | FALSE
2024-09-18 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | FALSE
2024-09-19 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | FALSE
2024-09-20 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | FALSE
2024-09-21 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | TRUE
2024-09-22 | 2024 | 9 | September | Q3 | FY2024-25 | 38 | TRUE
2024-09-23 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | FALSE
2024-09-24 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | FALSE
2024-09-25 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | FALSE
2024-09-26 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | FALSE
2024-09-27 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | FALSE
2024-09-28 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | TRUE
2024-09-29 | 2024 | 9 | September | Q3 | FY2024-25 | 39 | TRUE
2024-09-30 | 2024 | 9 | September | Q3 | FY2024-25 | 40 | FALSE
2024-10-01 | 2024 | 10 | October | Q4 | FY2024-25 | 40 | FALSE
2024-10-02 | 2024 | 10 | October | Q4 | FY2024-25 | 40 | FALSE
2024-10-03 | 2024 | 10 | October | Q4 | FY2024-25 | 40 | FALSE
2024-10-04 | 2024 | 10 | October | Q4 | FY2024-25 | 40 | FALSE
2024-10-05 | 2024 | 10 | October | Q4 | FY2024-25 | 40 | TRUE
2024-10-06 | 2024 | 10 | October | Q4 | FY2024-25 | 40 | TRUE
2024-10-07 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | FALSE
2024-10-08 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | FALSE
2024-10-09 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | FALSE
2024-10-10 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | FALSE
2024-10-11 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | FALSE
2024-10-12 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | TRUE
2024-10-13 | 2024 | 10 | October | Q4 | FY2024-25 | 41 | TRUE
2024-10-14 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | FALSE
2024-10-15 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | FALSE
2024-10-16 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | FALSE
2024-10-17 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | FALSE
2024-10-18 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | FALSE
2024-10-19 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | TRUE
2024-10-20 | 2024 | 10 | October | Q4 | FY2024-25 | 42 | TRUE
2024-10-21 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | FALSE
2024-10-22 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | FALSE
2024-10-23 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | FALSE
2024-10-24 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | FALSE
2024-10-25 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | FALSE
2024-10-26 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | TRUE
2024-10-27 | 2024 | 10 | October | Q4 | FY2024-25 | 43 | TRUE
2024-10-28 | 2024 | 10 | October | Q4 | FY2024-25 | 44 | FALSE
2024-10-29 | 2024 | 10 | October | Q4 | FY2024-25 | 44 | FALSE
2024-10-30 | 2024 | 10 | October | Q4 | FY2024-25 | 44 | FALSE
2024-10-31 | 2024 | 10 | October | Q4 | FY2024-25 | 44 | FALSE
2024-11-01 | 2024 | 11 | November | Q4 | FY2024-25 | 44 | FALSE
2024-11-02 | 2024 | 11 | November | Q4 | FY2024-25 | 44 | TRUE
2024-11-03 | 2024 | 11 | November | Q4 | FY2024-25 | 44 | TRUE
2024-11-04 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | FALSE
2024-11-05 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | FALSE
2024-11-06 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | FALSE
2024-11-07 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | FALSE
2024-11-08 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | FALSE
2024-11-09 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | TRUE
2024-11-10 | 2024 | 11 | November | Q4 | FY2024-25 | 45 | TRUE
2024-11-11 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | FALSE
2024-11-12 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | FALSE
2024-11-13 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | FALSE
2024-11-14 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | FALSE
2024-11-15 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | FALSE
2024-11-16 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | TRUE
2024-11-17 | 2024 | 11 | November | Q4 | FY2024-25 | 46 | TRUE
2024-11-18 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | FALSE
2024-11-19 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | FALSE
2024-11-20 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | FALSE
2024-11-21 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | FALSE
2024-11-22 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | FALSE
2024-11-23 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | TRUE
2024-11-24 | 2024 | 11 | November | Q4 | FY2024-25 | 47 | TRUE
2024-11-25 | 2024 | 11 | November | Q4 | FY2024-25 | 48 | FALSE
2024-11-26 | 2024 | 11 | November | Q4 | FY2024-25 | 48 | FALSE
2024-11-27 | 2024 | 11 | November | Q4 | FY2024-25 | 48 | FALSE
2024-11-28 | 2024 | 11 | November | Q4 | FY2024-25 | 48 | FALSE
2024-11-29 | 2024 | 11 | November | Q4 | FY2024-25 | 48 | FALSE
2024-11-30 | 2024 | 11 | November | Q4 | FY2024-25 | 48 | TRUE
2024-12-01 | 2024 | 12 | December | Q4 | FY2024-25 | 48 | TRUE
2024-12-02 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | FALSE
2024-12-03 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | FALSE
2024-12-04 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | FALSE
2024-12-05 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | FALSE
2024-12-06 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | FALSE
2024-12-07 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | TRUE
2024-12-08 | 2024 | 12 | December | Q4 | FY2024-25 | 49 | TRUE
2024-12-09 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | FALSE
2024-12-10 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | FALSE
2024-12-11 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | FALSE
2024-12-12 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | FALSE
2024-12-13 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | FALSE
2024-12-14 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | TRUE
2024-12-15 | 2024 | 12 | December | Q4 | FY2024-25 | 50 | TRUE
2024-12-16 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | FALSE
2024-12-17 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | FALSE
2024-12-18 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | FALSE
2024-12-19 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | FALSE
2024-12-20 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | FALSE
2024-12-21 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | TRUE
2024-12-22 | 2024 | 12 | December | Q4 | FY2024-25 | 51 | TRUE
2024-12-23 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | FALSE
2024-12-24 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | FALSE
2024-12-25 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | FALSE
2024-12-26 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | FALSE
2024-12-27 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | FALSE
2024-12-28 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | TRUE
2024-12-29 | 2024 | 12 | December | Q4 | FY2024-25 | 52 | TRUE
2024-12-30 | 2024 | 12 | December | Q4 | FY2024-25 | 1 | FALSE
2024-12-31 | 2024 | 12 | December | Q4 | FY2024-25 | 1 | FALSE
2025-01-01 | 2025 | 1 | January | Q1 | FY2024-25 | 1 | FALSE
2025-01-02 | 2025 | 1 | January | Q1 | FY2024-25 | 1 | FALSE
2025-01-03 | 2025 | 1 | January | Q1 | FY2024-25 | 1 | FALSE
2025-01-04 | 2025 | 1 | January | Q1 | FY2024-25 | 1 | TRUE
2025-01-05 | 2025 | 1 | January | Q1 | FY2024-25 | 1 | TRUE
2025-01-06 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | FALSE
2025-01-07 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | FALSE
2025-01-08 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | FALSE
2025-01-09 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | FALSE
2025-01-10 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | FALSE
2025-01-11 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | TRUE
2025-01-12 | 2025 | 1 | January | Q1 | FY2024-25 | 2 | TRUE
2025-01-13 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | FALSE
2025-01-14 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | FALSE
2025-01-15 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | FALSE
2025-01-16 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | FALSE
2025-01-17 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | FALSE
2025-01-18 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | TRUE
2025-01-19 | 2025 | 1 | January | Q1 | FY2024-25 | 3 | TRUE
2025-01-20 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | FALSE
2025-01-21 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | FALSE
2025-01-22 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | FALSE
2025-01-23 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | FALSE
2025-01-24 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | FALSE
2025-01-25 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | TRUE
2025-01-26 | 2025 | 1 | January | Q1 | FY2024-25 | 4 | TRUE
2025-01-27 | 2025 | 1 | January | Q1 | FY2024-25 | 5 | FALSE
2025-01-28 | 2025 | 1 | January | Q1 | FY2024-25 | 5 | FALSE
2025-01-29 | 2025 | 1 | January | Q1 | FY2024-25 | 5 | FALSE
2025-01-30 | 2025 | 1 | January | Q1 | FY2024-25 | 5 | FALSE
2025-01-31 | 2025 | 1 | January | Q1 | FY2024-25 | 5 | FALSE
2025-02-01 | 2025 | 2 | February | Q1 | FY2024-25 | 5 | TRUE
2025-02-02 | 2025 | 2 | February | Q1 | FY2024-25 | 5 | TRUE
2025-02-03 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | FALSE
2025-02-04 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | FALSE
2025-02-05 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | FALSE
2025-02-06 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | FALSE
2025-02-07 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | FALSE
2025-02-08 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | TRUE
2025-02-09 | 2025 | 2 | February | Q1 | FY2024-25 | 6 | TRUE
2025-02-10 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | FALSE
2025-02-11 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | FALSE
2025-02-12 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | FALSE
2025-02-13 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | FALSE
2025-02-14 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | FALSE
2025-02-15 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | TRUE
2025-02-16 | 2025 | 2 | February | Q1 | FY2024-25 | 7 | TRUE
2025-02-17 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | FALSE
2025-02-18 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | FALSE
2025-02-19 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | FALSE
2025-02-20 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | FALSE
2025-02-21 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | FALSE
2025-02-22 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | TRUE
2025-02-23 | 2025 | 2 | February | Q1 | FY2024-25 | 8 | TRUE
2025-02-24 | 2025 | 2 | February | Q1 | FY2024-25 | 9 | FALSE
2025-02-25 | 2025 | 2 | February | Q1 | FY2024-25 | 9 | FALSE
2025-02-26 | 2025 | 2 | February | Q1 | FY2024-25 | 9 | FALSE
2025-02-27 | 2025 | 2 | February | Q1 | FY2024-25 | 9 | FALSE
2025-02-28 | 2025 | 2 | February | Q1 | FY2024-25 | 9 | FALSE
2025-03-01 | 2025 | 3 | March | Q1 | FY2024-25 | 9 | TRUE
2025-03-02 | 2025 | 3 | March | Q1 | FY2024-25 | 9 | TRUE
2025-03-03 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | FALSE
2025-03-04 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | FALSE
2025-03-05 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | FALSE
2025-03-06 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | FALSE
2025-03-07 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | FALSE
2025-03-08 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | TRUE
2025-03-09 | 2025 | 3 | March | Q1 | FY2024-25 | 10 | TRUE
2025-03-10 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | FALSE
2025-03-11 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | FALSE
2025-03-12 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | FALSE
2025-03-13 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | FALSE
2025-03-14 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | FALSE
2025-03-15 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | TRUE
2025-03-16 | 2025 | 3 | March | Q1 | FY2024-25 | 11 | TRUE
2025-03-17 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | FALSE
2025-03-18 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | FALSE
2025-03-19 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | FALSE
2025-03-20 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | FALSE
2025-03-21 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | FALSE
2025-03-22 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | TRUE
2025-03-23 | 2025 | 3 | March | Q1 | FY2024-25 | 12 | TRUE
2025-03-24 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | FALSE
2025-03-25 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | FALSE
2025-03-26 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | FALSE
2025-03-27 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | FALSE
2025-03-28 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | FALSE
2025-03-29 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | TRUE
2025-03-30 | 2025 | 3 | March | Q1 | FY2024-25 | 13 | TRUE
2025-03-31 | 2025 | 3 | March | Q1 | FY2024-25 | 14 | FALSE
2025-04-01 | 2025 | 4 | April | Q2 | FY2025-26 | 14 | FALSE
2025-04-02 | 2025 | 4 | April | Q2 | FY2025-26 | 14 | FALSE
2025-04-03 | 2025 | 4 | April | Q2 | FY2025-26 | 14 | FALSE
2025-04-04 | 2025 | 4 | April | Q2 | FY2025-26 | 14 | FALSE
2025-04-05 | 2025 | 4 | April | Q2 | FY2025-26 | 14 | TRUE
2025-04-06 | 2025 | 4 | April | Q2 | FY2025-26 | 14 | TRUE
2025-04-07 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | FALSE
2025-04-08 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | FALSE
2025-04-09 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | FALSE
2025-04-10 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | FALSE
2025-04-11 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | FALSE
2025-04-12 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | TRUE
2025-04-13 | 2025 | 4 | April | Q2 | FY2025-26 | 15 | TRUE
2025-04-14 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | FALSE
2025-04-15 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | FALSE
2025-04-16 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | FALSE
2025-04-17 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | FALSE
2025-04-18 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | FALSE
2025-04-19 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | TRUE
2025-04-20 | 2025 | 4 | April | Q2 | FY2025-26 | 16 | TRUE
2025-04-21 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | FALSE
2025-04-22 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | FALSE
2025-04-23 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | FALSE
2025-04-24 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | FALSE
2025-04-25 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | FALSE
2025-04-26 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | TRUE
2025-04-27 | 2025 | 4 | April | Q2 | FY2025-26 | 17 | TRUE
2025-04-28 | 2025 | 4 | April | Q2 | FY2025-26 | 18 | FALSE
2025-04-29 | 2025 | 4 | April | Q2 | FY2025-26 | 18 | FALSE
2025-04-30 | 2025 | 4 | April | Q2 | FY2025-26 | 18 | FALSE
2025-05-01 | 2025 | 5 | May | Q2 | FY2025-26 | 18 | FALSE
2025-05-02 | 2025 | 5 | May | Q2 | FY2025-26 | 18 | FALSE
2025-05-03 | 2025 | 5 | May | Q2 | FY2025-26 | 18 | TRUE
2025-05-04 | 2025 | 5 | May | Q2 | FY2025-26 | 18 | TRUE
2025-05-05 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | FALSE
2025-05-06 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | FALSE
2025-05-07 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | FALSE
2025-05-08 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | FALSE
2025-05-09 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | FALSE
2025-05-10 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | TRUE
2025-05-11 | 2025 | 5 | May | Q2 | FY2025-26 | 19 | TRUE
2025-05-12 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | FALSE
2025-05-13 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | FALSE
2025-05-14 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | FALSE
2025-05-15 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | FALSE
2025-05-16 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | FALSE
2025-05-17 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | TRUE
2025-05-18 | 2025 | 5 | May | Q2 | FY2025-26 | 20 | TRUE
2025-05-19 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | FALSE
2025-05-20 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | FALSE
2025-05-21 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | FALSE
2025-05-22 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | FALSE
2025-05-23 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | FALSE
2025-05-24 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | TRUE
2025-05-25 | 2025 | 5 | May | Q2 | FY2025-26 | 21 | TRUE
2025-05-26 | 2025 | 5 | May | Q2 | FY2025-26 | 22 | FALSE
2025-05-27 | 2025 | 5 | May | Q2 | FY2025-26 | 22 | FALSE
2025-05-28 | 2025 | 5 | May | Q2 | FY2025-26 | 22 | FALSE
2025-05-29 | 2025 | 5 | May | Q2 | FY2025-26 | 22 | FALSE
2025-05-30 | 2025 | 5 | May | Q2 | FY2025-26 | 22 | FALSE
2025-05-31 | 2025 | 5 | May | Q2 | FY2025-26 | 22 | TRUE
2025-06-01 | 2025 | 6 | June | Q2 | FY2025-26 | 22 | TRUE
2025-06-02 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | FALSE
2025-06-03 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | FALSE
2025-06-04 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | FALSE
2025-06-05 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | FALSE
2025-06-06 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | FALSE
2025-06-07 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | TRUE
2025-06-08 | 2025 | 6 | June | Q2 | FY2025-26 | 23 | TRUE
2025-06-09 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | FALSE
2025-06-10 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | FALSE
2025-06-11 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | FALSE
2025-06-12 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | FALSE
2025-06-13 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | FALSE
2025-06-14 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | TRUE
2025-06-15 | 2025 | 6 | June | Q2 | FY2025-26 | 24 | TRUE
2025-06-16 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | FALSE
2025-06-17 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | FALSE
2025-06-18 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | FALSE
2025-06-19 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | FALSE
2025-06-20 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | FALSE
2025-06-21 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | TRUE
2025-06-22 | 2025 | 6 | June | Q2 | FY2025-26 | 25 | TRUE
2025-06-23 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | FALSE
2025-06-24 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | FALSE
2025-06-25 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | FALSE
2025-06-26 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | FALSE
2025-06-27 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | FALSE
2025-06-28 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | TRUE
2025-06-29 | 2025 | 6 | June | Q2 | FY2025-26 | 26 | TRUE
2025-06-30 | 2025 | 6 | June | Q2 | FY2025-26 | 27 | FALSE
2025-07-01 | 2025 | 7 | July | Q3 | FY2025-26 | 27 | FALSE
2025-07-02 | 2025 | 7 | July | Q3 | FY2025-26 | 27 | FALSE
2025-07-03 | 2025 | 7 | July | Q3 | FY2025-26 | 27 | FALSE
2025-07-04 | 2025 | 7 | July | Q3 | FY2025-26 | 27 | FALSE
2025-07-05 | 2025 | 7 | July | Q3 | FY2025-26 | 27 | TRUE
2025-07-06 | 2025 | 7 | July | Q3 | FY2025-26 | 27 | TRUE
2025-07-07 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | FALSE
2025-07-08 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | FALSE
2025-07-09 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | FALSE
2025-07-10 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | FALSE
2025-07-11 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | FALSE
2025-07-12 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | TRUE
2025-07-13 | 2025 | 7 | July | Q3 | FY2025-26 | 28 | TRUE
2025-07-14 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | FALSE
2025-07-15 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | FALSE
2025-07-16 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | FALSE
2025-07-17 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | FALSE
2025-07-18 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | FALSE
2025-07-19 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | TRUE
2025-07-20 | 2025 | 7 | July | Q3 | FY2025-26 | 29 | TRUE
2025-07-21 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | FALSE
2025-07-22 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | FALSE
2025-07-23 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | FALSE
2025-07-24 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | FALSE
2025-07-25 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | FALSE
2025-07-26 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | TRUE
2025-07-27 | 2025 | 7 | July | Q3 | FY2025-26 | 30 | TRUE
2025-07-28 | 2025 | 7 | July | Q3 | FY2025-26 | 31 | FALSE
2025-07-29 | 2025 | 7 | July | Q3 | FY2025-26 | 31 | FALSE
2025-07-30 | 2025 | 7 | July | Q3 | FY2025-26 | 31 | FALSE
2025-07-31 | 2025 | 7 | July | Q3 | FY2025-26 | 31 | FALSE
2025-08-01 | 2025 | 8 | August | Q3 | FY2025-26 | 31 | FALSE
2025-08-02 | 2025 | 8 | August | Q3 | FY2025-26 | 31 | TRUE
2025-08-03 | 2025 | 8 | August | Q3 | FY2025-26 | 31 | TRUE
2025-08-04 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | FALSE
2025-08-05 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | FALSE
2025-08-06 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | FALSE
2025-08-07 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | FALSE
2025-08-08 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | FALSE
2025-08-09 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | TRUE
2025-08-10 | 2025 | 8 | August | Q3 | FY2025-26 | 32 | TRUE
2025-08-11 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | FALSE
2025-08-12 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | FALSE
2025-08-13 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | FALSE
2025-08-14 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | FALSE
2025-08-15 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | FALSE
2025-08-16 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | TRUE
2025-08-17 | 2025 | 8 | August | Q3 | FY2025-26 | 33 | TRUE
2025-08-18 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | FALSE
2025-08-19 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | FALSE
2025-08-20 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | FALSE
2025-08-21 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | FALSE
2025-08-22 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | FALSE
2025-08-23 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | TRUE
2025-08-24 | 2025 | 8 | August | Q3 | FY2025-26 | 34 | TRUE
2025-08-25 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | FALSE
2025-08-26 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | FALSE
2025-08-27 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | FALSE
2025-08-28 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | FALSE
2025-08-29 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | FALSE
2025-08-30 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | TRUE
2025-08-31 | 2025 | 8 | August | Q3 | FY2025-26 | 35 | TRUE
2025-09-01 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | FALSE
2025-09-02 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | FALSE
2025-09-03 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | FALSE
2025-09-04 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | FALSE
2025-09-05 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | FALSE
2025-09-06 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | TRUE
2025-09-07 | 2025 | 9 | September | Q3 | FY2025-26 | 36 | TRUE
2025-09-08 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | FALSE
2025-09-09 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | FALSE
2025-09-10 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | FALSE
2025-09-11 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | FALSE
2025-09-12 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | FALSE
2025-09-13 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | TRUE
2025-09-14 | 2025 | 9 | September | Q3 | FY2025-26 | 37 | TRUE
2025-09-15 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | FALSE
2025-09-16 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | FALSE
2025-09-17 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | FALSE
2025-09-18 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | FALSE
2025-09-19 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | FALSE
2025-09-20 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | TRUE
2025-09-21 | 2025 | 9 | September | Q3 | FY2025-26 | 38 | TRUE
2025-09-22 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | FALSE
2025-09-23 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | FALSE
2025-09-24 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | FALSE
2025-09-25 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | FALSE
2025-09-26 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | FALSE
2025-09-27 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | TRUE
2025-09-28 | 2025 | 9 | September | Q3 | FY2025-26 | 39 | TRUE
2025-09-29 | 2025 | 9 | September | Q3 | FY2025-26 | 40 | FALSE
2025-09-30 | 2025 | 9 | September | Q3 | FY2025-26 | 40 | FALSE
2025-10-01 | 2025 | 10 | October | Q4 | FY2025-26 | 40 | FALSE
2025-10-02 | 2025 | 10 | October | Q4 | FY2025-26 | 40 | FALSE
2025-10-03 | 2025 | 10 | October | Q4 | FY2025-26 | 40 | FALSE
2025-10-04 | 2025 | 10 | October | Q4 | FY2025-26 | 40 | TRUE
2025-10-05 | 2025 | 10 | October | Q4 | FY2025-26 | 40 | TRUE
2025-10-06 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | FALSE
2025-10-07 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | FALSE
2025-10-08 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | FALSE
2025-10-09 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | FALSE
2025-10-10 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | FALSE
2025-10-11 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | TRUE
2025-10-12 | 2025 | 10 | October | Q4 | FY2025-26 | 41 | TRUE
2025-10-13 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | FALSE
2025-10-14 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | FALSE
2025-10-15 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | FALSE
2025-10-16 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | FALSE
2025-10-17 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | FALSE
2025-10-18 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | TRUE
2025-10-19 | 2025 | 10 | October | Q4 | FY2025-26 | 42 | TRUE
2025-10-20 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | FALSE
2025-10-21 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | FALSE
2025-10-22 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | FALSE
2025-10-23 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | FALSE
2025-10-24 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | FALSE
2025-10-25 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | TRUE
2025-10-26 | 2025 | 10 | October | Q4 | FY2025-26 | 43 | TRUE
2025-10-27 | 2025 | 10 | October | Q4 | FY2025-26 | 44 | FALSE
2025-10-28 | 2025 | 10 | October | Q4 | FY2025-26 | 44 | FALSE
2025-10-29 | 2025 | 10 | October | Q4 | FY2025-26 | 44 | FALSE
2025-10-30 | 2025 | 10 | October | Q4 | FY2025-26 | 44 | FALSE
2025-10-31 | 2025 | 10 | October | Q4 | FY2025-26 | 44 | FALSE
2025-11-01 | 2025 | 11 | November | Q4 | FY2025-26 | 44 | TRUE
2025-11-02 | 2025 | 11 | November | Q4 | FY2025-26 | 44 | TRUE
2025-11-03 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | FALSE
2025-11-04 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | FALSE
2025-11-05 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | FALSE
2025-11-06 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | FALSE
2025-11-07 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | FALSE
2025-11-08 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | TRUE
2025-11-09 | 2025 | 11 | November | Q4 | FY2025-26 | 45 | TRUE
2025-11-10 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | FALSE
2025-11-11 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | FALSE
2025-11-12 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | FALSE
2025-11-13 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | FALSE
2025-11-14 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | FALSE
2025-11-15 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | TRUE
2025-11-16 | 2025 | 11 | November | Q4 | FY2025-26 | 46 | TRUE
2025-11-17 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | FALSE
2025-11-18 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | FALSE
2025-11-19 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | FALSE
2025-11-20 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | FALSE
2025-11-21 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | FALSE
2025-11-22 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | TRUE
2025-11-23 | 2025 | 11 | November | Q4 | FY2025-26 | 47 | TRUE
2025-11-24 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | FALSE
2025-11-25 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | FALSE
2025-11-26 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | FALSE
2025-11-27 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | FALSE
2025-11-28 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | FALSE
2025-11-29 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | TRUE
2025-11-30 | 2025 | 11 | November | Q4 | FY2025-26 | 48 | TRUE
2025-12-01 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | FALSE
2025-12-02 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | FALSE
2025-12-03 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | FALSE
2025-12-04 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | FALSE
2025-12-05 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | FALSE
2025-12-06 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | TRUE
2025-12-07 | 2025 | 12 | December | Q4 | FY2025-26 | 49 | TRUE
2025-12-08 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | FALSE
2025-12-09 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | FALSE
2025-12-10 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | FALSE
2025-12-11 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | FALSE
2025-12-12 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | FALSE
2025-12-13 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | TRUE
2025-12-14 | 2025 | 12 | December | Q4 | FY2025-26 | 50 | TRUE
2025-12-15 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | FALSE
2025-12-16 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | FALSE
2025-12-17 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | FALSE
2025-12-18 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | FALSE
2025-12-19 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | FALSE
2025-12-20 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | TRUE
2025-12-21 | 2025 | 12 | December | Q4 | FY2025-26 | 51 | TRUE
2025-12-22 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | FALSE
2025-12-23 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | FALSE
2025-12-24 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | FALSE
2025-12-25 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | FALSE
2025-12-26 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | FALSE
2025-12-27 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | TRUE
2025-12-28 | 2025 | 12 | December | Q4 | FY2025-26 | 52 | TRUE
2025-12-29 | 2025 | 12 | December | Q4 | FY2025-26 | 1 | FALSE
2025-12-30 | 2025 | 12 | December | Q4 | FY2025-26 | 1 | FALSE
2025-12-31 | 2025 | 12 | December | Q4 | FY2025-26 | 1 | FALSE
2026-01-01 | 2026 | 1 | January | Q1 | FY2025-26 | 1 | FALSE
2026-01-02 | 2026 | 1 | January | Q1 | FY2025-26 | 1 | FALSE
2026-01-03 | 2026 | 1 | January | Q1 | FY2025-26 | 1 | TRUE
2026-01-04 | 2026 | 1 | January | Q1 | FY2025-26 | 1 | TRUE
2026-01-05 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | FALSE
2026-01-06 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | FALSE
2026-01-07 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | FALSE
2026-01-08 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | FALSE
2026-01-09 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | FALSE
2026-01-10 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | TRUE
2026-01-11 | 2026 | 1 | January | Q1 | FY2025-26 | 2 | TRUE
2026-01-12 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | FALSE
2026-01-13 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | FALSE
2026-01-14 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | FALSE
2026-01-15 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | FALSE
2026-01-16 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | FALSE
2026-01-17 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | TRUE
2026-01-18 | 2026 | 1 | January | Q1 | FY2025-26 | 3 | TRUE
2026-01-19 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | FALSE
2026-01-20 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | FALSE
2026-01-21 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | FALSE
2026-01-22 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | FALSE
2026-01-23 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | FALSE
2026-01-24 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | TRUE
2026-01-25 | 2026 | 1 | January | Q1 | FY2025-26 | 4 | TRUE
2026-01-26 | 2026 | 1 | January | Q1 | FY2025-26 | 5 | FALSE
2026-01-27 | 2026 | 1 | January | Q1 | FY2025-26 | 5 | FALSE
2026-01-28 | 2026 | 1 | January | Q1 | FY2025-26 | 5 | FALSE
2026-01-29 | 2026 | 1 | January | Q1 | FY2025-26 | 5 | FALSE
2026-01-30 | 2026 | 1 | January | Q1 | FY2025-26 | 5 | FALSE
2026-01-31 | 2026 | 1 | January | Q1 | FY2025-26 | 5 | TRUE
2026-02-01 | 2026 | 2 | February | Q1 | FY2025-26 | 5 | TRUE
2026-02-02 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | FALSE
2026-02-03 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | FALSE
2026-02-04 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | FALSE
2026-02-05 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | FALSE
2026-02-06 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | FALSE
2026-02-07 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | TRUE
2026-02-08 | 2026 | 2 | February | Q1 | FY2025-26 | 6 | TRUE
2026-02-09 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | FALSE
2026-02-10 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | FALSE
2026-02-11 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | FALSE
2026-02-12 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | FALSE
2026-02-13 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | FALSE
2026-02-14 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | TRUE
2026-02-15 | 2026 | 2 | February | Q1 | FY2025-26 | 7 | TRUE
2026-02-16 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | FALSE
2026-02-17 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | FALSE
2026-02-18 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | FALSE
2026-02-19 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | FALSE
2026-02-20 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | FALSE
2026-02-21 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | TRUE
2026-02-22 | 2026 | 2 | February | Q1 | FY2025-26 | 8 | TRUE
2026-02-23 | 2026 | 2 | February | Q1 | FY2025-26 | 9 | FALSE
2026-02-24 | 2026 | 2 | February | Q1 | FY2025-26 | 9 | FALSE
2026-02-25 | 2026 | 2 | February | Q1 | FY2025-26 | 9 | FALSE
2026-02-26 | 2026 | 2 | February | Q1 | FY2025-26 | 9 | FALSE
2026-02-27 | 2026 | 2 | February | Q1 | FY2025-26 | 9 | FALSE
2026-02-28 | 2026 | 2 | February | Q1 | FY2025-26 | 9 | TRUE
2026-03-01 | 2026 | 3 | March | Q1 | FY2025-26 | 9 | TRUE
2026-03-02 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | FALSE
2026-03-03 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | FALSE
2026-03-04 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | FALSE
2026-03-05 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | FALSE
2026-03-06 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | FALSE
2026-03-07 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | TRUE
2026-03-08 | 2026 | 3 | March | Q1 | FY2025-26 | 10 | TRUE
2026-03-09 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | FALSE
2026-03-10 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | FALSE
2026-03-11 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | FALSE
2026-03-12 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | FALSE
2026-03-13 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | FALSE
2026-03-14 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | TRUE
2026-03-15 | 2026 | 3 | March | Q1 | FY2025-26 | 11 | TRUE
2026-03-16 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | FALSE
2026-03-17 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | FALSE
2026-03-18 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | FALSE
2026-03-19 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | FALSE
2026-03-20 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | FALSE
2026-03-21 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | TRUE
2026-03-22 | 2026 | 3 | March | Q1 | FY2025-26 | 12 | TRUE
2026-03-23 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | FALSE
2026-03-24 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | FALSE
2026-03-25 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | FALSE
2026-03-26 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | FALSE
2026-03-27 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | FALSE
2026-03-28 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | TRUE
2026-03-29 | 2026 | 3 | March | Q1 | FY2025-26 | 13 | TRUE
2026-03-30 | 2026 | 3 | March | Q1 | FY2025-26 | 14 | FALSE
2026-03-31 | 2026 | 3 | March | Q1 | FY2025-26 | 14 | FALSE
2026-04-01 | 2026 | 4 | April | Q2 | FY2026-27 | 14 | FALSE
2026-04-02 | 2026 | 4 | April | Q2 | FY2026-27 | 14 | FALSE
2026-04-03 | 2026 | 4 | April | Q2 | FY2026-27 | 14 | FALSE
2026-04-04 | 2026 | 4 | April | Q2 | FY2026-27 | 14 | TRUE
2026-04-05 | 2026 | 4 | April | Q2 | FY2026-27 | 14 | TRUE
2026-04-06 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | FALSE
2026-04-07 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | FALSE
2026-04-08 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | FALSE
2026-04-09 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | FALSE
2026-04-10 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | FALSE
2026-04-11 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | TRUE
2026-04-12 | 2026 | 4 | April | Q2 | FY2026-27 | 15 | TRUE
2026-04-13 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | FALSE
2026-04-14 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | FALSE
2026-04-15 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | FALSE
2026-04-16 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | FALSE
2026-04-17 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | FALSE
2026-04-18 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | TRUE
2026-04-19 | 2026 | 4 | April | Q2 | FY2026-27 | 16 | TRUE
2026-04-20 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | FALSE
2026-04-21 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | FALSE
2026-04-22 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | FALSE
2026-04-23 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | FALSE
2026-04-24 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | FALSE
2026-04-25 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | TRUE
2026-04-26 | 2026 | 4 | April | Q2 | FY2026-27 | 17 | TRUE
2026-04-27 | 2026 | 4 | April | Q2 | FY2026-27 | 18 | FALSE
2026-04-28 | 2026 | 4 | April | Q2 | FY2026-27 | 18 | FALSE
2026-04-29 | 2026 | 4 | April | Q2 | FY2026-27 | 18 | FALSE
2026-04-30 | 2026 | 4 | April | Q2 | FY2026-27 | 18 | FALSE
2026-05-01 | 2026 | 5 | May | Q2 | FY2026-27 | 18 | FALSE
2026-05-02 | 2026 | 5 | May | Q2 | FY2026-27 | 18 | TRUE
2026-05-03 | 2026 | 5 | May | Q2 | FY2026-27 | 18 | TRUE
2026-05-04 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | FALSE
2026-05-05 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | FALSE
2026-05-06 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | FALSE
2026-05-07 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | FALSE
2026-05-08 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | FALSE
2026-05-09 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | TRUE
2026-05-10 | 2026 | 5 | May | Q2 | FY2026-27 | 19 | TRUE
2026-05-11 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | FALSE
2026-05-12 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | FALSE
2026-05-13 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | FALSE
2026-05-14 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | FALSE
2026-05-15 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | FALSE
2026-05-16 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | TRUE
2026-05-17 | 2026 | 5 | May | Q2 | FY2026-27 | 20 | TRUE
2026-05-18 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | FALSE
2026-05-19 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | FALSE
2026-05-20 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | FALSE
2026-05-21 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | FALSE
2026-05-22 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | FALSE
2026-05-23 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | TRUE
2026-05-24 | 2026 | 5 | May | Q2 | FY2026-27 | 21 | TRUE
2026-05-25 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | FALSE
2026-05-26 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | FALSE
2026-05-27 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | FALSE
2026-05-28 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | FALSE
2026-05-29 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | FALSE
2026-05-30 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | TRUE
2026-05-31 | 2026 | 5 | May | Q2 | FY2026-27 | 22 | TRUE
2026-06-01 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | FALSE
2026-06-02 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | FALSE
2026-06-03 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | FALSE
2026-06-04 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | FALSE
2026-06-05 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | FALSE
2026-06-06 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | TRUE
2026-06-07 | 2026 | 6 | June | Q2 | FY2026-27 | 23 | TRUE
2026-06-08 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | FALSE
2026-06-09 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | FALSE
2026-06-10 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | FALSE
2026-06-11 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | FALSE
2026-06-12 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | FALSE
2026-06-13 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | TRUE
2026-06-14 | 2026 | 6 | June | Q2 | FY2026-27 | 24 | TRUE
2026-06-15 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | FALSE
2026-06-16 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | FALSE
2026-06-17 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | FALSE
2026-06-18 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | FALSE
2026-06-19 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | FALSE
2026-06-20 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | TRUE
2026-06-21 | 2026 | 6 | June | Q2 | FY2026-27 | 25 | TRUE
2026-06-22 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | FALSE
2026-06-23 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | FALSE
2026-06-24 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | FALSE
2026-06-25 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | FALSE
2026-06-26 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | FALSE
2026-06-27 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | TRUE
2026-06-28 | 2026 | 6 | June | Q2 | FY2026-27 | 26 | TRUE
2026-06-29 | 2026 | 6 | June | Q2 | FY2026-27 | 27 | FALSE
2026-06-30 | 2026 | 6 | June | Q2 | FY2026-27 | 27 | FALSE
2026-07-01 | 2026 | 7 | July | Q3 | FY2026-27 | 27 | FALSE
2026-07-02 | 2026 | 7 | July | Q3 | FY2026-27 | 27 | FALSE
2026-07-03 | 2026 | 7 | July | Q3 | FY2026-27 | 27 | FALSE
2026-07-04 | 2026 | 7 | July | Q3 | FY2026-27 | 27 | TRUE
2026-07-05 | 2026 | 7 | July | Q3 | FY2026-27 | 27 | TRUE
2026-07-06 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | FALSE
2026-07-07 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | FALSE
2026-07-08 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | FALSE
2026-07-09 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | FALSE
2026-07-10 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | FALSE
2026-07-11 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | TRUE
2026-07-12 | 2026 | 7 | July | Q3 | FY2026-27 | 28 | TRUE
2026-07-13 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | FALSE
2026-07-14 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | FALSE
2026-07-15 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | FALSE
2026-07-16 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | FALSE
2026-07-17 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | FALSE
2026-07-18 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | TRUE
2026-07-19 | 2026 | 7 | July | Q3 | FY2026-27 | 29 | TRUE
2026-07-20 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | FALSE
2026-07-21 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | FALSE
2026-07-22 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | FALSE
2026-07-23 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | FALSE
2026-07-24 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | FALSE
2026-07-25 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | TRUE
2026-07-26 | 2026 | 7 | July | Q3 | FY2026-27 | 30 | TRUE
2026-07-27 | 2026 | 7 | July | Q3 | FY2026-27 | 31 | FALSE
2026-07-28 | 2026 | 7 | July | Q3 | FY2026-27 | 31 | FALSE
2026-07-29 | 2026 | 7 | July | Q3 | FY2026-27 | 31 | FALSE
2026-07-30 | 2026 | 7 | July | Q3 | FY2026-27 | 31 | FALSE
2026-07-31 | 2026 | 7 | July | Q3 | FY2026-27 | 31 | FALSE
2026-08-01 | 2026 | 8 | August | Q3 | FY2026-27 | 31 | TRUE
2026-08-02 | 2026 | 8 | August | Q3 | FY2026-27 | 31 | TRUE
2026-08-03 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | FALSE
2026-08-04 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | FALSE
2026-08-05 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | FALSE
2026-08-06 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | FALSE
2026-08-07 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | FALSE
2026-08-08 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | TRUE
2026-08-09 | 2026 | 8 | August | Q3 | FY2026-27 | 32 | TRUE
2026-08-10 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | FALSE
2026-08-11 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | FALSE
2026-08-12 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | FALSE
2026-08-13 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | FALSE
2026-08-14 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | FALSE
2026-08-15 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | TRUE
2026-08-16 | 2026 | 8 | August | Q3 | FY2026-27 | 33 | TRUE
2026-08-17 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | FALSE
2026-08-18 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | FALSE
2026-08-19 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | FALSE
2026-08-20 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | FALSE
2026-08-21 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | FALSE
2026-08-22 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | TRUE
2026-08-23 | 2026 | 8 | August | Q3 | FY2026-27 | 34 | TRUE
2026-08-24 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | FALSE
2026-08-25 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | FALSE
2026-08-26 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | FALSE
2026-08-27 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | FALSE
2026-08-28 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | FALSE
2026-08-29 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | TRUE
2026-08-30 | 2026 | 8 | August | Q3 | FY2026-27 | 35 | TRUE
2026-08-31 | 2026 | 8 | August | Q3 | FY2026-27 | 36 | FALSE
2026-09-01 | 2026 | 9 | September | Q3 | FY2026-27 | 36 | FALSE
2026-09-02 | 2026 | 9 | September | Q3 | FY2026-27 | 36 | FALSE
2026-09-03 | 2026 | 9 | September | Q3 | FY2026-27 | 36 | FALSE
2026-09-04 | 2026 | 9 | September | Q3 | FY2026-27 | 36 | FALSE
2026-09-05 | 2026 | 9 | September | Q3 | FY2026-27 | 36 | TRUE
2026-09-06 | 2026 | 9 | September | Q3 | FY2026-27 | 36 | TRUE
2026-09-07 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | FALSE
2026-09-08 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | FALSE
2026-09-09 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | FALSE
2026-09-10 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | FALSE
2026-09-11 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | FALSE
2026-09-12 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | TRUE
2026-09-13 | 2026 | 9 | September | Q3 | FY2026-27 | 37 | TRUE
2026-09-14 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | FALSE
2026-09-15 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | FALSE
2026-09-16 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | FALSE
2026-09-17 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | FALSE
2026-09-18 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | FALSE
2026-09-19 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | TRUE
2026-09-20 | 2026 | 9 | September | Q3 | FY2026-27 | 38 | TRUE
2026-09-21 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | FALSE
2026-09-22 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | FALSE
2026-09-23 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | FALSE
2026-09-24 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | FALSE
2026-09-25 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | FALSE
2026-09-26 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | TRUE
2026-09-27 | 2026 | 9 | September | Q3 | FY2026-27 | 39 | TRUE
2026-09-28 | 2026 | 9 | September | Q3 | FY2026-27 | 40 | FALSE
2026-09-29 | 2026 | 9 | September | Q3 | FY2026-27 | 40 | FALSE
2026-09-30 | 2026 | 9 | September | Q3 | FY2026-27 | 40 | FALSE
2026-10-01 | 2026 | 10 | October | Q4 | FY2026-27 | 40 | FALSE
2026-10-02 | 2026 | 10 | October | Q4 | FY2026-27 | 40 | FALSE
2026-10-03 | 2026 | 10 | October | Q4 | FY2026-27 | 40 | TRUE
2026-10-04 | 2026 | 10 | October | Q4 | FY2026-27 | 40 | TRUE
2026-10-05 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | FALSE
2026-10-06 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | FALSE
2026-10-07 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | FALSE
2026-10-08 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | FALSE
2026-10-09 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | FALSE
2026-10-10 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | TRUE
2026-10-11 | 2026 | 10 | October | Q4 | FY2026-27 | 41 | TRUE
2026-10-12 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | FALSE
2026-10-13 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | FALSE
2026-10-14 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | FALSE
2026-10-15 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | FALSE
2026-10-16 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | FALSE
2026-10-17 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | TRUE
2026-10-18 | 2026 | 10 | October | Q4 | FY2026-27 | 42 | TRUE
2026-10-19 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | FALSE
2026-10-20 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | FALSE
2026-10-21 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | FALSE
2026-10-22 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | FALSE
2026-10-23 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | FALSE
2026-10-24 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | TRUE
2026-10-25 | 2026 | 10 | October | Q4 | FY2026-27 | 43 | TRUE
2026-10-26 | 2026 | 10 | October | Q4 | FY2026-27 | 44 | FALSE
2026-10-27 | 2026 | 10 | October | Q4 | FY2026-27 | 44 | FALSE
2026-10-28 | 2026 | 10 | October | Q4 | FY2026-27 | 44 | FALSE
2026-10-29 | 2026 | 10 | October | Q4 | FY2026-27 | 44 | FALSE
2026-10-30 | 2026 | 10 | October | Q4 | FY2026-27 | 44 | FALSE
2026-10-31 | 2026 | 10 | October | Q4 | FY2026-27 | 44 | TRUE
2026-11-01 | 2026 | 11 | November | Q4 | FY2026-27 | 44 | TRUE
2026-11-02 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | FALSE
2026-11-03 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | FALSE
2026-11-04 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | FALSE
2026-11-05 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | FALSE
2026-11-06 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | FALSE
2026-11-07 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | TRUE
2026-11-08 | 2026 | 11 | November | Q4 | FY2026-27 | 45 | TRUE
2026-11-09 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | FALSE
2026-11-10 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | FALSE
2026-11-11 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | FALSE
2026-11-12 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | FALSE
2026-11-13 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | FALSE
2026-11-14 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | TRUE
2026-11-15 | 2026 | 11 | November | Q4 | FY2026-27 | 46 | TRUE
2026-11-16 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | FALSE
2026-11-17 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | FALSE
2026-11-18 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | FALSE
2026-11-19 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | FALSE
2026-11-20 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | FALSE
2026-11-21 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | TRUE
2026-11-22 | 2026 | 11 | November | Q4 | FY2026-27 | 47 | TRUE
2026-11-23 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | FALSE
2026-11-24 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | FALSE
2026-11-25 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | FALSE
2026-11-26 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | FALSE
2026-11-27 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | FALSE
2026-11-28 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | TRUE
2026-11-29 | 2026 | 11 | November | Q4 | FY2026-27 | 48 | TRUE
2026-11-30 | 2026 | 11 | November | Q4 | FY2026-27 | 49 | FALSE
2026-12-01 | 2026 | 12 | December | Q4 | FY2026-27 | 49 | FALSE
2026-12-02 | 2026 | 12 | December | Q4 | FY2026-27 | 49 | FALSE
2026-12-03 | 2026 | 12 | December | Q4 | FY2026-27 | 49 | FALSE
2026-12-04 | 2026 | 12 | December | Q4 | FY2026-27 | 49 | FALSE
2026-12-05 | 2026 | 12 | December | Q4 | FY2026-27 | 49 | TRUE
2026-12-06 | 2026 | 12 | December | Q4 | FY2026-27 | 49 | TRUE
2026-12-07 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | FALSE
2026-12-08 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | FALSE
2026-12-09 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | FALSE
2026-12-10 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | FALSE
2026-12-11 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | FALSE
2026-12-12 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | TRUE
2026-12-13 | 2026 | 12 | December | Q4 | FY2026-27 | 50 | TRUE
2026-12-14 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | FALSE
2026-12-15 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | FALSE
2026-12-16 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | FALSE
2026-12-17 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | FALSE
2026-12-18 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | FALSE
2026-12-19 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | TRUE
2026-12-20 | 2026 | 12 | December | Q4 | FY2026-27 | 51 | TRUE
2026-12-21 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | FALSE
2026-12-22 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | FALSE
2026-12-23 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | FALSE
2026-12-24 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | FALSE
2026-12-25 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | FALSE
2026-12-26 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | TRUE
2026-12-27 | 2026 | 12 | December | Q4 | FY2026-27 | 52 | TRUE
2026-12-28 | 2026 | 12 | December | Q4 | FY2026-27 | 53 | FALSE
2026-12-29 | 2026 | 12 | December | Q4 | FY2026-27 | 53 | FALSE
2026-12-30 | 2026 | 12 | December | Q4 | FY2026-27 | 53 | FALSE
2026-12-31 | 2026 | 12 | December | Q4 | FY2026-27 | 53 | FALSE