## Projects
ProjectID | ProjectName | ClientID | Region | Technology | ProjectType | ProjectManager | StartDate | PlannedEndDate | ActualEndDate | Status | HealthRAG | PercentComplete | TotalSitesPlanned | BudgetINR | ActualCostINR | ContractValueINR | Priority | SponsorName | ScrumFramework
PRJ-2024001 | Axis Bank Ltd - Last Mile Connectivity (SD-WAN) - East | CL002 | East | SD-WAN | Last Mile Connectivity | Rahul K. Patil | 2024-08-08 | 2024-11-11 | 2024-12-03 | Completed | Green | 100 | 150 | 7265100 | 7401457 | 7682474 | High | Mr. Kapoor | Waterfall
PRJ-2024002 | Bajaj Finance Ltd - Technology Refresh (Hybrid WAN (MPLS+SDWAN)) - South | CL004 | South | Hybrid WAN (MPLS+SDWAN) | Technology Refresh | Sandeep Rao | 2024-10-19 | 2025-02-27 | 2025-03-28 | Completed | Green | 100 | 200 | 7170200 | 7306762 | 8026808 | High | Ms. Singh | Waterfall
PRJ-2024003 | Muthoot Finance - Bandwidth Upgrade (SD-WAN) - East | CL007 | East | SD-WAN | Bandwidth Upgrade | Rahul K. Patil | 2024-11-09 | 2025-08-02 | 2025-08-11 | Completed | Green | 100 | 5 | 476085 | 419678 | 534783 | Medium | Mr. Verma | Waterfall
PRJ-2024004 | Hitachi Payments Services - Bandwidth Upgrade (MPLS) - North | CL001 | North | MPLS | Bandwidth Upgrade | Farah Khan | 2024-08-28 | 2024-11-21 | 2024-12-16 | Completed | Green | 100 | 30 | 2143020 | 2536573 | 2337313 | Medium | Mr. Verma | Waterfall
PRJ-2024005 | Axis Bank Ltd - Last Mile Connectivity (Hybrid WAN (MPLS+SDWAN)) - South | CL002 | South | Hybrid WAN (MPLS+SDWAN) | Last Mile Connectivity | Manish Agarwal | 2024-11-24 | 2025-03-26 | 2025-03-28 | Completed | Green | 100 | 10 | 955890 | 1190857 | 1156626 | High | Ms. Singh | Agile-Hybrid
PRJ-2024006 | Hitachi Payments Services - Technology Refresh (VSAT) - East | CL001 | East | VSAT | Technology Refresh | Ananya Joshi | 2024-07-07 | 2025-01-28 | 2025-02-23 | Completed | Green | 100 | 300 | 22873500 | 24010141 | 29076125 | Low | Mr. Mehta | Agile-Hybrid
PRJ-2024007 | Bajaj Finance Ltd - DR Site Setup (Hybrid WAN (MPLS+SDWAN)) - East | CL004 | East | Hybrid WAN (MPLS+SDWAN) | DR Site Setup | Manish Agarwal | 2024-12-19 | 2025-06-06 | 2025-06-14 | Completed | Green | 100 | 300 | 33445200 | 31362511 | 43458171 | Low | Mr. Singh | Waterfall
PRJ-2024008 | State Bank of India - Last Mile Connectivity (MPLS) - West | CL003 | West | MPLS | Last Mile Connectivity | Farah Khan | 2024-11-03 | 2025-04-10 | 2025-04-28 | Completed | Green | 100 | 30 | 3393120 | 3225383 | 4032066 | Critical | Mr. Verma | Waterfall
PRJ-2024009 | ICICI Bank Ltd - Bandwidth Upgrade (SD-WAN) - West | CL006 | West | SD-WAN | Bandwidth Upgrade | Sandeep Rao | 2024-08-15 | 2024-10-14 | 2024-10-31 | Completed | Green | 100 | 150 | 10428300 | 12670918 | 13219222 | Medium | Mr. Rao | Waterfall
PRJ-2024010 | State Bank of India - DR Site Setup (Hybrid WAN (MPLS+SDWAN)) - North | CL003 | North | Hybrid WAN (MPLS+SDWAN) | DR Site Setup | Deepa Nair | 2024-11-11 | 2025-05-15 | 2025-05-19 | Completed | Green | 100 | 5 | 248310 | 234847 | 275678 | Critical | Mr. Verma | Agile-Hybrid
PRJ-2024011 | Axis Bank Ltd - Network Migration (Hybrid WAN (MPLS+SDWAN)) - South | CL002 | South | Hybrid WAN (MPLS+SDWAN) | Network Migration | Manish Agarwal | 2024-12-16 | 2025-07-04 | 2025-07-02 | Completed | Green | 100 | 10 | 697410 | 851932 | 863962 | High | Ms. Iyer | Waterfall
PRJ-2024012 | Aditya Birla Finance - Technology Refresh (Hybrid WAN (MPLS+SDWAN)) - North | CL008 | North | Hybrid WAN (MPLS+SDWAN) | Technology Refresh | Ananya Joshi | 2024-08-08 | 2024-10-23 |  | In Progress | Yellow | 85 | 25 | 943925 | 684294 | 1158158 | Critical | Mr. Singh | Waterfall
PRJ-2024013 | ICICI Bank Ltd - DR Site Setup (SD-WAN) - South | CL006 | South | SD-WAN | DR Site Setup | Sandeep Rao | 2024-09-22 | 2025-03-25 |  | In Progress | Green | 83 | 15 | 1585170 | 1246221 | 1851864 | Low | Mr. Singh | Waterfall
PRJ-2024014 | Muthoot Finance - Technology Refresh (VSAT) - West | CL007 | West | VSAT | Technology Refresh | Rahul K. Patil | 2024-10-28 | 2025-07-01 |  | In Progress | Green | 17 | 5 | 598480 | 116116 | 748188 | Critical | Mr. Rao | Agile-Hybrid
PRJ-2024015 | Aditya Birla Finance - Technology Refresh (MPLS) - South | CL008 | South | MPLS | Technology Refresh | Farah Khan | 2024-09-15 | 2025-01-16 |  | In Progress | Green | 80 | 250 | 11220000 | 7811232 | 14583987 | Critical | Mr. Rao | Agile-Hybrid
PRJ-2024016 | Muthoot Finance - Technology Refresh (Leased Line) - South | CL007 | South | Leased Line | Technology Refresh | Manish Agarwal | 2024-10-02 | 2025-01-12 |  | In Progress | Green | 43 | 30 | 1058460 | 438798 | 1295711 | Low | Mr. Rao | Waterfall
PRJ-2024017 | Bajaj Finance Ltd - DR Site Setup (SD-WAN) - Central | CL004 | Central | SD-WAN | DR Site Setup | Farah Khan | 2024-07-24 | 2024-12-11 |  | In Progress | Yellow | 74 | 5 | 207860 | 134244 | 244642 | High | Mr. Kapoor | Waterfall
PRJ-2024018 | Bajaj Finance Ltd - New Site Rollout (Leased Line) - Central | CL004 | Central | Leased Line | New Site Rollout | Rahul K. Patil | 2024-08-19 | 2025-03-19 |  | In Progress | Green | 63 | 5 | 580915 | 447912 | 639625 | Medium | Mr. Mehta | Agile-Hybrid
PRJ-2024019 | State Bank of India - Technology Refresh (VSAT) - East | CL003 | East | VSAT | Technology Refresh | Rahul K. Patil | 2024-07-01 | 2024-12-25 |  | In Progress | Yellow | 19 | 75 | 8159400 | 1631449 | 8837561 | Medium | Mr. Rao | Waterfall
PRJ-2024020 | HDFC Bank Ltd - Technology Refresh (MPLS) - Central | CL005 | Central | MPLS | Technology Refresh | Chinmay Deshpande | 2024-12-10 | 2025-07-14 |  | In Progress | Green | 80 | 200 | 20865800 | 20410131 | 22449443 | High | Ms. Singh | Waterfall
PRJ-2024021 | State Bank of India - Bandwidth Upgrade (VSAT) - Central | CL003 | Central | VSAT | Bandwidth Upgrade | Karthik Subramanian | 2025-04-23 | 2025-09-17 |  | In Progress | Green | 74 | 15 | 1771950 | 1246269 | 2262850 | Critical | Mr. Verma | Agile-Hybrid
PRJ-2024022 | HDFC Bank Ltd - New Site Rollout (SD-WAN) - East | CL005 | East | SD-WAN | New Site Rollout | Manish Agarwal | 2025-03-21 | 2025-07-26 |  | In Progress | Green | 81 | 10 | 929120 | 673377 | 1195092 | High | Mr. Mehta | Agile-Hybrid
PRJ-2024023 | Muthoot Finance - New Site Rollout (MPLS) - East | CL007 | East | MPLS | New Site Rollout | Ananya Joshi | 2025-06-26 | 2025-09-04 |  | In Progress | Green | 41 | 300 | 24569400 | 9987542 | 29236870 | Low | Mr. Rao | Agile-Hybrid
PRJ-2024024 | State Bank of India - New Site Rollout (Leased Line) - South | CL003 | South | Leased Line | New Site Rollout | Ananya Joshi | 2025-12-11 | 2026-08-28 |  | In Progress | Yellow | 44 | 300 | 26689200 | 13680294 | 28744906 | Critical | Ms. Rao | Agile-Hybrid
PRJ-2024025 | Aditya Birla Finance - Bandwidth Upgrade (VSAT) - South | CL008 | South | VSAT | Bandwidth Upgrade | Deepa Nair | 2025-04-01 | 2025-11-15 |  | In Progress | Green | 45 | 15 | 1308405 | 728180 | 1465127 | Low | Ms. Singh | Waterfall
PRJ-2024026 | HDFC Bank Ltd - DR Site Setup (MPLS) - East | CL005 | East | MPLS | DR Site Setup | Deepa Nair | 2025-01-04 | 2025-08-04 |  | In Progress | Green | 65 | 30 | 2409270 | 1572412 | 2877022 | Medium | Mr. Verma | Agile-Hybrid
PRJ-2024027 | Hitachi Payments Services - DR Site Setup (Hybrid WAN (MPLS+SDWAN)) - South | CL001 | South | Hybrid WAN (MPLS+SDWAN) | DR Site Setup | Deepa Nair | 2025-06-14 | 2025-08-30 |  | In Progress | Green | 25 | 100 | 7827900 | 2060399 | 9524387 | Medium | Ms. Verma | Waterfall
PRJ-2024028 | State Bank of India - Technology Refresh (MPLS) - West | CL003 | West | MPLS | Technology Refresh | Karthik Subramanian | 2025-11-24 | 2026-03-08 |  | In Progress | Green | 61 | 75 | 8219475 | 4871235 | 9062346 | Medium | Ms. Iyer | Agile-Hybrid
PRJ-2024029 | Bajaj Finance Ltd - Technology Refresh (Hybrid WAN (MPLS+SDWAN)) - South | CL004 | South | Hybrid WAN (MPLS+SDWAN) | Technology Refresh | Deepa Nair | 2025-11-03 | 2026-03-15 |  | In Progress | Yellow | 21 | 50 | 5898000 | 1386118 | 6524132 | High | Mr. Singh | Waterfall
PRJ-2024030 | Bajaj Finance Ltd - DR Site Setup (Leased Line) - North | CL004 | North | Leased Line | DR Site Setup | Manish Agarwal | 2025-08-14 | 2026-03-23 |  | On Hold | Yellow | 51 | 75 | 4536375 | 2336366 | 4930553 | Critical | Mr. Iyer | Agile-Hybrid
PRJ-2024031 | State Bank of India - Technology Refresh (Hybrid WAN (MPLS+SDWAN)) - North | CL003 | North | Hybrid WAN (MPLS+SDWAN) | Technology Refresh | Farah Khan | 2025-09-08 | 2025-12-08 |  | On Hold | Yellow | 62 | 40 | 2099080 | 1382707 | 2497341 | Medium | Ms. Kapoor | Agile-Hybrid
PRJ-2024032 | Aditya Birla Finance - Last Mile Connectivity (MPLS) - West | CL008 | West | MPLS | Last Mile Connectivity | Karthik Subramanian | 2025-08-09 | 2026-04-18 |  | On Hold | Yellow | 69 | 15 | 1778685 | 1424973 | 2083105 | High | Ms. Iyer | Waterfall
PRJ-2024033 | HDFC Bank Ltd - Bandwidth Upgrade (MPLS) - East | CL005 | East | MPLS | Bandwidth Upgrade | Ananya Joshi | 2025-06-18 | 2025-09-06 |  | On Hold | Yellow | 44 | 10 | 547690 | 271728 | 671799 | Critical | Ms. Iyer | Waterfall
PRJ-2024034 | Aditya Birla Finance - New Site Rollout (Leased Line) - South | CL008 | South | Leased Line | New Site Rollout | Manish Agarwal | 2025-07-13 | 2026-03-27 |  | At Risk | Red | 45 | 75 | 2817000 | 1080492 | 3205576 | Low | Ms. Kapoor | Agile-Hybrid
PRJ-2024035 | Aditya Birla Finance - Bandwidth Upgrade (MPLS) - West | CL008 | West | MPLS | Bandwidth Upgrade | Sandeep Rao | 2025-08-01 | 2026-01-07 |  | At Risk | Red | 44 | 25 | 2199850 | 1178766 | 2849202 | Critical | Ms. Kapoor | Waterfall
PRJ-2024036 | Axis Bank Ltd - Network Migration (Leased Line) - West | CL002 | West | Leased Line | Network Migration | Ananya Joshi | 2025-03-02 | 2025-07-06 |  | At Risk | Red | 44 | 30 | 2337180 | 1008551 | 2898821 | Low | Ms. Iyer | Waterfall
PRJ-2024037 | Axis Bank Ltd - New Site Rollout (Leased Line) - Central | CL002 | Central | Leased Line | New Site Rollout | Chinmay Deshpande | 2025-01-12 | 2025-05-09 |  | At Risk | Red | 16 | 100 | 4399300 | 865673 | 4838526 | Critical | Mr. Rao | Agile-Hybrid
PRJ-2024038 | Aditya Birla Finance - DR Site Setup (SD-WAN) - South | CL008 | South | SD-WAN | DR Site Setup | Sandeep Rao | 2025-08-23 | 2025-12-26 |  | At Risk | Red | 53 | 200 | 16670200 | 9655988 | 20620727 | Critical | Mr. Mehta | Waterfall
PRJ-2024039 | Hitachi Payments Services - DR Site Setup (VSAT) - West | CL001 | West | VSAT | DR Site Setup | Ananya Joshi | 2025-07-23 | 2025-11-10 |  | Not Started | Grey | 0 | 8 | 900856 | 0 | 1119872 | Critical | Mr. Mehta | Agile-Hybrid
PRJ-2024040 | ICICI Bank Ltd - DR Site Setup (SD-WAN) - East | CL006 | East | SD-WAN | DR Site Setup | Rahul K. Patil | 2025-01-28 | 2025-07-14 |  | Not Started | Grey | 0 | 250 | 24812750 | 0 | 28300107 | Low | Mr. Iyer | Agile-Hybrid
PRJ-2024041 | HDFC Bank Ltd - DR Site Setup (Hybrid WAN (MPLS+SDWAN)) - West | CL005 | West | Hybrid WAN (MPLS+SDWAN) | DR Site Setup | Deepa Nair | 2025-08-14 | 2026-04-18 |  | Not Started | Grey | 0 | 75 | 5263425 | 0 | 6619718 | Critical | Ms. Iyer | Agile-Hybrid
PRJ-2024042 | Aditya Birla Finance - DR Site Setup (Hybrid WAN (MPLS+SDWAN)) - West | CL008 | West | Hybrid WAN (MPLS+SDWAN) | DR Site Setup | Sandeep Rao | 2025-06-01 | 2025-12-04 | 2025-12-20 | Completed | Green | 100 | 250 | 19400000 | 18136050 | 24239486 | Medium | Ms. Kapoor | Waterfall

## Sites_Milestones
SiteID | ProjectID | ClientID | Region | State | City | Technology | SiteType | Vendor | PlannedInstallDate | ActualInstallDate | DelayDays | CurrentMilestone | SiteStatus | SLAStatus | BandwidthMbps | InstallationCostINR | MonthlyRecurringChargeINR | AssignedEngineer
SITE-00001 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Branch | Airtel Business | 2024-09-30 |  | 637 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 92038 | 12596 | FE-488
SITE-00002 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Data Center | Vodafone Idea Business | 2025-01-25 |  | 520 | Site Survey | Survey Scheduled | Breached | 2 | 40196 | 8320 | FE-213
SITE-00003 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-01-29 | 2025-02-11 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 83771 | 15721 | FE-381
SITE-00004 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Corporate Office | Sify Technologies | 2024-12-07 |  |  | BOM Finalization | Cancelled | N/A | 10 | 43814 | 15317 | FE-198
SITE-00005 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | ATM/Off-site | Airtel Business | 2025-02-24 |  | 490 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 124810 | 11433 | FE-241
SITE-00006 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Airtel Business | 2025-03-14 | 2025-03-16 | 2 | Go-Live | Live - Operational | Met | 34 | 51519 | 8452 | FE-107
SITE-00007 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2024-08-24 | 2024-08-20 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 111606 | 17728 | FE-485
SITE-00008 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Vodafone Idea Business | 2025-01-06 | 2025-01-14 | 8 | Go-Live | Live - Operational | Breached | 100 | 72657 | 6520 | FE-126
SITE-00009 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Vodafone Idea Business | 2025-03-11 | 2025-03-05 | -6 | Go-Live | Live - Operational | Met | 4 | 103631 | 13812 | FE-451
SITE-00010 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Branch | Airtel Business | 2025-03-08 | 2025-03-17 | 9 | Go-Live | Live - Operational | Breached | 4 | 101147 | 16024 | FE-313
SITE-00011 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Data Center | Vodafone Idea Business | 2024-11-18 |  | 588 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 105139 | 10525 | FE-256
SITE-00012 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Branch | Airtel Business | 2025-02-18 |  | 496 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 62687 | 14320 | FE-141
SITE-00013 | PRJ-2024001 | CL002 | East | Odisha | Bhubaneswar | SD-WAN | ATM/Off-site | Tata Communications | 2025-01-01 | 2024-12-26 | -6 | Go-Live | Live - Operational | Met | 50 | 87048 | 14794 | FE-404
SITE-00014 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Local ISP Partner | 2024-10-11 | 2024-10-19 | 8 | Go-Live | Live - Operational | Breached | 100 | 37329 | 14762 | FE-219
SITE-00015 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2024-09-11 |  | 656 | Site Survey | Survey Scheduled | Breached | 6 | 62816 | 17043 | FE-172
SITE-00016 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-03-03 | 2025-03-12 | 9 | Go-Live | Live - Operational | Breached | 20 | 85560 | 5537 | FE-339
SITE-00017 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Vodafone Idea Business | 2024-12-19 | 2025-01-12 | 24 | Go-Live | Live - Operational | Breached | 4 | 106385 | 4153 | FE-321
SITE-00018 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2024-09-05 | 2024-09-09 | 4 | Go-Live | Live - Operational | Met | 2 | 128238 | 14514 | FE-237
SITE-00019 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Data Center | Sify Technologies | 2024-12-11 | 2025-01-03 | 23 | Go-Live | Live - Operational | Breached | 6 | 104720 | 10641 | FE-425
SITE-00020 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Sify Technologies | 2024-11-10 |  | 596 | Site Survey | Survey Scheduled | Breached | 34 | 115835 | 5213 | FE-182
SITE-00021 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Excitel Enterprise | 2024-12-17 |  |  | BOM Finalization | Cancelled | N/A | 2 | 87614 | 4942 | FE-261
SITE-00022 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-02-26 | 2025-03-13 | 15 | Go-Live | Live - Operational | Breached | 100 | 82165 | 4388 | FE-196
SITE-00023 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Data Center | Local ISP Partner | 2025-02-22 |  | 492 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 127613 | 4345 | FE-204
SITE-00024 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Data Center | Tata Communications | 2024-12-03 | 2024-12-20 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 110578 | 13475 | FE-222
SITE-00025 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-08-16 |  | 682 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 57451 | 17285 | FE-158
SITE-00026 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-03-14 |  | 472 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 94698 | 15057 | FE-239
SITE-00027 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Excitel Enterprise | 2024-10-14 |  | 623 | Site Survey | Survey Scheduled | Breached | 6 | 78277 | 6622 | FE-406
SITE-00028 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Corporate Office | Excitel Enterprise | 2024-10-22 | 2024-11-07 | 16 | Go-Live | Live - Operational | Breached | 20 | 28336 | 8134 | FE-471
SITE-00029 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Sify Technologies | 2024-12-05 | 2024-12-29 | 24 | Go-Live | Live - Operational | Breached | 34 | 100340 | 15998 | FE-378
SITE-00030 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-03-23 | 2025-03-24 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 58613 | 17524 | FE-497
SITE-00031 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Vodafone Idea Business | 2025-02-19 | 2025-03-01 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 92923 | 4106 | FE-164
SITE-00032 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Branch | Excitel Enterprise | 2025-03-24 | 2025-04-11 | 18 | Go-Live | Live - Operational | Breached | 100 | 30011 | 15336 | FE-173
SITE-00033 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Excitel Enterprise | 2024-12-11 | 2024-12-17 | 6 | Go-Live | Live - Operational | Breached | 50 | 113175 | 4815 | FE-268
SITE-00034 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Data Center | Excitel Enterprise | 2025-01-20 | 2025-02-06 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 108931 | 4621 | FE-220
SITE-00035 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Branch | Vodafone Idea Business | 2024-12-02 | 2024-11-28 | -4 | Go-Live | Live - Operational | Met | 6 | 118964 | 8406 | FE-114
SITE-00036 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-10-27 | 2024-11-08 | 12 | Go-Live | Live - Operational | Breached | 6 | 60007 | 12202 | FE-310
SITE-00037 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-09-26 | 2024-09-21 | -5 | Go-Live | Live - Operational | Met | 10 | 93230 | 13054 | FE-173
SITE-00038 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Data Center | Sify Technologies | 2024-10-17 |  | 620 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 133464 | 11122 | FE-247
SITE-00039 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2024-12-04 | 2024-12-16 | 12 | Go-Live | Live - Operational | Breached | 50 | 118480 | 7597 | FE-333
SITE-00040 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Data Center | Tata Communications | 2025-03-19 |  | 467 | Site Survey | Survey Complete | Breached | 10 | 77986 | 12870 | FE-283
SITE-00041 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Data Center | Sify Technologies | 2024-10-27 |  |  | Site Survey | Cancelled | N/A | 2 | 102177 | 17673 | FE-451
SITE-00042 | PRJ-2024001 | CL002 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Airtel Business | 2025-03-14 |  | 472 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 56705 | 13930 | FE-197
SITE-00043 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-02-22 |  | 492 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 110242 | 14089 | FE-120
SITE-00044 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Tata Communications | 2025-01-08 | 2025-01-21 | 13 | Go-Live | Live - Operational | Breached | 20 | 70823 | 15746 | FE-312
SITE-00045 | PRJ-2024001 | CL002 | East | Odisha | Bhubaneswar | SD-WAN | Corporate Office | Excitel Enterprise | 2025-03-02 | 2025-03-26 | 24 | Go-Live | Live - Operational | Breached | 20 | 49567 | 7710 | FE-346
SITE-00046 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Airtel Business | 2024-12-10 | 2024-12-04 | -6 | Go-Live | Live - Operational | Met | 50 | 133458 | 12631 | FE-287
SITE-00047 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Branch | Vodafone Idea Business | 2024-10-19 | 2024-11-12 | 24 | Go-Live | Live - Operational | Breached | 34 | 116188 | 15771 | FE-444
SITE-00048 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Branch | Local ISP Partner | 2024-11-16 |  | 590 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 89797 | 3910 | FE-417
SITE-00049 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Branch | Local ISP Partner | 2024-10-08 |  | 629 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 119891 | 8451 | FE-432
SITE-00050 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-08-24 | 2024-08-16 | -8 | Go-Live | Live - Operational | Met | 4 | 40739 | 7346 | FE-375
SITE-00051 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-11-15 |  | 591 | Site Survey | Survey Scheduled | Breached | 6 | 82379 | 14230 | FE-150
SITE-00052 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Airtel Business | 2024-08-21 | 2024-09-07 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 86287 | 7368 | FE-285
SITE-00053 | PRJ-2024001 | CL002 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Tata Communications | 2024-12-30 |  | 546 | Site Survey | Survey Complete | Breached | 50 | 64160 | 6609 | FE-162
SITE-00054 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-10-06 |  | 631 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 131126 | 8964 | FE-224
SITE-00055 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | ATM/Off-site | Excitel Enterprise | 2024-08-30 | 2024-09-24 | 25 | Go-Live | Live - Operational | Breached | 10 | 134568 | 17749 | FE-219
SITE-00056 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Corporate Office | Airtel Business | 2024-08-13 |  | 685 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 98807 | 7606 | FE-189
SITE-00057 | PRJ-2024001 | CL002 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Airtel Business | 2024-09-15 | 2024-09-05 | -10 | Go-Live | Live - Operational | Met | 34 | 30068 | 6354 | FE-235
SITE-00058 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-11-28 |  | 578 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 90422 | 10844 | FE-498
SITE-00059 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | ATM/Off-site | Excitel Enterprise | 2024-12-19 |  | 557 | Site Survey | Survey Scheduled | Breached | 2 | 123321 | 16332 | FE-437
SITE-00060 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Branch | Tata Communications | 2025-01-24 |  | 521 | Site Survey | Survey Scheduled | Breached | 100 | 80640 | 10484 | FE-451
SITE-00061 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Data Center | Tata Communications | 2025-04-02 |  | 453 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 70219 | 13466 | FE-175
SITE-00062 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-01-19 | 2025-02-03 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 77925 | 13287 | FE-371
SITE-00063 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Tata Communications | 2025-01-14 |  | 531 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 113814 | 14164 | FE-493
SITE-00064 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-12-06 |  | 570 | Site Survey | Survey Scheduled | Breached | 34 | 87441 | 10032 | FE-312
SITE-00065 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Sify Technologies | 2024-11-01 |  | 605 | Site Survey | Survey Scheduled | Breached | 6 | 118023 | 11270 | FE-134
SITE-00066 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Airtel Business | 2024-12-01 | 2024-11-27 | -4 | Go-Live | Live - Operational | Met | 2 | 104869 | 12701 | FE-387
SITE-00067 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Data Center | Local ISP Partner | 2024-11-11 |  | 595 | Site Survey | Survey Complete | Breached | 2 | 65700 | 13337 | FE-259
SITE-00068 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | ATM/Off-site | Airtel Business | 2024-12-20 |  | 556 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 57392 | 17381 | FE-155
SITE-00069 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-02-24 | 2025-03-03 | 7 | Go-Live | Live - Operational | Breached | 50 | 101526 | 16073 | FE-418
SITE-00070 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Corporate Office | Tata Communications | 2025-01-28 |  | 517 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 63818 | 15013 | FE-490
SITE-00071 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Excitel Enterprise | 2024-08-14 | 2024-08-14 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 37120 | 5824 | FE-479
SITE-00072 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Data Center | Vodafone Idea Business | 2024-10-07 |  | 630 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 72681 | 6078 | FE-289
SITE-00073 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Branch | Tata Communications | 2025-01-12 |  | 533 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 48632 | 15860 | FE-416
SITE-00074 | PRJ-2024001 | CL002 | East | West Bengal | Siliguri | SD-WAN | Data Center | Vodafone Idea Business | 2024-10-21 | 2024-11-08 | 18 | Go-Live | Live - Operational | Breached | 100 | 82287 | 7975 | FE-210
SITE-00075 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Corporate Office | Local ISP Partner | 2024-12-01 | 2024-11-29 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 97066 | 14430 | FE-257
SITE-00076 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Branch | Tata Communications | 2025-01-13 |  | 532 | Site Survey | Survey Complete | Breached | 10 | 67507 | 6960 | FE-492
SITE-00077 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Branch | Vodafone Idea Business | 2024-11-04 | 2024-11-02 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 51028 | 5616 | FE-294
SITE-00078 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Corporate Office | Tata Communications | 2025-01-03 |  | 542 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 125260 | 4193 | FE-323
SITE-00079 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-21 | 2025-03-31 | 10 | Go-Live | Live - Operational | Breached | 50 | 120995 | 13988 | FE-313
SITE-00080 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Corporate Office | Airtel Business | 2024-08-18 |  | 680 | Site Survey | Survey Complete | Breached | 100 | 118388 | 9428 | FE-145
SITE-00081 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-12-02 | 2024-12-17 | 15 | Go-Live | Live - Operational | Breached | 50 | 68668 | 15719 | FE-273
SITE-00082 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Branch | Excitel Enterprise | 2024-09-01 | 2024-09-23 | 22 | Go-Live | Live - Operational | Breached | 10 | 129741 | 9224 | FE-279
SITE-00083 | PRJ-2024001 | CL002 | East | Odisha | Bhubaneswar | SD-WAN | ATM/Off-site | Airtel Business | 2024-09-19 | 2024-09-25 | 6 | Go-Live | Live - Operational | Breached | 6 | 127642 | 15937 | FE-435
SITE-00084 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Data Center | Excitel Enterprise | 2024-12-17 |  | 559 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 117277 | 17951 | FE-389
SITE-00085 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-11-01 |  | 605 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 89462 | 10745 | FE-423
SITE-00086 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Corporate Office | Excitel Enterprise | 2024-08-27 |  | 671 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 68685 | 11065 | FE-331
SITE-00087 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Tata Communications | 2025-03-13 |  | 473 | Site Survey | Survey Complete | Breached | 4 | 108610 | 13233 | FE-359
SITE-00088 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Vodafone Idea Business | 2025-01-01 |  | 544 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 70143 | 13412 | FE-343
SITE-00089 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Corporate Office | Local ISP Partner | 2024-12-06 | 2024-12-02 | -4 | Go-Live | Live - Operational | Met | 4 | 94132 | 14086 | FE-188
SITE-00090 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Data Center | Excitel Enterprise | 2024-12-03 |  | 573 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 75696 | 9608 | FE-244
SITE-00091 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Local ISP Partner | 2025-02-02 | 2025-02-16 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 36639 | 8901 | FE-148
SITE-00092 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2024-10-16 | 2024-11-03 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 38682 | 13047 | FE-439
SITE-00093 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Data Center | Airtel Business | 2025-01-27 | 2025-02-13 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 68577 | 12657 | FE-292
SITE-00094 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-02-08 |  | 506 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 94648 | 9428 | FE-109
SITE-00095 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Airtel Business | 2024-10-06 | 2024-10-17 | 11 | Go-Live | Live - Operational | Breached | 10 | 46030 | 6038 | FE-139
SITE-00096 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-02-26 |  | 488 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 114760 | 9017 | FE-492
SITE-00097 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | ATM/Off-site | Airtel Business | 2024-11-17 |  | 589 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 118812 | 16133 | FE-419
SITE-00098 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Data Center | Sify Technologies | 2024-08-24 |  | 674 | Site Survey | Survey Scheduled | Breached | 10 | 86222 | 13503 | FE-245
SITE-00099 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-10-13 |  | 624 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 76213 | 14613 | FE-392
SITE-00100 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-28 | 2025-03-07 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 49241 | 16883 | FE-202
SITE-00101 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Corporate Office | Excitel Enterprise | 2024-08-26 | 2024-09-15 | 20 | Go-Live | Live - Operational | Breached | 4 | 121244 | 17359 | FE-364
SITE-00102 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-02-24 | 2025-02-24 | 0 | Go-Live | Live - Operational | Met | 6 | 85340 | 5002 | FE-213
SITE-00103 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Excitel Enterprise | 2024-11-27 | 2024-11-20 | -7 | Go-Live | Live - Operational | Met | 34 | 58903 | 9826 | FE-141
SITE-00104 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Corporate Office | Airtel Business | 2024-11-02 | 2024-10-29 | -4 | Go-Live | Live - Operational | Met | 6 | 33020 | 8200 | FE-341
SITE-00105 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-12-05 |  | 571 | Site Survey | Survey Scheduled | Breached | 4 | 30490 | 7693 | FE-210
SITE-00106 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-01-15 |  | 530 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 129734 | 8220 | FE-221
SITE-00107 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-13 | 2024-10-29 | 16 | Go-Live | Live - Operational | Breached | 4 | 42530 | 17208 | FE-355
SITE-00108 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2024-12-22 |  | 554 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 66177 | 10532 | FE-100
SITE-00109 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-01-06 | 2025-01-22 | 16 | Go-Live | Live - Operational | Breached | 4 | 96614 | 9408 | FE-134
SITE-00110 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Data Center | Tata Communications | 2025-03-24 |  | 462 | Site Survey | Survey Complete | Breached | 50 | 76929 | 7655 | FE-482
SITE-00111 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Branch | Excitel Enterprise | 2024-11-09 | 2024-11-14 | 5 | Go-Live | Live - Operational | Met | 34 | 45486 | 4226 | FE-280
SITE-00112 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Data Center | Local ISP Partner | 2024-09-26 |  | 641 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 110802 | 6486 | FE-169
SITE-00113 | PRJ-2024001 | CL002 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Airtel Business | 2024-08-22 |  | 676 | Site Survey | Survey Scheduled | Breached | 2 | 131692 | 6768 | FE-121
SITE-00114 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-11-22 |  | 584 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 32799 | 15841 | FE-431
SITE-00115 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Branch | Local ISP Partner | 2025-03-21 |  | 465 | Site Survey | Survey Complete | Breached | 34 | 63811 | 5539 | FE-288
SITE-00116 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Sify Technologies | 2025-03-30 |  | 456 | Site Survey | Survey Scheduled | Breached | 6 | 93038 | 14838 | FE-354
SITE-00117 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Branch | Vodafone Idea Business | 2025-02-15 | 2025-03-04 | 17 | Go-Live | Live - Operational | Breached | 6 | 99496 | 8313 | FE-264
SITE-00118 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-01-29 | 2025-02-02 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 49842 | 14801 | FE-327
SITE-00119 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-15 | 2025-02-27 | 12 | Go-Live | Live - Operational | Breached | 20 | 111816 | 16467 | FE-129
SITE-00120 | PRJ-2024001 | CL002 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Excitel Enterprise | 2024-11-24 |  | 582 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 32081 | 5839 | FE-411
SITE-00121 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Sify Technologies | 2024-08-30 | 2024-09-04 | 5 | Go-Live | Live - Operational | Met | 50 | 102349 | 4030 | FE-409
SITE-00122 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-11-15 |  | 591 | Site Survey | Survey Scheduled | Breached | 4 | 103225 | 5755 | FE-371
SITE-00123 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Tata Communications | 2025-01-26 | 2025-01-29 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 124426 | 6548 | FE-355
SITE-00124 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Sify Technologies | 2024-09-12 |  | 655 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 56124 | 13524 | FE-246
SITE-00125 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Airtel Business | 2024-09-16 | 2024-09-10 | -6 | Go-Live | Live - Operational | Met | 100 | 39506 | 16779 | FE-449
SITE-00126 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2024-08-29 |  | 669 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 67315 | 17448 | FE-180
SITE-00127 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Branch | Airtel Business | 2024-10-09 |  | 628 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 59029 | 16449 | FE-352
SITE-00128 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-01-06 |  | 539 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 108209 | 17987 | FE-144
SITE-00129 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Data Center | Excitel Enterprise | 2025-02-12 |  | 502 | Site Survey | Survey Complete | Breached | 50 | 128815 | 10208 | FE-394
SITE-00130 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Data Center | Vodafone Idea Business | 2025-01-24 | 2025-01-21 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 44821 | 17884 | FE-499
SITE-00131 | PRJ-2024001 | CL002 | East | Assam | Guwahati | SD-WAN | Branch | Tata Communications | 2024-12-01 | 2024-12-23 | 22 | Go-Live | Live - Operational | Breached | 6 | 67862 | 6197 | FE-182
SITE-00132 | PRJ-2024001 | CL002 | East | Bihar | Patna | SD-WAN | Branch | Sify Technologies | 2024-12-23 | 2024-12-27 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 111238 | 12524 | FE-240
SITE-00133 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Branch | Excitel Enterprise | 2025-01-17 | 2025-01-29 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 105569 | 13013 | FE-178
SITE-00134 | PRJ-2024001 | CL002 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-02-13 |  | 501 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 31718 | 4830 | FE-123
SITE-00135 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-05 |  | 632 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 93278 | 13775 | FE-379
SITE-00136 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Data Center | Sify Technologies | 2024-10-14 |  | 623 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 37564 | 14782 | FE-130
SITE-00137 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | Data Center | Airtel Business | 2024-12-14 |  | 562 | Site Survey | Survey Scheduled | Breached | 34 | 107516 | 5853 | FE-260
SITE-00138 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | Corporate Office | Excitel Enterprise | 2024-09-15 |  | 652 | Site Survey | Survey Complete | Breached | 4 | 69827 | 7460 | FE-338
SITE-00139 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | ATM/Off-site | Tata Communications | 2024-10-15 |  | 622 | Site Survey | Survey Scheduled | Breached | 2 | 66038 | 9793 | FE-415
SITE-00140 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-03-09 | 2025-03-19 | 10 | Go-Live | Live - Operational | Breached | 34 | 52881 | 16002 | FE-181
SITE-00141 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-03-26 |  | 460 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 39802 | 9942 | FE-358
SITE-00142 | PRJ-2024001 | CL002 | East | Jharkhand | Ranchi | SD-WAN | Branch | Tata Communications | 2025-01-09 | 2025-01-21 | 12 | Go-Live | Live - Operational | Breached | 20 | 92866 | 13289 | FE-434
SITE-00143 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Vodafone Idea Business | 2024-08-15 |  | 683 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 62664 | 15419 | FE-287
SITE-00144 | PRJ-2024001 | CL002 | East | Jharkhand | Jamshedpur | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2024-11-23 | 2024-11-16 | -7 | Go-Live | Live - Operational | Met | 10 | 75516 | 12564 | FE-247
SITE-00145 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2024-12-06 |  | 570 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 44864 | 5084 | FE-301
SITE-00146 | PRJ-2024001 | CL002 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Airtel Business | 2024-11-14 |  | 592 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 93546 | 4159 | FE-123
SITE-00147 | PRJ-2024001 | CL002 | East | West Bengal | Kolkata | SD-WAN | Data Center | Excitel Enterprise | 2024-11-06 |  | 600 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 47521 | 13432 | FE-363
SITE-00148 | PRJ-2024001 | CL002 | East | Odisha | Cuttack | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-11-02 |  | 604 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 105820 | 9011 | FE-359
SITE-00149 | PRJ-2024001 | CL002 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-01-04 |  | 541 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 76281 | 8927 | FE-444
SITE-00150 | PRJ-2024001 | CL002 | East | West Bengal | Howrah | SD-WAN | Branch | Excitel Enterprise | 2024-10-30 |  | 607 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 62803 | 14241 | FE-497
SITE-00151 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-26 | 2025-04-19 | -7 | Go-Live | Live - Operational | Met | 6 | 96712 | 13805 | FE-469
SITE-00152 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-05-22 | 2025-05-27 | 5 | Go-Live | Live - Operational | Met | 4 | 53006 | 3810 | FE-325
SITE-00153 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-02-06 | 2025-02-09 | 3 | Go-Live | Live - Operational | Met | 100 | 124447 | 15417 | FE-131
SITE-00154 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-01-15 |  | 530 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 69124 | 6337 | FE-335
SITE-00155 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-01-22 |  | 523 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 53200 | 7538 | FE-242
SITE-00156 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-01-08 | 2025-01-16 | 8 | Go-Live | Live - Operational | Breached | 100 | 69555 | 11361 | FE-278
SITE-00157 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-01-05 | 2025-01-03 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 79712 | 16908 | FE-276
SITE-00158 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-01-05 | 2024-12-31 | -5 | Go-Live | Live - Operational | Met | 20 | 125955 | 11349 | FE-209
SITE-00159 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-04-20 |  | 435 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 108698 | 15638 | FE-400
SITE-00160 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-04-13 | 2025-05-06 | 23 | Go-Live | Live - Operational | Breached | 10 | 34880 | 5141 | FE-311
SITE-00161 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-04-16 | 2025-04-14 | -2 | Go-Live | Live - Operational | Met | 6 | 81334 | 14196 | FE-343
SITE-00162 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-05-05 | 2025-05-13 | 8 | Go-Live | Live - Operational | Breached | 2 | 128758 | 4965 | FE-433
SITE-00163 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-05-01 |  | 424 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 51040 | 4095 | FE-303
SITE-00164 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-06-05 | 2025-06-01 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 71914 | 8162 | FE-332
SITE-00165 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-08 |  | 386 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 63761 | 6659 | FE-157
SITE-00166 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-02-18 |  | 496 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 29846 | 15568 | FE-272
SITE-00167 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-03-29 | 2025-04-13 | 15 | Go-Live | Live - Operational | Breached | 34 | 39368 | 10067 | FE-442
SITE-00168 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-02-23 | 2025-03-05 | 10 | Go-Live | Live - Operational | Breached | 20 | 78275 | 7358 | FE-328
SITE-00169 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-03-22 | 2025-04-09 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 113679 | 9390 | FE-454
SITE-00170 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2024-11-23 |  | 583 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 81138 | 14740 | FE-357
SITE-00171 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-06-15 |  | 379 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 56721 | 5688 | FE-344
SITE-00172 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-01-27 |  | 518 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 127267 | 12306 | FE-440
SITE-00173 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-05-05 |  | 420 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 97228 | 15030 | FE-285
SITE-00174 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2024-11-08 | 2024-12-03 | 25 | Go-Live | Live - Operational | Breached | 6 | 49566 | 8875 | FE-366
SITE-00175 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-15 |  | 561 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 94895 | 10798 | FE-128
SITE-00176 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-02-07 |  | 507 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 101242 | 11075 | FE-444
SITE-00177 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2024-12-28 |  | 548 | Site Survey | Survey Complete | Breached | 10 | 103800 | 4696 | FE-123
SITE-00178 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2024-11-09 |  |  | ROW / Permission | Cancelled | N/A | 100 | 32159 | 8203 | FE-309
SITE-00179 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-04-28 |  | 427 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 86790 | 17747 | FE-293
SITE-00180 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-04-11 |  | 444 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 43549 | 6424 | FE-375
SITE-00181 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-04-28 | 2025-05-02 | 4 | Go-Live | Live - Operational | Met | 20 | 88686 | 14534 | FE-468
SITE-00182 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-29 |  | 516 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 73371 | 6041 | FE-241
SITE-00183 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-05-19 | 2025-06-04 | 16 | Go-Live | Live - Operational | Breached | 10 | 55011 | 4602 | FE-151
SITE-00184 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-03-26 |  | 460 | Site Survey | Survey Scheduled | Breached | 2 | 80725 | 10691 | FE-219
SITE-00185 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2024-11-28 | 2024-12-20 | 22 | Go-Live | Live - Operational | Breached | 34 | 103690 | 13296 | FE-495
SITE-00186 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-06-05 | 2025-06-04 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 67387 | 8008 | FE-131
SITE-00187 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-06-14 |  | 380 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 100856 | 11620 | FE-124
SITE-00188 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-01-13 |  | 532 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 67306 | 9667 | FE-194
SITE-00189 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-05-29 | 2025-06-02 | 4 | Go-Live | Live - Operational | Met | 6 | 133614 | 11086 | FE-129
SITE-00190 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-03-15 |  | 471 | Site Survey | Survey Scheduled | Breached | 50 | 59831 | 7677 | FE-204
SITE-00191 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-05-28 |  | 397 | Site Survey | Survey Scheduled | Breached | 10 | 34755 | 7898 | FE-293
SITE-00192 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-04 | 2025-05-29 | -6 | Go-Live | Live - Operational | Met | 10 | 90835 | 6922 | FE-270
SITE-00193 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2024-12-11 | 2024-12-08 | -3 | Go-Live | Live - Operational | Met | 10 | 79987 | 7421 | FE-382
SITE-00194 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-02-20 |  | 494 | Site Survey | Survey Complete | Breached | 34 | 68425 | 7785 | FE-284
SITE-00195 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2024-11-18 |  | 588 | Site Survey | Survey Scheduled | Breached | 10 | 76589 | 8626 | FE-311
SITE-00196 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-05-01 | 2025-04-30 | -1 | Go-Live | Live - Operational | Met | 50 | 66691 | 5997 | FE-200
SITE-00197 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-03-18 |  | 468 | Site Survey | Survey Complete | Breached | 34 | 61728 | 16006 | FE-350
SITE-00198 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-04-29 | 2025-05-11 | 12 | Go-Live | Live - Operational | Breached | 100 | 52123 | 12382 | FE-428
SITE-00199 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-05-26 | 2025-05-20 | -6 | Go-Live | Live - Operational | Met | 50 | 46021 | 17304 | FE-422
SITE-00200 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2024-12-01 |  | 575 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 76916 | 4490 | FE-416
SITE-00201 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-02-25 |  | 489 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 29553 | 3774 | FE-371
SITE-00202 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-03-01 | 2025-03-18 | 17 | Go-Live | Live - Operational | Breached | 4 | 96732 | 5939 | FE-223
SITE-00203 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2024-12-31 |  | 545 | Site Survey | Survey Complete | Breached | 34 | 81218 | 11020 | FE-389
SITE-00204 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-04-17 | 2025-04-14 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 77710 | 9679 | FE-382
SITE-00205 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2024-10-26 |  | 611 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 84873 | 14066 | FE-269
SITE-00206 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-06-16 |  | 378 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 118739 | 12786 | FE-343
SITE-00207 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-04-17 | 2025-04-24 | 7 | Go-Live | Live - Operational | Breached | 2 | 51508 | 17433 | FE-261
SITE-00208 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2024-11-29 |  | 577 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 49292 | 12739 | FE-223
SITE-00209 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-06-10 |  | 384 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 127039 | 15619 | FE-171
SITE-00210 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2024-11-06 | 2024-11-04 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 72642 | 13415 | FE-493
SITE-00211 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-05-10 |  | 415 | Site Survey | Survey Complete | Breached | 20 | 130701 | 10881 | FE-351
SITE-00212 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-01-28 |  | 517 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 39232 | 16151 | FE-416
SITE-00213 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2024-11-11 |  | 595 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 77807 | 15160 | FE-424
SITE-00214 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-01-24 | 2025-01-22 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 86292 | 9396 | FE-489
SITE-00215 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2024-11-15 | 2024-11-16 | 1 | Go-Live | Live - Operational | Met | 50 | 41538 | 3930 | FE-145
SITE-00216 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-03-26 |  | 460 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 66253 | 10279 | FE-298
SITE-00217 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-12 |  | 382 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 117825 | 9737 | FE-186
SITE-00218 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2024-12-31 | 2025-01-10 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 84973 | 8021 | FE-315
SITE-00219 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-01-24 | 2025-01-30 | 6 | Go-Live | Live - Operational | Breached | 100 | 105831 | 13603 | FE-200
SITE-00220 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-01-09 | 2024-12-30 | -10 | Go-Live | Live - Operational | Met | 50 | 133391 | 17626 | FE-268
SITE-00221 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-05-20 |  | 405 | Site Survey | Survey Scheduled | Breached | 20 | 70030 | 13383 | FE-455
SITE-00222 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2024-12-08 | 2024-12-15 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 103481 | 16311 | FE-224
SITE-00223 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-05-21 | 2025-06-10 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 101905 | 6773 | FE-403
SITE-00224 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-05-08 |  | 417 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 120847 | 6934 | FE-324
SITE-00225 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-04-14 |  | 441 | Site Survey | Survey Complete | Breached | 20 | 59722 | 7639 | FE-437
SITE-00226 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2024-11-11 |  | 595 | Site Survey | Survey Complete | Breached | 100 | 104315 | 10066 | FE-373
SITE-00227 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-03-12 |  | 474 | Site Survey | Survey Scheduled | Breached | 4 | 42335 | 16098 | FE-227
SITE-00228 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-03-29 |  | 457 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 126655 | 8932 | FE-320
SITE-00229 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2024-12-29 | 2025-01-02 | 4 | Go-Live | Live - Operational | Met | 10 | 86429 | 9629 | FE-300
SITE-00230 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-04-18 |  | 437 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 31219 | 11409 | FE-153
SITE-00231 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2024-11-22 | 2024-11-21 | -1 | Go-Live | Live - Operational | Met | 34 | 87681 | 16349 | FE-205
SITE-00232 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-02-22 | 2025-02-20 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 69800 | 4600 | FE-253
SITE-00233 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2024-10-29 | 2024-11-09 | 11 | Go-Live | Live - Operational | Breached | 6 | 125057 | 7496 | FE-364
SITE-00234 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-16 | 2025-03-24 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 110543 | 6522 | FE-195
SITE-00235 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-04-30 | 2025-05-02 | 2 | Go-Live | Live - Operational | Met | 50 | 78965 | 3572 | FE-460
SITE-00236 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-05-04 | 2025-05-21 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 132792 | 17786 | FE-374
SITE-00237 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2024-12-13 | 2024-12-22 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 97168 | 13971 | FE-260
SITE-00238 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-02-01 |  | 513 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 74135 | 17352 | FE-334
SITE-00239 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-04-22 |  | 433 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 116094 | 5694 | FE-260
SITE-00240 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2024-11-22 | 2024-11-22 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 94954 | 9864 | FE-314
SITE-00241 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-01-30 |  | 515 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 111296 | 12304 | FE-455
SITE-00242 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-05 |  | 540 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 87113 | 13648 | FE-127
SITE-00243 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2024-11-27 |  | 579 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 81626 | 14718 | FE-351
SITE-00244 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-02-26 |  | 488 | Site Survey | Survey Scheduled | Breached | 2 | 132317 | 15969 | FE-212
SITE-00245 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2024-12-20 | 2025-01-01 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 102140 | 15665 | FE-495
SITE-00246 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2024-11-21 |  | 585 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 129595 | 12398 | FE-287
SITE-00247 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-02-13 |  | 501 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 41423 | 15558 | FE-434
SITE-00248 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-02-16 | 2025-02-22 | 6 | Go-Live | Live - Operational | Breached | 100 | 43386 | 16207 | FE-221
SITE-00249 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-29 |  | 457 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 130871 | 6885 | FE-205
SITE-00250 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-03-09 | 2025-03-12 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 70421 | 15035 | FE-249
SITE-00251 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-06-11 |  | 383 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 35770 | 8043 | FE-435
SITE-00252 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2024-11-30 | 2024-12-10 | 10 | Go-Live | Live - Operational | Breached | 50 | 92154 | 5829 | FE-395
SITE-00253 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-02-16 |  | 498 | Site Survey | Survey Complete | Breached | 4 | 80802 | 11947 | FE-483
SITE-00254 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-02-25 |  | 489 | Site Survey | Survey Scheduled | Breached | 2 | 129467 | 17379 | FE-475
SITE-00255 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-04-04 |  | 451 | Site Survey | Survey Scheduled | Breached | 50 | 56551 | 10539 | FE-208
SITE-00256 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-05-24 | 2025-05-28 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 102205 | 17466 | FE-348
SITE-00257 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2024-11-18 | 2024-12-07 | 19 | Go-Live | Live - Operational | Breached | 6 | 85840 | 10979 | FE-100
SITE-00258 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-06-13 |  |  | Site Survey | Cancelled | N/A | 20 | 40234 | 14224 | FE-284
SITE-00259 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-04-12 |  | 443 | Site Survey | Survey Complete | Breached | 50 | 109999 | 8505 | FE-471
SITE-00260 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2024-11-16 |  | 590 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 90496 | 4776 | FE-167
SITE-00261 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-04-16 |  | 439 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 119173 | 9129 | FE-161
SITE-00262 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-02-23 | 2025-02-17 | -6 | Go-Live | Live - Operational | Met | 4 | 123782 | 16704 | FE-152
SITE-00263 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-06-06 |  | 388 | Site Survey | Survey Complete | Breached | 50 | 129379 | 16826 | FE-485
SITE-00264 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-03-08 | 2025-02-26 | -10 | Go-Live | Live - Operational | Met | 6 | 85684 | 9253 | FE-469
SITE-00265 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-30 |  | 456 | Site Survey | Survey Complete | Breached | 4 | 41168 | 5793 | FE-485
SITE-00266 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-01-30 |  | 515 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 131688 | 5790 | FE-226
SITE-00267 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-03-14 | 2025-03-22 | 8 | Go-Live | Live - Operational | Breached | 20 | 54928 | 11982 | FE-410
SITE-00268 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-01-07 |  | 538 | Site Survey | Survey Complete | Breached | 100 | 78578 | 5347 | FE-223
SITE-00269 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2024-11-11 |  | 595 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 69480 | 5662 | FE-298
SITE-00270 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-03-12 |  | 474 | Site Survey | Survey Complete | Breached | 4 | 30187 | 13123 | FE-134
SITE-00271 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2024-11-03 | 2024-10-27 | -7 | Go-Live | Live - Operational | Met | 20 | 110388 | 15175 | FE-356
SITE-00272 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-03 |  |  | Site Survey | Cancelled | N/A | 6 | 64368 | 4869 | FE-258
SITE-00273 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-05-18 | 2025-05-17 | -1 | Go-Live | Live - Operational | Met | 50 | 104865 | 13892 | FE-490
SITE-00274 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-02-12 |  |  | ROW / Permission | Cancelled | N/A | 10 | 39300 | 10618 | FE-159
SITE-00275 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2024-11-07 |  | 599 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 43655 | 3707 | FE-462
SITE-00276 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-28 | 2025-03-12 | 12 | Go-Live | Live - Operational | Breached | 20 | 49884 | 9592 | FE-164
SITE-00277 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-01-17 | 2025-02-03 | 17 | Go-Live | Live - Operational | Breached | 4 | 62465 | 15170 | FE-395
SITE-00278 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-03-03 |  | 483 | Site Survey | Survey Scheduled | Breached | 100 | 102302 | 6234 | FE-288
SITE-00279 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-06-09 | 2025-06-06 | -3 | Go-Live | Live - Operational | Met | 2 | 33772 | 17568 | FE-106
SITE-00280 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-01-25 |  | 520 | Site Survey | Survey Scheduled | Breached | 6 | 32635 | 12558 | FE-465
SITE-00281 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2024-12-26 | 2025-01-03 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 102912 | 9608 | FE-161
SITE-00282 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2024-12-08 | 2024-12-12 | 4 | Go-Live | Live - Operational | Met | 50 | 37034 | 17868 | FE-338
SITE-00283 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2024-11-15 | 2024-11-27 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 54302 | 8277 | FE-388
SITE-00284 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-01-26 |  | 519 | Site Survey | Survey Scheduled | Breached | 10 | 124005 | 12454 | FE-489
SITE-00285 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-02-05 | 2025-01-27 | -9 | Go-Live | Live - Operational | Met | 34 | 111354 | 17255 | FE-455
SITE-00286 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-05-06 | 2025-05-20 | 14 | Go-Live | Live - Operational | Breached | 10 | 97443 | 7402 | FE-314
SITE-00287 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-04-24 | 2025-05-01 | 7 | Go-Live | Live - Operational | Breached | 10 | 96125 | 10267 | FE-458
SITE-00288 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-03-21 | 2025-03-17 | -4 | Go-Live | Live - Operational | Met | 50 | 37808 | 13197 | FE-390
SITE-00289 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2024-11-26 |  | 580 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 69288 | 16620 | FE-301
SITE-00290 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-01-01 |  | 544 | Site Survey | Survey Scheduled | Breached | 10 | 45840 | 16278 | FE-494
SITE-00291 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2024-11-20 | 2024-11-20 | 0 | Go-Live | Live - Operational | Met | 34 | 81282 | 5478 | FE-374
SITE-00292 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-01-10 |  | 535 | Site Survey | Survey Scheduled | Breached | 4 | 39851 | 6082 | FE-451
SITE-00293 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-05-25 | 2025-06-04 | 10 | Go-Live | Live - Operational | Breached | 10 | 74627 | 9992 | FE-362
SITE-00294 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2024-12-29 | 2024-12-29 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 100869 | 15756 | FE-381
SITE-00295 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2024-11-19 |  | 587 | Site Survey | Survey Scheduled | Breached | 2 | 36083 | 17104 | FE-499
SITE-00296 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-05-22 | 2025-06-06 | 15 | Go-Live | Live - Operational | Breached | 4 | 104326 | 13102 | FE-232
SITE-00297 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2024-12-13 | 2024-12-31 | 18 | Go-Live | Live - Operational | Breached | 34 | 44059 | 4199 | FE-336
SITE-00298 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-02-11 |  | 503 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 78165 | 14693 | FE-318
SITE-00299 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-06-13 | 2025-06-14 | 1 | Go-Live | Live - Operational | Met | 100 | 47481 | 4067 | FE-414
SITE-00300 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-04-07 | 2025-04-15 | 8 | Go-Live | Live - Operational | Breached | 100 | 35992 | 4937 | FE-243
SITE-00301 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2024-12-14 |  | 562 | Site Survey | Survey Scheduled | Breached | 2 | 78134 | 16310 | FE-465
SITE-00302 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-05-12 |  | 413 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 78905 | 7930 | FE-192
SITE-00303 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2024-12-19 |  | 557 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 133991 | 11228 | FE-371
SITE-00304 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2024-11-18 | 2024-11-23 | 5 | Go-Live | Live - Operational | Met | 2 | 128145 | 7094 | FE-394
SITE-00305 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2024-12-08 | 2024-12-13 | 5 | Go-Live | Live - Operational | Met | 34 | 105537 | 3962 | FE-460
SITE-00306 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2024-12-11 |  | 565 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 51010 | 11535 | FE-119
SITE-00307 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-03-27 | 2025-03-31 | 4 | Go-Live | Live - Operational | Met | 100 | 28089 | 8935 | FE-414
SITE-00308 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-04-25 | 2025-04-25 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 47360 | 13111 | FE-460
SITE-00309 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-06-01 |  | 393 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 120345 | 14348 | FE-302
SITE-00310 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-09 | 2025-01-14 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 131788 | 13973 | FE-349
SITE-00311 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-03-16 |  | 470 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 115232 | 13149 | FE-189
SITE-00312 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-04-18 |  | 437 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 123529 | 3529 | FE-459
SITE-00313 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2024-11-01 |  | 605 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 134011 | 13516 | FE-213
SITE-00314 | PRJ-2024002 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2024-11-29 |  | 577 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 59194 | 9182 | FE-263
SITE-00315 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-04-13 |  | 442 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 62761 | 6935 | FE-227
SITE-00316 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-05-13 | 2025-05-09 | -4 | Go-Live | Live - Operational | Met | 50 | 85438 | 15502 | FE-314
SITE-00317 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-06 |  | 388 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 41294 | 17079 | FE-345
SITE-00318 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2024-12-20 |  | 556 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 132752 | 17356 | FE-117
SITE-00319 | PRJ-2024002 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2024-12-29 | 2024-12-27 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 77212 | 6136 | FE-474
SITE-00320 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-01-18 | 2025-02-07 | 20 | Go-Live | Live - Operational | Breached | 6 | 107602 | 10613 | FE-180
SITE-00321 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2024-12-15 | 2024-12-16 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 114585 | 8112 | FE-252
SITE-00322 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-02-01 | 2025-02-26 | 25 | Go-Live | Live - Operational | Breached | 2 | 75294 | 3562 | FE-318
SITE-00323 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-02 |  | 453 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 40712 | 3921 | FE-205
SITE-00324 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-02-22 | 2025-02-19 | -3 | Go-Live | Live - Operational | Met | 100 | 92106 | 14330 | FE-235
SITE-00325 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-01-31 |  | 514 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 76418 | 6556 | FE-328
SITE-00326 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-02-20 |  | 494 | Site Survey | Survey Scheduled | Breached | 20 | 101956 | 4509 | FE-177
SITE-00327 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-01-20 |  | 525 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 100561 | 4499 | FE-298
SITE-00328 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-04-17 |  | 438 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 90424 | 8396 | FE-140
SITE-00329 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-03-01 | 2025-03-24 | 23 | Go-Live | Live - Operational | Breached | 6 | 43765 | 15905 | FE-329
SITE-00330 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-05-18 | 2025-05-20 | 2 | Go-Live | Live - Operational | Met | 50 | 38271 | 14692 | FE-322
SITE-00331 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2024-12-29 |  | 547 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 39406 | 9858 | FE-384
SITE-00332 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-31 | 2025-06-03 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 131094 | 14975 | FE-419
SITE-00333 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2024-11-21 |  | 585 | Site Survey | Survey Scheduled | Breached | 6 | 102264 | 13132 | FE-398
SITE-00334 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-05-11 |  | 414 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 81856 | 7827 | FE-296
SITE-00335 | PRJ-2024002 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-02-22 |  | 492 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 80818 | 5856 | FE-416
SITE-00336 | PRJ-2024002 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-02-03 |  |  | Site Survey | Cancelled | N/A | 10 | 34460 | 15718 | FE-343
SITE-00337 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-01-18 | 2025-01-27 | 9 | Go-Live | Live - Operational | Breached | 100 | 119250 | 14720 | FE-150
SITE-00338 | PRJ-2024002 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-05-02 | 2025-05-11 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 107295 | 14076 | FE-145
SITE-00339 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-06-14 | 2025-06-30 | 16 | Go-Live | Live - Operational | Breached | 34 | 35367 | 11942 | FE-181
SITE-00340 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-02 |  | 484 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 50772 | 6658 | FE-202
SITE-00341 | PRJ-2024002 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-02-17 | 2025-02-10 | -7 | Go-Live | Live - Operational | Met | 10 | 63910 | 9535 | FE-337
SITE-00342 | PRJ-2024002 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2024-11-24 |  | 582 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 92066 | 13232 | FE-328
SITE-00343 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-03-14 |  | 472 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 61903 | 15770 | FE-452
SITE-00344 | PRJ-2024002 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-01-30 | 2025-01-23 | -7 | Go-Live | Live - Operational | Met | 10 | 57012 | 14106 | FE-215
SITE-00345 | PRJ-2024002 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-02-05 |  | 509 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 90140 | 5667 | FE-431
SITE-00346 | PRJ-2024002 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2024-12-27 | 2025-01-05 | 9 | Go-Live | Live - Operational | Breached | 50 | 73706 | 11020 | FE-229
SITE-00347 | PRJ-2024002 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-15 | 2025-04-26 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 28963 | 11880 | FE-439
SITE-00348 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-04-17 | 2025-04-15 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 64239 | 13995 | FE-266
SITE-00349 | PRJ-2024002 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-04-24 |  | 431 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 95802 | 16041 | FE-223
SITE-00350 | PRJ-2024002 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-04-11 |  | 444 | Site Survey | Survey Complete | Breached | 6 | 122540 | 3917 | FE-435
SITE-00351 | PRJ-2024003 | CL007 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Vodafone Idea Business | 2025-07-04 | 2025-07-20 | 16 | Go-Live | Live - Operational | Breached | 2 | 104418 | 15101 | FE-392
SITE-00352 | PRJ-2024003 | CL007 | East | Odisha | Cuttack | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-05-15 |  | 410 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 116063 | 9373 | FE-359
SITE-00353 | PRJ-2024003 | CL007 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-06-26 |  | 368 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 40793 | 11213 | FE-165
SITE-00354 | PRJ-2024003 | CL007 | East | Bihar | Patna | SD-WAN | Corporate Office | Local ISP Partner | 2025-07-02 |  | 362 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 57131 | 9320 | FE-214
SITE-00355 | PRJ-2024003 | CL007 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-02-17 | 2025-02-20 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 43437 | 11209 | FE-127
SITE-00356 | PRJ-2024004 | CL001 | North | Uttarakhand | Dehradun | MPLS | ATM/Off-site | Excitel Enterprise | 2025-04-17 |  | 438 | Site Survey | Survey Scheduled | Breached | 4 | 117220 | 9753 | FE-371
SITE-00357 | PRJ-2024004 | CL001 | North | Haryana | Faridabad | MPLS | ATM/Off-site | Airtel Business | 2025-04-12 | 2025-04-11 | -1 | Go-Live | Live - Operational | Met | 34 | 81633 | 12829 | FE-334
SITE-00358 | PRJ-2024004 | CL001 | North | Punjab | Amritsar | MPLS | Branch | Vodafone Idea Business | 2024-10-18 |  | 619 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 110710 | 6397 | FE-260
SITE-00359 | PRJ-2024004 | CL001 | North | Uttarakhand | Dehradun | MPLS | ATM/Off-site | Airtel Business | 2024-12-26 | 2025-01-02 | 7 | Go-Live | Live - Operational | Breached | 6 | 92169 | 16364 | FE-490
SITE-00360 | PRJ-2024004 | CL001 | North | Delhi NCR | Gurugram | MPLS | Data Center | Vodafone Idea Business | 2024-12-22 |  | 554 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 90573 | 9780 | FE-102
SITE-00361 | PRJ-2024004 | CL001 | North | Delhi NCR | Gurugram | MPLS | Branch | Sify Technologies | 2024-12-06 |  | 570 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 30348 | 14587 | FE-102
SITE-00362 | PRJ-2024004 | CL001 | North | Uttarakhand | Dehradun | MPLS | Corporate Office | Airtel Business | 2025-02-26 | 2025-03-10 | 12 | Go-Live | Live - Operational | Breached | 4 | 78272 | 11746 | FE-401
SITE-00363 | PRJ-2024004 | CL001 | North | Haryana | Gurugram | MPLS | Corporate Office | Sify Technologies | 2025-03-31 | 2025-03-23 | -8 | Go-Live | Live - Operational | Met | 100 | 123398 | 12024 | FE-405
SITE-00364 | PRJ-2024004 | CL001 | North | Rajasthan | Udaipur | MPLS | ATM/Off-site | Sify Technologies | 2025-04-17 |  | 438 | Site Survey | Survey Scheduled | Breached | 100 | 75087 | 15789 | FE-196
SITE-00365 | PRJ-2024004 | CL001 | North | Punjab | Amritsar | MPLS | ATM/Off-site | Airtel Business | 2024-10-30 | 2024-11-03 | 4 | Go-Live | Live - Operational | Met | 2 | 105292 | 11767 | FE-186
SITE-00366 | PRJ-2024004 | CL001 | North | Delhi NCR | Noida | MPLS | Branch | Vodafone Idea Business | 2025-02-15 |  | 499 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 129089 | 12261 | FE-419
SITE-00367 | PRJ-2024004 | CL001 | North | Delhi NCR | New Delhi | MPLS | Branch | Tata Communications | 2024-09-29 |  | 638 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 82627 | 10779 | FE-294
SITE-00368 | PRJ-2024004 | CL001 | North | Delhi NCR | Noida | MPLS | ATM/Off-site | Airtel Business | 2025-02-28 |  | 486 | Site Survey | Survey Scheduled | Breached | 2 | 67467 | 10395 | FE-438
SITE-00369 | PRJ-2024004 | CL001 | North | Delhi NCR | Noida | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-02-04 |  | 510 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 95054 | 15276 | FE-416
SITE-00370 | PRJ-2024004 | CL001 | North | Delhi NCR | Noida | MPLS | Data Center | Airtel Business | 2025-03-21 | 2025-03-17 | -4 | Go-Live | Live - Operational | Met | 10 | 129968 | 7808 | FE-367
SITE-00371 | PRJ-2024004 | CL001 | North | Punjab | Amritsar | MPLS | Corporate Office | Airtel Business | 2024-12-15 |  | 561 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 99845 | 11632 | FE-206
SITE-00372 | PRJ-2024004 | CL001 | North | Uttarakhand | Haridwar | MPLS | Branch | Local ISP Partner | 2024-11-01 | 2024-10-27 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 42474 | 17184 | FE-393
SITE-00373 | PRJ-2024004 | CL001 | North | Uttarakhand | Haridwar | MPLS | Branch | Local ISP Partner | 2024-09-25 | 2024-10-17 | 22 | Go-Live | Live - Operational | Breached | 4 | 61540 | 14056 | FE-218
SITE-00374 | PRJ-2024004 | CL001 | North | Uttar Pradesh | Noida | MPLS | Branch | Airtel Business | 2024-12-29 | 2024-12-22 | -7 | Go-Live | Live - Operational | Met | 2 | 66085 | 9401 | FE-446
SITE-00375 | PRJ-2024004 | CL001 | North | Haryana | Faridabad | MPLS | Branch | Tata Communications | 2024-10-01 |  | 636 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 46139 | 14368 | FE-431
SITE-00376 | PRJ-2024004 | CL001 | North | Punjab | Amritsar | MPLS | Data Center | Excitel Enterprise | 2025-04-18 |  | 437 | Site Survey | Survey Complete | Breached | 20 | 124084 | 5022 | FE-290
SITE-00377 | PRJ-2024004 | CL001 | North | Haryana | Gurugram | MPLS | Data Center | Sify Technologies | 2024-12-13 | 2024-12-28 | 15 | Go-Live | Live - Operational | Breached | 50 | 118426 | 17437 | FE-344
SITE-00378 | PRJ-2024004 | CL001 | North | Uttar Pradesh | Kanpur | MPLS | ATM/Off-site | Tata Communications | 2024-10-05 | 2024-09-28 | -7 | Go-Live | Live - Operational | Met | 50 | 105430 | 11408 | FE-391
SITE-00379 | PRJ-2024004 | CL001 | North | Uttarakhand | Haridwar | MPLS | Corporate Office | Excitel Enterprise | 2025-02-05 | 2025-02-19 | 14 | Go-Live | Live - Operational | Breached | 2 | 117714 | 17917 | FE-472
SITE-00380 | PRJ-2024004 | CL001 | North | Punjab | Amritsar | MPLS | Data Center | Vodafone Idea Business | 2024-09-30 |  | 637 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 36301 | 7786 | FE-435
SITE-00381 | PRJ-2024004 | CL001 | North | Haryana | Gurugram | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-04-12 |  | 443 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 115797 | 17805 | FE-273
SITE-00382 | PRJ-2024004 | CL001 | North | Rajasthan | Jaipur | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-02-18 |  | 496 | Site Survey | Survey Scheduled | Breached | 34 | 114993 | 14580 | FE-428
SITE-00383 | PRJ-2024004 | CL001 | North | Uttar Pradesh | Kanpur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-04-18 |  | 437 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 112331 | 6071 | FE-358
SITE-00384 | PRJ-2024004 | CL001 | North | Uttar Pradesh | Varanasi | MPLS | Corporate Office | Airtel Business | 2024-09-21 | 2024-10-12 | 21 | Go-Live | Live - Operational | Breached | 34 | 64458 | 4324 | FE-359
SITE-00385 | PRJ-2024004 | CL001 | North | Punjab | Jalandhar | MPLS | Data Center | Airtel Business | 2024-12-07 |  | 569 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 88174 | 10777 | FE-393
SITE-00386 | PRJ-2024005 | CL002 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-03-23 |  | 463 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 125679 | 14204 | FE-109
SITE-00387 | PRJ-2024005 | CL002 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2024-12-08 |  | 568 | Site Survey | Survey Complete | Breached | 2 | 39913 | 16472 | FE-409
SITE-00388 | PRJ-2024005 | CL002 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-07-14 | 2025-07-25 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 72676 | 9453 | FE-127
SITE-00389 | PRJ-2024005 | CL002 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-04-21 | 2025-05-10 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 121933 | 14267 | FE-286
SITE-00390 | PRJ-2024005 | CL002 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-06-11 | 2025-06-15 | 4 | Go-Live | Live - Operational | Met | 34 | 111055 | 16605 | FE-249
SITE-00391 | PRJ-2024005 | CL002 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-05-27 |  | 398 | Site Survey | Survey Complete | Breached | 6 | 92542 | 5801 | FE-467
SITE-00392 | PRJ-2024005 | CL002 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-05-04 | 2025-05-06 | 2 | Go-Live | Live - Operational | Met | 50 | 56257 | 10988 | FE-197
SITE-00393 | PRJ-2024005 | CL002 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2024-12-10 |  | 566 | Site Survey | Survey Scheduled | Breached | 100 | 87950 | 14288 | FE-401
SITE-00394 | PRJ-2024005 | CL002 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2024-11-30 |  | 576 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 100512 | 10591 | FE-399
SITE-00395 | PRJ-2024005 | CL002 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-05-25 | 2025-05-26 | 1 | Go-Live | Live - Operational | Met | 50 | 114182 | 13339 | FE-410
SITE-00396 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | ATM/Off-site | Sify Technologies | 2024-12-14 |  | 562 | Site Survey | Survey Scheduled | Breached | 50 | 72939 | 8319 | FE-331
SITE-00397 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-12-13 |  | 563 | Site Survey | Survey Complete | Breached | 34 | 121306 | 15572 | FE-383
SITE-00398 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Corporate Office | Local ISP Partner | 2024-12-18 | 2024-12-26 | 8 | Go-Live | Live - Operational | Breached | 6 | 121113 | 14151 | FE-191
SITE-00399 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Corporate Office | Excitel Enterprise | 2024-08-10 |  | 688 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 104389 | 12849 | FE-441
SITE-00400 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Branch | Excitel Enterprise | 2025-02-03 |  | 511 | Site Survey | Survey Scheduled | Breached | 4 | 31312 | 9740 | FE-174
SITE-00401 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | ATM/Off-site | Sify Technologies | 2024-09-01 | 2024-09-08 | 7 | Go-Live | Live - Operational | Breached | 20 | 47192 | 17252 | FE-131
SITE-00402 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Vodafone Idea Business | 2024-07-20 |  | 709 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 108754 | 17721 | FE-445
SITE-00403 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Airtel Business | 2024-12-02 |  | 574 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 118824 | 14387 | FE-124
SITE-00404 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Excitel Enterprise | 2025-01-29 |  | 516 | Site Survey | Survey Scheduled | Breached | 2 | 29699 | 15684 | FE-228
SITE-00405 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | ATM/Off-site | Local ISP Partner | 2025-02-09 |  | 505 | Site Survey | Survey Scheduled | Breached | 34 | 126973 | 13140 | FE-379
SITE-00406 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Corporate Office | Vodafone Idea Business | 2024-08-30 |  | 668 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 117477 | 4720 | FE-195
SITE-00407 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Data Center | Tata Communications | 2024-08-11 |  | 687 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 64583 | 12619 | FE-235
SITE-00408 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Corporate Office | Tata Communications | 2025-02-13 |  | 501 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 89122 | 15127 | FE-179
SITE-00409 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-12-11 | 2024-12-07 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 92297 | 16441 | FE-393
SITE-00410 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-01-28 | 2025-02-07 | 10 | Go-Live | Live - Operational | Breached | 6 | 96236 | 4617 | FE-358
SITE-00411 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Data Center | Tata Communications | 2024-11-26 |  | 580 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 56992 | 17973 | FE-209
SITE-00412 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | ATM/Off-site | Excitel Enterprise | 2024-09-25 |  | 642 | Site Survey | Survey Complete | Breached | 100 | 101575 | 16995 | FE-485
SITE-00413 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Airtel Business | 2024-10-08 |  | 629 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 33226 | 14682 | FE-264
SITE-00414 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-09-15 |  | 652 | Site Survey | Survey Complete | Breached | 20 | 31238 | 11968 | FE-494
SITE-00415 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Local ISP Partner | 2024-07-23 |  | 706 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 69984 | 11919 | FE-142
SITE-00416 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Branch | Local ISP Partner | 2024-11-25 |  | 581 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 55627 | 14482 | FE-422
SITE-00417 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Airtel Business | 2025-02-10 |  | 504 | Site Survey | Survey Scheduled | Breached | 50 | 112746 | 16881 | FE-136
SITE-00418 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Corporate Office | Tata Communications | 2025-01-11 |  | 534 | Site Survey | Survey Scheduled | Breached | 4 | 37600 | 4389 | FE-191
SITE-00419 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | ATM/Off-site | Sify Technologies | 2025-02-07 |  | 507 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 78860 | 10891 | FE-422
SITE-00420 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Branch | Excitel Enterprise | 2024-07-16 | 2024-07-23 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 112072 | 15301 | FE-416
SITE-00421 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Branch | Sify Technologies | 2024-07-23 |  | 706 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 65989 | 16392 | FE-451
SITE-00422 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Data Center | Vodafone Idea Business | 2025-01-23 | 2025-02-01 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 90126 | 6061 | FE-373
SITE-00423 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Warehouse/Ops Hub | Sify Technologies | 2025-01-31 |  | 514 | Site Survey | Survey Complete | Breached | 6 | 67066 | 14596 | FE-473
SITE-00424 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-02-20 |  | 494 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 33475 | 3582 | FE-393
SITE-00425 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Branch | Sify Technologies | 2024-11-29 |  | 577 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 126080 | 15647 | FE-471
SITE-00426 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-02-28 |  | 486 | Site Survey | Survey Complete | Breached | 6 | 52116 | 7117 | FE-415
SITE-00427 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2024-08-27 | 2024-08-20 | -7 | Go-Live | Live - Operational | Met | 4 | 66096 | 14504 | FE-134
SITE-00428 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Sify Technologies | 2025-01-13 | 2025-02-03 | 21 | Go-Live | Live - Operational | Breached | 6 | 115988 | 14239 | FE-220
SITE-00429 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | ATM/Off-site | Sify Technologies | 2024-07-29 |  | 700 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 87067 | 8879 | FE-415
SITE-00430 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Sify Technologies | 2024-12-04 |  | 572 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 50103 | 3579 | FE-260
SITE-00431 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Data Center | Sify Technologies | 2025-01-17 |  | 528 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 45603 | 14634 | FE-475
SITE-00432 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Sify Technologies | 2024-11-03 |  | 603 | Site Survey | Survey Scheduled | Breached | 100 | 100308 | 5283 | FE-189
SITE-00433 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-02-16 | 2025-02-15 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 124147 | 13766 | FE-139
SITE-00434 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Branch | Excitel Enterprise | 2024-12-20 |  | 556 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 128820 | 13167 | FE-208
SITE-00435 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Data Center | Local ISP Partner | 2024-11-28 | 2024-12-22 | 24 | Go-Live | Live - Operational | Breached | 6 | 75948 | 9930 | FE-214
SITE-00436 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-11-07 | 2024-11-29 | 22 | Go-Live | Live - Operational | Breached | 50 | 75692 | 11727 | FE-105
SITE-00437 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-08-23 |  | 675 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 48869 | 6435 | FE-389
SITE-00438 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Sify Technologies | 2025-01-15 |  | 530 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 56681 | 15975 | FE-349
SITE-00439 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Branch | Local ISP Partner | 2024-10-14 | 2024-10-18 | 4 | Go-Live | Live - Operational | Met | 10 | 95880 | 16467 | FE-284
SITE-00440 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Branch | Tata Communications | 2025-02-22 |  | 492 | Site Survey | Survey Scheduled | Breached | 34 | 41529 | 15030 | FE-366
SITE-00441 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-11-28 |  | 578 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 113678 | 9701 | FE-287
SITE-00442 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Airtel Business | 2024-09-14 |  | 653 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 74255 | 16889 | FE-276
SITE-00443 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-07-13 |  | 716 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 49706 | 7268 | FE-139
SITE-00444 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | ATM/Off-site | Sify Technologies | 2024-08-19 | 2024-08-20 | 1 | Go-Live | Live - Operational | Met | 4 | 114652 | 7273 | FE-312
SITE-00445 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Data Center | Vodafone Idea Business | 2024-12-31 |  | 545 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 105436 | 6141 | FE-431
SITE-00446 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-07-23 | 2024-07-21 | -2 | Go-Live | Live - Operational | Met | 6 | 45658 | 13814 | FE-362
SITE-00447 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Corporate Office | Airtel Business | 2024-07-26 | 2024-07-26 | 0 | Go-Live | Live - Operational | Met | 50 | 106558 | 12734 | FE-426
SITE-00448 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Corporate Office | Tata Communications | 2024-12-28 |  | 548 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 86877 | 13437 | FE-341
SITE-00449 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-02-09 | 2025-02-25 | 16 | Go-Live | Live - Operational | Breached | 6 | 109685 | 14307 | FE-361
SITE-00450 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Vodafone Idea Business | 2025-01-03 |  | 542 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 58122 | 9696 | FE-297
SITE-00451 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-09-01 | 2024-09-24 | 23 | Go-Live | Live - Operational | Breached | 50 | 47603 | 13420 | FE-149
SITE-00452 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Branch | Excitel Enterprise | 2024-12-12 |  | 564 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 40214 | 11401 | FE-437
SITE-00453 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Local ISP Partner | 2025-02-08 |  | 506 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 96425 | 10392 | FE-289
SITE-00454 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-10-29 |  | 608 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 73943 | 13150 | FE-479
SITE-00455 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Corporate Office | Vodafone Idea Business | 2024-08-15 |  | 683 | Site Survey | Survey Scheduled | Breached | 10 | 38986 | 8141 | FE-406
SITE-00456 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Branch | Excitel Enterprise | 2024-08-29 | 2024-08-19 | -10 | Go-Live | Live - Operational | Met | 4 | 96126 | 3617 | FE-292
SITE-00457 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Airtel Business | 2024-10-24 | 2024-10-30 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 113403 | 13090 | FE-229
SITE-00458 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-10-13 |  | 624 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 126955 | 6837 | FE-311
SITE-00459 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-14 | 2024-11-08 | 25 | Go-Live | Live - Operational | Breached | 20 | 68193 | 12964 | FE-276
SITE-00460 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-08-11 |  | 687 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 41143 | 7013 | FE-360
SITE-00461 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Branch | Airtel Business | 2024-12-16 |  | 560 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 111345 | 3586 | FE-146
SITE-00462 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Branch | Tata Communications | 2024-10-31 |  | 606 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 57067 | 9575 | FE-140
SITE-00463 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Excitel Enterprise | 2024-10-18 |  | 619 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 121271 | 13288 | FE-129
SITE-00464 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Airtel Business | 2024-11-01 |  | 605 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 53525 | 4050 | FE-406
SITE-00465 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Branch | Sify Technologies | 2024-08-24 |  | 674 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 113854 | 3504 | FE-180
SITE-00466 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Data Center | Vodafone Idea Business | 2024-10-10 |  | 627 | Site Survey | Survey Complete | Breached | 10 | 95861 | 3751 | FE-477
SITE-00467 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-09-22 |  | 645 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 73544 | 16861 | FE-241
SITE-00468 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-11-05 | 2024-11-20 | 15 | Go-Live | Live - Operational | Breached | 20 | 50942 | 10170 | FE-359
SITE-00469 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Corporate Office | Tata Communications | 2024-11-17 | 2024-11-25 | 8 | Go-Live | Live - Operational | Breached | 20 | 98504 | 16822 | FE-394
SITE-00470 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Airtel Business | 2024-12-03 |  | 573 | Site Survey | Survey Complete | Breached | 34 | 129659 | 11017 | FE-448
SITE-00471 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Tata Communications | 2024-08-10 |  | 688 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 111055 | 16421 | FE-212
SITE-00472 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-10-10 |  | 627 | Site Survey | Survey Complete | Breached | 2 | 119857 | 17134 | FE-234
SITE-00473 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Branch | Excitel Enterprise | 2024-10-22 | 2024-11-02 | 11 | Go-Live | Live - Operational | Breached | 6 | 90463 | 8642 | FE-281
SITE-00474 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Data Center | Local ISP Partner | 2024-08-27 | 2024-08-29 | 2 | Go-Live | Live - Operational | Met | 10 | 58783 | 15549 | FE-223
SITE-00475 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-09-01 | 2024-09-06 | 5 | Go-Live | Live - Operational | Met | 6 | 130097 | 5247 | FE-161
SITE-00476 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-11-15 |  | 591 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 91214 | 9581 | FE-417
SITE-00477 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Vodafone Idea Business | 2025-02-19 |  | 495 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 128173 | 11874 | FE-243
SITE-00478 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Branch | Excitel Enterprise | 2024-08-13 |  | 685 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 90694 | 12359 | FE-116
SITE-00479 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | ATM/Off-site | Vodafone Idea Business | 2025-02-17 |  | 497 | Site Survey | Survey Complete | Breached | 4 | 119520 | 11990 | FE-335
SITE-00480 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Data Center | Excitel Enterprise | 2024-12-31 | 2025-01-03 | 3 | Go-Live | Live - Operational | Met | 4 | 70655 | 9424 | FE-413
SITE-00481 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | ATM/Off-site | Sify Technologies | 2024-09-17 |  | 650 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 108358 | 9121 | FE-287
SITE-00482 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Data Center | Local ISP Partner | 2024-09-03 |  | 664 | Site Survey | Survey Scheduled | Breached | 34 | 75851 | 17497 | FE-305
SITE-00483 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-12-05 | 2024-12-03 | -2 | Go-Live | Live - Operational | Met | 10 | 134717 | 5136 | FE-469
SITE-00484 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Data Center | Airtel Business | 2024-10-30 |  | 607 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 132862 | 15600 | FE-176
SITE-00485 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Local ISP Partner | 2024-10-27 | 2024-11-17 | 21 | Go-Live | Live - Operational | Breached | 34 | 130935 | 11472 | FE-253
SITE-00486 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | ATM/Off-site | Tata Communications | 2024-08-06 |  | 692 | Site Survey | Survey Complete | Breached | 10 | 134668 | 7666 | FE-343
SITE-00487 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Corporate Office | Excitel Enterprise | 2024-09-16 | 2024-09-22 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 73107 | 3824 | FE-310
SITE-00488 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | ATM/Off-site | Excitel Enterprise | 2024-12-14 |  | 562 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 130276 | 8163 | FE-281
SITE-00489 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Branch | Vodafone Idea Business | 2024-11-03 |  | 603 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 88784 | 13849 | FE-174
SITE-00490 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-10-27 | 2024-11-11 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 37351 | 4796 | FE-182
SITE-00491 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Local ISP Partner | 2024-10-01 | 2024-10-16 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 107349 | 14061 | FE-302
SITE-00492 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2025-01-19 |  | 526 | Site Survey | Survey Complete | Breached | 100 | 82262 | 6241 | FE-194
SITE-00493 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Corporate Office | Local ISP Partner | 2024-09-10 |  | 657 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 55600 | 6234 | FE-303
SITE-00494 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Tata Communications | 2025-02-21 | 2025-03-13 | 20 | Go-Live | Live - Operational | Breached | 2 | 129047 | 10004 | FE-368
SITE-00495 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Branch | Local ISP Partner | 2024-12-17 | 2024-12-16 | -1 | Go-Live | Live - Operational | Met | 50 | 68549 | 7257 | FE-226
SITE-00496 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | ATM/Off-site | Excitel Enterprise | 2024-08-13 |  | 685 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 31744 | 4075 | FE-439
SITE-00497 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-11-08 |  | 598 | Site Survey | Survey Scheduled | Breached | 100 | 45709 | 14929 | FE-376
SITE-00498 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2024-11-05 |  | 601 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 73504 | 11391 | FE-376
SITE-00499 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Corporate Office | Vodafone Idea Business | 2024-09-28 |  | 639 | Site Survey | Survey Scheduled | Breached | 20 | 48410 | 8473 | FE-105
SITE-00500 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Data Center | Excitel Enterprise | 2024-10-08 | 2024-10-16 | 8 | Go-Live | Live - Operational | Breached | 2 | 118147 | 11559 | FE-486
SITE-00501 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Excitel Enterprise | 2025-01-24 | 2025-02-10 | 17 | Go-Live | Live - Operational | Breached | 10 | 132433 | 3618 | FE-380
SITE-00502 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-22 |  | 492 | Site Survey | Survey Complete | Breached | 50 | 60754 | 6175 | FE-466
SITE-00503 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Data Center | Local ISP Partner | 2024-09-17 | 2024-09-12 | -5 | Go-Live | Live - Operational | Met | 10 | 95713 | 16026 | FE-413
SITE-00504 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Sify Technologies | 2025-01-18 |  | 527 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 52641 | 17483 | FE-135
SITE-00505 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Data Center | Excitel Enterprise | 2024-08-09 | 2024-08-24 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 63669 | 14976 | FE-418
SITE-00506 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Branch | Excitel Enterprise | 2024-07-16 | 2024-07-15 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 52371 | 5175 | FE-244
SITE-00507 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Branch | Airtel Business | 2024-11-01 |  | 605 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 47750 | 3741 | FE-352
SITE-00508 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Data Center | Sify Technologies | 2024-09-29 |  | 638 | Site Survey | Survey Scheduled | Breached | 100 | 119348 | 16466 | FE-116
SITE-00509 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Data Center | Tata Communications | 2024-07-26 | 2024-08-02 | 7 | Go-Live | Live - Operational | Breached | 100 | 51803 | 6648 | FE-228
SITE-00510 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Vodafone Idea Business | 2025-01-24 | 2025-01-29 | 5 | Go-Live | Live - Operational | Met | 10 | 124681 | 4049 | FE-201
SITE-00511 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-12-29 |  | 547 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 117318 | 8613 | FE-265
SITE-00512 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-07-22 |  | 707 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 61202 | 11384 | FE-426
SITE-00513 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Branch | Local ISP Partner | 2025-02-24 |  | 490 | Site Survey | Survey Complete | Breached | 10 | 42801 | 7366 | FE-424
SITE-00514 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-08-23 | 2024-08-30 | 7 | Go-Live | Live - Operational | Breached | 50 | 131434 | 7482 | FE-104
SITE-00515 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-11-10 |  |  | ROW / Permission | Cancelled | N/A | 34 | 129029 | 4966 | FE-227
SITE-00516 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Branch | Tata Communications | 2025-01-03 | 2025-01-14 | 11 | Go-Live | Live - Operational | Breached | 34 | 112485 | 6021 | FE-459
SITE-00517 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Corporate Office | Excitel Enterprise | 2024-11-13 | 2024-11-17 | 4 | Go-Live | Live - Operational | Met | 34 | 133581 | 10687 | FE-475
SITE-00518 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | ATM/Off-site | Sify Technologies | 2024-10-16 |  |  | BOM Finalization | Cancelled | N/A | 2 | 91609 | 15077 | FE-324
SITE-00519 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Data Center | Airtel Business | 2025-01-06 |  | 539 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 99253 | 9196 | FE-265
SITE-00520 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-03-03 |  | 483 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 97617 | 6039 | FE-330
SITE-00521 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Tata Communications | 2024-10-13 |  | 624 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 124161 | 6539 | FE-109
SITE-00522 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Corporate Office | Local ISP Partner | 2024-09-11 |  | 656 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 114283 | 12330 | FE-298
SITE-00523 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-11-16 |  | 590 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 70283 | 10214 | FE-428
SITE-00524 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Branch | Airtel Business | 2024-11-22 | 2024-11-16 | -6 | Go-Live | Live - Operational | Met | 6 | 32099 | 6810 | FE-154
SITE-00525 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Excitel Enterprise | 2024-07-20 | 2024-08-03 | 14 | Go-Live | Live - Operational | Breached | 20 | 34433 | 9502 | FE-213
SITE-00526 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Tata Communications | 2025-03-04 | 2025-03-07 | 3 | Go-Live | Live - Operational | Met | 100 | 132991 | 13968 | FE-131
SITE-00527 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Branch | Excitel Enterprise | 2025-01-31 |  | 514 | Site Survey | Survey Complete | Breached | 20 | 97339 | 4166 | FE-475
SITE-00528 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Branch | Tata Communications | 2024-09-05 | 2024-09-28 | 23 | Go-Live | Live - Operational | Breached | 10 | 97685 | 9813 | FE-197
SITE-00529 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-09-13 |  | 654 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 101193 | 15774 | FE-385
SITE-00530 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Local ISP Partner | 2024-12-06 |  | 570 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 120084 | 14399 | FE-318
SITE-00531 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-11-29 | 2024-12-14 | 15 | Go-Live | Live - Operational | Breached | 6 | 97979 | 13329 | FE-326
SITE-00532 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Vodafone Idea Business | 2024-10-03 |  | 634 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 123140 | 8799 | FE-411
SITE-00533 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Data Center | Excitel Enterprise | 2024-09-04 |  | 663 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 75187 | 10912 | FE-329
SITE-00534 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Excitel Enterprise | 2024-07-20 |  | 709 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 95844 | 5713 | FE-254
SITE-00535 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Branch | Local ISP Partner | 2024-09-04 | 2024-09-14 | 10 | Go-Live | Live - Operational | Breached | 20 | 100569 | 11876 | FE-384
SITE-00536 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Corporate Office | Airtel Business | 2024-07-21 | 2024-08-09 | 19 | Go-Live | Live - Operational | Breached | 6 | 62732 | 9514 | FE-398
SITE-00537 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Branch | Excitel Enterprise | 2025-02-04 | 2025-02-13 | 9 | Go-Live | Live - Operational | Breached | 50 | 102588 | 7062 | FE-475
SITE-00538 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | ATM/Off-site | Vodafone Idea Business | 2025-01-30 | 2025-02-09 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 106018 | 14022 | FE-253
SITE-00539 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Branch | Tata Communications | 2024-10-17 |  | 620 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 73603 | 17914 | FE-322
SITE-00540 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Tata Communications | 2025-01-19 | 2025-01-09 | -10 | Go-Live | Live - Operational | Met | 20 | 96731 | 4174 | FE-263
SITE-00541 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | ATM/Off-site | Airtel Business | 2024-11-17 | 2024-12-04 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 116294 | 15486 | FE-301
SITE-00542 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Airtel Business | 2024-10-30 | 2024-11-07 | 8 | Go-Live | Live - Operational | Breached | 6 | 72062 | 4852 | FE-343
SITE-00543 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Corporate Office | Tata Communications | 2024-10-22 |  | 615 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 93774 | 10618 | FE-496
SITE-00544 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-12-02 |  | 574 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 113491 | 12860 | FE-200
SITE-00545 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Sify Technologies | 2024-07-30 | 2024-08-06 | 7 | Go-Live | Live - Operational | Breached | 4 | 42749 | 14505 | FE-311
SITE-00546 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Excitel Enterprise | 2024-08-29 | 2024-09-03 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 128883 | 8494 | FE-186
SITE-00547 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Tata Communications | 2024-08-18 |  | 680 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 54173 | 14728 | FE-291
SITE-00548 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | ATM/Off-site | Excitel Enterprise | 2024-08-09 | 2024-08-02 | -7 | Go-Live | Live - Operational | Met | 6 | 65707 | 3725 | FE-275
SITE-00549 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Branch | Sify Technologies | 2024-11-09 |  | 597 | Site Survey | Survey Scheduled | Breached | 10 | 124994 | 12314 | FE-208
SITE-00550 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Corporate Office | Excitel Enterprise | 2025-01-20 |  | 525 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 109663 | 15459 | FE-172
SITE-00551 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Warehouse/Ops Hub | Tata Communications | 2025-02-28 |  | 486 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 50324 | 4484 | FE-245
SITE-00552 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Vodafone Idea Business | 2024-09-19 |  | 648 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 36729 | 9867 | FE-438
SITE-00553 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Airtel Business | 2024-07-16 | 2024-07-24 | 8 | Go-Live | Live - Operational | Breached | 50 | 94655 | 15127 | FE-150
SITE-00554 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Branch | Airtel Business | 2024-11-25 |  | 581 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 93621 | 11003 | FE-387
SITE-00555 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Corporate Office | Vodafone Idea Business | 2024-11-24 | 2024-12-03 | 9 | Go-Live | Live - Operational | Breached | 50 | 125568 | 6072 | FE-109
SITE-00556 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Airtel Business | 2024-12-19 |  | 557 | Site Survey | Survey Complete | Breached | 20 | 134416 | 4515 | FE-420
SITE-00557 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | ATM/Off-site | Airtel Business | 2024-12-01 | 2024-12-08 | 7 | Go-Live | Live - Operational | Breached | 34 | 79491 | 14263 | FE-170
SITE-00558 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-11-22 |  | 584 | Site Survey | Survey Complete | Breached | 10 | 82700 | 7438 | FE-393
SITE-00559 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Corporate Office | Vodafone Idea Business | 2025-03-01 | 2025-03-15 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 55100 | 14190 | FE-170
SITE-00560 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-09-29 | 2024-10-22 | 23 | Go-Live | Live - Operational | Breached | 6 | 114013 | 12754 | FE-180
SITE-00561 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Branch | Airtel Business | 2024-11-25 |  | 581 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 47073 | 15412 | FE-115
SITE-00562 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Local ISP Partner | 2024-09-27 |  | 640 | Site Survey | Survey Complete | Breached | 20 | 47917 | 16264 | FE-196
SITE-00563 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-07-18 | 2024-07-25 | 7 | Go-Live | Live - Operational | Breached | 10 | 106166 | 7304 | FE-218
SITE-00564 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | ATM/Off-site | Excitel Enterprise | 2025-01-04 | 2025-01-24 | 20 | Go-Live | Live - Operational | Breached | 100 | 121325 | 14142 | FE-291
SITE-00565 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | ATM/Off-site | Airtel Business | 2024-11-10 |  | 596 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 57658 | 4028 | FE-309
SITE-00566 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | ATM/Off-site | Airtel Business | 2024-09-06 |  | 661 | Site Survey | Survey Complete | Breached | 4 | 51209 | 10697 | FE-415
SITE-00567 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | ATM/Off-site | Vodafone Idea Business | 2025-02-24 |  | 490 | Site Survey | Survey Scheduled | Breached | 50 | 129740 | 4185 | FE-411
SITE-00568 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-12-15 |  | 561 | Site Survey | Survey Complete | Breached | 2 | 96242 | 5291 | FE-331
SITE-00569 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Local ISP Partner | 2024-11-21 | 2024-12-15 | 24 | Go-Live | Live - Operational | Breached | 2 | 101098 | 9847 | FE-364
SITE-00570 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Corporate Office | Sify Technologies | 2024-11-01 | 2024-11-08 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 49821 | 10421 | FE-250
SITE-00571 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Local ISP Partner | 2024-11-21 |  |  | Site Survey | Cancelled | N/A | 100 | 39854 | 15339 | FE-356
SITE-00572 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-02-25 |  | 489 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 82206 | 8799 | FE-330
SITE-00573 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-12-10 |  | 566 | Site Survey | Survey Scheduled | Breached | 4 | 60778 | 8809 | FE-454
SITE-00574 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Tata Communications | 2024-08-12 |  | 686 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 111109 | 9446 | FE-143
SITE-00575 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2025-01-30 |  | 515 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 77634 | 12516 | FE-294
SITE-00576 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Airtel Business | 2024-12-03 | 2024-12-19 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 51444 | 16101 | FE-464
SITE-00577 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Data Center | Sify Technologies | 2024-09-29 | 2024-10-17 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 43408 | 5655 | FE-203
SITE-00578 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Data Center | Vodafone Idea Business | 2024-07-15 | 2024-08-03 | 19 | Go-Live | Live - Operational | Breached | 2 | 107689 | 17962 | FE-352
SITE-00579 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Data Center | Vodafone Idea Business | 2024-12-27 |  | 549 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 85917 | 4800 | FE-407
SITE-00580 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Corporate Office | Excitel Enterprise | 2025-02-22 | 2025-03-19 | 25 | Go-Live | Live - Operational | Breached | 10 | 34411 | 6528 | FE-175
SITE-00581 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Branch | Local ISP Partner | 2024-07-21 | 2024-07-20 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 71399 | 4936 | FE-125
SITE-00582 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-08-22 | 2024-08-30 | 8 | Go-Live | Live - Operational | Breached | 6 | 87682 | 15777 | FE-396
SITE-00583 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Sify Technologies | 2025-01-24 | 2025-02-02 | 9 | Go-Live | Live - Operational | Breached | 50 | 36869 | 15926 | FE-318
SITE-00584 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Branch | Local ISP Partner | 2024-11-09 | 2024-11-08 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 71150 | 12135 | FE-311
SITE-00585 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Branch | Tata Communications | 2024-09-03 |  |  | ROW / Permission | Cancelled | N/A | 4 | 91394 | 15363 | FE-452
SITE-00586 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Corporate Office | Sify Technologies | 2024-12-14 |  | 562 | Site Survey | Survey Scheduled | Breached | 34 | 45001 | 13564 | FE-388
SITE-00587 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | ATM/Off-site | Excitel Enterprise | 2025-02-03 |  | 511 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 120875 | 8259 | FE-199
SITE-00588 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Excitel Enterprise | 2024-11-08 | 2024-11-05 | -3 | Go-Live | Live - Operational | Met | 50 | 82269 | 4245 | FE-270
SITE-00589 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Sify Technologies | 2024-12-22 | 2024-12-24 | 2 | Go-Live | Live - Operational | Met | 4 | 68340 | 8419 | FE-359
SITE-00590 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Corporate Office | Vodafone Idea Business | 2024-08-10 | 2024-08-21 | 11 | Go-Live | Live - Operational | Breached | 2 | 51020 | 6678 | FE-269
SITE-00591 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Branch | Local ISP Partner | 2025-02-01 |  | 513 | Site Survey | Survey Scheduled | Breached | 6 | 91110 | 6045 | FE-421
SITE-00592 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Data Center | Local ISP Partner | 2025-01-28 |  | 517 | Site Survey | Survey Scheduled | Breached | 2 | 96298 | 8404 | FE-389
SITE-00593 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Tata Communications | 2024-12-06 | 2024-12-17 | 11 | Go-Live | Live - Operational | Breached | 6 | 64760 | 17274 | FE-115
SITE-00594 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | ATM/Off-site | Excitel Enterprise | 2024-11-25 |  | 581 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 52560 | 13251 | FE-159
SITE-00595 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Vodafone Idea Business | 2024-07-20 |  | 709 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 93149 | 17869 | FE-221
SITE-00596 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Airtel Business | 2024-09-05 | 2024-09-16 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 77049 | 16360 | FE-119
SITE-00597 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Branch | Vodafone Idea Business | 2024-11-18 |  | 588 | Site Survey | Survey Scheduled | Breached | 6 | 52931 | 9072 | FE-347
SITE-00598 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Branch | Excitel Enterprise | 2024-08-17 | 2024-09-05 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 54894 | 15371 | FE-118
SITE-00599 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Warehouse/Ops Hub | Tata Communications | 2025-02-18 |  | 496 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 68760 | 4221 | FE-451
SITE-00600 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Branch | Excitel Enterprise | 2024-11-08 | 2024-11-04 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 30946 | 12962 | FE-488
SITE-00601 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Sify Technologies | 2024-09-01 | 2024-09-02 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 129290 | 10727 | FE-443
SITE-00602 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Branch | Tata Communications | 2024-08-21 | 2024-08-28 | 7 | Go-Live | Live - Operational | Breached | 4 | 55076 | 12388 | FE-279
SITE-00603 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-08-17 | 2024-08-25 | 8 | Go-Live | Live - Operational | Breached | 6 | 37337 | 8601 | FE-413
SITE-00604 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Local ISP Partner | 2024-08-14 | 2024-08-05 | -9 | Go-Live | Live - Operational | Met | 2 | 41884 | 9784 | FE-127
SITE-00605 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-08-26 |  | 672 | Site Survey | Survey Complete | Breached | 100 | 108781 | 9326 | FE-259
SITE-00606 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Tata Communications | 2025-01-22 |  | 523 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 102421 | 5659 | FE-147
SITE-00607 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Vodafone Idea Business | 2024-09-29 |  | 638 | Site Survey | Survey Scheduled | Breached | 10 | 57333 | 5854 | FE-415
SITE-00608 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Sify Technologies | 2024-08-27 |  | 671 | Site Survey | Survey Complete | Breached | 100 | 91898 | 3995 | FE-133
SITE-00609 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Sify Technologies | 2024-11-11 | 2024-11-20 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 107225 | 12915 | FE-165
SITE-00610 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Branch | Sify Technologies | 2025-02-06 |  | 508 | Site Survey | Survey Complete | Breached | 4 | 131865 | 8449 | FE-372
SITE-00611 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | ATM/Off-site | Excitel Enterprise | 2024-10-25 |  | 612 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 99820 | 6105 | FE-346
SITE-00612 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2024-09-03 | 2024-09-20 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 102345 | 16399 | FE-275
SITE-00613 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-28 | 2024-12-22 | -6 | Go-Live | Live - Operational | Met | 4 | 105616 | 13266 | FE-337
SITE-00614 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Vodafone Idea Business | 2024-08-26 |  | 672 | Site Survey | Survey Scheduled | Breached | 4 | 106415 | 5281 | FE-450
SITE-00615 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Branch | Tata Communications | 2024-11-15 | 2024-11-30 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 46208 | 13015 | FE-486
SITE-00616 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Excitel Enterprise | 2024-08-19 |  | 679 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 79115 | 13585 | FE-395
SITE-00617 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Excitel Enterprise | 2025-01-02 | 2025-01-12 | 10 | Go-Live | Live - Operational | Breached | 20 | 84980 | 15260 | FE-276
SITE-00618 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Data Center | Airtel Business | 2024-12-15 | 2025-01-06 | 22 | Go-Live | Live - Operational | Breached | 20 | 36180 | 9549 | FE-381
SITE-00619 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Corporate Office | Tata Communications | 2024-12-02 |  | 574 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 32087 | 7354 | FE-321
SITE-00620 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Data Center | Vodafone Idea Business | 2024-10-01 |  | 636 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 85041 | 12431 | FE-208
SITE-00621 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Data Center | Sify Technologies | 2024-08-29 | 2024-09-23 | 25 | Go-Live | Live - Operational | Breached | 50 | 48220 | 8226 | FE-443
SITE-00622 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | ATM/Off-site | Local ISP Partner | 2024-07-30 | 2024-07-21 | -9 | Go-Live | Live - Operational | Met | 100 | 114235 | 10655 | FE-169
SITE-00623 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Vodafone Idea Business | 2025-02-03 |  | 511 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 109690 | 6445 | FE-332
SITE-00624 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Data Center | Vodafone Idea Business | 2025-02-06 |  | 508 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 57588 | 6544 | FE-317
SITE-00625 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | ATM/Off-site | Local ISP Partner | 2024-11-16 |  | 590 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 81849 | 12448 | FE-395
SITE-00626 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Corporate Office | Tata Communications | 2024-12-04 | 2024-12-24 | 20 | Go-Live | Live - Operational | Breached | 100 | 118504 | 4811 | FE-172
SITE-00627 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Branch | Excitel Enterprise | 2024-11-21 |  | 585 | Site Survey | Survey Scheduled | Breached | 4 | 60142 | 11240 | FE-422
SITE-00628 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-11-27 |  | 579 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 73029 | 12265 | FE-498
SITE-00629 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Data Center | Excitel Enterprise | 2024-11-20 |  | 586 | Site Survey | Survey Scheduled | Breached | 34 | 83183 | 9282 | FE-250
SITE-00630 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Sify Technologies | 2025-01-05 | 2025-01-14 | 9 | Go-Live | Live - Operational | Breached | 2 | 110483 | 11252 | FE-396
SITE-00631 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-12-27 | 2025-01-04 | 8 | Go-Live | Live - Operational | Breached | 20 | 91538 | 4851 | FE-164
SITE-00632 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-09-14 | 2024-09-13 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 61679 | 3732 | FE-479
SITE-00633 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Data Center | Sify Technologies | 2025-03-01 | 2025-02-28 | -1 | Go-Live | Live - Operational | Met | 6 | 62242 | 16320 | FE-458
SITE-00634 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Branch | Sify Technologies | 2025-02-01 | 2025-02-24 | 23 | Go-Live | Live - Operational | Breached | 4 | 47014 | 13257 | FE-178
SITE-00635 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Data Center | Local ISP Partner | 2024-09-10 |  | 657 | Site Survey | Survey Complete | Breached | 6 | 55637 | 12965 | FE-475
SITE-00636 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Branch | Tata Communications | 2024-09-17 |  | 650 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 88819 | 10033 | FE-343
SITE-00637 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Local ISP Partner | 2024-09-09 |  | 658 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 90205 | 7802 | FE-174
SITE-00638 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Data Center | Local ISP Partner | 2024-09-23 | 2024-10-11 | 18 | Go-Live | Live - Operational | Breached | 34 | 97501 | 14688 | FE-121
SITE-00639 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Data Center | Excitel Enterprise | 2024-10-10 |  | 627 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 71904 | 7929 | FE-236
SITE-00640 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Data Center | Vodafone Idea Business | 2024-12-08 |  | 568 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 124247 | 14508 | FE-401
SITE-00641 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | ATM/Off-site | Sify Technologies | 2025-01-01 | 2025-01-18 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 116185 | 3638 | FE-134
SITE-00642 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Data Center | Sify Technologies | 2024-11-23 | 2024-11-19 | -4 | Go-Live | Live - Operational | Met | 10 | 123060 | 8141 | FE-228
SITE-00643 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Branch | Excitel Enterprise | 2024-12-17 | 2024-12-12 | -5 | Go-Live | Live - Operational | Met | 10 | 106562 | 13954 | FE-162
SITE-00644 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Local ISP Partner | 2024-08-14 |  | 684 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 42528 | 14897 | FE-194
SITE-00645 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Branch | Local ISP Partner | 2024-12-28 |  | 548 | Site Survey | Survey Scheduled | Breached | 100 | 64226 | 16105 | FE-318
SITE-00646 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Corporate Office | Tata Communications | 2025-01-27 | 2025-01-21 | -6 | Go-Live | Live - Operational | Met | 50 | 78933 | 8950 | FE-130
SITE-00647 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Airtel Business | 2024-11-01 | 2024-10-26 | -6 | Go-Live | Live - Operational | Met | 50 | 51388 | 14075 | FE-351
SITE-00648 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Airtel Business | 2025-01-24 |  | 521 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 85878 | 15221 | FE-232
SITE-00649 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Tata Communications | 2024-07-30 | 2024-08-05 | 6 | Go-Live | Live - Operational | Breached | 100 | 47510 | 14196 | FE-427
SITE-00650 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Corporate Office | Airtel Business | 2024-10-19 |  | 618 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 79292 | 12914 | FE-101
SITE-00651 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Data Center | Local ISP Partner | 2024-10-31 |  | 606 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 98795 | 7200 | FE-101
SITE-00652 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Sify Technologies | 2024-12-04 | 2024-12-28 | 24 | Go-Live | Live - Operational | Breached | 20 | 80509 | 4404 | FE-423
SITE-00653 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Corporate Office | Tata Communications | 2025-02-15 |  | 499 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 127674 | 16058 | FE-248
SITE-00654 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Data Center | Local ISP Partner | 2024-07-22 |  | 707 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 67173 | 14901 | FE-299
SITE-00655 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | Branch | Local ISP Partner | 2024-10-11 |  |  | BOM Finalization | Cancelled | N/A | 100 | 124380 | 6604 | FE-171
SITE-00656 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Vodafone Idea Business | 2025-01-12 | 2025-01-17 | 5 | Go-Live | Live - Operational | Met | 4 | 131905 | 12356 | FE-429
SITE-00657 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Tata Communications | 2025-02-10 |  | 504 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 72470 | 4418 | FE-272
SITE-00658 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Data Center | Local ISP Partner | 2024-09-04 | 2024-09-27 | 23 | Go-Live | Live - Operational | Breached | 6 | 125131 | 12992 | FE-219
SITE-00659 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Local ISP Partner | 2024-08-17 |  | 681 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 89763 | 13631 | FE-123
SITE-00660 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Branch | Airtel Business | 2024-08-14 |  | 684 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 68283 | 16946 | FE-149
SITE-00661 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Branch | Tata Communications | 2024-07-28 |  | 701 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 105984 | 16593 | FE-415
SITE-00662 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Data Center | Sify Technologies | 2024-10-29 | 2024-11-09 | 11 | Go-Live | Live - Operational | Breached | 4 | 117664 | 12936 | FE-379
SITE-00663 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-01-23 | 2025-01-15 | -8 | Go-Live | Live - Operational | Met | 34 | 36286 | 5478 | FE-240
SITE-00664 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-01-06 | 2025-01-19 | 13 | Go-Live | Live - Operational | Breached | 100 | 59934 | 13035 | FE-120
SITE-00665 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Data Center | Airtel Business | 2024-12-15 |  | 561 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 91827 | 4822 | FE-103
SITE-00666 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Local ISP Partner | 2025-01-08 | 2025-01-16 | 8 | Go-Live | Live - Operational | Breached | 100 | 118748 | 5579 | FE-205
SITE-00667 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Data Center | Airtel Business | 2024-11-22 | 2024-12-10 | 18 | Go-Live | Live - Operational | Breached | 6 | 108024 | 14832 | FE-119
SITE-00668 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-11-16 |  | 590 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 73593 | 10361 | FE-102
SITE-00669 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Branch | Excitel Enterprise | 2024-08-11 | 2024-09-03 | 23 | Go-Live | Live - Operational | Breached | 34 | 127762 | 12342 | FE-359
SITE-00670 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | ATM/Off-site | Sify Technologies | 2024-12-27 |  | 549 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 53391 | 5346 | FE-176
SITE-00671 | PRJ-2024006 | CL001 | East | Jharkhand | Jamshedpur | VSAT | Branch | Local ISP Partner | 2024-08-21 | 2024-08-13 | -8 | Go-Live | Live - Operational | Met | 34 | 65363 | 6933 | FE-322
SITE-00672 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Data Center | Tata Communications | 2025-02-03 |  | 511 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 125047 | 4359 | FE-375
SITE-00673 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | Branch | Tata Communications | 2024-11-13 | 2024-12-05 | 22 | Go-Live | Live - Operational | Breached | 10 | 122555 | 10787 | FE-403
SITE-00674 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Corporate Office | Airtel Business | 2024-08-31 |  | 667 | Site Survey | Survey Scheduled | Breached | 4 | 70746 | 7231 | FE-150
SITE-00675 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | ATM/Off-site | Vodafone Idea Business | 2025-02-19 |  | 495 | Site Survey | Survey Complete | Breached | 10 | 37637 | 11216 | FE-399
SITE-00676 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Excitel Enterprise | 2024-08-18 |  | 680 | Site Survey | Survey Scheduled | Breached | 100 | 51338 | 9846 | FE-291
SITE-00677 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Corporate Office | Sify Technologies | 2024-08-30 |  | 668 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 72025 | 5584 | FE-116
SITE-00678 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Data Center | Vodafone Idea Business | 2024-08-15 | 2024-08-13 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 50439 | 15957 | FE-275
SITE-00679 | PRJ-2024006 | CL001 | East | Odisha | Cuttack | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-08-21 |  | 677 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 39334 | 10245 | FE-367
SITE-00680 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Data Center | Sify Technologies | 2024-11-10 |  | 596 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 123684 | 10514 | FE-476
SITE-00681 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | ATM/Off-site | Excitel Enterprise | 2024-10-31 | 2024-11-13 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 103196 | 3583 | FE-313
SITE-00682 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Tata Communications | 2025-01-15 |  | 530 | Site Survey | Survey Scheduled | Breached | 50 | 97615 | 9960 | FE-345
SITE-00683 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Branch | Excitel Enterprise | 2024-09-11 |  | 656 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 118853 | 15489 | FE-308
SITE-00684 | PRJ-2024006 | CL001 | East | Odisha | Bhubaneswar | VSAT | ATM/Off-site | Local ISP Partner | 2024-09-25 |  | 642 | Site Survey | Survey Complete | Breached | 4 | 30087 | 11360 | FE-442
SITE-00685 | PRJ-2024006 | CL001 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-11-06 |  | 600 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 87616 | 11098 | FE-495
SITE-00686 | PRJ-2024006 | CL001 | East | Odisha | Rourkela | VSAT | Corporate Office | Local ISP Partner | 2024-08-28 |  | 670 | Site Survey | Survey Complete | Breached | 100 | 120261 | 13877 | FE-100
SITE-00687 | PRJ-2024006 | CL001 | East | West Bengal | Howrah | VSAT | Branch | Sify Technologies | 2024-10-05 |  |  | ROW / Permission | Cancelled | N/A | 50 | 126682 | 7920 | FE-457
SITE-00688 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-08-01 |  | 697 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 95467 | 14553 | FE-286
SITE-00689 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | Data Center | Excitel Enterprise | 2024-10-13 |  | 624 | Site Survey | Survey Complete | Breached | 2 | 75916 | 9503 | FE-189
SITE-00690 | PRJ-2024006 | CL001 | East | Assam | Guwahati | VSAT | ATM/Off-site | Airtel Business | 2025-01-09 |  | 536 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 59278 | 12341 | FE-158
SITE-00691 | PRJ-2024006 | CL001 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Excitel Enterprise | 2024-10-02 | 2024-10-14 | 12 | Go-Live | Live - Operational | Breached | 50 | 64325 | 4392 | FE-132
SITE-00692 | PRJ-2024006 | CL001 | East | Bihar | Gaya | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-11-13 |  | 593 | Site Survey | Survey Scheduled | Breached | 4 | 89625 | 15129 | FE-372
SITE-00693 | PRJ-2024006 | CL001 | East | Assam | Dibrugarh | VSAT | Corporate Office | Local ISP Partner | 2024-12-17 |  | 559 | Site Survey | Survey Scheduled | Breached | 4 | 52687 | 17983 | FE-334
SITE-00694 | PRJ-2024006 | CL001 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Sify Technologies | 2025-02-26 |  | 488 | Site Survey | Survey Complete | Breached | 4 | 42334 | 6199 | FE-241
SITE-00695 | PRJ-2024006 | CL001 | East | West Bengal | Siliguri | VSAT | ATM/Off-site | Excitel Enterprise | 2024-11-16 | 2024-11-15 | -1 | Go-Live | Live - Operational | Met | 2 | 66426 | 10324 | FE-449
SITE-00696 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-03-22 |  | 464 | Site Survey | Survey Scheduled | Breached | 2 | 66209 | 6597 | FE-132
SITE-00697 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-06-07 |  | 387 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 113951 | 14084 | FE-267
SITE-00698 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-03-11 |  | 475 | Site Survey | Survey Scheduled | Breached | 20 | 50509 | 16431 | FE-233
SITE-00699 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-03-07 |  | 479 | Site Survey | Survey Complete | Breached | 34 | 65274 | 10969 | FE-185
SITE-00700 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-05-10 |  | 415 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 120813 | 14851 | FE-441
SITE-00701 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-01-22 | 2025-01-14 | -8 | Go-Live | Live - Operational | Met | 6 | 85788 | 7766 | FE-289
SITE-00702 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-06-23 |  | 371 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 73068 | 5923 | FE-290
SITE-00703 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-03-11 |  | 475 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 93459 | 16091 | FE-174
SITE-00704 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2024-12-25 | 2025-01-18 | 24 | Go-Live | Live - Operational | Breached | 20 | 90116 | 8248 | FE-486
SITE-00705 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-28 |  | 366 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 123897 | 11347 | FE-120
SITE-00706 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-01-22 |  | 523 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 108939 | 17276 | FE-212
SITE-00707 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-03-17 | 2025-03-10 | -7 | Go-Live | Live - Operational | Met | 10 | 104471 | 12125 | FE-213
SITE-00708 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-01-14 | 2025-02-07 | 24 | Go-Live | Live - Operational | Breached | 4 | 95081 | 9962 | FE-199
SITE-00709 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-05-27 |  | 398 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 80108 | 5923 | FE-466
SITE-00710 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-03-29 |  | 457 | Site Survey | Survey Complete | Breached | 34 | 74052 | 8547 | FE-328
SITE-00711 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-06-28 | 2025-07-16 | 18 | Go-Live | Live - Operational | Breached | 20 | 49468 | 16700 | FE-472
SITE-00712 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-07-25 | 2025-07-20 | -5 | Go-Live | Live - Operational | Met | 20 | 90208 | 17713 | FE-368
SITE-00713 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-07-05 |  | 359 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 81668 | 13966 | FE-239
SITE-00714 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-04-21 |  | 434 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 52380 | 17136 | FE-295
SITE-00715 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-07-22 | 2025-07-31 | 9 | Go-Live | Live - Operational | Breached | 100 | 101306 | 15621 | FE-337
SITE-00716 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-02-01 | 2025-02-07 | 6 | Go-Live | Live - Operational | Breached | 100 | 44276 | 14212 | FE-440
SITE-00717 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-04-28 | 2025-05-03 | 5 | Go-Live | Live - Operational | Met | 20 | 92625 | 4593 | FE-406
SITE-00718 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-04-14 |  | 441 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 118996 | 16906 | FE-161
SITE-00719 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-02-03 | 2025-01-27 | -7 | Go-Live | Live - Operational | Met | 100 | 118869 | 5719 | FE-282
SITE-00720 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-03-26 | 2025-04-11 | 16 | Go-Live | Live - Operational | Breached | 20 | 66228 | 12177 | FE-427
SITE-00721 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-07-08 | 2025-07-09 | 1 | Go-Live | Live - Operational | Met | 6 | 99265 | 8785 | FE-261
SITE-00722 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-06-20 |  | 374 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 46837 | 3711 | FE-170
SITE-00723 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-07-11 |  | 353 | Site Survey | Survey Complete | Breached | 34 | 49368 | 5178 | FE-211
SITE-00724 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-24 | 2025-07-26 | 2 | Go-Live | Live - Operational | Met | 4 | 82702 | 11044 | FE-139
SITE-00725 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-04-25 | 2025-05-07 | 12 | Go-Live | Live - Operational | Breached | 34 | 46220 | 16886 | FE-326
SITE-00726 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-06-23 | 2025-07-02 | 9 | Go-Live | Live - Operational | Breached | 4 | 57144 | 5608 | FE-455
SITE-00727 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-03-12 | 2025-03-10 | -2 | Go-Live | Live - Operational | Met | 4 | 83680 | 14818 | FE-490
SITE-00728 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-07-10 | 2025-07-30 | 20 | Go-Live | Live - Operational | Breached | 10 | 42131 | 4037 | FE-437
SITE-00729 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-01-23 |  | 522 | Site Survey | Survey Scheduled | Breached | 4 | 67537 | 14437 | FE-105
SITE-00730 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-02-14 |  | 500 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 115896 | 9259 | FE-114
SITE-00731 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-05-21 | 2025-05-27 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 94179 | 12842 | FE-134
SITE-00732 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-05-08 | 2025-05-11 | 3 | Go-Live | Live - Operational | Met | 6 | 126830 | 12300 | FE-102
SITE-00733 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-07-29 |  | 335 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 85627 | 14535 | FE-154
SITE-00734 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-04-11 |  | 444 | Site Survey | Survey Complete | Breached | 10 | 81422 | 5348 | FE-489
SITE-00735 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-01-21 |  | 524 | Site Survey | Survey Scheduled | Breached | 100 | 127912 | 9418 | FE-460
SITE-00736 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-03-17 | 2025-04-07 | 21 | Go-Live | Live - Operational | Breached | 20 | 87892 | 13336 | FE-476
SITE-00737 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-05-14 | 2025-05-30 | 16 | Go-Live | Live - Operational | Breached | 10 | 37123 | 17279 | FE-343
SITE-00738 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-06-14 | 2025-07-05 | 21 | Go-Live | Live - Operational | Breached | 100 | 96506 | 14289 | FE-446
SITE-00739 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-04-04 | 2025-04-19 | 15 | Go-Live | Live - Operational | Breached | 6 | 36481 | 9459 | FE-201
SITE-00740 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-07-28 |  | 336 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 83666 | 15381 | FE-355
SITE-00741 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-04-05 |  | 450 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 91508 | 11879 | FE-242
SITE-00742 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-01-24 | 2025-01-30 | 6 | Go-Live | Live - Operational | Breached | 10 | 110361 | 5705 | FE-115
SITE-00743 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-24 | 2025-07-18 | -6 | Go-Live | Live - Operational | Met | 2 | 51474 | 9769 | FE-409
SITE-00744 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-06-01 | 2025-06-15 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 131904 | 11135 | FE-203
SITE-00745 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-05-02 |  | 423 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 134100 | 17584 | FE-376
SITE-00746 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-04-13 | 2025-04-10 | -3 | Go-Live | Live - Operational | Met | 34 | 77327 | 10750 | FE-335
SITE-00747 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-05-15 | 2025-05-24 | 9 | Go-Live | Live - Operational | Breached | 50 | 45627 | 8619 | FE-466
SITE-00748 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-05-18 | 2025-06-08 | 21 | Go-Live | Live - Operational | Breached | 100 | 90378 | 12711 | FE-180
SITE-00749 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-03-01 |  | 485 | Site Survey | Survey Complete | Breached | 50 | 108863 | 14583 | FE-280
SITE-00750 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2024-12-31 | 2024-12-23 | -8 | Go-Live | Live - Operational | Met | 34 | 134109 | 15657 | FE-398
SITE-00751 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-03-31 | 2025-03-29 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 81992 | 9255 | FE-128
SITE-00752 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-06-07 | 2025-06-16 | 9 | Go-Live | Live - Operational | Breached | 4 | 67965 | 5375 | FE-272
SITE-00753 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-03-17 |  | 469 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 102455 | 11933 | FE-315
SITE-00754 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-04-23 |  |  | ROW / Permission | Cancelled | N/A | 50 | 102757 | 9894 | FE-265
SITE-00755 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-01-18 |  | 527 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 93898 | 16794 | FE-491
SITE-00756 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-03-10 |  | 476 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 93136 | 13911 | FE-138
SITE-00757 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-03-01 | 2025-02-25 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 133460 | 7200 | FE-419
SITE-00758 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-01-17 |  | 528 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 36817 | 12780 | FE-371
SITE-00759 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-03-22 | 2025-03-16 | -6 | Go-Live | Live - Operational | Met | 20 | 84742 | 14370 | FE-376
SITE-00760 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-04-05 |  | 450 | Site Survey | Survey Scheduled | Breached | 100 | 116022 | 16008 | FE-380
SITE-00761 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-06-22 |  | 372 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 55912 | 14326 | FE-480
SITE-00762 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-09 |  | 416 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 96454 | 6787 | FE-286
SITE-00763 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-01-31 | 2025-02-09 | 9 | Go-Live | Live - Operational | Breached | 34 | 36444 | 13886 | FE-204
SITE-00764 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-06-07 | 2025-06-07 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 81197 | 7407 | FE-158
SITE-00765 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-02-24 | 2025-03-05 | 9 | Go-Live | Live - Operational | Breached | 50 | 83314 | 14099 | FE-118
SITE-00766 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-01-27 | 2025-01-18 | -9 | Go-Live | Live - Operational | Met | 6 | 112448 | 17467 | FE-121
SITE-00767 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-08-01 | 2025-07-27 | -5 | Go-Live | Live - Operational | Met | 20 | 36333 | 10168 | FE-286
SITE-00768 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-07-27 |  | 337 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 102838 | 15533 | FE-356
SITE-00769 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-24 |  | 340 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 93070 | 17992 | FE-146
SITE-00770 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-07-09 | 2025-07-19 | 10 | Go-Live | Live - Operational | Breached | 50 | 133623 | 15761 | FE-480
SITE-00771 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-29 | 2025-01-25 | -4 | Go-Live | Live - Operational | Met | 20 | 85602 | 10190 | FE-230
SITE-00772 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-05-09 |  | 416 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 69482 | 12441 | FE-316
SITE-00773 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-08-06 | 2025-08-26 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 121804 | 9525 | FE-257
SITE-00774 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-01-01 |  | 544 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 61158 | 12555 | FE-296
SITE-00775 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-01-24 |  | 521 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 78917 | 3628 | FE-301
SITE-00776 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-07-22 | 2025-07-27 | 5 | Go-Live | Live - Operational | Met | 6 | 85520 | 13844 | FE-262
SITE-00777 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-02 | 2025-07-30 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 71610 | 15253 | FE-316
SITE-00778 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-02-28 |  |  | ROW / Permission | Cancelled | N/A | 50 | 106920 | 15447 | FE-380
SITE-00779 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2024-12-31 |  |  | Site Survey | Cancelled | N/A | 100 | 131680 | 14003 | FE-169
SITE-00780 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-06-02 | 2025-06-11 | 9 | Go-Live | Live - Operational | Breached | 4 | 42526 | 6085 | FE-227
SITE-00781 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-17 |  | 377 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 90700 | 17811 | FE-476
SITE-00782 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-06-17 | 2025-06-27 | 10 | Go-Live | Live - Operational | Breached | 4 | 82328 | 9522 | FE-193
SITE-00783 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-02-19 |  | 495 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 39662 | 11076 | FE-201
SITE-00784 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-04-05 | 2025-04-22 | 17 | Go-Live | Live - Operational | Breached | 6 | 39673 | 9528 | FE-187
SITE-00785 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-06-25 | 2025-07-18 | 23 | Go-Live | Live - Operational | Breached | 100 | 43533 | 7177 | FE-465
SITE-00786 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-07 | 2025-03-28 | 21 | Go-Live | Live - Operational | Breached | 50 | 55080 | 13331 | FE-210
SITE-00787 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-02-08 |  | 506 | Site Survey | Survey Scheduled | Breached | 2 | 66036 | 7789 | FE-220
SITE-00788 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-03-28 | 2025-04-16 | 19 | Go-Live | Live - Operational | Breached | 100 | 45459 | 17777 | FE-265
SITE-00789 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-04-01 |  | 454 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 37575 | 5061 | FE-385
SITE-00790 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-02-22 | 2025-03-04 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 28702 | 7655 | FE-358
SITE-00791 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-04-04 | 2025-04-20 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 104085 | 6438 | FE-233
SITE-00792 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-20 |  | 466 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 69591 | 15136 | FE-371
SITE-00793 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-01-22 | 2025-02-01 | 10 | Go-Live | Live - Operational | Breached | 100 | 64831 | 15752 | FE-284
SITE-00794 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-05-29 | 2025-06-04 | 6 | Go-Live | Live - Operational | Breached | 50 | 49624 | 8669 | FE-477
SITE-00795 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-07-30 |  | 334 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 47480 | 4394 | FE-217
SITE-00796 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-02-28 |  | 486 | Site Survey | Survey Scheduled | Breached | 100 | 85203 | 5400 | FE-353
SITE-00797 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-06-23 |  | 371 | Site Survey | Survey Complete | Breached | 100 | 92616 | 5343 | FE-468
SITE-00798 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-01-16 | 2025-01-17 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 126295 | 11835 | FE-239
SITE-00799 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2024-12-25 |  | 551 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 82580 | 4758 | FE-226
SITE-00800 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2024-12-30 | 2025-01-03 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 105376 | 5237 | FE-265
SITE-00801 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-04-20 | 2025-05-10 | 20 | Go-Live | Live - Operational | Breached | 20 | 105883 | 14280 | FE-102
SITE-00802 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-01 |  | 393 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 55704 | 17643 | FE-124
SITE-00803 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-02 | 2025-06-26 | -6 | Go-Live | Live - Operational | Met | 50 | 40130 | 10034 | FE-230
SITE-00804 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-01-15 |  | 530 | Site Survey | Survey Complete | Breached | 6 | 78921 | 16271 | FE-306
SITE-00805 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-03-10 | 2025-03-31 | 21 | Go-Live | Live - Operational | Breached | 20 | 117779 | 13387 | FE-167
SITE-00806 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-05-04 |  | 421 | Site Survey | Survey Complete | Breached | 100 | 78867 | 11305 | FE-237
SITE-00807 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-07-05 | 2025-07-22 | 17 | Go-Live | Live - Operational | Breached | 6 | 84899 | 13833 | FE-318
SITE-00808 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-03-21 |  | 465 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 112883 | 14743 | FE-465
SITE-00809 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-06-03 |  | 391 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 89370 | 10665 | FE-140
SITE-00810 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-01-25 | 2025-02-03 | 9 | Go-Live | Live - Operational | Breached | 50 | 66729 | 12814 | FE-124
SITE-00811 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-04 | 2025-04-30 | -4 | Go-Live | Live - Operational | Met | 50 | 40384 | 11112 | FE-438
SITE-00812 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-02-27 |  | 487 | Site Survey | Survey Complete | Breached | 2 | 42933 | 15632 | FE-438
SITE-00813 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-07-27 | 2025-08-11 | 15 | Go-Live | Live - Operational | Breached | 50 | 120324 | 8376 | FE-260
SITE-00814 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-04-18 |  | 437 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 134169 | 6566 | FE-208
SITE-00815 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-02-28 |  | 486 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 28766 | 9970 | FE-159
SITE-00816 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-04-25 |  | 430 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 114208 | 15693 | FE-408
SITE-00817 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-07-20 |  | 344 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 133465 | 8458 | FE-144
SITE-00818 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-02-10 | 2025-02-07 | -3 | Go-Live | Live - Operational | Met | 10 | 31514 | 6928 | FE-346
SITE-00819 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-04-14 | 2025-05-08 | 24 | Go-Live | Live - Operational | Breached | 20 | 128888 | 11092 | FE-175
SITE-00820 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-01-22 | 2025-01-22 | 0 | Go-Live | Live - Operational | Met | 100 | 91576 | 11224 | FE-110
SITE-00821 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-03-09 | 2025-03-24 | 15 | Go-Live | Live - Operational | Breached | 2 | 41456 | 13828 | FE-465
SITE-00822 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-06-30 |  | 364 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 32851 | 11487 | FE-304
SITE-00823 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-06-24 | 2025-06-17 | -7 | Go-Live | Live - Operational | Met | 50 | 103550 | 8674 | FE-383
SITE-00824 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-04-09 |  | 446 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 109618 | 14087 | FE-277
SITE-00825 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-02-03 | 2025-02-11 | 8 | Go-Live | Live - Operational | Breached | 34 | 85424 | 7302 | FE-359
SITE-00826 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-03-20 |  | 466 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 45191 | 17969 | FE-250
SITE-00827 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-06-09 |  | 385 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 109506 | 6894 | FE-244
SITE-00828 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-26 |  | 519 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 107396 | 11563 | FE-151
SITE-00829 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-02-22 | 2025-02-23 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 75026 | 17932 | FE-233
SITE-00830 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-07-23 | 2025-08-14 | 22 | Go-Live | Live - Operational | Breached | 34 | 84442 | 5367 | FE-416
SITE-00831 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-02-19 |  | 495 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 130876 | 9320 | FE-493
SITE-00832 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-10 | 2025-08-09 | -1 | Go-Live | Live - Operational | Met | 4 | 120589 | 4326 | FE-324
SITE-00833 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-07-12 | 2025-07-08 | -4 | Go-Live | Live - Operational | Met | 4 | 49895 | 13820 | FE-160
SITE-00834 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-06-28 | 2025-07-06 | 8 | Go-Live | Live - Operational | Breached | 100 | 124017 | 17762 | FE-150
SITE-00835 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-03-19 |  | 467 | Site Survey | Survey Complete | Breached | 10 | 85554 | 10311 | FE-493
SITE-00836 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-03-21 |  | 465 | Site Survey | Survey Scheduled | Breached | 6 | 39171 | 7858 | FE-290
SITE-00837 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-06-12 |  | 382 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 131181 | 7238 | FE-170
SITE-00838 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-08-10 |  | 323 | Site Survey | Survey Complete | Breached | 34 | 31901 | 10751 | FE-174
SITE-00839 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-01-10 |  | 535 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 80645 | 16154 | FE-184
SITE-00840 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-07-06 |  | 358 | Site Survey | Survey Complete | Breached | 6 | 103308 | 4447 | FE-423
SITE-00841 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-04-05 |  | 450 | Site Survey | Survey Scheduled | Breached | 34 | 73109 | 3629 | FE-243
SITE-00842 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-04-06 |  |  | BOM Finalization | Cancelled | N/A | 100 | 119418 | 9156 | FE-432
SITE-00843 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-01-14 | 2025-01-10 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 123040 | 15278 | FE-478
SITE-00844 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-03-06 |  | 480 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 96332 | 9082 | FE-487
SITE-00845 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-08-08 | 2025-09-01 | 24 | Go-Live | Live - Operational | Breached | 10 | 129470 | 8479 | FE-471
SITE-00846 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-01-08 |  | 537 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 44228 | 4282 | FE-487
SITE-00847 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-05-19 | 2025-06-06 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 58945 | 16695 | FE-481
SITE-00848 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-03-10 | 2025-03-14 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 121631 | 9687 | FE-366
SITE-00849 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-05-05 | 2025-05-18 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 40843 | 5901 | FE-464
SITE-00850 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-01-16 | 2025-01-09 | -7 | Go-Live | Live - Operational | Met | 100 | 56152 | 10809 | FE-139
SITE-00851 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-16 |  | 409 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 104585 | 11672 | FE-425
SITE-00852 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-04-28 |  |  | ROW / Permission | Cancelled | N/A | 6 | 94294 | 5582 | FE-348
SITE-00853 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-05-04 |  | 421 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 87694 | 11255 | FE-116
SITE-00854 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-08-16 |  | 317 | Site Survey | Survey Complete | Breached | 50 | 42461 | 5480 | FE-289
SITE-00855 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-05-06 | 2025-05-05 | -1 | Go-Live | Live - Operational | Met | 20 | 77081 | 8468 | FE-250
SITE-00856 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-01-29 | 2025-02-14 | 16 | Go-Live | Live - Operational | Breached | 20 | 56256 | 6499 | FE-478
SITE-00857 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-05-13 | 2025-05-25 | 12 | Go-Live | Live - Operational | Breached | 50 | 91068 | 12889 | FE-258
SITE-00858 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-12 | 2025-07-19 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 127870 | 5769 | FE-358
SITE-00859 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-04-17 |  | 438 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 39706 | 16604 | FE-419
SITE-00860 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-02-21 |  | 493 | Site Survey | Survey Complete | Breached | 2 | 115876 | 10759 | FE-476
SITE-00861 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-06-23 | 2025-06-14 | -9 | Go-Live | Live - Operational | Met | 20 | 101537 | 14070 | FE-163
SITE-00862 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-05-31 | 2025-06-24 | 24 | Go-Live | Live - Operational | Breached | 10 | 126377 | 11296 | FE-357
SITE-00863 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-05-09 |  | 416 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 131121 | 6871 | FE-225
SITE-00864 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-07-18 | 2025-08-11 | 24 | Go-Live | Live - Operational | Breached | 50 | 105187 | 4237 | FE-351
SITE-00865 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-02-08 |  | 506 | Site Survey | Survey Scheduled | Breached | 34 | 78070 | 7713 | FE-146
SITE-00866 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-02-05 |  | 509 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 61496 | 16087 | FE-145
SITE-00867 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-06-15 |  | 379 | Site Survey | Survey Complete | Breached | 34 | 51784 | 3945 | FE-465
SITE-00868 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-01-18 |  | 527 | Site Survey | Survey Complete | Breached | 50 | 70495 | 7725 | FE-292
SITE-00869 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-02-23 | 2025-02-28 | 5 | Go-Live | Live - Operational | Met | 50 | 43083 | 7912 | FE-131
SITE-00870 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-04-07 |  | 448 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 81411 | 13879 | FE-219
SITE-00871 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-05-23 |  | 402 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 67926 | 12810 | FE-308
SITE-00872 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-05-01 |  | 424 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 98836 | 6255 | FE-225
SITE-00873 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-04-18 |  | 437 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 109360 | 8239 | FE-434
SITE-00874 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-08-16 | 2025-09-05 | 20 | Go-Live | Live - Operational | Breached | 20 | 117128 | 9728 | FE-279
SITE-00875 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-03-06 |  | 480 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 67405 | 4969 | FE-302
SITE-00876 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-05-15 |  | 410 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 108012 | 11770 | FE-262
SITE-00877 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-04-18 |  | 437 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 72778 | 6950 | FE-335
SITE-00878 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-08-14 | 2025-08-12 | -2 | Go-Live | Live - Operational | Met | 100 | 28560 | 3656 | FE-444
SITE-00879 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-10 |  | 323 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 131193 | 17864 | FE-432
SITE-00880 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-08-09 | 2025-08-27 | 18 | Go-Live | Live - Operational | Breached | 50 | 106815 | 9364 | FE-298
SITE-00881 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-01-24 | 2025-02-12 | 19 | Go-Live | Live - Operational | Breached | 100 | 29227 | 7129 | FE-480
SITE-00882 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-08-16 |  | 317 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 134991 | 13550 | FE-420
SITE-00883 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-04-29 | 2025-05-12 | 13 | Go-Live | Live - Operational | Breached | 100 | 120280 | 15082 | FE-410
SITE-00884 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-07-22 | 2025-08-06 | 15 | Go-Live | Live - Operational | Breached | 100 | 50344 | 12540 | FE-199
SITE-00885 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-05-23 | 2025-05-21 | -2 | Go-Live | Live - Operational | Met | 20 | 102698 | 17516 | FE-216
SITE-00886 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-29 | 2025-07-20 | -9 | Go-Live | Live - Operational | Met | 20 | 117218 | 12676 | FE-332
SITE-00887 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-06-14 |  | 380 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 81330 | 7989 | FE-162
SITE-00888 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-03-26 |  | 460 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 34155 | 8053 | FE-315
SITE-00889 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2024-12-25 | 2025-01-01 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 102949 | 16732 | FE-112
SITE-00890 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-12 |  | 533 | Site Survey | Survey Scheduled | Breached | 6 | 71152 | 8592 | FE-132
SITE-00891 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-04-13 |  | 442 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 60821 | 7549 | FE-155
SITE-00892 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-07-25 | 2025-07-21 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 37556 | 16209 | FE-407
SITE-00893 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-06-02 | 2025-06-20 | 18 | Go-Live | Live - Operational | Breached | 4 | 35954 | 4046 | FE-293
SITE-00894 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-01-08 | 2025-01-26 | 18 | Go-Live | Live - Operational | Breached | 50 | 36623 | 5168 | FE-446
SITE-00895 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-03-09 | 2025-03-23 | 14 | Go-Live | Live - Operational | Breached | 50 | 58554 | 17665 | FE-406
SITE-00896 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-04-01 |  | 454 | Site Survey | Survey Scheduled | Breached | 4 | 72514 | 14164 | FE-445
SITE-00897 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-03-18 |  | 468 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 41459 | 3701 | FE-404
SITE-00898 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-08-12 | 2025-08-10 | -2 | Go-Live | Live - Operational | Met | 34 | 83182 | 11387 | FE-471
SITE-00899 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-02-24 | 2025-02-22 | -2 | Go-Live | Live - Operational | Met | 6 | 68850 | 13076 | FE-323
SITE-00900 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-05-22 | 2025-06-03 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 68458 | 13384 | FE-275
SITE-00901 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-05-05 | 2025-05-04 | -1 | Go-Live | Live - Operational | Met | 2 | 83320 | 9133 | FE-200
SITE-00902 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-07-13 | 2025-07-07 | -6 | Go-Live | Live - Operational | Met | 100 | 119066 | 14835 | FE-339
SITE-00903 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-05-17 |  | 408 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 82879 | 8884 | FE-183
SITE-00904 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-04-29 | 2025-05-03 | 4 | Go-Live | Live - Operational | Met | 10 | 118861 | 7272 | FE-338
SITE-00905 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-04-26 | 2025-05-07 | 11 | Go-Live | Live - Operational | Breached | 50 | 52149 | 17034 | FE-103
SITE-00906 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-03-25 | 2025-03-16 | -9 | Go-Live | Live - Operational | Met | 6 | 66086 | 10715 | FE-199
SITE-00907 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2024-12-31 | 2025-01-02 | 2 | Go-Live | Live - Operational | Met | 6 | 56697 | 7792 | FE-468
SITE-00908 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-02-24 |  | 490 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 51078 | 17309 | FE-234
SITE-00909 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-01-28 |  | 517 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 72352 | 6944 | FE-256
SITE-00910 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-07-19 |  | 345 | Site Survey | Survey Complete | Breached | 6 | 97065 | 16591 | FE-419
SITE-00911 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-01-29 | 2025-01-27 | -2 | Go-Live | Live - Operational | Met | 50 | 119010 | 9631 | FE-262
SITE-00912 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-02-24 |  | 490 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 98184 | 8319 | FE-176
SITE-00913 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-03 | 2025-06-10 | 7 | Go-Live | Live - Operational | Breached | 100 | 55425 | 15416 | FE-141
SITE-00914 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-05-03 | 2025-05-17 | 14 | Go-Live | Live - Operational | Breached | 100 | 96012 | 11106 | FE-191
SITE-00915 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-06-19 |  | 375 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 90096 | 7896 | FE-397
SITE-00916 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-02-18 | 2025-02-20 | 2 | Go-Live | Live - Operational | Met | 50 | 56651 | 8513 | FE-317
SITE-00917 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-02-27 |  | 487 | Site Survey | Survey Complete | Breached | 6 | 126516 | 4876 | FE-251
SITE-00918 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-05-22 | 2025-05-14 | -8 | Go-Live | Live - Operational | Met | 34 | 83850 | 10891 | FE-339
SITE-00919 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-07-17 |  | 347 | Site Survey | Survey Complete | Breached | 20 | 78118 | 3904 | FE-191
SITE-00920 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-06-07 | 2025-06-01 | -6 | Go-Live | Live - Operational | Met | 20 | 93767 | 11901 | FE-379
SITE-00921 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-01-18 | 2025-01-15 | -3 | Go-Live | Live - Operational | Met | 2 | 99568 | 6781 | FE-270
SITE-00922 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-02-26 | 2025-03-02 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 126616 | 15233 | FE-478
SITE-00923 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-07-09 | 2025-07-18 | 9 | Go-Live | Live - Operational | Breached | 50 | 81183 | 16965 | FE-396
SITE-00924 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-05-04 |  | 421 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 57743 | 15351 | FE-483
SITE-00925 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-05-05 | 2025-05-30 | 25 | Go-Live | Live - Operational | Breached | 100 | 72650 | 16474 | FE-143
SITE-00926 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-07-09 |  | 355 | Site Survey | Survey Scheduled | Breached | 100 | 86978 | 17474 | FE-385
SITE-00927 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-05-20 | 2025-05-18 | -2 | Go-Live | Live - Operational | Met | 2 | 93509 | 16777 | FE-437
SITE-00928 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-04-10 | 2025-04-27 | 17 | Go-Live | Live - Operational | Breached | 20 | 70739 | 13116 | FE-111
SITE-00929 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-02-01 | 2025-02-12 | 11 | Go-Live | Live - Operational | Breached | 50 | 77980 | 6845 | FE-300
SITE-00930 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-02-10 |  | 504 | Site Survey | Survey Complete | Breached | 34 | 102647 | 10897 | FE-427
SITE-00931 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-01-19 | 2025-02-13 | 25 | Go-Live | Live - Operational | Breached | 100 | 31517 | 6558 | FE-201
SITE-00932 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-02-14 | 2025-02-16 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 87593 | 4441 | FE-288
SITE-00933 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-17 | 2025-04-02 | 16 | Go-Live | Live - Operational | Breached | 4 | 44926 | 12289 | FE-314
SITE-00934 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-08-12 |  | 321 | Site Survey | Survey Complete | Breached | 10 | 68600 | 10581 | FE-463
SITE-00935 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-05-20 |  | 405 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 93860 | 15243 | FE-450
SITE-00936 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2024-12-25 | 2024-12-24 | -1 | Go-Live | Live - Operational | Met | 50 | 107278 | 16731 | FE-226
SITE-00937 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-06 |  | 327 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 103514 | 4140 | FE-477
SITE-00938 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-08-06 |  | 327 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 79260 | 13543 | FE-189
SITE-00939 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-11 | 2025-08-28 | 17 | Go-Live | Live - Operational | Breached | 6 | 119556 | 12816 | FE-148
SITE-00940 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-08-07 | 2025-08-07 | 0 | Go-Live | Live - Operational | Met | 20 | 115380 | 4593 | FE-457
SITE-00941 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-07-07 |  | 357 | Site Survey | Survey Complete | Breached | 34 | 38031 | 15876 | FE-153
SITE-00942 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-04-18 |  | 437 | Site Survey | Survey Complete | Breached | 10 | 94330 | 4231 | FE-336
SITE-00943 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-06-19 |  | 375 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 125774 | 10042 | FE-199
SITE-00944 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-02-26 | 2025-02-23 | -3 | Go-Live | Live - Operational | Met | 100 | 91538 | 11058 | FE-134
SITE-00945 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-02-24 |  | 490 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 64587 | 17288 | FE-182
SITE-00946 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-01-18 |  | 527 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 98078 | 15647 | FE-300
SITE-00947 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-07-07 |  | 357 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 48119 | 10719 | FE-283
SITE-00948 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-01-01 |  | 544 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 119323 | 4282 | FE-425
SITE-00949 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-06-18 |  | 376 | Site Survey | Survey Complete | Breached | 2 | 106407 | 3576 | FE-124
SITE-00950 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-03-29 | 2025-04-03 | 5 | Go-Live | Live - Operational | Met | 2 | 83270 | 3957 | FE-107
SITE-00951 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-06-13 |  | 381 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 132454 | 17186 | FE-440
SITE-00952 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-01-04 | 2025-01-20 | 16 | Go-Live | Live - Operational | Breached | 34 | 70294 | 12708 | FE-420
SITE-00953 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-05-11 | 2025-05-26 | 15 | Go-Live | Live - Operational | Breached | 10 | 56020 | 5234 | FE-282
SITE-00954 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-04-05 | 2025-04-15 | 10 | Go-Live | Live - Operational | Breached | 10 | 88132 | 7106 | FE-133
SITE-00955 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-01-10 | 2025-01-13 | 3 | Go-Live | Live - Operational | Met | 100 | 41344 | 15174 | FE-374
SITE-00956 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-01-17 | 2025-01-27 | 10 | Go-Live | Live - Operational | Breached | 6 | 71522 | 6372 | FE-425
SITE-00957 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-03-19 | 2025-03-10 | -9 | Go-Live | Live - Operational | Met | 100 | 78118 | 11872 | FE-427
SITE-00958 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-06-22 |  | 372 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 108786 | 15934 | FE-163
SITE-00959 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-04-12 |  | 443 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 35854 | 5753 | FE-291
SITE-00960 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-01-31 | 2025-02-14 | 14 | Go-Live | Live - Operational | Breached | 2 | 59203 | 15383 | FE-406
SITE-00961 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-03-05 | 2025-03-15 | 10 | Go-Live | Live - Operational | Breached | 50 | 112940 | 16815 | FE-247
SITE-00962 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-03-18 |  | 468 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 98688 | 4385 | FE-440
SITE-00963 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-06-26 |  |  | Site Survey | Cancelled | N/A | 34 | 52057 | 10747 | FE-422
SITE-00964 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-01-10 |  | 535 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 54767 | 5557 | FE-146
SITE-00965 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-07-24 |  | 340 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 83868 | 15378 | FE-339
SITE-00966 | PRJ-2024007 | CL004 | East | Bihar | Patna | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-02-12 |  | 502 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 107410 | 7579 | FE-255
SITE-00967 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-02-13 |  | 501 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 75131 | 10024 | FE-293
SITE-00968 | PRJ-2024007 | CL004 | East | Odisha | Cuttack | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-04-11 |  | 444 | Site Survey | Survey Scheduled | Breached | 50 | 127657 | 6053 | FE-346
SITE-00969 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-07-30 |  | 334 | Site Survey | Survey Scheduled | Breached | 6 | 100463 | 15405 | FE-189
SITE-00970 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-03-12 |  | 474 | Site Survey | Survey Scheduled | Breached | 50 | 101681 | 13429 | FE-346
SITE-00971 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-06-25 | 2025-07-15 | 20 | Go-Live | Live - Operational | Breached | 10 | 28547 | 3710 | FE-356
SITE-00972 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-04-09 |  | 446 | Site Survey | Survey Complete | Breached | 34 | 78336 | 11520 | FE-257
SITE-00973 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-08-07 |  | 326 | Site Survey | Survey Complete | Breached | 50 | 102135 | 6160 | FE-199
SITE-00974 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-03-23 |  | 463 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 111228 | 14780 | FE-288
SITE-00975 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-04-11 |  | 444 | Site Survey | Survey Complete | Breached | 100 | 32522 | 16822 | FE-285
SITE-00976 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-06-07 |  | 387 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 117268 | 5914 | FE-230
SITE-00977 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-06-11 |  | 383 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 129052 | 5012 | FE-429
SITE-00978 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-05-23 |  | 402 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 83436 | 6216 | FE-318
SITE-00979 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-05-09 |  | 416 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 124198 | 10243 | FE-485
SITE-00980 | PRJ-2024007 | CL004 | East | West Bengal | Kolkata | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-05-19 |  | 406 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 126137 | 6932 | FE-483
SITE-00981 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-02-05 | 2025-02-26 | 21 | Go-Live | Live - Operational | Breached | 4 | 129416 | 14908 | FE-313
SITE-00982 | PRJ-2024007 | CL004 | East | Assam | Dibrugarh | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-03-07 |  | 479 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 77106 | 6553 | FE-460
SITE-00983 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-02-08 |  | 506 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 102329 | 16842 | FE-208
SITE-00984 | PRJ-2024007 | CL004 | East | Odisha | Bhubaneswar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-07-03 | 2025-07-04 | 1 | Go-Live | Live - Operational | Met | 50 | 85767 | 13770 | FE-419
SITE-00985 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-01-13 | 2025-01-21 | 8 | Go-Live | Live - Operational | Breached | 4 | 64275 | 4552 | FE-275
SITE-00986 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-04-25 | 2025-05-16 | 21 | Go-Live | Live - Operational | Breached | 2 | 62875 | 15817 | FE-103
SITE-00987 | PRJ-2024007 | CL004 | East | Assam | Guwahati | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-02-16 | 2025-03-11 | 23 | Go-Live | Live - Operational | Breached | 20 | 91691 | 11253 | FE-487
SITE-00988 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-03-28 | 2025-04-13 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 75344 | 14396 | FE-304
SITE-00989 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-08-04 |  | 329 | Site Survey | Survey Complete | Breached | 2 | 87889 | 17762 | FE-457
SITE-00990 | PRJ-2024007 | CL004 | East | Jharkhand | Ranchi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-05-27 | 2025-05-24 | -3 | Go-Live | Live - Operational | Met | 10 | 76290 | 10904 | FE-416
SITE-00991 | PRJ-2024007 | CL004 | East | Jharkhand | Jamshedpur | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-02-10 |  | 504 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 30179 | 13883 | FE-284
SITE-00992 | PRJ-2024007 | CL004 | East | West Bengal | Siliguri | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-15 | 2025-06-24 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 80450 | 15611 | FE-413
SITE-00993 | PRJ-2024007 | CL004 | East | West Bengal | Howrah | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-04-24 |  | 431 | Site Survey | Survey Scheduled | Breached | 50 | 66517 | 13447 | FE-199
SITE-00994 | PRJ-2024007 | CL004 | East | Odisha | Rourkela | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-07-12 |  | 352 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 93264 | 16555 | FE-144
SITE-00995 | PRJ-2024007 | CL004 | East | Bihar | Gaya | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-08-10 | 2025-08-28 | 18 | Go-Live | Live - Operational | Breached | 10 | 59897 | 6967 | FE-187
SITE-00996 | PRJ-2024008 | CL003 | West | Maharashtra | Mumbai | MPLS | Branch | Airtel Business | 2025-05-10 |  | 415 | Site Survey | Survey Scheduled | Breached | 34 | 78264 | 16055 | FE-243
SITE-00997 | PRJ-2024008 | CL003 | West | Gujarat | Vadodara | MPLS | Branch | Local ISP Partner | 2025-03-09 |  | 477 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 98063 | 13880 | FE-471
SITE-00998 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-01 |  |  | Site Survey | Cancelled | N/A | 4 | 112408 | 9123 | FE-293
SITE-00999 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | Branch | Sify Technologies | 2025-01-04 | 2025-01-10 | 6 | Go-Live | Live - Operational | Breached | 4 | 42599 | 4960 | FE-274
SITE-01000 | PRJ-2024008 | CL003 | West | Gujarat | Ahmedabad | MPLS | ATM/Off-site | Sify Technologies | 2025-02-10 |  | 504 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 103617 | 15573 | FE-100
SITE-01001 | PRJ-2024008 | CL003 | West | Goa | Panaji | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-03-25 |  | 461 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 69896 | 16136 | FE-286
SITE-01002 | PRJ-2024008 | CL003 | West | Gujarat | Surat | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-17 | 2025-02-07 | -10 | Go-Live | Live - Operational | Met | 34 | 46966 | 16871 | FE-251
SITE-01003 | PRJ-2024008 | CL003 | West | Gujarat | Rajkot | MPLS | ATM/Off-site | Excitel Enterprise | 2025-03-04 |  | 482 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 47119 | 15739 | FE-440
SITE-01004 | PRJ-2024008 | CL003 | West | Maharashtra | Thane | MPLS | Branch | Sify Technologies | 2025-01-26 | 2025-02-06 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 110716 | 17077 | FE-210
SITE-01005 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Jabalpur | MPLS | Branch | Sify Technologies | 2025-02-12 |  | 502 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 121947 | 6950 | FE-475
SITE-01006 | PRJ-2024008 | CL003 | West | Gujarat | Ahmedabad | MPLS | Data Center | Sify Technologies | 2025-06-15 | 2025-07-06 | 21 | Go-Live | Live - Operational | Breached | 6 | 30826 | 12477 | FE-300
SITE-01007 | PRJ-2024008 | CL003 | West | Goa | Margao | MPLS | Corporate Office | Vodafone Idea Business | 2025-03-09 |  | 477 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 37414 | 12148 | FE-472
SITE-01008 | PRJ-2024008 | CL003 | West | Goa | Margao | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-27 |  |  | ROW / Permission | Cancelled | N/A | 4 | 45157 | 8798 | FE-485
SITE-01009 | PRJ-2024008 | CL003 | West | Maharashtra | Nagpur | MPLS | ATM/Off-site | Excitel Enterprise | 2025-04-24 |  | 431 | Site Survey | Survey Scheduled | Breached | 6 | 85918 | 14902 | FE-347
SITE-01010 | PRJ-2024008 | CL003 | West | Goa | Panaji | MPLS | Branch | Sify Technologies | 2025-01-02 | 2025-01-04 | 2 | Go-Live | Live - Operational | Met | 4 | 116908 | 16369 | FE-175
SITE-01011 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Tata Communications | 2025-06-11 |  | 383 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 74607 | 11263 | FE-191
SITE-01012 | PRJ-2024008 | CL003 | West | Maharashtra | Mumbai | MPLS | Corporate Office | Excitel Enterprise | 2025-04-23 |  | 432 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 47473 | 13772 | FE-469
SITE-01013 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Indore | MPLS | Data Center | Vodafone Idea Business | 2024-12-08 | 2024-12-13 | 5 | Go-Live | Live - Operational | Met | 20 | 118175 | 13267 | FE-188
SITE-01014 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Data Center | Sify Technologies | 2025-06-17 |  | 377 | Site Survey | Survey Scheduled | Breached | 100 | 76145 | 3690 | FE-161
SITE-01015 | PRJ-2024008 | CL003 | West | Maharashtra | Mumbai | MPLS | ATM/Off-site | Tata Communications | 2025-03-13 | 2025-04-04 | 22 | Go-Live | Live - Operational | Breached | 100 | 63877 | 14866 | FE-481
SITE-01016 | PRJ-2024008 | CL003 | West | Maharashtra | Thane | MPLS | Data Center | Sify Technologies | 2025-02-14 | 2025-03-06 | 20 | Go-Live | Live - Operational | Breached | 6 | 41033 | 8828 | FE-132
SITE-01017 | PRJ-2024008 | CL003 | West | Gujarat | Rajkot | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-11-13 |  |  | BOM Finalization | Cancelled | N/A | 100 | 36379 | 12001 | FE-399
SITE-01018 | PRJ-2024008 | CL003 | West | Maharashtra | Pune | MPLS | Branch | Airtel Business | 2025-06-25 |  | 369 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 28697 | 12588 | FE-328
SITE-01019 | PRJ-2024008 | CL003 | West | Goa | Panaji | MPLS | ATM/Off-site | Tata Communications | 2024-12-10 | 2024-12-13 | 3 | Go-Live | Live - Operational | Met | 20 | 126706 | 4073 | FE-143
SITE-01020 | PRJ-2024008 | CL003 | West | Maharashtra | Thane | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-02-09 | 2025-02-21 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 60550 | 8425 | FE-123
SITE-01021 | PRJ-2024008 | CL003 | West | Goa | Margao | MPLS | Corporate Office | Excitel Enterprise | 2025-04-04 | 2025-04-25 | 21 | Go-Live | Live - Operational | Breached | 34 | 107452 | 12318 | FE-361
SITE-01022 | PRJ-2024008 | CL003 | West | Gujarat | Ahmedabad | MPLS | Branch | Airtel Business | 2025-06-05 |  | 389 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 52651 | 5821 | FE-253
SITE-01023 | PRJ-2024008 | CL003 | West | Gujarat | Surat | MPLS | ATM/Off-site | Excitel Enterprise | 2025-03-29 |  | 457 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 64358 | 5605 | FE-473
SITE-01024 | PRJ-2024008 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Vodafone Idea Business | 2025-01-12 |  | 533 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 80436 | 10972 | FE-142
SITE-01025 | PRJ-2024008 | CL003 | West | Goa | Margao | MPLS | ATM/Off-site | Tata Communications | 2024-12-14 |  |  | ROW / Permission | Cancelled | N/A | 20 | 110984 | 14916 | FE-430
SITE-01026 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-04 |  | 510 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 83009 | 16960 | FE-178
SITE-01027 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2024-08-26 |  | 672 | Site Survey | Survey Complete | Breached | 4 | 63405 | 5541 | FE-372
SITE-01028 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | Corporate Office | Local ISP Partner | 2024-09-05 |  | 662 | Site Survey | Survey Complete | Breached | 4 | 75555 | 8964 | FE-498
SITE-01029 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Branch | Vodafone Idea Business | 2024-10-29 | 2024-10-19 | -10 | Go-Live | Live - Operational | Met | 10 | 77628 | 5220 | FE-163
SITE-01030 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Data Center | Tata Communications | 2025-03-18 |  | 468 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 119810 | 12874 | FE-244
SITE-01031 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Airtel Business | 2024-10-02 | 2024-10-12 | 10 | Go-Live | Live - Operational | Breached | 34 | 133655 | 15645 | FE-447
SITE-01032 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | Corporate Office | Tata Communications | 2024-09-21 |  | 646 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 114188 | 5570 | FE-173
SITE-01033 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-04-12 | 2025-04-25 | 13 | Go-Live | Live - Operational | Breached | 50 | 120639 | 11000 | FE-193
SITE-01034 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Corporate Office | Sify Technologies | 2024-12-26 |  | 550 | Site Survey | Survey Scheduled | Breached | 50 | 96235 | 15271 | FE-217
SITE-01035 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Corporate Office | Tata Communications | 2024-12-02 | 2024-12-21 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 38052 | 15459 | FE-222
SITE-01036 | PRJ-2024009 | CL006 | West | Maharashtra | Pune | SD-WAN | Branch | Local ISP Partner | 2024-09-03 |  | 664 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 100634 | 11574 | FE-105
SITE-01037 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2024-12-25 |  | 551 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 81145 | 3727 | FE-415
SITE-01038 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2024-12-06 |  | 570 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 60011 | 15607 | FE-438
SITE-01039 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2024-10-02 |  | 635 | Site Survey | Survey Scheduled | Breached | 6 | 37846 | 9513 | FE-168
SITE-01040 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Airtel Business | 2024-12-24 |  | 552 | Site Survey | Survey Scheduled | Breached | 34 | 42841 | 9037 | FE-447
SITE-01041 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Corporate Office | Sify Technologies | 2024-11-04 | 2024-11-14 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 28292 | 15591 | FE-423
SITE-01042 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Branch | Vodafone Idea Business | 2025-01-31 | 2025-02-11 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 35536 | 9328 | FE-103
SITE-01043 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Branch | Sify Technologies | 2024-11-18 | 2024-11-16 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 80699 | 9308 | FE-104
SITE-01044 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Branch | Excitel Enterprise | 2024-10-09 |  | 628 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 81833 | 5529 | FE-349
SITE-01045 | PRJ-2024009 | CL006 | West | Maharashtra | Pune | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-10-23 |  | 614 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 77061 | 8403 | FE-286
SITE-01046 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Corporate Office | Tata Communications | 2025-03-15 |  | 471 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 114019 | 17252 | FE-324
SITE-01047 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | Data Center | Tata Communications | 2025-02-27 |  | 487 | Site Survey | Survey Complete | Breached | 34 | 120958 | 6751 | FE-156
SITE-01048 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Data Center | Local ISP Partner | 2024-09-23 | 2024-10-08 | 15 | Go-Live | Live - Operational | Breached | 34 | 32142 | 6126 | FE-441
SITE-01049 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Branch | Vodafone Idea Business | 2024-10-27 |  | 610 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 100105 | 11619 | FE-449
SITE-01050 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Data Center | Airtel Business | 2024-12-26 |  | 550 | Site Survey | Survey Complete | Breached | 4 | 42139 | 16487 | FE-110
SITE-01051 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | ATM/Off-site | Tata Communications | 2024-12-26 | 2024-12-21 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 84317 | 13282 | FE-477
SITE-01052 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-11-02 |  | 604 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 127732 | 10527 | FE-226
SITE-01053 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | Corporate Office | Local ISP Partner | 2024-10-30 | 2024-10-27 | -3 | Go-Live | Live - Operational | Met | 10 | 115337 | 16944 | FE-319
SITE-01054 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Branch | Local ISP Partner | 2025-03-08 |  | 478 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 52729 | 17506 | FE-402
SITE-01055 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | Branch | Sify Technologies | 2024-09-22 | 2024-10-07 | 15 | Go-Live | Live - Operational | Breached | 10 | 47163 | 10484 | FE-109
SITE-01056 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2024-11-25 | 2024-12-11 | 16 | Go-Live | Live - Operational | Breached | 10 | 57068 | 9007 | FE-318
SITE-01057 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | Branch | Sify Technologies | 2024-12-07 |  | 569 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 63290 | 9456 | FE-243
SITE-01058 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Tata Communications | 2024-11-09 | 2024-11-02 | -7 | Go-Live | Live - Operational | Met | 2 | 34832 | 14320 | FE-481
SITE-01059 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-12-18 | 2024-12-21 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 52227 | 7633 | FE-351
SITE-01060 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Branch | Local ISP Partner | 2024-09-17 | 2024-09-15 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 71412 | 9407 | FE-479
SITE-01061 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-02-02 | 2025-02-09 | 7 | Go-Live | Live - Operational | Breached | 50 | 39433 | 5242 | FE-166
SITE-01062 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | ATM/Off-site | Airtel Business | 2025-04-10 |  | 445 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 40928 | 4726 | FE-379
SITE-01063 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Excitel Enterprise | 2024-12-19 |  | 557 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 33742 | 5594 | FE-198
SITE-01064 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-11-16 |  | 590 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 85163 | 4609 | FE-347
SITE-01065 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | ATM/Off-site | Sify Technologies | 2025-01-20 | 2025-01-27 | 7 | Go-Live | Live - Operational | Breached | 2 | 102209 | 4496 | FE-455
SITE-01066 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-11 |  | 503 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 49694 | 10672 | FE-484
SITE-01067 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | Corporate Office | Airtel Business | 2025-01-22 |  | 523 | Site Survey | Survey Complete | Breached | 6 | 28471 | 6121 | FE-392
SITE-01068 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2024-12-14 |  | 562 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 67768 | 17466 | FE-212
SITE-01069 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Airtel Business | 2024-09-19 |  | 648 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 97935 | 7402 | FE-249
SITE-01070 | PRJ-2024009 | CL006 | West | Maharashtra | Pune | SD-WAN | Branch | Local ISP Partner | 2024-09-23 | 2024-09-26 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 55521 | 12258 | FE-159
SITE-01071 | PRJ-2024009 | CL006 | West | Maharashtra | Nagpur | SD-WAN | Corporate Office | Sify Technologies | 2025-01-21 |  | 524 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 120466 | 17983 | FE-381
SITE-01072 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-04-06 |  | 449 | Site Survey | Survey Complete | Breached | 34 | 35505 | 13755 | FE-105
SITE-01073 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | ATM/Off-site | Sify Technologies | 2024-10-30 |  | 607 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 98436 | 14269 | FE-498
SITE-01074 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2024-10-24 |  | 613 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 85958 | 7114 | FE-266
SITE-01075 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Airtel Business | 2025-01-28 |  | 517 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 58372 | 15457 | FE-471
SITE-01076 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Branch | Vodafone Idea Business | 2025-04-07 | 2025-04-27 | 20 | Go-Live | Live - Operational | Breached | 6 | 88213 | 6531 | FE-190
SITE-01077 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Corporate Office | Tata Communications | 2024-10-05 |  | 632 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 49354 | 6411 | FE-301
SITE-01078 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-09-07 | 2024-09-24 | 17 | Go-Live | Live - Operational | Breached | 50 | 41137 | 15367 | FE-369
SITE-01079 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Data Center | Vodafone Idea Business | 2024-09-14 |  | 653 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 42422 | 17042 | FE-106
SITE-01080 | PRJ-2024009 | CL006 | West | Maharashtra | Pune | SD-WAN | Corporate Office | Airtel Business | 2025-03-05 | 2025-02-28 | -5 | Go-Live | Live - Operational | Met | 2 | 131861 | 3653 | FE-154
SITE-01081 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-09-24 | 2024-10-14 | 20 | Go-Live | Live - Operational | Breached | 6 | 68289 | 8935 | FE-345
SITE-01082 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-01-06 | 2025-01-13 | 7 | Go-Live | Live - Operational | Breached | 2 | 33836 | 5184 | FE-378
SITE-01083 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Airtel Business | 2025-04-03 |  | 452 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 57401 | 3893 | FE-216
SITE-01084 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | ATM/Off-site | Local ISP Partner | 2024-11-18 | 2024-11-26 | 8 | Go-Live | Live - Operational | Breached | 50 | 118015 | 17987 | FE-466
SITE-01085 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Branch | Sify Technologies | 2024-09-17 | 2024-09-21 | 4 | Go-Live | Live - Operational | Met | 34 | 37999 | 13587 | FE-270
SITE-01086 | PRJ-2024009 | CL006 | West | Maharashtra | Nagpur | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-04-06 | 2025-03-29 | -8 | Go-Live | Live - Operational | Met | 6 | 84181 | 12191 | FE-271
SITE-01087 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-04-05 | 2025-04-14 | 9 | Go-Live | Live - Operational | Breached | 34 | 41621 | 7941 | FE-355
SITE-01088 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Branch | Tata Communications | 2025-03-12 |  | 474 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 129945 | 14245 | FE-175
SITE-01089 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Tata Communications | 2024-12-12 |  | 564 | Site Survey | Survey Complete | Breached | 4 | 103739 | 10503 | FE-472
SITE-01090 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-11-10 | 2024-11-08 | -2 | Go-Live | Live - Operational | Met | 34 | 69853 | 11597 | FE-317
SITE-01091 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | Corporate Office | Airtel Business | 2025-03-11 |  | 475 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 78224 | 10359 | FE-381
SITE-01092 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-01-04 |  | 541 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 104148 | 15213 | FE-315
SITE-01093 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | ATM/Off-site | Tata Communications | 2024-11-20 | 2024-11-10 | -10 | Go-Live | Live - Operational | Met | 34 | 101187 | 11264 | FE-168
SITE-01094 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | ATM/Off-site | Sify Technologies | 2024-11-20 | 2024-12-09 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 46892 | 17184 | FE-382
SITE-01095 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Branch | Local ISP Partner | 2025-03-19 | 2025-03-23 | 4 | Go-Live | Live - Operational | Met | 6 | 43366 | 14899 | FE-460
SITE-01096 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Data Center | Sify Technologies | 2024-08-26 |  | 672 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 119934 | 5236 | FE-439
SITE-01097 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | ATM/Off-site | Tata Communications | 2025-03-30 |  | 456 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 75873 | 5814 | FE-140
SITE-01098 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | ATM/Off-site | Airtel Business | 2025-01-12 | 2025-01-28 | 16 | Go-Live | Live - Operational | Breached | 100 | 125459 | 5795 | FE-483
SITE-01099 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-02-20 |  | 494 | Site Survey | Survey Complete | Breached | 2 | 65587 | 5322 | FE-179
SITE-01100 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-02-28 |  | 486 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 29424 | 9994 | FE-316
SITE-01101 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Corporate Office | Local ISP Partner | 2024-12-26 |  | 550 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 83531 | 6069 | FE-239
SITE-01102 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-09-21 |  | 646 | Site Survey | Survey Complete | Breached | 2 | 56692 | 9927 | FE-194
SITE-01103 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Data Center | Vodafone Idea Business | 2024-11-08 |  | 598 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 35165 | 16661 | FE-290
SITE-01104 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Branch | Sify Technologies | 2024-09-16 | 2024-09-12 | -4 | Go-Live | Live - Operational | Met | 34 | 31676 | 7424 | FE-244
SITE-01105 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Corporate Office | Airtel Business | 2024-10-13 | 2024-10-03 | -10 | Go-Live | Live - Operational | Met | 10 | 111674 | 4030 | FE-223
SITE-01106 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Branch | Excitel Enterprise | 2025-01-11 |  | 534 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 33987 | 4287 | FE-261
SITE-01107 | PRJ-2024009 | CL006 | West | Maharashtra | Nagpur | SD-WAN | Data Center | Excitel Enterprise | 2024-11-19 | 2024-11-27 | 8 | Go-Live | Live - Operational | Breached | 10 | 69218 | 15818 | FE-300
SITE-01108 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-02-08 |  |  | Site Survey | Cancelled | N/A | 4 | 93821 | 16729 | FE-496
SITE-01109 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Data Center | Vodafone Idea Business | 2025-03-11 |  | 475 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 66026 | 6141 | FE-177
SITE-01110 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | ATM/Off-site | Airtel Business | 2024-09-12 |  | 655 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 128771 | 15272 | FE-182
SITE-01111 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Corporate Office | Excitel Enterprise | 2024-11-14 | 2024-11-22 | 8 | Go-Live | Live - Operational | Breached | 50 | 33244 | 15177 | FE-496
SITE-01112 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-01-23 | 2025-01-17 | -6 | Go-Live | Live - Operational | Met | 100 | 40767 | 16684 | FE-107
SITE-01113 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Branch | Vodafone Idea Business | 2025-03-30 |  | 456 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 87612 | 8639 | FE-186
SITE-01114 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Corporate Office | Tata Communications | 2024-10-30 | 2024-11-12 | 13 | Go-Live | Live - Operational | Breached | 4 | 51486 | 15143 | FE-495
SITE-01115 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Data Center | Local ISP Partner | 2024-10-24 |  | 613 | Site Survey | Survey Scheduled | Breached | 6 | 44248 | 12818 | FE-349
SITE-01116 | PRJ-2024009 | CL006 | West | Maharashtra | Nagpur | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2024-11-30 | 2024-12-08 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 85780 | 9508 | FE-362
SITE-01117 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-10 | 2025-02-26 | 16 | Go-Live | Live - Operational | Breached | 20 | 117463 | 4199 | FE-417
SITE-01118 | PRJ-2024009 | CL006 | West | Maharashtra | Pune | SD-WAN | Branch | Airtel Business | 2025-03-18 |  |  | ROW / Permission | Cancelled | N/A | 4 | 66097 | 9657 | FE-181
SITE-01119 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | Branch | Sify Technologies | 2024-11-27 | 2024-12-16 | 19 | Go-Live | Live - Operational | Breached | 100 | 89405 | 14026 | FE-373
SITE-01120 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | Data Center | Vodafone Idea Business | 2024-10-05 | 2024-10-01 | -4 | Go-Live | Live - Operational | Met | 10 | 80628 | 8885 | FE-133
SITE-01121 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Local ISP Partner | 2024-12-22 |  | 554 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 42984 | 8060 | FE-332
SITE-01122 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | ATM/Off-site | Sify Technologies | 2024-12-18 | 2024-12-17 | -1 | Go-Live | Live - Operational | Met | 2 | 106784 | 16184 | FE-294
SITE-01123 | PRJ-2024009 | CL006 | West | Maharashtra | Nagpur | SD-WAN | ATM/Off-site | Tata Communications | 2024-12-19 |  | 557 | Site Survey | Survey Scheduled | Breached | 10 | 31007 | 15929 | FE-450
SITE-01124 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Branch | Airtel Business | 2025-01-29 | 2025-01-30 | 1 | Go-Live | Live - Operational | Met | 4 | 63901 | 10136 | FE-141
SITE-01125 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-01-01 |  | 544 | Site Survey | Survey Scheduled | Breached | 20 | 52127 | 17107 | FE-127
SITE-01126 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | ATM/Off-site | Airtel Business | 2025-02-28 | 2025-03-04 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 82932 | 11390 | FE-343
SITE-01127 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-10 |  | 445 | Site Survey | Survey Complete | Breached | 2 | 101519 | 16329 | FE-405
SITE-01128 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-06 |  | 508 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 70432 | 14380 | FE-475
SITE-01129 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-04-06 | 2025-04-25 | 19 | Go-Live | Live - Operational | Breached | 34 | 42890 | 16476 | FE-445
SITE-01130 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Branch | Vodafone Idea Business | 2025-02-20 |  | 494 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 111138 | 10861 | FE-427
SITE-01131 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | Data Center | Local ISP Partner | 2025-02-26 | 2025-02-28 | 2 | Go-Live | Live - Operational | Met | 6 | 106766 | 9685 | FE-210
SITE-01132 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Corporate Office | Sify Technologies | 2025-02-09 | 2025-01-30 | -10 | Go-Live | Live - Operational | Met | 2 | 67576 | 8529 | FE-357
SITE-01133 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Data Center | Vodafone Idea Business | 2024-12-14 |  | 562 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 74165 | 17068 | FE-377
SITE-01134 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Data Center | Sify Technologies | 2024-10-04 | 2024-10-23 | 19 | Go-Live | Live - Operational | Breached | 6 | 100450 | 13246 | FE-183
SITE-01135 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | Data Center | Local ISP Partner | 2025-03-24 | 2025-04-09 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 120024 | 13664 | FE-150
SITE-01136 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-02 | 2025-01-24 | -9 | Go-Live | Live - Operational | Met | 4 | 93064 | 15787 | FE-484
SITE-01137 | PRJ-2024009 | CL006 | West | Maharashtra | Nashik | SD-WAN | Branch | Local ISP Partner | 2025-01-15 |  | 530 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 83134 | 6971 | FE-214
SITE-01138 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | Branch | Sify Technologies | 2024-10-09 | 2024-10-29 | 20 | Go-Live | Live - Operational | Breached | 100 | 82124 | 16941 | FE-430
SITE-01139 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-03-08 |  | 478 | Site Survey | Survey Complete | Breached | 20 | 63076 | 17911 | FE-437
SITE-01140 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | ATM/Off-site | Tata Communications | 2025-02-08 |  | 506 | Site Survey | Survey Scheduled | Breached | 50 | 32282 | 3754 | FE-113
SITE-01141 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-03-17 |  | 469 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 50336 | 12874 | FE-320
SITE-01142 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Branch | Excitel Enterprise | 2025-01-24 | 2025-02-08 | 15 | Go-Live | Live - Operational | Breached | 50 | 44891 | 13924 | FE-299
SITE-01143 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | Data Center | Airtel Business | 2024-12-30 | 2024-12-30 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 121064 | 16626 | FE-164
SITE-01144 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | Corporate Office | Excitel Enterprise | 2025-03-23 |  | 463 | Site Survey | Survey Complete | Breached | 6 | 70258 | 6838 | FE-147
SITE-01145 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2024-08-22 |  | 676 | Site Survey | Survey Scheduled | Breached | 2 | 109015 | 15092 | FE-378
SITE-01146 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-08-26 |  | 672 | Site Survey | Survey Complete | Breached | 34 | 52452 | 7427 | FE-434
SITE-01147 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Data Center | Sify Technologies | 2025-01-04 | 2025-01-09 | 5 | Go-Live | Live - Operational | Met | 2 | 64040 | 4859 | FE-173
SITE-01148 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-09-17 | 2024-10-06 | 19 | Go-Live | Live - Operational | Breached | 4 | 46590 | 8127 | FE-234
SITE-01149 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2024-12-24 | 2025-01-06 | 13 | Go-Live | Live - Operational | Breached | 4 | 92361 | 16532 | FE-111
SITE-01150 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | Branch | Airtel Business | 2025-01-27 |  | 518 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 77185 | 8637 | FE-424
SITE-01151 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | ATM/Off-site | Local ISP Partner | 2024-11-04 | 2024-10-25 | -10 | Go-Live | Live - Operational | Met | 2 | 43362 | 9116 | FE-277
SITE-01152 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | Branch | Airtel Business | 2024-12-31 | 2025-01-06 | 6 | Go-Live | Live - Operational | Breached | 2 | 98248 | 3877 | FE-365
SITE-01153 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | ATM/Off-site | Tata Communications | 2024-09-18 |  | 649 | Site Survey | Survey Complete | Breached | 34 | 46161 | 7100 | FE-142
SITE-01154 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Branch | Sify Technologies | 2024-12-21 | 2024-12-22 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 89216 | 15709 | FE-353
SITE-01155 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Gwalior | SD-WAN | ATM/Off-site | Local ISP Partner | 2024-10-23 | 2024-10-24 | 1 | Go-Live | Live - Operational | Met | 20 | 79488 | 5185 | FE-398
SITE-01156 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Vodafone Idea Business | 2025-02-20 | 2025-03-13 | 21 | Go-Live | Live - Operational | Breached | 50 | 106162 | 15740 | FE-239
SITE-01157 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Data Center | Airtel Business | 2024-11-26 |  | 580 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 77015 | 13866 | FE-132
SITE-01158 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-28 | 2025-01-03 | 6 | Go-Live | Live - Operational | Breached | 20 | 107152 | 17044 | FE-430
SITE-01159 | PRJ-2024009 | CL006 | West | Goa | Margao | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-09-18 | 2024-09-19 | 1 | Go-Live | Live - Operational | Met | 6 | 74890 | 7519 | FE-137
SITE-01160 | PRJ-2024009 | CL006 | West | Gujarat | Vadodara | SD-WAN | Corporate Office | Tata Communications | 2024-09-26 |  | 641 | Site Survey | Survey Complete | Breached | 2 | 69758 | 14776 | FE-105
SITE-01161 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Corporate Office | Airtel Business | 2025-01-12 |  | 533 | Site Survey | Survey Scheduled | Breached | 4 | 78540 | 8146 | FE-408
SITE-01162 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-01-10 | 2025-01-17 | 7 | Go-Live | Live - Operational | Breached | 4 | 103228 | 14088 | FE-315
SITE-01163 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Branch | Vodafone Idea Business | 2024-10-09 | 2024-10-10 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 34133 | 7996 | FE-315
SITE-01164 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2024-10-02 |  | 635 | Site Survey | Survey Scheduled | Breached | 50 | 58988 | 12943 | FE-110
SITE-01165 | PRJ-2024009 | CL006 | West | Goa | Panaji | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-03-08 |  | 478 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 65272 | 5647 | FE-306
SITE-01166 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | Corporate Office | Local ISP Partner | 2024-08-30 |  | 668 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 37103 | 11198 | FE-148
SITE-01167 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Jabalpur | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-11-09 | 2024-11-28 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 100935 | 16191 | FE-260
SITE-01168 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Bhopal | SD-WAN | Data Center | Vodafone Idea Business | 2024-11-04 |  | 602 | Site Survey | Survey Complete | Breached | 4 | 77008 | 13624 | FE-152
SITE-01169 | PRJ-2024009 | CL006 | West | Maharashtra | Pune | SD-WAN | ATM/Off-site | Tata Communications | 2025-03-19 | 2025-03-09 | -10 | Go-Live | Live - Operational | Met | 34 | 118124 | 15366 | FE-323
SITE-01170 | PRJ-2024009 | CL006 | West | Gujarat | Surat | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2024-10-07 | 2024-10-20 | 13 | Go-Live | Live - Operational | Breached | 2 | 62037 | 17972 | FE-122
SITE-01171 | PRJ-2024009 | CL006 | West | Maharashtra | Mumbai | SD-WAN | Corporate Office | Local ISP Partner | 2024-09-08 | 2024-09-11 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 63377 | 14946 | FE-187
SITE-01172 | PRJ-2024009 | CL006 | West | Gujarat | Rajkot | SD-WAN | ATM/Off-site | Excitel Enterprise | 2024-09-21 | 2024-10-01 | 10 | Go-Live | Live - Operational | Breached | 50 | 111480 | 10820 | FE-442
SITE-01173 | PRJ-2024009 | CL006 | West | Maharashtra | Thane | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-20 |  | 617 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 64771 | 8774 | FE-495
SITE-01174 | PRJ-2024009 | CL006 | West | Madhya Pradesh | Indore | SD-WAN | Branch | Sify Technologies | 2024-10-26 | 2024-11-03 | 8 | Go-Live | Live - Operational | Breached | 10 | 114439 | 14102 | FE-476
SITE-01175 | PRJ-2024009 | CL006 | West | Gujarat | Ahmedabad | SD-WAN | ATM/Off-site | Tata Communications | 2024-12-24 | 2024-12-17 | -7 | Go-Live | Live - Operational | Met | 10 | 89361 | 16910 | FE-297
SITE-01176 | PRJ-2024010 | CL003 | North | Punjab | Amritsar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-11 | 2025-02-14 | 3 | Go-Live | Live - Operational | Met | 34 | 127678 | 8608 | FE-462
SITE-01177 | PRJ-2024010 | CL003 | North | Uttar Pradesh | Kanpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2024-12-13 |  | 563 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 78538 | 10912 | FE-417
SITE-01178 | PRJ-2024010 | CL003 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-01-03 |  | 542 | Site Survey | Survey Complete | Breached | 50 | 49521 | 14743 | FE-257
SITE-01179 | PRJ-2024010 | CL003 | North | Rajasthan | Jaipur | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-03-14 | 2025-03-10 | -4 | Go-Live | Live - Operational | Met | 2 | 88404 | 6564 | FE-236
SITE-01180 | PRJ-2024010 | CL003 | North | Delhi NCR | Faridabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-03-31 |  | 455 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 43509 | 12516 | FE-143
SITE-01181 | PRJ-2024011 | CL002 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-01-28 | 2025-02-12 | 15 | Go-Live | Live - Operational | Breached | 34 | 34967 | 10730 | FE-239
SITE-01182 | PRJ-2024011 | CL002 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-06-05 | 2025-06-19 | 14 | Go-Live | Live - Operational | Breached | 20 | 52831 | 10097 | FE-190
SITE-01183 | PRJ-2024011 | CL002 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-05-25 |  | 400 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 42311 | 14660 | FE-125
SITE-01184 | PRJ-2024011 | CL002 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-01-19 | 2025-01-12 | -7 | Go-Live | Live - Operational | Met | 20 | 59295 | 4578 | FE-372
SITE-01185 | PRJ-2024011 | CL002 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-03 | 2025-08-18 | 15 | Go-Live | Live - Operational | Breached | 4 | 56821 | 15524 | FE-454
SITE-01186 | PRJ-2024011 | CL002 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-02-02 | 2025-02-05 | 3 | Go-Live | Live - Operational | Met | 20 | 120517 | 13269 | FE-247
SITE-01187 | PRJ-2024011 | CL002 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-04-28 | 2025-05-18 | 20 | Go-Live | Live - Operational | Breached | 10 | 50312 | 8662 | FE-448
SITE-01188 | PRJ-2024011 | CL002 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-03-16 | 2025-04-04 | 19 | Go-Live | Live - Operational | Breached | 100 | 84088 | 8973 | FE-110
SITE-01189 | PRJ-2024011 | CL002 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-02-02 | 2025-01-23 | -10 | Go-Live | Live - Operational | Met | 100 | 104435 | 3516 | FE-350
SITE-01190 | PRJ-2024011 | CL002 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-01-01 | 2024-12-23 | -9 | Go-Live | Live - Operational | Met | 20 | 57922 | 12106 | FE-357
SITE-01191 | PRJ-2024012 | CL008 | North | Punjab | Ludhiana | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2024-09-07 | 2024-09-16 | 9 | Go-Live | Live - Operational | Breached | 100 | 124313 | 9247 | FE-379
SITE-01192 | PRJ-2024012 | CL008 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2024-10-16 |  | 621 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 74219 | 8433 | FE-463
SITE-01193 | PRJ-2024012 | CL008 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-20 |  | 466 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 63381 | 14735 | FE-365
SITE-01194 | PRJ-2024012 | CL008 | North | Uttarakhand | Dehradun | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2024-11-26 | 2024-11-30 | 4 | Go-Live | Live - Operational | Met | 100 | 32050 | 7503 | FE-395
SITE-01195 | PRJ-2024012 | CL008 | North | Uttarakhand | Haridwar | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2024-10-04 |  | 633 | Site Survey | Survey Complete | Breached | 50 | 111720 | 5268 | FE-240
SITE-01196 | PRJ-2024012 | CL008 | North | Uttarakhand | Haridwar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2024-09-26 |  | 641 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 71410 | 9906 | FE-401
SITE-01197 | PRJ-2024012 | CL008 | North | Uttar Pradesh | Noida | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2024-09-30 | 2024-09-26 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 108264 | 5514 | FE-321
SITE-01198 | PRJ-2024012 | CL008 | North | Uttar Pradesh | Agra | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2024-10-25 | 2024-10-23 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 89121 | 14656 | FE-176
SITE-01199 | PRJ-2024012 | CL008 | North | Rajasthan | Udaipur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-01-02 |  | 543 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 65782 | 4558 | FE-250
SITE-01200 | PRJ-2024012 | CL008 | North | Delhi NCR | Faridabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2024-10-07 | 2024-10-15 | 8 | Go-Live | Live - Operational | Breached | 2 | 92011 | 8510 | FE-102
SITE-01201 | PRJ-2024012 | CL008 | North | Uttar Pradesh | Noida | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-03-14 |  | 472 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 46051 | 9237 | FE-245
SITE-01202 | PRJ-2024012 | CL008 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-02-11 | 2025-02-18 | 7 | Go-Live | Live - Operational | Breached | 10 | 84629 | 13088 | FE-141
SITE-01203 | PRJ-2024012 | CL008 | North | Haryana | Gurugram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2024-12-12 | 2024-12-24 | 12 | Go-Live | Live - Operational | Breached | 50 | 83386 | 10039 | FE-150
SITE-01204 | PRJ-2024012 | CL008 | North | Haryana | Faridabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2024-10-31 |  | 606 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 116987 | 17851 | FE-265
SITE-01205 | PRJ-2024012 | CL008 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-02-25 |  | 489 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 82566 | 12581 | FE-202
SITE-01206 | PRJ-2024012 | CL008 | North | Haryana | Faridabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2024-10-28 | 2024-11-16 | 19 | Go-Live | Live - Operational | Breached | 50 | 130551 | 17851 | FE-323
SITE-01207 | PRJ-2024012 | CL008 | North | Delhi NCR | Gurugram | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2024-12-04 |  | 572 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 89391 | 9303 | FE-318
SITE-01208 | PRJ-2024012 | CL008 | North | Uttar Pradesh | Varanasi | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2024-12-09 |  | 567 | Site Survey | Survey Complete | Breached | 2 | 128502 | 10396 | FE-145
SITE-01209 | PRJ-2024012 | CL008 | North | Punjab | Jalandhar | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-03-02 | 2025-03-04 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 44682 | 13672 | FE-378
SITE-01210 | PRJ-2024012 | CL008 | North | Rajasthan | Udaipur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-02-22 | 2025-03-09 | 15 | Go-Live | Live - Operational | Breached | 2 | 88661 | 16729 | FE-490
SITE-01211 | PRJ-2024012 | CL008 | North | Rajasthan | Kota | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2024-09-03 | 2024-08-27 | -7 | Go-Live | Live - Operational | Met | 4 | 71710 | 13237 | FE-149
SITE-01212 | PRJ-2024012 | CL008 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-02-05 |  | 509 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 125055 | 13078 | FE-445
SITE-01213 | PRJ-2024012 | CL008 | North | Rajasthan | Jaipur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2024-10-04 |  |  | ROW / Permission | Cancelled | N/A | 100 | 45878 | 7162 | FE-445
SITE-01214 | PRJ-2024012 | CL008 | North | Uttarakhand | Dehradun | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-01-20 | 2025-01-24 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 43035 | 4600 | FE-100
SITE-01215 | PRJ-2024012 | CL008 | North | Punjab | Jalandhar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2024-12-24 | 2024-12-20 | -4 | Go-Live | Live - Operational | Met | 4 | 90094 | 3903 | FE-358
SITE-01216 | PRJ-2024013 | CL006 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Vodafone Idea Business | 2024-10-28 | 2024-11-06 | 9 | Go-Live | Live - Operational | Breached | 6 | 58792 | 17290 | FE-379
SITE-01217 | PRJ-2024013 | CL006 | South | Telangana | Warangal | SD-WAN | Branch | Vodafone Idea Business | 2025-03-03 |  | 483 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 111387 | 3854 | FE-194
SITE-01218 | PRJ-2024013 | CL006 | South | Tamil Nadu | Coimbatore | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-02-04 | 2025-02-28 | 24 | Go-Live | Live - Operational | Breached | 100 | 66015 | 8242 | FE-441
SITE-01219 | PRJ-2024013 | CL006 | South | Karnataka | Hubli | SD-WAN | Corporate Office | Vodafone Idea Business | 2024-12-30 |  | 546 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 119442 | 16604 | FE-154
SITE-01220 | PRJ-2024013 | CL006 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Branch | Sify Technologies | 2024-11-03 |  | 603 | Site Survey | Survey Scheduled | Breached | 100 | 43745 | 12744 | FE-299
SITE-01221 | PRJ-2024013 | CL006 | South | Karnataka | Hubli | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-05 | 2024-10-20 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 74494 | 5782 | FE-339
SITE-01222 | PRJ-2024013 | CL006 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2024-11-06 | 2024-11-18 | 12 | Go-Live | Live - Operational | Breached | 10 | 73722 | 15070 | FE-368
SITE-01223 | PRJ-2024013 | CL006 | South | Andhra Pradesh | Guntur | SD-WAN | Corporate Office | Local ISP Partner | 2024-11-10 | 2024-11-09 | -1 | Go-Live | Live - Operational | Met | 34 | 88225 | 15217 | FE-171
SITE-01224 | PRJ-2024013 | CL006 | South | Telangana | Warangal | SD-WAN | Data Center | Vodafone Idea Business | 2024-10-14 |  | 623 | Site Survey | Survey Complete | Breached | 100 | 107408 | 14296 | FE-192
SITE-01225 | PRJ-2024013 | CL006 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-04-13 |  | 442 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 119457 | 8809 | FE-401
SITE-01226 | PRJ-2024013 | CL006 | South | Kerala | Thiruvananthapuram | SD-WAN | Data Center | Tata Communications | 2025-03-04 |  | 482 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 31869 | 17459 | FE-475
SITE-01227 | PRJ-2024013 | CL006 | South | Tamil Nadu | Coimbatore | SD-WAN | Data Center | Local ISP Partner | 2025-03-16 | 2025-03-12 | -4 | Go-Live | Live - Operational | Met | 100 | 70422 | 15950 | FE-218
SITE-01228 | PRJ-2024013 | CL006 | South | Tamil Nadu | Chennai | SD-WAN | Data Center | Tata Communications | 2025-04-01 | 2025-04-15 | 14 | Go-Live | Live - Operational | Breached | 2 | 108203 | 7603 | FE-158
SITE-01229 | PRJ-2024013 | CL006 | South | Karnataka | Hubli | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-01-18 | 2025-01-31 | 13 | Go-Live | Live - Operational | Breached | 2 | 50815 | 8761 | FE-155
SITE-01230 | PRJ-2024013 | CL006 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | ATM/Off-site | Airtel Business | 2025-03-09 | 2025-04-03 | 25 | Go-Live | Live - Operational | Breached | 20 | 92369 | 10668 | FE-447
SITE-01231 | PRJ-2024014 | CL007 | West | Goa | Panaji | VSAT | Data Center | Excitel Enterprise | 2025-05-10 | 2025-05-10 | 0 | Go-Live | Live - Operational | Met | 10 | 39274 | 13037 | FE-112
SITE-01232 | PRJ-2024014 | CL007 | West | Maharashtra | Pune | VSAT | Branch | Sify Technologies | 2025-05-28 | 2025-05-26 | -2 | Go-Live | Live - Operational | Met | 50 | 102487 | 12455 | FE-136
SITE-01233 | PRJ-2024014 | CL007 | West | Goa | Panaji | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-07 |  | 418 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 55194 | 12844 | FE-342
SITE-01234 | PRJ-2024014 | CL007 | West | Goa | Margao | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-06-20 |  | 374 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 85524 | 10504 | FE-420
SITE-01235 | PRJ-2024014 | CL007 | West | Madhya Pradesh | Bhopal | VSAT | ATM/Off-site | Excitel Enterprise | 2024-11-22 |  | 584 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 41226 | 5432 | FE-355
SITE-01236 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | Corporate Office | Tata Communications | 2025-02-05 |  | 509 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 65997 | 17068 | FE-228
SITE-01237 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | ATM/Off-site | Sify Technologies | 2024-10-07 |  | 630 | Site Survey | Survey Complete | Breached | 4 | 98047 | 12926 | FE-223
SITE-01238 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Excitel Enterprise | 2024-12-08 |  | 568 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 99557 | 14928 | FE-156
SITE-01239 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Branch | Sify Technologies | 2025-03-06 | 2025-02-25 | -9 | Go-Live | Live - Operational | Met | 50 | 62194 | 6785 | FE-271
SITE-01240 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Branch | Airtel Business | 2025-02-07 | 2025-02-18 | 11 | Go-Live | Live - Operational | Breached | 100 | 37556 | 16699 | FE-388
SITE-01241 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Excitel Enterprise | 2024-12-17 | 2024-12-11 | -6 | Go-Live | Live - Operational | Met | 4 | 100276 | 11344 | FE-166
SITE-01242 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Warehouse/Ops Hub | Airtel Business | 2024-09-29 | 2024-10-20 | 21 | Go-Live | Live - Operational | Breached | 34 | 84559 | 11324 | FE-255
SITE-01243 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-09-26 | 2024-09-28 | 2 | Go-Live | Live - Operational | Met | 50 | 117383 | 14700 | FE-477
SITE-01244 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Data Center | Vodafone Idea Business | 2024-10-03 |  | 634 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 84324 | 14990 | FE-318
SITE-01245 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-01-10 | 2025-01-07 | -3 | Go-Live | Live - Operational | Met | 34 | 53381 | 9121 | FE-323
SITE-01246 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-10-13 | 2024-10-03 | -10 | Go-Live | Live - Operational | Met | 2 | 133089 | 3744 | FE-468
SITE-01247 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | Data Center | Airtel Business | 2024-10-04 | 2024-10-02 | -2 | Go-Live | Live - Operational | Met | 20 | 33730 | 8646 | FE-279
SITE-01248 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-03 | 2024-12-01 | -2 | Go-Live | Live - Operational | Met | 100 | 114190 | 5505 | FE-436
SITE-01249 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Data Center | Local ISP Partner | 2025-02-06 | 2025-02-09 | 3 | Go-Live | Live - Operational | Met | 34 | 56873 | 10766 | FE-465
SITE-01250 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | ATM/Off-site | Excitel Enterprise | 2024-12-03 |  | 573 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 69793 | 14932 | FE-377
SITE-01251 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-17 | 2025-01-02 | 16 | Go-Live | Live - Operational | Breached | 20 | 38282 | 6835 | FE-170
SITE-01252 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | ATM/Off-site | Tata Communications | 2025-03-28 | 2025-04-09 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 123015 | 16875 | FE-172
SITE-01253 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Data Center | Tata Communications | 2025-01-10 |  |  | ROW / Permission | Cancelled | N/A | 2 | 93392 | 17202 | FE-117
SITE-01254 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Corporate Office | Tata Communications | 2024-12-27 |  | 549 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 64581 | 17501 | FE-412
SITE-01255 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Data Center | Vodafone Idea Business | 2025-04-28 | 2025-05-12 | 14 | Go-Live | Live - Operational | Breached | 2 | 57418 | 6870 | FE-294
SITE-01256 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Tata Communications | 2024-10-03 |  | 634 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 31406 | 13473 | FE-486
SITE-01257 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Sify Technologies | 2024-11-14 |  | 592 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 84039 | 16322 | FE-473
SITE-01258 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Corporate Office | Excitel Enterprise | 2024-12-28 |  | 548 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 83552 | 12881 | FE-468
SITE-01259 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Local ISP Partner | 2024-10-31 | 2024-11-14 | 14 | Go-Live | Live - Operational | Breached | 10 | 45284 | 3748 | FE-243
SITE-01260 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Corporate Office | Sify Technologies | 2025-04-05 | 2025-04-29 | 24 | Go-Live | Live - Operational | Breached | 50 | 33060 | 13585 | FE-240
SITE-01261 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Tata Communications | 2024-11-23 |  | 583 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 68225 | 12813 | FE-438
SITE-01262 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Vodafone Idea Business | 2025-01-11 | 2025-01-30 | 19 | Go-Live | Live - Operational | Breached | 2 | 89137 | 4106 | FE-283
SITE-01263 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Data Center | Tata Communications | 2024-11-14 |  | 592 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 64234 | 13499 | FE-382
SITE-01264 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Corporate Office | Sify Technologies | 2024-11-05 |  | 601 | Site Survey | Survey Scheduled | Breached | 20 | 92871 | 5584 | FE-216
SITE-01265 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Branch | Airtel Business | 2025-03-06 |  | 480 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 113799 | 4130 | FE-194
SITE-01266 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Branch | Excitel Enterprise | 2024-12-10 |  | 566 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 35970 | 15207 | FE-232
SITE-01267 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Corporate Office | Excitel Enterprise | 2025-04-24 |  | 431 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 106719 | 7345 | FE-279
SITE-01268 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Branch | Excitel Enterprise | 2025-01-11 |  | 534 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 59061 | 6843 | FE-266
SITE-01269 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Branch | Local ISP Partner | 2025-01-04 |  | 541 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 65104 | 5844 | FE-112
SITE-01270 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Corporate Office | Vodafone Idea Business | 2025-01-02 | 2025-01-17 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 109515 | 4010 | FE-182
SITE-01271 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Branch | Tata Communications | 2024-10-28 | 2024-11-10 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 133910 | 8629 | FE-361
SITE-01272 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-12-17 |  | 559 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 114122 | 15399 | FE-176
SITE-01273 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-10-09 | 2024-10-13 | 4 | Go-Live | Live - Operational | Met | 50 | 98643 | 15510 | FE-162
SITE-01274 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-01-18 |  | 527 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 69541 | 7910 | FE-199
SITE-01275 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Corporate Office | Airtel Business | 2024-12-13 | 2024-12-18 | 5 | Go-Live | Live - Operational | Met | 100 | 69263 | 15758 | FE-159
SITE-01276 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Data Center | Sify Technologies | 2025-05-03 |  | 422 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 74135 | 12682 | FE-358
SITE-01277 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-01-21 |  | 524 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 131062 | 10362 | FE-217
SITE-01278 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Data Center | Local ISP Partner | 2024-11-21 |  | 585 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 107370 | 7764 | FE-246
SITE-01279 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Data Center | Excitel Enterprise | 2024-10-10 | 2024-10-26 | 16 | Go-Live | Live - Operational | Breached | 6 | 103499 | 11596 | FE-423
SITE-01280 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | ATM/Off-site | Tata Communications | 2024-09-23 |  | 644 | Site Survey | Survey Scheduled | Breached | 50 | 62521 | 16042 | FE-383
SITE-01281 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Data Center | Tata Communications | 2024-10-22 | 2024-10-14 | -8 | Go-Live | Live - Operational | Met | 6 | 37570 | 5668 | FE-363
SITE-01282 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-12-19 |  | 557 | Site Survey | Survey Scheduled | Breached | 10 | 121321 | 8306 | FE-160
SITE-01283 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-02-22 |  | 492 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 37666 | 15603 | FE-281
SITE-01284 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Data Center | Sify Technologies | 2025-01-13 |  | 532 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 119765 | 5705 | FE-475
SITE-01285 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-05-07 | 2025-04-27 | -10 | Go-Live | Live - Operational | Met | 34 | 116330 | 14139 | FE-332
SITE-01286 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2024-11-04 |  | 602 | Site Survey | Survey Scheduled | Breached | 20 | 129319 | 5087 | FE-218
SITE-01287 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-10-02 | 2024-10-15 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 65389 | 8788 | FE-296
SITE-01288 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Data Center | Excitel Enterprise | 2024-09-30 | 2024-10-03 | 3 | Go-Live | Live - Operational | Met | 20 | 103384 | 17911 | FE-415
SITE-01289 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Branch | Sify Technologies | 2024-12-01 | 2024-12-01 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 91784 | 10691 | FE-214
SITE-01290 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | ATM/Off-site | Local ISP Partner | 2025-02-22 | 2025-02-18 | -4 | Go-Live | Live - Operational | Met | 20 | 46481 | 5072 | FE-205
SITE-01291 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-09-27 | 2024-09-19 | -8 | Go-Live | Live - Operational | Met | 10 | 28873 | 11501 | FE-113
SITE-01292 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Data Center | Excitel Enterprise | 2025-02-13 | 2025-02-21 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 87486 | 8332 | FE-156
SITE-01293 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Corporate Office | Tata Communications | 2025-01-24 |  | 521 | Site Survey | Survey Scheduled | Breached | 6 | 64497 | 15487 | FE-442
SITE-01294 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Branch | Sify Technologies | 2025-03-29 | 2025-04-02 | 4 | Go-Live | Live - Operational | Met | 6 | 94461 | 8994 | FE-241
SITE-01295 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Branch | Local ISP Partner | 2025-01-29 |  | 516 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 33027 | 10600 | FE-151
SITE-01296 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Branch | Local ISP Partner | 2025-04-23 | 2025-05-18 | 25 | Go-Live | Live - Operational | Breached | 2 | 60232 | 5742 | FE-400
SITE-01297 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Corporate Office | Vodafone Idea Business | 2024-11-09 |  | 597 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 91505 | 16834 | FE-195
SITE-01298 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2024-11-09 | 2024-11-04 | -5 | Go-Live | Live - Operational | Met | 10 | 28419 | 10615 | FE-134
SITE-01299 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | ATM/Off-site | Tata Communications | 2024-11-12 |  | 594 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 118175 | 7810 | FE-414
SITE-01300 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Corporate Office | Vodafone Idea Business | 2024-11-19 |  | 587 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 67334 | 17273 | FE-218
SITE-01301 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Data Center | Excitel Enterprise | 2025-04-11 |  | 444 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 99226 | 11380 | FE-251
SITE-01302 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Data Center | Vodafone Idea Business | 2025-05-03 | 2025-05-11 | 8 | Go-Live | Live - Operational | Breached | 34 | 60426 | 14353 | FE-317
SITE-01303 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Branch | Sify Technologies | 2024-12-10 |  | 566 | Site Survey | Survey Scheduled | Breached | 50 | 120382 | 5598 | FE-496
SITE-01304 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | ATM/Off-site | Tata Communications | 2025-01-03 |  | 542 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 63117 | 11814 | FE-210
SITE-01305 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Corporate Office | Sify Technologies | 2025-04-05 |  | 450 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 81900 | 9912 | FE-326
SITE-01306 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Corporate Office | Vodafone Idea Business | 2025-05-11 | 2025-05-04 | -7 | Go-Live | Live - Operational | Met | 10 | 72543 | 13924 | FE-123
SITE-01307 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Airtel Business | 2024-11-15 |  | 591 | Site Survey | Survey Complete | Breached | 10 | 130177 | 13744 | FE-156
SITE-01308 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Tata Communications | 2024-10-23 | 2024-11-06 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 133173 | 9712 | FE-146
SITE-01309 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Excitel Enterprise | 2024-10-06 |  | 631 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 75460 | 12273 | FE-201
SITE-01310 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Airtel Business | 2024-11-17 |  | 589 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 71450 | 10273 | FE-210
SITE-01311 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Branch | Excitel Enterprise | 2024-09-23 | 2024-09-15 | -8 | Go-Live | Live - Operational | Met | 4 | 93732 | 10019 | FE-348
SITE-01312 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | ATM/Off-site | Local ISP Partner | 2024-12-06 | 2024-12-01 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 32427 | 7963 | FE-483
SITE-01313 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | ATM/Off-site | Local ISP Partner | 2024-12-31 |  | 545 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 39130 | 4753 | FE-137
SITE-01314 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Tata Communications | 2025-04-03 |  | 452 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 125340 | 17102 | FE-377
SITE-01315 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | ATM/Off-site | Excitel Enterprise | 2025-03-27 | 2025-04-11 | 15 | Go-Live | Live - Operational | Breached | 20 | 130861 | 8803 | FE-317
SITE-01316 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Airtel Business | 2024-12-06 | 2024-12-13 | 7 | Go-Live | Live - Operational | Breached | 4 | 62638 | 14248 | FE-395
SITE-01317 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-01-07 | 2025-01-04 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 91353 | 8159 | FE-459
SITE-01318 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Local ISP Partner | 2024-12-26 | 2024-12-17 | -9 | Go-Live | Live - Operational | Met | 50 | 76855 | 15996 | FE-379
SITE-01319 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Data Center | Airtel Business | 2025-02-14 | 2025-02-05 | -9 | Go-Live | Live - Operational | Met | 100 | 76473 | 11311 | FE-388
SITE-01320 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Branch | Tata Communications | 2024-12-14 | 2024-12-13 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 55221 | 17669 | FE-350
SITE-01321 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-26 | 2024-11-10 | 15 | Go-Live | Live - Operational | Breached | 10 | 35724 | 16073 | FE-352
SITE-01322 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | ATM/Off-site | Tata Communications | 2025-03-28 | 2025-04-02 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 118308 | 12762 | FE-406
SITE-01323 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-15 | 2025-03-18 | 3 | Go-Live | Live - Operational | Met | 100 | 69027 | 14182 | FE-220
SITE-01324 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-01-21 |  | 524 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 41768 | 10474 | FE-458
SITE-01325 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | ATM/Off-site | Excitel Enterprise | 2025-04-01 | 2025-03-22 | -10 | Go-Live | Live - Operational | Met | 4 | 49783 | 6733 | FE-324
SITE-01326 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | ATM/Off-site | Local ISP Partner | 2025-01-24 |  | 521 | Site Survey | Survey Scheduled | Breached | 100 | 46332 | 15771 | FE-380
SITE-01327 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Data Center | Sify Technologies | 2024-12-04 | 2024-12-01 | -3 | Go-Live | Live - Operational | Met | 20 | 96482 | 8781 | FE-414
SITE-01328 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Excitel Enterprise | 2024-12-03 | 2024-12-26 | 23 | Go-Live | Live - Operational | Breached | 34 | 96076 | 13404 | FE-228
SITE-01329 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | ATM/Off-site | Excitel Enterprise | 2024-12-13 | 2024-12-11 | -2 | Go-Live | Live - Operational | Met | 100 | 29287 | 8705 | FE-313
SITE-01330 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Branch | Sify Technologies | 2024-10-07 |  | 630 | Site Survey | Survey Scheduled | Breached | 10 | 54118 | 14871 | FE-148
SITE-01331 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-10-14 | 2024-10-10 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 36751 | 9241 | FE-425
SITE-01332 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | ATM/Off-site | Sify Technologies | 2025-02-27 | 2025-02-22 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 83858 | 13075 | FE-473
SITE-01333 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Data Center | Sify Technologies | 2025-04-04 |  | 451 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 38154 | 13209 | FE-178
SITE-01334 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Corporate Office | Excitel Enterprise | 2024-11-30 | 2024-12-01 | 1 | Go-Live | Live - Operational | Met | 4 | 44607 | 16556 | FE-367
SITE-01335 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-12-13 |  | 563 | Site Survey | Survey Complete | Breached | 20 | 133814 | 15579 | FE-415
SITE-01336 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | ATM/Off-site | Tata Communications | 2024-09-20 | 2024-09-24 | 4 | Go-Live | Live - Operational | Met | 6 | 46786 | 6200 | FE-343
SITE-01337 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | ATM/Off-site | Excitel Enterprise | 2025-05-07 | 2025-04-30 | -7 | Go-Live | Live - Operational | Met | 100 | 83758 | 14392 | FE-341
SITE-01338 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Airtel Business | 2025-04-02 |  | 453 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 77454 | 16179 | FE-297
SITE-01339 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Corporate Office | Excitel Enterprise | 2025-04-22 | 2025-05-03 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 107348 | 17298 | FE-209
SITE-01340 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Data Center | Excitel Enterprise | 2024-10-26 |  | 611 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 92237 | 14888 | FE-228
SITE-01341 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Corporate Office | Airtel Business | 2025-03-05 |  | 481 | Site Survey | Survey Scheduled | Breached | 2 | 75931 | 17514 | FE-338
SITE-01342 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-02-24 | 2025-03-21 | 25 | Go-Live | Live - Operational | Breached | 34 | 51462 | 15749 | FE-105
SITE-01343 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | ATM/Off-site | Tata Communications | 2025-02-01 |  | 513 | Site Survey | Survey Complete | Breached | 20 | 71050 | 5041 | FE-288
SITE-01344 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Branch | Local ISP Partner | 2024-11-28 |  | 578 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 112105 | 11343 | FE-303
SITE-01345 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Corporate Office | Local ISP Partner | 2024-11-23 |  | 583 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 102996 | 16989 | FE-115
SITE-01346 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Data Center | Airtel Business | 2025-01-14 |  | 531 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 126295 | 17834 | FE-431
SITE-01347 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2024-12-23 | 2024-12-14 | -9 | Go-Live | Live - Operational | Met | 6 | 120489 | 15561 | FE-190
SITE-01348 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | Branch | Tata Communications | 2025-04-21 |  | 434 | Site Survey | Survey Scheduled | Breached | 100 | 111555 | 15142 | FE-131
SITE-01349 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Local ISP Partner | 2024-11-30 |  | 576 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 71603 | 17217 | FE-444
SITE-01350 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Corporate Office | Excitel Enterprise | 2025-03-23 |  | 463 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 115096 | 10105 | FE-313
SITE-01351 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | ATM/Off-site | Local ISP Partner | 2025-04-19 | 2025-05-11 | 22 | Go-Live | Live - Operational | Breached | 20 | 39005 | 6327 | FE-327
SITE-01352 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-11-09 |  | 597 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 111270 | 15736 | FE-101
SITE-01353 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Sify Technologies | 2024-12-18 |  | 558 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 102471 | 17198 | FE-456
SITE-01354 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Branch | Tata Communications | 2024-10-12 |  | 625 | Site Survey | Survey Scheduled | Breached | 6 | 123623 | 4915 | FE-195
SITE-01355 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Local ISP Partner | 2025-04-09 | 2025-03-30 | -10 | Go-Live | Live - Operational | Met | 34 | 88338 | 4831 | FE-470
SITE-01356 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | ATM/Off-site | Local ISP Partner | 2025-03-03 |  | 483 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 68696 | 4373 | FE-294
SITE-01357 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Corporate Office | Vodafone Idea Business | 2024-10-25 | 2024-11-07 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 52673 | 7969 | FE-202
SITE-01358 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Corporate Office | Tata Communications | 2025-03-17 | 2025-04-04 | 18 | Go-Live | Live - Operational | Breached | 100 | 74550 | 12981 | FE-286
SITE-01359 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | ATM/Off-site | Tata Communications | 2025-03-14 |  | 472 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 48408 | 12313 | FE-391
SITE-01360 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Airtel Business | 2025-03-04 | 2025-03-24 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 119705 | 11753 | FE-382
SITE-01361 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Sify Technologies | 2025-04-05 |  | 450 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 89300 | 7773 | FE-116
SITE-01362 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-02-28 |  | 486 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 89242 | 13114 | FE-265
SITE-01363 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Sify Technologies | 2025-02-17 |  | 497 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 110506 | 9379 | FE-104
SITE-01364 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Local ISP Partner | 2024-12-14 |  | 562 | Site Survey | Survey Scheduled | Breached | 4 | 52525 | 9365 | FE-256
SITE-01365 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Branch | Vodafone Idea Business | 2024-11-06 |  | 600 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 105801 | 12936 | FE-455
SITE-01366 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | ATM/Off-site | Sify Technologies | 2025-01-19 |  | 526 | Site Survey | Survey Complete | Breached | 34 | 106766 | 9035 | FE-347
SITE-01367 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-05-02 | 2025-05-06 | 4 | Go-Live | Live - Operational | Met | 50 | 83822 | 16182 | FE-237
SITE-01368 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | ATM/Off-site | Excitel Enterprise | 2024-09-27 |  | 640 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 67397 | 13278 | FE-457
SITE-01369 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | ATM/Off-site | Airtel Business | 2025-03-31 |  | 455 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 131359 | 4381 | FE-146
SITE-01370 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-01-15 | 2025-01-22 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 114325 | 5916 | FE-202
SITE-01371 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | ATM/Off-site | Airtel Business | 2024-10-10 | 2024-10-10 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 39818 | 15364 | FE-225
SITE-01372 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Corporate Office | Tata Communications | 2025-01-20 | 2025-01-20 | 0 | Go-Live | Live - Operational | Met | 100 | 100067 | 14752 | FE-301
SITE-01373 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Data Center | Local ISP Partner | 2024-12-25 |  | 551 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 128015 | 5069 | FE-298
SITE-01374 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Corporate Office | Local ISP Partner | 2024-12-31 | 2025-01-10 | 10 | Go-Live | Live - Operational | Breached | 50 | 106241 | 9952 | FE-373
SITE-01375 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-03-10 |  | 476 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 107760 | 6418 | FE-493
SITE-01376 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Warehouse/Ops Hub | Tata Communications | 2024-12-16 |  | 560 | Site Survey | Survey Complete | Breached | 50 | 38127 | 14077 | FE-217
SITE-01377 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Vodafone Idea Business | 2024-10-01 | 2024-10-04 | 3 | Go-Live | Live - Operational | Met | 4 | 72510 | 9792 | FE-434
SITE-01378 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Data Center | Local ISP Partner | 2024-12-01 | 2024-12-10 | 9 | Go-Live | Live - Operational | Breached | 100 | 32564 | 7776 | FE-315
SITE-01379 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-03-13 |  | 473 | Site Survey | Survey Complete | Breached | 100 | 133674 | 4853 | FE-277
SITE-01380 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Branch | Airtel Business | 2025-04-13 |  | 442 | Site Survey | Survey Complete | Breached | 34 | 44874 | 12915 | FE-359
SITE-01381 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Data Center | Local ISP Partner | 2024-09-22 |  | 645 | Site Survey | Survey Scheduled | Breached | 50 | 83372 | 16137 | FE-127
SITE-01382 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-28 | 2025-03-25 | -3 | Go-Live | Live - Operational | Met | 34 | 130367 | 11258 | FE-464
SITE-01383 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Data Center | Excitel Enterprise | 2025-04-09 | 2025-04-10 | 1 | Go-Live | Live - Operational | Met | 50 | 116436 | 4810 | FE-176
SITE-01384 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Corporate Office | Airtel Business | 2025-02-18 |  | 496 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 85001 | 4295 | FE-337
SITE-01385 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Data Center | Sify Technologies | 2025-04-30 | 2025-05-21 | 21 | Go-Live | Live - Operational | Breached | 2 | 106555 | 14745 | FE-289
SITE-01386 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Excitel Enterprise | 2025-03-11 | 2025-03-15 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 51426 | 8304 | FE-282
SITE-01387 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Corporate Office | Local ISP Partner | 2024-12-12 |  | 564 | Site Survey | Survey Scheduled | Breached | 2 | 106089 | 5329 | FE-282
SITE-01388 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | ATM/Off-site | Airtel Business | 2024-12-30 |  | 546 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 98121 | 5049 | FE-164
SITE-01389 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Sify Technologies | 2025-05-06 |  | 419 | Site Survey | Survey Scheduled | Breached | 100 | 118307 | 13612 | FE-224
SITE-01390 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Branch | Sify Technologies | 2024-09-30 |  | 637 | Site Survey | Survey Scheduled | Breached | 34 | 33018 | 5904 | FE-411
SITE-01391 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Branch | Sify Technologies | 2025-03-24 |  | 462 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 83381 | 10065 | FE-111
SITE-01392 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Branch | Vodafone Idea Business | 2025-03-06 |  | 480 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 132024 | 6639 | FE-392
SITE-01393 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-01-29 |  | 516 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 77051 | 12893 | FE-342
SITE-01394 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | ATM/Off-site | Sify Technologies | 2025-03-30 | 2025-04-16 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 107249 | 10031 | FE-192
SITE-01395 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Vodafone Idea Business | 2025-01-02 | 2025-01-05 | 3 | Go-Live | Live - Operational | Met | 6 | 64014 | 7875 | FE-336
SITE-01396 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | ATM/Off-site | Tata Communications | 2024-10-14 | 2024-10-16 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 56974 | 4544 | FE-413
SITE-01397 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-01-05 |  | 540 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 90338 | 12636 | FE-106
SITE-01398 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-12-17 | 2024-12-26 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 55608 | 12220 | FE-457
SITE-01399 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-01-01 | 2024-12-24 | -8 | Go-Live | Live - Operational | Met | 100 | 101574 | 9157 | FE-142
SITE-01400 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Corporate Office | Vodafone Idea Business | 2024-12-03 | 2024-12-22 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 31875 | 6054 | FE-419
SITE-01401 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-19 |  | 557 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 128262 | 3883 | FE-484
SITE-01402 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-12-25 | 2025-01-18 | 24 | Go-Live | Live - Operational | Breached | 4 | 40711 | 9983 | FE-211
SITE-01403 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | ATM/Off-site | Airtel Business | 2024-12-03 |  | 573 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 100098 | 10193 | FE-280
SITE-01404 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Corporate Office | Sify Technologies | 2024-11-30 |  | 576 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 115062 | 17995 | FE-451
SITE-01405 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Data Center | Vodafone Idea Business | 2025-04-27 | 2025-05-12 | 15 | Go-Live | Live - Operational | Breached | 20 | 86911 | 6071 | FE-190
SITE-01406 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Data Center | Local ISP Partner | 2025-02-03 | 2025-02-14 | 11 | Go-Live | Live - Operational | Breached | 6 | 117568 | 5110 | FE-296
SITE-01407 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Airtel Business | 2025-01-05 |  | 540 | Site Survey | Survey Scheduled | Breached | 2 | 109117 | 7173 | FE-170
SITE-01408 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-10-10 |  | 627 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 30992 | 8825 | FE-412
SITE-01409 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Data Center | Local ISP Partner | 2025-02-27 |  | 487 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 76535 | 3872 | FE-480
SITE-01410 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-02-08 |  | 506 | Site Survey | Survey Complete | Breached | 6 | 88000 | 9546 | FE-470
SITE-01411 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | ATM/Off-site | Sify Technologies | 2025-03-21 |  | 465 | Site Survey | Survey Scheduled | Breached | 6 | 66401 | 4561 | FE-115
SITE-01412 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-11-21 |  | 585 | Site Survey | Survey Scheduled | Breached | 10 | 132432 | 6397 | FE-336
SITE-01413 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | ATM/Off-site | Airtel Business | 2025-04-13 | 2025-04-24 | 11 | Go-Live | Live - Operational | Breached | 100 | 122640 | 4644 | FE-103
SITE-01414 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-01-02 |  | 543 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 37222 | 16329 | FE-313
SITE-01415 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-04-06 |  | 449 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 85477 | 11377 | FE-471
SITE-01416 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Branch | Sify Technologies | 2025-04-20 |  | 435 | Site Survey | Survey Complete | Breached | 50 | 121929 | 11881 | FE-422
SITE-01417 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Corporate Office | Excitel Enterprise | 2024-10-16 | 2024-10-15 | -1 | Go-Live | Live - Operational | Met | 4 | 122633 | 6268 | FE-287
SITE-01418 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Data Center | Airtel Business | 2024-10-26 | 2024-10-28 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 40730 | 8907 | FE-428
SITE-01419 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | ATM/Off-site | Sify Technologies | 2025-01-23 |  | 522 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 66704 | 14791 | FE-327
SITE-01420 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Corporate Office | Excitel Enterprise | 2024-11-25 |  |  | ROW / Permission | Cancelled | N/A | 2 | 127788 | 5794 | FE-175
SITE-01421 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Warehouse/Ops Hub | Sify Technologies | 2024-11-15 | 2024-11-28 | 13 | Go-Live | Live - Operational | Breached | 20 | 68194 | 15228 | FE-181
SITE-01422 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Local ISP Partner | 2025-01-19 | 2025-02-05 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 48242 | 15685 | FE-455
SITE-01423 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Data Center | Sify Technologies | 2024-12-03 |  | 573 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 31670 | 17441 | FE-208
SITE-01424 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Corporate Office | Sify Technologies | 2025-02-16 | 2025-02-06 | -10 | Go-Live | Live - Operational | Met | 50 | 90517 | 13632 | FE-187
SITE-01425 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-04-26 |  | 429 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 77542 | 17678 | FE-348
SITE-01426 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Branch | Local ISP Partner | 2025-01-21 | 2025-02-04 | 14 | Go-Live | Live - Operational | Breached | 4 | 72874 | 7183 | FE-258
SITE-01427 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | ATM/Off-site | Sify Technologies | 2024-11-30 | 2024-11-27 | -3 | Go-Live | Live - Operational | Met | 100 | 88204 | 12829 | FE-426
SITE-01428 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | ATM/Off-site | Local ISP Partner | 2025-05-07 |  | 418 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 75652 | 14382 | FE-116
SITE-01429 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Guntur | MPLS | Branch | Sify Technologies | 2024-12-13 | 2025-01-04 | 22 | Go-Live | Live - Operational | Breached | 4 | 132584 | 4417 | FE-328
SITE-01430 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | ATM/Off-site | Local ISP Partner | 2024-11-21 | 2024-11-27 | 6 | Go-Live | Live - Operational | Breached | 10 | 57928 | 14799 | FE-467
SITE-01431 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-02-22 | 2025-03-01 | 7 | Go-Live | Live - Operational | Breached | 4 | 125400 | 6613 | FE-475
SITE-01432 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Branch | Airtel Business | 2024-12-06 |  | 570 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 59973 | 13095 | FE-489
SITE-01433 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Warehouse/Ops Hub | Tata Communications | 2024-10-15 |  | 622 | Site Survey | Survey Scheduled | Breached | 34 | 131548 | 13885 | FE-137
SITE-01434 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Data Center | Airtel Business | 2025-01-11 | 2025-01-06 | -5 | Go-Live | Live - Operational | Met | 4 | 99089 | 13156 | FE-210
SITE-01435 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-12 | 2025-02-07 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 122369 | 10752 | FE-498
SITE-01436 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Warehouse/Ops Hub | Sify Technologies | 2024-11-23 | 2024-12-09 | 16 | Go-Live | Live - Operational | Breached | 100 | 110723 | 6392 | FE-268
SITE-01437 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Corporate Office | Sify Technologies | 2024-12-01 |  | 575 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 72714 | 8010 | FE-447
SITE-01438 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Branch | Airtel Business | 2025-02-27 | 2025-03-08 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 28854 | 8729 | FE-360
SITE-01439 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Data Center | Local ISP Partner | 2024-11-04 | 2024-10-29 | -6 | Go-Live | Live - Operational | Met | 20 | 40395 | 17623 | FE-326
SITE-01440 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Airtel Business | 2025-04-07 | 2025-04-03 | -4 | Go-Live | Live - Operational | Met | 20 | 93769 | 8503 | FE-263
SITE-01441 | PRJ-2024015 | CL008 | South | Kerala | Thiruvananthapuram | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-03-14 | 2025-03-23 | 9 | Go-Live | Live - Operational | Breached | 6 | 70436 | 6062 | FE-198
SITE-01442 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Corporate Office | Excitel Enterprise | 2025-02-23 | 2025-02-23 | 0 | Go-Live | Live - Operational | Met | 100 | 113654 | 13252 | FE-313
SITE-01443 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Corporate Office | Airtel Business | 2025-01-18 | 2025-01-27 | 9 | Go-Live | Live - Operational | Breached | 20 | 71741 | 15406 | FE-281
SITE-01444 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Data Center | Vodafone Idea Business | 2025-01-06 | 2025-01-19 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 127906 | 10120 | FE-128
SITE-01445 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-04-14 |  | 441 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 30553 | 16910 | FE-460
SITE-01446 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Corporate Office | Sify Technologies | 2025-03-22 |  | 464 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 31103 | 8773 | FE-318
SITE-01447 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | ATM/Off-site | Airtel Business | 2025-02-10 |  | 504 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 63908 | 5250 | FE-138
SITE-01448 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-24 | 2025-04-03 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 130397 | 14303 | FE-299
SITE-01449 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Data Center | Tata Communications | 2025-02-22 | 2025-03-07 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 35355 | 13979 | FE-275
SITE-01450 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Vodafone Idea Business | 2024-12-01 |  | 575 | Site Survey | Survey Scheduled | Breached | 6 | 126281 | 4712 | FE-266
SITE-01451 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-02-17 | 2025-02-26 | 9 | Go-Live | Live - Operational | Breached | 4 | 85443 | 7517 | FE-267
SITE-01452 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2024-11-25 |  | 581 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 118383 | 3858 | FE-171
SITE-01453 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Corporate Office | Sify Technologies | 2025-03-28 |  | 458 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 125946 | 17993 | FE-209
SITE-01454 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Data Center | Sify Technologies | 2024-11-17 |  | 589 | Site Survey | Survey Scheduled | Breached | 34 | 54081 | 14602 | FE-460
SITE-01455 | PRJ-2024015 | CL008 | South | Telangana | Warangal | MPLS | Branch | Airtel Business | 2025-03-30 |  | 456 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 112179 | 10230 | FE-318
SITE-01456 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Visakhapatnam | MPLS | Branch | Excitel Enterprise | 2025-04-20 | 2025-05-13 | 23 | Go-Live | Live - Operational | Breached | 34 | 30123 | 12768 | FE-323
SITE-01457 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Data Center | Sify Technologies | 2025-04-10 | 2025-04-22 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 111148 | 4599 | FE-476
SITE-01458 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-02-09 | 2025-02-06 | -3 | Go-Live | Live - Operational | Met | 4 | 103225 | 11175 | FE-412
SITE-01459 | PRJ-2024015 | CL008 | South | Tamil Nadu | Chennai | MPLS | Corporate Office | Vodafone Idea Business | 2025-01-08 |  | 537 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 124853 | 5993 | FE-433
SITE-01460 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Data Center | Excitel Enterprise | 2025-03-04 | 2025-03-15 | 11 | Go-Live | Live - Operational | Breached | 50 | 30815 | 10077 | FE-394
SITE-01461 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | Data Center | Tata Communications | 2025-04-20 |  | 435 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 57521 | 8781 | FE-318
SITE-01462 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-16 | 2025-02-26 | 10 | Go-Live | Live - Operational | Breached | 10 | 128915 | 16959 | FE-394
SITE-01463 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Sify Technologies | 2025-04-05 | 2025-04-04 | -1 | Go-Live | Live - Operational | Met | 6 | 41224 | 3929 | FE-373
SITE-01464 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Branch | Sify Technologies | 2025-02-05 | 2025-02-17 | 12 | Go-Live | Live - Operational | Breached | 34 | 58160 | 14283 | FE-206
SITE-01465 | PRJ-2024015 | CL008 | South | Tamil Nadu | Madurai | MPLS | ATM/Off-site | Airtel Business | 2025-01-06 | 2025-01-13 | 7 | Go-Live | Live - Operational | Breached | 34 | 31577 | 5749 | FE-325
SITE-01466 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Data Center | Tata Communications | 2025-01-11 | 2025-01-14 | 3 | Go-Live | Live - Operational | Met | 100 | 85481 | 10040 | FE-201
SITE-01467 | PRJ-2024015 | CL008 | South | Tamil Nadu | Trichy | MPLS | Branch | Tata Communications | 2025-04-16 |  | 439 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 94414 | 12974 | FE-470
SITE-01468 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Branch | Vodafone Idea Business | 2025-04-01 | 2025-04-04 | 3 | Go-Live | Live - Operational | Met | 34 | 126262 | 8691 | FE-312
SITE-01469 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Corporate Office | Vodafone Idea Business | 2025-04-12 | 2025-05-04 | 22 | Go-Live | Live - Operational | Breached | 20 | 94680 | 5334 | FE-333
SITE-01470 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | Data Center | Vodafone Idea Business | 2025-04-13 |  | 442 | Site Survey | Survey Complete | Breached | 4 | 74488 | 9404 | FE-258
SITE-01471 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | ATM/Off-site | Local ISP Partner | 2024-12-05 |  | 571 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 113253 | 14044 | FE-299
SITE-01472 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Corporate Office | Tata Communications | 2025-03-25 | 2025-04-09 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 60636 | 6405 | FE-389
SITE-01473 | PRJ-2024015 | CL008 | South | Karnataka | Bengaluru | MPLS | ATM/Off-site | Local ISP Partner | 2024-10-29 |  | 608 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 127914 | 4138 | FE-131
SITE-01474 | PRJ-2024015 | CL008 | South | Kerala | Kochi | MPLS | Corporate Office | Sify Technologies | 2025-03-08 |  | 478 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 48641 | 10368 | FE-188
SITE-01475 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | ATM/Off-site | Sify Technologies | 2025-04-15 |  | 440 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 131095 | 6160 | FE-115
SITE-01476 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Corporate Office | Sify Technologies | 2025-01-01 | 2025-01-16 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 31732 | 16333 | FE-113
SITE-01477 | PRJ-2024015 | CL008 | South | Telangana | Hyderabad | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-09-28 |  | 639 | Site Survey | Survey Scheduled | Breached | 2 | 98710 | 9677 | FE-490
SITE-01478 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | ATM/Off-site | Tata Communications | 2024-11-02 |  | 604 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 73700 | 7148 | FE-147
SITE-01479 | PRJ-2024015 | CL008 | South | Andhra Pradesh | Vijayawada | MPLS | Data Center | Excitel Enterprise | 2025-01-19 | 2025-02-07 | 19 | Go-Live | Live - Operational | Breached | 100 | 45616 | 17539 | FE-408
SITE-01480 | PRJ-2024015 | CL008 | South | Karnataka | Mysuru | MPLS | Corporate Office | Airtel Business | 2025-01-18 |  | 527 | Site Survey | Survey Scheduled | Breached | 34 | 114032 | 12347 | FE-287
SITE-01481 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Data Center | Vodafone Idea Business | 2024-10-14 |  | 623 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 44493 | 7093 | FE-363
SITE-01482 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Branch | Local ISP Partner | 2025-03-07 | 2025-03-02 | -5 | Go-Live | Live - Operational | Met | 50 | 65001 | 13576 | FE-153
SITE-01483 | PRJ-2024015 | CL008 | South | Tamil Nadu | Coimbatore | MPLS | Corporate Office | Local ISP Partner | 2024-11-06 | 2024-11-15 | 9 | Go-Live | Live - Operational | Breached | 100 | 115602 | 13179 | FE-366
SITE-01484 | PRJ-2024015 | CL008 | South | Kerala | Kozhikode | MPLS | Corporate Office | Vodafone Idea Business | 2025-04-02 | 2025-03-31 | -2 | Go-Live | Live - Operational | Met | 34 | 114665 | 5879 | FE-396
SITE-01485 | PRJ-2024015 | CL008 | South | Karnataka | Hubli | MPLS | Branch | Airtel Business | 2025-02-28 |  | 486 | Site Survey | Survey Complete | Breached | 6 | 29877 | 5842 | FE-424
SITE-01486 | PRJ-2024016 | CL007 | South | Karnataka | Bengaluru | Leased Line | Branch | Excitel Enterprise | 2025-01-16 | 2025-01-26 | 10 | Go-Live | Live - Operational | Breached | 100 | 91418 | 17552 | FE-276
SITE-01487 | PRJ-2024016 | CL007 | South | Tamil Nadu | Trichy | Leased Line | Data Center | Excitel Enterprise | 2024-11-30 |  | 576 | Site Survey | Survey Scheduled | Breached | 20 | 99549 | 10706 | FE-160
SITE-01488 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Corporate Office | Sify Technologies | 2025-05-23 | 2025-05-23 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 129188 | 12493 | FE-333
SITE-01489 | PRJ-2024016 | CL007 | South | Karnataka | Hubli | Leased Line | Corporate Office | Tata Communications | 2025-04-20 | 2025-05-01 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 83904 | 14023 | FE-113
SITE-01490 | PRJ-2024016 | CL007 | South | Kerala | Kochi | Leased Line | Branch | Tata Communications | 2024-12-04 | 2024-12-23 | 19 | Go-Live | Live - Operational | Breached | 20 | 44554 | 17808 | FE-277
SITE-01491 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Branch | Excitel Enterprise | 2025-02-25 |  | 489 | Site Survey | Survey Scheduled | Breached | 6 | 80108 | 16935 | FE-361
SITE-01492 | PRJ-2024016 | CL007 | South | Tamil Nadu | Coimbatore | Leased Line | Branch | Airtel Business | 2024-12-02 |  | 574 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 96888 | 13345 | FE-499
SITE-01493 | PRJ-2024016 | CL007 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-01-07 |  | 538 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 77082 | 6100 | FE-151
SITE-01494 | PRJ-2024016 | CL007 | South | Tamil Nadu | Coimbatore | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2024-11-14 |  | 592 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 54502 | 8061 | FE-125
SITE-01495 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-25 |  | 400 | Site Survey | Survey Complete | Breached | 100 | 89342 | 8774 | FE-169
SITE-01496 | PRJ-2024016 | CL007 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Airtel Business | 2024-12-10 | 2025-01-04 | 25 | Go-Live | Live - Operational | Breached | 4 | 35762 | 15872 | FE-310
SITE-01497 | PRJ-2024016 | CL007 | South | Tamil Nadu | Coimbatore | Leased Line | ATM/Off-site | Airtel Business | 2025-05-05 |  | 420 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 131063 | 6112 | FE-430
SITE-01498 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Sify Technologies | 2024-11-25 |  | 581 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 57662 | 8025 | FE-171
SITE-01499 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-04-14 |  | 441 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 54978 | 10764 | FE-172
SITE-01500 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-03-19 | 2025-03-16 | -3 | Go-Live | Live - Operational | Met | 4 | 129142 | 13798 | FE-406
SITE-01501 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Vijayawada | Leased Line | Corporate Office | Tata Communications | 2025-01-27 |  | 518 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 48142 | 4653 | FE-486
SITE-01502 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Branch | Local ISP Partner | 2025-01-12 | 2025-01-18 | 6 | Go-Live | Live - Operational | Breached | 100 | 83824 | 13084 | FE-186
SITE-01503 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Branch | Local ISP Partner | 2025-02-17 | 2025-02-13 | -4 | Go-Live | Live - Operational | Met | 34 | 59626 | 17743 | FE-440
SITE-01504 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Guntur | Leased Line | Branch | Local ISP Partner | 2025-01-22 |  | 523 | Site Survey | Survey Scheduled | Breached | 4 | 128918 | 8090 | FE-470
SITE-01505 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Corporate Office | Vodafone Idea Business | 2025-02-14 |  | 500 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 74748 | 4861 | FE-106
SITE-01506 | PRJ-2024016 | CL007 | South | Karnataka | Hubli | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-08 |  | 568 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 105474 | 10606 | FE-440
SITE-01507 | PRJ-2024016 | CL007 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-08 |  | 506 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 107511 | 12002 | FE-441
SITE-01508 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2024-11-03 |  | 603 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 103448 | 5055 | FE-160
SITE-01509 | PRJ-2024016 | CL007 | South | Tamil Nadu | Madurai | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-28 |  | 458 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 122147 | 15694 | FE-120
SITE-01510 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-03-02 |  | 484 | Site Survey | Survey Scheduled | Breached | 50 | 134582 | 16692 | FE-421
SITE-01511 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Guntur | Leased Line | Branch | Local ISP Partner | 2024-12-01 | 2024-12-02 | 1 | Go-Live | Live - Operational | Met | 34 | 40950 | 8288 | FE-311
SITE-01512 | PRJ-2024016 | CL007 | South | Karnataka | Hubli | Leased Line | Corporate Office | Sify Technologies | 2025-05-12 |  | 413 | Site Survey | Survey Scheduled | Breached | 34 | 74186 | 7574 | FE-241
SITE-01513 | PRJ-2024016 | CL007 | South | Andhra Pradesh | Vijayawada | Leased Line | Corporate Office | Airtel Business | 2025-02-01 | 2025-02-18 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 101200 | 16128 | FE-380
SITE-01514 | PRJ-2024016 | CL007 | South | Telangana | Warangal | Leased Line | Data Center | Tata Communications | 2025-04-24 | 2025-04-24 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 74111 | 13599 | FE-375
SITE-01515 | PRJ-2024016 | CL007 | South | Tamil Nadu | Madurai | Leased Line | Branch | Local ISP Partner | 2024-11-01 | 2024-11-19 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 69015 | 13687 | FE-354
SITE-01516 | PRJ-2024017 | CL004 | Central | Chhattisgarh | Bilaspur | SD-WAN | Corporate Office | Sify Technologies | 2024-10-04 | 2024-10-25 | 21 | Go-Live | Live - Operational | Breached | 100 | 75377 | 15866 | FE-181
SITE-01517 | PRJ-2024017 | CL004 | Central | Chhattisgarh | Bilaspur | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2024-08-26 | 2024-08-28 | 2 | Go-Live | Live - Operational | Met | 20 | 127191 | 12673 | FE-375
SITE-01518 | PRJ-2024017 | CL004 | Central | Chhattisgarh | Bilaspur | SD-WAN | Branch | Airtel Business | 2025-01-23 |  | 522 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 39867 | 15159 | FE-406
SITE-01519 | PRJ-2024017 | CL004 | Central | Madhya Pradesh | Jabalpur | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-01-28 | 2025-02-08 | 11 | Go-Live | Live - Operational | Breached | 50 | 45436 | 9811 | FE-153
SITE-01520 | PRJ-2024017 | CL004 | Central | Madhya Pradesh | Bhopal | SD-WAN | Branch | Airtel Business | 2024-09-24 | 2024-10-03 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 115493 | 7985 | FE-113
SITE-01521 | PRJ-2024018 | CL004 | Central | Madhya Pradesh | Indore | Leased Line | ATM/Off-site | Vodafone Idea Business | 2024-10-19 |  |  | Site Survey | Cancelled | N/A | 10 | 47054 | 3703 | FE-251
SITE-01522 | PRJ-2024018 | CL004 | Central | Chhattisgarh | Raipur | Leased Line | Data Center | Vodafone Idea Business | 2024-12-25 |  | 551 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 82044 | 6548 | FE-365
SITE-01523 | PRJ-2024018 | CL004 | Central | Madhya Pradesh | Gwalior | Leased Line | Corporate Office | Vodafone Idea Business | 2025-02-20 | 2025-03-05 | 13 | Go-Live | Live - Operational | Breached | 34 | 75777 | 7345 | FE-263
SITE-01524 | PRJ-2024018 | CL004 | Central | Madhya Pradesh | Bhopal | Leased Line | ATM/Off-site | Excitel Enterprise | 2024-09-27 |  |  | BOM Finalization | Cancelled | N/A | 6 | 40664 | 16348 | FE-359
SITE-01525 | PRJ-2024018 | CL004 | Central | Madhya Pradesh | Jabalpur | Leased Line | Corporate Office | Local ISP Partner | 2025-03-18 | 2025-03-22 | 4 | Go-Live | Live - Operational | Met | 10 | 88986 | 7909 | FE-394
SITE-01526 | PRJ-2024019 | CL003 | East | West Bengal | Howrah | VSAT | Data Center | Excitel Enterprise | 2024-10-26 |  | 611 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 36474 | 6307 | FE-111
SITE-01527 | PRJ-2024019 | CL003 | East | Assam | Dibrugarh | VSAT | Branch | Sify Technologies | 2024-12-19 |  | 557 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 120577 | 5922 | FE-132
SITE-01528 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Sify Technologies | 2024-09-14 |  | 653 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 121534 | 13293 | FE-351
SITE-01529 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | Data Center | Sify Technologies | 2024-08-30 |  | 668 | Site Survey | Survey Complete | Breached | 20 | 71323 | 7310 | FE-391
SITE-01530 | PRJ-2024019 | CL003 | East | Assam | Dibrugarh | VSAT | Warehouse/Ops Hub | Sify Technologies | 2025-01-18 | 2025-02-11 | 24 | Go-Live | Live - Operational | Breached | 2 | 107900 | 4367 | FE-464
SITE-01531 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-10 | 2024-12-04 | -6 | Go-Live | Live - Operational | Met | 6 | 124017 | 6688 | FE-227
SITE-01532 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | Branch | Sify Technologies | 2024-07-13 | 2024-08-03 | 21 | Go-Live | Live - Operational | Breached | 4 | 40341 | 10111 | FE-393
SITE-01533 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Data Center | Airtel Business | 2024-12-31 |  | 545 | Site Survey | Survey Complete | Breached | 34 | 51984 | 5070 | FE-259
SITE-01534 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Corporate Office | Vodafone Idea Business | 2024-10-24 |  | 613 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 52191 | 7768 | FE-305
SITE-01535 | PRJ-2024019 | CL003 | East | Odisha | Bhubaneswar | VSAT | Branch | Sify Technologies | 2024-12-18 | 2025-01-02 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 126541 | 5040 | FE-368
SITE-01536 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-07-21 |  | 708 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 40516 | 6260 | FE-100
SITE-01537 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | Corporate Office | Tata Communications | 2024-09-27 | 2024-10-11 | 14 | Go-Live | Live - Operational | Breached | 34 | 37094 | 6324 | FE-196
SITE-01538 | PRJ-2024019 | CL003 | East | Assam | Dibrugarh | VSAT | Corporate Office | Tata Communications | 2024-11-20 | 2024-11-23 | 3 | Go-Live | Live - Operational | Met | 6 | 106606 | 9630 | FE-393
SITE-01539 | PRJ-2024019 | CL003 | East | Odisha | Cuttack | VSAT | ATM/Off-site | Excitel Enterprise | 2025-02-07 |  | 507 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 134739 | 16918 | FE-327
SITE-01540 | PRJ-2024019 | CL003 | East | West Bengal | Siliguri | VSAT | Corporate Office | Sify Technologies | 2024-11-20 | 2024-11-17 | -3 | Go-Live | Live - Operational | Met | 4 | 73751 | 14690 | FE-192
SITE-01541 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-11-10 | 2024-11-12 | 2 | Go-Live | Live - Operational | Met | 34 | 87594 | 14288 | FE-380
SITE-01542 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Branch | Sify Technologies | 2024-12-24 | 2025-01-18 | 25 | Go-Live | Live - Operational | Breached | 10 | 75932 | 5816 | FE-222
SITE-01543 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Tata Communications | 2024-07-16 |  | 713 | Site Survey | Survey Complete | Breached | 100 | 134287 | 17321 | FE-437
SITE-01544 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | Corporate Office | Excitel Enterprise | 2024-07-29 |  | 700 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 127211 | 12451 | FE-429
SITE-01545 | PRJ-2024019 | CL003 | East | Odisha | Cuttack | VSAT | ATM/Off-site | Sify Technologies | 2024-08-09 | 2024-08-18 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 80984 | 10629 | FE-293
SITE-01546 | PRJ-2024019 | CL003 | East | West Bengal | Howrah | VSAT | Corporate Office | Excitel Enterprise | 2024-11-08 | 2024-11-04 | -4 | Go-Live | Live - Operational | Met | 100 | 107909 | 9870 | FE-256
SITE-01547 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Branch | Excitel Enterprise | 2024-12-31 |  | 545 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 52651 | 4961 | FE-257
SITE-01548 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | Branch | Excitel Enterprise | 2024-09-24 |  | 643 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 34187 | 8463 | FE-297
SITE-01549 | PRJ-2024019 | CL003 | East | Odisha | Cuttack | VSAT | Data Center | Local ISP Partner | 2024-07-19 |  | 710 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 94682 | 9575 | FE-448
SITE-01550 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Local ISP Partner | 2024-10-31 | 2024-11-01 | 1 | Go-Live | Live - Operational | Met | 34 | 37563 | 15198 | FE-204
SITE-01551 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | Warehouse/Ops Hub | Tata Communications | 2024-12-16 |  | 560 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 78002 | 6875 | FE-452
SITE-01552 | PRJ-2024019 | CL003 | East | West Bengal | Howrah | VSAT | Corporate Office | Airtel Business | 2025-02-22 | 2025-02-27 | 5 | Go-Live | Live - Operational | Met | 50 | 57933 | 9591 | FE-305
SITE-01553 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-12-06 | 2024-12-11 | 5 | Go-Live | Live - Operational | Met | 20 | 83422 | 14647 | FE-392
SITE-01554 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Corporate Office | Vodafone Idea Business | 2025-01-10 |  | 535 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 82511 | 16993 | FE-311
SITE-01555 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Excitel Enterprise | 2025-01-31 | 2025-02-21 | 21 | Go-Live | Live - Operational | Breached | 2 | 110121 | 14846 | FE-302
SITE-01556 | PRJ-2024019 | CL003 | East | West Bengal | Siliguri | VSAT | ATM/Off-site | Tata Communications | 2024-08-07 |  | 691 | Site Survey | Survey Scheduled | Breached | 4 | 43109 | 6103 | FE-350
SITE-01557 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Local ISP Partner | 2024-09-27 |  | 640 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 117247 | 15214 | FE-455
SITE-01558 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Excitel Enterprise | 2024-09-17 |  | 650 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 42220 | 15968 | FE-161
SITE-01559 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Airtel Business | 2024-11-25 | 2024-12-16 | 21 | Go-Live | Live - Operational | Breached | 2 | 89467 | 11344 | FE-155
SITE-01560 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | ATM/Off-site | Tata Communications | 2025-02-04 | 2025-02-18 | 14 | Go-Live | Live - Operational | Breached | 4 | 59686 | 10642 | FE-415
SITE-01561 | PRJ-2024019 | CL003 | East | Bihar | Gaya | VSAT | Data Center | Excitel Enterprise | 2024-08-11 |  | 687 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 114884 | 11751 | FE-492
SITE-01562 | PRJ-2024019 | CL003 | East | Odisha | Bhubaneswar | VSAT | Branch | Excitel Enterprise | 2024-09-25 |  | 642 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 48016 | 9092 | FE-228
SITE-01563 | PRJ-2024019 | CL003 | East | Odisha | Cuttack | VSAT | Branch | Vodafone Idea Business | 2024-08-26 |  | 672 | Site Survey | Survey Scheduled | Breached | 50 | 48066 | 8280 | FE-358
SITE-01564 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Corporate Office | Local ISP Partner | 2024-12-13 | 2024-12-15 | 2 | Go-Live | Live - Operational | Met | 100 | 31317 | 17775 | FE-325
SITE-01565 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Corporate Office | Excitel Enterprise | 2024-11-18 |  | 588 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 46790 | 12464 | FE-262
SITE-01566 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Data Center | Excitel Enterprise | 2024-07-22 |  | 707 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 109079 | 15304 | FE-186
SITE-01567 | PRJ-2024019 | CL003 | East | Bihar | Gaya | VSAT | ATM/Off-site | Tata Communications | 2024-08-11 | 2024-08-07 | -4 | Go-Live | Live - Operational | Met | 50 | 28448 | 12719 | FE-129
SITE-01568 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2025-01-17 | 2025-01-09 | -8 | Go-Live | Live - Operational | Met | 4 | 30594 | 14130 | FE-343
SITE-01569 | PRJ-2024019 | CL003 | East | Assam | Dibrugarh | VSAT | Data Center | Vodafone Idea Business | 2024-12-28 | 2025-01-11 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 117506 | 11537 | FE-413
SITE-01570 | PRJ-2024019 | CL003 | East | Bihar | Gaya | VSAT | Data Center | Airtel Business | 2024-10-30 |  | 607 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 98314 | 17908 | FE-284
SITE-01571 | PRJ-2024019 | CL003 | East | Odisha | Bhubaneswar | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-12-16 | 2025-01-03 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 49013 | 9530 | FE-478
SITE-01572 | PRJ-2024019 | CL003 | East | West Bengal | Howrah | VSAT | Data Center | Vodafone Idea Business | 2024-08-11 | 2024-08-07 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 80721 | 5548 | FE-420
SITE-01573 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Data Center | Vodafone Idea Business | 2024-10-21 |  | 616 | Site Survey | Survey Complete | Breached | 100 | 86181 | 9864 | FE-337
SITE-01574 | PRJ-2024019 | CL003 | East | Bihar | Gaya | VSAT | ATM/Off-site | Local ISP Partner | 2024-12-23 | 2024-12-30 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 60244 | 7054 | FE-464
SITE-01575 | PRJ-2024019 | CL003 | East | Odisha | Rourkela | VSAT | Data Center | Excitel Enterprise | 2025-02-14 | 2025-02-27 | 13 | Go-Live | Live - Operational | Breached | 50 | 77127 | 14051 | FE-257
SITE-01576 | PRJ-2024019 | CL003 | East | Odisha | Cuttack | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2024-11-03 | 2024-10-30 | -4 | Go-Live | Live - Operational | Met | 100 | 67363 | 17146 | FE-496
SITE-01577 | PRJ-2024019 | CL003 | East | Assam | Dibrugarh | VSAT | Corporate Office | Excitel Enterprise | 2024-08-26 | 2024-08-29 | 3 | Go-Live | Live - Operational | Met | 6 | 114461 | 9796 | FE-364
SITE-01578 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-07-12 |  | 717 | Site Survey | Survey Scheduled | Breached | 6 | 63824 | 15722 | FE-448
SITE-01579 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-10-16 |  | 621 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 81908 | 8685 | FE-339
SITE-01580 | PRJ-2024019 | CL003 | East | Odisha | Rourkela | VSAT | Corporate Office | Excitel Enterprise | 2025-01-17 | 2025-02-07 | 21 | Go-Live | Live - Operational | Breached | 2 | 116629 | 5090 | FE-133
SITE-01581 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Corporate Office | Tata Communications | 2025-02-26 | 2025-02-19 | -7 | Go-Live | Live - Operational | Met | 34 | 74752 | 6826 | FE-480
SITE-01582 | PRJ-2024019 | CL003 | East | Odisha | Bhubaneswar | VSAT | Corporate Office | Excitel Enterprise | 2025-02-06 | 2025-02-03 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 104473 | 17070 | FE-328
SITE-01583 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Corporate Office | Sify Technologies | 2024-08-19 |  | 679 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 133163 | 12705 | FE-181
SITE-01584 | PRJ-2024019 | CL003 | East | Odisha | Bhubaneswar | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2024-08-05 |  | 693 | Site Survey | Survey Scheduled | Breached | 50 | 48746 | 12702 | FE-382
SITE-01585 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Branch | Local ISP Partner | 2025-02-08 |  |  | Site Survey | Cancelled | N/A | 6 | 86314 | 5090 | FE-486
SITE-01586 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Data Center | Vodafone Idea Business | 2024-11-04 |  | 602 | Site Survey | Survey Complete | Breached | 6 | 128550 | 3826 | FE-400
SITE-01587 | PRJ-2024019 | CL003 | East | Bihar | Gaya | VSAT | ATM/Off-site | Vodafone Idea Business | 2024-11-29 |  | 577 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 92456 | 14506 | FE-390
SITE-01588 | PRJ-2024019 | CL003 | East | Bihar | Gaya | VSAT | Branch | Airtel Business | 2025-02-17 | 2025-03-02 | 13 | Go-Live | Live - Operational | Breached | 6 | 109793 | 8416 | FE-446
SITE-01589 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Sify Technologies | 2025-01-24 | 2025-01-26 | 2 | Go-Live | Live - Operational | Met | 4 | 74492 | 13376 | FE-353
SITE-01590 | PRJ-2024019 | CL003 | East | West Bengal | Siliguri | VSAT | ATM/Off-site | Sify Technologies | 2024-10-20 |  | 617 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 53168 | 11911 | FE-243
SITE-01591 | PRJ-2024019 | CL003 | East | Assam | Guwahati | VSAT | ATM/Off-site | Tata Communications | 2024-09-25 |  | 642 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 119817 | 8523 | FE-234
SITE-01592 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Data Center | Local ISP Partner | 2024-07-16 | 2024-07-19 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 71636 | 12532 | FE-116
SITE-01593 | PRJ-2024019 | CL003 | East | Odisha | Rourkela | VSAT | Corporate Office | Vodafone Idea Business | 2025-01-10 | 2025-01-01 | -9 | Go-Live | Live - Operational | Met | 10 | 89619 | 9726 | FE-298
SITE-01594 | PRJ-2024019 | CL003 | East | West Bengal | Siliguri | VSAT | Data Center | Sify Technologies | 2024-09-13 |  | 654 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 133269 | 11898 | FE-317
SITE-01595 | PRJ-2024019 | CL003 | East | Jharkhand | Jamshedpur | VSAT | Warehouse/Ops Hub | Airtel Business | 2024-10-02 | 2024-10-08 | 6 | Go-Live | Live - Operational | Breached | 100 | 64915 | 7869 | FE-142
SITE-01596 | PRJ-2024019 | CL003 | East | Jharkhand | Ranchi | VSAT | Corporate Office | Excitel Enterprise | 2025-02-24 |  | 490 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 31015 | 16783 | FE-165
SITE-01597 | PRJ-2024019 | CL003 | East | West Bengal | Kolkata | VSAT | Branch | Airtel Business | 2024-08-20 | 2024-09-02 | 13 | Go-Live | Live - Operational | Breached | 10 | 130088 | 4931 | FE-138
SITE-01598 | PRJ-2024019 | CL003 | East | West Bengal | Siliguri | VSAT | Warehouse/Ops Hub | Tata Communications | 2025-01-10 | 2025-01-21 | 11 | Go-Live | Live - Operational | Breached | 6 | 104382 | 13758 | FE-335
SITE-01599 | PRJ-2024019 | CL003 | East | Bihar | Patna | VSAT | Branch | Local ISP Partner | 2024-08-06 |  | 692 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 54151 | 15723 | FE-141
SITE-01600 | PRJ-2024019 | CL003 | East | Odisha | Bhubaneswar | VSAT | Branch | Vodafone Idea Business | 2024-07-29 |  | 700 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 55553 | 4319 | FE-467
SITE-01601 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-05-24 | 2025-06-04 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 120830 | 11615 | FE-409
SITE-01602 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-06-20 | 2025-07-06 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 52238 | 11816 | FE-103
SITE-01603 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-20 | 2025-02-19 | -1 | Go-Live | Live - Operational | Met | 10 | 119746 | 5531 | FE-459
SITE-01604 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Airtel Business | 2025-07-20 | 2025-07-30 | 10 | Go-Live | Live - Operational | Breached | 50 | 111269 | 17197 | FE-403
SITE-01605 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Airtel Business | 2025-05-27 |  | 398 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 60892 | 17008 | FE-276
SITE-01606 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Sify Technologies | 2025-07-30 |  | 334 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 36474 | 4509 | FE-132
SITE-01607 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2024-12-30 |  | 546 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 116347 | 16024 | FE-466
SITE-01608 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Excitel Enterprise | 2025-01-06 |  | 539 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 119498 | 14658 | FE-410
SITE-01609 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Vodafone Idea Business | 2025-07-17 |  | 347 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 125280 | 16786 | FE-345
SITE-01610 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Excitel Enterprise | 2025-06-28 | 2025-07-08 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 57899 | 13121 | FE-187
SITE-01611 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Sify Technologies | 2025-04-13 |  | 442 | Site Survey | Survey Complete | Breached | 50 | 88768 | 17732 | FE-337
SITE-01612 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Tata Communications | 2025-06-21 | 2025-07-05 | 14 | Go-Live | Live - Operational | Breached | 6 | 131319 | 8689 | FE-295
SITE-01613 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Local ISP Partner | 2024-12-18 |  | 558 | Site Survey | Survey Complete | Breached | 6 | 47796 | 13214 | FE-194
SITE-01614 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Sify Technologies | 2025-03-25 | 2025-04-14 | 20 | Go-Live | Live - Operational | Breached | 34 | 53920 | 3855 | FE-354
SITE-01615 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Airtel Business | 2025-07-15 | 2025-07-27 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 91771 | 13442 | FE-470
SITE-01616 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-07-21 |  | 343 | Site Survey | Survey Scheduled | Breached | 2 | 74316 | 5236 | FE-134
SITE-01617 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Airtel Business | 2025-02-27 |  | 487 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 133332 | 7045 | FE-313
SITE-01618 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Local ISP Partner | 2025-05-25 | 2025-05-25 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 117660 | 13633 | FE-319
SITE-01619 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Local ISP Partner | 2025-02-25 |  | 489 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 133791 | 14780 | FE-165
SITE-01620 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Vodafone Idea Business | 2024-12-19 | 2025-01-06 | 18 | Go-Live | Live - Operational | Breached | 10 | 55453 | 8844 | FE-452
SITE-01621 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Sify Technologies | 2025-08-06 |  | 327 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 103657 | 16505 | FE-269
SITE-01622 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-07-03 | 2025-07-18 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 134603 | 16929 | FE-227
SITE-01623 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Branch | Vodafone Idea Business | 2025-03-05 | 2025-03-27 | 22 | Go-Live | Live - Operational | Breached | 6 | 109737 | 8769 | FE-141
SITE-01624 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Tata Communications | 2025-08-02 |  | 331 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 79062 | 16237 | FE-198
SITE-01625 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Branch | Vodafone Idea Business | 2025-07-20 |  | 344 | Site Survey | Survey Complete | Breached | 10 | 57272 | 13872 | FE-101
SITE-01626 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-04-17 |  | 438 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 69947 | 11441 | FE-260
SITE-01627 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Sify Technologies | 2025-05-18 |  | 407 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 124402 | 17996 | FE-199
SITE-01628 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Branch | Sify Technologies | 2025-04-02 |  | 453 | Site Survey | Survey Complete | Breached | 20 | 54770 | 5860 | FE-251
SITE-01629 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Tata Communications | 2025-05-28 |  | 397 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 88940 | 16210 | FE-175
SITE-01630 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-01-24 |  | 521 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 42122 | 7981 | FE-333
SITE-01631 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Sify Technologies | 2025-05-19 |  | 406 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 104871 | 5605 | FE-265
SITE-01632 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-07-25 | 2025-08-04 | 10 | Go-Live | Live - Operational | Breached | 34 | 46579 | 8665 | FE-468
SITE-01633 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Vodafone Idea Business | 2025-04-05 |  | 450 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 70809 | 13544 | FE-489
SITE-01634 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-05-08 | 2025-05-27 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 122735 | 15251 | FE-465
SITE-01635 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Tata Communications | 2025-01-01 | 2024-12-30 | -2 | Go-Live | Live - Operational | Met | 6 | 121566 | 7350 | FE-147
SITE-01636 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Corporate Office | Tata Communications | 2025-01-04 | 2025-01-12 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 80502 | 12431 | FE-131
SITE-01637 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Branch | Airtel Business | 2025-01-23 |  |  | ROW / Permission | Cancelled | N/A | 100 | 48848 | 5388 | FE-490
SITE-01638 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Branch | Tata Communications | 2024-12-29 | 2025-01-23 | 25 | Go-Live | Live - Operational | Breached | 10 | 90743 | 4194 | FE-121
SITE-01639 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-07-25 | 2025-07-23 | -2 | Go-Live | Live - Operational | Met | 34 | 78793 | 15885 | FE-424
SITE-01640 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Vodafone Idea Business | 2025-06-28 |  | 366 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 115771 | 15210 | FE-456
SITE-01641 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | ATM/Off-site | Airtel Business | 2025-02-04 | 2025-01-27 | -8 | Go-Live | Live - Operational | Met | 100 | 28937 | 9224 | FE-459
SITE-01642 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-08-02 |  | 331 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 47956 | 12285 | FE-103
SITE-01643 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-20 |  | 466 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 54422 | 15856 | FE-411
SITE-01644 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Tata Communications | 2025-03-08 | 2025-03-14 | 6 | Go-Live | Live - Operational | Breached | 20 | 87198 | 3972 | FE-328
SITE-01645 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Tata Communications | 2025-01-12 | 2025-01-04 | -8 | Go-Live | Live - Operational | Met | 10 | 54233 | 15947 | FE-391
SITE-01646 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Sify Technologies | 2025-07-12 |  | 352 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 35126 | 14114 | FE-420
SITE-01647 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Tata Communications | 2025-04-24 | 2025-04-15 | -9 | Go-Live | Live - Operational | Met | 10 | 51713 | 17596 | FE-270
SITE-01648 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Vodafone Idea Business | 2025-03-24 |  | 462 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 106880 | 15851 | FE-184
SITE-01649 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Local ISP Partner | 2025-05-16 |  | 409 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 38180 | 13598 | FE-154
SITE-01650 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Sify Technologies | 2024-12-27 |  | 549 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 67773 | 10791 | FE-295
SITE-01651 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-03-19 | 2025-03-22 | 3 | Go-Live | Live - Operational | Met | 34 | 37974 | 8087 | FE-313
SITE-01652 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Airtel Business | 2025-08-02 | 2025-07-30 | -3 | Go-Live | Live - Operational | Met | 20 | 87890 | 16616 | FE-204
SITE-01653 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Tata Communications | 2025-01-28 |  | 517 | Site Survey | Survey Scheduled | Breached | 4 | 123002 | 7347 | FE-333
SITE-01654 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Branch | Local ISP Partner | 2025-06-12 | 2025-07-02 | 20 | Go-Live | Live - Operational | Breached | 6 | 56242 | 4567 | FE-303
SITE-01655 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Data Center | Vodafone Idea Business | 2025-04-21 | 2025-05-08 | 17 | Go-Live | Live - Operational | Breached | 6 | 29739 | 12949 | FE-122
SITE-01656 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Airtel Business | 2025-02-25 |  | 489 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 31199 | 14497 | FE-239
SITE-01657 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Excitel Enterprise | 2025-04-08 |  |  | Site Survey | Cancelled | N/A | 50 | 101261 | 15017 | FE-350
SITE-01658 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-03-18 | 2025-03-15 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 89928 | 12422 | FE-183
SITE-01659 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-05-05 |  | 420 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 124363 | 13974 | FE-277
SITE-01660 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Vodafone Idea Business | 2025-03-27 |  | 459 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 128573 | 8291 | FE-175
SITE-01661 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Branch | Excitel Enterprise | 2025-04-04 |  | 451 | Site Survey | Survey Complete | Breached | 20 | 46040 | 8952 | FE-283
SITE-01662 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Tata Communications | 2025-07-23 |  | 341 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 94368 | 17585 | FE-420
SITE-01663 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Excitel Enterprise | 2025-05-25 |  | 400 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 134988 | 16480 | FE-205
SITE-01664 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Branch | Excitel Enterprise | 2025-07-28 |  | 336 | Site Survey | Survey Scheduled | Breached | 2 | 96100 | 5200 | FE-394
SITE-01665 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Local ISP Partner | 2025-06-03 |  | 391 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 117654 | 15128 | FE-271
SITE-01666 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Excitel Enterprise | 2025-06-20 | 2025-07-10 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 96566 | 14262 | FE-301
SITE-01667 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Branch | Airtel Business | 2025-06-09 |  | 385 | Site Survey | Survey Complete | Breached | 100 | 48408 | 17169 | FE-455
SITE-01668 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Vodafone Idea Business | 2025-07-07 |  | 357 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 37464 | 14885 | FE-256
SITE-01669 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-07-14 | 2025-07-15 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 134757 | 6629 | FE-112
SITE-01670 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Local ISP Partner | 2025-01-14 | 2025-01-15 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 36784 | 7652 | FE-331
SITE-01671 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Tata Communications | 2025-06-02 |  | 392 | Site Survey | Survey Complete | Breached | 20 | 72979 | 9852 | FE-291
SITE-01672 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-22 |  | 403 | Site Survey | Survey Scheduled | Breached | 2 | 117013 | 11550 | FE-116
SITE-01673 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Vodafone Idea Business | 2024-12-22 | 2024-12-25 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 83404 | 14781 | FE-400
SITE-01674 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Data Center | Tata Communications | 2025-03-22 | 2025-03-14 | -8 | Go-Live | Live - Operational | Met | 100 | 61050 | 12408 | FE-147
SITE-01675 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Vodafone Idea Business | 2025-07-15 |  | 349 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 126179 | 9027 | FE-223
SITE-01676 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Data Center | Airtel Business | 2025-03-04 | 2025-03-16 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 40445 | 3668 | FE-450
SITE-01677 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Excitel Enterprise | 2025-04-07 |  | 448 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 88709 | 8001 | FE-456
SITE-01678 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-13 | 2025-05-10 | -3 | Go-Live | Live - Operational | Met | 6 | 87208 | 8306 | FE-183
SITE-01679 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Tata Communications | 2025-03-09 |  | 477 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 38069 | 6762 | FE-346
SITE-01680 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Tata Communications | 2025-03-24 | 2025-03-25 | 1 | Go-Live | Live - Operational | Met | 20 | 51943 | 7160 | FE-274
SITE-01681 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Branch | Tata Communications | 2025-04-07 |  | 448 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 46245 | 5662 | FE-479
SITE-01682 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Tata Communications | 2025-03-18 |  | 468 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 111208 | 12404 | FE-154
SITE-01683 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-02-24 | 2025-03-13 | 17 | Go-Live | Live - Operational | Breached | 50 | 36773 | 4567 | FE-144
SITE-01684 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-03-27 |  | 459 | Site Survey | Survey Scheduled | Breached | 6 | 43861 | 3895 | FE-182
SITE-01685 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Local ISP Partner | 2025-02-03 |  | 511 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 101055 | 7809 | FE-344
SITE-01686 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Excitel Enterprise | 2025-03-30 |  | 456 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 58441 | 6816 | FE-175
SITE-01687 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Tata Communications | 2025-03-25 |  |  | Site Survey | Cancelled | N/A | 2 | 42778 | 12094 | FE-440
SITE-01688 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | ATM/Off-site | Sify Technologies | 2025-07-28 | 2025-08-17 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 90965 | 16627 | FE-209
SITE-01689 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Tata Communications | 2025-04-16 |  | 439 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 78837 | 12560 | FE-424
SITE-01690 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-01-16 |  | 529 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 90611 | 11911 | FE-137
SITE-01691 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Local ISP Partner | 2025-06-25 |  | 369 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 57536 | 17065 | FE-234
SITE-01692 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Vodafone Idea Business | 2024-12-25 |  | 551 | Site Survey | Survey Scheduled | Breached | 2 | 53245 | 14504 | FE-471
SITE-01693 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Local ISP Partner | 2025-05-19 |  | 406 | Site Survey | Survey Scheduled | Breached | 6 | 90831 | 13574 | FE-360
SITE-01694 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Vodafone Idea Business | 2025-05-17 | 2025-06-09 | 23 | Go-Live | Live - Operational | Breached | 4 | 84720 | 13327 | FE-115
SITE-01695 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | ATM/Off-site | Local ISP Partner | 2025-01-05 |  | 540 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 76433 | 8044 | FE-301
SITE-01696 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Sify Technologies | 2025-07-09 |  | 355 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 68388 | 17514 | FE-340
SITE-01697 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-05-14 |  |  | ROW / Permission | Cancelled | N/A | 6 | 89515 | 9022 | FE-146
SITE-01698 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-04-26 |  | 429 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 60976 | 13807 | FE-237
SITE-01699 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | ATM/Off-site | Sify Technologies | 2025-04-25 |  | 430 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 59380 | 12773 | FE-197
SITE-01700 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-07-14 | 2025-07-25 | 11 | Go-Live | Live - Operational | Breached | 50 | 64506 | 7823 | FE-406
SITE-01701 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Local ISP Partner | 2025-07-30 |  | 334 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 52899 | 14757 | FE-451
SITE-01702 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-07 | 2025-07-26 | 19 | Go-Live | Live - Operational | Breached | 6 | 43363 | 15371 | FE-470
SITE-01703 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Local ISP Partner | 2025-05-17 | 2025-05-28 | 11 | Go-Live | Live - Operational | Breached | 100 | 77151 | 7524 | FE-300
SITE-01704 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-04-11 |  | 444 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 61387 | 13428 | FE-136
SITE-01705 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-07-11 |  | 353 | Site Survey | Survey Complete | Breached | 2 | 36722 | 6595 | FE-230
SITE-01706 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Excitel Enterprise | 2025-05-13 |  | 412 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 54108 | 7853 | FE-126
SITE-01707 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Data Center | Vodafone Idea Business | 2025-01-11 |  | 534 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 69044 | 5456 | FE-171
SITE-01708 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Tata Communications | 2025-06-27 |  | 367 | Site Survey | Survey Complete | Breached | 4 | 64353 | 5260 | FE-380
SITE-01709 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Tata Communications | 2025-06-23 | 2025-07-10 | 17 | Go-Live | Live - Operational | Breached | 2 | 29291 | 5325 | FE-272
SITE-01710 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | ATM/Off-site | Airtel Business | 2025-02-14 |  | 500 | Site Survey | Survey Scheduled | Breached | 20 | 100432 | 9292 | FE-221
SITE-01711 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Airtel Business | 2025-05-13 |  | 412 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 133606 | 17018 | FE-296
SITE-01712 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Tata Communications | 2025-01-07 | 2025-01-14 | 7 | Go-Live | Live - Operational | Breached | 4 | 60269 | 17350 | FE-308
SITE-01713 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Airtel Business | 2025-05-20 |  | 405 | Site Survey | Survey Scheduled | Breached | 10 | 64630 | 5259 | FE-101
SITE-01714 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-12 |  | 413 | Site Survey | Survey Scheduled | Breached | 100 | 55969 | 7304 | FE-151
SITE-01715 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Airtel Business | 2025-04-07 |  | 448 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 108616 | 15799 | FE-294
SITE-01716 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Excitel Enterprise | 2025-07-28 | 2025-08-18 | 21 | Go-Live | Live - Operational | Breached | 34 | 70215 | 3839 | FE-355
SITE-01717 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Airtel Business | 2025-02-05 |  | 509 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 106768 | 17212 | FE-457
SITE-01718 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Sify Technologies | 2025-02-06 |  | 508 | Site Survey | Survey Complete | Breached | 34 | 81097 | 7991 | FE-227
SITE-01719 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Tata Communications | 2025-05-17 |  | 408 | Site Survey | Survey Complete | Breached | 10 | 112603 | 14929 | FE-133
SITE-01720 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Sify Technologies | 2025-05-10 |  | 415 | Site Survey | Survey Complete | Breached | 50 | 30686 | 11543 | FE-323
SITE-01721 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Corporate Office | Airtel Business | 2025-04-05 | 2025-04-11 | 6 | Go-Live | Live - Operational | Breached | 20 | 76050 | 7757 | FE-345
SITE-01722 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-21 | 2025-08-13 | 23 | Go-Live | Live - Operational | Breached | 10 | 32757 | 9749 | FE-286
SITE-01723 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Excitel Enterprise | 2025-06-14 | 2025-06-14 | 0 | Go-Live | Live - Operational | Met | 2 | 60819 | 4798 | FE-368
SITE-01724 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Data Center | Sify Technologies | 2025-02-28 | 2025-02-27 | -1 | Go-Live | Live - Operational | Met | 6 | 58027 | 10208 | FE-259
SITE-01725 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-07-26 | 2025-07-21 | -5 | Go-Live | Live - Operational | Met | 6 | 65780 | 12477 | FE-340
SITE-01726 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2024-12-19 | 2024-12-21 | 2 | Go-Live | Live - Operational | Met | 4 | 36831 | 16162 | FE-151
SITE-01727 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Excitel Enterprise | 2025-01-15 |  | 530 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 122792 | 6431 | FE-178
SITE-01728 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Excitel Enterprise | 2025-03-08 | 2025-03-08 | 0 | Go-Live | Live - Operational | Met | 2 | 93655 | 11765 | FE-129
SITE-01729 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Airtel Business | 2024-12-27 | 2025-01-16 | 20 | Go-Live | Live - Operational | Breached | 10 | 107818 | 17168 | FE-288
SITE-01730 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Branch | Local ISP Partner | 2025-04-10 | 2025-04-11 | 1 | Go-Live | Live - Operational | Met | 10 | 49245 | 13987 | FE-410
SITE-01731 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Sify Technologies | 2025-01-18 |  | 527 | Site Survey | Survey Complete | Breached | 100 | 97323 | 16588 | FE-350
SITE-01732 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-04-13 |  | 442 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 126517 | 7619 | FE-368
SITE-01733 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Airtel Business | 2025-07-22 |  | 342 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 55117 | 4702 | FE-407
SITE-01734 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Vodafone Idea Business | 2025-05-18 | 2025-06-03 | 16 | Go-Live | Live - Operational | Breached | 20 | 76971 | 3891 | FE-261
SITE-01735 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-02-08 | 2025-02-25 | 17 | Go-Live | Live - Operational | Breached | 6 | 113075 | 16504 | FE-254
SITE-01736 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Sify Technologies | 2024-12-19 | 2024-12-23 | 4 | Go-Live | Live - Operational | Met | 100 | 80329 | 11140 | FE-464
SITE-01737 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Tata Communications | 2025-04-12 | 2025-04-10 | -2 | Go-Live | Live - Operational | Met | 10 | 47075 | 13986 | FE-151
SITE-01738 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Local ISP Partner | 2025-03-14 | 2025-04-02 | 19 | Go-Live | Live - Operational | Breached | 50 | 38239 | 13301 | FE-250
SITE-01739 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Branch | Sify Technologies | 2025-07-25 | 2025-08-14 | 20 | Go-Live | Live - Operational | Breached | 34 | 53359 | 8584 | FE-359
SITE-01740 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Tata Communications | 2025-01-21 | 2025-02-15 | 25 | Go-Live | Live - Operational | Breached | 2 | 94782 | 7083 | FE-422
SITE-01741 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Excitel Enterprise | 2025-03-28 |  | 458 | Site Survey | Survey Scheduled | Breached | 100 | 73472 | 13687 | FE-267
SITE-01742 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-07-08 | 2025-07-31 | 23 | Go-Live | Live - Operational | Breached | 100 | 127417 | 11487 | FE-321
SITE-01743 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Local ISP Partner | 2025-07-14 | 2025-07-28 | 14 | Go-Live | Live - Operational | Breached | 100 | 123872 | 15338 | FE-425
SITE-01744 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Branch | Excitel Enterprise | 2025-06-28 | 2025-06-30 | 2 | Go-Live | Live - Operational | Met | 50 | 64144 | 9961 | FE-212
SITE-01745 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Vodafone Idea Business | 2024-12-18 | 2024-12-17 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 82734 | 16598 | FE-177
SITE-01746 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | ATM/Off-site | Tata Communications | 2024-12-15 | 2024-12-09 | -6 | Go-Live | Live - Operational | Met | 20 | 123320 | 11407 | FE-133
SITE-01747 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Branch | Tata Communications | 2025-06-05 | 2025-06-26 | 21 | Go-Live | Live - Operational | Breached | 100 | 134389 | 9115 | FE-415
SITE-01748 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-05-11 | 2025-06-05 | 25 | Go-Live | Live - Operational | Breached | 34 | 110775 | 14394 | FE-267
SITE-01749 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Airtel Business | 2025-07-02 |  | 362 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 84868 | 11419 | FE-239
SITE-01750 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Tata Communications | 2025-06-18 |  | 376 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 133076 | 17641 | FE-231
SITE-01751 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Airtel Business | 2025-02-10 |  | 504 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 48087 | 5115 | FE-457
SITE-01752 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-04-01 |  | 454 | Site Survey | Survey Complete | Breached | 20 | 38633 | 7473 | FE-183
SITE-01753 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Data Center | Vodafone Idea Business | 2025-07-30 | 2025-07-26 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 48191 | 10286 | FE-342
SITE-01754 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Airtel Business | 2025-01-14 |  | 531 | Site Survey | Survey Complete | Breached | 100 | 92469 | 9993 | FE-401
SITE-01755 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Sify Technologies | 2025-07-20 |  | 344 | Site Survey | Survey Scheduled | Breached | 10 | 108028 | 16681 | FE-184
SITE-01756 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-08 |  | 478 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 41193 | 4845 | FE-142
SITE-01757 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Tata Communications | 2025-04-03 |  | 452 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 34731 | 3534 | FE-341
SITE-01758 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Local ISP Partner | 2025-02-27 | 2025-03-12 | 13 | Go-Live | Live - Operational | Breached | 4 | 33299 | 6206 | FE-258
SITE-01759 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Branch | Excitel Enterprise | 2025-05-13 | 2025-05-08 | -5 | Go-Live | Live - Operational | Met | 2 | 53198 | 16435 | FE-187
SITE-01760 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-21 | 2025-03-01 | 8 | Go-Live | Live - Operational | Breached | 4 | 108312 | 8160 | FE-170
SITE-01761 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Airtel Business | 2025-07-21 |  | 343 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 93066 | 13436 | FE-214
SITE-01762 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Local ISP Partner | 2025-07-21 |  | 343 | Site Survey | Survey Complete | Breached | 6 | 119083 | 11244 | FE-331
SITE-01763 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Data Center | Vodafone Idea Business | 2025-05-31 | 2025-06-17 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 132104 | 17379 | FE-258
SITE-01764 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Tata Communications | 2025-04-12 | 2025-04-11 | -1 | Go-Live | Live - Operational | Met | 4 | 35700 | 13128 | FE-160
SITE-01765 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | ATM/Off-site | Local ISP Partner | 2025-01-16 |  | 529 | Site Survey | Survey Scheduled | Breached | 4 | 65024 | 16121 | FE-270
SITE-01766 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Data Center | Vodafone Idea Business | 2025-04-17 |  | 438 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 112451 | 14448 | FE-443
SITE-01767 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Branch | Sify Technologies | 2025-05-31 |  | 394 | Site Survey | Survey Scheduled | Breached | 6 | 79222 | 6637 | FE-276
SITE-01768 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Airtel Business | 2025-07-18 | 2025-07-24 | 6 | Go-Live | Live - Operational | Breached | 100 | 88752 | 14286 | FE-303
SITE-01769 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Data Center | Local ISP Partner | 2025-07-11 | 2025-07-21 | 10 | Go-Live | Live - Operational | Breached | 34 | 126502 | 12782 | FE-458
SITE-01770 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Vodafone Idea Business | 2025-02-17 | 2025-03-05 | 16 | Go-Live | Live - Operational | Breached | 34 | 47420 | 4188 | FE-171
SITE-01771 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-08-04 | 2025-08-05 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 129038 | 3651 | FE-423
SITE-01772 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Corporate Office | Tata Communications | 2025-03-20 |  | 466 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 91281 | 16141 | FE-356
SITE-01773 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Corporate Office | Excitel Enterprise | 2025-03-10 | 2025-04-01 | 22 | Go-Live | Live - Operational | Breached | 50 | 97302 | 13174 | FE-413
SITE-01774 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Branch | Vodafone Idea Business | 2025-07-07 |  | 357 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 98620 | 15882 | FE-333
SITE-01775 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2024-12-19 | 2024-12-27 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 90195 | 17091 | FE-313
SITE-01776 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-07-16 | 2025-07-29 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 67358 | 14183 | FE-119
SITE-01777 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Branch | Excitel Enterprise | 2025-02-20 |  | 494 | Site Survey | Survey Complete | Breached | 10 | 33314 | 7133 | FE-330
SITE-01778 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Branch | Sify Technologies | 2025-04-04 | 2025-03-28 | -7 | Go-Live | Live - Operational | Met | 50 | 30142 | 11720 | FE-475
SITE-01779 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | ATM/Off-site | Excitel Enterprise | 2025-05-12 |  | 413 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 130193 | 5398 | FE-220
SITE-01780 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Branch | Local ISP Partner | 2025-05-03 | 2025-05-05 | 2 | Go-Live | Live - Operational | Met | 50 | 38443 | 8886 | FE-431
SITE-01781 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Airtel Business | 2025-01-09 | 2025-01-07 | -2 | Go-Live | Live - Operational | Met | 20 | 116055 | 7712 | FE-312
SITE-01782 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Tata Communications | 2025-06-19 | 2025-06-19 | 0 | Go-Live | Live - Operational | Met | 20 | 68565 | 12385 | FE-454
SITE-01783 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Branch | Airtel Business | 2025-07-26 | 2025-07-23 | -3 | Go-Live | Live - Operational | Met | 4 | 130061 | 16121 | FE-488
SITE-01784 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Tata Communications | 2025-06-28 | 2025-07-16 | 18 | Go-Live | Live - Operational | Breached | 100 | 94948 | 5500 | FE-346
SITE-01785 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Branch | Sify Technologies | 2025-07-04 |  | 360 | Site Survey | Survey Complete | Breached | 6 | 78840 | 16715 | FE-196
SITE-01786 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Branch | Tata Communications | 2025-07-08 |  | 356 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 47111 | 9104 | FE-182
SITE-01787 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Branch | Sify Technologies | 2025-03-14 |  | 472 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 131896 | 15898 | FE-321
SITE-01788 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-01-26 | 2025-01-28 | 2 | Go-Live | Live - Operational | Met | 100 | 129379 | 13106 | FE-482
SITE-01789 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Excitel Enterprise | 2025-08-05 |  | 328 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 78760 | 8779 | FE-428
SITE-01790 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Tata Communications | 2024-12-24 | 2025-01-11 | 18 | Go-Live | Live - Operational | Breached | 34 | 30244 | 14388 | FE-290
SITE-01791 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Gwalior | MPLS | Branch | Airtel Business | 2025-03-05 | 2025-03-24 | 19 | Go-Live | Live - Operational | Breached | 4 | 105941 | 12028 | FE-387
SITE-01792 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-04-20 |  | 435 | Site Survey | Survey Scheduled | Breached | 34 | 43696 | 13739 | FE-116
SITE-01793 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Indore | MPLS | Corporate Office | Tata Communications | 2025-05-01 | 2025-05-09 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 35197 | 8418 | FE-440
SITE-01794 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Sify Technologies | 2025-01-23 |  | 522 | Site Survey | Survey Complete | Breached | 50 | 37751 | 12199 | FE-286
SITE-01795 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Data Center | Tata Communications | 2025-06-22 | 2025-06-26 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 65375 | 8869 | FE-194
SITE-01796 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-05-18 |  | 407 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 42860 | 5059 | FE-235
SITE-01797 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-01-30 | 2025-02-02 | 3 | Go-Live | Live - Operational | Met | 10 | 34432 | 8030 | FE-259
SITE-01798 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Bilaspur | MPLS | Corporate Office | Tata Communications | 2025-06-01 |  | 393 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 126605 | 4167 | FE-259
SITE-01799 | PRJ-2024020 | CL005 | Central | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Local ISP Partner | 2025-03-10 |  | 476 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 45942 | 4626 | FE-148
SITE-01800 | PRJ-2024020 | CL005 | Central | Chhattisgarh | Raipur | MPLS | Data Center | Sify Technologies | 2024-12-25 |  | 551 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 99036 | 5251 | FE-235
SITE-01801 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Raipur | VSAT | ATM/Off-site | Local ISP Partner | 2025-07-22 | 2025-07-22 | 0 | Go-Live | Live - Operational | Met | 4 | 110685 | 16807 | FE-108
SITE-01802 | PRJ-2024021 | CL003 | Central | Madhya Pradesh | Indore | VSAT | ATM/Off-site | Airtel Business | 2025-10-26 |  | 246 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 81465 | 3586 | FE-448
SITE-01803 | PRJ-2024021 | CL003 | Central | Madhya Pradesh | Indore | VSAT | ATM/Off-site | Tata Communications | 2025-09-15 |  | 287 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 55657 | 13547 | FE-441
SITE-01804 | PRJ-2024021 | CL003 | Central | Madhya Pradesh | Indore | VSAT | Corporate Office | Airtel Business | 2025-07-11 |  | 353 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 105433 | 10242 | FE-396
SITE-01805 | PRJ-2024021 | CL003 | Central | Madhya Pradesh | Jabalpur | VSAT | Data Center | Sify Technologies | 2025-10-02 | 2025-09-29 | -3 | Go-Live | Live - Operational | Met | 100 | 28190 | 5377 | FE-307
SITE-01806 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Bilaspur | VSAT | ATM/Off-site | Local ISP Partner | 2025-05-30 |  |  | ROW / Permission | Cancelled | N/A | 4 | 115952 | 7576 | FE-167
SITE-01807 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Raipur | VSAT | Branch | Local ISP Partner | 2025-11-04 | 2025-10-27 | -8 | Go-Live | Live - Operational | Met | 50 | 45427 | 7073 | FE-241
SITE-01808 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Raipur | VSAT | Branch | Local ISP Partner | 2025-06-20 |  | 374 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 82179 | 5252 | FE-274
SITE-01809 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Bilaspur | VSAT | Corporate Office | Sify Technologies | 2025-06-04 | 2025-06-01 | -3 | Go-Live | Live - Operational | Met | 50 | 77640 | 14305 | FE-365
SITE-01810 | PRJ-2024021 | CL003 | Central | Madhya Pradesh | Gwalior | VSAT | ATM/Off-site | Airtel Business | 2025-06-18 |  | 376 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 74291 | 6580 | FE-440
SITE-01811 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Bilaspur | VSAT | Data Center | Tata Communications | 2025-07-07 |  | 357 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 28400 | 10599 | FE-337
SITE-01812 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Raipur | VSAT | Warehouse/Ops Hub | Sify Technologies | 2025-11-05 | 2025-11-24 | 19 | Go-Live | Live - Operational | Breached | 10 | 82185 | 5309 | FE-247
SITE-01813 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Bilaspur | VSAT | Branch | Vodafone Idea Business | 2025-06-12 | 2025-06-20 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 104871 | 10945 | FE-278
SITE-01814 | PRJ-2024021 | CL003 | Central | Madhya Pradesh | Indore | VSAT | Corporate Office | Vodafone Idea Business | 2025-06-18 |  | 376 | Site Survey | Survey Scheduled | Breached | 50 | 63342 | 6128 | FE-345
SITE-01815 | PRJ-2024021 | CL003 | Central | Chhattisgarh | Bilaspur | VSAT | Data Center | Vodafone Idea Business | 2025-05-02 | 2025-05-07 | 5 | Go-Live | Live - Operational | Met | 10 | 100318 | 11850 | FE-428
SITE-01816 | PRJ-2024022 | CL005 | East | Odisha | Bhubaneswar | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-09-26 | 2025-10-09 | 13 | Go-Live | Live - Operational | Breached | 4 | 63626 | 17623 | FE-437
SITE-01817 | PRJ-2024022 | CL005 | East | Assam | Dibrugarh | SD-WAN | Branch | Excitel Enterprise | 2025-03-31 |  | 455 | Site Survey | Survey Complete | Breached | 4 | 59617 | 8133 | FE-229
SITE-01818 | PRJ-2024022 | CL005 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-10-31 |  | 241 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 110250 | 11643 | FE-370
SITE-01819 | PRJ-2024022 | CL005 | East | West Bengal | Kolkata | SD-WAN | Data Center | Excitel Enterprise | 2025-06-17 | 2025-07-12 | 25 | Go-Live | Live - Operational | Breached | 34 | 28191 | 11381 | FE-199
SITE-01820 | PRJ-2024022 | CL005 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Sify Technologies | 2025-06-12 |  | 382 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 104833 | 6768 | FE-421
SITE-01821 | PRJ-2024022 | CL005 | East | Jharkhand | Jamshedpur | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-07-01 | 2025-07-21 | 20 | Go-Live | Live - Operational | Breached | 10 | 70561 | 4250 | FE-272
SITE-01822 | PRJ-2024022 | CL005 | East | Bihar | Gaya | SD-WAN | Data Center | Airtel Business | 2025-08-09 | 2025-08-20 | 11 | Go-Live | Live - Operational | Breached | 50 | 101719 | 3769 | FE-453
SITE-01823 | PRJ-2024022 | CL005 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Airtel Business | 2025-11-10 |  | 231 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 33751 | 6858 | FE-339
SITE-01824 | PRJ-2024022 | CL005 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Local ISP Partner | 2025-09-16 | 2025-10-11 | 25 | Go-Live | Live - Operational | Breached | 6 | 56931 | 15591 | FE-209
SITE-01825 | PRJ-2024022 | CL005 | East | Odisha | Cuttack | SD-WAN | Branch | Excitel Enterprise | 2025-04-04 | 2025-04-10 | 6 | Go-Live | Live - Operational | Breached | 50 | 43765 | 8094 | FE-429
SITE-01826 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Excitel Enterprise | 2025-07-24 | 2025-08-04 | 11 | Go-Live | Live - Operational | Breached | 4 | 40256 | 16695 | FE-228
SITE-01827 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-10-30 | 2025-11-06 | 7 | Go-Live | Live - Operational | Breached | 2 | 92166 | 16886 | FE-210
SITE-01828 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-07-23 | 2025-08-14 | 22 | Go-Live | Live - Operational | Breached | 20 | 28012 | 10497 | FE-456
SITE-01829 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | ATM/Off-site | Tata Communications | 2025-11-20 |  | 221 | Site Survey | Survey Scheduled | Breached | 4 | 110209 | 12866 | FE-110
SITE-01830 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | ATM/Off-site | Local ISP Partner | 2026-01-27 | 2026-01-27 | 0 | Go-Live | Live - Operational | Met | 2 | 124002 | 6439 | FE-200
SITE-01831 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Branch | Local ISP Partner | 2025-09-14 | 2025-10-03 | 19 | Go-Live | Live - Operational | Breached | 100 | 57573 | 13635 | FE-168
SITE-01832 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | ATM/Off-site | Sify Technologies | 2026-02-19 |  | 130 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 118014 | 10574 | FE-178
SITE-01833 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Branch | Airtel Business | 2025-10-05 |  | 267 | Site Survey | Survey Scheduled | Breached | 34 | 32604 | 12233 | FE-189
SITE-01834 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Tata Communications | 2026-01-12 | 2026-01-12 | 0 | Go-Live | Live - Operational | Met | 6 | 82401 | 5276 | FE-322
SITE-01835 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-09-07 | 2025-09-30 | 23 | Go-Live | Live - Operational | Breached | 34 | 87382 | 6078 | FE-404
SITE-01836 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | ATM/Off-site | Excitel Enterprise | 2025-10-17 |  | 255 | Site Survey | Survey Scheduled | Breached | 100 | 64592 | 8672 | FE-233
SITE-01837 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Airtel Business | 2026-01-21 |  | 159 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 66736 | 9652 | FE-495
SITE-01838 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Tata Communications | 2026-02-09 | 2026-02-06 | -3 | Go-Live | Live - Operational | Met | 10 | 124600 | 14973 | FE-373
SITE-01839 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-10-10 |  | 262 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 34924 | 11986 | FE-192
SITE-01840 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-31 | 2025-08-24 | -7 | Go-Live | Live - Operational | Met | 4 | 59653 | 12331 | FE-382
SITE-01841 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Branch | Sify Technologies | 2025-11-15 |  | 226 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 71525 | 12493 | FE-169
SITE-01842 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Airtel Business | 2025-11-03 |  | 238 | Site Survey | Survey Scheduled | Breached | 10 | 119589 | 13924 | FE-145
SITE-01843 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Vodafone Idea Business | 2025-10-22 |  | 250 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 124697 | 15954 | FE-264
SITE-01844 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Tata Communications | 2025-09-09 |  | 293 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 128332 | 3688 | FE-499
SITE-01845 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Branch | Tata Communications | 2025-07-07 |  |  | ROW / Permission | Cancelled | N/A | 34 | 49616 | 15911 | FE-480
SITE-01846 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Data Center | Tata Communications | 2025-12-24 | 2025-12-26 | 2 | Go-Live | Live - Operational | Met | 100 | 130714 | 12331 | FE-431
SITE-01847 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Warehouse/Ops Hub | Tata Communications | 2026-01-08 |  | 172 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 74312 | 8625 | FE-294
SITE-01848 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Corporate Office | Sify Technologies | 2025-09-13 |  | 289 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 39146 | 12441 | FE-175
SITE-01849 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Airtel Business | 2025-11-03 | 2025-11-14 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 128037 | 8234 | FE-356
SITE-01850 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Excitel Enterprise | 2025-10-06 | 2025-10-16 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 89251 | 3930 | FE-122
SITE-01851 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-12-17 | 2025-12-23 | 6 | Go-Live | Live - Operational | Breached | 34 | 111449 | 9094 | FE-145
SITE-01852 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Vodafone Idea Business | 2025-08-08 |  | 325 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 58907 | 10266 | FE-176
SITE-01853 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Sify Technologies | 2025-10-03 | 2025-10-19 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 50313 | 16363 | FE-395
SITE-01854 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Branch | Local ISP Partner | 2025-12-30 |  | 181 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 34951 | 10163 | FE-206
SITE-01855 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-05 |  | 144 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 109014 | 9317 | FE-108
SITE-01856 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Corporate Office | Tata Communications | 2025-07-17 | 2025-07-10 | -7 | Go-Live | Live - Operational | Met | 4 | 79337 | 7642 | FE-370
SITE-01857 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Branch | Sify Technologies | 2026-01-06 |  | 174 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 112381 | 6407 | FE-380
SITE-01858 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Local ISP Partner | 2025-11-10 | 2025-11-12 | 2 | Go-Live | Live - Operational | Met | 10 | 97248 | 14112 | FE-132
SITE-01859 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Local ISP Partner | 2025-08-09 | 2025-08-03 | -6 | Go-Live | Live - Operational | Met | 50 | 109143 | 14606 | FE-251
SITE-01860 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Corporate Office | Vodafone Idea Business | 2025-12-13 |  | 198 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 48787 | 3839 | FE-224
SITE-01861 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-01 |  | 179 | Site Survey | Survey Complete | Breached | 10 | 41643 | 8572 | FE-498
SITE-01862 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Vodafone Idea Business | 2026-02-09 |  | 140 | Site Survey | Survey Scheduled | Breached | 20 | 110789 | 9887 | FE-180
SITE-01863 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-02-07 | 2026-02-03 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 122519 | 14571 | FE-288
SITE-01864 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Local ISP Partner | 2025-08-19 | 2025-09-06 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 89581 | 9681 | FE-257
SITE-01865 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-09 | 2025-11-22 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 129192 | 7200 | FE-474
SITE-01866 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-11-20 | 2025-12-12 | 22 | Go-Live | Live - Operational | Breached | 20 | 71457 | 15386 | FE-168
SITE-01867 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Tata Communications | 2025-12-24 |  | 187 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 118023 | 13970 | FE-129
SITE-01868 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | ATM/Off-site | Sify Technologies | 2026-02-20 | 2026-02-23 | 3 | Go-Live | Live - Operational | Met | 10 | 96971 | 7722 | FE-400
SITE-01869 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | ATM/Off-site | Airtel Business | 2026-01-03 |  | 177 | Site Survey | Survey Complete | Breached | 4 | 39804 | 5049 | FE-464
SITE-01870 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Excitel Enterprise | 2025-10-28 |  | 244 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 107489 | 6754 | FE-223
SITE-01871 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-12-21 |  | 190 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 45656 | 10135 | FE-429
SITE-01872 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Local ISP Partner | 2026-02-11 | 2026-02-27 | 16 | Go-Live | Live - Operational | Breached | 4 | 38992 | 15788 | FE-413
SITE-01873 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Data Center | Excitel Enterprise | 2025-10-08 | 2025-10-06 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 130093 | 12552 | FE-468
SITE-01874 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | ATM/Off-site | Tata Communications | 2026-02-19 | 2026-02-20 | 1 | Go-Live | Live - Operational | Met | 2 | 104820 | 5248 | FE-271
SITE-01875 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-02 |  | 331 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 60032 | 14778 | FE-293
SITE-01876 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Sify Technologies | 2025-12-27 |  | 184 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 106128 | 5461 | FE-471
SITE-01877 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-12-22 |  | 189 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 107920 | 16477 | FE-277
SITE-01878 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Branch | Excitel Enterprise | 2025-09-18 | 2025-09-12 | -6 | Go-Live | Live - Operational | Met | 20 | 42267 | 12334 | FE-249
SITE-01879 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Data Center | Sify Technologies | 2025-11-13 |  | 228 | Site Survey | Survey Complete | Breached | 2 | 104881 | 5782 | FE-487
SITE-01880 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Excitel Enterprise | 2026-01-25 | 2026-01-25 | 0 | Go-Live | Live - Operational | Met | 6 | 37633 | 7434 | FE-331
SITE-01881 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Branch | Sify Technologies | 2025-10-16 | 2025-10-13 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 119149 | 15722 | FE-474
SITE-01882 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Local ISP Partner | 2025-11-15 |  | 226 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 76081 | 13829 | FE-110
SITE-01883 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Vodafone Idea Business | 2025-10-10 |  | 262 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 96070 | 14865 | FE-149
SITE-01884 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Branch | Airtel Business | 2025-10-18 | 2025-10-09 | -9 | Go-Live | Live - Operational | Met | 2 | 96191 | 17998 | FE-204
SITE-01885 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Warehouse/Ops Hub | Tata Communications | 2026-02-12 |  | 137 | Site Survey | Survey Complete | Breached | 2 | 78631 | 6023 | FE-450
SITE-01886 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Branch | Airtel Business | 2026-01-07 | 2026-01-08 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 61295 | 9079 | FE-282
SITE-01887 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-11-18 |  | 223 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 91620 | 13762 | FE-348
SITE-01888 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-08-23 |  | 310 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 126259 | 4160 | FE-159
SITE-01889 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-07-02 |  | 362 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 72906 | 8389 | FE-221
SITE-01890 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Airtel Business | 2025-07-12 |  | 352 | Site Survey | Survey Complete | Breached | 34 | 108544 | 15359 | FE-163
SITE-01891 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Data Center | Local ISP Partner | 2025-10-03 |  | 269 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 107387 | 16971 | FE-124
SITE-01892 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Sify Technologies | 2025-11-26 |  | 215 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 103246 | 6478 | FE-108
SITE-01893 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-01-23 |  | 157 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 128483 | 13731 | FE-393
SITE-01894 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-12 |  | 199 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 39751 | 12055 | FE-251
SITE-01895 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Data Center | Local ISP Partner | 2025-11-26 |  | 215 | Site Survey | Survey Complete | Breached | 10 | 47258 | 8912 | FE-389
SITE-01896 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Corporate Office | Excitel Enterprise | 2026-01-14 | 2026-02-05 | 22 | Go-Live | Live - Operational | Breached | 10 | 50953 | 6619 | FE-155
SITE-01897 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Data Center | Vodafone Idea Business | 2026-01-16 | 2026-01-15 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 81453 | 13694 | FE-458
SITE-01898 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Data Center | Local ISP Partner | 2025-08-09 |  | 324 | Site Survey | Survey Scheduled | Breached | 4 | 87923 | 16013 | FE-313
SITE-01899 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | ATM/Off-site | Sify Technologies | 2025-08-14 |  | 319 | Site Survey | Survey Scheduled | Breached | 10 | 96156 | 13440 | FE-212
SITE-01900 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-09-01 |  | 301 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 65316 | 17066 | FE-101
SITE-01901 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | ATM/Off-site | Local ISP Partner | 2025-07-31 |  | 333 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 72740 | 3990 | FE-381
SITE-01902 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Corporate Office | Excitel Enterprise | 2026-01-12 |  | 168 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 84904 | 14328 | FE-236
SITE-01903 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Data Center | Sify Technologies | 2025-11-24 |  | 217 | Site Survey | Survey Complete | Breached | 50 | 110621 | 4692 | FE-210
SITE-01904 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Data Center | Tata Communications | 2026-01-24 |  | 156 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 128465 | 6617 | FE-370
SITE-01905 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Corporate Office | Vodafone Idea Business | 2025-09-03 | 2025-09-05 | 2 | Go-Live | Live - Operational | Met | 6 | 59536 | 13127 | FE-495
SITE-01906 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Branch | Tata Communications | 2026-02-16 |  | 133 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 90707 | 15826 | FE-214
SITE-01907 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-04 |  | 145 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 79024 | 4525 | FE-128
SITE-01908 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Branch | Tata Communications | 2025-08-21 |  | 312 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 134733 | 13525 | FE-271
SITE-01909 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Branch | Excitel Enterprise | 2025-10-05 | 2025-10-28 | 23 | Go-Live | Live - Operational | Breached | 20 | 38499 | 8301 | FE-422
SITE-01910 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Vodafone Idea Business | 2025-09-21 |  | 281 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 129404 | 6403 | FE-422
SITE-01911 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Data Center | Local ISP Partner | 2025-10-22 |  | 250 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 34592 | 15459 | FE-288
SITE-01912 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Data Center | Vodafone Idea Business | 2025-09-08 | 2025-09-03 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 106490 | 8112 | FE-300
SITE-01913 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Local ISP Partner | 2025-10-23 |  | 249 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 128003 | 17639 | FE-310
SITE-01914 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-09-27 | 2025-09-18 | -9 | Go-Live | Live - Operational | Met | 100 | 123025 | 13746 | FE-342
SITE-01915 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Tata Communications | 2025-11-22 | 2025-11-16 | -6 | Go-Live | Live - Operational | Met | 50 | 96679 | 14553 | FE-373
SITE-01916 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Airtel Business | 2025-08-20 | 2025-08-22 | 2 | Go-Live | Live - Operational | Met | 4 | 45388 | 8647 | FE-283
SITE-01917 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Branch | Vodafone Idea Business | 2026-02-20 | 2026-02-27 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 88850 | 3674 | FE-204
SITE-01918 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Branch | Vodafone Idea Business | 2025-07-21 | 2025-07-21 | 0 | Go-Live | Live - Operational | Met | 4 | 56687 | 15793 | FE-316
SITE-01919 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-09-20 |  | 282 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 99580 | 12895 | FE-276
SITE-01920 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Branch | Local ISP Partner | 2025-08-25 | 2025-09-12 | 18 | Go-Live | Live - Operational | Breached | 20 | 68251 | 7835 | FE-403
SITE-01921 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Branch | Airtel Business | 2026-02-07 | 2026-02-17 | 10 | Go-Live | Live - Operational | Breached | 50 | 66537 | 11860 | FE-122
SITE-01922 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-09-11 | 2025-09-07 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 117397 | 7598 | FE-152
SITE-01923 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-07-28 |  | 336 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 115461 | 11911 | FE-187
SITE-01924 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Branch | Vodafone Idea Business | 2026-01-30 | 2026-01-30 | 0 | Go-Live | Live - Operational | Met | 6 | 41413 | 13793 | FE-199
SITE-01925 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Corporate Office | Local ISP Partner | 2025-11-24 | 2025-12-18 | 24 | Go-Live | Live - Operational | Breached | 100 | 130812 | 15480 | FE-451
SITE-01926 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Excitel Enterprise | 2026-01-11 | 2026-01-28 | 17 | Go-Live | Live - Operational | Breached | 10 | 43071 | 17394 | FE-363
SITE-01927 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Data Center | Tata Communications | 2025-09-20 |  | 282 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 58003 | 12878 | FE-484
SITE-01928 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-18 |  | 162 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 80793 | 14653 | FE-160
SITE-01929 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Airtel Business | 2025-07-16 |  |  | BOM Finalization | Cancelled | N/A | 50 | 95931 | 16277 | FE-175
SITE-01930 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | ATM/Off-site | Tata Communications | 2025-10-05 | 2025-10-29 | 24 | Go-Live | Live - Operational | Breached | 6 | 51651 | 7168 | FE-422
SITE-01931 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Branch | Vodafone Idea Business | 2025-08-10 |  | 323 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 29944 | 16235 | FE-271
SITE-01932 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Data Center | Excitel Enterprise | 2025-12-23 | 2025-12-29 | 6 | Go-Live | Live - Operational | Breached | 6 | 124008 | 4693 | FE-367
SITE-01933 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Corporate Office | Excitel Enterprise | 2025-08-05 |  | 328 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 87863 | 15869 | FE-404
SITE-01934 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Corporate Office | Airtel Business | 2025-11-14 |  | 227 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 109715 | 13477 | FE-377
SITE-01935 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Corporate Office | Tata Communications | 2025-08-02 | 2025-07-25 | -8 | Go-Live | Live - Operational | Met | 10 | 114810 | 17291 | FE-377
SITE-01936 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Sify Technologies | 2025-09-13 |  | 289 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 124393 | 13489 | FE-362
SITE-01937 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Corporate Office | Sify Technologies | 2025-07-22 |  | 342 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 110059 | 12440 | FE-359
SITE-01938 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Branch | Sify Technologies | 2025-12-15 |  |  | BOM Finalization | Cancelled | N/A | 6 | 58838 | 12412 | FE-305
SITE-01939 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-08-20 |  | 313 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 31436 | 13585 | FE-331
SITE-01940 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Vodafone Idea Business | 2025-12-05 | 2025-11-29 | -6 | Go-Live | Live - Operational | Met | 100 | 78393 | 12379 | FE-176
SITE-01941 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Airtel Business | 2025-11-05 |  | 236 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 95648 | 12950 | FE-200
SITE-01942 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Local ISP Partner | 2025-11-14 |  | 227 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 80244 | 14043 | FE-195
SITE-01943 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Branch | Local ISP Partner | 2025-12-26 | 2026-01-02 | 7 | Go-Live | Live - Operational | Breached | 34 | 127033 | 9892 | FE-295
SITE-01944 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-10-25 |  | 247 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 116212 | 5545 | FE-185
SITE-01945 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Corporate Office | Sify Technologies | 2026-02-04 | 2026-02-10 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 96627 | 9941 | FE-335
SITE-01946 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-08-05 | 2025-08-17 | 12 | Go-Live | Live - Operational | Breached | 6 | 111663 | 7540 | FE-424
SITE-01947 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Warehouse/Ops Hub | Sify Technologies | 2026-01-06 |  | 174 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 57123 | 17693 | FE-199
SITE-01948 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Corporate Office | Tata Communications | 2025-10-12 | 2025-10-12 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 52458 | 12233 | FE-489
SITE-01949 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Airtel Business | 2026-02-19 | 2026-03-02 | 11 | Go-Live | Live - Operational | Breached | 6 | 80907 | 13152 | FE-213
SITE-01950 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Corporate Office | Tata Communications | 2025-12-03 |  | 208 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 94123 | 5240 | FE-386
SITE-01951 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Excitel Enterprise | 2025-07-07 |  | 357 | Site Survey | Survey Complete | Breached | 20 | 78630 | 17428 | FE-386
SITE-01952 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Local ISP Partner | 2025-09-21 |  | 281 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 62302 | 7173 | FE-103
SITE-01953 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Branch | Local ISP Partner | 2025-12-07 |  | 204 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 42836 | 11384 | FE-406
SITE-01954 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Excitel Enterprise | 2025-08-20 | 2025-09-12 | 23 | Go-Live | Live - Operational | Breached | 10 | 63275 | 16499 | FE-119
SITE-01955 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Branch | Sify Technologies | 2025-10-09 | 2025-10-18 | 9 | Go-Live | Live - Operational | Breached | 20 | 87464 | 5261 | FE-267
SITE-01956 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Corporate Office | Excitel Enterprise | 2025-08-25 | 2025-08-26 | 1 | Go-Live | Live - Operational | Met | 10 | 82982 | 11296 | FE-472
SITE-01957 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Data Center | Sify Technologies | 2026-01-21 | 2026-02-07 | 17 | Go-Live | Live - Operational | Breached | 2 | 30104 | 13670 | FE-236
SITE-01958 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Branch | Sify Technologies | 2026-01-22 |  | 158 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 32612 | 16219 | FE-281
SITE-01959 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-12-05 |  | 206 | Site Survey | Survey Complete | Breached | 100 | 101595 | 4485 | FE-409
SITE-01960 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | ATM/Off-site | Airtel Business | 2025-09-08 | 2025-09-21 | 13 | Go-Live | Live - Operational | Breached | 34 | 80716 | 6167 | FE-170
SITE-01961 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Corporate Office | Excitel Enterprise | 2025-07-15 |  | 349 | Site Survey | Survey Scheduled | Breached | 50 | 131847 | 15858 | FE-330
SITE-01962 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-09-15 | 2025-09-15 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 94874 | 9026 | FE-479
SITE-01963 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Sify Technologies | 2025-11-28 |  | 213 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 131233 | 15176 | FE-414
SITE-01964 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Corporate Office | Excitel Enterprise | 2025-08-02 |  | 331 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 38876 | 16810 | FE-454
SITE-01965 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Tata Communications | 2025-08-04 | 2025-07-25 | -10 | Go-Live | Live - Operational | Met | 6 | 133070 | 8527 | FE-290
SITE-01966 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | ATM/Off-site | Tata Communications | 2026-02-10 |  | 139 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 45187 | 14029 | FE-159
SITE-01967 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Corporate Office | Sify Technologies | 2025-08-23 | 2025-08-13 | -10 | Go-Live | Live - Operational | Met | 100 | 32428 | 12048 | FE-204
SITE-01968 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Sify Technologies | 2025-07-26 |  | 338 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 96132 | 12098 | FE-415
SITE-01969 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Airtel Business | 2025-12-06 |  | 205 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 118486 | 7138 | FE-316
SITE-01970 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Airtel Business | 2025-09-13 |  | 289 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 45004 | 9501 | FE-363
SITE-01971 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-08-23 | 2025-08-20 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 120742 | 12402 | FE-154
SITE-01972 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-08-02 | 2025-08-04 | 2 | Go-Live | Live - Operational | Met | 2 | 110170 | 8494 | FE-419
SITE-01973 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Branch | Tata Communications | 2026-01-06 |  | 174 | Site Survey | Survey Complete | Breached | 10 | 82443 | 7799 | FE-350
SITE-01974 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Data Center | Sify Technologies | 2025-11-19 |  | 222 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 97797 | 6204 | FE-492
SITE-01975 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Local ISP Partner | 2025-12-28 |  | 183 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 51192 | 16392 | FE-192
SITE-01976 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Corporate Office | Local ISP Partner | 2025-09-21 |  | 281 | Site Survey | Survey Scheduled | Breached | 34 | 101667 | 13784 | FE-236
SITE-01977 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-08-09 |  | 324 | Site Survey | Survey Complete | Breached | 34 | 46670 | 13635 | FE-146
SITE-01978 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Warehouse/Ops Hub | Airtel Business | 2026-02-16 |  | 133 | Site Survey | Survey Complete | Breached | 4 | 79445 | 4369 | FE-381
SITE-01979 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Data Center | Airtel Business | 2025-07-31 |  | 333 | Site Survey | Survey Scheduled | Breached | 4 | 87921 | 14763 | FE-210
SITE-01980 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | ATM/Off-site | Excitel Enterprise | 2026-01-03 |  | 177 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 31836 | 8838 | FE-193
SITE-01981 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-11-23 |  | 218 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 50438 | 5151 | FE-475
SITE-01982 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Tata Communications | 2026-02-04 |  | 145 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 58968 | 12562 | FE-381
SITE-01983 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Excitel Enterprise | 2025-09-22 | 2025-10-05 | 13 | Go-Live | Live - Operational | Breached | 10 | 69969 | 12608 | FE-257
SITE-01984 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Airtel Business | 2025-11-03 | 2025-11-22 | 19 | Go-Live | Live - Operational | Breached | 6 | 133937 | 9940 | FE-248
SITE-01985 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Corporate Office | Sify Technologies | 2025-09-24 |  | 278 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 108112 | 15222 | FE-471
SITE-01986 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-02 |  | 209 | Site Survey | Survey Scheduled | Breached | 2 | 52483 | 12855 | FE-189
SITE-01987 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Local ISP Partner | 2025-07-15 | 2025-07-26 | 11 | Go-Live | Live - Operational | Breached | 100 | 127581 | 12134 | FE-354
SITE-01988 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Corporate Office | Airtel Business | 2025-12-29 |  | 182 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 45126 | 5945 | FE-114
SITE-01989 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Branch | Excitel Enterprise | 2025-10-10 |  | 262 | Site Survey | Survey Complete | Breached | 10 | 50710 | 4116 | FE-122
SITE-01990 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Excitel Enterprise | 2026-01-24 |  | 156 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 73785 | 14700 | FE-207
SITE-01991 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Tata Communications | 2025-08-30 | 2025-09-23 | 24 | Go-Live | Live - Operational | Breached | 2 | 54475 | 3784 | FE-242
SITE-01992 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Excitel Enterprise | 2025-12-13 |  | 198 | Site Survey | Survey Complete | Breached | 34 | 42349 | 11040 | FE-134
SITE-01993 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Airtel Business | 2026-02-09 | 2026-02-04 | -5 | Go-Live | Live - Operational | Met | 6 | 130133 | 15456 | FE-400
SITE-01994 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Sify Technologies | 2025-09-16 | 2025-09-18 | 2 | Go-Live | Live - Operational | Met | 10 | 35430 | 13528 | FE-200
SITE-01995 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Branch | Airtel Business | 2025-10-29 |  | 243 | Site Survey | Survey Scheduled | Breached | 100 | 40180 | 13472 | FE-158
SITE-01996 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | ATM/Off-site | Tata Communications | 2025-12-10 | 2025-12-09 | -1 | Go-Live | Live - Operational | Met | 10 | 48631 | 5434 | FE-451
SITE-01997 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Tata Communications | 2026-01-09 |  | 171 | Site Survey | Survey Scheduled | Breached | 4 | 107408 | 16138 | FE-481
SITE-01998 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Branch | Airtel Business | 2025-10-06 | 2025-10-21 | 15 | Go-Live | Live - Operational | Breached | 6 | 33485 | 5481 | FE-416
SITE-01999 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-02 | 2026-01-13 | 11 | Go-Live | Live - Operational | Breached | 10 | 53945 | 13706 | FE-482
SITE-02000 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Data Center | Vodafone Idea Business | 2025-11-24 | 2025-11-25 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 55315 | 12284 | FE-106
SITE-02001 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Corporate Office | Excitel Enterprise | 2026-02-10 |  | 139 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 47612 | 16023 | FE-244
SITE-02002 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-09-11 | 2025-09-02 | -9 | Go-Live | Live - Operational | Met | 50 | 109965 | 12098 | FE-171
SITE-02003 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Corporate Office | Airtel Business | 2025-12-18 |  | 193 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 106161 | 8197 | FE-292
SITE-02004 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Corporate Office | Sify Technologies | 2025-08-19 |  | 314 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 131674 | 4581 | FE-479
SITE-02005 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-18 |  | 193 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 44803 | 16266 | FE-455
SITE-02006 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-01-15 | 2026-01-11 | -4 | Go-Live | Live - Operational | Met | 4 | 46596 | 8013 | FE-197
SITE-02007 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-09-22 |  | 280 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 68231 | 15993 | FE-166
SITE-02008 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Branch | Airtel Business | 2025-07-20 | 2025-07-19 | -1 | Go-Live | Live - Operational | Met | 100 | 35053 | 10421 | FE-163
SITE-02009 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-08-29 |  | 304 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 35904 | 6225 | FE-406
SITE-02010 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Vodafone Idea Business | 2026-01-01 |  | 179 | Site Survey | Survey Scheduled | Breached | 50 | 105438 | 3866 | FE-311
SITE-02011 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2026-02-06 | 2026-02-14 | 8 | Go-Live | Live - Operational | Breached | 4 | 72877 | 8733 | FE-233
SITE-02012 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Branch | Airtel Business | 2025-12-12 |  | 199 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 32244 | 7591 | FE-130
SITE-02013 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Data Center | Vodafone Idea Business | 2025-10-01 |  | 271 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 76308 | 10433 | FE-257
SITE-02014 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-10-22 |  | 250 | Site Survey | Survey Complete | Breached | 34 | 76754 | 8170 | FE-317
SITE-02015 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Sify Technologies | 2025-10-31 | 2025-10-27 | -4 | Go-Live | Live - Operational | Met | 100 | 84909 | 3544 | FE-156
SITE-02016 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Warehouse/Ops Hub | Tata Communications | 2026-01-13 | 2026-01-10 | -3 | Go-Live | Live - Operational | Met | 2 | 55160 | 3936 | FE-477
SITE-02017 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Tata Communications | 2025-10-24 | 2025-11-08 | 15 | Go-Live | Live - Operational | Breached | 100 | 49217 | 10443 | FE-364
SITE-02018 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Corporate Office | Vodafone Idea Business | 2025-11-10 | 2025-11-06 | -4 | Go-Live | Live - Operational | Met | 4 | 47415 | 13211 | FE-115
SITE-02019 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Data Center | Tata Communications | 2025-07-16 |  | 348 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 94632 | 4195 | FE-309
SITE-02020 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Sify Technologies | 2025-07-14 | 2025-08-02 | 19 | Go-Live | Live - Operational | Breached | 4 | 34265 | 16820 | FE-247
SITE-02021 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-09-15 |  | 287 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 42969 | 15035 | FE-200
SITE-02022 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | ATM/Off-site | Sify Technologies | 2025-10-20 |  | 252 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 86565 | 10478 | FE-460
SITE-02023 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Tata Communications | 2025-07-08 |  | 356 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 71746 | 6759 | FE-443
SITE-02024 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Data Center | Sify Technologies | 2025-08-10 |  | 323 | Site Survey | Survey Complete | Breached | 50 | 79593 | 10656 | FE-176
SITE-02025 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-07-17 |  | 347 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 119681 | 17487 | FE-343
SITE-02026 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Data Center | Vodafone Idea Business | 2025-09-07 | 2025-09-22 | 15 | Go-Live | Live - Operational | Breached | 4 | 68711 | 8912 | FE-420
SITE-02027 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Vodafone Idea Business | 2026-01-20 | 2026-01-17 | -3 | Go-Live | Live - Operational | Met | 100 | 115364 | 11157 | FE-163
SITE-02028 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Warehouse/Ops Hub | Airtel Business | 2026-01-08 | 2026-01-14 | 6 | Go-Live | Live - Operational | Breached | 4 | 121703 | 12722 | FE-487
SITE-02029 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Sify Technologies | 2025-09-02 | 2025-09-18 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 33543 | 7686 | FE-412
SITE-02030 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-09-15 |  | 287 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 130672 | 13430 | FE-370
SITE-02031 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-07-17 |  | 347 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 117804 | 5470 | FE-312
SITE-02032 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Airtel Business | 2025-10-14 | 2025-10-28 | 14 | Go-Live | Live - Operational | Breached | 10 | 91564 | 8196 | FE-125
SITE-02033 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Airtel Business | 2025-09-07 |  | 295 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 127902 | 8780 | FE-323
SITE-02034 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-12-24 |  | 187 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 104397 | 12813 | FE-158
SITE-02035 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-07-18 | 2025-07-24 | 6 | Go-Live | Live - Operational | Breached | 6 | 31448 | 7011 | FE-339
SITE-02036 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Warehouse/Ops Hub | Airtel Business | 2026-01-26 |  | 154 | Site Survey | Survey Scheduled | Breached | 4 | 39668 | 10229 | FE-128
SITE-02037 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Branch | Local ISP Partner | 2025-12-16 |  | 195 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 40462 | 17420 | FE-379
SITE-02038 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-23 |  | 188 | Site Survey | Survey Complete | Breached | 100 | 47215 | 5334 | FE-142
SITE-02039 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-31 |  | 149 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 114702 | 11826 | FE-115
SITE-02040 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Corporate Office | Sify Technologies | 2026-02-14 |  | 135 | Site Survey | Survey Complete | Breached | 6 | 49065 | 15916 | FE-161
SITE-02041 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Excitel Enterprise | 2025-11-09 |  | 232 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 94433 | 9624 | FE-324
SITE-02042 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Corporate Office | Excitel Enterprise | 2025-07-16 | 2025-07-07 | -9 | Go-Live | Live - Operational | Met | 2 | 82891 | 11271 | FE-263
SITE-02043 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Data Center | Excitel Enterprise | 2026-02-01 | 2026-02-03 | 2 | Go-Live | Live - Operational | Met | 4 | 67263 | 13259 | FE-306
SITE-02044 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | ATM/Off-site | Excitel Enterprise | 2025-07-22 |  | 342 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 116387 | 16888 | FE-402
SITE-02045 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Excitel Enterprise | 2025-12-19 |  | 192 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 88733 | 15398 | FE-485
SITE-02046 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Sify Technologies | 2025-12-10 |  | 201 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 105180 | 9310 | FE-217
SITE-02047 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Branch | Sify Technologies | 2026-01-19 | 2026-02-05 | 17 | Go-Live | Live - Operational | Breached | 50 | 33769 | 11599 | FE-382
SITE-02048 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-09-11 |  | 291 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 71687 | 15343 | FE-293
SITE-02049 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Airtel Business | 2025-11-26 |  | 215 | Site Survey | Survey Scheduled | Breached | 20 | 111885 | 4240 | FE-409
SITE-02050 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Excitel Enterprise | 2025-10-05 |  | 267 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 122418 | 7838 | FE-413
SITE-02051 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Airtel Business | 2025-10-24 | 2025-11-15 | 22 | Go-Live | Live - Operational | Breached | 4 | 86188 | 3690 | FE-178
SITE-02052 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Sify Technologies | 2025-10-07 | 2025-10-06 | -1 | Go-Live | Live - Operational | Met | 10 | 110616 | 10162 | FE-240
SITE-02053 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Corporate Office | Excitel Enterprise | 2025-11-06 | 2025-11-10 | 4 | Go-Live | Live - Operational | Met | 50 | 97822 | 14914 | FE-356
SITE-02054 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | ATM/Off-site | Sify Technologies | 2026-02-11 | 2026-02-28 | 17 | Go-Live | Live - Operational | Breached | 50 | 90852 | 5979 | FE-485
SITE-02055 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Vodafone Idea Business | 2025-11-25 |  | 216 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 109689 | 17148 | FE-132
SITE-02056 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-08-24 | 2025-08-21 | -3 | Go-Live | Live - Operational | Met | 10 | 74890 | 14332 | FE-486
SITE-02057 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Airtel Business | 2025-12-30 | 2026-01-15 | 16 | Go-Live | Live - Operational | Breached | 10 | 90273 | 15291 | FE-308
SITE-02058 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | Corporate Office | Sify Technologies | 2025-09-02 | 2025-08-25 | -8 | Go-Live | Live - Operational | Met | 4 | 80508 | 8946 | FE-499
SITE-02059 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Corporate Office | Sify Technologies | 2026-02-18 |  | 131 | Site Survey | Survey Complete | Breached | 100 | 46958 | 7795 | FE-163
SITE-02060 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Airtel Business | 2025-09-20 |  | 282 | Site Survey | Survey Scheduled | Breached | 20 | 63861 | 3962 | FE-390
SITE-02061 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Excitel Enterprise | 2025-10-29 | 2025-11-18 | 20 | Go-Live | Live - Operational | Breached | 6 | 119775 | 7738 | FE-404
SITE-02062 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Vodafone Idea Business | 2025-11-16 |  | 225 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 100240 | 5883 | FE-149
SITE-02063 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Excitel Enterprise | 2025-09-08 |  | 294 | Site Survey | Survey Scheduled | Breached | 4 | 131189 | 7210 | FE-267
SITE-02064 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Data Center | Sify Technologies | 2025-12-08 |  | 203 | Site Survey | Survey Complete | Breached | 50 | 108801 | 14365 | FE-375
SITE-02065 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-26 |  |  | BOM Finalization | Cancelled | N/A | 100 | 68844 | 11802 | FE-295
SITE-02066 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Corporate Office | Sify Technologies | 2026-02-14 |  |  | Site Survey | Cancelled | N/A | 20 | 69098 | 16665 | FE-437
SITE-02067 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-12-05 | 2025-12-03 | -2 | Go-Live | Live - Operational | Met | 6 | 35679 | 17341 | FE-451
SITE-02068 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Sify Technologies | 2025-12-26 | 2026-01-09 | 14 | Go-Live | Live - Operational | Breached | 4 | 37225 | 11273 | FE-140
SITE-02069 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-30 | 2026-02-23 | 24 | Go-Live | Live - Operational | Breached | 10 | 83213 | 8650 | FE-227
SITE-02070 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Sify Technologies | 2025-11-09 | 2025-11-15 | 6 | Go-Live | Live - Operational | Breached | 2 | 77674 | 11454 | FE-103
SITE-02071 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-12-15 |  | 196 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 67152 | 12189 | FE-397
SITE-02072 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Local ISP Partner | 2025-09-14 | 2025-09-28 | 14 | Go-Live | Live - Operational | Breached | 20 | 130959 | 15633 | FE-385
SITE-02073 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Data Center | Tata Communications | 2025-11-05 |  | 236 | Site Survey | Survey Scheduled | Breached | 34 | 131439 | 10640 | FE-234
SITE-02074 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Corporate Office | Vodafone Idea Business | 2025-09-19 | 2025-09-27 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 72553 | 12306 | FE-114
SITE-02075 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Airtel Business | 2026-01-13 | 2026-01-18 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 83725 | 5643 | FE-224
SITE-02076 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Data Center | Airtel Business | 2026-02-10 |  | 139 | Site Survey | Survey Complete | Breached | 6 | 128981 | 10360 | FE-272
SITE-02077 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-10-10 | 2025-10-21 | 11 | Go-Live | Live - Operational | Breached | 34 | 58002 | 4379 | FE-104
SITE-02078 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Sify Technologies | 2025-07-31 | 2025-08-01 | 1 | Go-Live | Live - Operational | Met | 6 | 127881 | 16577 | FE-331
SITE-02079 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Corporate Office | Vodafone Idea Business | 2025-12-16 |  |  | BOM Finalization | Cancelled | N/A | 6 | 128113 | 8677 | FE-413
SITE-02080 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | ATM/Off-site | Sify Technologies | 2025-07-27 | 2025-07-22 | -5 | Go-Live | Live - Operational | Met | 4 | 40097 | 9603 | FE-357
SITE-02081 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Branch | Tata Communications | 2025-07-02 | 2025-07-26 | 24 | Go-Live | Live - Operational | Breached | 100 | 105176 | 11958 | FE-302
SITE-02082 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Tata Communications | 2025-08-02 |  | 331 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 103738 | 13257 | FE-283
SITE-02083 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Data Center | Sify Technologies | 2025-10-23 | 2025-10-21 | -2 | Go-Live | Live - Operational | Met | 6 | 111701 | 16803 | FE-317
SITE-02084 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | ATM/Off-site | Tata Communications | 2025-07-29 |  | 335 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 97305 | 7616 | FE-217
SITE-02085 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Local ISP Partner | 2025-10-19 | 2025-10-31 | 12 | Go-Live | Live - Operational | Breached | 50 | 126639 | 12221 | FE-124
SITE-02086 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Corporate Office | Sify Technologies | 2025-08-13 |  | 320 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 68601 | 5595 | FE-163
SITE-02087 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Corporate Office | Sify Technologies | 2025-09-22 |  | 280 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 34179 | 4015 | FE-446
SITE-02088 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Corporate Office | Local ISP Partner | 2025-12-15 | 2025-12-21 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 72373 | 15620 | FE-174
SITE-02089 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Local ISP Partner | 2025-08-05 | 2025-08-07 | 2 | Go-Live | Live - Operational | Met | 100 | 65416 | 16111 | FE-375
SITE-02090 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Vodafone Idea Business | 2025-12-06 |  | 205 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 129391 | 10023 | FE-491
SITE-02091 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-09-14 |  | 288 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 32024 | 6639 | FE-384
SITE-02092 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Vodafone Idea Business | 2025-08-13 |  | 320 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 121613 | 3706 | FE-435
SITE-02093 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | ATM/Off-site | Tata Communications | 2025-12-03 | 2025-12-17 | 14 | Go-Live | Live - Operational | Breached | 20 | 71116 | 15210 | FE-425
SITE-02094 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | ATM/Off-site | Sify Technologies | 2025-12-03 |  | 208 | Site Survey | Survey Complete | Breached | 6 | 62965 | 13725 | FE-217
SITE-02095 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Branch | Excitel Enterprise | 2025-07-04 | 2025-06-30 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 121736 | 17796 | FE-302
SITE-02096 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-09-12 |  | 290 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 73264 | 6322 | FE-242
SITE-02097 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Corporate Office | Sify Technologies | 2025-10-01 |  | 271 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 35010 | 17030 | FE-372
SITE-02098 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Branch | Vodafone Idea Business | 2025-12-24 |  | 187 | Site Survey | Survey Complete | Breached | 10 | 87026 | 15043 | FE-382
SITE-02099 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Corporate Office | Airtel Business | 2025-12-23 |  | 188 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 47278 | 12292 | FE-333
SITE-02100 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Data Center | Excitel Enterprise | 2026-01-05 |  | 175 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 104850 | 12145 | FE-363
SITE-02101 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Corporate Office | Sify Technologies | 2025-07-16 |  | 348 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 103861 | 15019 | FE-168
SITE-02102 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Sify Technologies | 2026-01-31 | 2026-02-09 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 58480 | 4096 | FE-145
SITE-02103 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | ATM/Off-site | Sify Technologies | 2025-09-03 |  | 299 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 54703 | 17125 | FE-385
SITE-02104 | PRJ-2024023 | CL007 | East | Odisha | Rourkela | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-08-11 |  | 322 | Site Survey | Survey Scheduled | Breached | 10 | 102450 | 16481 | FE-152
SITE-02105 | PRJ-2024023 | CL007 | East | Odisha | Bhubaneswar | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-16 |  | 195 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 79366 | 16884 | FE-180
SITE-02106 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Branch | Local ISP Partner | 2025-11-10 | 2025-12-02 | 22 | Go-Live | Live - Operational | Breached | 10 | 49991 | 5887 | FE-162
SITE-02107 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | ATM/Off-site | Tata Communications | 2025-08-17 | 2025-08-21 | 4 | Go-Live | Live - Operational | Met | 2 | 36261 | 14832 | FE-367
SITE-02108 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Tata Communications | 2025-10-06 |  | 266 | Site Survey | Survey Scheduled | Breached | 2 | 94574 | 17283 | FE-423
SITE-02109 | PRJ-2024023 | CL007 | East | Assam | Dibrugarh | MPLS | Branch | Tata Communications | 2025-10-07 |  | 265 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 66728 | 6602 | FE-290
SITE-02110 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Excitel Enterprise | 2025-07-16 | 2025-08-03 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 69854 | 14147 | FE-224
SITE-02111 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Branch | Vodafone Idea Business | 2026-01-10 |  | 170 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 83199 | 16329 | FE-484
SITE-02112 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Data Center | Excitel Enterprise | 2025-09-19 | 2025-09-28 | 9 | Go-Live | Live - Operational | Breached | 34 | 116641 | 16445 | FE-150
SITE-02113 | PRJ-2024023 | CL007 | East | West Bengal | Kolkata | MPLS | Data Center | Vodafone Idea Business | 2026-01-04 | 2025-12-26 | -9 | Go-Live | Live - Operational | Met | 6 | 28459 | 9563 | FE-242
SITE-02114 | PRJ-2024023 | CL007 | East | Bihar | Gaya | MPLS | Branch | Sify Technologies | 2026-01-30 |  | 150 | Site Survey | Survey Scheduled | Breached | 2 | 118312 | 4254 | FE-323
SITE-02115 | PRJ-2024023 | CL007 | East | Jharkhand | Jamshedpur | MPLS | Branch | Tata Communications | 2025-09-07 |  | 295 | Site Survey | Survey Scheduled | Breached | 2 | 112843 | 9938 | FE-289
SITE-02116 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | ATM/Off-site | Sify Technologies | 2025-07-24 |  | 340 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 133875 | 10823 | FE-377
SITE-02117 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-12-05 |  | 206 | Site Survey | Survey Complete | Breached | 100 | 33499 | 12065 | FE-414
SITE-02118 | PRJ-2024023 | CL007 | East | West Bengal | Howrah | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-01-11 |  | 169 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 99858 | 6814 | FE-250
SITE-02119 | PRJ-2024023 | CL007 | East | Assam | Guwahati | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-14 |  | 227 | Site Survey | Survey Complete | Breached | 50 | 48880 | 9863 | FE-410
SITE-02120 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-08-29 |  | 304 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 89928 | 12169 | FE-449
SITE-02121 | PRJ-2024023 | CL007 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Excitel Enterprise | 2025-07-08 |  | 356 | Site Survey | Survey Complete | Breached | 50 | 51672 | 9447 | FE-332
SITE-02122 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | Data Center | Tata Communications | 2026-02-15 |  | 134 | Site Survey | Survey Scheduled | Breached | 10 | 44581 | 3864 | FE-144
SITE-02123 | PRJ-2024023 | CL007 | East | Odisha | Cuttack | MPLS | Data Center | Local ISP Partner | 2026-01-12 |  |  | BOM Finalization | Cancelled | N/A | 6 | 77825 | 3740 | FE-254
SITE-02124 | PRJ-2024023 | CL007 | East | West Bengal | Siliguri | MPLS | ATM/Off-site | Tata Communications | 2026-01-11 | 2026-01-24 | 13 | Go-Live | Live - Operational | Breached | 100 | 75344 | 8998 | FE-361
SITE-02125 | PRJ-2024023 | CL007 | East | Bihar | Patna | MPLS | Data Center | Sify Technologies | 2025-11-02 |  | 239 | Site Survey | Survey Scheduled | Breached | 4 | 115944 | 15754 | FE-170
SITE-02126 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Tata Communications | 2026-05-19 |  | 41 | Site Survey | Survey Complete | Breached | 4 | 99016 | 14526 | FE-430
SITE-02127 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-08 | 2026-01-22 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 85113 | 7862 | FE-190
SITE-02128 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Corporate Office | Excitel Enterprise | 2026-04-17 |  | 73 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 86887 | 4374 | FE-462
SITE-02129 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Branch | Excitel Enterprise | 2026-08-07 | 2026-08-05 | -2 | Go-Live | Live - Operational | Met | 34 | 117262 | 8311 | FE-290
SITE-02130 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-04-06 | 2026-04-25 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 103756 | 5818 | FE-164
SITE-02131 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Branch | Tata Communications | 2026-06-15 | 2026-06-06 | -9 | Go-Live | Live - Operational | Met | 50 | 56777 | 15036 | FE-275
SITE-02132 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Airtel Business | 2026-04-12 | 2026-04-12 | 0 | Go-Live | Live - Operational | Met | 20 | 89604 | 6410 | FE-357
SITE-02133 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Corporate Office | Tata Communications | 2026-07-30 |  | 0 | BOM Finalization | Delayed - Vendor Issue | On Track | 2 | 39660 | 11454 | FE-366
SITE-02134 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Data Center | Airtel Business | 2026-06-10 | 2026-06-16 | 6 | Go-Live | Live - Operational | Breached | 4 | 45858 | 10376 | FE-137
SITE-02135 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Data Center | Tata Communications | 2025-12-17 |  | 194 | Site Survey | Survey Complete | Breached | 2 | 131062 | 9257 | FE-387
SITE-02136 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Branch | Excitel Enterprise | 2026-05-12 | 2026-05-25 | 13 | Go-Live | Live - Operational | Breached | 6 | 88794 | 16726 | FE-155
SITE-02137 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Branch | Local ISP Partner | 2026-04-04 | 2026-03-30 | -5 | Go-Live | Live - Operational | Met | 34 | 57807 | 16884 | FE-325
SITE-02138 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Branch | Vodafone Idea Business | 2026-02-05 | 2026-01-28 | -8 | Go-Live | Live - Operational | Met | 4 | 134124 | 10548 | FE-403
SITE-02139 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Excitel Enterprise | 2026-04-18 | 2026-04-24 | 6 | Go-Live | Live - Operational | Breached | 20 | 101632 | 15155 | FE-267
SITE-02140 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-21 |  | 159 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 82159 | 13217 | FE-384
SITE-02141 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-03-14 |  | 107 | Site Survey | Survey Complete | Breached | 20 | 64572 | 11236 | FE-492
SITE-02142 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-01-07 |  | 173 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 90145 | 6812 | FE-259
SITE-02143 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Branch | Sify Technologies | 2026-08-03 | 2026-07-28 | -6 | Go-Live | Live - Operational | Met | 34 | 33951 | 6018 | FE-280
SITE-02144 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | ATM/Off-site | Local ISP Partner | 2026-03-29 |  | 92 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 37007 | 11172 | FE-251
SITE-02145 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-02-19 |  | 130 | Site Survey | Survey Scheduled | Breached | 34 | 47842 | 10392 | FE-371
SITE-02146 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Branch | Local ISP Partner | 2026-05-04 | 2026-05-21 | 17 | Go-Live | Live - Operational | Breached | 50 | 86694 | 6674 | FE-401
SITE-02147 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Corporate Office | Excitel Enterprise | 2026-02-18 |  | 131 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 99717 | 8474 | FE-190
SITE-02148 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Vodafone Idea Business | 2026-08-08 |  | 0 | Site Survey | Survey Complete | On Track | 6 | 98804 | 4277 | FE-269
SITE-02149 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Data Center | Sify Technologies | 2026-07-12 |  | 0 | Site Survey | Survey Scheduled | On Track | 2 | 79573 | 9399 | FE-329
SITE-02150 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Corporate Office | Vodafone Idea Business | 2026-01-05 |  | 175 | Site Survey | Survey Complete | Breached | 6 | 54999 | 12749 | FE-193
SITE-02151 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Corporate Office | Tata Communications | 2026-05-03 | 2026-05-14 | 11 | Go-Live | Live - Operational | Breached | 2 | 92668 | 13804 | FE-458
SITE-02152 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Airtel Business | 2026-05-18 |  | 42 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 38922 | 5140 | FE-336
SITE-02153 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Sify Technologies | 2026-05-18 | 2026-05-09 | -9 | Go-Live | Live - Operational | Met | 20 | 120295 | 10793 | FE-449
SITE-02154 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | ATM/Off-site | Airtel Business | 2026-06-13 |  | 16 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 81231 | 15248 | FE-417
SITE-02155 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Local ISP Partner | 2026-07-13 | 2026-07-16 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 28085 | 4854 | FE-441
SITE-02156 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Corporate Office | Excitel Enterprise | 2026-08-03 |  | 0 | Site Survey | Survey Scheduled | On Track | 34 | 35801 | 3673 | FE-180
SITE-02157 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Branch | Sify Technologies | 2026-01-05 | 2026-01-15 | 10 | Go-Live | Live - Operational | Breached | 10 | 122302 | 6499 | FE-277
SITE-02158 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-05-27 |  | 33 | Site Survey | Survey Scheduled | Breached | 2 | 85417 | 8128 | FE-122
SITE-02159 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | ATM/Off-site | Airtel Business | 2026-06-14 |  | 15 | Site Survey | Survey Scheduled | Breached | 100 | 105982 | 12523 | FE-125
SITE-02160 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Local ISP Partner | 2025-12-23 |  | 188 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 34310 | 3659 | FE-301
SITE-02161 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Airtel Business | 2026-07-01 | 2026-07-19 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 28393 | 8045 | FE-278
SITE-02162 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-04-04 | 2026-03-27 | -8 | Go-Live | Live - Operational | Met | 20 | 36442 | 4679 | FE-377
SITE-02163 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-06-01 | 2026-06-12 | 11 | Go-Live | Live - Operational | Breached | 6 | 99492 | 9384 | FE-277
SITE-02164 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Corporate Office | Airtel Business | 2026-05-10 |  | 50 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 75362 | 9855 | FE-136
SITE-02165 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-04-19 |  | 71 | Site Survey | Survey Complete | Breached | 2 | 112426 | 3814 | FE-303
SITE-02166 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Excitel Enterprise | 2025-12-31 |  | 180 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 121995 | 10696 | FE-344
SITE-02167 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Data Center | Excitel Enterprise | 2026-08-02 |  |  | Site Survey | Cancelled | N/A | 20 | 119014 | 14644 | FE-164
SITE-02168 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Corporate Office | Sify Technologies | 2026-07-21 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 34 | 57494 | 3836 | FE-101
SITE-02169 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Sify Technologies | 2026-03-22 |  | 99 | Site Survey | Survey Scheduled | Breached | 34 | 29055 | 7071 | FE-182
SITE-02170 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Data Center | Sify Technologies | 2026-04-21 | 2026-04-24 | 3 | Go-Live | Live - Operational | Met | 20 | 45040 | 9908 | FE-194
SITE-02171 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Airtel Business | 2026-05-02 |  | 58 | Site Survey | Survey Scheduled | Breached | 2 | 110278 | 6560 | FE-438
SITE-02172 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Sify Technologies | 2026-02-10 | 2026-02-14 | 4 | Go-Live | Live - Operational | Met | 4 | 37141 | 3749 | FE-477
SITE-02173 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Branch | Sify Technologies | 2026-05-29 | 2026-06-14 | 16 | Go-Live | Live - Operational | Breached | 10 | 28736 | 13939 | FE-491
SITE-02174 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Airtel Business | 2026-04-25 |  | 65 | Site Survey | Survey Complete | Breached | 2 | 47853 | 5411 | FE-145
SITE-02175 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-02-10 |  | 139 | Site Survey | Survey Scheduled | Breached | 2 | 64908 | 14613 | FE-271
SITE-02176 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-05-07 |  | 53 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 102133 | 17601 | FE-195
SITE-02177 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-06-22 |  | 7 | Last Mile Provisioning | Last Mile - ROW Pending | At Risk | 20 | 49952 | 9975 | FE-123
SITE-02178 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | ATM/Off-site | Tata Communications | 2026-06-05 |  | 24 | Site Survey | Survey Scheduled | Breached | 6 | 87975 | 9562 | FE-281
SITE-02179 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Data Center | Tata Communications | 2026-02-19 | 2026-03-10 | 19 | Go-Live | Live - Operational | Breached | 6 | 28143 | 10789 | FE-158
SITE-02180 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Branch | Airtel Business | 2026-02-11 | 2026-03-08 | 25 | Go-Live | Live - Operational | Breached | 10 | 84550 | 14975 | FE-186
SITE-02181 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | ATM/Off-site | Tata Communications | 2026-06-19 |  | 10 | Last Mile Provisioning | Last Mile - ROW Pending | At Risk | 34 | 96738 | 16372 | FE-163
SITE-02182 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Branch | Local ISP Partner | 2026-06-19 |  | 10 | Equipment Dispatch | Equipment Dispatched | At Risk | 34 | 102126 | 5047 | FE-322
SITE-02183 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-04-06 |  | 84 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 71557 | 12515 | FE-381
SITE-02184 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Corporate Office | Excitel Enterprise | 2026-07-29 |  | 0 | Last Mile Provisioning | Last Mile - ROW Pending | On Track | 100 | 118474 | 11207 | FE-185
SITE-02185 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Branch | Local ISP Partner | 2026-04-27 |  | 63 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 126358 | 16166 | FE-273
SITE-02186 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-06-29 |  | 0 | Equipment Dispatch | Equipment Dispatched | On Track | 4 | 99760 | 9651 | FE-411
SITE-02187 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Sify Technologies | 2026-07-09 | 2026-07-31 | 22 | Go-Live | Live - Operational | Breached | 20 | 35001 | 14270 | FE-149
SITE-02188 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | ATM/Off-site | Tata Communications | 2026-06-18 | 2026-07-08 | 20 | Go-Live | Live - Operational | Breached | 2 | 51282 | 12530 | FE-209
SITE-02189 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Airtel Business | 2026-01-17 |  | 163 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 35754 | 7628 | FE-145
SITE-02190 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Local ISP Partner | 2026-02-25 |  | 124 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 126213 | 17594 | FE-368
SITE-02191 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-03-18 |  | 103 | Site Survey | Survey Scheduled | Breached | 10 | 119894 | 3667 | FE-444
SITE-02192 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Sify Technologies | 2025-12-25 | 2025-12-28 | 3 | Go-Live | Live - Operational | Met | 6 | 56707 | 17465 | FE-167
SITE-02193 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | ATM/Off-site | Local ISP Partner | 2026-03-17 |  | 104 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 59942 | 9610 | FE-467
SITE-02194 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Data Center | Sify Technologies | 2026-04-23 | 2026-04-18 | -5 | Go-Live | Live - Operational | Met | 2 | 81367 | 7652 | FE-302
SITE-02195 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Sify Technologies | 2026-07-15 |  | 0 | ROW / Permission | On Hold - Client Site Not Ready | On Track | 10 | 85667 | 10986 | FE-335
SITE-02196 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-09 |  | 171 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 45304 | 16081 | FE-136
SITE-02197 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Local ISP Partner | 2026-05-18 | 2026-05-13 | -5 | Go-Live | Live - Operational | Met | 4 | 89561 | 8391 | FE-293
SITE-02198 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | ATM/Off-site | Tata Communications | 2026-05-14 | 2026-06-06 | 23 | Go-Live | Live - Operational | Breached | 2 | 62559 | 7562 | FE-479
SITE-02199 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Data Center | Airtel Business | 2026-05-23 | 2026-06-06 | 14 | Go-Live | Live - Operational | Breached | 6 | 102381 | 4829 | FE-203
SITE-02200 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-12-19 |  | 192 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 81197 | 12628 | FE-288
SITE-02201 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Branch | Vodafone Idea Business | 2026-06-26 |  | 3 | Site Survey | Survey Scheduled | At Risk | 10 | 119806 | 9955 | FE-178
SITE-02202 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Sify Technologies | 2026-07-09 |  | 0 | Equipment Dispatch | Equipment Dispatched | On Track | 34 | 35922 | 8467 | FE-397
SITE-02203 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Data Center | Vodafone Idea Business | 2026-06-01 | 2026-05-28 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 53735 | 14720 | FE-256
SITE-02204 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-11 |  | 138 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 29118 | 8452 | FE-431
SITE-02205 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Airtel Business | 2026-04-11 | 2026-04-13 | 2 | Go-Live | Live - Operational | Met | 50 | 45654 | 10608 | FE-160
SITE-02206 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Local ISP Partner | 2026-02-19 | 2026-02-22 | 3 | Go-Live | Live - Operational | Met | 6 | 124841 | 9128 | FE-435
SITE-02207 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | ATM/Off-site | Tata Communications | 2026-02-22 | 2026-03-10 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 97966 | 15541 | FE-352
SITE-02208 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-10 |  | 170 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 111816 | 7433 | FE-470
SITE-02209 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-05-18 |  | 42 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 62559 | 7114 | FE-202
SITE-02210 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Corporate Office | Vodafone Idea Business | 2026-07-31 | 2026-07-29 | -2 | Go-Live | Live - Operational | Met | 6 | 75924 | 14423 | FE-129
SITE-02211 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Tata Communications | 2026-02-16 | 2026-02-22 | 6 | Go-Live | Live - Operational | Breached | 10 | 38164 | 4789 | FE-461
SITE-02212 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Corporate Office | Local ISP Partner | 2025-12-23 |  | 188 | Site Survey | Survey Complete | Breached | 20 | 76469 | 17648 | FE-339
SITE-02213 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Corporate Office | Vodafone Idea Business | 2026-06-06 |  | 23 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 132341 | 10930 | FE-305
SITE-02214 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Local ISP Partner | 2026-07-08 |  | 0 | BOM Finalization | Delayed - Vendor Issue | On Track | 34 | 54131 | 9406 | FE-222
SITE-02215 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Corporate Office | Vodafone Idea Business | 2026-04-15 |  | 75 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 123437 | 13242 | FE-497
SITE-02216 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Corporate Office | Airtel Business | 2026-04-05 | 2026-04-08 | 3 | Go-Live | Live - Operational | Met | 4 | 51210 | 9123 | FE-246
SITE-02217 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Excitel Enterprise | 2026-06-12 |  | 17 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 109045 | 8519 | FE-360
SITE-02218 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-06-28 | 2026-07-13 | 15 | Go-Live | Live - Operational | Breached | 34 | 131091 | 9581 | FE-394
SITE-02219 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Tata Communications | 2026-07-20 | 2026-07-29 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 29775 | 10925 | FE-241
SITE-02220 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-07-02 |  | 0 | Site Survey | Survey Complete | On Track | 20 | 51801 | 9804 | FE-162
SITE-02221 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-21 |  | 128 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 60481 | 16486 | FE-180
SITE-02222 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Corporate Office | Airtel Business | 2026-07-02 | 2026-07-07 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 87350 | 12782 | FE-311
SITE-02223 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Branch | Excitel Enterprise | 2026-01-11 | 2026-01-02 | -9 | Go-Live | Live - Operational | Met | 4 | 92970 | 12197 | FE-282
SITE-02224 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-05 | 2026-01-18 | 13 | Go-Live | Live - Operational | Breached | 4 | 101004 | 8101 | FE-262
SITE-02225 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Corporate Office | Local ISP Partner | 2026-07-12 |  | 0 | Site Survey | Survey Complete | On Track | 6 | 84747 | 11781 | FE-335
SITE-02226 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Data Center | Tata Communications | 2026-05-31 |  | 29 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 93171 | 6678 | FE-429
SITE-02227 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Corporate Office | Local ISP Partner | 2026-04-30 |  |  | BOM Finalization | Cancelled | N/A | 6 | 57171 | 10786 | FE-336
SITE-02228 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Data Center | Local ISP Partner | 2026-04-05 |  | 85 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 81311 | 6585 | FE-199
SITE-02229 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Branch | Local ISP Partner | 2026-02-25 | 2026-02-18 | -7 | Go-Live | Live - Operational | Met | 34 | 134861 | 5998 | FE-324
SITE-02230 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-03-20 | 2026-03-30 | 10 | Go-Live | Live - Operational | Breached | 2 | 32766 | 3914 | FE-177
SITE-02231 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Branch | Sify Technologies | 2026-06-20 | 2026-06-18 | -2 | Go-Live | Live - Operational | Met | 6 | 69915 | 11087 | FE-439
SITE-02232 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-12-22 |  | 189 | Site Survey | Survey Scheduled | Breached | 10 | 103191 | 14842 | FE-163
SITE-02233 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Branch | Vodafone Idea Business | 2026-07-10 |  | 0 | Equipment Dispatch | Equipment Dispatched | On Track | 6 | 32598 | 6751 | FE-162
SITE-02234 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Local ISP Partner | 2026-03-14 |  | 107 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 95908 | 16206 | FE-300
SITE-02235 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-05-30 |  | 30 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 130772 | 7532 | FE-276
SITE-02236 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | ATM/Off-site | Airtel Business | 2026-03-16 |  | 105 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 50148 | 5970 | FE-427
SITE-02237 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-05-22 |  |  | Site Survey | Cancelled | N/A | 6 | 28186 | 8207 | FE-286
SITE-02238 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Corporate Office | Airtel Business | 2026-07-16 |  |  | Site Survey | Cancelled | N/A | 6 | 57705 | 10434 | FE-318
SITE-02239 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Tata Communications | 2025-12-24 | 2026-01-03 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 100250 | 11022 | FE-123
SITE-02240 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Data Center | Tata Communications | 2026-05-20 |  | 40 | Site Survey | Survey Complete | Breached | 6 | 54201 | 9744 | FE-119
SITE-02241 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Vodafone Idea Business | 2026-01-16 |  | 164 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 74428 | 14064 | FE-383
SITE-02242 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Data Center | Local ISP Partner | 2026-01-07 |  | 173 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 120727 | 15985 | FE-234
SITE-02243 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Sify Technologies | 2026-04-17 |  | 73 | Site Survey | Survey Complete | Breached | 100 | 126795 | 7803 | FE-167
SITE-02244 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | ATM/Off-site | Airtel Business | 2026-06-10 | 2026-06-09 | -1 | Go-Live | Live - Operational | Met | 2 | 111196 | 5238 | FE-486
SITE-02245 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-01-24 | 2026-02-05 | 12 | Go-Live | Live - Operational | Breached | 6 | 122025 | 16864 | FE-440
SITE-02246 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Data Center | Tata Communications | 2026-03-16 |  | 105 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 51991 | 16952 | FE-416
SITE-02247 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Vodafone Idea Business | 2026-06-01 |  | 28 | Site Survey | Survey Complete | Breached | 10 | 111287 | 16449 | FE-469
SITE-02248 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-07-22 | 2026-07-19 | -3 | Go-Live | Live - Operational | Met | 20 | 80011 | 14701 | FE-351
SITE-02249 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Airtel Business | 2025-12-17 | 2026-01-07 | 21 | Go-Live | Live - Operational | Breached | 20 | 129209 | 5499 | FE-434
SITE-02250 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-12-19 | 2025-12-13 | -6 | Go-Live | Live - Operational | Met | 6 | 80598 | 14331 | FE-129
SITE-02251 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-03-28 |  | 93 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 114094 | 9486 | FE-297
SITE-02252 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Tata Communications | 2026-02-24 |  | 125 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 69736 | 7619 | FE-391
SITE-02253 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Branch | Sify Technologies | 2026-06-02 |  | 27 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 84114 | 15302 | FE-237
SITE-02254 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Corporate Office | Sify Technologies | 2026-06-30 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 50 | 63601 | 3777 | FE-391
SITE-02255 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-03-22 |  | 99 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 87095 | 12464 | FE-354
SITE-02256 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Tata Communications | 2026-04-17 | 2026-04-07 | -10 | Go-Live | Live - Operational | Met | 20 | 50115 | 10620 | FE-181
SITE-02257 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Data Center | Tata Communications | 2026-07-25 |  | 0 | Last Mile Provisioning | Last Mile - ROW Pending | On Track | 6 | 123546 | 14340 | FE-145
SITE-02258 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Data Center | Excitel Enterprise | 2026-02-05 | 2026-02-10 | 5 | Go-Live | Live - Operational | Met | 50 | 88654 | 12215 | FE-390
SITE-02259 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Data Center | Airtel Business | 2026-05-09 | 2026-06-01 | 23 | Go-Live | Live - Operational | Breached | 4 | 49623 | 10485 | FE-351
SITE-02260 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | ATM/Off-site | Vodafone Idea Business | 2026-07-08 | 2026-07-09 | 1 | Go-Live | Live - Operational | Met | 50 | 116467 | 16027 | FE-114
SITE-02261 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-05-12 |  |  | ROW / Permission | Cancelled | N/A | 100 | 113032 | 12424 | FE-315
SITE-02262 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-02-07 |  | 142 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 54609 | 5388 | FE-408
SITE-02263 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Corporate Office | Airtel Business | 2026-03-10 |  | 111 | Site Survey | Survey Complete | Breached | 2 | 95173 | 14511 | FE-471
SITE-02264 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Branch | Airtel Business | 2026-01-31 | 2026-02-02 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 48780 | 5483 | FE-400
SITE-02265 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Vodafone Idea Business | 2026-07-02 | 2026-07-14 | 12 | Go-Live | Live - Operational | Breached | 20 | 65065 | 12724 | FE-427
SITE-02266 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Branch | Tata Communications | 2025-12-17 |  | 194 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 83163 | 12695 | FE-337
SITE-02267 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Data Center | Vodafone Idea Business | 2026-05-04 | 2026-05-20 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 67025 | 12878 | FE-329
SITE-02268 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Data Center | Airtel Business | 2026-07-30 | 2026-07-27 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 73555 | 10489 | FE-453
SITE-02269 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Airtel Business | 2025-12-24 | 2025-12-19 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 69252 | 14952 | FE-212
SITE-02270 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Corporate Office | Excitel Enterprise | 2026-05-15 | 2026-05-29 | 14 | Go-Live | Live - Operational | Breached | 50 | 108800 | 6555 | FE-337
SITE-02271 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-07-29 | 2026-08-10 | 12 | Go-Live | Live - Operational | Breached | 50 | 57194 | 8760 | FE-205
SITE-02272 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Local ISP Partner | 2026-05-16 |  | 44 | Site Survey | Survey Complete | Breached | 2 | 51494 | 9529 | FE-279
SITE-02273 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Data Center | Vodafone Idea Business | 2026-01-26 |  | 154 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 83910 | 8410 | FE-220
SITE-02274 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-28 |  | 121 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 108179 | 9946 | FE-278
SITE-02275 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Sify Technologies | 2026-04-06 |  | 84 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 126791 | 7788 | FE-249
SITE-02276 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Branch | Sify Technologies | 2026-02-19 |  | 130 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 79841 | 12828 | FE-408
SITE-02277 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Corporate Office | Sify Technologies | 2026-02-16 |  | 133 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 65367 | 7209 | FE-394
SITE-02278 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-12-20 | 2026-01-12 | 23 | Go-Live | Live - Operational | Breached | 6 | 57429 | 4282 | FE-403
SITE-02279 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-05-19 | 2026-06-08 | 20 | Go-Live | Live - Operational | Breached | 20 | 41075 | 7582 | FE-180
SITE-02280 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Tata Communications | 2026-04-09 |  | 81 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 43092 | 17597 | FE-345
SITE-02281 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Airtel Business | 2026-03-03 | 2026-03-14 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 110614 | 15128 | FE-311
SITE-02282 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-07-08 |  | 0 | Site Survey | Survey Scheduled | On Track | 6 | 32887 | 7504 | FE-105
SITE-02283 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Vodafone Idea Business | 2026-05-10 | 2026-05-18 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 47448 | 15354 | FE-412
SITE-02284 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Airtel Business | 2026-01-21 | 2026-02-02 | 12 | Go-Live | Live - Operational | Breached | 4 | 54743 | 15523 | FE-336
SITE-02285 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-04-30 |  | 60 | Site Survey | Survey Complete | Breached | 10 | 71354 | 13041 | FE-272
SITE-02286 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Branch | Excitel Enterprise | 2026-04-05 |  | 85 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 37015 | 7777 | FE-461
SITE-02287 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Data Center | Vodafone Idea Business | 2026-02-20 | 2026-03-02 | 10 | Go-Live | Live - Operational | Breached | 10 | 39094 | 4687 | FE-214
SITE-02288 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | ATM/Off-site | Sify Technologies | 2025-12-28 |  | 183 | Site Survey | Survey Complete | Breached | 6 | 52968 | 17079 | FE-308
SITE-02289 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | ATM/Off-site | Sify Technologies | 2026-07-23 | 2026-07-28 | 5 | Go-Live | Live - Operational | Met | 100 | 66371 | 6500 | FE-235
SITE-02290 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Branch | Sify Technologies | 2026-01-12 |  | 168 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 114938 | 10885 | FE-465
SITE-02291 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Data Center | Excitel Enterprise | 2026-06-23 |  | 6 | Equipment Dispatch | Equipment Dispatched | At Risk | 2 | 32282 | 12546 | FE-433
SITE-02292 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Vodafone Idea Business | 2026-07-24 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 2 | 48052 | 16684 | FE-434
SITE-02293 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Sify Technologies | 2026-04-19 |  | 71 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 89055 | 7817 | FE-196
SITE-02294 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Branch | Airtel Business | 2026-07-19 | 2026-07-29 | 10 | Go-Live | Live - Operational | Breached | 10 | 98328 | 16507 | FE-287
SITE-02295 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-07-12 | 2026-08-06 | 25 | Go-Live | Live - Operational | Breached | 50 | 79228 | 9043 | FE-192
SITE-02296 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Airtel Business | 2026-07-27 |  | 0 | BOM Finalization | Delayed - Vendor Issue | On Track | 10 | 45495 | 12024 | FE-178
SITE-02297 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | ATM/Off-site | Sify Technologies | 2026-01-19 | 2026-01-10 | -9 | Go-Live | Live - Operational | Met | 50 | 103185 | 5266 | FE-210
SITE-02298 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | ATM/Off-site | Sify Technologies | 2025-12-21 | 2025-12-25 | 4 | Go-Live | Live - Operational | Met | 50 | 89400 | 10724 | FE-134
SITE-02299 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Sify Technologies | 2026-07-04 |  | 0 | Site Survey | Survey Scheduled | On Track | 2 | 85349 | 17523 | FE-318
SITE-02300 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Sify Technologies | 2026-05-21 |  | 39 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 126093 | 4428 | FE-188
SITE-02301 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Airtel Business | 2025-12-30 | 2025-12-25 | -5 | Go-Live | Live - Operational | Met | 20 | 134963 | 11489 | FE-187
SITE-02302 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Airtel Business | 2026-02-23 | 2026-02-21 | -2 | Go-Live | Live - Operational | Met | 20 | 88090 | 4615 | FE-397
SITE-02303 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Airtel Business | 2026-06-17 |  | 12 | Site Survey | Survey Scheduled | Breached | 6 | 66361 | 4353 | FE-291
SITE-02304 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Local ISP Partner | 2026-03-31 |  | 90 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 123636 | 16217 | FE-152
SITE-02305 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Data Center | Sify Technologies | 2026-06-10 |  | 19 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 82253 | 5234 | FE-418
SITE-02306 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Corporate Office | Local ISP Partner | 2025-12-28 | 2026-01-11 | 14 | Go-Live | Live - Operational | Breached | 10 | 98362 | 17793 | FE-325
SITE-02307 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Excitel Enterprise | 2026-01-22 |  | 158 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 51577 | 6048 | FE-262
SITE-02308 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Corporate Office | Vodafone Idea Business | 2026-07-04 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 50 | 127385 | 12245 | FE-244
SITE-02309 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Vodafone Idea Business | 2026-04-19 | 2026-04-24 | 5 | Go-Live | Live - Operational | Met | 4 | 132127 | 6552 | FE-151
SITE-02310 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-28 | 2025-12-25 | -3 | Go-Live | Live - Operational | Met | 2 | 58894 | 14917 | FE-277
SITE-02311 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Vodafone Idea Business | 2025-12-28 |  | 183 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 91534 | 8273 | FE-455
SITE-02312 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Corporate Office | Tata Communications | 2026-05-18 | 2026-05-17 | -1 | Go-Live | Live - Operational | Met | 20 | 119022 | 9315 | FE-191
SITE-02313 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Vodafone Idea Business | 2026-07-30 |  | 0 | BOM Finalization | Delayed - Vendor Issue | On Track | 4 | 50631 | 6375 | FE-172
SITE-02314 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-17 | 2026-02-21 | 4 | Go-Live | Live - Operational | Met | 6 | 49436 | 3851 | FE-284
SITE-02315 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Vodafone Idea Business | 2026-01-13 | 2026-01-27 | 14 | Go-Live | Live - Operational | Breached | 34 | 117797 | 16785 | FE-233
SITE-02316 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | ATM/Off-site | Airtel Business | 2026-07-21 |  | 0 | Site Survey | Survey Complete | On Track | 2 | 118748 | 12340 | FE-200
SITE-02317 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Branch | Sify Technologies | 2026-03-03 | 2026-03-12 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 94659 | 13317 | FE-397
SITE-02318 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Tata Communications | 2026-04-13 | 2026-04-04 | -9 | Go-Live | Live - Operational | Met | 34 | 108458 | 14692 | FE-293
SITE-02319 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Airtel Business | 2026-01-03 | 2026-01-17 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 93121 | 7716 | FE-419
SITE-02320 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | ATM/Off-site | Airtel Business | 2026-05-27 |  | 33 | Site Survey | Survey Scheduled | Breached | 34 | 82278 | 7320 | FE-237
SITE-02321 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Airtel Business | 2026-04-16 |  | 74 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 75014 | 12793 | FE-178
SITE-02322 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Excitel Enterprise | 2026-07-30 | 2026-08-14 | 15 | Go-Live | Live - Operational | Breached | 4 | 46580 | 16763 | FE-409
SITE-02323 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-03-20 |  | 101 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 47779 | 13207 | FE-246
SITE-02324 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Data Center | Airtel Business | 2026-07-25 | 2026-08-13 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 47875 | 13189 | FE-262
SITE-02325 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Data Center | Local ISP Partner | 2026-04-06 | 2026-04-11 | 5 | Go-Live | Live - Operational | Met | 6 | 112640 | 10194 | FE-188
SITE-02326 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | ATM/Off-site | Tata Communications | 2026-06-04 | 2026-06-23 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 77411 | 4745 | FE-271
SITE-02327 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-06-05 |  | 24 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 53497 | 6854 | FE-470
SITE-02328 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | Branch | Tata Communications | 2026-05-02 |  | 58 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 103221 | 12256 | FE-214
SITE-02329 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | ATM/Off-site | Airtel Business | 2026-01-06 |  | 174 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 50661 | 16314 | FE-139
SITE-02330 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Branch | Local ISP Partner | 2026-06-03 |  | 26 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 98559 | 6017 | FE-322
SITE-02331 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Data Center | Sify Technologies | 2026-04-22 |  | 68 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 41629 | 16010 | FE-398
SITE-02332 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-02-21 | 2026-03-05 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 68541 | 8506 | FE-484
SITE-02333 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-07-07 | 2026-07-21 | 14 | Go-Live | Live - Operational | Breached | 100 | 85965 | 13957 | FE-368
SITE-02334 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Data Center | Local ISP Partner | 2026-04-28 | 2026-05-03 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 64932 | 17757 | FE-304
SITE-02335 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Airtel Business | 2026-04-06 |  | 84 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 114311 | 6453 | FE-157
SITE-02336 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | ATM/Off-site | Airtel Business | 2026-04-06 |  | 84 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 53337 | 6498 | FE-108
SITE-02337 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-02-26 | 2026-02-26 | 0 | Go-Live | Live - Operational | Met | 10 | 132312 | 5347 | FE-244
SITE-02338 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Branch | Tata Communications | 2026-07-01 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 100 | 108608 | 10815 | FE-178
SITE-02339 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-05-17 |  | 43 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 113418 | 6135 | FE-363
SITE-02340 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Tata Communications | 2026-05-05 |  | 55 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 84621 | 10418 | FE-309
SITE-02341 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Branch | Tata Communications | 2026-06-24 |  |  | Site Survey | Cancelled | N/A | 2 | 73591 | 6722 | FE-482
SITE-02342 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | ATM/Off-site | Tata Communications | 2026-05-04 | 2026-05-19 | 15 | Go-Live | Live - Operational | Breached | 2 | 70174 | 13851 | FE-123
SITE-02343 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-02-16 | 2026-03-11 | 23 | Go-Live | Live - Operational | Breached | 2 | 74567 | 12562 | FE-452
SITE-02344 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-28 |  | 152 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 35817 | 10890 | FE-303
SITE-02345 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Data Center | Vodafone Idea Business | 2026-01-26 |  | 154 | Site Survey | Survey Scheduled | Breached | 10 | 57771 | 6405 | FE-384
SITE-02346 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | ATM/Off-site | Airtel Business | 2026-07-06 |  | 0 | ROW / Permission | On Hold - Client Site Not Ready | On Track | 100 | 81413 | 15738 | FE-142
SITE-02347 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-14 |  | 166 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 80120 | 10952 | FE-153
SITE-02348 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Branch | Tata Communications | 2026-03-04 |  | 117 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 52886 | 6040 | FE-439
SITE-02349 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-08-03 | 2026-08-07 | 4 | Go-Live | Live - Operational | Met | 4 | 116214 | 12356 | FE-360
SITE-02350 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-04-13 | 2026-04-07 | -6 | Go-Live | Live - Operational | Met | 34 | 120831 | 16021 | FE-476
SITE-02351 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Tata Communications | 2026-04-21 |  | 69 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 83376 | 15878 | FE-422
SITE-02352 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-05-27 | 2026-06-20 | 24 | Go-Live | Live - Operational | Breached | 20 | 60422 | 16120 | FE-138
SITE-02353 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Data Center | Vodafone Idea Business | 2026-05-20 |  | 40 | Site Survey | Survey Scheduled | Breached | 4 | 88377 | 11743 | FE-455
SITE-02354 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-04-02 |  | 88 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 98912 | 14850 | FE-253
SITE-02355 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Local ISP Partner | 2026-06-22 | 2026-06-13 | -9 | Go-Live | Live - Operational | Met | 50 | 77397 | 9539 | FE-456
SITE-02356 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-06-29 |  | 0 | Site Survey | Survey Complete | On Track | 34 | 103333 | 17089 | FE-148
SITE-02357 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Corporate Office | Excitel Enterprise | 2026-02-06 |  | 143 | Site Survey | Survey Scheduled | Breached | 6 | 73013 | 8843 | FE-214
SITE-02358 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Vodafone Idea Business | 2026-04-06 |  | 84 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 45891 | 12991 | FE-411
SITE-02359 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-05-25 | 2026-06-14 | 20 | Go-Live | Live - Operational | Breached | 50 | 83450 | 13170 | FE-255
SITE-02360 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Vodafone Idea Business | 2026-05-23 |  | 37 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 101719 | 3563 | FE-383
SITE-02361 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Data Center | Sify Technologies | 2026-06-09 | 2026-06-25 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 117860 | 13622 | FE-392
SITE-02362 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-01-04 | 2026-01-15 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 42751 | 10233 | FE-336
SITE-02363 | PRJ-2024024 | CL003 | South | Tamil Nadu | Madurai | Leased Line | Corporate Office | Airtel Business | 2026-04-27 |  | 63 | Site Survey | Survey Scheduled | Breached | 50 | 124085 | 13027 | FE-374
SITE-02364 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-28 |  | 121 | Site Survey | Survey Complete | Breached | 2 | 62763 | 8251 | FE-261
SITE-02365 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Tata Communications | 2026-06-03 | 2026-06-25 | 22 | Go-Live | Live - Operational | Breached | 34 | 50400 | 5437 | FE-116
SITE-02366 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Data Center | Vodafone Idea Business | 2026-04-12 | 2026-04-04 | -8 | Go-Live | Live - Operational | Met | 20 | 100466 | 13360 | FE-131
SITE-02367 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Corporate Office | Sify Technologies | 2026-02-23 | 2026-03-19 | 24 | Go-Live | Live - Operational | Breached | 4 | 128948 | 7128 | FE-100
SITE-02368 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | ATM/Off-site | Local ISP Partner | 2026-05-07 |  | 53 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 71238 | 11404 | FE-256
SITE-02369 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Local ISP Partner | 2026-05-23 | 2026-06-12 | 20 | Go-Live | Live - Operational | Breached | 4 | 100526 | 9195 | FE-312
SITE-02370 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Tata Communications | 2026-04-09 | 2026-04-22 | 13 | Go-Live | Live - Operational | Breached | 2 | 55899 | 4252 | FE-447
SITE-02371 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Branch | Excitel Enterprise | 2026-03-29 |  | 92 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 112547 | 6830 | FE-108
SITE-02372 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Corporate Office | Excitel Enterprise | 2026-01-09 | 2026-01-21 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 85445 | 12369 | FE-440
SITE-02373 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Branch | Excitel Enterprise | 2026-05-10 |  | 50 | Site Survey | Survey Scheduled | Breached | 100 | 122504 | 3819 | FE-434
SITE-02374 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Data Center | Local ISP Partner | 2026-01-26 |  | 154 | Site Survey | Survey Scheduled | Breached | 2 | 32093 | 5351 | FE-423
SITE-02375 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Branch | Tata Communications | 2026-07-31 |  | 0 | Site Survey | Survey Complete | On Track | 10 | 63570 | 8343 | FE-255
SITE-02376 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Vodafone Idea Business | 2026-05-17 |  | 43 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 63947 | 14399 | FE-275
SITE-02377 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Corporate Office | Airtel Business | 2026-07-13 |  | 0 | Site Survey | Survey Complete | On Track | 20 | 33061 | 9690 | FE-172
SITE-02378 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-08-06 | 2026-08-12 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 90611 | 5743 | FE-261
SITE-02379 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Branch | Excitel Enterprise | 2026-07-22 | 2026-07-23 | 1 | Go-Live | Live - Operational | Met | 2 | 71487 | 7365 | FE-210
SITE-02380 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Corporate Office | Vodafone Idea Business | 2026-02-20 | 2026-03-13 | 21 | Go-Live | Live - Operational | Breached | 50 | 67790 | 12366 | FE-247
SITE-02381 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-11 |  | 138 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 50376 | 5079 | FE-218
SITE-02382 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Branch | Airtel Business | 2025-12-17 | 2025-12-27 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 71649 | 15438 | FE-278
SITE-02383 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Branch | Local ISP Partner | 2026-06-13 | 2026-06-06 | -7 | Go-Live | Live - Operational | Met | 10 | 79693 | 5592 | FE-437
SITE-02384 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | ATM/Off-site | Local ISP Partner | 2026-06-17 | 2026-07-07 | 20 | Go-Live | Live - Operational | Breached | 6 | 111008 | 11090 | FE-353
SITE-02385 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | ATM/Off-site | Excitel Enterprise | 2026-05-02 | 2026-05-26 | 24 | Go-Live | Live - Operational | Breached | 34 | 100834 | 8759 | FE-464
SITE-02386 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Local ISP Partner | 2026-01-31 | 2026-02-09 | 9 | Go-Live | Live - Operational | Breached | 34 | 46342 | 15178 | FE-260
SITE-02387 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Data Center | Sify Technologies | 2026-04-23 | 2026-05-03 | 10 | Go-Live | Live - Operational | Breached | 4 | 86802 | 4590 | FE-128
SITE-02388 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Sify Technologies | 2026-07-22 |  | 0 | Equipment Dispatch | Equipment Dispatched | On Track | 20 | 106549 | 5019 | FE-232
SITE-02389 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Sify Technologies | 2026-02-22 | 2026-03-04 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 74743 | 16154 | FE-172
SITE-02390 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Corporate Office | Tata Communications | 2026-06-21 |  | 8 | Equipment Dispatch | Equipment Dispatched | At Risk | 100 | 43608 | 9339 | FE-397
SITE-02391 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-02-20 | 2026-02-28 | 8 | Go-Live | Live - Operational | Breached | 2 | 71695 | 7290 | FE-350
SITE-02392 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Branch | Excitel Enterprise | 2026-02-10 | 2026-02-12 | 2 | Go-Live | Live - Operational | Met | 10 | 83218 | 4862 | FE-135
SITE-02393 | PRJ-2024024 | CL003 | South | Tamil Nadu | Coimbatore | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-04-28 |  | 62 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 32906 | 11904 | FE-342
SITE-02394 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Branch | Sify Technologies | 2026-07-11 | 2026-08-05 | 25 | Go-Live | Live - Operational | Breached | 6 | 90903 | 12401 | FE-343
SITE-02395 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Data Center | Airtel Business | 2026-07-15 | 2026-07-27 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 117688 | 4525 | FE-260
SITE-02396 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Corporate Office | Vodafone Idea Business | 2026-06-11 |  | 18 | Site Survey | Survey Scheduled | Breached | 34 | 114624 | 6984 | FE-267
SITE-02397 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Branch | Excitel Enterprise | 2025-12-28 |  | 183 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 74693 | 10460 | FE-451
SITE-02398 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Data Center | Tata Communications | 2026-02-25 | 2026-03-04 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 86024 | 15661 | FE-293
SITE-02399 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Airtel Business | 2026-01-01 |  | 179 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 134644 | 9988 | FE-169
SITE-02400 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Data Center | Local ISP Partner | 2026-02-19 |  | 130 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 62339 | 9094 | FE-126
SITE-02401 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Branch | Local ISP Partner | 2026-05-14 |  | 46 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 42701 | 4290 | FE-372
SITE-02402 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-04-17 | 2026-04-19 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 117621 | 15114 | FE-274
SITE-02403 | PRJ-2024024 | CL003 | South | Tamil Nadu | Chennai | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-06 |  | 174 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 114975 | 12053 | FE-248
SITE-02404 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Data Center | Sify Technologies | 2026-03-01 |  | 120 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 109166 | 15805 | FE-443
SITE-02405 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Vodafone Idea Business | 2026-05-14 |  | 46 | Site Survey | Survey Scheduled | Breached | 6 | 101536 | 17866 | FE-289
SITE-02406 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-06-15 |  | 14 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 95936 | 15655 | FE-156
SITE-02407 | PRJ-2024024 | CL003 | South | Kerala | Kochi | Leased Line | Data Center | Local ISP Partner | 2026-01-21 | 2026-01-15 | -6 | Go-Live | Live - Operational | Met | 100 | 123830 | 12327 | FE-411
SITE-02408 | PRJ-2024024 | CL003 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Local ISP Partner | 2026-04-30 | 2026-05-12 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 38741 | 11071 | FE-107
SITE-02409 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Corporate Office | Airtel Business | 2026-03-10 | 2026-03-06 | -4 | Go-Live | Live - Operational | Met | 50 | 93056 | 15960 | FE-181
SITE-02410 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Airtel Business | 2026-01-11 |  | 169 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 111649 | 3986 | FE-207
SITE-02411 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-06-26 | 2026-07-04 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 103775 | 7526 | FE-412
SITE-02412 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Guntur | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-02-24 | 2026-03-07 | 11 | Go-Live | Live - Operational | Breached | 2 | 124716 | 16524 | FE-416
SITE-02413 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Data Center | Vodafone Idea Business | 2026-07-17 | 2026-07-13 | -4 | Go-Live | Live - Operational | Met | 2 | 76549 | 8671 | FE-175
SITE-02414 | PRJ-2024024 | CL003 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Airtel Business | 2026-05-14 |  | 46 | Site Survey | Survey Scheduled | Breached | 34 | 39721 | 13789 | FE-436
SITE-02415 | PRJ-2024024 | CL003 | South | Telangana | Hyderabad | Leased Line | Branch | Local ISP Partner | 2026-04-13 |  | 77 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 53579 | 5573 | FE-444
SITE-02416 | PRJ-2024024 | CL003 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-01-16 | 2026-01-21 | 5 | Go-Live | Live - Operational | Met | 2 | 60587 | 17551 | FE-372
SITE-02417 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Sify Technologies | 2026-01-19 | 2026-02-03 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 59896 | 15353 | FE-318
SITE-02418 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Corporate Office | Excitel Enterprise | 2026-06-10 | 2026-07-03 | 23 | Go-Live | Live - Operational | Breached | 4 | 93835 | 15250 | FE-162
SITE-02419 | PRJ-2024024 | CL003 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Airtel Business | 2025-12-31 | 2025-12-30 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 55077 | 10061 | FE-135
SITE-02420 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Vodafone Idea Business | 2026-03-23 | 2026-04-07 | 15 | Go-Live | Live - Operational | Breached | 4 | 56446 | 14808 | FE-278
SITE-02421 | PRJ-2024024 | CL003 | South | Kerala | Kozhikode | Leased Line | Warehouse/Ops Hub | Airtel Business | 2026-03-28 |  | 93 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 74298 | 7464 | FE-416
SITE-02422 | PRJ-2024024 | CL003 | South | Karnataka | Hubli | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2026-05-25 | 2026-06-05 | 11 | Go-Live | Live - Operational | Breached | 50 | 39842 | 9508 | FE-424
SITE-02423 | PRJ-2024024 | CL003 | South | Telangana | Warangal | Leased Line | Branch | Local ISP Partner | 2026-02-17 |  | 132 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 78572 | 16941 | FE-292
SITE-02424 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Corporate Office | Sify Technologies | 2026-02-01 |  | 148 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 41272 | 9723 | FE-248
SITE-02425 | PRJ-2024024 | CL003 | South | Tamil Nadu | Trichy | Leased Line | Branch | Local ISP Partner | 2026-05-22 |  | 38 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 94592 | 7431 | FE-341
SITE-02426 | PRJ-2024025 | CL008 | South | Andhra Pradesh | Vijayawada | VSAT | ATM/Off-site | Excitel Enterprise | 2025-04-13 |  | 442 | Site Survey | Survey Scheduled | Breached | 50 | 128363 | 14152 | FE-293
SITE-02427 | PRJ-2024025 | CL008 | South | Andhra Pradesh | Vijayawada | VSAT | Corporate Office | Airtel Business | 2025-11-26 | 2025-11-28 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 77507 | 16725 | FE-230
SITE-02428 | PRJ-2024025 | CL008 | South | Telangana | Hyderabad | VSAT | Data Center | Tata Communications | 2025-09-27 |  | 275 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 41741 | 13714 | FE-456
SITE-02429 | PRJ-2024025 | CL008 | South | Andhra Pradesh | Visakhapatnam | VSAT | ATM/Off-site | Sify Technologies | 2025-11-20 |  | 221 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 81686 | 17069 | FE-235
SITE-02430 | PRJ-2024025 | CL008 | South | Karnataka | Mysuru | VSAT | Warehouse/Ops Hub | Excitel Enterprise | 2025-04-15 | 2025-04-17 | 2 | Go-Live | Live - Operational | Met | 2 | 45743 | 11534 | FE-209
SITE-02431 | PRJ-2024025 | CL008 | South | Karnataka | Mysuru | VSAT | ATM/Off-site | Vodafone Idea Business | 2025-08-08 | 2025-08-24 | 16 | Go-Live | Live - Operational | Breached | 6 | 94730 | 17792 | FE-152
SITE-02432 | PRJ-2024025 | CL008 | South | Telangana | Warangal | VSAT | Data Center | Tata Communications | 2025-06-14 |  | 380 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 105591 | 8693 | FE-208
SITE-02433 | PRJ-2024025 | CL008 | South | Karnataka | Hubli | VSAT | Branch | Vodafone Idea Business | 2025-08-31 |  | 302 | Site Survey | Survey Complete | Breached | 100 | 80708 | 7761 | FE-455
SITE-02434 | PRJ-2024025 | CL008 | South | Kerala | Kozhikode | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-11-27 |  |  | Site Survey | Cancelled | N/A | 6 | 94277 | 12291 | FE-490
SITE-02435 | PRJ-2024025 | CL008 | South | Telangana | Warangal | VSAT | Corporate Office | Tata Communications | 2025-11-15 | 2025-11-25 | 10 | Go-Live | Live - Operational | Breached | 10 | 128521 | 8884 | FE-375
SITE-02436 | PRJ-2024025 | CL008 | South | Andhra Pradesh | Vijayawada | VSAT | Data Center | Sify Technologies | 2025-05-07 |  | 418 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 30788 | 14015 | FE-317
SITE-02437 | PRJ-2024025 | CL008 | South | Kerala | Kozhikode | VSAT | Data Center | Sify Technologies | 2025-10-24 | 2025-10-20 | -4 | Go-Live | Live - Operational | Met | 2 | 54620 | 8498 | FE-206
SITE-02438 | PRJ-2024025 | CL008 | South | Kerala | Kozhikode | VSAT | Branch | Excitel Enterprise | 2025-11-22 |  | 219 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 54941 | 12484 | FE-340
SITE-02439 | PRJ-2024025 | CL008 | South | Andhra Pradesh | Guntur | VSAT | ATM/Off-site | Local ISP Partner | 2025-08-15 |  | 318 | Site Survey | Survey Complete | Breached | 10 | 56108 | 10130 | FE-245
SITE-02440 | PRJ-2024025 | CL008 | South | Andhra Pradesh | Visakhapatnam | VSAT | Branch | Airtel Business | 2025-11-04 | 2025-11-10 | 6 | Go-Live | Live - Operational | Breached | 2 | 107304 | 3704 | FE-418
SITE-02441 | PRJ-2024026 | CL005 | East | West Bengal | Howrah | MPLS | Branch | Airtel Business | 2025-05-20 | 2025-06-05 | 16 | Go-Live | Live - Operational | Breached | 6 | 79891 | 5683 | FE-278
SITE-02442 | PRJ-2024026 | CL005 | East | Bihar | Patna | MPLS | ATM/Off-site | Airtel Business | 2025-03-17 | 2025-03-11 | -6 | Go-Live | Live - Operational | Met | 4 | 108112 | 4070 | FE-470
SITE-02443 | PRJ-2024026 | CL005 | East | Bihar | Gaya | MPLS | Branch | Sify Technologies | 2025-02-12 |  | 502 | Site Survey | Survey Scheduled | Breached | 20 | 36688 | 3822 | FE-128
SITE-02444 | PRJ-2024026 | CL005 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Sify Technologies | 2025-06-02 | 2025-06-05 | 3 | Go-Live | Live - Operational | Met | 34 | 130338 | 7435 | FE-382
SITE-02445 | PRJ-2024026 | CL005 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-05-12 |  | 413 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 111137 | 5866 | FE-173
SITE-02446 | PRJ-2024026 | CL005 | East | Bihar | Gaya | MPLS | Data Center | Airtel Business | 2025-06-08 | 2025-07-03 | 25 | Go-Live | Live - Operational | Breached | 50 | 61522 | 17681 | FE-394
SITE-02447 | PRJ-2024026 | CL005 | East | Jharkhand | Ranchi | MPLS | Branch | Vodafone Idea Business | 2025-02-23 | 2025-03-08 | 13 | Go-Live | Live - Operational | Breached | 20 | 131999 | 5861 | FE-194
SITE-02448 | PRJ-2024026 | CL005 | East | Bihar | Patna | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-08-10 | 2025-08-13 | 3 | Go-Live | Live - Operational | Met | 4 | 42140 | 12242 | FE-418
SITE-02449 | PRJ-2024026 | CL005 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-28 | 2025-04-11 | 14 | Go-Live | Live - Operational | Breached | 4 | 118117 | 9750 | FE-210
SITE-02450 | PRJ-2024026 | CL005 | East | West Bengal | Howrah | MPLS | Data Center | Vodafone Idea Business | 2025-02-16 | 2025-03-12 | 24 | Go-Live | Live - Operational | Breached | 6 | 35351 | 5981 | FE-498
SITE-02451 | PRJ-2024026 | CL005 | East | West Bengal | Kolkata | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-04-04 |  | 451 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 122560 | 5720 | FE-135
SITE-02452 | PRJ-2024026 | CL005 | East | Assam | Dibrugarh | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-04-23 | 2025-05-17 | 24 | Go-Live | Live - Operational | Breached | 2 | 72428 | 11116 | FE-343
SITE-02453 | PRJ-2024026 | CL005 | East | Assam | Dibrugarh | MPLS | Data Center | Airtel Business | 2025-01-24 | 2025-01-20 | -4 | Go-Live | Live - Operational | Met | 6 | 71717 | 16573 | FE-388
SITE-02454 | PRJ-2024026 | CL005 | East | West Bengal | Kolkata | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-05 |  | 481 | Site Survey | Survey Scheduled | Breached | 4 | 52839 | 15831 | FE-498
SITE-02455 | PRJ-2024026 | CL005 | East | West Bengal | Siliguri | MPLS | ATM/Off-site | Tata Communications | 2025-02-21 |  | 493 | Site Survey | Survey Scheduled | Breached | 4 | 54764 | 12356 | FE-294
SITE-02456 | PRJ-2024026 | CL005 | East | Assam | Guwahati | MPLS | Branch | Local ISP Partner | 2025-05-09 |  | 416 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 92961 | 5835 | FE-195
SITE-02457 | PRJ-2024026 | CL005 | East | West Bengal | Kolkata | MPLS | Data Center | Tata Communications | 2025-03-30 | 2025-04-06 | 7 | Go-Live | Live - Operational | Breached | 100 | 42543 | 12830 | FE-185
SITE-02458 | PRJ-2024026 | CL005 | East | Assam | Guwahati | MPLS | Branch | Vodafone Idea Business | 2025-08-10 |  | 323 | Site Survey | Survey Scheduled | Breached | 20 | 68159 | 7512 | FE-308
SITE-02459 | PRJ-2024026 | CL005 | East | West Bengal | Kolkata | MPLS | Corporate Office | Airtel Business | 2025-07-22 | 2025-07-31 | 9 | Go-Live | Live - Operational | Breached | 6 | 75257 | 5862 | FE-147
SITE-02460 | PRJ-2024026 | CL005 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Excitel Enterprise | 2025-04-06 | 2025-04-07 | 1 | Go-Live | Live - Operational | Met | 20 | 127002 | 4848 | FE-172
SITE-02461 | PRJ-2024026 | CL005 | East | West Bengal | Siliguri | MPLS | Data Center | Airtel Business | 2025-03-28 | 2025-04-15 | 18 | Go-Live | Live - Operational | Breached | 50 | 108874 | 3870 | FE-206
SITE-02462 | PRJ-2024026 | CL005 | East | Odisha | Cuttack | MPLS | Corporate Office | Sify Technologies | 2025-06-18 |  | 376 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 57445 | 5638 | FE-340
SITE-02463 | PRJ-2024026 | CL005 | East | Jharkhand | Ranchi | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-05-08 |  | 417 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 116752 | 5694 | FE-238
SITE-02464 | PRJ-2024026 | CL005 | East | Bihar | Gaya | MPLS | Corporate Office | Tata Communications | 2025-05-27 |  | 398 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 32856 | 5653 | FE-154
SITE-02465 | PRJ-2024026 | CL005 | East | West Bengal | Siliguri | MPLS | Corporate Office | Excitel Enterprise | 2025-02-06 |  | 508 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 50377 | 16696 | FE-320
SITE-02466 | PRJ-2024026 | CL005 | East | Assam | Dibrugarh | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2025-03-23 |  |  | ROW / Permission | Cancelled | N/A | 50 | 61462 | 11347 | FE-384
SITE-02467 | PRJ-2024026 | CL005 | East | Jharkhand | Jamshedpur | MPLS | Data Center | Tata Communications | 2025-03-04 | 2025-03-23 | 19 | Go-Live | Live - Operational | Breached | 2 | 93562 | 12110 | FE-237
SITE-02468 | PRJ-2024026 | CL005 | East | Bihar | Gaya | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-01-15 | 2025-02-06 | 22 | Go-Live | Live - Operational | Breached | 4 | 101997 | 5294 | FE-392
SITE-02469 | PRJ-2024026 | CL005 | East | West Bengal | Howrah | MPLS | ATM/Off-site | Tata Communications | 2025-06-16 | 2025-06-29 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 67423 | 4214 | FE-125
SITE-02470 | PRJ-2024026 | CL005 | East | Jharkhand | Ranchi | MPLS | ATM/Off-site | Airtel Business | 2025-06-13 |  | 381 | Site Survey | Survey Complete | Breached | 34 | 58207 | 8064 | FE-376
SITE-02471 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-10-11 | 2025-10-03 | -8 | Go-Live | Live - Operational | Met | 4 | 57360 | 12905 | FE-370
SITE-02472 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-07 | 2025-10-07 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 50042 | 4580 | FE-185
SITE-02473 | PRJ-2024027 | CL001 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-12-26 |  | 185 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 71103 | 3524 | FE-206
SITE-02474 | PRJ-2024027 | CL001 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-06-24 | 2025-06-15 | -9 | Go-Live | Live - Operational | Met | 50 | 60593 | 16497 | FE-249
SITE-02475 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-11-17 | 2025-11-14 | -3 | Go-Live | Live - Operational | Met | 2 | 95653 | 12037 | FE-392
SITE-02476 | PRJ-2024027 | CL001 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-08-22 | 2025-08-19 | -3 | Go-Live | Live - Operational | Met | 2 | 103975 | 17522 | FE-147
SITE-02477 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-11-26 |  | 215 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 117851 | 11601 | FE-203
SITE-02478 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-08 |  | 203 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 124994 | 15236 | FE-416
SITE-02479 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-11-04 | 2025-11-15 | 11 | Go-Live | Live - Operational | Breached | 4 | 99776 | 10467 | FE-345
SITE-02480 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-06-29 | 2025-06-22 | -7 | Go-Live | Live - Operational | Met | 20 | 117692 | 7090 | FE-227
SITE-02481 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-12-21 | 2025-12-26 | 5 | Go-Live | Live - Operational | Met | 4 | 96601 | 17956 | FE-143
SITE-02482 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-11-20 |  | 221 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 119003 | 7745 | FE-268
SITE-02483 | PRJ-2024027 | CL001 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2026-01-11 |  | 169 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 52787 | 13918 | FE-233
SITE-02484 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-08-10 |  | 323 | Site Survey | Survey Complete | Breached | 20 | 82116 | 10235 | FE-115
SITE-02485 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-13 |  | 228 | Site Survey | Survey Complete | Breached | 20 | 65143 | 13035 | FE-460
SITE-02486 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-10 |  | 262 | Site Survey | Survey Scheduled | Breached | 2 | 40516 | 4459 | FE-381
SITE-02487 | PRJ-2024027 | CL001 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-12-20 |  | 191 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 118271 | 11806 | FE-177
SITE-02488 | PRJ-2024027 | CL001 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-10-11 |  | 261 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 47567 | 9907 | FE-172
SITE-02489 | PRJ-2024027 | CL001 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-10-25 | 2025-10-22 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 45818 | 11160 | FE-216
SITE-02490 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-09-06 |  | 296 | Site Survey | Survey Complete | Breached | 34 | 87563 | 3785 | FE-104
SITE-02491 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-11-24 | 2025-11-20 | -4 | Go-Live | Live - Operational | Met | 34 | 42048 | 12494 | FE-159
SITE-02492 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-08-03 |  | 330 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 65599 | 14404 | FE-303
SITE-02493 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-10-15 | 2025-10-16 | 1 | Go-Live | Live - Operational | Met | 20 | 83898 | 10191 | FE-112
SITE-02494 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-11-09 | 2025-11-14 | 5 | Go-Live | Live - Operational | Met | 100 | 39359 | 3985 | FE-145
SITE-02495 | PRJ-2024027 | CL001 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-11-11 | 2025-11-28 | 17 | Go-Live | Live - Operational | Breached | 4 | 44396 | 3981 | FE-435
SITE-02496 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-10-24 | 2025-11-10 | 17 | Go-Live | Live - Operational | Breached | 10 | 134810 | 16146 | FE-474
SITE-02497 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-12-21 |  | 190 | Site Survey | Survey Complete | Breached | 6 | 46917 | 10705 | FE-314
SITE-02498 | PRJ-2024027 | CL001 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2026-01-16 |  | 164 | Site Survey | Survey Complete | Breached | 4 | 71633 | 7376 | FE-103
SITE-02499 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-12-26 |  | 185 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 92463 | 17350 | FE-176
SITE-02500 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-11-08 | 2025-11-16 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 98091 | 6270 | FE-183
SITE-02501 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-21 |  | 343 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 79673 | 10922 | FE-101
SITE-02502 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-12-16 |  | 195 | Site Survey | Survey Scheduled | Breached | 50 | 48007 | 17523 | FE-166
SITE-02503 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2026-01-30 |  | 150 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 94930 | 17528 | FE-238
SITE-02504 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-10-16 |  | 256 | Site Survey | Survey Scheduled | Breached | 6 | 103783 | 4484 | FE-427
SITE-02505 | PRJ-2024027 | CL001 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-06-28 | 2025-07-14 | 16 | Go-Live | Live - Operational | Breached | 20 | 93614 | 12767 | FE-347
SITE-02506 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-08-18 | 2025-08-28 | 10 | Go-Live | Live - Operational | Breached | 20 | 35031 | 8533 | FE-471
SITE-02507 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-11-06 |  | 235 | Site Survey | Survey Complete | Breached | 6 | 39387 | 9009 | FE-426
SITE-02508 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-12-24 |  | 187 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 61656 | 12918 | FE-188
SITE-02509 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-12-12 |  | 199 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 128455 | 5527 | FE-151
SITE-02510 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-11-05 | 2025-11-30 | 25 | Go-Live | Live - Operational | Breached | 6 | 88764 | 7580 | FE-101
SITE-02511 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-08-15 | 2025-08-20 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 122898 | 4561 | FE-370
SITE-02512 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2026-01-10 |  | 170 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 81104 | 10138 | FE-232
SITE-02513 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2026-01-14 | 2026-01-10 | -4 | Go-Live | Live - Operational | Met | 4 | 49102 | 16855 | FE-289
SITE-02514 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-12-27 |  | 184 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 60392 | 17642 | FE-115
SITE-02515 | PRJ-2024027 | CL001 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-07-02 |  | 362 | Site Survey | Survey Complete | Breached | 50 | 28549 | 16997 | FE-222
SITE-02516 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-12-18 | 2026-01-09 | 22 | Go-Live | Live - Operational | Breached | 2 | 54559 | 6173 | FE-131
SITE-02517 | PRJ-2024027 | CL001 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-10-11 |  | 261 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 38509 | 4965 | FE-241
SITE-02518 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-09-03 | 2025-09-23 | 20 | Go-Live | Live - Operational | Breached | 4 | 126331 | 14802 | FE-354
SITE-02519 | PRJ-2024027 | CL001 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-31 |  | 180 | Site Survey | Survey Scheduled | Breached | 2 | 130324 | 15775 | FE-153
SITE-02520 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-12-11 |  | 200 | Site Survey | Survey Complete | Breached | 20 | 40913 | 13032 | FE-431
SITE-02521 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-09-11 |  | 291 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 38097 | 6875 | FE-324
SITE-02522 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-11-01 | 2025-11-01 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 49819 | 12644 | FE-370
SITE-02523 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-10-17 | 2025-10-15 | -2 | Go-Live | Live - Operational | Met | 2 | 121724 | 7214 | FE-339
SITE-02524 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-10-06 | 2025-09-27 | -9 | Go-Live | Live - Operational | Met | 4 | 130130 | 13585 | FE-340
SITE-02525 | PRJ-2024027 | CL001 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-12-09 | 2025-12-23 | 14 | Go-Live | Live - Operational | Breached | 100 | 129566 | 5476 | FE-374
SITE-02526 | PRJ-2024027 | CL001 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2026-01-19 | 2026-01-21 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 101355 | 17644 | FE-154
SITE-02527 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-11-06 | 2025-11-01 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 89016 | 17707 | FE-356
SITE-02528 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-12-02 | 2025-12-08 | 6 | Go-Live | Live - Operational | Breached | 6 | 55955 | 17857 | FE-302
SITE-02529 | PRJ-2024027 | CL001 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-09-27 | 2025-09-19 | -8 | Go-Live | Live - Operational | Met | 50 | 100284 | 9273 | FE-333
SITE-02530 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-10-17 |  | 255 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 117422 | 14684 | FE-282
SITE-02531 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-12-12 |  | 199 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 119354 | 15764 | FE-172
SITE-02532 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-12-24 | 2025-12-21 | -3 | Go-Live | Live - Operational | Met | 6 | 78907 | 4691 | FE-102
SITE-02533 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-08-08 | 2025-08-21 | 13 | Go-Live | Live - Operational | Breached | 20 | 130468 | 6064 | FE-244
SITE-02534 | PRJ-2024027 | CL001 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-11-03 |  | 238 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 65821 | 12377 | FE-249
SITE-02535 | PRJ-2024027 | CL001 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-06-25 | 2025-06-15 | -10 | Go-Live | Live - Operational | Met | 50 | 106733 | 16760 | FE-138
SITE-02536 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-06-30 | 2025-06-29 | -1 | Go-Live | Live - Operational | Met | 4 | 77421 | 11303 | FE-468
SITE-02537 | PRJ-2024027 | CL001 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-09-01 |  |  | BOM Finalization | Cancelled | N/A | 34 | 58496 | 8576 | FE-381
SITE-02538 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-09-10 | 2025-09-01 | -9 | Go-Live | Live - Operational | Met | 100 | 83130 | 7752 | FE-493
SITE-02539 | PRJ-2024027 | CL001 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-14 |  | 166 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 69950 | 11240 | FE-226
SITE-02540 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-12-26 | 2026-01-14 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 86856 | 11572 | FE-268
SITE-02541 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-17 | 2025-11-30 | 13 | Go-Live | Live - Operational | Breached | 4 | 72743 | 9435 | FE-232
SITE-02542 | PRJ-2024027 | CL001 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-06-30 |  | 364 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 57764 | 15531 | FE-296
SITE-02543 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2026-01-06 | 2026-01-10 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 129148 | 8090 | FE-316
SITE-02544 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-06-28 | 2025-07-10 | 12 | Go-Live | Live - Operational | Breached | 4 | 31580 | 11047 | FE-204
SITE-02545 | PRJ-2024027 | CL001 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-07-20 |  | 344 | Site Survey | Survey Scheduled | Breached | 20 | 126919 | 14187 | FE-346
SITE-02546 | PRJ-2024027 | CL001 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-10-20 | 2025-10-13 | -7 | Go-Live | Live - Operational | Met | 100 | 69687 | 8528 | FE-216
SITE-02547 | PRJ-2024027 | CL001 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2026-02-01 | 2026-02-19 | 18 | Go-Live | Live - Operational | Breached | 20 | 93962 | 17371 | FE-266
SITE-02548 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-09-25 | 2025-09-18 | -7 | Go-Live | Live - Operational | Met | 6 | 71559 | 7752 | FE-494
SITE-02549 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-09-30 |  | 272 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 100745 | 11957 | FE-253
SITE-02550 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-10-06 |  | 266 | Site Survey | Survey Scheduled | Breached | 2 | 86368 | 14193 | FE-293
SITE-02551 | PRJ-2024027 | CL001 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-07-06 |  | 358 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 123240 | 12486 | FE-305
SITE-02552 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-07-24 |  |  | BOM Finalization | Cancelled | N/A | 10 | 97338 | 10565 | FE-469
SITE-02553 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-02 |  | 362 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 132507 | 7813 | FE-364
SITE-02554 | PRJ-2024027 | CL001 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-12-09 |  | 202 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 118953 | 8982 | FE-499
SITE-02555 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-06-20 | 2025-07-02 | 12 | Go-Live | Live - Operational | Breached | 6 | 90162 | 6777 | FE-395
SITE-02556 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-05 | 2026-02-15 | 10 | Go-Live | Live - Operational | Breached | 50 | 61734 | 16222 | FE-104
SITE-02557 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-12-03 |  | 208 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 35572 | 15570 | FE-342
SITE-02558 | PRJ-2024027 | CL001 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-10-24 |  | 248 | Site Survey | Survey Scheduled | Breached | 20 | 48812 | 10648 | FE-139
SITE-02559 | PRJ-2024027 | CL001 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-08-19 | 2025-09-11 | 23 | Go-Live | Live - Operational | Breached | 6 | 90502 | 6941 | FE-306
SITE-02560 | PRJ-2024027 | CL001 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-08-10 |  | 323 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 50995 | 14042 | FE-175
SITE-02561 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-12-30 | 2025-12-24 | -6 | Go-Live | Live - Operational | Met | 100 | 83827 | 13440 | FE-161
SITE-02562 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-07-31 |  | 333 | Site Survey | Survey Scheduled | Breached | 6 | 108843 | 17967 | FE-378
SITE-02563 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-08-26 | 2025-09-07 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 32244 | 9640 | FE-189
SITE-02564 | PRJ-2024027 | CL001 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-21 |  | 373 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 52534 | 3984 | FE-192
SITE-02565 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-06-22 |  | 372 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 116946 | 10012 | FE-237
SITE-02566 | PRJ-2024027 | CL001 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-10-05 | 2025-10-29 | 24 | Go-Live | Live - Operational | Breached | 100 | 88889 | 17975 | FE-488
SITE-02567 | PRJ-2024027 | CL001 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-09-29 | 2025-10-01 | 2 | Go-Live | Live - Operational | Met | 34 | 117817 | 3676 | FE-116
SITE-02568 | PRJ-2024027 | CL001 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-08-05 | 2025-08-21 | 16 | Go-Live | Live - Operational | Breached | 20 | 64655 | 9672 | FE-395
SITE-02569 | PRJ-2024027 | CL001 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-07-29 |  | 335 | Site Survey | Survey Scheduled | Breached | 100 | 84784 | 7459 | FE-384
SITE-02570 | PRJ-2024027 | CL001 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-11-10 | 2025-11-02 | -8 | Go-Live | Live - Operational | Met | 20 | 35977 | 6060 | FE-279
SITE-02571 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Warehouse/Ops Hub | Airtel Business | 2026-05-02 |  |  | Site Survey | Cancelled | N/A | 6 | 88557 | 14980 | FE-180
SITE-02572 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Indore | MPLS | Branch | Airtel Business | 2026-07-07 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 4 | 78805 | 7140 | FE-278
SITE-02573 | PRJ-2024028 | CL003 | West | Maharashtra | Nagpur | MPLS | Data Center | Tata Communications | 2026-06-26 |  | 3 | Installation & Commissioning | Civil Work In Progress | At Risk | 6 | 84419 | 15272 | FE-314
SITE-02574 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-02-21 |  | 128 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 100478 | 14059 | FE-255
SITE-02575 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Corporate Office | Excitel Enterprise | 2026-04-03 |  | 87 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 31066 | 10916 | FE-470
SITE-02576 | PRJ-2024028 | CL003 | West | Maharashtra | Thane | MPLS | Corporate Office | Tata Communications | 2026-03-20 |  | 101 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 126065 | 11612 | FE-286
SITE-02577 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Branch | Local ISP Partner | 2025-12-10 | 2026-01-03 | 24 | Go-Live | Live - Operational | Breached | 4 | 102061 | 17301 | FE-187
SITE-02578 | PRJ-2024028 | CL003 | West | Maharashtra | Pune | MPLS | Corporate Office | Sify Technologies | 2026-06-14 | 2026-06-08 | -6 | Go-Live | Live - Operational | Met | 10 | 109224 | 4033 | FE-243
SITE-02579 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | ATM/Off-site | Airtel Business | 2026-01-25 |  | 155 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 53221 | 7551 | FE-205
SITE-02580 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Branch | Tata Communications | 2026-01-30 | 2026-02-11 | 12 | Go-Live | Live - Operational | Breached | 6 | 134114 | 9631 | FE-433
SITE-02581 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | Corporate Office | Sify Technologies | 2025-12-28 | 2026-01-01 | 4 | Go-Live | Live - Operational | Met | 34 | 132361 | 15262 | FE-449
SITE-02582 | PRJ-2024028 | CL003 | West | Maharashtra | Pune | MPLS | Warehouse/Ops Hub | Excitel Enterprise | 2026-04-26 |  | 64 | Site Survey | Survey Complete | Breached | 20 | 119113 | 16334 | FE-206
SITE-02583 | PRJ-2024028 | CL003 | West | Gujarat | Surat | MPLS | Corporate Office | Airtel Business | 2026-07-11 | 2026-07-11 | 0 | Go-Live | Live - Operational | Met | 50 | 49392 | 13200 | FE-318
SITE-02584 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Corporate Office | Excitel Enterprise | 2025-12-05 |  | 206 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 44049 | 5569 | FE-237
SITE-02585 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Data Center | Sify Technologies | 2026-07-12 | 2026-07-05 | -7 | Go-Live | Live - Operational | Met | 50 | 69032 | 17828 | FE-413
SITE-02586 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Data Center | Vodafone Idea Business | 2026-01-04 | 2026-01-09 | 5 | Go-Live | Live - Operational | Met | 10 | 37863 | 11382 | FE-335
SITE-02587 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | Branch | Vodafone Idea Business | 2026-01-08 | 2026-01-05 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 106026 | 16195 | FE-237
SITE-02588 | PRJ-2024028 | CL003 | West | Maharashtra | Thane | MPLS | Corporate Office | Excitel Enterprise | 2026-07-17 | 2026-08-04 | 18 | Go-Live | Live - Operational | Breached | 4 | 104802 | 5669 | FE-192
SITE-02589 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | Branch | Vodafone Idea Business | 2026-05-27 | 2026-05-31 | 4 | Go-Live | Live - Operational | Met | 34 | 58424 | 15338 | FE-305
SITE-02590 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | ATM/Off-site | Local ISP Partner | 2026-03-30 | 2026-04-04 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 61013 | 9776 | FE-152
SITE-02591 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Branch | Vodafone Idea Business | 2026-03-17 |  | 104 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 31466 | 3573 | FE-392
SITE-02592 | PRJ-2024028 | CL003 | West | Gujarat | Vadodara | MPLS | Corporate Office | Tata Communications | 2026-07-10 | 2026-07-09 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 49786 | 15053 | FE-154
SITE-02593 | PRJ-2024028 | CL003 | West | Maharashtra | Nagpur | MPLS | Corporate Office | Tata Communications | 2026-01-26 |  |  | BOM Finalization | Cancelled | N/A | 34 | 40332 | 7938 | FE-207
SITE-02594 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Branch | Sify Technologies | 2026-05-11 |  | 49 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 115318 | 17284 | FE-125
SITE-02595 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Sify Technologies | 2026-03-27 |  | 94 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 107359 | 5578 | FE-291
SITE-02596 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-12-22 | 2026-01-13 | 22 | Go-Live | Live - Operational | Breached | 20 | 110350 | 16572 | FE-445
SITE-02597 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Branch | Sify Technologies | 2026-01-14 |  | 166 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 92571 | 4179 | FE-320
SITE-02598 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | ATM/Off-site | Airtel Business | 2026-01-18 |  | 162 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 105189 | 13159 | FE-385
SITE-02599 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Jabalpur | MPLS | ATM/Off-site | Sify Technologies | 2026-02-28 | 2026-02-21 | -7 | Go-Live | Live - Operational | Met | 100 | 121901 | 12394 | FE-440
SITE-02600 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | Corporate Office | Local ISP Partner | 2025-12-13 | 2025-12-24 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 124369 | 12139 | FE-371
SITE-02601 | PRJ-2024028 | CL003 | West | Gujarat | Surat | MPLS | Data Center | Airtel Business | 2026-05-27 | 2026-06-04 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 131355 | 6316 | FE-109
SITE-02602 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | Warehouse/Ops Hub | Airtel Business | 2025-12-31 |  | 180 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 67995 | 7050 | FE-499
SITE-02603 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | ATM/Off-site | Excitel Enterprise | 2026-06-18 | 2026-07-03 | 15 | Go-Live | Live - Operational | Breached | 6 | 50624 | 6507 | FE-279
SITE-02604 | PRJ-2024028 | CL003 | West | Maharashtra | Mumbai | MPLS | Corporate Office | Local ISP Partner | 2026-01-14 |  | 166 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 50020 | 15901 | FE-253
SITE-02605 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Excitel Enterprise | 2026-03-14 |  | 107 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 51629 | 14086 | FE-106
SITE-02606 | PRJ-2024028 | CL003 | West | Maharashtra | Pune | MPLS | Branch | Sify Technologies | 2026-01-30 | 2026-02-06 | 7 | Go-Live | Live - Operational | Breached | 6 | 105859 | 3687 | FE-106
SITE-02607 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Gwalior | MPLS | Branch | Airtel Business | 2026-06-29 | 2026-07-17 | 18 | Go-Live | Live - Operational | Breached | 50 | 80232 | 3504 | FE-234
SITE-02608 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Data Center | Airtel Business | 2026-03-01 |  | 120 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 36749 | 11318 | FE-245
SITE-02609 | PRJ-2024028 | CL003 | West | Maharashtra | Mumbai | MPLS | Warehouse/Ops Hub | Tata Communications | 2026-01-27 |  | 153 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 124642 | 15956 | FE-143
SITE-02610 | PRJ-2024028 | CL003 | West | Gujarat | Surat | MPLS | ATM/Off-site | Excitel Enterprise | 2026-06-12 |  | 17 | Site Survey | Survey Complete | Breached | 6 | 45625 | 6126 | FE-252
SITE-02611 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Data Center | Tata Communications | 2026-04-29 | 2026-05-03 | 4 | Go-Live | Live - Operational | Met | 2 | 83033 | 3848 | FE-370
SITE-02612 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | Branch | Sify Technologies | 2026-05-16 |  | 44 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 64829 | 10057 | FE-156
SITE-02613 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-03-20 |  | 101 | Site Survey | Survey Scheduled | Breached | 20 | 56624 | 15111 | FE-369
SITE-02614 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | ATM/Off-site | Vodafone Idea Business | 2026-04-24 | 2026-05-04 | 10 | Go-Live | Live - Operational | Breached | 6 | 54199 | 7946 | FE-316
SITE-02615 | PRJ-2024028 | CL003 | West | Maharashtra | Nashik | MPLS | ATM/Off-site | Airtel Business | 2026-05-16 |  | 44 | Site Survey | Survey Scheduled | Breached | 4 | 54946 | 17710 | FE-201
SITE-02616 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Local ISP Partner | 2026-05-12 | 2026-05-18 | 6 | Go-Live | Live - Operational | Breached | 4 | 85052 | 8409 | FE-170
SITE-02617 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Corporate Office | Sify Technologies | 2026-02-26 |  | 123 | Site Survey | Survey Complete | Breached | 4 | 126155 | 6721 | FE-335
SITE-02618 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | Data Center | Excitel Enterprise | 2026-05-16 |  | 44 | Site Survey | Survey Scheduled | Breached | 34 | 90470 | 10384 | FE-485
SITE-02619 | PRJ-2024028 | CL003 | West | Maharashtra | Nashik | MPLS | Warehouse/Ops Hub | Sify Technologies | 2026-01-21 |  |  | BOM Finalization | Cancelled | N/A | 6 | 109746 | 4237 | FE-242
SITE-02620 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Corporate Office | Tata Communications | 2026-02-20 |  | 129 | Site Survey | Survey Scheduled | Breached | 100 | 30591 | 4917 | FE-353
SITE-02621 | PRJ-2024028 | CL003 | West | Gujarat | Surat | MPLS | Branch | Airtel Business | 2026-05-26 | 2026-05-26 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 101447 | 7091 | FE-327
SITE-02622 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | ATM/Off-site | Airtel Business | 2025-12-18 | 2026-01-08 | 21 | Go-Live | Live - Operational | Breached | 20 | 73265 | 10518 | FE-499
SITE-02623 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Data Center | Excitel Enterprise | 2026-06-27 |  | 2 | Equipment Dispatch | Equipment Dispatched | At Risk | 20 | 86803 | 12843 | FE-489
SITE-02624 | PRJ-2024028 | CL003 | West | Maharashtra | Pune | MPLS | Corporate Office | Excitel Enterprise | 2026-07-10 |  | 0 | Site Survey | Survey Complete | On Track | 34 | 125695 | 7192 | FE-293
SITE-02625 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | Branch | Sify Technologies | 2026-04-23 |  | 67 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 50669 | 6741 | FE-364
SITE-02626 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Jabalpur | MPLS | Branch | Excitel Enterprise | 2026-05-15 | 2026-05-05 | -10 | Go-Live | Live - Operational | Met | 34 | 57771 | 11706 | FE-272
SITE-02627 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | ATM/Off-site | Tata Communications | 2026-02-05 |  | 144 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 123173 | 8063 | FE-220
SITE-02628 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Data Center | Excitel Enterprise | 2026-04-26 | 2026-04-30 | 4 | Go-Live | Live - Operational | Met | 4 | 62321 | 14509 | FE-318
SITE-02629 | PRJ-2024028 | CL003 | West | Maharashtra | Nagpur | MPLS | Data Center | Local ISP Partner | 2026-07-03 |  | 0 | Equipment Dispatch | Equipment Dispatched | On Track | 4 | 66482 | 7139 | FE-333
SITE-02630 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | Data Center | Local ISP Partner | 2026-03-26 | 2026-03-19 | -7 | Go-Live | Live - Operational | Met | 50 | 38794 | 12383 | FE-485
SITE-02631 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Jabalpur | MPLS | Data Center | Vodafone Idea Business | 2026-02-02 |  | 147 | Site Survey | Survey Scheduled | Breached | 6 | 117055 | 17866 | FE-298
SITE-02632 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | Branch | Sify Technologies | 2026-06-24 |  | 5 | Installation & Commissioning | Civil Work In Progress | At Risk | 20 | 118964 | 4927 | FE-365
SITE-02633 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Data Center | Local ISP Partner | 2026-01-06 | 2026-01-24 | 18 | Go-Live | Live - Operational | Breached | 6 | 103610 | 17313 | FE-156
SITE-02634 | PRJ-2024028 | CL003 | West | Maharashtra | Thane | MPLS | Data Center | Local ISP Partner | 2026-02-22 | 2026-02-18 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 30678 | 8252 | FE-220
SITE-02635 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | Corporate Office | Tata Communications | 2025-12-07 |  | 204 | Site Survey | Survey Scheduled | Breached | 10 | 120522 | 7562 | FE-327
SITE-02636 | PRJ-2024028 | CL003 | West | Goa | Margao | MPLS | ATM/Off-site | Airtel Business | 2026-04-08 |  | 82 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 79951 | 11414 | FE-430
SITE-02637 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Indore | MPLS | Data Center | Local ISP Partner | 2026-06-26 | 2026-07-11 | 15 | Go-Live | Live - Operational | Breached | 4 | 99826 | 5722 | FE-193
SITE-02638 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | Data Center | Excitel Enterprise | 2026-07-14 |  | 0 | Site Survey | Survey Complete | On Track | 20 | 129725 | 4831 | FE-414
SITE-02639 | PRJ-2024028 | CL003 | West | Maharashtra | Thane | MPLS | Warehouse/Ops Hub | Vodafone Idea Business | 2026-04-08 |  | 82 | Site Survey | Survey Scheduled | Breached | 34 | 56577 | 11731 | FE-489
SITE-02640 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | ATM/Off-site | Excitel Enterprise | 2026-03-29 |  | 92 | Site Survey | Survey Complete | Breached | 50 | 54784 | 8491 | FE-448
SITE-02641 | PRJ-2024028 | CL003 | West | Gujarat | Rajkot | MPLS | Corporate Office | Local ISP Partner | 2025-12-05 |  | 206 | Site Survey | Survey Complete | Breached | 34 | 30871 | 17325 | FE-443
SITE-02642 | PRJ-2024028 | CL003 | West | Goa | Panaji | MPLS | Data Center | Tata Communications | 2026-06-29 | 2026-06-26 | -3 | Go-Live | Live - Operational | Met | 20 | 112923 | 17532 | FE-387
SITE-02643 | PRJ-2024028 | CL003 | West | Madhya Pradesh | Bhopal | MPLS | Data Center | Local ISP Partner | 2026-07-08 |  | 0 | Installation & Commissioning | Civil Work In Progress | On Track | 100 | 31898 | 10170 | FE-300
SITE-02644 | PRJ-2024028 | CL003 | West | Gujarat | Surat | MPLS | Data Center | Airtel Business | 2026-06-12 | 2026-06-06 | -6 | Go-Live | Live - Operational | Met | 2 | 90202 | 6640 | FE-397
SITE-02645 | PRJ-2024028 | CL003 | West | Gujarat | Ahmedabad | MPLS | Warehouse/Ops Hub | Airtel Business | 2026-04-23 |  | 67 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 43728 | 12705 | FE-178
SITE-02646 | PRJ-2024029 | CL004 | South | Andhra Pradesh | Guntur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-06-22 | 2026-07-11 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 39853 | 10996 | FE-477
SITE-02647 | PRJ-2024029 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2026-06-06 |  | 23 | Site Survey | Survey Scheduled | Breached | 20 | 50494 | 10139 | FE-400
SITE-02648 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-12-30 | 2026-01-23 | 24 | Go-Live | Live - Operational | Breached | 10 | 70838 | 8455 | FE-451
SITE-02649 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-12-06 | 2025-12-14 | 8 | Go-Live | Live - Operational | Breached | 50 | 86935 | 3938 | FE-294
SITE-02650 | PRJ-2024029 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-04-14 | 2026-04-25 | 11 | Go-Live | Live - Operational | Breached | 10 | 28261 | 9527 | FE-232
SITE-02651 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-16 | 2026-01-20 | 4 | Go-Live | Live - Operational | Met | 20 | 114335 | 16383 | FE-225
SITE-02652 | PRJ-2024029 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2026-05-27 | 2026-05-21 | -6 | Go-Live | Live - Operational | Met | 4 | 82301 | 11224 | FE-357
SITE-02653 | PRJ-2024029 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2026-02-12 |  | 137 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 116840 | 5366 | FE-275
SITE-02654 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-12-04 | 2025-12-18 | 14 | Go-Live | Live - Operational | Breached | 6 | 113727 | 11872 | FE-147
SITE-02655 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2026-03-02 | 2026-02-22 | -8 | Go-Live | Live - Operational | Met | 2 | 106522 | 6057 | FE-311
SITE-02656 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2026-06-21 |  | 8 | Site Survey | Survey Scheduled | At Risk | 2 | 95263 | 13807 | FE-376
SITE-02657 | PRJ-2024029 | CL004 | South | Karnataka | Hubli | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2026-06-25 |  | 4 | Last Mile Provisioning | Last Mile - ROW Pending | At Risk | 6 | 80705 | 5961 | FE-370
SITE-02658 | PRJ-2024029 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-12-22 |  | 189 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 126600 | 3994 | FE-438
SITE-02659 | PRJ-2024029 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2026-03-20 | 2026-04-11 | 22 | Go-Live | Live - Operational | Breached | 6 | 112093 | 14097 | FE-339
SITE-02660 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2026-02-23 | 2026-03-19 | 24 | Go-Live | Live - Operational | Breached | 4 | 122271 | 13327 | FE-297
SITE-02661 | PRJ-2024029 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2026-02-19 |  | 130 | Site Survey | Survey Scheduled | Breached | 2 | 101068 | 4042 | FE-371
SITE-02662 | PRJ-2024029 | CL004 | South | Tamil Nadu | Chennai | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2026-04-16 | 2026-04-13 | -3 | Go-Live | Live - Operational | Met | 6 | 83217 | 6688 | FE-444
SITE-02663 | PRJ-2024029 | CL004 | South | Telangana | Warangal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-02 | 2026-01-12 | 10 | Go-Live | Live - Operational | Breached | 6 | 112138 | 7646 | FE-271
SITE-02664 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2026-06-26 |  | 3 | Equipment Dispatch | Equipment Dispatched | At Risk | 6 | 29435 | 15555 | FE-482
SITE-02665 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-12-19 | 2026-01-04 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 106206 | 3804 | FE-399
SITE-02666 | PRJ-2024029 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-03-05 | 2026-03-18 | 13 | Go-Live | Live - Operational | Breached | 6 | 100262 | 7862 | FE-391
SITE-02667 | PRJ-2024029 | CL004 | South | Andhra Pradesh | Visakhapatnam | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-11-23 |  | 218 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 113069 | 15968 | FE-329
SITE-02668 | PRJ-2024029 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2026-01-09 | 2026-01-16 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 33508 | 9266 | FE-281
SITE-02669 | PRJ-2024029 | CL004 | South | Tamil Nadu | Trichy | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-03-16 | 2026-03-11 | -5 | Go-Live | Live - Operational | Met | 34 | 130089 | 8061 | FE-447
SITE-02670 | PRJ-2024029 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2026-06-07 |  | 22 | Site Survey | Survey Complete | Breached | 6 | 43578 | 9271 | FE-467
SITE-02671 | PRJ-2024029 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2026-01-10 |  | 170 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 121362 | 10054 | FE-310
SITE-02672 | PRJ-2024029 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2026-01-06 | 2026-01-23 | 17 | Go-Live | Live - Operational | Breached | 50 | 133748 | 11095 | FE-409
SITE-02673 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2026-01-19 |  | 161 | Site Survey | Survey Complete | Breached | 6 | 76867 | 13026 | FE-258
SITE-02674 | PRJ-2024029 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-06-27 |  | 2 | ROW / Permission | On Hold - Client Site Not Ready | At Risk | 2 | 61629 | 6547 | FE-409
SITE-02675 | PRJ-2024029 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-20 | 2026-01-05 | 16 | Go-Live | Live - Operational | Breached | 6 | 29452 | 9788 | FE-313
SITE-02676 | PRJ-2024029 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-04-02 |  | 88 | Site Survey | Survey Scheduled | Breached | 6 | 52791 | 9148 | FE-293
SITE-02677 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2026-04-25 |  | 65 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 56224 | 8752 | FE-484
SITE-02678 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2026-06-17 |  | 12 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 121076 | 11617 | FE-330
SITE-02679 | PRJ-2024029 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2026-06-30 |  | 0 | Site Survey | Survey Complete | On Track | 20 | 43914 | 7547 | FE-230
SITE-02680 | PRJ-2024029 | CL004 | South | Kerala | Kochi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2026-03-21 | 2026-03-27 | 6 | Go-Live | Live - Operational | Breached | 4 | 70909 | 6779 | FE-408
SITE-02681 | PRJ-2024029 | CL004 | South | Kerala | Kozhikode | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-05-22 | 2026-05-17 | -5 | Go-Live | Live - Operational | Met | 50 | 29290 | 3980 | FE-102
SITE-02682 | PRJ-2024029 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-11-20 | 2025-12-05 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 108863 | 15368 | FE-482
SITE-02683 | PRJ-2024029 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-04-23 |  | 67 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 123825 | 12740 | FE-136
SITE-02684 | PRJ-2024029 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-12 | 2025-11-15 | 3 | Go-Live | Live - Operational | Met | 100 | 70126 | 5995 | FE-425
SITE-02685 | PRJ-2024029 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-11-16 | 2025-12-10 | 24 | Go-Live | Live - Operational | Breached | 34 | 115996 | 9787 | FE-252
SITE-02686 | PRJ-2024029 | CL004 | South | Tamil Nadu | Coimbatore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2026-06-28 | 2026-06-23 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 35289 | 11996 | FE-193
SITE-02687 | PRJ-2024029 | CL004 | South | Tamil Nadu | Madurai | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-11-15 | 2025-12-06 | 21 | Go-Live | Live - Operational | Breached | 4 | 109577 | 7776 | FE-386
SITE-02688 | PRJ-2024029 | CL004 | South | Kerala | Thiruvananthapuram | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2026-06-30 | 2026-07-24 | 24 | Go-Live | Live - Operational | Breached | 34 | 80730 | 12248 | FE-167
SITE-02689 | PRJ-2024029 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2026-04-25 |  | 65 | Site Survey | Survey Scheduled | Breached | 2 | 86794 | 13587 | FE-309
SITE-02690 | PRJ-2024029 | CL004 | South | Andhra Pradesh | Vijayawada | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2026-02-26 |  | 123 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 48045 | 15914 | FE-491
SITE-02691 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2026-01-10 | 2026-01-30 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 43796 | 15146 | FE-183
SITE-02692 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2026-04-25 | 2026-04-27 | 2 | Go-Live | Live - Operational | Met | 34 | 81045 | 5088 | FE-106
SITE-02693 | PRJ-2024029 | CL004 | South | Karnataka | Mysuru | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2026-03-14 |  | 107 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 37604 | 11631 | FE-279
SITE-02694 | PRJ-2024029 | CL004 | South | Karnataka | Bengaluru | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-11-30 |  | 211 | Site Survey | Survey Scheduled | Breached | 6 | 33896 | 5902 | FE-455
SITE-02695 | PRJ-2024029 | CL004 | South | Telangana | Hyderabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-28 |  | 183 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 55520 | 11030 | FE-120
SITE-02696 | PRJ-2024030 | CL004 | North | Punjab | Amritsar | Leased Line | Corporate Office | Sify Technologies | 2025-10-05 |  | 267 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 86792 | 8195 | FE-381
SITE-02697 | PRJ-2024030 | CL004 | North | Rajasthan | Jaipur | Leased Line | Branch | Vodafone Idea Business | 2025-12-23 | 2026-01-09 | 17 | Go-Live | Live - Operational | Breached | 50 | 44865 | 16188 | FE-215
SITE-02698 | PRJ-2024030 | CL004 | North | Haryana | Gurugram | Leased Line | Data Center | Sify Technologies | 2026-02-12 | 2026-03-04 | 20 | Go-Live | Live - Operational | Breached | 4 | 129894 | 15903 | FE-411
SITE-02699 | PRJ-2024030 | CL004 | North | Delhi NCR | Faridabad | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-08-27 |  | 306 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 91349 | 14888 | FE-222
SITE-02700 | PRJ-2024030 | CL004 | North | Uttarakhand | Dehradun | Leased Line | Corporate Office | Tata Communications | 2026-01-17 |  | 163 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 74094 | 9783 | FE-198
SITE-02701 | PRJ-2024030 | CL004 | North | Haryana | Gurugram | Leased Line | Branch | Excitel Enterprise | 2026-03-15 |  | 106 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 94700 | 3523 | FE-276
SITE-02702 | PRJ-2024030 | CL004 | North | Haryana | Panchkula | Leased Line | Branch | Sify Technologies | 2025-09-08 |  | 294 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 62153 | 7944 | FE-467
SITE-02703 | PRJ-2024030 | CL004 | North | Rajasthan | Kota | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-11-20 |  | 221 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 80215 | 4268 | FE-431
SITE-02704 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Varanasi | Leased Line | Branch | Excitel Enterprise | 2025-08-31 | 2025-09-08 | 8 | Go-Live | Live - Operational | Breached | 10 | 133009 | 3706 | FE-467
SITE-02705 | PRJ-2024030 | CL004 | North | Haryana | Faridabad | Leased Line | Corporate Office | Tata Communications | 2025-09-18 | 2025-09-30 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 107194 | 16418 | FE-464
SITE-02706 | PRJ-2024030 | CL004 | North | Rajasthan | Jodhpur | Leased Line | Branch | Local ISP Partner | 2025-09-08 | 2025-10-02 | 24 | Go-Live | Live - Operational | Breached | 10 | 105144 | 9768 | FE-301
SITE-02707 | PRJ-2024030 | CL004 | North | Punjab | Jalandhar | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-08-29 |  | 304 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 99301 | 12587 | FE-304
SITE-02708 | PRJ-2024030 | CL004 | North | Uttarakhand | Haridwar | Leased Line | Branch | Local ISP Partner | 2026-02-12 |  | 137 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 98015 | 12355 | FE-106
SITE-02709 | PRJ-2024030 | CL004 | North | Punjab | Amritsar | Leased Line | Corporate Office | Tata Communications | 2025-09-28 | 2025-10-12 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 65025 | 14838 | FE-323
SITE-02710 | PRJ-2024030 | CL004 | North | Uttarakhand | Dehradun | Leased Line | Corporate Office | Local ISP Partner | 2026-02-19 | 2026-02-24 | 5 | Go-Live | Live - Operational | Met | 50 | 45321 | 6778 | FE-128
SITE-02711 | PRJ-2024030 | CL004 | North | Punjab | Jalandhar | Leased Line | Corporate Office | Tata Communications | 2025-11-03 |  | 238 | Site Survey | Survey Scheduled | Breached | 2 | 127888 | 16093 | FE-321
SITE-02712 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Lucknow | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-19 |  | 130 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 33578 | 13274 | FE-186
SITE-02713 | PRJ-2024030 | CL004 | North | Delhi NCR | New Delhi | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-02-14 |  | 135 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 57144 | 4792 | FE-147
SITE-02714 | PRJ-2024030 | CL004 | North | Punjab | Jalandhar | Leased Line | Data Center | Tata Communications | 2026-03-14 | 2026-03-28 | 14 | Go-Live | Live - Operational | Breached | 4 | 71946 | 12300 | FE-241
SITE-02715 | PRJ-2024030 | CL004 | North | Rajasthan | Udaipur | Leased Line | Corporate Office | Airtel Business | 2025-08-31 |  | 302 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 59584 | 6555 | FE-436
SITE-02716 | PRJ-2024030 | CL004 | North | Delhi NCR | New Delhi | Leased Line | Data Center | Tata Communications | 2026-02-02 |  | 147 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 87614 | 16586 | FE-450
SITE-02717 | PRJ-2024030 | CL004 | North | Uttarakhand | Dehradun | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-08-23 | 2025-09-02 | 10 | Go-Live | Live - Operational | Breached | 100 | 116882 | 3614 | FE-343
SITE-02718 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Noida | Leased Line | Corporate Office | Sify Technologies | 2026-02-17 |  | 132 | Site Survey | Survey Complete | Breached | 100 | 123211 | 14939 | FE-129
SITE-02719 | PRJ-2024030 | CL004 | North | Rajasthan | Jodhpur | Leased Line | ATM/Off-site | Tata Communications | 2026-04-05 |  | 85 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 126397 | 4540 | FE-248
SITE-02720 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Lucknow | Leased Line | Corporate Office | Local ISP Partner | 2026-01-12 |  | 168 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 103573 | 7961 | FE-315
SITE-02721 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Varanasi | Leased Line | Data Center | Airtel Business | 2025-09-21 |  | 281 | Site Survey | Survey Complete | Breached | 10 | 70823 | 15019 | FE-488
SITE-02722 | PRJ-2024030 | CL004 | North | Rajasthan | Kota | Leased Line | Branch | Airtel Business | 2025-11-20 | 2025-11-24 | 4 | Go-Live | Live - Operational | Met | 50 | 37656 | 15621 | FE-373
SITE-02723 | PRJ-2024030 | CL004 | North | Haryana | Gurugram | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-22 | 2025-12-13 | 21 | Go-Live | Live - Operational | Breached | 2 | 56322 | 9861 | FE-364
SITE-02724 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Lucknow | Leased Line | Data Center | Airtel Business | 2026-03-15 | 2026-03-11 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 79934 | 9984 | FE-222
SITE-02725 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Lucknow | Leased Line | ATM/Off-site | Local ISP Partner | 2025-08-30 |  | 303 | Site Survey | Survey Complete | Breached | 4 | 112800 | 13875 | FE-319
SITE-02726 | PRJ-2024030 | CL004 | North | Haryana | Gurugram | Leased Line | Warehouse/Ops Hub | Tata Communications | 2026-01-05 |  | 175 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 56358 | 13111 | FE-122
SITE-02727 | PRJ-2024030 | CL004 | North | Rajasthan | Jaipur | Leased Line | Branch | Airtel Business | 2025-09-03 | 2025-09-08 | 5 | Go-Live | Live - Operational | Met | 34 | 45728 | 3881 | FE-411
SITE-02728 | PRJ-2024030 | CL004 | North | Haryana | Faridabad | Leased Line | Data Center | Sify Technologies | 2026-02-11 | 2026-02-13 | 2 | Go-Live | Live - Operational | Met | 100 | 119241 | 13288 | FE-287
SITE-02729 | PRJ-2024030 | CL004 | North | Punjab | Ludhiana | Leased Line | ATM/Off-site | Vodafone Idea Business | 2026-02-01 |  | 148 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 34493 | 13711 | FE-466
SITE-02730 | PRJ-2024030 | CL004 | North | Rajasthan | Kota | Leased Line | Corporate Office | Vodafone Idea Business | 2025-09-22 | 2025-10-11 | 19 | Go-Live | Live - Operational | Breached | 20 | 114715 | 8770 | FE-231
SITE-02731 | PRJ-2024030 | CL004 | North | Haryana | Panchkula | Leased Line | Branch | Sify Technologies | 2025-09-23 |  | 279 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 125932 | 12623 | FE-409
SITE-02732 | PRJ-2024030 | CL004 | North | Haryana | Panchkula | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-11-11 | 2025-11-13 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 101064 | 3766 | FE-422
SITE-02733 | PRJ-2024030 | CL004 | North | Rajasthan | Jaipur | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-06 |  | 174 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 110477 | 9240 | FE-371
SITE-02734 | PRJ-2024030 | CL004 | North | Punjab | Amritsar | Leased Line | Data Center | Vodafone Idea Business | 2026-03-02 | 2026-03-07 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 50003 | 13283 | FE-451
SITE-02735 | PRJ-2024030 | CL004 | North | Haryana | Gurugram | Leased Line | Branch | Sify Technologies | 2025-12-23 | 2026-01-13 | 21 | Go-Live | Live - Operational | Breached | 50 | 77792 | 3697 | FE-220
SITE-02736 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Lucknow | Leased Line | ATM/Off-site | Sify Technologies | 2026-03-22 |  | 99 | Site Survey | Survey Scheduled | Breached | 50 | 31995 | 10834 | FE-105
SITE-02737 | PRJ-2024030 | CL004 | North | Haryana | Faridabad | Leased Line | Data Center | Vodafone Idea Business | 2025-09-27 |  | 275 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 45181 | 6723 | FE-280
SITE-02738 | PRJ-2024030 | CL004 | North | Delhi NCR | Noida | Leased Line | Branch | Tata Communications | 2025-11-20 |  | 221 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 54089 | 14655 | FE-102
SITE-02739 | PRJ-2024030 | CL004 | North | Delhi NCR | Faridabad | Leased Line | Data Center | Vodafone Idea Business | 2026-02-08 | 2026-02-03 | -5 | Go-Live | Live - Operational | Met | 4 | 69423 | 10434 | FE-127
SITE-02740 | PRJ-2024030 | CL004 | North | Haryana | Panchkula | Leased Line | Branch | Sify Technologies | 2026-01-12 |  | 168 | Site Survey | Survey Scheduled | Breached | 6 | 51493 | 7688 | FE-254
SITE-02741 | PRJ-2024030 | CL004 | North | Delhi NCR | Gurugram | Leased Line | Corporate Office | Vodafone Idea Business | 2026-01-17 | 2026-01-27 | 10 | Go-Live | Live - Operational | Breached | 20 | 35420 | 15126 | FE-292
SITE-02742 | PRJ-2024030 | CL004 | North | Haryana | Panchkula | Leased Line | Branch | Local ISP Partner | 2025-10-12 |  | 260 | Site Survey | Survey Complete | Breached | 34 | 119015 | 11160 | FE-398
SITE-02743 | PRJ-2024030 | CL004 | North | Delhi NCR | Noida | Leased Line | Branch | Excitel Enterprise | 2025-12-14 |  | 197 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 127414 | 14034 | FE-368
SITE-02744 | PRJ-2024030 | CL004 | North | Uttarakhand | Haridwar | Leased Line | Corporate Office | Local ISP Partner | 2026-02-25 |  | 124 | Site Survey | Survey Scheduled | Breached | 50 | 104118 | 7019 | FE-319
SITE-02745 | PRJ-2024030 | CL004 | North | Haryana | Faridabad | Leased Line | ATM/Off-site | Sify Technologies | 2026-01-07 | 2026-01-12 | 5 | Go-Live | Live - Operational | Met | 100 | 62582 | 13776 | FE-443
SITE-02746 | PRJ-2024030 | CL004 | North | Rajasthan | Kota | Leased Line | Branch | Sify Technologies | 2026-01-06 |  | 174 | Site Survey | Survey Complete | Breached | 100 | 34445 | 16148 | FE-195
SITE-02747 | PRJ-2024030 | CL004 | North | Punjab | Jalandhar | Leased Line | Branch | Excitel Enterprise | 2025-12-19 |  |  | BOM Finalization | Cancelled | N/A | 20 | 60028 | 17517 | FE-103
SITE-02748 | PRJ-2024030 | CL004 | North | Uttarakhand | Dehradun | Leased Line | ATM/Off-site | Tata Communications | 2025-10-05 |  | 267 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 84686 | 11509 | FE-223
SITE-02749 | PRJ-2024030 | CL004 | North | Punjab | Ludhiana | Leased Line | ATM/Off-site | Local ISP Partner | 2026-02-11 | 2026-03-03 | 20 | Go-Live | Live - Operational | Breached | 6 | 55568 | 12765 | FE-307
SITE-02750 | PRJ-2024030 | CL004 | North | Haryana | Faridabad | Leased Line | ATM/Off-site | Sify Technologies | 2025-10-05 | 2025-10-30 | 25 | Go-Live | Live - Operational | Breached | 10 | 128019 | 6184 | FE-302
SITE-02751 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Varanasi | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-03-27 |  | 94 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 61854 | 6208 | FE-324
SITE-02752 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Kanpur | Leased Line | ATM/Off-site | Airtel Business | 2026-02-16 |  | 133 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 113420 | 5805 | FE-123
SITE-02753 | PRJ-2024030 | CL004 | North | Punjab | Ludhiana | Leased Line | Branch | Excitel Enterprise | 2025-10-04 |  | 268 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 60946 | 14784 | FE-100
SITE-02754 | PRJ-2024030 | CL004 | North | Delhi NCR | Faridabad | Leased Line | ATM/Off-site | Airtel Business | 2025-10-06 |  | 266 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 66448 | 5765 | FE-208
SITE-02755 | PRJ-2024030 | CL004 | North | Haryana | Faridabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2025-09-06 |  | 296 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 107705 | 3648 | FE-444
SITE-02756 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Noida | Leased Line | Corporate Office | Sify Technologies | 2026-03-27 | 2026-03-24 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 44624 | 9873 | FE-129
SITE-02757 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Noida | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-11 |  | 169 | Site Survey | Survey Scheduled | Breached | 4 | 54442 | 12529 | FE-213
SITE-02758 | PRJ-2024030 | CL004 | North | Delhi NCR | New Delhi | Leased Line | Corporate Office | Airtel Business | 2026-02-18 | 2026-03-05 | 15 | Go-Live | Live - Operational | Breached | 10 | 116268 | 6035 | FE-194
SITE-02759 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Kanpur | Leased Line | Data Center | Vodafone Idea Business | 2025-12-23 | 2026-01-10 | 18 | Go-Live | Live - Operational | Breached | 10 | 54706 | 4735 | FE-312
SITE-02760 | PRJ-2024030 | CL004 | North | Uttarakhand | Dehradun | Leased Line | Corporate Office | Local ISP Partner | 2025-11-29 |  | 212 | Site Survey | Survey Complete | Breached | 100 | 31706 | 16650 | FE-326
SITE-02761 | PRJ-2024030 | CL004 | North | Delhi NCR | Gurugram | Leased Line | Branch | Airtel Business | 2025-11-19 |  | 222 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 132539 | 4066 | FE-271
SITE-02762 | PRJ-2024030 | CL004 | North | Rajasthan | Udaipur | Leased Line | Corporate Office | Airtel Business | 2026-01-25 | 2026-02-16 | 22 | Go-Live | Live - Operational | Breached | 20 | 39116 | 15426 | FE-119
SITE-02763 | PRJ-2024030 | CL004 | North | Uttarakhand | Haridwar | Leased Line | Branch | Airtel Business | 2025-11-03 |  | 238 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 63422 | 3803 | FE-445
SITE-02764 | PRJ-2024030 | CL004 | North | Uttarakhand | Haridwar | Leased Line | Corporate Office | Excitel Enterprise | 2026-03-07 |  | 114 | Site Survey | Survey Scheduled | Breached | 6 | 84102 | 10929 | FE-315
SITE-02765 | PRJ-2024030 | CL004 | North | Punjab | Amritsar | Leased Line | Data Center | Airtel Business | 2025-08-19 |  | 314 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 33244 | 7515 | FE-461
SITE-02766 | PRJ-2024030 | CL004 | North | Uttar Pradesh | Kanpur | Leased Line | Corporate Office | Local ISP Partner | 2026-02-04 |  | 145 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 132262 | 7798 | FE-310
SITE-02767 | PRJ-2024030 | CL004 | North | Uttarakhand | Dehradun | Leased Line | Corporate Office | Sify Technologies | 2026-01-12 | 2026-01-21 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 112631 | 13104 | FE-206
SITE-02768 | PRJ-2024030 | CL004 | North | Delhi NCR | Gurugram | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2026-02-13 |  | 136 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 126115 | 12909 | FE-377
SITE-02769 | PRJ-2024030 | CL004 | North | Uttarakhand | Haridwar | Leased Line | Branch | Sify Technologies | 2026-03-09 |  | 112 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 32506 | 13154 | FE-478
SITE-02770 | PRJ-2024030 | CL004 | North | Rajasthan | Udaipur | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-08-22 | 2025-08-26 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 46733 | 16992 | FE-313
SITE-02771 | PRJ-2024031 | CL003 | North | Uttar Pradesh | Noida | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-10-15 | 2025-10-13 | -2 | Go-Live | Live - Operational | Met | 20 | 77939 | 5161 | FE-166
SITE-02772 | PRJ-2024031 | CL003 | North | Delhi NCR | Gurugram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2026-01-31 |  | 149 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 114577 | 17705 | FE-153
SITE-02773 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2026-02-03 | 2026-02-08 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 28535 | 14965 | FE-137
SITE-02774 | PRJ-2024031 | CL003 | North | Punjab | Jalandhar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-01-02 |  | 178 | Site Survey | Survey Scheduled | Breached | 10 | 105539 | 12200 | FE-460
SITE-02775 | PRJ-2024031 | CL003 | North | Haryana | Faridabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-10-27 | 2025-11-11 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 121733 | 11054 | FE-482
SITE-02776 | PRJ-2024031 | CL003 | North | Rajasthan | Kota | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2026-04-17 | 2026-05-09 | 22 | Go-Live | Live - Operational | Breached | 6 | 44877 | 6859 | FE-330
SITE-02777 | PRJ-2024031 | CL003 | North | Rajasthan | Kota | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-12-06 | 2025-12-30 | 24 | Go-Live | Live - Operational | Breached | 50 | 96440 | 4310 | FE-296
SITE-02778 | PRJ-2024031 | CL003 | North | Uttarakhand | Dehradun | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-11-03 |  | 238 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 80535 | 8512 | FE-339
SITE-02779 | PRJ-2024031 | CL003 | North | Uttarakhand | Haridwar | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-09-19 |  | 283 | Site Survey | Survey Complete | Breached | 50 | 118006 | 10771 | FE-419
SITE-02780 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-11-01 |  | 240 | Site Survey | Survey Complete | Breached | 2 | 109382 | 17558 | FE-327
SITE-02781 | PRJ-2024031 | CL003 | North | Punjab | Ludhiana | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2026-04-06 |  | 84 | Site Survey | Survey Complete | Breached | 2 | 103226 | 17918 | FE-172
SITE-02782 | PRJ-2024031 | CL003 | North | Uttar Pradesh | Lucknow | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-12-24 |  | 187 | Site Survey | Survey Complete | Breached | 4 | 82879 | 8786 | FE-282
SITE-02783 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-03-07 |  | 114 | Site Survey | Survey Scheduled | Breached | 20 | 71325 | 11679 | FE-440
SITE-02784 | PRJ-2024031 | CL003 | North | Rajasthan | Kota | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-12-05 | 2025-12-24 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 41090 | 6320 | FE-230
SITE-02785 | PRJ-2024031 | CL003 | North | Uttar Pradesh | Varanasi | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-09-14 | 2025-09-09 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 72247 | 12036 | FE-312
SITE-02786 | PRJ-2024031 | CL003 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2026-03-06 | 2026-03-02 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 78150 | 9281 | FE-230
SITE-02787 | PRJ-2024031 | CL003 | North | Haryana | Gurugram | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-10-27 | 2025-11-02 | 6 | Go-Live | Live - Operational | Breached | 4 | 128904 | 11893 | FE-401
SITE-02788 | PRJ-2024031 | CL003 | North | Rajasthan | Kota | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-09-14 | 2025-09-13 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 98046 | 10476 | FE-108
SITE-02789 | PRJ-2024031 | CL003 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2026-04-11 | 2026-04-21 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 87327 | 3825 | FE-225
SITE-02790 | PRJ-2024031 | CL003 | North | Uttar Pradesh | Kanpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2026-04-26 | 2026-05-05 | 9 | Go-Live | Live - Operational | Breached | 10 | 95199 | 14034 | FE-310
SITE-02791 | PRJ-2024031 | CL003 | North | Delhi NCR | Gurugram | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2026-04-05 | 2026-04-16 | 11 | Go-Live | Live - Operational | Breached | 10 | 31984 | 13473 | FE-497
SITE-02792 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-11-06 | 2025-11-13 | 7 | Go-Live | Live - Operational | Breached | 50 | 111620 | 4584 | FE-410
SITE-02793 | PRJ-2024031 | CL003 | North | Uttar Pradesh | Agra | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-04-23 |  | 67 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 63748 | 9015 | FE-178
SITE-02794 | PRJ-2024031 | CL003 | North | Rajasthan | Udaipur | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-11-05 | 2025-11-18 | 13 | Go-Live | Live - Operational | Breached | 20 | 97026 | 3715 | FE-252
SITE-02795 | PRJ-2024031 | CL003 | North | Haryana | Gurugram | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-11-04 |  | 237 | Site Survey | Survey Scheduled | Breached | 100 | 67210 | 11846 | FE-107
SITE-02796 | PRJ-2024031 | CL003 | North | Rajasthan | Udaipur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2026-02-23 |  | 126 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 116713 | 3808 | FE-272
SITE-02797 | PRJ-2024031 | CL003 | North | Rajasthan | Jaipur | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2026-02-28 | 2026-03-17 | 17 | Go-Live | Live - Operational | Breached | 20 | 63424 | 5910 | FE-433
SITE-02798 | PRJ-2024031 | CL003 | North | Delhi NCR | Gurugram | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-12-12 | 2026-01-04 | 23 | Go-Live | Live - Operational | Breached | 34 | 96234 | 8093 | FE-412
SITE-02799 | PRJ-2024031 | CL003 | North | Delhi NCR | Faridabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-04-17 | 2026-04-26 | 9 | Go-Live | Live - Operational | Breached | 10 | 40631 | 12732 | FE-480
SITE-02800 | PRJ-2024031 | CL003 | North | Uttar Pradesh | Varanasi | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-25 |  | 216 | Site Survey | Survey Scheduled | Breached | 100 | 75523 | 13488 | FE-287
SITE-02801 | PRJ-2024031 | CL003 | North | Delhi NCR | Noida | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2026-01-22 | 2026-02-08 | 17 | Go-Live | Live - Operational | Breached | 6 | 54406 | 3560 | FE-356
SITE-02802 | PRJ-2024031 | CL003 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-03 |  | 208 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 41896 | 12847 | FE-315
SITE-02803 | PRJ-2024031 | CL003 | North | Punjab | Ludhiana | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-03-28 |  | 93 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 32080 | 15572 | FE-429
SITE-02804 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-12-18 |  | 193 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 88194 | 10381 | FE-346
SITE-02805 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-08 | 2025-10-26 | 18 | Go-Live | Live - Operational | Breached | 2 | 78324 | 10100 | FE-193
SITE-02806 | PRJ-2024031 | CL003 | North | Rajasthan | Jodhpur | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2026-02-24 |  | 125 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 134425 | 12177 | FE-491
SITE-02807 | PRJ-2024031 | CL003 | North | Delhi NCR | Faridabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2026-01-19 |  | 161 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 78001 | 16989 | FE-285
SITE-02808 | PRJ-2024031 | CL003 | North | Haryana | Panchkula | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-28 | 2026-01-11 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 83103 | 6002 | FE-220
SITE-02809 | PRJ-2024031 | CL003 | North | Punjab | Amritsar | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-19 |  | 253 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 43603 | 10877 | FE-419
SITE-02810 | PRJ-2024031 | CL003 | North | Rajasthan | Jaipur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2026-04-27 | 2026-04-27 | 0 | Go-Live | Live - Operational | Met | 2 | 32707 | 15106 | FE-490
SITE-02811 | PRJ-2024032 | CL008 | West | Madhya Pradesh | Jabalpur | MPLS | Data Center | Tata Communications | 2026-03-25 | 2026-04-18 | 24 | Go-Live | Live - Operational | Breached | 20 | 134157 | 11135 | FE-328
SITE-02812 | PRJ-2024032 | CL008 | West | Goa | Margao | MPLS | Data Center | Vodafone Idea Business | 2026-01-21 | 2026-02-08 | 18 | Go-Live | Live - Operational | Breached | 34 | 69140 | 6818 | FE-403
SITE-02813 | PRJ-2024032 | CL008 | West | Maharashtra | Thane | MPLS | Branch | Vodafone Idea Business | 2026-01-20 |  | 160 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 88656 | 11924 | FE-133
SITE-02814 | PRJ-2024032 | CL008 | West | Goa | Panaji | MPLS | Branch | Excitel Enterprise | 2025-12-18 | 2026-01-01 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 76443 | 11854 | FE-411
SITE-02815 | PRJ-2024032 | CL008 | West | Madhya Pradesh | Indore | MPLS | Warehouse/Ops Hub | Airtel Business | 2026-03-13 |  | 108 | Site Survey | Survey Complete | Breached | 20 | 100154 | 11884 | FE-326
SITE-02816 | PRJ-2024032 | CL008 | West | Madhya Pradesh | Indore | MPLS | ATM/Off-site | Tata Communications | 2025-08-19 |  | 314 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 80244 | 4798 | FE-177
SITE-02817 | PRJ-2024032 | CL008 | West | Gujarat | Rajkot | MPLS | ATM/Off-site | Tata Communications | 2025-09-10 |  | 292 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 110842 | 17421 | FE-270
SITE-02818 | PRJ-2024032 | CL008 | West | Maharashtra | Thane | MPLS | ATM/Off-site | Excitel Enterprise | 2025-09-08 |  | 294 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 113939 | 16347 | FE-490
SITE-02819 | PRJ-2024032 | CL008 | West | Maharashtra | Thane | MPLS | Data Center | Tata Communications | 2026-03-10 | 2026-03-01 | -9 | Go-Live | Live - Operational | Met | 50 | 78859 | 15218 | FE-489
SITE-02820 | PRJ-2024032 | CL008 | West | Maharashtra | Mumbai | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-12-08 | 2025-12-06 | -2 | Go-Live | Live - Operational | Met | 6 | 105264 | 12590 | FE-173
SITE-02821 | PRJ-2024032 | CL008 | West | Madhya Pradesh | Indore | MPLS | Data Center | Local ISP Partner | 2025-10-23 | 2025-11-14 | 22 | Go-Live | Live - Operational | Breached | 20 | 107622 | 10940 | FE-123
SITE-02822 | PRJ-2024032 | CL008 | West | Gujarat | Vadodara | MPLS | Corporate Office | Vodafone Idea Business | 2025-11-29 | 2025-12-20 | 21 | Go-Live | Live - Operational | Breached | 50 | 95969 | 16327 | FE-473
SITE-02823 | PRJ-2024032 | CL008 | West | Gujarat | Surat | MPLS | Data Center | Tata Communications | 2025-11-12 | 2025-11-29 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 85967 | 7368 | FE-478
SITE-02824 | PRJ-2024032 | CL008 | West | Maharashtra | Pune | MPLS | ATM/Off-site | Tata Communications | 2026-04-01 |  | 89 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 71158 | 9074 | FE-423
SITE-02825 | PRJ-2024032 | CL008 | West | Maharashtra | Nagpur | MPLS | Branch | Sify Technologies | 2026-02-03 |  | 146 | Site Survey | Survey Scheduled | Breached | 6 | 112372 | 5033 | FE-368
SITE-02826 | PRJ-2024033 | CL005 | East | Jharkhand | Ranchi | MPLS | Corporate Office | Sify Technologies | 2025-09-01 |  | 301 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 68786 | 9523 | FE-360
SITE-02827 | PRJ-2024033 | CL005 | East | Assam | Guwahati | MPLS | Branch | Sify Technologies | 2025-07-12 | 2025-07-21 | 9 | Go-Live | Live - Operational | Breached | 100 | 34737 | 14172 | FE-459
SITE-02828 | PRJ-2024033 | CL005 | East | West Bengal | Kolkata | MPLS | Branch | Airtel Business | 2025-12-05 | 2025-12-15 | 10 | Go-Live | Live - Operational | Breached | 50 | 98222 | 10773 | FE-158
SITE-02829 | PRJ-2024033 | CL005 | East | Bihar | Gaya | MPLS | Branch | Local ISP Partner | 2025-11-24 |  | 217 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 104386 | 13967 | FE-324
SITE-02830 | PRJ-2024033 | CL005 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Airtel Business | 2025-07-06 |  | 358 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 133420 | 16246 | FE-421
SITE-02831 | PRJ-2024033 | CL005 | East | Bihar | Gaya | MPLS | Corporate Office | Sify Technologies | 2025-11-01 |  | 240 | Site Survey | Survey Scheduled | Breached | 50 | 90000 | 12912 | FE-250
SITE-02832 | PRJ-2024033 | CL005 | East | West Bengal | Kolkata | MPLS | Data Center | Sify Technologies | 2025-12-25 |  | 186 | Site Survey | Survey Scheduled | Breached | 2 | 36702 | 10577 | FE-211
SITE-02833 | PRJ-2024033 | CL005 | East | Odisha | Rourkela | MPLS | Data Center | Excitel Enterprise | 2025-10-23 | 2025-10-24 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 43600 | 9317 | FE-398
SITE-02834 | PRJ-2024033 | CL005 | East | Jharkhand | Jamshedpur | MPLS | ATM/Off-site | Excitel Enterprise | 2025-12-20 |  | 191 | Site Survey | Survey Scheduled | Breached | 6 | 114841 | 10695 | FE-219
SITE-02835 | PRJ-2024033 | CL005 | East | West Bengal | Siliguri | MPLS | ATM/Off-site | Local ISP Partner | 2025-11-13 |  | 228 | Site Survey | Survey Complete | Breached | 2 | 45918 | 12755 | FE-145
SITE-02836 | PRJ-2024034 | CL008 | South | Telangana | Warangal | Leased Line | Corporate Office | Local ISP Partner | 2026-01-03 |  | 177 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 57723 | 7213 | FE-189
SITE-02837 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Tata Communications | 2026-02-21 |  | 128 | Site Survey | Survey Complete | Breached | 34 | 110159 | 15605 | FE-230
SITE-02838 | PRJ-2024034 | CL008 | South | Kerala | Kochi | Leased Line | Data Center | Tata Communications | 2025-11-05 |  | 236 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 55171 | 8413 | FE-249
SITE-02839 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Data Center | Airtel Business | 2025-09-21 |  | 281 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 73269 | 15673 | FE-423
SITE-02840 | PRJ-2024034 | CL008 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Local ISP Partner | 2025-09-28 |  | 274 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 63092 | 15636 | FE-412
SITE-02841 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Tata Communications | 2025-11-08 | 2025-10-29 | -10 | Go-Live | Live - Operational | Met | 6 | 49703 | 4760 | FE-362
SITE-02842 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Branch | Local ISP Partner | 2025-12-06 |  | 205 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 40960 | 7234 | FE-490
SITE-02843 | PRJ-2024034 | CL008 | South | Telangana | Warangal | Leased Line | Data Center | Local ISP Partner | 2025-11-17 |  | 224 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 120436 | 13179 | FE-230
SITE-02844 | PRJ-2024034 | CL008 | South | Kerala | Kochi | Leased Line | Corporate Office | Tata Communications | 2025-11-19 |  |  | BOM Finalization | Cancelled | N/A | 6 | 105527 | 16777 | FE-468
SITE-02845 | PRJ-2024034 | CL008 | South | Tamil Nadu | Trichy | Leased Line | ATM/Off-site | Airtel Business | 2026-01-04 | 2026-01-19 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 134418 | 5983 | FE-317
SITE-02846 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-19 |  | 161 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 43279 | 12639 | FE-196
SITE-02847 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Branch | Excitel Enterprise | 2025-11-12 |  | 229 | Site Survey | Survey Scheduled | Breached | 50 | 82458 | 10280 | FE-322
SITE-02848 | PRJ-2024034 | CL008 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Sify Technologies | 2025-10-06 | 2025-10-21 | 15 | Go-Live | Live - Operational | Breached | 6 | 134339 | 4025 | FE-168
SITE-02849 | PRJ-2024034 | CL008 | South | Tamil Nadu | Coimbatore | Leased Line | ATM/Off-site | Sify Technologies | 2026-01-12 |  | 168 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 37485 | 6920 | FE-471
SITE-02850 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Data Center | Vodafone Idea Business | 2025-09-12 |  | 290 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 108897 | 15630 | FE-108
SITE-02851 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Branch | Sify Technologies | 2025-12-22 |  | 189 | Site Survey | Survey Scheduled | Breached | 6 | 111317 | 8487 | FE-241
SITE-02852 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-10-01 | 2025-09-26 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 60153 | 16228 | FE-279
SITE-02853 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Corporate Office | Vodafone Idea Business | 2026-02-20 | 2026-02-27 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 46364 | 17730 | FE-292
SITE-02854 | PRJ-2024034 | CL008 | South | Karnataka | Bengaluru | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-10-24 |  | 248 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 77756 | 7074 | FE-134
SITE-02855 | PRJ-2024034 | CL008 | South | Kerala | Kozhikode | Leased Line | Data Center | Excitel Enterprise | 2026-01-22 |  | 158 | Site Survey | Survey Complete | Breached | 34 | 74663 | 13046 | FE-488
SITE-02856 | PRJ-2024034 | CL008 | South | Tamil Nadu | Coimbatore | Leased Line | Data Center | Vodafone Idea Business | 2026-01-09 |  | 171 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 134416 | 5018 | FE-252
SITE-02857 | PRJ-2024034 | CL008 | South | Kerala | Kochi | Leased Line | Corporate Office | Tata Communications | 2025-09-11 | 2025-10-06 | 25 | Go-Live | Live - Operational | Breached | 6 | 125380 | 16633 | FE-271
SITE-02858 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Sify Technologies | 2026-01-18 |  | 162 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 117567 | 7691 | FE-381
SITE-02859 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Visakhapatnam | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-09-02 | 2025-09-26 | 24 | Go-Live | Live - Operational | Breached | 2 | 67412 | 11181 | FE-486
SITE-02860 | PRJ-2024034 | CL008 | South | Tamil Nadu | Coimbatore | Leased Line | Corporate Office | Vodafone Idea Business | 2025-09-20 | 2025-10-03 | 13 | Go-Live | Live - Operational | Breached | 4 | 76993 | 14749 | FE-346
SITE-02861 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Branch | Sify Technologies | 2025-10-17 | 2025-10-12 | -5 | Go-Live | Live - Operational | Met | 100 | 96941 | 11971 | FE-338
SITE-02862 | PRJ-2024034 | CL008 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Sify Technologies | 2025-08-03 | 2025-08-01 | -2 | Go-Live | Live - Operational | Met | 2 | 104436 | 8779 | FE-246
SITE-02863 | PRJ-2024034 | CL008 | South | Tamil Nadu | Trichy | Leased Line | Data Center | Vodafone Idea Business | 2025-12-31 |  | 180 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 95349 | 6683 | FE-126
SITE-02864 | PRJ-2024034 | CL008 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Tata Communications | 2025-07-31 |  | 333 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 59877 | 4905 | FE-259
SITE-02865 | PRJ-2024034 | CL008 | South | Tamil Nadu | Chennai | Leased Line | Corporate Office | Airtel Business | 2025-08-10 | 2025-08-07 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 91095 | 12263 | FE-311
SITE-02866 | PRJ-2024034 | CL008 | South | Tamil Nadu | Chennai | Leased Line | Branch | Excitel Enterprise | 2025-11-19 | 2025-12-14 | 25 | Go-Live | Live - Operational | Breached | 100 | 40755 | 4242 | FE-414
SITE-02867 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Guntur | Leased Line | Data Center | Sify Technologies | 2025-10-07 |  | 265 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 71341 | 15967 | FE-332
SITE-02868 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Branch | Airtel Business | 2025-12-05 |  | 206 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 103784 | 14256 | FE-201
SITE-02869 | PRJ-2024034 | CL008 | South | Tamil Nadu | Chennai | Leased Line | ATM/Off-site | Local ISP Partner | 2025-09-23 |  | 279 | Site Survey | Survey Complete | Breached | 10 | 29603 | 10123 | FE-117
SITE-02870 | PRJ-2024034 | CL008 | South | Karnataka | Bengaluru | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-07-31 | 2025-08-01 | 1 | Go-Live | Live - Operational | Met | 34 | 112807 | 14827 | FE-271
SITE-02871 | PRJ-2024034 | CL008 | South | Karnataka | Hubli | Leased Line | ATM/Off-site | Sify Technologies | 2026-03-09 | 2026-03-08 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 40561 | 8239 | FE-178
SITE-02872 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Branch | Tata Communications | 2025-11-17 |  | 224 | Site Survey | Survey Complete | Breached | 34 | 37881 | 7695 | FE-263
SITE-02873 | PRJ-2024034 | CL008 | South | Kerala | Kozhikode | Leased Line | Data Center | Vodafone Idea Business | 2025-07-22 | 2025-07-18 | -4 | Go-Live | Live - Operational | Met | 10 | 54975 | 17406 | FE-478
SITE-02874 | PRJ-2024034 | CL008 | South | Kerala | Kochi | Leased Line | Corporate Office | Tata Communications | 2025-08-21 | 2025-08-19 | -2 | Go-Live | Live - Operational | Met | 2 | 69879 | 7302 | FE-400
SITE-02875 | PRJ-2024034 | CL008 | South | Tamil Nadu | Coimbatore | Leased Line | Branch | Sify Technologies | 2025-09-01 |  | 301 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 46328 | 14231 | FE-114
SITE-02876 | PRJ-2024034 | CL008 | South | Karnataka | Hubli | Leased Line | Branch | Tata Communications | 2025-12-22 |  | 189 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 127374 | 6903 | FE-231
SITE-02877 | PRJ-2024034 | CL008 | South | Kerala | Thiruvananthapuram | Leased Line | ATM/Off-site | Airtel Business | 2025-09-13 | 2025-09-09 | -4 | Go-Live | Live - Operational | Met | 6 | 75660 | 6474 | FE-364
SITE-02878 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-08-27 | 2025-09-01 | 5 | Go-Live | Live - Operational | Met | 34 | 81965 | 14629 | FE-245
SITE-02879 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-10-03 | 2025-10-04 | 1 | Go-Live | Live - Operational | Met | 20 | 129255 | 16675 | FE-252
SITE-02880 | PRJ-2024034 | CL008 | South | Kerala | Thiruvananthapuram | Leased Line | Branch | Airtel Business | 2026-02-06 |  | 143 | Site Survey | Survey Scheduled | Breached | 20 | 104500 | 11888 | FE-320
SITE-02881 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Vijayawada | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-08-31 | 2025-08-24 | -7 | Go-Live | Live - Operational | Met | 10 | 85313 | 15793 | FE-332
SITE-02882 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Guntur | Leased Line | Corporate Office | Airtel Business | 2025-09-26 | 2025-10-21 | 25 | Go-Live | Live - Operational | Breached | 100 | 58415 | 9336 | FE-307
SITE-02883 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Data Center | Sify Technologies | 2025-09-01 |  |  | BOM Finalization | Cancelled | N/A | 34 | 101756 | 17378 | FE-133
SITE-02884 | PRJ-2024034 | CL008 | South | Telangana | Warangal | Leased Line | Corporate Office | Airtel Business | 2025-08-27 |  | 306 | Site Survey | Survey Complete | Breached | 2 | 109210 | 10324 | FE-313
SITE-02885 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Airtel Business | 2025-11-16 | 2025-11-29 | 13 | Go-Live | Live - Operational | Breached | 50 | 104232 | 14935 | FE-289
SITE-02886 | PRJ-2024034 | CL008 | South | Tamil Nadu | Madurai | Leased Line | Corporate Office | Vodafone Idea Business | 2026-02-02 |  | 147 | Site Survey | Survey Scheduled | Breached | 50 | 122329 | 8706 | FE-441
SITE-02887 | PRJ-2024034 | CL008 | South | Tamil Nadu | Madurai | Leased Line | ATM/Off-site | Local ISP Partner | 2025-12-08 | 2025-12-24 | 16 | Go-Live | Live - Operational | Breached | 34 | 126033 | 7593 | FE-178
SITE-02888 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Data Center | Vodafone Idea Business | 2026-01-27 |  | 153 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 67034 | 5191 | FE-273
SITE-02889 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Vijayawada | Leased Line | Data Center | Airtel Business | 2025-12-29 | 2026-01-17 | 19 | Go-Live | Live - Operational | Breached | 10 | 70464 | 7947 | FE-208
SITE-02890 | PRJ-2024034 | CL008 | South | Telangana | Warangal | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-10-10 |  | 262 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 60289 | 14456 | FE-395
SITE-02891 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | ATM/Off-site | Sify Technologies | 2025-10-26 | 2025-11-19 | 24 | Go-Live | Live - Operational | Breached | 100 | 105363 | 13967 | FE-221
SITE-02892 | PRJ-2024034 | CL008 | South | Kerala | Kozhikode | Leased Line | Branch | Vodafone Idea Business | 2026-02-04 |  | 145 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 74463 | 17597 | FE-214
SITE-02893 | PRJ-2024034 | CL008 | South | Kerala | Kochi | Leased Line | ATM/Off-site | Local ISP Partner | 2025-10-26 | 2025-11-17 | 22 | Go-Live | Live - Operational | Breached | 100 | 39584 | 3978 | FE-225
SITE-02894 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Data Center | Tata Communications | 2025-11-16 | 2025-11-14 | -2 | Go-Live | Live - Operational | Met | 100 | 118588 | 6220 | FE-496
SITE-02895 | PRJ-2024034 | CL008 | South | Karnataka | Bengaluru | Leased Line | Data Center | Vodafone Idea Business | 2025-12-02 | 2025-12-16 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 100867 | 5792 | FE-297
SITE-02896 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Corporate Office | Vodafone Idea Business | 2025-08-20 | 2025-08-17 | -3 | Go-Live | Live - Operational | Met | 10 | 105614 | 16086 | FE-252
SITE-02897 | PRJ-2024034 | CL008 | South | Andhra Pradesh | Visakhapatnam | Leased Line | ATM/Off-site | Local ISP Partner | 2025-10-08 | 2025-10-15 | 7 | Go-Live | Live - Operational | Breached | 6 | 78934 | 17302 | FE-459
SITE-02898 | PRJ-2024034 | CL008 | South | Telangana | Warangal | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-09-08 |  | 294 | Site Survey | Survey Complete | Breached | 4 | 88294 | 5772 | FE-483
SITE-02899 | PRJ-2024034 | CL008 | South | Kerala | Kozhikode | Leased Line | Corporate Office | Tata Communications | 2026-03-05 |  | 116 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 79827 | 16945 | FE-393
SITE-02900 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | ATM/Off-site | Local ISP Partner | 2025-08-15 |  | 318 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 120080 | 9779 | FE-467
SITE-02901 | PRJ-2024034 | CL008 | South | Telangana | Warangal | Leased Line | Data Center | Local ISP Partner | 2025-12-23 | 2026-01-08 | 16 | Go-Live | Live - Operational | Breached | 2 | 81961 | 14672 | FE-381
SITE-02902 | PRJ-2024034 | CL008 | South | Tamil Nadu | Coimbatore | Leased Line | Branch | Tata Communications | 2025-09-12 | 2025-09-26 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 79069 | 5260 | FE-186
SITE-02903 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2025-10-28 | 2025-11-02 | 5 | Go-Live | Live - Operational | Met | 20 | 123863 | 13086 | FE-117
SITE-02904 | PRJ-2024034 | CL008 | South | Karnataka | Bengaluru | Leased Line | Corporate Office | Airtel Business | 2025-09-15 | 2025-09-22 | 7 | Go-Live | Live - Operational | Breached | 100 | 115278 | 10369 | FE-346
SITE-02905 | PRJ-2024034 | CL008 | South | Tamil Nadu | Madurai | Leased Line | Branch | Sify Technologies | 2026-02-06 |  | 143 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 101839 | 12437 | FE-453
SITE-02906 | PRJ-2024034 | CL008 | South | Telangana | Hyderabad | Leased Line | Branch | Vodafone Idea Business | 2025-08-02 |  | 331 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 106708 | 7047 | FE-119
SITE-02907 | PRJ-2024034 | CL008 | South | Karnataka | Mysuru | Leased Line | Branch | Vodafone Idea Business | 2025-08-10 |  | 323 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 65083 | 12975 | FE-435
SITE-02908 | PRJ-2024034 | CL008 | South | Kerala | Kozhikode | Leased Line | Branch | Tata Communications | 2025-08-08 |  | 325 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 114003 | 6146 | FE-119
SITE-02909 | PRJ-2024034 | CL008 | South | Tamil Nadu | Trichy | Leased Line | Data Center | Excitel Enterprise | 2025-08-17 |  | 316 | Site Survey | Survey Scheduled | Breached | 2 | 126040 | 4685 | FE-417
SITE-02910 | PRJ-2024034 | CL008 | South | Kerala | Kochi | Leased Line | Branch | Airtel Business | 2025-09-30 | 2025-09-29 | -1 | Go-Live | Live - Operational | Met | 20 | 93790 | 15668 | FE-268
SITE-02911 | PRJ-2024035 | CL008 | West | Goa | Margao | MPLS | Corporate Office | Airtel Business | 2025-08-21 | 2025-08-24 | 3 | Go-Live | Live - Operational | Met | 4 | 83766 | 4505 | FE-456
SITE-02912 | PRJ-2024035 | CL008 | West | Madhya Pradesh | Bhopal | MPLS | Warehouse/Ops Hub | Tata Communications | 2026-03-08 |  | 113 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 99243 | 9761 | FE-130
SITE-02913 | PRJ-2024035 | CL008 | West | Maharashtra | Nagpur | MPLS | Branch | Vodafone Idea Business | 2025-08-31 |  | 302 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 54644 | 17867 | FE-169
SITE-02914 | PRJ-2024035 | CL008 | West | Maharashtra | Thane | MPLS | Branch | Airtel Business | 2025-10-24 |  | 248 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 88808 | 14461 | FE-102
SITE-02915 | PRJ-2024035 | CL008 | West | Gujarat | Ahmedabad | MPLS | ATM/Off-site | Excitel Enterprise | 2025-08-29 | 2025-08-27 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 110837 | 8400 | FE-262
SITE-02916 | PRJ-2024035 | CL008 | West | Gujarat | Rajkot | MPLS | ATM/Off-site | Vodafone Idea Business | 2025-08-25 |  |  | ROW / Permission | Cancelled | N/A | 100 | 94856 | 9537 | FE-351
SITE-02917 | PRJ-2024035 | CL008 | West | Madhya Pradesh | Jabalpur | MPLS | Warehouse/Ops Hub | Tata Communications | 2025-09-23 |  | 279 | Site Survey | Survey Scheduled | Breached | 10 | 100628 | 16420 | FE-140
SITE-02918 | PRJ-2024035 | CL008 | West | Maharashtra | Nashik | MPLS | Data Center | Tata Communications | 2026-01-10 | 2026-01-08 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 50193 | 7587 | FE-428
SITE-02919 | PRJ-2024035 | CL008 | West | Gujarat | Ahmedabad | MPLS | Branch | Local ISP Partner | 2025-10-17 | 2025-10-13 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 38800 | 8997 | FE-211
SITE-02920 | PRJ-2024035 | CL008 | West | Goa | Panaji | MPLS | Data Center | Local ISP Partner | 2026-01-05 |  | 175 | Site Survey | Survey Complete | Breached | 6 | 78926 | 4588 | FE-308
SITE-02921 | PRJ-2024035 | CL008 | West | Goa | Margao | MPLS | ATM/Off-site | Local ISP Partner | 2025-09-17 | 2025-09-22 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 124940 | 8609 | FE-138
SITE-02922 | PRJ-2024035 | CL008 | West | Maharashtra | Pune | MPLS | Corporate Office | Vodafone Idea Business | 2025-11-07 |  | 234 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 120744 | 11143 | FE-398
SITE-02923 | PRJ-2024035 | CL008 | West | Goa | Margao | MPLS | Warehouse/Ops Hub | Sify Technologies | 2025-11-13 |  | 228 | Site Survey | Survey Scheduled | Breached | 10 | 35648 | 4001 | FE-289
SITE-02924 | PRJ-2024035 | CL008 | West | Maharashtra | Thane | MPLS | Corporate Office | Vodafone Idea Business | 2026-02-01 |  | 148 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 73595 | 14369 | FE-305
SITE-02925 | PRJ-2024035 | CL008 | West | Gujarat | Vadodara | MPLS | Warehouse/Ops Hub | Sify Technologies | 2026-02-21 |  | 128 | Site Survey | Survey Complete | Breached | 6 | 52147 | 10844 | FE-426
SITE-02926 | PRJ-2024035 | CL008 | West | Maharashtra | Nashik | MPLS | ATM/Off-site | Local ISP Partner | 2025-11-13 | 2025-11-28 | 15 | Go-Live | Live - Operational | Breached | 34 | 81096 | 9512 | FE-113
SITE-02927 | PRJ-2024035 | CL008 | West | Goa | Margao | MPLS | Branch | Tata Communications | 2025-12-05 | 2025-11-26 | -9 | Go-Live | Live - Operational | Met | 20 | 113709 | 7996 | FE-156
SITE-02928 | PRJ-2024035 | CL008 | West | Gujarat | Ahmedabad | MPLS | Data Center | Airtel Business | 2025-12-14 |  | 197 | Site Survey | Survey Complete | Breached | 20 | 33311 | 16401 | FE-458
SITE-02929 | PRJ-2024035 | CL008 | West | Madhya Pradesh | Bhopal | MPLS | Data Center | Excitel Enterprise | 2025-08-06 | 2025-08-22 | 16 | Go-Live | Live - Operational | Breached | 2 | 116121 | 7955 | FE-488
SITE-02930 | PRJ-2024035 | CL008 | West | Maharashtra | Nashik | MPLS | Branch | Vodafone Idea Business | 2025-12-21 | 2025-12-20 | -1 | Go-Live | Live - Operational | Met | 50 | 50085 | 6648 | FE-356
SITE-02931 | PRJ-2024035 | CL008 | West | Maharashtra | Mumbai | MPLS | ATM/Off-site | Airtel Business | 2026-03-16 | 2026-04-05 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 46720 | 12547 | FE-175
SITE-02932 | PRJ-2024035 | CL008 | West | Gujarat | Surat | MPLS | Corporate Office | Tata Communications | 2025-09-14 |  | 288 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 89740 | 8853 | FE-179
SITE-02933 | PRJ-2024035 | CL008 | West | Gujarat | Vadodara | MPLS | Warehouse/Ops Hub | Sify Technologies | 2026-01-04 |  | 176 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 28168 | 7971 | FE-147
SITE-02934 | PRJ-2024035 | CL008 | West | Maharashtra | Thane | MPLS | ATM/Off-site | Sify Technologies | 2025-11-29 | 2025-11-26 | -3 | Go-Live | Live - Operational | Met | 4 | 120344 | 5391 | FE-226
SITE-02935 | PRJ-2024035 | CL008 | West | Goa | Panaji | MPLS | Data Center | Airtel Business | 2025-09-24 | 2025-09-29 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 128419 | 14037 | FE-371
SITE-02936 | PRJ-2024036 | CL002 | West | Gujarat | Ahmedabad | Leased Line | Branch | Local ISP Partner | 2025-05-20 |  | 405 | Site Survey | Survey Scheduled | Breached | 34 | 92143 | 12618 | FE-120
SITE-02937 | PRJ-2024036 | CL002 | West | Madhya Pradesh | Indore | Leased Line | Branch | Tata Communications | 2025-04-08 | 2025-05-02 | 24 | Go-Live | Live - Operational | Breached | 2 | 67334 | 5176 | FE-418
SITE-02938 | PRJ-2024036 | CL002 | West | Goa | Margao | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-05-23 | 2025-05-17 | -6 | Go-Live | Live - Operational | Met | 6 | 131106 | 15986 | FE-361
SITE-02939 | PRJ-2024036 | CL002 | West | Maharashtra | Nagpur | Leased Line | Data Center | Vodafone Idea Business | 2025-07-05 | 2025-07-17 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 124044 | 17979 | FE-421
SITE-02940 | PRJ-2024036 | CL002 | West | Gujarat | Ahmedabad | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2025-03-28 | 2025-04-19 | 22 | Go-Live | Live - Operational | Breached | 10 | 30958 | 9816 | FE-213
SITE-02941 | PRJ-2024036 | CL002 | West | Goa | Margao | Leased Line | Branch | Local ISP Partner | 2025-08-18 |  | 315 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 88903 | 12647 | FE-399
SITE-02942 | PRJ-2024036 | CL002 | West | Maharashtra | Pune | Leased Line | Corporate Office | Airtel Business | 2025-05-02 | 2025-05-20 | 18 | Go-Live | Live - Operational | Breached | 50 | 106153 | 12932 | FE-107
SITE-02943 | PRJ-2024036 | CL002 | West | Goa | Margao | Leased Line | Corporate Office | Vodafone Idea Business | 2025-05-28 |  | 397 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 105641 | 12874 | FE-256
SITE-02944 | PRJ-2024036 | CL002 | West | Maharashtra | Thane | Leased Line | Branch | Vodafone Idea Business | 2025-04-23 | 2025-05-06 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 102244 | 13946 | FE-125
SITE-02945 | PRJ-2024036 | CL002 | West | Goa | Margao | Leased Line | Data Center | Tata Communications | 2025-07-18 | 2025-08-11 | 24 | Go-Live | Live - Operational | Breached | 50 | 36739 | 15425 | FE-124
SITE-02946 | PRJ-2024036 | CL002 | West | Madhya Pradesh | Jabalpur | Leased Line | ATM/Off-site | Airtel Business | 2025-07-02 |  | 362 | Site Survey | Survey Scheduled | Breached | 100 | 127109 | 7978 | FE-290
SITE-02947 | PRJ-2024036 | CL002 | West | Madhya Pradesh | Bhopal | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-06-17 | 2025-06-27 | 10 | Go-Live | Live - Operational | Breached | 50 | 40220 | 7148 | FE-314
SITE-02948 | PRJ-2024036 | CL002 | West | Maharashtra | Nagpur | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-10-23 |  | 249 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 74886 | 7103 | FE-425
SITE-02949 | PRJ-2024036 | CL002 | West | Maharashtra | Thane | Leased Line | Data Center | Excitel Enterprise | 2025-04-25 | 2025-05-05 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 111905 | 13541 | FE-303
SITE-02950 | PRJ-2024036 | CL002 | West | Goa | Margao | Leased Line | Data Center | Airtel Business | 2025-07-02 | 2025-07-21 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 133212 | 17859 | FE-104
SITE-02951 | PRJ-2024036 | CL002 | West | Goa | Panaji | Leased Line | Corporate Office | Airtel Business | 2025-09-13 | 2025-09-12 | -1 | Go-Live | Live - Operational | Met | 10 | 67515 | 11893 | FE-102
SITE-02952 | PRJ-2024036 | CL002 | West | Maharashtra | Nagpur | Leased Line | Corporate Office | Tata Communications | 2025-07-01 | 2025-06-29 | -2 | Go-Live | Live - Operational | Met | 34 | 72827 | 7540 | FE-303
SITE-02953 | PRJ-2024036 | CL002 | West | Maharashtra | Nagpur | Leased Line | Corporate Office | Vodafone Idea Business | 2025-06-01 |  | 393 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 104671 | 3971 | FE-296
SITE-02954 | PRJ-2024036 | CL002 | West | Gujarat | Rajkot | Leased Line | Data Center | Tata Communications | 2025-09-30 |  | 272 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 64379 | 6195 | FE-288
SITE-02955 | PRJ-2024036 | CL002 | West | Madhya Pradesh | Bhopal | Leased Line | ATM/Off-site | Local ISP Partner | 2025-09-18 | 2025-09-21 | 3 | Go-Live | Live - Operational | Met | 6 | 109341 | 16522 | FE-273
SITE-02956 | PRJ-2024036 | CL002 | West | Goa | Margao | Leased Line | Corporate Office | Local ISP Partner | 2025-05-02 | 2025-04-27 | -5 | Go-Live | Live - Operational | Met | 6 | 96860 | 9838 | FE-215
SITE-02957 | PRJ-2024036 | CL002 | West | Maharashtra | Nagpur | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-10-26 | 2025-10-24 | -2 | Go-Live | Live - Operational | Met | 50 | 52093 | 17946 | FE-453
SITE-02958 | PRJ-2024036 | CL002 | West | Maharashtra | Nashik | Leased Line | Corporate Office | Airtel Business | 2025-04-01 | 2025-04-22 | 21 | Go-Live | Live - Operational | Breached | 6 | 45173 | 3933 | FE-254
SITE-02959 | PRJ-2024036 | CL002 | West | Maharashtra | Nashik | Leased Line | ATM/Off-site | Tata Communications | 2025-07-23 |  | 341 | Site Survey | Survey Scheduled | Breached | 34 | 117718 | 7444 | FE-402
SITE-02960 | PRJ-2024036 | CL002 | West | Gujarat | Rajkot | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-08-08 |  | 325 | Site Survey | Survey Complete | Breached | 2 | 79932 | 7125 | FE-164
SITE-02961 | PRJ-2024036 | CL002 | West | Goa | Panaji | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-04-07 | 2025-04-11 | 4 | Go-Live | Live - Operational | Met | 2 | 67592 | 12210 | FE-499
SITE-02962 | PRJ-2024036 | CL002 | West | Goa | Panaji | Leased Line | Data Center | Tata Communications | 2025-04-14 | 2025-04-06 | -8 | Go-Live | Live - Operational | Met | 2 | 41925 | 12944 | FE-222
SITE-02963 | PRJ-2024036 | CL002 | West | Gujarat | Surat | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-08-12 |  | 321 | Site Survey | Survey Complete | Breached | 100 | 39108 | 13391 | FE-131
SITE-02964 | PRJ-2024036 | CL002 | West | Maharashtra | Mumbai | Leased Line | ATM/Off-site | Local ISP Partner | 2025-03-12 |  | 474 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 84398 | 5129 | FE-292
SITE-02965 | PRJ-2024036 | CL002 | West | Gujarat | Surat | Leased Line | Corporate Office | Local ISP Partner | 2025-06-11 | 2025-06-28 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 36387 | 11923 | FE-478
SITE-02966 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | Branch | Local ISP Partner | 2025-04-06 |  | 449 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 103938 | 13685 | FE-173
SITE-02967 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Local ISP Partner | 2025-08-08 | 2025-08-27 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 45919 | 15671 | FE-219
SITE-02968 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Data Center | Vodafone Idea Business | 2025-06-26 |  | 368 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 65337 | 8931 | FE-292
SITE-02969 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-03-31 |  | 455 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 130546 | 15625 | FE-160
SITE-02970 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | Branch | Local ISP Partner | 2025-07-09 | 2025-07-05 | -4 | Go-Live | Live - Operational | Met | 100 | 93398 | 10510 | FE-315
SITE-02971 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | Data Center | Local ISP Partner | 2025-04-15 | 2025-04-16 | 1 | Go-Live | Live - Operational | Met | 50 | 36768 | 5548 | FE-113
SITE-02972 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Data Center | Excitel Enterprise | 2025-07-01 |  |  | BOM Finalization | Cancelled | N/A | 2 | 81317 | 14349 | FE-137
SITE-02973 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Vodafone Idea Business | 2025-03-20 | 2025-03-14 | -6 | Go-Live | Live - Operational | Met | 100 | 110059 | 12463 | FE-448
SITE-02974 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | Data Center | Local ISP Partner | 2025-06-27 |  | 367 | Site Survey | Survey Complete | Breached | 50 | 54803 | 8993 | FE-225
SITE-02975 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Excitel Enterprise | 2025-07-11 | 2025-08-01 | 21 | Go-Live | Live - Operational | Breached | 34 | 104778 | 6044 | FE-136
SITE-02976 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Local ISP Partner | 2025-05-29 |  | 396 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 82274 | 7115 | FE-354
SITE-02977 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-08-21 | 2025-08-20 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 30827 | 4156 | FE-114
SITE-02978 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-02 | 2025-08-04 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 59888 | 15018 | FE-457
SITE-02979 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Excitel Enterprise | 2025-03-24 | 2025-04-10 | 17 | Go-Live | Live - Operational | Breached | 50 | 77805 | 13536 | FE-206
SITE-02980 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Tata Communications | 2025-07-18 |  | 346 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 114390 | 12572 | FE-203
SITE-02981 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Corporate Office | Airtel Business | 2025-06-11 | 2025-06-08 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 33405 | 5044 | FE-150
SITE-02982 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | Corporate Office | Airtel Business | 2025-08-10 |  | 323 | Site Survey | Survey Complete | Breached | 50 | 79500 | 8297 | FE-194
SITE-02983 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Branch | Airtel Business | 2025-08-28 | 2025-09-10 | 13 | Go-Live | Live - Operational | Breached | 100 | 51996 | 8081 | FE-261
SITE-02984 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | Data Center | Sify Technologies | 2025-05-22 | 2025-06-04 | 13 | Go-Live | Live - Operational | Breached | 50 | 108425 | 11188 | FE-310
SITE-02985 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-02 |  | 453 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 49585 | 8065 | FE-395
SITE-02986 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | Data Center | Local ISP Partner | 2025-01-22 | 2025-01-31 | 9 | Go-Live | Live - Operational | Breached | 6 | 69274 | 3595 | FE-311
SITE-02987 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Tata Communications | 2025-04-25 | 2025-05-07 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 116102 | 4388 | FE-315
SITE-02988 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Data Center | Airtel Business | 2025-07-18 |  | 346 | Site Survey | Survey Scheduled | Breached | 10 | 124953 | 8735 | FE-459
SITE-02989 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | ATM/Off-site | Sify Technologies | 2025-08-04 |  | 329 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 46151 | 4695 | FE-167
SITE-02990 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Tata Communications | 2025-08-27 |  | 306 | Site Survey | Survey Scheduled | Breached | 6 | 47312 | 16401 | FE-200
SITE-02991 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Branch | Sify Technologies | 2025-06-06 |  | 388 | Site Survey | Survey Scheduled | Breached | 34 | 92585 | 15346 | FE-390
SITE-02992 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-02-15 |  | 499 | Site Survey | Survey Complete | Breached | 2 | 88156 | 3896 | FE-204
SITE-02993 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-04-01 | 2025-04-19 | 18 | Go-Live | Live - Operational | Breached | 6 | 129472 | 7481 | FE-198
SITE-02994 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | Corporate Office | Sify Technologies | 2025-01-31 |  |  | ROW / Permission | Cancelled | N/A | 4 | 122079 | 9966 | FE-349
SITE-02995 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Data Center | Local ISP Partner | 2025-04-28 | 2025-04-30 | 2 | Go-Live | Live - Operational | Met | 10 | 115936 | 5803 | FE-366
SITE-02996 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | ATM/Off-site | Airtel Business | 2025-02-14 | 2025-02-08 | -6 | Go-Live | Live - Operational | Met | 2 | 34423 | 15297 | FE-446
SITE-02997 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-04-26 | 2025-05-02 | 6 | Go-Live | Live - Operational | Breached | 10 | 126662 | 6981 | FE-316
SITE-02998 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | ATM/Off-site | Local ISP Partner | 2025-08-07 | 2025-08-29 | 22 | Go-Live | Live - Operational | Breached | 50 | 93374 | 15358 | FE-478
SITE-02999 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Local ISP Partner | 2025-01-19 |  | 526 | Site Survey | Survey Complete | Breached | 20 | 107506 | 8186 | FE-322
SITE-03000 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Data Center | Sify Technologies | 2025-04-21 |  | 434 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 42906 | 17706 | FE-196
SITE-03001 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Branch | Excitel Enterprise | 2025-04-21 |  | 434 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 77047 | 4317 | FE-434
SITE-03002 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Vodafone Idea Business | 2025-09-04 | 2025-09-15 | 11 | Go-Live | Live - Operational | Breached | 4 | 90284 | 9152 | FE-371
SITE-03003 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-05-31 | 2025-06-22 | 22 | Go-Live | Live - Operational | Breached | 2 | 65465 | 7682 | FE-426
SITE-03004 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | ATM/Off-site | Tata Communications | 2025-02-01 | 2025-02-04 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 81171 | 9807 | FE-360
SITE-03005 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | Corporate Office | Airtel Business | 2025-03-12 |  | 474 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 63971 | 11938 | FE-430
SITE-03006 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Excitel Enterprise | 2025-05-14 | 2025-05-19 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 53832 | 4189 | FE-419
SITE-03007 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Vodafone Idea Business | 2025-05-29 |  | 396 | Site Survey | Survey Complete | Breached | 20 | 86638 | 5302 | FE-349
SITE-03008 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-02-09 | 2025-02-01 | -8 | Go-Live | Live - Operational | Met | 4 | 81057 | 13433 | FE-369
SITE-03009 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Branch | Tata Communications | 2025-02-12 |  |  | BOM Finalization | Cancelled | N/A | 34 | 95627 | 9877 | FE-317
SITE-03010 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | Data Center | Vodafone Idea Business | 2025-06-11 | 2025-07-01 | 20 | Go-Live | Live - Operational | Breached | 34 | 103909 | 15556 | FE-464
SITE-03011 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Data Center | Tata Communications | 2025-05-02 | 2025-04-26 | -6 | Go-Live | Live - Operational | Met | 34 | 31681 | 8953 | FE-374
SITE-03012 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-03-23 | 2025-04-04 | 12 | Go-Live | Live - Operational | Breached | 34 | 83310 | 8860 | FE-325
SITE-03013 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-04-20 | 2025-04-25 | 5 | Go-Live | Live - Operational | Met | 6 | 65000 | 6108 | FE-298
SITE-03014 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | Corporate Office | Excitel Enterprise | 2025-05-16 | 2025-06-05 | 20 | Go-Live | Live - Operational | Breached | 2 | 36720 | 14662 | FE-269
SITE-03015 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Data Center | Excitel Enterprise | 2025-06-06 |  | 388 | Site Survey | Survey Scheduled | Breached | 10 | 28563 | 16849 | FE-497
SITE-03016 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Airtel Business | 2025-08-06 | 2025-08-28 | 22 | Go-Live | Live - Operational | Breached | 6 | 88558 | 6428 | FE-345
SITE-03017 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | ATM/Off-site | Sify Technologies | 2025-06-09 |  | 385 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 37126 | 13952 | FE-289
SITE-03018 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Sify Technologies | 2025-02-18 | 2025-03-01 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 41958 | 7408 | FE-102
SITE-03019 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | ATM/Off-site | Local ISP Partner | 2025-06-03 | 2025-06-23 | 20 | Go-Live | Live - Operational | Breached | 2 | 111743 | 10982 | FE-491
SITE-03020 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Data Center | Vodafone Idea Business | 2025-08-08 |  | 325 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 125897 | 15880 | FE-159
SITE-03021 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Data Center | Local ISP Partner | 2025-04-08 | 2025-04-06 | -2 | Go-Live | Live - Operational | Met | 50 | 54007 | 3517 | FE-499
SITE-03022 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Airtel Business | 2025-09-06 |  | 296 | Site Survey | Survey Scheduled | Breached | 4 | 34298 | 17054 | FE-172
SITE-03023 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | Data Center | Airtel Business | 2025-04-02 | 2025-04-10 | 8 | Go-Live | Live - Operational | Breached | 2 | 73717 | 15605 | FE-437
SITE-03024 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-02-10 |  | 504 | Site Survey | Survey Scheduled | Breached | 50 | 43769 | 14605 | FE-396
SITE-03025 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-20 |  | 435 | Site Survey | Survey Complete | Breached | 34 | 129171 | 10033 | FE-306
SITE-03026 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-01-27 | 2025-02-10 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 96683 | 17503 | FE-220
SITE-03027 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-01-21 | 2025-01-12 | -9 | Go-Live | Live - Operational | Met | 34 | 47967 | 6145 | FE-244
SITE-03028 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Airtel Business | 2025-07-18 |  | 346 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 109807 | 6781 | FE-455
SITE-03029 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Corporate Office | Airtel Business | 2025-06-14 | 2025-06-08 | -6 | Go-Live | Live - Operational | Met | 2 | 88116 | 3848 | FE-285
SITE-03030 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Data Center | Tata Communications | 2025-03-20 |  | 466 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 71853 | 11574 | FE-427
SITE-03031 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Tata Communications | 2025-01-26 | 2025-02-13 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 80031 | 15113 | FE-177
SITE-03032 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-05-26 | 2025-05-18 | -8 | Go-Live | Live - Operational | Met | 34 | 101469 | 12868 | FE-467
SITE-03033 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Excitel Enterprise | 2025-09-06 |  | 296 | Site Survey | Survey Scheduled | Breached | 100 | 100916 | 17490 | FE-204
SITE-03034 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | ATM/Off-site | Sify Technologies | 2025-05-26 | 2025-06-06 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 39699 | 13332 | FE-195
SITE-03035 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Data Center | Excitel Enterprise | 2025-04-30 |  | 425 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 61049 | 9798 | FE-224
SITE-03036 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | ATM/Off-site | Tata Communications | 2025-07-09 | 2025-07-11 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 40008 | 11607 | FE-454
SITE-03037 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-04-20 |  | 435 | Site Survey | Survey Scheduled | Breached | 6 | 68681 | 9936 | FE-375
SITE-03038 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Jabalpur | Leased Line | ATM/Off-site | Local ISP Partner | 2025-09-04 |  | 298 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 115793 | 5605 | FE-248
SITE-03039 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Excitel Enterprise | 2025-07-12 | 2025-07-11 | -1 | Go-Live | Live - Operational | Met | 50 | 115041 | 4313 | FE-144
SITE-03040 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-04-08 | 2025-04-03 | -5 | Go-Live | Live - Operational | Met | 34 | 64674 | 6915 | FE-173
SITE-03041 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | ATM/Off-site | Local ISP Partner | 2025-07-02 |  | 362 | Site Survey | Survey Complete | Breached | 2 | 112536 | 14904 | FE-471
SITE-03042 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | ATM/Off-site | Vodafone Idea Business | 2025-09-04 | 2025-09-12 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 134407 | 3710 | FE-145
SITE-03043 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-01-26 |  | 519 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 36646 | 12561 | FE-327
SITE-03044 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Airtel Business | 2025-08-23 | 2025-09-04 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 72030 | 14952 | FE-242
SITE-03045 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Warehouse/Ops Hub | Airtel Business | 2025-08-30 |  | 303 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 109479 | 15617 | FE-217
SITE-03046 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Data Center | Vodafone Idea Business | 2025-03-14 |  | 472 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 39602 | 7472 | FE-494
SITE-03047 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-06-02 | 2025-05-24 | -9 | Go-Live | Live - Operational | Met | 6 | 45970 | 14549 | FE-425
SITE-03048 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | Warehouse/Ops Hub | Sify Technologies | 2025-08-23 | 2025-09-11 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 119410 | 7701 | FE-493
SITE-03049 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Bhopal | Leased Line | ATM/Off-site | Tata Communications | 2025-09-07 | 2025-09-24 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 32762 | 9215 | FE-448
SITE-03050 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Data Center | Airtel Business | 2025-08-25 | 2025-09-11 | 17 | Go-Live | Live - Operational | Breached | 100 | 109098 | 11754 | FE-248
SITE-03051 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Local ISP Partner | 2025-06-15 |  | 379 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 46341 | 14432 | FE-316
SITE-03052 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Local ISP Partner | 2025-07-23 |  | 341 | Site Survey | Survey Complete | Breached | 2 | 127282 | 15435 | FE-153
SITE-03053 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Branch | Excitel Enterprise | 2025-05-19 |  | 406 | Site Survey | Survey Scheduled | Breached | 100 | 90746 | 10022 | FE-164
SITE-03054 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-05-07 | 2025-05-31 | 24 | Go-Live | Live - Operational | Breached | 34 | 31221 | 4938 | FE-473
SITE-03055 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Indore | Leased Line | ATM/Off-site | Excitel Enterprise | 2025-04-29 |  | 426 | Site Survey | Survey Scheduled | Breached | 6 | 52127 | 10465 | FE-321
SITE-03056 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Tata Communications | 2025-08-17 |  | 316 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 86660 | 14044 | FE-303
SITE-03057 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Warehouse/Ops Hub | Local ISP Partner | 2025-03-01 | 2025-03-01 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 88791 | 8274 | FE-397
SITE-03058 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Branch | Airtel Business | 2025-06-03 |  | 391 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 72747 | 13698 | FE-344
SITE-03059 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-08 | 2025-05-18 | 10 | Go-Live | Live - Operational | Breached | 50 | 66847 | 3908 | FE-381
SITE-03060 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Branch | Sify Technologies | 2025-06-02 |  | 392 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 37494 | 15142 | FE-248
SITE-03061 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Corporate Office | Vodafone Idea Business | 2025-09-02 | 2025-09-16 | 14 | Go-Live | Live - Operational | Breached | 10 | 102928 | 4646 | FE-171
SITE-03062 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-10 | 2025-08-07 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 38522 | 14121 | FE-158
SITE-03063 | PRJ-2024037 | CL002 | Central | Madhya Pradesh | Gwalior | Leased Line | Branch | Tata Communications | 2025-01-31 | 2025-02-13 | 13 | Go-Live | Live - Operational | Breached | 6 | 62326 | 7919 | FE-404
SITE-03064 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Bilaspur | Leased Line | Data Center | Sify Technologies | 2025-08-18 |  | 315 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 34526 | 13763 | FE-219
SITE-03065 | PRJ-2024037 | CL002 | Central | Chhattisgarh | Raipur | Leased Line | Branch | Tata Communications | 2025-03-08 |  | 478 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 123824 | 17871 | FE-176
SITE-03066 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Data Center | Local ISP Partner | 2026-02-08 | 2026-03-02 | 22 | Go-Live | Live - Operational | Breached | 2 | 92671 | 8009 | FE-187
SITE-03067 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2026-02-13 |  | 136 | Site Survey | Survey Complete | Breached | 6 | 51744 | 6155 | FE-216
SITE-03068 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Branch | Local ISP Partner | 2025-10-20 |  | 252 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 78389 | 6254 | FE-121
SITE-03069 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Branch | Airtel Business | 2025-10-17 |  | 255 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 130956 | 6330 | FE-297
SITE-03070 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Corporate Office | Airtel Business | 2026-02-23 | 2026-03-13 | 18 | Go-Live | Live - Operational | Breached | 100 | 131888 | 15538 | FE-425
SITE-03071 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Data Center | Local ISP Partner | 2026-03-23 |  |  | BOM Finalization | Cancelled | N/A | 4 | 133743 | 14018 | FE-490
SITE-03072 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2026-02-13 |  | 136 | Site Survey | Survey Complete | Breached | 50 | 116904 | 16229 | FE-353
SITE-03073 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-03 |  | 208 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 75433 | 14083 | FE-255
SITE-03074 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Branch | Sify Technologies | 2025-11-01 | 2025-11-12 | 11 | Go-Live | Live - Operational | Breached | 50 | 113893 | 10530 | FE-381
SITE-03075 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-11-26 |  | 215 | Site Survey | Survey Scheduled | Breached | 20 | 94411 | 6748 | FE-251
SITE-03076 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-13 | 2026-02-25 | 12 | Go-Live | Live - Operational | Breached | 6 | 82590 | 17133 | FE-353
SITE-03077 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Corporate Office | Excitel Enterprise | 2026-03-28 |  | 93 | Site Survey | Survey Complete | Breached | 34 | 59501 | 6027 | FE-115
SITE-03078 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Tata Communications | 2026-01-09 |  | 171 | Site Survey | Survey Complete | Breached | 20 | 59942 | 6106 | FE-495
SITE-03079 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Corporate Office | Sify Technologies | 2025-10-22 |  | 250 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 123525 | 10555 | FE-405
SITE-03080 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Corporate Office | Sify Technologies | 2025-09-03 |  | 299 | Site Survey | Survey Complete | Breached | 2 | 75340 | 15308 | FE-116
SITE-03081 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Data Center | Vodafone Idea Business | 2025-11-04 |  | 237 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 124051 | 16979 | FE-104
SITE-03082 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-11-07 | 2025-11-08 | 1 | Go-Live | Live - Operational | Met | 2 | 119349 | 11158 | FE-328
SITE-03083 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Corporate Office | Local ISP Partner | 2026-04-01 | 2026-04-11 | 10 | Go-Live | Live - Operational | Breached | 34 | 115419 | 13803 | FE-451
SITE-03084 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Branch | Vodafone Idea Business | 2025-09-04 |  | 298 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 71919 | 12660 | FE-279
SITE-03085 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Branch | Sify Technologies | 2026-02-17 | 2026-02-15 | -2 | Go-Live | Live - Operational | Met | 34 | 31035 | 14279 | FE-194
SITE-03086 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | ATM/Off-site | Tata Communications | 2025-10-20 | 2025-10-25 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 88816 | 13275 | FE-235
SITE-03087 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | Corporate Office | Airtel Business | 2026-02-02 |  | 147 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 132528 | 15321 | FE-471
SITE-03088 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-10-28 | 2025-11-09 | 12 | Go-Live | Live - Operational | Breached | 20 | 49871 | 10071 | FE-283
SITE-03089 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Data Center | Local ISP Partner | 2025-10-05 | 2025-10-30 | 25 | Go-Live | Live - Operational | Breached | 50 | 52009 | 16707 | FE-441
SITE-03090 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-10 |  |  | ROW / Permission | Cancelled | N/A | 10 | 97275 | 6652 | FE-383
SITE-03091 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Corporate Office | Local ISP Partner | 2025-11-23 | 2025-11-20 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 33371 | 16577 | FE-409
SITE-03092 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Branch | Vodafone Idea Business | 2025-11-18 | 2025-11-14 | -4 | Go-Live | Live - Operational | Met | 20 | 73091 | 17079 | FE-283
SITE-03093 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Branch | Vodafone Idea Business | 2025-12-22 |  |  | ROW / Permission | Cancelled | N/A | 6 | 90115 | 6555 | FE-378
SITE-03094 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-10-18 |  | 254 | Site Survey | Survey Scheduled | Breached | 20 | 78498 | 5064 | FE-171
SITE-03095 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Corporate Office | Vodafone Idea Business | 2026-03-28 | 2026-04-07 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 127752 | 10469 | FE-231
SITE-03096 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-09-04 |  | 298 | Site Survey | Survey Scheduled | Breached | 4 | 94999 | 16337 | FE-435
SITE-03097 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Excitel Enterprise | 2025-08-31 | 2025-08-24 | -7 | Go-Live | Live - Operational | Met | 10 | 38988 | 13387 | FE-320
SITE-03098 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Branch | Vodafone Idea Business | 2026-02-02 | 2026-02-13 | 11 | Go-Live | Live - Operational | Breached | 100 | 35774 | 8591 | FE-271
SITE-03099 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-28 | 2026-03-14 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 44389 | 14594 | FE-460
SITE-03100 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | ATM/Off-site | Airtel Business | 2026-02-17 | 2026-02-13 | -4 | Go-Live | Live - Operational | Met | 20 | 130451 | 7254 | FE-497
SITE-03101 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Corporate Office | Excitel Enterprise | 2025-09-06 |  | 296 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 39855 | 14273 | FE-249
SITE-03102 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Data Center | Sify Technologies | 2025-11-30 | 2025-12-05 | 5 | Go-Live | Live - Operational | Met | 34 | 34055 | 17574 | FE-447
SITE-03103 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | Branch | Airtel Business | 2025-10-27 |  | 245 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 45368 | 11223 | FE-285
SITE-03104 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-12-25 |  | 186 | Site Survey | Survey Complete | Breached | 4 | 42444 | 15269 | FE-269
SITE-03105 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Tata Communications | 2026-02-04 | 2026-02-07 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 112790 | 8401 | FE-227
SITE-03106 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Branch | Tata Communications | 2025-10-24 |  | 248 | Site Survey | Survey Complete | Breached | 6 | 115093 | 13088 | FE-347
SITE-03107 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Branch | Sify Technologies | 2026-02-08 |  | 141 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 81477 | 5909 | FE-449
SITE-03108 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-12-25 |  | 186 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 130532 | 9066 | FE-132
SITE-03109 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Data Center | Airtel Business | 2026-01-05 | 2026-01-02 | -3 | Go-Live | Live - Operational | Met | 4 | 125470 | 4377 | FE-474
SITE-03110 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | ATM/Off-site | Tata Communications | 2026-03-25 | 2026-03-24 | -1 | Go-Live | Live - Operational | Met | 10 | 80044 | 12793 | FE-138
SITE-03111 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Vodafone Idea Business | 2026-02-17 | 2026-03-08 | 19 | Go-Live | Live - Operational | Breached | 4 | 129302 | 3940 | FE-283
SITE-03112 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Data Center | Local ISP Partner | 2025-08-28 |  | 305 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 73384 | 17433 | FE-404
SITE-03113 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Branch | Sify Technologies | 2025-12-01 | 2025-12-03 | 2 | Go-Live | Live - Operational | Met | 20 | 69654 | 4337 | FE-105
SITE-03114 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2026-03-14 | 2026-03-28 | 14 | Go-Live | Live - Operational | Breached | 100 | 100738 | 13542 | FE-117
SITE-03115 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Branch | Airtel Business | 2025-11-24 |  | 217 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 93929 | 10049 | FE-331
SITE-03116 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Corporate Office | Tata Communications | 2026-02-10 | 2026-02-03 | -7 | Go-Live | Live - Operational | Met | 10 | 63801 | 10186 | FE-450
SITE-03117 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Branch | Excitel Enterprise | 2025-11-12 | 2025-11-27 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 59469 | 16423 | FE-317
SITE-03118 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-09-08 | 2025-09-02 | -6 | Go-Live | Live - Operational | Met | 6 | 86511 | 6326 | FE-136
SITE-03119 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-10-29 | 2025-11-03 | 5 | Go-Live | Live - Operational | Met | 2 | 41179 | 12437 | FE-258
SITE-03120 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-09-22 | 2025-09-27 | 5 | Go-Live | Live - Operational | Met | 6 | 75403 | 16543 | FE-220
SITE-03121 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | ATM/Off-site | Local ISP Partner | 2026-03-05 |  | 116 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 126600 | 14511 | FE-298
SITE-03122 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Data Center | Airtel Business | 2026-03-15 |  | 106 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 29184 | 7392 | FE-375
SITE-03123 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Branch | Local ISP Partner | 2026-02-18 |  | 131 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 60182 | 15595 | FE-294
SITE-03124 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2026-03-07 |  | 114 | Site Survey | Survey Scheduled | Breached | 20 | 112936 | 11464 | FE-319
SITE-03125 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Corporate Office | Airtel Business | 2025-09-07 | 2025-08-29 | -9 | Go-Live | Live - Operational | Met | 4 | 61682 | 14948 | FE-467
SITE-03126 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Branch | Vodafone Idea Business | 2026-04-18 |  | 72 | Site Survey | Survey Scheduled | Breached | 4 | 84846 | 7455 | FE-237
SITE-03127 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2026-03-19 | 2026-04-12 | 24 | Go-Live | Live - Operational | Breached | 4 | 51632 | 7050 | FE-334
SITE-03128 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Branch | Excitel Enterprise | 2025-09-17 |  | 285 | Site Survey | Survey Complete | Breached | 4 | 109555 | 7838 | FE-429
SITE-03129 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-29 | 2025-12-15 | 16 | Go-Live | Live - Operational | Breached | 6 | 108849 | 9978 | FE-276
SITE-03130 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Vodafone Idea Business | 2026-01-28 | 2026-01-29 | 1 | Go-Live | Live - Operational | Met | 100 | 38256 | 7371 | FE-324
SITE-03131 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Branch | Local ISP Partner | 2026-03-23 |  | 98 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 126314 | 5816 | FE-317
SITE-03132 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-09-24 |  | 278 | Site Survey | Survey Complete | Breached | 50 | 128258 | 17085 | FE-295
SITE-03133 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-03 | 2025-09-16 | 13 | Go-Live | Live - Operational | Breached | 10 | 88131 | 5112 | FE-200
SITE-03134 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Corporate Office | Tata Communications | 2026-03-07 |  | 114 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 123608 | 5790 | FE-211
SITE-03135 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Vodafone Idea Business | 2025-11-13 | 2025-11-22 | 9 | Go-Live | Live - Operational | Breached | 6 | 92780 | 10451 | FE-204
SITE-03136 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Branch | Vodafone Idea Business | 2026-02-18 | 2026-02-16 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 130122 | 5085 | FE-450
SITE-03137 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Branch | Sify Technologies | 2026-02-15 |  | 134 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 66734 | 11878 | FE-216
SITE-03138 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Data Center | Airtel Business | 2026-01-11 |  | 169 | Site Survey | Survey Complete | Breached | 50 | 62331 | 11351 | FE-113
SITE-03139 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-02 | 2025-12-14 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 30863 | 7046 | FE-293
SITE-03140 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Corporate Office | Excitel Enterprise | 2025-08-28 | 2025-08-19 | -9 | Go-Live | Live - Operational | Met | 10 | 91756 | 14688 | FE-408
SITE-03141 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Branch | Sify Technologies | 2025-10-25 |  | 247 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 125887 | 5875 | FE-499
SITE-03142 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2026-02-08 |  | 141 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 78240 | 8903 | FE-406
SITE-03143 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Branch | Vodafone Idea Business | 2025-09-08 | 2025-09-14 | 6 | Go-Live | Live - Operational | Breached | 6 | 103891 | 5043 | FE-141
SITE-03144 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | ATM/Off-site | Sify Technologies | 2025-09-29 | 2025-10-21 | 22 | Go-Live | Live - Operational | Breached | 100 | 44263 | 11996 | FE-198
SITE-03145 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Data Center | Local ISP Partner | 2025-09-26 |  | 276 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 113459 | 4375 | FE-345
SITE-03146 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2026-01-31 |  | 149 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 103569 | 11316 | FE-245
SITE-03147 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2026-02-03 |  | 146 | Site Survey | Survey Scheduled | Breached | 34 | 49132 | 17725 | FE-169
SITE-03148 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-09-25 | 2025-10-02 | 7 | Go-Live | Live - Operational | Breached | 34 | 82723 | 9331 | FE-364
SITE-03149 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Branch | Tata Communications | 2026-01-11 |  | 169 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 38088 | 11569 | FE-208
SITE-03150 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | ATM/Off-site | Tata Communications | 2025-09-21 | 2025-10-07 | 16 | Go-Live | Live - Operational | Breached | 6 | 106168 | 11052 | FE-287
SITE-03151 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Branch | Vodafone Idea Business | 2026-03-06 | 2026-03-22 | 16 | Go-Live | Live - Operational | Breached | 20 | 107796 | 10225 | FE-211
SITE-03152 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Branch | Excitel Enterprise | 2025-09-15 |  | 287 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 96885 | 17474 | FE-453
SITE-03153 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2026-04-12 |  | 78 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 97520 | 6231 | FE-457
SITE-03154 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Data Center | Tata Communications | 2026-02-08 | 2026-01-29 | -10 | Go-Live | Live - Operational | Met | 50 | 92717 | 9202 | FE-196
SITE-03155 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-10-23 |  | 249 | Site Survey | Survey Complete | Breached | 4 | 133163 | 17222 | FE-223
SITE-03156 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2026-04-05 |  | 85 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 103811 | 4100 | FE-486
SITE-03157 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2026-01-29 |  |  | Site Survey | Cancelled | N/A | 6 | 106823 | 9353 | FE-483
SITE-03158 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Corporate Office | Excitel Enterprise | 2026-03-14 |  | 107 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 72793 | 14884 | FE-315
SITE-03159 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-12-29 | 2026-01-05 | 7 | Go-Live | Live - Operational | Breached | 6 | 47070 | 8778 | FE-497
SITE-03160 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Corporate Office | Tata Communications | 2026-03-23 |  | 98 | Site Survey | Survey Scheduled | Breached | 6 | 70293 | 12636 | FE-134
SITE-03161 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | ATM/Off-site | Tata Communications | 2026-04-14 |  | 76 | Site Survey | Survey Scheduled | Breached | 6 | 120624 | 6578 | FE-307
SITE-03162 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | ATM/Off-site | Excitel Enterprise | 2026-01-13 |  |  | BOM Finalization | Cancelled | N/A | 20 | 74924 | 7730 | FE-150
SITE-03163 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-10-26 | 2025-10-24 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 129709 | 4363 | FE-408
SITE-03164 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Data Center | Excitel Enterprise | 2026-01-28 |  | 152 | Site Survey | Survey Scheduled | Breached | 34 | 129603 | 13686 | FE-123
SITE-03165 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Corporate Office | Excitel Enterprise | 2026-02-13 |  |  | BOM Finalization | Cancelled | N/A | 100 | 45774 | 13815 | FE-242
SITE-03166 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | ATM/Off-site | Local ISP Partner | 2026-01-29 |  | 151 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 88411 | 11420 | FE-425
SITE-03167 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Branch | Vodafone Idea Business | 2026-03-10 |  | 111 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 94613 | 4554 | FE-134
SITE-03168 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-12-26 |  | 185 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 31772 | 11335 | FE-454
SITE-03169 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | ATM/Off-site | Local ISP Partner | 2026-02-12 |  | 137 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 29468 | 15072 | FE-192
SITE-03170 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-10-10 |  | 262 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 40328 | 14777 | FE-415
SITE-03171 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Data Center | Local ISP Partner | 2026-03-23 | 2026-03-16 | -7 | Go-Live | Live - Operational | Met | 10 | 52225 | 15517 | FE-220
SITE-03172 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Branch | Excitel Enterprise | 2026-04-15 | 2026-04-10 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 113041 | 16458 | FE-258
SITE-03173 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Corporate Office | Airtel Business | 2025-11-11 | 2025-12-06 | 25 | Go-Live | Live - Operational | Breached | 2 | 48623 | 14856 | FE-243
SITE-03174 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Data Center | Vodafone Idea Business | 2026-02-22 | 2026-03-03 | 9 | Go-Live | Live - Operational | Breached | 34 | 119953 | 4988 | FE-160
SITE-03175 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-13 |  | 289 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 29057 | 13538 | FE-394
SITE-03176 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Excitel Enterprise | 2026-01-01 | 2026-01-07 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 53234 | 11158 | FE-119
SITE-03177 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Corporate Office | Sify Technologies | 2025-10-01 |  | 271 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 117702 | 13878 | FE-419
SITE-03178 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Branch | Tata Communications | 2025-12-04 | 2025-11-28 | -6 | Go-Live | Live - Operational | Met | 10 | 69721 | 9780 | FE-263
SITE-03179 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Branch | Local ISP Partner | 2026-03-07 | 2026-03-08 | 1 | Go-Live | Live - Operational | Met | 6 | 59701 | 11368 | FE-295
SITE-03180 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Excitel Enterprise | 2026-02-13 |  | 136 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 129628 | 6250 | FE-391
SITE-03181 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Branch | Excitel Enterprise | 2026-01-12 | 2026-01-26 | 14 | Go-Live | Live - Operational | Breached | 20 | 40172 | 17176 | FE-133
SITE-03182 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Branch | Excitel Enterprise | 2026-02-17 |  | 132 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 130687 | 16508 | FE-256
SITE-03183 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | ATM/Off-site | Sify Technologies | 2026-02-05 |  | 144 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 77616 | 10457 | FE-444
SITE-03184 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | ATM/Off-site | Sify Technologies | 2025-12-10 | 2025-12-12 | 2 | Go-Live | Live - Operational | Met | 10 | 59212 | 7716 | FE-206
SITE-03185 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Vodafone Idea Business | 2026-03-04 | 2026-03-27 | 23 | Go-Live | Live - Operational | Breached | 20 | 123899 | 4110 | FE-359
SITE-03186 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-10-11 | 2025-10-15 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 78294 | 13661 | FE-168
SITE-03187 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Corporate Office | Airtel Business | 2025-09-02 | 2025-09-11 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 30845 | 12963 | FE-277
SITE-03188 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Data Center | Local ISP Partner | 2025-11-05 |  | 236 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 60602 | 12827 | FE-318
SITE-03189 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Corporate Office | Excitel Enterprise | 2025-11-19 | 2025-11-20 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 89646 | 10133 | FE-268
SITE-03190 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-09-28 |  | 274 | Site Survey | Survey Scheduled | Breached | 10 | 28593 | 4116 | FE-490
SITE-03191 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-06 | 2025-11-05 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 100 | 55822 | 8001 | FE-245
SITE-03192 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Data Center | Excitel Enterprise | 2026-02-14 |  | 135 | Site Survey | Survey Complete | Breached | 50 | 84321 | 10872 | FE-401
SITE-03193 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Data Center | Tata Communications | 2025-11-02 |  | 239 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 119854 | 5244 | FE-334
SITE-03194 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Branch | Sify Technologies | 2025-09-10 |  | 292 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 38752 | 4823 | FE-113
SITE-03195 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Branch | Sify Technologies | 2025-12-20 |  | 191 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 90971 | 17086 | FE-283
SITE-03196 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Branch | Local ISP Partner | 2025-11-19 |  | 222 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 38036 | 12393 | FE-472
SITE-03197 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Data Center | Vodafone Idea Business | 2026-02-19 | 2026-02-15 | -4 | Go-Live | Live - Operational | Met | 20 | 62178 | 12723 | FE-470
SITE-03198 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | Corporate Office | Excitel Enterprise | 2026-02-21 | 2026-02-22 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 103429 | 11972 | FE-267
SITE-03199 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Corporate Office | Vodafone Idea Business | 2026-03-10 | 2026-03-05 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 120721 | 12947 | FE-217
SITE-03200 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Corporate Office | Airtel Business | 2025-09-08 | 2025-09-07 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 37450 | 11227 | FE-459
SITE-03201 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Data Center | Tata Communications | 2026-04-15 | 2026-04-26 | 11 | Go-Live | Live - Operational | Breached | 20 | 32363 | 17336 | FE-166
SITE-03202 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Excitel Enterprise | 2026-04-04 |  | 86 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 120500 | 11536 | FE-319
SITE-03203 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Branch | Local ISP Partner | 2026-01-06 | 2026-01-26 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 127692 | 15884 | FE-227
SITE-03204 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Data Center | Excitel Enterprise | 2026-01-21 | 2026-01-23 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 115972 | 9813 | FE-200
SITE-03205 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Branch | Tata Communications | 2025-09-01 | 2025-08-27 | -5 | Go-Live | Live - Operational | Met | 6 | 85576 | 12499 | FE-395
SITE-03206 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-09-18 | 2025-10-08 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 28201 | 15936 | FE-250
SITE-03207 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | Data Center | Sify Technologies | 2026-04-17 | 2026-05-08 | 21 | Go-Live | Live - Operational | Breached | 50 | 127481 | 11279 | FE-124
SITE-03208 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Branch | Airtel Business | 2025-12-12 | 2025-12-11 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 56263 | 7657 | FE-255
SITE-03209 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Corporate Office | Vodafone Idea Business | 2026-01-27 |  | 153 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 125938 | 15603 | FE-467
SITE-03210 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | ATM/Off-site | Airtel Business | 2026-01-12 | 2026-01-06 | -6 | Go-Live | Live - Operational | Met | 10 | 76599 | 10704 | FE-447
SITE-03211 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Branch | Vodafone Idea Business | 2026-02-26 |  | 123 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 44257 | 10815 | FE-254
SITE-03212 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Airtel Business | 2025-12-24 |  | 187 | Site Survey | Survey Scheduled | Breached | 50 | 45813 | 9859 | FE-225
SITE-03213 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Branch | Excitel Enterprise | 2025-11-16 |  | 225 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 134655 | 11624 | FE-235
SITE-03214 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Corporate Office | Local ISP Partner | 2025-11-05 |  | 236 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 65389 | 17251 | FE-357
SITE-03215 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-11-26 |  | 215 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 131181 | 7657 | FE-114
SITE-03216 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Data Center | Excitel Enterprise | 2025-12-25 |  | 186 | Site Survey | Survey Complete | Breached | 100 | 64882 | 3909 | FE-235
SITE-03217 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Data Center | Sify Technologies | 2025-12-13 |  | 198 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 68386 | 13277 | FE-327
SITE-03218 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-19 | 2025-09-16 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 113424 | 16229 | FE-206
SITE-03219 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Branch | Local ISP Partner | 2025-09-11 |  | 291 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 102838 | 17444 | FE-242
SITE-03220 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Corporate Office | Local ISP Partner | 2025-12-07 |  | 204 | Site Survey | Survey Complete | Breached | 6 | 59741 | 15703 | FE-248
SITE-03221 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Sify Technologies | 2026-01-09 | 2026-01-20 | 11 | Go-Live | Live - Operational | Breached | 10 | 72820 | 6453 | FE-202
SITE-03222 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Branch | Tata Communications | 2025-09-05 |  | 297 | Site Survey | Survey Scheduled | Breached | 20 | 89133 | 3973 | FE-392
SITE-03223 | PRJ-2024038 | CL008 | South | Karnataka | Bengaluru | SD-WAN | Corporate Office | Excitel Enterprise | 2026-03-04 | 2026-03-09 | 5 | Go-Live | Live - Operational | Met | 34 | 83235 | 4774 | FE-140
SITE-03224 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-03 |  | 177 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 69203 | 4816 | FE-144
SITE-03225 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Corporate Office | Excitel Enterprise | 2026-04-12 |  | 78 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 126156 | 10837 | FE-241
SITE-03226 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Vodafone Idea Business | 2025-11-15 | 2025-11-24 | 9 | Go-Live | Live - Operational | Breached | 50 | 40190 | 11867 | FE-429
SITE-03227 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Branch | Sify Technologies | 2026-02-15 |  | 134 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 124085 | 13060 | FE-310
SITE-03228 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Data Center | Excitel Enterprise | 2026-04-04 |  | 86 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 120821 | 13561 | FE-108
SITE-03229 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | Corporate Office | Excitel Enterprise | 2025-12-09 |  | 202 | Site Survey | Survey Complete | Breached | 34 | 30198 | 12130 | FE-428
SITE-03230 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | ATM/Off-site | Local ISP Partner | 2026-02-27 | 2026-02-27 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 28473 | 15460 | FE-192
SITE-03231 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Corporate Office | Tata Communications | 2026-01-02 | 2026-01-19 | 17 | Go-Live | Live - Operational | Breached | 34 | 64469 | 17232 | FE-346
SITE-03232 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Branch | Sify Technologies | 2026-04-19 | 2026-04-18 | -1 | Go-Live | Live - Operational | Met | 2 | 74472 | 4601 | FE-210
SITE-03233 | PRJ-2024038 | CL008 | South | Karnataka | Hubli | SD-WAN | Branch | Sify Technologies | 2025-12-02 |  | 209 | Site Survey | Survey Complete | Breached | 100 | 68308 | 10890 | FE-224
SITE-03234 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Corporate Office | Airtel Business | 2025-12-22 | 2026-01-13 | 22 | Go-Live | Live - Operational | Breached | 20 | 87664 | 8402 | FE-254
SITE-03235 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Corporate Office | Tata Communications | 2025-11-19 | 2025-11-25 | 6 | Go-Live | Live - Operational | Breached | 2 | 125819 | 17815 | FE-444
SITE-03236 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | ATM/Off-site | Sify Technologies | 2025-12-29 |  | 182 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 98421 | 15750 | FE-449
SITE-03237 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Data Center | Sify Technologies | 2026-04-06 | 2026-04-16 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 54710 | 4977 | FE-204
SITE-03238 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Tata Communications | 2026-02-16 |  | 133 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 74575 | 11923 | FE-291
SITE-03239 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Corporate Office | Excitel Enterprise | 2026-03-13 |  | 108 | Site Survey | Survey Scheduled | Breached | 4 | 73778 | 6941 | FE-418
SITE-03240 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | ATM/Off-site | Local ISP Partner | 2026-02-07 |  | 142 | Site Survey | Survey Complete | Breached | 4 | 92088 | 12517 | FE-408
SITE-03241 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2026-03-22 |  | 99 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 120521 | 14598 | FE-138
SITE-03242 | PRJ-2024038 | CL008 | South | Tamil Nadu | Trichy | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-11-28 | 2025-12-18 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 88386 | 9155 | FE-488
SITE-03243 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Branch | Excitel Enterprise | 2026-01-12 | 2026-01-15 | 3 | Go-Live | Live - Operational | Met | 10 | 68769 | 12224 | FE-490
SITE-03244 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Branch | Local ISP Partner | 2026-04-13 |  | 77 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 53700 | 12230 | FE-133
SITE-03245 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-11-02 | 2025-10-31 | -2 | Go-Live | Live - Operational | Met | 20 | 48576 | 5184 | FE-452
SITE-03246 | PRJ-2024038 | CL008 | South | Kerala | Thiruvananthapuram | SD-WAN | ATM/Off-site | Tata Communications | 2025-12-24 |  | 187 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 50726 | 4537 | FE-363
SITE-03247 | PRJ-2024038 | CL008 | South | Telangana | Hyderabad | SD-WAN | ATM/Off-site | Sify Technologies | 2026-04-16 |  | 74 | Site Survey | Survey Scheduled | Breached | 4 | 39423 | 8345 | FE-470
SITE-03248 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Vijayawada | SD-WAN | Corporate Office | Local ISP Partner | 2025-10-30 | 2025-10-25 | -5 | Go-Live | Live - Operational | Met | 34 | 75506 | 6707 | FE-127
SITE-03249 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Branch | Sify Technologies | 2025-09-06 | 2025-09-08 | 2 | Go-Live | Live - Operational | Met | 20 | 29345 | 10869 | FE-325
SITE-03250 | PRJ-2024038 | CL008 | South | Kerala | Kochi | SD-WAN | Branch | Tata Communications | 2026-02-26 |  | 123 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 75259 | 13558 | FE-381
SITE-03251 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Airtel Business | 2025-12-22 | 2025-12-30 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 70668 | 8473 | FE-161
SITE-03252 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2026-01-27 | 2026-01-23 | -4 | Go-Live | Live - Operational | Met | 20 | 72727 | 6001 | FE-128
SITE-03253 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Visakhapatnam | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-09-18 |  | 284 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 31002 | 10370 | FE-153
SITE-03254 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2026-02-20 |  | 129 | Site Survey | Survey Complete | Breached | 2 | 35716 | 15849 | FE-459
SITE-03255 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-10-07 | 2025-10-13 | 6 | Go-Live | Live - Operational | Breached | 4 | 81018 | 12274 | FE-172
SITE-03256 | PRJ-2024038 | CL008 | South | Andhra Pradesh | Guntur | SD-WAN | Data Center | Sify Technologies | 2025-10-05 | 2025-09-30 | -5 | Go-Live | Live - Operational | Met | 50 | 50347 | 14155 | FE-295
SITE-03257 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Branch | Excitel Enterprise | 2025-10-04 |  | 268 | Site Survey | Survey Complete | Breached | 10 | 110762 | 7939 | FE-354
SITE-03258 | PRJ-2024038 | CL008 | South | Kerala | Kozhikode | SD-WAN | Branch | Sify Technologies | 2026-03-06 | 2026-02-24 | -10 | Go-Live | Live - Operational | Met | 10 | 46238 | 14347 | FE-424
SITE-03259 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2026-03-10 | 2026-03-08 | -2 | Go-Live | Live - Operational | Met | 100 | 34443 | 15025 | FE-203
SITE-03260 | PRJ-2024038 | CL008 | South | Tamil Nadu | Coimbatore | SD-WAN | Corporate Office | Excitel Enterprise | 2025-09-08 | 2025-09-27 | 19 | Go-Live | Live - Operational | Breached | 34 | 108699 | 11582 | FE-476
SITE-03261 | PRJ-2024038 | CL008 | South | Tamil Nadu | Madurai | SD-WAN | Branch | Airtel Business | 2026-01-17 | 2026-02-05 | 19 | Go-Live | Live - Operational | Breached | 34 | 39583 | 8337 | FE-271
SITE-03262 | PRJ-2024038 | CL008 | South | Tamil Nadu | Chennai | SD-WAN | Branch | Local ISP Partner | 2026-02-17 | 2026-02-28 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 110805 | 11954 | FE-304
SITE-03263 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Branch | Airtel Business | 2025-11-09 | 2025-12-04 | 25 | Go-Live | Live - Operational | Breached | 6 | 62360 | 3709 | FE-314
SITE-03264 | PRJ-2024038 | CL008 | South | Telangana | Warangal | SD-WAN | Data Center | Vodafone Idea Business | 2025-11-03 |  | 238 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 33460 | 15263 | FE-396
SITE-03265 | PRJ-2024038 | CL008 | South | Karnataka | Mysuru | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-06 | 2026-02-28 | 22 | Go-Live | Live - Operational | Breached | 34 | 85101 | 9924 | FE-452
SITE-03266 | PRJ-2024039 | CL001 | West | Goa | Panaji | VSAT | Corporate Office | Local ISP Partner | 2025-08-21 | 2025-09-04 | 14 | Go-Live | Live - Operational | Breached | 34 | 84546 | 16693 | FE-168
SITE-03267 | PRJ-2024039 | CL001 | West | Gujarat | Rajkot | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-05 |  | 206 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 73559 | 10472 | FE-456
SITE-03268 | PRJ-2024039 | CL001 | West | Gujarat | Ahmedabad | VSAT | Data Center | Local ISP Partner | 2025-11-04 | 2025-10-28 | -7 | Go-Live | Live - Operational | Met | 6 | 46094 | 17317 | FE-402
SITE-03269 | PRJ-2024039 | CL001 | West | Maharashtra | Mumbai | VSAT | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-17 | 2026-02-19 | 2 | Go-Live | Live - Operational | Met | 2 | 64627 | 11396 | FE-401
SITE-03270 | PRJ-2024039 | CL001 | West | Goa | Margao | VSAT | ATM/Off-site | Excitel Enterprise | 2026-02-05 | 2026-01-26 | -10 | Go-Live | Live - Operational | Met | 2 | 55173 | 8894 | FE-162
SITE-03271 | PRJ-2024039 | CL001 | West | Goa | Margao | VSAT | Warehouse/Ops Hub | Airtel Business | 2025-09-28 |  | 274 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 68375 | 4702 | FE-401
SITE-03272 | PRJ-2024039 | CL001 | West | Maharashtra | Nagpur | VSAT | Warehouse/Ops Hub | Local ISP Partner | 2026-02-20 |  | 129 | Site Survey | Survey Scheduled | Breached | 2 | 75407 | 7323 | FE-257
SITE-03273 | PRJ-2024039 | CL001 | West | Madhya Pradesh | Indore | VSAT | Warehouse/Ops Hub | Sify Technologies | 2025-09-27 |  | 275 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 124392 | 10198 | FE-342
SITE-03274 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | ATM/Off-site | Airtel Business | 2025-08-30 | 2025-09-10 | 11 | Go-Live | Live - Operational | Breached | 50 | 92674 | 3628 | FE-384
SITE-03275 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Data Center | Sify Technologies | 2025-06-17 |  | 377 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 118278 | 14327 | FE-176
SITE-03276 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-08-19 |  | 314 | Site Survey | Survey Complete | Breached | 6 | 48820 | 12110 | FE-184
SITE-03277 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | ATM/Off-site | Airtel Business | 2025-06-16 | 2025-06-19 | 3 | Go-Live | Live - Operational | Met | 34 | 55481 | 4183 | FE-323
SITE-03278 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Local ISP Partner | 2025-06-19 |  | 375 | Site Survey | Survey Scheduled | Breached | 50 | 91564 | 10209 | FE-427
SITE-03279 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Sify Technologies | 2025-05-15 |  | 410 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 90866 | 7904 | FE-475
SITE-03280 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Corporate Office | Airtel Business | 2025-06-03 |  | 391 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 58284 | 9355 | FE-425
SITE-03281 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Corporate Office | Local ISP Partner | 2025-04-25 |  | 430 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 106603 | 13797 | FE-181
SITE-03282 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Data Center | Sify Technologies | 2025-06-19 | 2025-07-06 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 117893 | 4554 | FE-461
SITE-03283 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-09-17 |  | 285 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 70366 | 15961 | FE-161
SITE-03284 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Data Center | Sify Technologies | 2025-06-08 |  | 386 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 57362 | 7894 | FE-413
SITE-03285 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Local ISP Partner | 2025-02-20 | 2025-03-11 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 68721 | 5328 | FE-413
SITE-03286 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Airtel Business | 2025-07-05 |  | 359 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 134029 | 4316 | FE-389
SITE-03287 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | ATM/Off-site | Tata Communications | 2025-06-11 |  | 383 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 79904 | 16349 | FE-198
SITE-03288 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-26 |  | 429 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 50616 | 8100 | FE-174
SITE-03289 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | ATM/Off-site | Sify Technologies | 2025-08-15 | 2025-08-27 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 90861 | 9751 | FE-310
SITE-03290 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-07-12 |  | 352 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 113839 | 14873 | FE-125
SITE-03291 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Tata Communications | 2025-02-10 |  | 504 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 53760 | 8415 | FE-383
SITE-03292 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Data Center | Local ISP Partner | 2025-09-12 | 2025-09-14 | 2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 77116 | 16518 | FE-369
SITE-03293 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Sify Technologies | 2025-02-28 |  | 486 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 63725 | 10329 | FE-108
SITE-03294 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Data Center | Tata Communications | 2025-03-13 |  | 473 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 91511 | 17521 | FE-236
SITE-03295 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Branch | Local ISP Partner | 2025-03-08 |  | 478 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 126223 | 6878 | FE-302
SITE-03296 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-07-05 | 2025-07-04 | -1 | Go-Live | Live - Operational | Met | 50 | 86254 | 15605 | FE-420
SITE-03297 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Branch | Airtel Business | 2025-08-09 |  | 324 | Site Survey | Survey Complete | Breached | 4 | 74847 | 8758 | FE-469
SITE-03298 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Data Center | Vodafone Idea Business | 2025-09-10 | 2025-09-01 | -9 | Go-Live | Live - Operational | Met | 34 | 69946 | 12495 | FE-171
SITE-03299 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Data Center | Sify Technologies | 2025-03-20 |  | 466 | Site Survey | Survey Complete | Breached | 10 | 107605 | 9574 | FE-303
SITE-03300 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Vodafone Idea Business | 2025-08-12 | 2025-08-19 | 7 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 90979 | 17100 | FE-275
SITE-03301 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-07-30 |  | 334 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 87779 | 11417 | FE-291
SITE-03302 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Corporate Office | Tata Communications | 2025-06-28 | 2025-07-05 | 7 | Go-Live | Live - Operational | Breached | 20 | 107169 | 16291 | FE-184
SITE-03303 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Data Center | Sify Technologies | 2025-02-27 |  | 487 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 96159 | 15940 | FE-444
SITE-03304 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-29 |  | 426 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 85668 | 10789 | FE-322
SITE-03305 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Data Center | Tata Communications | 2025-07-01 | 2025-06-27 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 70748 | 8464 | FE-471
SITE-03306 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-08-24 |  | 309 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 57183 | 16047 | FE-321
SITE-03307 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Sify Technologies | 2025-06-08 |  | 386 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 132949 | 12735 | FE-189
SITE-03308 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-09-02 | 2025-09-09 | 7 | Go-Live | Live - Operational | Breached | 100 | 81073 | 14869 | FE-223
SITE-03309 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-03-27 | 2025-04-02 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 44382 | 4334 | FE-439
SITE-03310 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Data Center | Vodafone Idea Business | 2025-04-28 | 2025-05-04 | 6 | Go-Live | Live - Operational | Breached | 10 | 128466 | 8214 | FE-414
SITE-03311 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Corporate Office | Local ISP Partner | 2025-02-20 |  | 494 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 45497 | 6333 | FE-280
SITE-03312 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Data Center | Sify Technologies | 2025-04-29 |  | 426 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 57261 | 9113 | FE-238
SITE-03313 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Local ISP Partner | 2025-05-13 | 2025-06-06 | 24 | Go-Live | Live - Operational | Breached | 34 | 89288 | 7006 | FE-417
SITE-03314 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-09-10 | 2025-09-09 | -1 | Go-Live | Live - Operational | Met | 34 | 73812 | 12555 | FE-109
SITE-03315 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-08-12 |  | 321 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 75464 | 11717 | FE-150
SITE-03316 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Local ISP Partner | 2025-03-13 | 2025-04-05 | 23 | Go-Live | Live - Operational | Breached | 4 | 129802 | 6668 | FE-310
SITE-03317 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Tata Communications | 2025-08-10 | 2025-08-19 | 9 | Go-Live | Live - Operational | Breached | 20 | 30391 | 11118 | FE-152
SITE-03318 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Branch | Sify Technologies | 2025-05-26 |  | 399 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 115744 | 13164 | FE-350
SITE-03319 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Corporate Office | Excitel Enterprise | 2025-06-24 | 2025-07-06 | 12 | Go-Live | Live - Operational | Breached | 34 | 33470 | 11990 | FE-464
SITE-03320 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Data Center | Tata Communications | 2025-05-08 | 2025-05-25 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 88487 | 3916 | FE-197
SITE-03321 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Data Center | Sify Technologies | 2025-02-06 | 2025-01-31 | -6 | Go-Live | Live - Operational | Met | 2 | 114383 | 17367 | FE-120
SITE-03322 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-05-11 | 2025-05-30 | 19 | Go-Live | Live - Operational | Breached | 20 | 103317 | 4047 | FE-350
SITE-03323 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-07-04 |  |  | Site Survey | Cancelled | N/A | 34 | 117116 | 5103 | FE-303
SITE-03324 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-06-30 |  | 364 | Site Survey | Survey Complete | Breached | 50 | 86349 | 10083 | FE-446
SITE-03325 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Data Center | Airtel Business | 2025-08-23 | 2025-09-09 | 17 | Go-Live | Live - Operational | Breached | 34 | 116317 | 16534 | FE-282
SITE-03326 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Data Center | Airtel Business | 2025-06-07 | 2025-05-31 | -7 | Go-Live | Live - Operational | Met | 6 | 97989 | 12320 | FE-209
SITE-03327 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Branch | Airtel Business | 2025-04-02 | 2025-04-14 | 12 | Go-Live | Live - Operational | Breached | 2 | 37753 | 7958 | FE-197
SITE-03328 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Airtel Business | 2025-09-23 |  | 279 | Site Survey | Survey Scheduled | Breached | 100 | 111263 | 8575 | FE-414
SITE-03329 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | ATM/Off-site | Sify Technologies | 2025-09-07 |  | 295 | Site Survey | Survey Complete | Breached | 100 | 121358 | 16146 | FE-472
SITE-03330 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Local ISP Partner | 2025-08-17 |  | 316 | Site Survey | Survey Scheduled | Breached | 20 | 96178 | 3866 | FE-200
SITE-03331 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | ATM/Off-site | Sify Technologies | 2025-09-24 | 2025-10-13 | 19 | Go-Live | Live - Operational | Breached | 50 | 75809 | 12686 | FE-178
SITE-03332 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Airtel Business | 2025-03-18 |  | 468 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 59101 | 15451 | FE-341
SITE-03333 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Airtel Business | 2025-08-20 |  | 313 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 84251 | 13056 | FE-153
SITE-03334 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Airtel Business | 2025-03-06 |  | 480 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 62583 | 13766 | FE-436
SITE-03335 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Branch | Tata Communications | 2025-08-27 | 2025-09-10 | 14 | Go-Live | Live - Operational | Breached | 100 | 131509 | 14017 | FE-379
SITE-03336 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-08-28 | 2025-09-11 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 87179 | 7827 | FE-422
SITE-03337 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Airtel Business | 2025-07-31 |  | 333 | Site Survey | Survey Complete | Breached | 34 | 117973 | 16918 | FE-262
SITE-03338 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Branch | Local ISP Partner | 2025-03-02 | 2025-03-25 | 23 | Go-Live | Live - Operational | Breached | 34 | 39184 | 7003 | FE-295
SITE-03339 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Airtel Business | 2025-02-06 |  | 508 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 55010 | 12554 | FE-431
SITE-03340 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Data Center | Local ISP Partner | 2025-07-03 |  |  | Site Survey | Cancelled | N/A | 50 | 95238 | 8430 | FE-499
SITE-03341 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Branch | Sify Technologies | 2025-09-10 | 2025-09-20 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 115917 | 5704 | FE-184
SITE-03342 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Airtel Business | 2025-07-21 | 2025-08-13 | 23 | Go-Live | Live - Operational | Breached | 10 | 70420 | 7873 | FE-130
SITE-03343 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-05-26 | 2025-05-26 | 0 | Go-Live | Live - Operational | Met | 50 | 29496 | 6704 | FE-100
SITE-03344 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-25 |  | 277 | Site Survey | Survey Complete | Breached | 100 | 34056 | 15498 | FE-393
SITE-03345 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Data Center | Vodafone Idea Business | 2025-07-22 |  | 342 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 99232 | 7386 | FE-497
SITE-03346 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Vodafone Idea Business | 2025-08-10 | 2025-08-23 | 13 | Go-Live | Live - Operational | Breached | 50 | 113748 | 11409 | FE-452
SITE-03347 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Branch | Vodafone Idea Business | 2025-03-21 |  | 465 | Site Survey | Survey Scheduled | Breached | 6 | 33478 | 8119 | FE-379
SITE-03348 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Tata Communications | 2025-02-14 |  | 500 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 134682 | 12909 | FE-213
SITE-03349 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Data Center | Sify Technologies | 2025-03-15 |  | 471 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 132313 | 10063 | FE-231
SITE-03350 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Excitel Enterprise | 2025-04-19 |  | 436 | Site Survey | Survey Scheduled | Breached | 4 | 80596 | 4106 | FE-265
SITE-03351 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Data Center | Sify Technologies | 2025-02-07 |  | 507 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 101997 | 15285 | FE-463
SITE-03352 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Local ISP Partner | 2025-04-19 | 2025-04-17 | -2 | Go-Live | Live - Operational | Met | 4 | 120427 | 13267 | FE-330
SITE-03353 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Excitel Enterprise | 2025-02-19 |  | 495 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 52619 | 10006 | FE-378
SITE-03354 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Branch | Vodafone Idea Business | 2025-05-31 |  | 394 | Site Survey | Survey Complete | Breached | 20 | 50957 | 5431 | FE-270
SITE-03355 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Local ISP Partner | 2025-04-06 |  | 449 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 130361 | 17829 | FE-274
SITE-03356 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Branch | Vodafone Idea Business | 2025-03-09 | 2025-03-10 | 1 | Go-Live | Live - Operational | Met | 2 | 100142 | 15097 | FE-361
SITE-03357 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-06-13 | 2025-06-08 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 54081 | 16159 | FE-288
SITE-03358 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Corporate Office | Airtel Business | 2025-09-01 |  | 301 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 28558 | 10188 | FE-285
SITE-03359 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Sify Technologies | 2025-09-07 | 2025-09-04 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 61255 | 9683 | FE-393
SITE-03360 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Branch | Tata Communications | 2025-05-01 |  | 424 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 124259 | 4835 | FE-255
SITE-03361 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Airtel Business | 2025-09-23 | 2025-10-17 | 24 | Go-Live | Live - Operational | Breached | 4 | 102888 | 8913 | FE-288
SITE-03362 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Airtel Business | 2025-06-30 |  | 364 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 133909 | 15925 | FE-408
SITE-03363 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Branch | Vodafone Idea Business | 2025-06-08 |  | 386 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 53198 | 4035 | FE-276
SITE-03364 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Airtel Business | 2025-09-18 | 2025-09-27 | 9 | Go-Live | Live - Operational | Breached | 20 | 119573 | 9758 | FE-102
SITE-03365 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-04-07 |  | 448 | Site Survey | Survey Complete | Breached | 34 | 55372 | 7416 | FE-329
SITE-03366 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Vodafone Idea Business | 2025-08-14 | 2025-09-08 | 25 | Go-Live | Live - Operational | Breached | 100 | 88920 | 17683 | FE-441
SITE-03367 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | ATM/Off-site | Sify Technologies | 2025-05-12 | 2025-05-19 | 7 | Go-Live | Live - Operational | Breached | 34 | 113990 | 17308 | FE-465
SITE-03368 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Tata Communications | 2025-07-14 |  | 350 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 127654 | 7372 | FE-122
SITE-03369 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Sify Technologies | 2025-04-10 | 2025-04-26 | 16 | Go-Live | Live - Operational | Breached | 100 | 62606 | 17725 | FE-274
SITE-03370 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-06-20 | 2025-06-23 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 119869 | 17807 | FE-324
SITE-03371 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-02-25 |  | 489 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 72683 | 17346 | FE-248
SITE-03372 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-05-29 | 2025-06-11 | 13 | Go-Live | Live - Operational | Breached | 20 | 133217 | 11320 | FE-311
SITE-03373 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-15 | 2025-03-07 | 20 | Go-Live | Live - Operational | Breached | 50 | 68196 | 17936 | FE-330
SITE-03374 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-08-11 |  | 322 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 88468 | 5955 | FE-362
SITE-03375 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-03-16 | 2025-03-30 | 14 | Go-Live | Live - Operational | Breached | 20 | 94441 | 9035 | FE-237
SITE-03376 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-04 |  | 510 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 117821 | 9729 | FE-370
SITE-03377 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Data Center | Local ISP Partner | 2025-09-05 | 2025-09-22 | 17 | Go-Live | Live - Operational | Breached | 6 | 113190 | 15260 | FE-308
SITE-03378 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Data Center | Excitel Enterprise | 2025-03-07 |  | 479 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 32426 | 13736 | FE-492
SITE-03379 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-05-25 |  | 400 | Site Survey | Survey Scheduled | Breached | 100 | 33358 | 15900 | FE-434
SITE-03380 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Data Center | Airtel Business | 2025-09-18 |  | 284 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 57205 | 11642 | FE-339
SITE-03381 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Branch | Tata Communications | 2025-02-19 |  | 495 | Site Survey | Survey Scheduled | Breached | 100 | 127521 | 7405 | FE-283
SITE-03382 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Data Center | Airtel Business | 2025-07-04 |  | 360 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 114597 | 16492 | FE-116
SITE-03383 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | ATM/Off-site | Airtel Business | 2025-03-25 | 2025-03-25 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 34800 | 16407 | FE-173
SITE-03384 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Corporate Office | Sify Technologies | 2025-04-01 |  | 454 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 30956 | 16402 | FE-305
SITE-03385 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-04-09 |  | 446 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 80275 | 13526 | FE-276
SITE-03386 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Sify Technologies | 2025-05-25 | 2025-06-06 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 106484 | 8505 | FE-146
SITE-03387 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Branch | Tata Communications | 2025-04-05 | 2025-04-15 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 62721 | 7658 | FE-371
SITE-03388 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Airtel Business | 2025-06-18 | 2025-06-28 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 43263 | 12980 | FE-423
SITE-03389 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Corporate Office | Sify Technologies | 2025-03-16 | 2025-03-29 | 13 | Go-Live | Live - Operational | Breached | 6 | 97390 | 16642 | FE-103
SITE-03390 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Corporate Office | Airtel Business | 2025-05-18 |  | 407 | Site Survey | Survey Scheduled | Breached | 34 | 71649 | 16618 | FE-115
SITE-03391 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Excitel Enterprise | 2025-06-17 |  | 377 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 31593 | 14620 | FE-192
SITE-03392 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Airtel Business | 2025-07-03 |  | 361 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 60650 | 4731 | FE-346
SITE-03393 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Excitel Enterprise | 2025-08-04 |  | 329 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 82356 | 6921 | FE-403
SITE-03394 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Data Center | Excitel Enterprise | 2025-08-28 |  | 305 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 48903 | 12009 | FE-354
SITE-03395 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Corporate Office | Excitel Enterprise | 2025-04-07 | 2025-04-07 | 0 | Go-Live | Live - Operational | Met | 34 | 132491 | 10196 | FE-188
SITE-03396 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-09-24 |  | 278 | Site Survey | Survey Scheduled | Breached | 20 | 67376 | 5381 | FE-318
SITE-03397 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-15 | 2025-08-16 | 1 | Go-Live | Live - Operational | Met | 2 | 89735 | 3573 | FE-109
SITE-03398 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-12 |  |  | Site Survey | Cancelled | N/A | 20 | 72364 | 14719 | FE-140
SITE-03399 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Branch | Tata Communications | 2025-07-26 | 2025-07-26 | 0 | Go-Live | Live - Operational | Met | 100 | 75297 | 8375 | FE-287
SITE-03400 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-04-13 |  | 442 | Site Survey | Survey Complete | Breached | 6 | 114317 | 17670 | FE-456
SITE-03401 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-05-16 | 2025-06-01 | 16 | Go-Live | Live - Operational | Breached | 34 | 113227 | 15619 | FE-109
SITE-03402 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Sify Technologies | 2025-05-16 | 2025-06-03 | 18 | Go-Live | Live - Operational | Breached | 6 | 34658 | 7265 | FE-469
SITE-03403 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Corporate Office | Sify Technologies | 2025-06-18 |  | 376 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 54432 | 3719 | FE-393
SITE-03404 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-09-20 | 2025-09-25 | 5 | Go-Live | Live - Operational | Met | 50 | 98111 | 15087 | FE-429
SITE-03405 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Sify Technologies | 2025-08-24 | 2025-08-19 | -5 | Go-Live | Live - Operational | Met | 100 | 105911 | 6015 | FE-217
SITE-03406 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Corporate Office | Local ISP Partner | 2025-02-21 |  | 493 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 93557 | 15029 | FE-151
SITE-03407 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Local ISP Partner | 2025-02-26 | 2025-03-11 | 13 | Go-Live | Live - Operational | Breached | 4 | 102120 | 10582 | FE-354
SITE-03408 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Excitel Enterprise | 2025-03-07 |  | 479 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 73927 | 4706 | FE-392
SITE-03409 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-09-07 | 2025-10-02 | 25 | Go-Live | Live - Operational | Breached | 34 | 44558 | 7403 | FE-216
SITE-03410 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Branch | Sify Technologies | 2025-09-05 |  | 297 | Site Survey | Survey Scheduled | Breached | 10 | 126821 | 11308 | FE-399
SITE-03411 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Branch | Sify Technologies | 2025-09-22 |  | 280 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 70298 | 16780 | FE-163
SITE-03412 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Branch | Sify Technologies | 2025-08-26 | 2025-09-13 | 18 | Go-Live | Live - Operational | Breached | 6 | 30542 | 16403 | FE-338
SITE-03413 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Corporate Office | Airtel Business | 2025-07-30 | 2025-07-28 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 101569 | 16782 | FE-339
SITE-03414 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Data Center | Airtel Business | 2025-03-14 |  | 472 | Site Survey | Survey Complete | Breached | 34 | 106812 | 4806 | FE-364
SITE-03415 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Corporate Office | Local ISP Partner | 2025-02-19 |  |  | Site Survey | Cancelled | N/A | 100 | 123370 | 10865 | FE-220
SITE-03416 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Corporate Office | Sify Technologies | 2025-03-17 |  | 469 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 111277 | 8508 | FE-201
SITE-03417 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Data Center | Excitel Enterprise | 2025-09-19 |  | 283 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 49599 | 13389 | FE-292
SITE-03418 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Corporate Office | Airtel Business | 2025-04-29 | 2025-05-14 | 15 | Go-Live | Live - Operational | Breached | 2 | 48537 | 13549 | FE-392
SITE-03419 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Airtel Business | 2025-06-18 | 2025-06-09 | -9 | Go-Live | Live - Operational | Met | 20 | 89721 | 13022 | FE-314
SITE-03420 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-08-05 | 2025-07-29 | -7 | Go-Live | Live - Operational | Met | 2 | 106827 | 4578 | FE-314
SITE-03421 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Sify Technologies | 2025-06-04 | 2025-06-20 | 16 | Go-Live | Live - Operational | Breached | 6 | 81151 | 9757 | FE-455
SITE-03422 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-04-09 |  | 446 | Site Survey | Survey Complete | Breached | 2 | 56943 | 10259 | FE-406
SITE-03423 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Branch | Local ISP Partner | 2025-08-15 |  | 318 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 110513 | 4460 | FE-151
SITE-03424 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Branch | Local ISP Partner | 2025-04-04 |  | 451 | Site Survey | Survey Scheduled | Breached | 4 | 126584 | 11038 | FE-194
SITE-03425 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-23 | 2025-09-20 | -3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 34 | 83194 | 12864 | FE-106
SITE-03426 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-06-15 | 2025-06-22 | 7 | Go-Live | Live - Operational | Breached | 10 | 56498 | 8906 | FE-412
SITE-03427 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Airtel Business | 2025-08-26 |  | 307 | Site Survey | Survey Scheduled | Breached | 6 | 103393 | 12326 | FE-426
SITE-03428 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Data Center | Local ISP Partner | 2025-07-09 | 2025-07-17 | 8 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 131221 | 11309 | FE-142
SITE-03429 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | ATM/Off-site | Airtel Business | 2025-02-07 |  | 507 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 128813 | 6179 | FE-479
SITE-03430 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-08-20 |  | 313 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 29389 | 4199 | FE-468
SITE-03431 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Branch | Excitel Enterprise | 2025-06-26 |  | 368 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 120166 | 13922 | FE-128
SITE-03432 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Local ISP Partner | 2025-05-17 |  | 408 | Site Survey | Survey Scheduled | Breached | 20 | 67466 | 5886 | FE-331
SITE-03433 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Corporate Office | Sify Technologies | 2025-09-05 | 2025-09-15 | 10 | Go-Live | Live - Operational | Breached | 2 | 121637 | 8155 | FE-190
SITE-03434 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Excitel Enterprise | 2025-07-10 |  | 354 | Site Survey | Survey Complete | Breached | 6 | 122911 | 15056 | FE-483
SITE-03435 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Sify Technologies | 2025-05-26 |  | 399 | Site Survey | Survey Scheduled | Breached | 10 | 109523 | 6718 | FE-256
SITE-03436 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-05-15 |  | 410 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 69872 | 17486 | FE-208
SITE-03437 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-05-01 |  |  | Site Survey | Cancelled | N/A | 10 | 71827 | 10982 | FE-201
SITE-03438 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | ATM/Off-site | Tata Communications | 2025-09-18 | 2025-09-22 | 4 | Go-Live | Live - Operational | Met | 100 | 58466 | 8042 | FE-274
SITE-03439 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Branch | Airtel Business | 2025-03-27 |  | 459 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 83456 | 8582 | FE-151
SITE-03440 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Corporate Office | Tata Communications | 2025-08-15 | 2025-08-25 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 53018 | 15207 | FE-334
SITE-03441 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Branch | Sify Technologies | 2025-04-01 | 2025-04-13 | 12 | Go-Live | Live - Operational | Breached | 4 | 80397 | 4289 | FE-164
SITE-03442 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Local ISP Partner | 2025-02-26 | 2025-02-21 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 75924 | 9340 | FE-266
SITE-03443 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Sify Technologies | 2025-08-26 | 2025-09-02 | 7 | Go-Live | Live - Operational | Breached | 6 | 47963 | 14110 | FE-451
SITE-03444 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Branch | Tata Communications | 2025-04-21 |  | 434 | Site Survey | Survey Complete | Breached | 6 | 76671 | 16820 | FE-290
SITE-03445 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Branch | Vodafone Idea Business | 2025-04-02 | 2025-04-13 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 104858 | 4993 | FE-227
SITE-03446 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | ATM/Off-site | Local ISP Partner | 2025-08-04 | 2025-08-22 | 18 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 108116 | 7660 | FE-490
SITE-03447 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Data Center | Tata Communications | 2025-09-13 |  | 289 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 118702 | 11646 | FE-487
SITE-03448 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Data Center | Vodafone Idea Business | 2025-03-05 |  | 481 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 50764 | 11936 | FE-423
SITE-03449 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Branch | Vodafone Idea Business | 2025-04-05 |  | 450 | Site Survey | Survey Complete | Breached | 4 | 125646 | 10225 | FE-168
SITE-03450 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Warehouse/Ops Hub | Local ISP Partner | 2025-09-13 |  | 289 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 121863 | 10587 | FE-221
SITE-03451 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Data Center | Vodafone Idea Business | 2025-09-13 | 2025-09-03 | -10 | Go-Live | Live - Operational | Met | 4 | 68981 | 4180 | FE-248
SITE-03452 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Excitel Enterprise | 2025-07-07 | 2025-07-19 | 12 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 115509 | 14184 | FE-315
SITE-03453 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Sify Technologies | 2025-09-14 |  | 288 | Site Survey | Survey Scheduled | Breached | 10 | 117894 | 7035 | FE-454
SITE-03454 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-02-12 |  | 502 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 33784 | 4788 | FE-245
SITE-03455 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-08-08 | 2025-08-11 | 3 | Go-Live | Live - Operational | Met | 100 | 95298 | 12092 | FE-356
SITE-03456 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | ATM/Off-site | Tata Communications | 2025-07-04 |  | 360 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 132759 | 9901 | FE-436
SITE-03457 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Branch | Vodafone Idea Business | 2025-06-24 | 2025-07-17 | 23 | Go-Live | Live - Operational | Breached | 100 | 120762 | 12276 | FE-475
SITE-03458 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-08-30 |  | 303 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 73943 | 13784 | FE-118
SITE-03459 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-05-15 | 2025-06-03 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 6 | 77832 | 11341 | FE-190
SITE-03460 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Data Center | Airtel Business | 2025-06-04 | 2025-06-03 | -1 | Go-Live | Live - Operational | Met | 2 | 122896 | 13958 | FE-383
SITE-03461 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-11 |  | 291 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 110873 | 6664 | FE-334
SITE-03462 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Branch | Vodafone Idea Business | 2025-04-15 |  | 440 | Site Survey | Survey Scheduled | Breached | 10 | 123309 | 15369 | FE-464
SITE-03463 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Warehouse/Ops Hub | Vodafone Idea Business | 2025-02-14 | 2025-03-01 | 15 | Go-Live | Live - Operational | Breached | 34 | 41531 | 14011 | FE-230
SITE-03464 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-06-22 |  | 372 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 38411 | 7763 | FE-298
SITE-03465 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Vodafone Idea Business | 2025-02-11 |  | 503 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 86909 | 9604 | FE-135
SITE-03466 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Branch | Tata Communications | 2025-09-18 |  | 284 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 67888 | 9305 | FE-320
SITE-03467 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-07-07 |  | 357 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 67802 | 7578 | FE-484
SITE-03468 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-09-24 | 2025-10-12 | 18 | Go-Live | Live - Operational | Breached | 6 | 30130 | 15292 | FE-116
SITE-03469 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-09-03 |  | 299 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 127407 | 16459 | FE-209
SITE-03470 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Data Center | Airtel Business | 2025-06-04 |  | 390 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 116736 | 6777 | FE-150
SITE-03471 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Excitel Enterprise | 2025-06-24 |  |  | BOM Finalization | Cancelled | N/A | 6 | 82484 | 5265 | FE-290
SITE-03472 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Branch | Tata Communications | 2025-03-13 |  | 473 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 6 | 62422 | 14391 | FE-129
SITE-03473 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Branch | Local ISP Partner | 2025-04-29 | 2025-05-04 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 72839 | 8346 | FE-402
SITE-03474 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Warehouse/Ops Hub | Excitel Enterprise | 2025-02-11 |  | 503 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 102452 | 17371 | FE-353
SITE-03475 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Data Center | Airtel Business | 2025-06-15 | 2025-07-07 | 22 | Go-Live | Live - Operational | Breached | 20 | 77480 | 5095 | FE-300
SITE-03476 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | ATM/Off-site | Excitel Enterprise | 2025-08-25 | 2025-09-02 | 8 | Go-Live | Live - Operational | Breached | 10 | 129246 | 14497 | FE-130
SITE-03477 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Airtel Business | 2025-02-22 |  | 492 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 48629 | 13577 | FE-257
SITE-03478 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Branch | Vodafone Idea Business | 2025-06-07 | 2025-06-14 | 7 | Go-Live | Live - Operational | Breached | 50 | 69168 | 7947 | FE-311
SITE-03479 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Local ISP Partner | 2025-07-10 |  | 354 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 75084 | 5134 | FE-367
SITE-03480 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-03-11 | 2025-03-22 | 11 | Go-Live | Live - Operational | Breached | 34 | 110816 | 10122 | FE-128
SITE-03481 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | ATM/Off-site | Airtel Business | 2025-04-06 | 2025-03-29 | -8 | Go-Live | Live - Operational | Met | 20 | 33105 | 9599 | FE-295
SITE-03482 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Local ISP Partner | 2025-03-21 | 2025-04-03 | 13 | Go-Live | Live - Operational | Breached | 34 | 95981 | 12738 | FE-477
SITE-03483 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-06-14 | 2025-06-14 | 0 | Go-Live | Live - Operational | Met | 34 | 37102 | 10263 | FE-306
SITE-03484 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Branch | Airtel Business | 2025-06-20 |  | 374 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 103905 | 5582 | FE-349
SITE-03485 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-06-06 | 2025-06-21 | 15 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 132812 | 6673 | FE-313
SITE-03486 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-06-03 | 2025-06-18 | 15 | Go-Live | Live - Operational | Breached | 20 | 67681 | 8463 | FE-179
SITE-03487 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-08-25 | 2025-08-31 | 6 | Go-Live | Live - Operational | Breached | 20 | 98345 | 12416 | FE-301
SITE-03488 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | ATM/Off-site | Vodafone Idea Business | 2025-04-05 | 2025-04-24 | 19 | Go-Live | Live - Operational | Breached | 4 | 67348 | 9512 | FE-121
SITE-03489 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Branch | Local ISP Partner | 2025-09-23 | 2025-10-17 | 24 | Go-Live | Live - Operational | Breached | 6 | 77841 | 14625 | FE-294
SITE-03490 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Warehouse/Ops Hub | Airtel Business | 2025-08-22 | 2025-08-19 | -3 | Go-Live | Live - Operational | Met | 50 | 28839 | 9778 | FE-143
SITE-03491 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Branch | Excitel Enterprise | 2025-08-21 |  | 312 | Site Survey | Survey Scheduled | Breached | 4 | 41360 | 16846 | FE-397
SITE-03492 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Data Center | Local ISP Partner | 2025-04-23 |  | 432 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 67816 | 15399 | FE-348
SITE-03493 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | ATM/Off-site | Sify Technologies | 2025-02-18 | 2025-02-14 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 64818 | 5027 | FE-201
SITE-03494 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Branch | Sify Technologies | 2025-03-02 | 2025-03-27 | 25 | Go-Live | Live - Operational | Breached | 2 | 72801 | 4907 | FE-457
SITE-03495 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Excitel Enterprise | 2025-07-14 | 2025-07-12 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 2 | 68595 | 8608 | FE-330
SITE-03496 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Branch | Excitel Enterprise | 2025-05-19 |  | 406 | Site Survey | Survey Complete | Breached | 20 | 131859 | 4282 | FE-297
SITE-03497 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Excitel Enterprise | 2025-07-21 | 2025-08-01 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 37071 | 3856 | FE-201
SITE-03498 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Data Center | Sify Technologies | 2025-08-16 |  | 317 | Site Survey | Survey Complete | Breached | 34 | 90102 | 5550 | FE-491
SITE-03499 | PRJ-2024040 | CL006 | East | Odisha | Cuttack | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-07-21 | 2025-07-31 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 87636 | 15388 | FE-237
SITE-03500 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Sify Technologies | 2025-09-09 | 2025-09-27 | 18 | Go-Live | Live - Operational | Breached | 100 | 28486 | 13400 | FE-217
SITE-03501 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Data Center | Local ISP Partner | 2025-08-02 | 2025-08-06 | 4 | Go-Live | Live - Operational | Met | 20 | 39660 | 6544 | FE-422
SITE-03502 | PRJ-2024040 | CL006 | East | Jharkhand | Jamshedpur | SD-WAN | Branch | Airtel Business | 2025-02-03 | 2025-02-17 | 14 | Go-Live | Live - Operational | Breached | 6 | 83918 | 15936 | FE-330
SITE-03503 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Branch | Sify Technologies | 2025-07-31 | 2025-08-25 | 25 | Go-Live | Live - Operational | Breached | 100 | 79980 | 7455 | FE-144
SITE-03504 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Sify Technologies | 2025-06-18 | 2025-07-03 | 15 | Go-Live | Live - Operational | Breached | 50 | 131128 | 5050 | FE-184
SITE-03505 | PRJ-2024040 | CL006 | East | Bihar | Patna | SD-WAN | Data Center | Sify Technologies | 2025-02-11 |  | 503 | Site Survey | Survey Complete | Breached | 2 | 36052 | 8102 | FE-325
SITE-03506 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Corporate Office | Excitel Enterprise | 2025-07-05 |  | 359 | Site Survey | Survey Scheduled | Breached | 50 | 129567 | 13913 | FE-425
SITE-03507 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | Warehouse/Ops Hub | Tata Communications | 2025-04-07 |  | 448 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 29588 | 14143 | FE-226
SITE-03508 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Tata Communications | 2025-02-15 | 2025-03-06 | 19 | Go-Live | Live - Operational | Breached | 4 | 86263 | 11467 | FE-491
SITE-03509 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Warehouse/Ops Hub | Sify Technologies | 2025-04-23 |  | 432 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 134030 | 6809 | FE-118
SITE-03510 | PRJ-2024040 | CL006 | East | Jharkhand | Ranchi | SD-WAN | Data Center | Tata Communications | 2025-09-16 | 2025-09-10 | -6 | Go-Live | Live - Operational | Met | 50 | 34825 | 4098 | FE-242
SITE-03511 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Corporate Office | Sify Technologies | 2025-02-25 | 2025-03-04 | 7 | Go-Live | Live - Operational | Breached | 4 | 134188 | 9343 | FE-271
SITE-03512 | PRJ-2024040 | CL006 | East | Assam | Dibrugarh | SD-WAN | ATM/Off-site | Airtel Business | 2025-04-14 |  | 441 | Site Survey | Survey Scheduled | Breached | 10 | 115239 | 14345 | FE-365
SITE-03513 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | ATM/Off-site | Airtel Business | 2025-04-30 |  |  | BOM Finalization | Cancelled | N/A | 4 | 90920 | 16216 | FE-448
SITE-03514 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Corporate Office | Airtel Business | 2025-04-02 |  | 453 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 127238 | 4407 | FE-259
SITE-03515 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Data Center | Sify Technologies | 2025-07-12 |  | 352 | Site Survey | Survey Complete | Breached | 10 | 122285 | 9822 | FE-467
SITE-03516 | PRJ-2024040 | CL006 | East | West Bengal | Siliguri | SD-WAN | Data Center | Airtel Business | 2025-06-04 |  | 390 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 87563 | 7046 | FE-390
SITE-03517 | PRJ-2024040 | CL006 | East | Bihar | Gaya | SD-WAN | Corporate Office | Excitel Enterprise | 2025-09-23 |  |  | Site Survey | Cancelled | N/A | 100 | 122064 | 15341 | FE-177
SITE-03518 | PRJ-2024040 | CL006 | East | Odisha | Rourkela | SD-WAN | Corporate Office | Excitel Enterprise | 2025-08-31 |  | 302 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 71197 | 14333 | FE-224
SITE-03519 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Data Center | Excitel Enterprise | 2025-07-20 |  | 344 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 115003 | 5015 | FE-233
SITE-03520 | PRJ-2024040 | CL006 | East | West Bengal | Kolkata | SD-WAN | Branch | Vodafone Idea Business | 2025-06-29 | 2025-06-30 | 1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 85713 | 4046 | FE-320
SITE-03521 | PRJ-2024040 | CL006 | East | West Bengal | Howrah | SD-WAN | Branch | Vodafone Idea Business | 2025-06-25 |  | 369 | Site Survey | Survey Complete | Breached | 10 | 69868 | 11077 | FE-411
SITE-03522 | PRJ-2024040 | CL006 | East | Odisha | Bhubaneswar | SD-WAN | Data Center | Airtel Business | 2025-03-05 |  | 481 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 31210 | 9942 | FE-457
SITE-03523 | PRJ-2024040 | CL006 | East | Assam | Guwahati | SD-WAN | Corporate Office | Vodafone Idea Business | 2025-08-13 |  | 320 | Site Survey | Survey Complete | Breached | 20 | 80513 | 6918 | FE-403
SITE-03524 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-11-02 | 2025-11-12 | 10 | Go-Live | Live - Operational | Breached | 2 | 58248 | 13318 | FE-467
SITE-03525 | PRJ-2024041 | CL005 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-09-21 |  | 281 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 122935 | 12363 | FE-302
SITE-03526 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-11-09 |  | 232 | Site Survey | Survey Complete | Breached | 2 | 71157 | 3890 | FE-418
SITE-03527 | PRJ-2024041 | CL005 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-08-20 | 2025-08-13 | -7 | Go-Live | Live - Operational | Met | 2 | 38900 | 16901 | FE-267
SITE-03528 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-09-06 |  | 296 | Site Survey | Survey Scheduled | Breached | 10 | 101642 | 7725 | FE-229
SITE-03529 | PRJ-2024041 | CL005 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2026-03-25 | 2026-03-29 | 4 | Go-Live | Live - Operational | Met | 6 | 113871 | 16013 | FE-198
SITE-03530 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2026-01-25 |  | 155 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 90661 | 5594 | FE-200
SITE-03531 | PRJ-2024041 | CL005 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-10-25 | 2025-10-31 | 6 | Go-Live | Live - Operational | Breached | 100 | 116639 | 11138 | FE-421
SITE-03532 | PRJ-2024041 | CL005 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-11-08 |  | 233 | Site Survey | Survey Complete | Breached | 6 | 44573 | 4676 | FE-495
SITE-03533 | PRJ-2024041 | CL005 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-12-02 | 2025-12-05 | 3 | Go-Live | Live - Operational | Met | 50 | 65673 | 5491 | FE-346
SITE-03534 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-01-27 |  | 153 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 6 | 52849 | 10274 | FE-234
SITE-03535 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-10-19 |  | 253 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 69532 | 13751 | FE-412
SITE-03536 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-12-08 |  | 203 | Site Survey | Survey Scheduled | Breached | 10 | 47312 | 7191 | FE-395
SITE-03537 | PRJ-2024041 | CL005 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-10-16 |  | 256 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 131336 | 12243 | FE-176
SITE-03538 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-10-02 | 2025-10-16 | 14 | Go-Live | Live - Operational | Breached | 100 | 104437 | 7760 | FE-409
SITE-03539 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-07 | 2025-11-08 | 1 | Go-Live | Live - Operational | Met | 20 | 61834 | 8436 | FE-450
SITE-03540 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-12-06 |  | 205 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 43223 | 4718 | FE-258
SITE-03541 | PRJ-2024041 | CL005 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-12-06 | 2025-12-12 | 6 | Go-Live | Live - Operational | Breached | 2 | 70005 | 12706 | FE-355
SITE-03542 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-11-08 | 2025-11-25 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 129046 | 13990 | FE-298
SITE-03543 | PRJ-2024041 | CL005 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-12-19 |  | 192 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 74704 | 12955 | FE-150
SITE-03544 | PRJ-2024041 | CL005 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2026-02-21 |  | 128 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 89336 | 6257 | FE-159
SITE-03545 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-11-28 |  | 213 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 56359 | 5888 | FE-197
SITE-03546 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2026-01-03 | 2025-12-24 | -10 | Go-Live | Live - Operational | Met | 34 | 73180 | 14278 | FE-417
SITE-03547 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2026-02-19 | 2026-03-10 | 19 | Go-Live | Live - Operational | Breached | 34 | 92076 | 17470 | FE-396
SITE-03548 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2026-01-10 | 2026-01-09 | -1 | Go-Live | Live - Operational | Met | 100 | 63315 | 14676 | FE-143
SITE-03549 | PRJ-2024041 | CL005 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2026-02-07 |  | 142 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 29553 | 7078 | FE-463
SITE-03550 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-11-27 |  | 214 | Site Survey | Survey Complete | Breached | 4 | 41554 | 6126 | FE-286
SITE-03551 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-10-11 | 2025-10-02 | -9 | Go-Live | Live - Operational | Met | 2 | 75381 | 10019 | FE-227
SITE-03552 | PRJ-2024041 | CL005 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-09-25 |  |  | ROW / Permission | Cancelled | N/A | 20 | 111557 | 12652 | FE-171
SITE-03553 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2026-03-11 | 2026-03-08 | -3 | Go-Live | Live - Operational | Met | 10 | 38908 | 6314 | FE-425
SITE-03554 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-12-06 |  | 205 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 47575 | 6512 | FE-101
SITE-03555 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-09-04 | 2025-09-22 | 18 | Go-Live | Live - Operational | Breached | 20 | 46052 | 12425 | FE-340
SITE-03556 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2026-02-09 |  | 140 | Site Survey | Survey Scheduled | Breached | 50 | 127881 | 6929 | FE-422
SITE-03557 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-09-28 | 2025-10-08 | 10 | Go-Live | Live - Operational | Breached | 4 | 117709 | 15122 | FE-109
SITE-03558 | PRJ-2024041 | CL005 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-08-27 | 2025-09-18 | 22 | Go-Live | Live - Operational | Breached | 20 | 118260 | 12310 | FE-493
SITE-03559 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-12-06 | 2025-12-07 | 1 | Go-Live | Live - Operational | Met | 2 | 29686 | 6937 | FE-314
SITE-03560 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-09-21 | 2025-09-26 | 5 | Go-Live | Live - Operational | Met | 6 | 125756 | 14218 | FE-370
SITE-03561 | PRJ-2024041 | CL005 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2026-04-07 |  | 83 | BOM Finalization | Delayed - Vendor Issue | Breached | 20 | 117496 | 5832 | FE-427
SITE-03562 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-11-11 |  | 230 | Site Survey | Survey Scheduled | Breached | 4 | 84982 | 16075 | FE-393
SITE-03563 | PRJ-2024041 | CL005 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-09-16 |  | 286 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 50 | 56981 | 5531 | FE-316
SITE-03564 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-12-17 |  | 194 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 55045 | 17559 | FE-100
SITE-03565 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2026-04-08 | 2026-04-11 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 41053 | 10641 | FE-300
SITE-03566 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-08-26 | 2025-09-19 | 24 | Go-Live | Live - Operational | Breached | 34 | 100393 | 3950 | FE-151
SITE-03567 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-12-01 |  | 210 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 118871 | 6284 | FE-364
SITE-03568 | PRJ-2024041 | CL005 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-11-02 | 2025-10-29 | -4 | Go-Live | Live - Operational | Met | 2 | 69661 | 16904 | FE-109
SITE-03569 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2026-02-22 | 2026-02-24 | 2 | Go-Live | Live - Operational | Met | 6 | 120844 | 8929 | FE-290
SITE-03570 | PRJ-2024041 | CL005 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-09-29 |  |  | Site Survey | Cancelled | N/A | 34 | 93957 | 17220 | FE-380
SITE-03571 | PRJ-2024041 | CL005 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-12-10 |  | 201 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 63522 | 15626 | FE-129
SITE-03572 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-10-02 |  | 270 | Site Survey | Survey Complete | Breached | 10 | 106094 | 9465 | FE-123
SITE-03573 | PRJ-2024041 | CL005 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2026-04-10 | 2026-04-21 | 11 | Go-Live | Live - Operational | Breached | 34 | 94393 | 14736 | FE-322
SITE-03574 | PRJ-2024041 | CL005 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2026-02-15 |  | 134 | Site Survey | Survey Scheduled | Breached | 6 | 80673 | 4161 | FE-213
SITE-03575 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2026-01-02 | 2026-01-15 | 13 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 61387 | 9377 | FE-373
SITE-03576 | PRJ-2024041 | CL005 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-09-18 |  | 284 | Site Survey | Survey Scheduled | Breached | 4 | 132762 | 17418 | FE-258
SITE-03577 | PRJ-2024041 | CL005 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2026-04-04 |  | 86 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 118719 | 16085 | FE-251
SITE-03578 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-10 | 2025-11-22 | 12 | Go-Live | Live - Operational | Breached | 100 | 70097 | 10789 | FE-353
SITE-03579 | PRJ-2024041 | CL005 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-10-06 |  | 266 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 30401 | 15110 | FE-256
SITE-03580 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-09-24 |  | 278 | Site Survey | Survey Complete | Breached | 34 | 128539 | 17721 | FE-449
SITE-03581 | PRJ-2024041 | CL005 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-19 |  | 314 | Site Survey | Survey Complete | Breached | 34 | 97547 | 12846 | FE-337
SITE-03582 | PRJ-2024041 | CL005 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-02-03 | 2026-02-03 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 54400 | 9708 | FE-463
SITE-03583 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2026-04-10 | 2026-05-02 | 22 | Go-Live | Live - Operational | Breached | 100 | 84704 | 14653 | FE-483
SITE-03584 | PRJ-2024041 | CL005 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-26 |  | 185 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 10 | 28921 | 14753 | FE-353
SITE-03585 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2026-02-24 | 2026-02-21 | -3 | Go-Live | Live - Operational | Met | 100 | 103669 | 17981 | FE-404
SITE-03586 | PRJ-2024041 | CL005 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2026-01-28 | 2026-02-08 | 11 | Go-Live | Live - Operational | Breached | 10 | 55688 | 12033 | FE-446
SITE-03587 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-12-28 | 2026-01-10 | 13 | Go-Live | Live - Operational | Breached | 50 | 95178 | 14181 | FE-153
SITE-03588 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-12-16 |  | 195 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 34704 | 15161 | FE-391
SITE-03589 | PRJ-2024041 | CL005 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-10-18 |  | 254 | Site Survey | Survey Scheduled | Breached | 20 | 108671 | 13041 | FE-413
SITE-03590 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-12-15 | 2025-12-31 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 20 | 42459 | 17426 | FE-122
SITE-03591 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2026-04-07 |  | 83 | Installation & Commissioning | Civil Work In Progress | Breached | 50 | 45752 | 9817 | FE-427
SITE-03592 | PRJ-2024041 | CL005 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-10-17 |  | 255 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 102454 | 5287 | FE-452
SITE-03593 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-10-24 |  | 248 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 108114 | 11949 | FE-268
SITE-03594 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-02-15 |  | 134 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 34 | 94359 | 17509 | FE-260
SITE-03595 | PRJ-2024041 | CL005 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-12-24 |  | 187 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 77599 | 11314 | FE-369
SITE-03596 | PRJ-2024041 | CL005 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2026-02-08 | 2026-02-04 | -4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 35443 | 10755 | FE-433
SITE-03597 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-11-26 |  | 215 | Site Survey | Survey Scheduled | Breached | 10 | 69458 | 14273 | FE-113
SITE-03598 | PRJ-2024041 | CL005 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2026-01-02 |  | 178 | Equipment Dispatch | Equipment Dispatched | Breached | 6 | 47478 | 6625 | FE-201
SITE-03599 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-08-05 | 2025-08-07 | 2 | Go-Live | Live - Operational | Met | 34 | 45025 | 12582 | FE-270
SITE-03600 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-28 | 2025-06-26 | -2 | Go-Live | Live - Operational | Met | 10 | 48790 | 11013 | FE-221
SITE-03601 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-08-17 | 2025-09-04 | 18 | Go-Live | Live - Operational | Breached | 2 | 52690 | 5788 | FE-165
SITE-03602 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-10-08 |  | 264 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 131836 | 13533 | FE-268
SITE-03603 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-12-04 | 2025-12-16 | 12 | Go-Live | Live - Operational | Breached | 34 | 119076 | 10897 | FE-121
SITE-03604 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-09-19 | 2025-09-16 | -3 | Go-Live | Live - Operational | Met | 4 | 53501 | 10350 | FE-258
SITE-03605 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-15 |  | 318 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 128397 | 6123 | FE-155
SITE-03606 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-13 |  | 351 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 82850 | 8823 | FE-115
SITE-03607 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-01-23 | 2026-01-22 | -1 | Go-Live | Live - Operational | Met | 10 | 114011 | 15134 | FE-423
SITE-03608 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-08-20 |  | 313 | Site Survey | Survey Complete | Breached | 34 | 60549 | 14496 | FE-102
SITE-03609 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-08-27 |  | 306 | Site Survey | Survey Complete | Breached | 34 | 34691 | 5565 | FE-308
SITE-03610 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-06-07 |  | 387 | Site Survey | Survey Scheduled | Breached | 100 | 128684 | 12329 | FE-410
SITE-03611 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-11-18 | 2025-11-16 | -2 | Go-Live | Live - Operational | Met | 10 | 103570 | 15348 | FE-407
SITE-03612 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2026-01-02 |  | 178 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 96098 | 6415 | FE-455
SITE-03613 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-09-10 |  | 292 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 52083 | 14733 | FE-194
SITE-03614 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-09-27 |  | 275 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 80482 | 5206 | FE-334
SITE-03615 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2026-01-26 |  | 154 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 72664 | 14611 | FE-155
SITE-03616 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-07-29 | 2025-08-01 | 3 | Go-Live | Live - Operational | Met | 2 | 87912 | 10650 | FE-406
SITE-03617 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-09-11 | 2025-09-12 | 1 | Go-Live | Live - Operational | Met | 10 | 117897 | 7393 | FE-486
SITE-03618 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-11-05 |  | 236 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 130655 | 14129 | FE-412
SITE-03619 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-01-09 | 2026-01-20 | 11 | Go-Live | Live - Operational | Breached | 100 | 39146 | 6115 | FE-188
SITE-03620 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-01-21 | 2026-02-15 | 25 | Go-Live | Live - Operational | Breached | 10 | 113507 | 11090 | FE-327
SITE-03621 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-12-22 |  | 189 | Site Survey | Survey Scheduled | Breached | 20 | 109322 | 12669 | FE-265
SITE-03622 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2026-01-20 | 2026-02-14 | 25 | Go-Live | Live - Operational | Breached | 50 | 53364 | 5969 | FE-181
SITE-03623 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-09-21 | 2025-10-16 | 25 | Go-Live | Live - Operational | Breached | 20 | 82520 | 15029 | FE-314
SITE-03624 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-12-12 | 2025-12-19 | 7 | Go-Live | Live - Operational | Breached | 2 | 102431 | 10331 | FE-454
SITE-03625 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-09-26 | 2025-09-25 | -1 | Go-Live | Live - Operational | Met | 6 | 75420 | 11053 | FE-211
SITE-03626 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-08-09 |  |  | BOM Finalization | Cancelled | N/A | 20 | 29847 | 10733 | FE-101
SITE-03627 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-10-06 | 2025-10-15 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 39326 | 5831 | FE-414
SITE-03628 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-08-23 |  | 310 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 132276 | 13309 | FE-169
SITE-03629 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-12-07 |  | 204 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 61706 | 5458 | FE-324
SITE-03630 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-07-26 | 2025-08-05 | 10 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 32361 | 8983 | FE-298
SITE-03631 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-25 | 2025-07-10 | 15 | Go-Live | Live - Operational | Breached | 100 | 103658 | 17231 | FE-288
SITE-03632 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-11-02 |  | 239 | Site Survey | Survey Scheduled | Breached | 4 | 50832 | 15967 | FE-490
SITE-03633 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-11-28 |  | 213 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 116113 | 14734 | FE-238
SITE-03634 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-06-27 | 2025-06-22 | -5 | Go-Live | Live - Operational | Met | 20 | 100897 | 3823 | FE-367
SITE-03635 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-07-06 |  |  | BOM Finalization | Cancelled | N/A | 50 | 91687 | 17790 | FE-152
SITE-03636 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-10-06 | 2025-10-25 | 19 | Go-Live | Live - Operational | Breached | 2 | 89773 | 17049 | FE-246
SITE-03637 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-02 | 2025-08-19 | 17 | Go-Live | Live - Operational | Breached | 34 | 123945 | 10752 | FE-405
SITE-03638 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-07-14 |  |  | ROW / Permission | Cancelled | N/A | 4 | 115777 | 4379 | FE-267
SITE-03639 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2026-01-04 | 2025-12-25 | -10 | Go-Live | Live - Operational | Met | 100 | 34684 | 16856 | FE-154
SITE-03640 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-12-08 | 2025-12-09 | 1 | Go-Live | Live - Operational | Met | 2 | 47476 | 9201 | FE-440
SITE-03641 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-11-28 | 2025-12-02 | 4 | Go-Live | Live - Operational | Met | 2 | 38735 | 3695 | FE-445
SITE-03642 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-23 |  | 157 | Site Survey | Survey Complete | Breached | 100 | 63262 | 14123 | FE-335
SITE-03643 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-09-22 |  | 280 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 126063 | 8566 | FE-230
SITE-03644 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-09-12 | 2025-09-18 | 6 | Go-Live | Live - Operational | Breached | 20 | 38928 | 10126 | FE-245
SITE-03645 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-07-30 |  | 334 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 131985 | 16392 | FE-448
SITE-03646 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-08-06 | 2025-08-25 | 19 | Go-Live | Live - Operational | Breached | 100 | 131470 | 10442 | FE-484
SITE-03647 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-10-20 |  | 252 | Site Survey | Survey Complete | Breached | 50 | 128548 | 3578 | FE-371
SITE-03648 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-12-19 |  | 192 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 106474 | 14269 | FE-123
SITE-03649 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-12-08 |  | 203 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 4 | 64049 | 7970 | FE-401
SITE-03650 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-07-30 | 2025-08-10 | 11 | Go-Live | Live - Operational | Breached | 6 | 65125 | 15533 | FE-123
SITE-03651 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-08-12 | 2025-08-23 | 11 | Go-Live | Live - Operational | Breached | 50 | 55407 | 6492 | FE-232
SITE-03652 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-07-13 | 2025-07-22 | 9 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 43277 | 4983 | FE-454
SITE-03653 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-12-27 |  | 184 | Site Survey | Survey Complete | Breached | 20 | 81786 | 14598 | FE-317
SITE-03654 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-06-25 | 2025-06-30 | 5 | Go-Live | Live - Operational | Met | 50 | 43438 | 11693 | FE-440
SITE-03655 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-09-30 |  | 272 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 118856 | 17449 | FE-372
SITE-03656 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-07-13 | 2025-07-29 | 16 | Go-Live | Live - Operational | Breached | 34 | 108766 | 11615 | FE-439
SITE-03657 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2026-01-09 | 2026-01-14 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 103293 | 11971 | FE-347
SITE-03658 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-06-22 | 2025-06-30 | 8 | Go-Live | Live - Operational | Breached | 20 | 107803 | 15441 | FE-376
SITE-03659 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-09-12 | 2025-09-07 | -5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 87725 | 5198 | FE-346
SITE-03660 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-06-26 | 2025-07-02 | 6 | Go-Live | Live - Operational | Breached | 100 | 52007 | 11676 | FE-272
SITE-03661 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-12-27 | 2025-12-26 | -1 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 86459 | 17660 | FE-319
SITE-03662 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-08-29 |  | 304 | Site Survey | Survey Scheduled | Breached | 34 | 95203 | 7726 | FE-331
SITE-03663 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-08-16 | 2025-08-06 | -10 | Go-Live | Live - Operational | Met | 6 | 122639 | 13023 | FE-454
SITE-03664 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-11-29 | 2025-12-10 | 11 | Go-Live | Live - Operational | Breached | 6 | 119144 | 10933 | FE-270
SITE-03665 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-08-09 | 2025-08-23 | 14 | Go-Live | Live - Operational | Breached | 2 | 42533 | 6009 | FE-242
SITE-03666 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-11-07 |  | 234 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 81362 | 5446 | FE-135
SITE-03667 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-12-28 |  | 183 | Installation & Commissioning | Civil Work In Progress | Breached | 6 | 119911 | 7432 | FE-131
SITE-03668 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-09-21 |  | 281 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 95955 | 3995 | FE-261
SITE-03669 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-06-14 |  | 380 | Site Survey | Survey Complete | Breached | 6 | 86918 | 13914 | FE-253
SITE-03670 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-07-30 | 2025-08-17 | 18 | Go-Live | Live - Operational | Breached | 100 | 36835 | 12296 | FE-311
SITE-03671 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-09-30 | 2025-10-06 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 132831 | 16713 | FE-153
SITE-03672 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-10-23 | 2025-10-13 | -10 | Go-Live | Live - Operational | Met | 6 | 101085 | 11499 | FE-376
SITE-03673 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-06-25 |  | 369 | Site Survey | Survey Scheduled | Breached | 20 | 73444 | 13700 | FE-361
SITE-03674 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-08-04 |  | 329 | Site Survey | Survey Complete | Breached | 34 | 120884 | 17154 | FE-251
SITE-03675 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-07-18 | 2025-08-12 | 25 | Go-Live | Live - Operational | Breached | 34 | 46285 | 4745 | FE-187
SITE-03676 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-06-16 |  | 378 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 79132 | 13155 | FE-465
SITE-03677 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-12 |  | 260 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 86852 | 17974 | FE-118
SITE-03678 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-08-07 | 2025-08-02 | -5 | Go-Live | Live - Operational | Met | 6 | 134757 | 13607 | FE-376
SITE-03679 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-12-16 |  | 195 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 30198 | 6907 | FE-321
SITE-03680 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-08 | 2025-07-28 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 100 | 99452 | 9876 | FE-169
SITE-03681 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-10-04 | 2025-10-03 | -1 | Go-Live | Live - Operational | Met | 50 | 31808 | 15335 | FE-224
SITE-03682 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2026-01-25 |  | 155 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 63210 | 10670 | FE-140
SITE-03683 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-11-23 | 2025-12-17 | 24 | Go-Live | Live - Operational | Breached | 20 | 111588 | 13875 | FE-277
SITE-03684 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-09-01 | 2025-09-18 | 17 | Go-Live | Live - Operational | Breached | 6 | 133410 | 17448 | FE-331
SITE-03685 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-08-10 | 2025-08-21 | 11 | Go-Live | Live - Operational | Breached | 34 | 120499 | 13068 | FE-340
SITE-03686 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-12-21 | 2026-01-09 | 19 | Go-Live | Live - Operational | Breached | 6 | 50310 | 12523 | FE-276
SITE-03687 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-12-04 | 2025-12-04 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 71393 | 9106 | FE-272
SITE-03688 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-11-07 |  | 234 | Equipment Dispatch | Equipment Dispatched | Breached | 100 | 88051 | 14137 | FE-119
SITE-03689 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-09-20 | 2025-10-10 | 20 | Go-Live | Live - Operational | Breached | 4 | 75144 | 16422 | FE-398
SITE-03690 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2026-01-14 |  | 166 | Site Survey | Survey Complete | Breached | 50 | 131123 | 17815 | FE-275
SITE-03691 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-08-16 | 2025-08-27 | 11 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 93465 | 15724 | FE-216
SITE-03692 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-07-21 |  | 343 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 65148 | 12418 | FE-408
SITE-03693 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-10-03 |  | 269 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 114407 | 17410 | FE-316
SITE-03694 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-11-10 |  | 231 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 20 | 48926 | 10409 | FE-240
SITE-03695 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-06-12 |  | 382 | Site Survey | Survey Complete | Breached | 34 | 55043 | 4469 | FE-143
SITE-03696 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2026-01-12 | 2026-01-17 | 5 | Go-Live | Live - Operational | Met | 2 | 118938 | 5422 | FE-223
SITE-03697 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-07-12 |  | 352 | Site Survey | Survey Complete | Breached | 10 | 74642 | 10451 | FE-381
SITE-03698 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-12-21 |  | 190 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 43331 | 9496 | FE-211
SITE-03699 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2026-01-06 | 2026-01-26 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 88081 | 3846 | FE-166
SITE-03700 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-10-14 | 2025-11-02 | 19 | Go-Live | Live - Operational | Breached | 50 | 75948 | 13463 | FE-320
SITE-03701 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2026-01-26 |  |  | ROW / Permission | Cancelled | N/A | 100 | 72646 | 12811 | FE-275
SITE-03702 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2026-01-20 | 2026-01-31 | 11 | Go-Live | Live - Operational | Breached | 10 | 118220 | 13808 | FE-298
SITE-03703 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-07-05 |  | 359 | Site Survey | Survey Scheduled | Breached | 34 | 65516 | 4717 | FE-386
SITE-03704 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-11-29 | 2025-12-09 | 10 | Go-Live | Live - Operational | Breached | 34 | 46797 | 16754 | FE-131
SITE-03705 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-09-14 | 2025-09-24 | 10 | Go-Live | Live - Operational | Breached | 6 | 40128 | 8404 | FE-291
SITE-03706 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-08-20 |  | 313 | BOM Finalization | Delayed - Vendor Issue | Breached | 2 | 133359 | 6850 | FE-120
SITE-03707 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-09-12 |  | 290 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 100 | 54539 | 3921 | FE-362
SITE-03708 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-07-24 | 2025-08-06 | 13 | Go-Live | Live - Operational | Breached | 4 | 130992 | 6261 | FE-477
SITE-03709 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-12-11 | 2025-12-12 | 1 | Go-Live | Live - Operational | Met | 50 | 58612 | 8244 | FE-429
SITE-03710 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-06-29 | 2025-06-30 | 1 | Go-Live | Live - Operational | Met | 2 | 75408 | 15270 | FE-437
SITE-03711 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-10-30 |  | 242 | Equipment Dispatch | Equipment Dispatched | Breached | 2 | 120720 | 3940 | FE-244
SITE-03712 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-07-10 | 2025-07-15 | 5 | Go-Live | Live - Operational | Met | 20 | 81298 | 3633 | FE-144
SITE-03713 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-12-27 | 2026-01-05 | 9 | Go-Live | Live - Operational | Breached | 34 | 89995 | 4624 | FE-203
SITE-03714 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-07-21 |  |  | BOM Finalization | Cancelled | N/A | 50 | 39427 | 6541 | FE-352
SITE-03715 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-07-05 | 2025-07-02 | -3 | Go-Live | Live - Operational | Met | 6 | 109165 | 4914 | FE-456
SITE-03716 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-06-16 | 2025-06-11 | -5 | Go-Live | Live - Operational | Met | 20 | 101463 | 4063 | FE-183
SITE-03717 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-11-18 |  | 223 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 103811 | 9723 | FE-446
SITE-03718 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-07-16 |  | 348 | Site Survey | Survey Complete | Breached | 4 | 116617 | 12932 | FE-402
SITE-03719 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Sify Technologies | 2025-06-23 | 2025-06-26 | 3 | Go-Live | Live - Operational | Met | 50 | 101608 | 15412 | FE-456
SITE-03720 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-07-14 |  | 350 | Site Survey | Survey Scheduled | Breached | 50 | 92101 | 4382 | FE-253
SITE-03721 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-06-08 | 2025-06-11 | 3 | Go-Live | Live - Operational | Met | 4 | 109052 | 5386 | FE-359
SITE-03722 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-08-27 | 2025-08-18 | -9 | Go-Live | Live - Operational | Met | 10 | 130461 | 6103 | FE-111
SITE-03723 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-11-04 | 2025-11-17 | 13 | Go-Live | Live - Operational | Breached | 100 | 38041 | 7695 | FE-365
SITE-03724 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-06-20 | 2025-07-07 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 126452 | 15023 | FE-178
SITE-03725 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-08-02 | 2025-07-27 | -6 | Go-Live | Live - Operational | Met | 10 | 43423 | 9961 | FE-113
SITE-03726 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-10-12 |  | 260 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 2 | 69347 | 16124 | FE-453
SITE-03727 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-12-17 | 2025-12-31 | 14 | Go-Live | Live - Operational | Breached | 50 | 80289 | 17748 | FE-336
SITE-03728 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-11-05 | 2025-11-19 | 14 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 50 | 80063 | 14746 | FE-409
SITE-03729 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-07-31 | 2025-08-19 | 19 | Go-Live | Live - Operational | Breached | 100 | 42168 | 15660 | FE-448
SITE-03730 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-11-01 | 2025-11-22 | 21 | Go-Live | Live - Operational | Breached | 2 | 101326 | 10395 | FE-201
SITE-03731 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-08-21 | 2025-08-24 | 3 | Go-Live | Live - Operational | Met | 34 | 98060 | 16251 | FE-351
SITE-03732 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-10-22 |  |  | ROW / Permission | Cancelled | N/A | 10 | 109664 | 17840 | FE-433
SITE-03733 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-08-30 |  | 303 | Site Survey | Survey Scheduled | Breached | 2 | 103729 | 11575 | FE-195
SITE-03734 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2026-01-06 |  | 174 | Installation & Commissioning | Civil Work In Progress | Breached | 34 | 100143 | 9032 | FE-480
SITE-03735 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2026-01-14 | 2026-01-12 | -2 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 4 | 103511 | 10394 | FE-112
SITE-03736 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2026-01-12 |  | 168 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 92960 | 12390 | FE-387
SITE-03737 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-09-15 | 2025-09-17 | 2 | Go-Live | Live - Operational | Met | 2 | 32265 | 7728 | FE-455
SITE-03738 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-09-26 | 2025-10-09 | 13 | Go-Live | Live - Operational | Breached | 50 | 83193 | 16600 | FE-240
SITE-03739 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-08-13 |  | 320 | BOM Finalization | Delayed - Vendor Issue | Breached | 10 | 92368 | 16062 | FE-145
SITE-03740 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-08-03 |  | 330 | Site Survey | Survey Complete | Breached | 34 | 73246 | 6263 | FE-394
SITE-03741 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-06-15 |  | 379 | Site Survey | Survey Complete | Breached | 34 | 95290 | 8446 | FE-102
SITE-03742 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-08-09 | 2025-08-04 | -5 | Go-Live | Live - Operational | Met | 6 | 99309 | 5347 | FE-461
SITE-03743 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Vodafone Idea Business | 2025-09-11 |  |  | Site Survey | Cancelled | N/A | 50 | 43500 | 5170 | FE-257
SITE-03744 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2026-01-16 | 2026-01-30 | 14 | Go-Live | Live - Operational | Breached | 6 | 80385 | 15763 | FE-483
SITE-03745 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-08-31 | 2025-09-17 | 17 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 61843 | 6374 | FE-479
SITE-03746 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-10-13 |  | 259 | Site Survey | Survey Complete | Breached | 100 | 87254 | 4966 | FE-236
SITE-03747 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2026-01-16 | 2026-02-05 | 20 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 34 | 64806 | 9037 | FE-390
SITE-03748 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-06-13 |  | 381 | Site Survey | Survey Scheduled | Breached | 2 | 39302 | 5019 | FE-407
SITE-03749 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-10-11 | 2025-10-10 | -1 | Go-Live | Live - Operational | Met | 50 | 132839 | 13118 | FE-341
SITE-03750 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-01 |  |  | ROW / Permission | Cancelled | N/A | 10 | 79193 | 16571 | FE-371
SITE-03751 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Branch | Excitel Enterprise | 2025-12-24 |  | 187 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 117021 | 13837 | FE-330
SITE-03752 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-08-11 | 2025-08-02 | -9 | Go-Live | Live - Operational | Met | 4 | 81266 | 14689 | FE-284
SITE-03753 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-06-23 | 2025-06-25 | 2 | Go-Live | Live - Operational | Met | 20 | 126778 | 16175 | FE-109
SITE-03754 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-11-13 |  | 228 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 52748 | 17780 | FE-481
SITE-03755 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-06-09 | 2025-06-25 | 16 | Go-Live | Live - Operational | Breached | 34 | 121392 | 14325 | FE-395
SITE-03756 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-12-30 | 2025-12-30 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 65366 | 13544 | FE-483
SITE-03757 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-08-29 |  | 304 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 125239 | 15813 | FE-456
SITE-03758 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-07-09 |  | 355 | Site Survey | Survey Scheduled | Breached | 6 | 93600 | 3627 | FE-106
SITE-03759 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2026-01-13 |  | 167 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 54829 | 7938 | FE-256
SITE-03760 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-12-15 |  |  | BOM Finalization | Cancelled | N/A | 10 | 69031 | 14545 | FE-160
SITE-03761 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-08-03 |  | 330 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 123981 | 11927 | FE-410
SITE-03762 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-11-27 |  | 214 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 4 | 86321 | 3709 | FE-338
SITE-03763 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-12-05 |  | 206 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 86782 | 10136 | FE-138
SITE-03764 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2026-01-15 | 2026-01-24 | 9 | Go-Live | Live - Operational | Breached | 4 | 119599 | 17478 | FE-247
SITE-03765 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-12-05 | 2025-12-11 | 6 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 10 | 111873 | 6994 | FE-347
SITE-03766 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-09-05 |  | 297 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 103206 | 12589 | FE-163
SITE-03767 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-09-20 | 2025-09-30 | 10 | Go-Live | Live - Operational | Breached | 100 | 121188 | 11239 | FE-149
SITE-03768 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-27 |  | 245 | Equipment Dispatch | Equipment Dispatched | Breached | 4 | 96771 | 17677 | FE-339
SITE-03769 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-08-16 |  | 317 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 2 | 91916 | 15422 | FE-395
SITE-03770 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Branch | Sify Technologies | 2025-07-06 |  | 358 | Site Survey | Survey Scheduled | Breached | 50 | 61789 | 7671 | FE-295
SITE-03771 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2026-01-11 |  | 169 | Installation & Commissioning | Civil Work In Progress | Breached | 2 | 127385 | 12946 | FE-334
SITE-03772 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-12-10 | 2025-12-19 | 9 | Go-Live | Live - Operational | Breached | 34 | 121119 | 6526 | FE-223
SITE-03773 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-10-27 | 2025-11-12 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 35406 | 11180 | FE-386
SITE-03774 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-08-07 | 2025-08-07 | 0 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 6 | 39343 | 15803 | FE-432
SITE-03775 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-12-16 | 2025-12-16 | 0 | Go-Live | Live - Operational | Met | 2 | 108544 | 10202 | FE-440
SITE-03776 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-10 |  | 384 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 75262 | 15278 | FE-204
SITE-03777 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-22 |  | 372 | Site Survey | Survey Scheduled | Breached | 50 | 127350 | 17021 | FE-442
SITE-03778 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-06-06 |  | 388 | BOM Finalization | Delayed - Vendor Issue | Breached | 100 | 29261 | 17130 | FE-487
SITE-03779 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-12-30 | 2026-01-04 | 5 | Go-Live | Live - Operational | Met | 2 | 97170 | 13846 | FE-362
SITE-03780 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-08-02 |  | 331 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 132929 | 17273 | FE-485
SITE-03781 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-08-05 |  | 328 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 105839 | 6032 | FE-444
SITE-03782 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-08-22 |  | 311 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 117668 | 6383 | FE-415
SITE-03783 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2026-01-10 | 2026-01-30 | 20 | Go-Live | Live - Operational | Breached | 20 | 134440 | 9075 | FE-302
SITE-03784 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-09-23 | 2025-10-13 | 20 | Go-Live | Live - Operational | Breached | 20 | 39771 | 16171 | FE-406
SITE-03785 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-11-03 |  | 238 | Site Survey | Survey Scheduled | Breached | 100 | 103680 | 9234 | FE-101
SITE-03786 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-08-30 | 2025-09-18 | 19 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 2 | 52366 | 10667 | FE-191
SITE-03787 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Data Center | Local ISP Partner | 2025-07-31 | 2025-07-29 | -2 | Go-Live | Live - Operational | Met | 20 | 73260 | 6315 | FE-290
SITE-03788 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2025-06-08 | 2025-05-31 | -8 | Go-Live | Live - Operational | Met | 2 | 124002 | 9743 | FE-216
SITE-03789 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-10-15 |  | 257 | Site Survey | Survey Scheduled | Breached | 6 | 63620 | 11118 | FE-304
SITE-03790 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-07-08 | 2025-07-19 | 11 | Go-Live | Live - Operational | Breached | 100 | 127622 | 13869 | FE-394
SITE-03791 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Airtel Business | 2025-12-27 |  | 184 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 122808 | 16067 | FE-308
SITE-03792 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-10-10 | 2025-10-27 | 17 | Go-Live | Live - Operational | Breached | 20 | 44976 | 5948 | FE-372
SITE-03793 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-12-20 | 2026-01-12 | 23 | Go-Live | Live - Operational | Breached | 6 | 131091 | 17146 | FE-212
SITE-03794 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Branch | Tata Communications | 2025-08-31 | 2025-09-03 | 3 | Go-Live | Live - Operational | Met | 10 | 134156 | 7258 | FE-467
SITE-03795 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-10-23 | 2025-11-01 | 9 | Go-Live | Live - Operational | Breached | 10 | 60896 | 4057 | FE-204
SITE-03796 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-07-26 | 2025-07-28 | 2 | Go-Live | Live - Operational | Met | 4 | 110871 | 13768 | FE-375
SITE-03797 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-09-16 |  | 286 | Site Survey | Survey Complete | Breached | 34 | 112629 | 11476 | FE-380
SITE-03798 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-08-01 |  | 332 | Site Survey | Survey Scheduled | Breached | 34 | 126663 | 14757 | FE-446
SITE-03799 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2025-10-30 |  | 242 | Site Survey | Survey Scheduled | Breached | 2 | 113530 | 13786 | FE-297
SITE-03800 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-09-05 |  | 297 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 40564 | 9523 | FE-350
SITE-03801 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Vodafone Idea Business | 2025-11-24 |  | 217 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 20 | 31947 | 8795 | FE-205
SITE-03802 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-11-18 | 2025-12-05 | 17 | Go-Live | Live - Operational | Breached | 34 | 108837 | 6845 | FE-234
SITE-03803 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-12-28 |  | 183 | Last Mile Provisioning | Last Mile - ROW Pending | Breached | 10 | 107066 | 10984 | FE-414
SITE-03804 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-07-30 |  | 334 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 34 | 30995 | 7399 | FE-184
SITE-03805 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-09-09 |  | 293 | Equipment Dispatch | Equipment Dispatched | Breached | 50 | 73278 | 16572 | FE-285
SITE-03806 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-08-29 | 2025-08-19 | -10 | Go-Live | Live - Operational | Met | 50 | 124526 | 14138 | FE-368
SITE-03807 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-11-18 |  | 223 | Site Survey | Survey Complete | Breached | 20 | 92777 | 10341 | FE-341
SITE-03808 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-10-31 |  | 241 | Installation & Commissioning | Civil Work In Progress | Breached | 10 | 46654 | 12667 | FE-398
SITE-03809 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-06-06 |  | 388 | BOM Finalization | Delayed - Vendor Issue | Breached | 34 | 52274 | 8585 | FE-175
SITE-03810 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Gwalior | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Sify Technologies | 2025-07-15 | 2025-07-11 | -4 | Go-Live | Live - Operational | Met | 50 | 59721 | 14592 | FE-326
SITE-03811 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-11-26 |  | 215 | Installation & Commissioning | Civil Work In Progress | Breached | 20 | 108620 | 9018 | FE-405
SITE-03812 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-10-26 | 2025-11-07 | 12 | Go-Live | Live - Operational | Breached | 20 | 82363 | 9435 | FE-322
SITE-03813 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-10-04 | 2025-09-27 | -7 | Go-Live | Live - Operational | Met | 10 | 32104 | 4377 | FE-176
SITE-03814 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-07-13 |  | 351 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 50 | 116012 | 9661 | FE-213
SITE-03815 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-09-13 |  | 289 | BOM Finalization | Delayed - Vendor Issue | Breached | 6 | 50283 | 15455 | FE-204
SITE-03816 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-10-28 | 2025-10-31 | 3 | Go-Live | Live - Operational | Met | 50 | 115494 | 9913 | FE-102
SITE-03817 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Excitel Enterprise | 2025-06-14 | 2025-06-04 | -10 | Go-Live | Live - Operational | Met | 50 | 79947 | 15296 | FE-472
SITE-03818 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Data Center | Sify Technologies | 2026-01-11 | 2026-01-10 | -1 | Go-Live | Live - Operational | Met | 20 | 127018 | 10828 | FE-496
SITE-03819 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-09-05 |  | 297 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 39975 | 11435 | FE-320
SITE-03820 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Airtel Business | 2025-06-11 |  | 383 | ROW / Permission | On Hold - Client Site Not Ready | Breached | 100 | 40678 | 10296 | FE-249
SITE-03821 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Data Center | Airtel Business | 2025-08-18 | 2025-08-30 | 12 | Go-Live | Live - Operational | Breached | 20 | 82849 | 10632 | FE-394
SITE-03822 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Local ISP Partner | 2025-12-25 |  | 186 | Equipment Dispatch | Equipment Dispatched | Breached | 10 | 98721 | 10716 | FE-493
SITE-03823 | PRJ-2024042 | CL008 | West | Maharashtra | Nagpur | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-10-12 | 2025-10-03 | -9 | Go-Live | Live - Operational | Met | 50 | 73189 | 4939 | FE-383
SITE-03824 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Local ISP Partner | 2025-12-27 |  | 184 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 86004 | 4983 | FE-403
SITE-03825 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-08-07 | 2025-08-10 | 3 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 50 | 94599 | 8725 | FE-416
SITE-03826 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2025-07-16 |  | 348 | Site Survey | Survey Complete | Breached | 6 | 59423 | 4238 | FE-361
SITE-03827 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Local ISP Partner | 2025-12-28 |  | 183 | Site Survey | Survey Complete | Breached | 6 | 62762 | 7142 | FE-252
SITE-03828 | PRJ-2024042 | CL008 | West | Gujarat | Vadodara | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Sify Technologies | 2025-10-19 | 2025-11-03 | 15 | Go-Live | Live - Operational | Breached | 6 | 42692 | 6558 | FE-152
SITE-03829 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-02 | 2026-01-07 | 5 | Go-Live | Live - Operational | Met | 4 | 28669 | 12037 | FE-379
SITE-03830 | PRJ-2024042 | CL008 | West | Maharashtra | Pune | Hybrid WAN (MPLS+SDWAN) | Data Center | Excitel Enterprise | 2026-01-14 | 2026-01-18 | 4 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 20 | 78038 | 10498 | FE-100
SITE-03831 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Vodafone Idea Business | 2025-10-06 | 2025-10-21 | 15 | Go-Live | Live - Operational | Breached | 20 | 88234 | 10550 | FE-476
SITE-03832 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-06-26 |  | 368 | Site Survey | Survey Scheduled | Breached | 4 | 134494 | 9038 | FE-122
SITE-03833 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2025-08-25 |  |  | BOM Finalization | Cancelled | N/A | 4 | 111686 | 12724 | FE-427
SITE-03834 | PRJ-2024042 | CL008 | West | Maharashtra | Mumbai | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-07-07 | 2025-07-12 | 5 | Testing & Acceptance | Installation Complete - Pending Acceptance | Met | 10 | 56161 | 7050 | FE-290
SITE-03835 | PRJ-2024042 | CL008 | West | Gujarat | Rajkot | Hybrid WAN (MPLS+SDWAN) | Data Center | Tata Communications | 2025-12-06 |  | 205 | BOM Finalization | Delayed - Vendor Issue | Breached | 4 | 134813 | 7160 | FE-363
SITE-03836 | PRJ-2024042 | CL008 | West | Goa | Margao | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Excitel Enterprise | 2025-12-19 | 2025-12-10 | -9 | Go-Live | Live - Operational | Met | 34 | 130944 | 17501 | FE-346
SITE-03837 | PRJ-2024042 | CL008 | West | Gujarat | Ahmedabad | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2026-01-16 | 2026-01-07 | -9 | Go-Live | Live - Operational | Met | 20 | 134253 | 9296 | FE-338
SITE-03838 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2026-01-25 | 2026-02-07 | 13 | Go-Live | Live - Operational | Breached | 50 | 125999 | 14216 | FE-146
SITE-03839 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2026-01-25 | 2026-02-09 | 15 | Go-Live | Live - Operational | Breached | 34 | 72045 | 5479 | FE-394
SITE-03840 | PRJ-2024042 | CL008 | West | Maharashtra | Thane | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Vodafone Idea Business | 2026-01-05 | 2026-01-21 | 16 | Go-Live | Live - Operational | Breached | 4 | 93754 | 10595 | FE-438
SITE-03841 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Tata Communications | 2025-06-07 |  | 387 | Equipment Dispatch | Equipment Dispatched | Breached | 20 | 107995 | 5918 | FE-405
SITE-03842 | PRJ-2024042 | CL008 | West | Gujarat | Surat | Hybrid WAN (MPLS+SDWAN) | Corporate Office | Tata Communications | 2026-01-24 |  | 156 | Installation & Commissioning | Civil Work In Progress | Breached | 100 | 120011 | 5161 | FE-407
SITE-03843 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Bhopal | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Airtel Business | 2025-11-04 | 2025-11-08 | 4 | Go-Live | Live - Operational | Met | 4 | 127930 | 6690 | FE-243
SITE-03844 | PRJ-2024042 | CL008 | West | Goa | Panaji | Hybrid WAN (MPLS+SDWAN) | Branch | Local ISP Partner | 2025-06-16 | 2025-06-22 | 6 | Go-Live | Live - Operational | Breached | 2 | 55944 | 11331 | FE-446
SITE-03845 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Warehouse/Ops Hub | Excitel Enterprise | 2025-09-06 |  | 296 | Equipment Dispatch | Equipment Dispatched | Breached | 34 | 78509 | 6031 | FE-466
SITE-03846 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Jabalpur | Hybrid WAN (MPLS+SDWAN) | Data Center | Vodafone Idea Business | 2025-06-07 |  | 387 | Installation & Commissioning | Civil Work In Progress | Breached | 4 | 36951 | 14813 | FE-192
SITE-03847 | PRJ-2024042 | CL008 | West | Madhya Pradesh | Indore | Hybrid WAN (MPLS+SDWAN) | ATM/Off-site | Tata Communications | 2025-06-14 |  | 380 | BOM Finalization | Delayed - Vendor Issue | Breached | 50 | 105582 | 17101 | FE-289
SITE-03848 | PRJ-2024042 | CL008 | West | Maharashtra | Nashik | Hybrid WAN (MPLS+SDWAN) | Branch | Airtel Business | 2025-10-09 | 2025-10-25 | 16 | Testing & Acceptance | Installation Complete - Pending Acceptance | Breached | 4 | 43450 | 12582 | FE-320

## Tasks_WBS
TaskID | ProjectID | TaskName | WBSPhase | PlannedStartDate | PlannedFinishDate | ActualFinishDate | DurationDays | PercentComplete | TaskStatus | Owner | Dependency
TSK-00001 | PRJ-2024001 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-08-08 | 2024-08-13 | 2024-08-11 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00002 | PRJ-2024001 | Site Survey Planning | Site Survey Planning | 2024-08-13 | 2024-08-20 | 2024-08-20 | 7 | 100 | Completed | Sandeep Rao | FS
TSK-00003 | PRJ-2024001 | BOM & Procurement | BOM & Procurement | 2024-08-20 | 2024-08-30 | 2024-09-03 | 10 | 100 | Completed | Ananya Joshi | SS
TSK-00004 | PRJ-2024001 | Vendor Coordination | Vendor Coordination | 2024-08-30 | 2024-09-07 | 2024-09-09 | 8 | 100 | Completed | Deepa Nair | FS
TSK-00005 | PRJ-2024001 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-09-07 | 2024-09-22 | 2024-10-04 | 15 | 100 | Completed | Sandeep Rao | SS
TSK-00006 | PRJ-2024001 | Last Mile Tie-up | Last Mile Tie-up | 2024-09-22 | 2024-10-04 | 2024-10-05 | 12 | 100 | Completed | Ananya Joshi | SS
TSK-00007 | PRJ-2024001 | Equipment Staging | Equipment Staging | 2024-10-04 | 2024-10-10 | 2024-10-16 | 6 | 100 | Completed | Deepa Nair | FS
TSK-00008 | PRJ-2024001 | Installation & Commissioning | Installation & Commissioning | 2024-10-10 | 2024-10-20 | 2024-10-20 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00009 | PRJ-2024001 | UAT / Testing | UAT / Testing | 2024-10-20 | 2024-10-25 | 2024-11-03 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00010 | PRJ-2024001 | Go-Live & Handover | Go-Live & Handover | 2024-10-25 | 2024-10-28 | 2024-11-06 | 3 | 100 | Completed | Chinmay Deshpande | FS
TSK-00011 | PRJ-2024001 | Documentation & Closure | Documentation & Closure | 2024-10-28 | 2024-11-01 | 2024-11-09 | 4 | 100 | Completed | Chinmay Deshpande | FS
TSK-00012 | PRJ-2024001 | Hypercare Support | Hypercare Support | 2024-11-01 | 2024-11-15 | 2024-11-14 | 14 | 100 | Completed | Rahul K. Patil | SS
TSK-00013 | PRJ-2024002 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-10-19 | 2024-10-24 | 2024-10-22 | 5 | 100 | Completed | Ananya Joshi | FS
TSK-00014 | PRJ-2024002 | Site Survey Planning | Site Survey Planning | 2024-10-24 | 2024-10-31 | 2024-10-28 | 7 | 100 | Completed | Rahul K. Patil | FS
TSK-00015 | PRJ-2024002 | BOM & Procurement | BOM & Procurement | 2024-10-31 | 2024-11-10 | 2024-11-15 | 10 | 100 | Completed | Rahul K. Patil | FS
TSK-00016 | PRJ-2024002 | Vendor Coordination | Vendor Coordination | 2024-11-10 | 2024-11-18 | 2024-11-15 | 8 | 100 | Completed | Karthik Subramanian | FS
TSK-00017 | PRJ-2024002 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-11-18 | 2024-12-03 | 2024-12-13 | 15 | 100 | Completed | Chinmay Deshpande | FS
TSK-00018 | PRJ-2024002 | Last Mile Tie-up | Last Mile Tie-up | 2024-12-03 | 2024-12-15 | 2024-12-14 | 12 | 100 | Completed | Farah Khan | FS
TSK-00019 | PRJ-2024002 | Equipment Staging | Equipment Staging | 2024-12-15 | 2024-12-21 | 2024-12-26 | 6 | 100 | Completed | Chinmay Deshpande | FS
TSK-00020 | PRJ-2024002 | Installation & Commissioning | Installation & Commissioning | 2024-12-21 | 2024-12-31 | 2025-01-04 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00021 | PRJ-2024002 | UAT / Testing | UAT / Testing | 2024-12-31 | 2025-01-05 | 2025-01-12 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00022 | PRJ-2024002 | Go-Live & Handover | Go-Live & Handover | 2025-01-05 | 2025-01-08 | 2025-01-16 | 3 | 100 | Completed | Chinmay Deshpande | FS
TSK-00023 | PRJ-2024002 | Documentation & Closure | Documentation & Closure | 2025-01-08 | 2025-01-12 | 2025-01-09 | 4 | 100 | Completed | Deepa Nair | FS
TSK-00024 | PRJ-2024002 | Hypercare Support | Hypercare Support | 2025-01-12 | 2025-01-26 | 2025-01-24 | 14 | 100 | Completed | Manish Agarwal | FS
TSK-00025 | PRJ-2024003 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-11-09 | 2024-11-14 | 2024-11-25 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00026 | PRJ-2024003 | Site Survey Planning | Site Survey Planning | 2024-11-14 | 2024-11-21 | 2024-12-01 | 7 | 100 | Completed | Ananya Joshi | FS
TSK-00027 | PRJ-2024003 | BOM & Procurement | BOM & Procurement | 2024-11-21 | 2024-12-01 | 2024-12-09 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00028 | PRJ-2024003 | Vendor Coordination | Vendor Coordination | 2024-12-01 | 2024-12-09 | 2024-12-10 | 8 | 100 | Completed | Karthik Subramanian | SS
TSK-00029 | PRJ-2024003 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-12-09 | 2024-12-24 | 2024-12-25 | 15 | 100 | Completed | Chinmay Deshpande | FS
TSK-00030 | PRJ-2024003 | Last Mile Tie-up | Last Mile Tie-up | 2024-12-24 | 2025-01-05 | 2025-01-13 | 12 | 100 | Completed | Farah Khan | FS
TSK-00031 | PRJ-2024003 | Equipment Staging | Equipment Staging | 2025-01-05 | 2025-01-11 | 2025-01-22 | 6 | 100 | Completed | Manish Agarwal | SS
TSK-00032 | PRJ-2024003 | Installation & Commissioning | Installation & Commissioning | 2025-01-11 | 2025-01-21 | 2025-01-24 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00033 | PRJ-2024003 | UAT / Testing | UAT / Testing | 2025-01-21 | 2025-01-26 | 2025-02-04 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00034 | PRJ-2024003 | Go-Live & Handover | Go-Live & Handover | 2025-01-26 | 2025-01-29 | 2025-02-06 | 3 | 100 | Completed | Ananya Joshi | SS
TSK-00035 | PRJ-2024003 | Documentation & Closure | Documentation & Closure | 2025-01-29 | 2025-02-02 | 2025-02-11 | 4 | 100 | Completed | Karthik Subramanian | FS
TSK-00036 | PRJ-2024003 | Hypercare Support | Hypercare Support | 2025-02-02 | 2025-02-16 | 2025-02-25 | 14 | 100 | Completed | Rahul K. Patil | FS
TSK-00037 | PRJ-2024004 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-08-28 | 2024-09-02 | 2024-09-08 | 5 | 100 | Completed | Manish Agarwal | FS
TSK-00038 | PRJ-2024004 | Site Survey Planning | Site Survey Planning | 2024-09-02 | 2024-09-09 | 2024-09-16 | 7 | 100 | Completed | Chinmay Deshpande | SS
TSK-00039 | PRJ-2024004 | BOM & Procurement | BOM & Procurement | 2024-09-09 | 2024-09-19 | 2024-09-28 | 10 | 100 | Completed | Sandeep Rao | FS
TSK-00040 | PRJ-2024004 | Vendor Coordination | Vendor Coordination | 2024-09-19 | 2024-09-27 | 2024-10-08 | 8 | 100 | Completed | Manish Agarwal | SS
TSK-00041 | PRJ-2024004 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-09-27 | 2024-10-12 | 2024-10-21 | 15 | 100 | Completed | Manish Agarwal | SS
TSK-00042 | PRJ-2024004 | Last Mile Tie-up | Last Mile Tie-up | 2024-10-12 | 2024-10-24 | 2024-11-02 | 12 | 100 | Completed | Manish Agarwal | SS
TSK-00043 | PRJ-2024004 | Equipment Staging | Equipment Staging | 2024-10-24 | 2024-10-30 | 2024-11-02 | 6 | 100 | Completed | Karthik Subramanian | FS
TSK-00044 | PRJ-2024004 | Installation & Commissioning | Installation & Commissioning | 2024-10-30 | 2024-11-09 | 2024-11-10 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00045 | PRJ-2024004 | UAT / Testing | UAT / Testing | 2024-11-09 | 2024-11-14 | 2024-11-23 | 5 | 100 | Completed | Manish Agarwal | FS
TSK-00046 | PRJ-2024004 | Go-Live & Handover | Go-Live & Handover | 2024-11-14 | 2024-11-17 | 2024-11-15 | 3 | 100 | Completed | Rahul K. Patil | FS
TSK-00047 | PRJ-2024004 | Documentation & Closure | Documentation & Closure | 2024-11-17 | 2024-11-21 | 2024-11-30 | 4 | 100 | Completed | Sandeep Rao | FS
TSK-00048 | PRJ-2024004 | Hypercare Support | Hypercare Support | 2024-11-21 | 2024-12-05 | 2024-12-17 | 14 | 100 | Completed | Karthik Subramanian | SS
TSK-00049 | PRJ-2024005 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-11-24 | 2024-11-29 | 2024-11-28 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00050 | PRJ-2024005 | Site Survey Planning | Site Survey Planning | 2024-11-29 | 2024-12-06 | 2024-12-18 | 7 | 100 | Completed | Sandeep Rao | FS
TSK-00051 | PRJ-2024005 | BOM & Procurement | BOM & Procurement | 2024-12-06 | 2024-12-16 | 2024-12-17 | 10 | 100 | Completed | Deepa Nair | SS
TSK-00052 | PRJ-2024005 | Vendor Coordination | Vendor Coordination | 2024-12-16 | 2024-12-24 | 2024-12-26 | 8 | 100 | Completed | Ananya Joshi | FS
TSK-00053 | PRJ-2024005 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-12-24 | 2025-01-08 | 2025-01-15 | 15 | 100 | Completed | Manish Agarwal | FS
TSK-00054 | PRJ-2024005 | Last Mile Tie-up | Last Mile Tie-up | 2025-01-08 | 2025-01-20 | 2025-01-17 | 12 | 100 | Completed | Deepa Nair | FS
TSK-00055 | PRJ-2024005 | Equipment Staging | Equipment Staging | 2025-01-20 | 2025-01-26 | 2025-02-01 | 6 | 100 | Completed | Manish Agarwal | FS
TSK-00056 | PRJ-2024005 | Installation & Commissioning | Installation & Commissioning | 2025-01-26 | 2025-02-05 | 2025-02-16 | 10 | 100 | Completed | Sandeep Rao | SS
TSK-00057 | PRJ-2024005 | UAT / Testing | UAT / Testing | 2025-02-05 | 2025-02-10 | 2025-02-08 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00058 | PRJ-2024005 | Go-Live & Handover | Go-Live & Handover | 2025-02-10 | 2025-02-13 | 2025-02-10 | 3 | 100 | Completed | Deepa Nair | FS
TSK-00059 | PRJ-2024005 | Documentation & Closure | Documentation & Closure | 2025-02-13 | 2025-02-17 | 2025-02-21 | 4 | 100 | Completed | Deepa Nair | SS
TSK-00060 | PRJ-2024005 | Hypercare Support | Hypercare Support | 2025-02-17 | 2025-03-03 | 2025-03-02 | 14 | 100 | Completed | Ananya Joshi | FS
TSK-00061 | PRJ-2024006 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-07-07 | 2024-07-12 | 2024-07-17 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00062 | PRJ-2024006 | Site Survey Planning | Site Survey Planning | 2024-07-12 | 2024-07-19 | 2024-07-16 | 7 | 100 | Completed | Deepa Nair | FS
TSK-00063 | PRJ-2024006 | BOM & Procurement | BOM & Procurement | 2024-07-19 | 2024-07-29 | 2024-08-02 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00064 | PRJ-2024006 | Vendor Coordination | Vendor Coordination | 2024-07-29 | 2024-08-06 | 2024-08-10 | 8 | 100 | Completed | Sandeep Rao | SS
TSK-00065 | PRJ-2024006 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-08-06 | 2024-08-21 | 2024-08-21 | 15 | 100 | Completed | Chinmay Deshpande | FS
TSK-00066 | PRJ-2024006 | Last Mile Tie-up | Last Mile Tie-up | 2024-08-21 | 2024-09-02 | 2024-09-03 | 12 | 100 | Completed | Karthik Subramanian | FS
TSK-00067 | PRJ-2024006 | Equipment Staging | Equipment Staging | 2024-09-02 | 2024-09-08 | 2024-09-12 | 6 | 100 | Completed | Rahul K. Patil | FS
TSK-00068 | PRJ-2024006 | Installation & Commissioning | Installation & Commissioning | 2024-09-08 | 2024-09-18 | 2024-09-23 | 10 | 100 | Completed | Rahul K. Patil | FS
TSK-00069 | PRJ-2024006 | UAT / Testing | UAT / Testing | 2024-09-18 | 2024-09-23 | 2024-09-20 | 5 | 100 | Completed | Farah Khan | FS
TSK-00070 | PRJ-2024006 | Go-Live & Handover | Go-Live & Handover | 2024-09-23 | 2024-09-26 | 2024-10-01 | 3 | 100 | Completed | Ananya Joshi | FS
TSK-00071 | PRJ-2024006 | Documentation & Closure | Documentation & Closure | 2024-09-26 | 2024-09-30 | 2024-10-11 | 4 | 100 | Completed | Farah Khan | FS
TSK-00072 | PRJ-2024006 | Hypercare Support | Hypercare Support | 2024-09-30 | 2024-10-14 | 2024-10-15 | 14 | 100 | Completed | Karthik Subramanian | SS
TSK-00073 | PRJ-2024007 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-12-19 | 2024-12-24 | 2024-12-25 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00074 | PRJ-2024007 | Site Survey Planning | Site Survey Planning | 2024-12-24 | 2024-12-31 | 2025-01-10 | 7 | 100 | Completed | Sandeep Rao | FS
TSK-00075 | PRJ-2024007 | BOM & Procurement | BOM & Procurement | 2024-12-31 | 2025-01-10 | 2025-01-13 | 10 | 100 | Completed | Farah Khan | FS
TSK-00076 | PRJ-2024007 | Vendor Coordination | Vendor Coordination | 2025-01-10 | 2025-01-18 | 2025-01-17 | 8 | 100 | Completed | Rahul K. Patil | FS
TSK-00077 | PRJ-2024007 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-01-18 | 2025-02-02 | 2025-01-31 | 15 | 100 | Completed | Manish Agarwal | SS
TSK-00078 | PRJ-2024007 | Last Mile Tie-up | Last Mile Tie-up | 2025-02-02 | 2025-02-14 | 2025-02-20 | 12 | 100 | Completed | Sandeep Rao | FS
TSK-00079 | PRJ-2024007 | Equipment Staging | Equipment Staging | 2025-02-14 | 2025-02-20 | 2025-02-28 | 6 | 100 | Completed | Farah Khan | FS
TSK-00080 | PRJ-2024007 | Installation & Commissioning | Installation & Commissioning | 2025-02-20 | 2025-03-02 | 2025-03-12 | 10 | 100 | Completed | Ananya Joshi | FS
TSK-00081 | PRJ-2024007 | UAT / Testing | UAT / Testing | 2025-03-02 | 2025-03-07 | 2025-03-15 | 5 | 100 | Completed | Farah Khan | FS
TSK-00082 | PRJ-2024007 | Go-Live & Handover | Go-Live & Handover | 2025-03-07 | 2025-03-10 | 2025-03-16 | 3 | 100 | Completed | Deepa Nair | FS
TSK-00083 | PRJ-2024007 | Documentation & Closure | Documentation & Closure | 2025-03-10 | 2025-03-14 | 2025-03-24 | 4 | 100 | Completed | Ananya Joshi | FS
TSK-00084 | PRJ-2024007 | Hypercare Support | Hypercare Support | 2025-03-14 | 2025-03-28 | 2025-04-03 | 14 | 100 | Completed | Sandeep Rao | SS
TSK-00085 | PRJ-2024008 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-11-03 | 2024-11-08 | 2024-11-20 | 5 | 100 | Completed | Sandeep Rao | FS
TSK-00086 | PRJ-2024008 | Site Survey Planning | Site Survey Planning | 2024-11-08 | 2024-11-15 | 2024-11-21 | 7 | 100 | Completed | Sandeep Rao | SS
TSK-00087 | PRJ-2024008 | BOM & Procurement | BOM & Procurement | 2024-11-15 | 2024-11-25 | 2024-12-02 | 10 | 100 | Completed | Ananya Joshi | FS
TSK-00088 | PRJ-2024008 | Vendor Coordination | Vendor Coordination | 2024-11-25 | 2024-12-03 | 2024-12-02 | 8 | 100 | Completed | Farah Khan | FS
TSK-00089 | PRJ-2024008 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-12-03 | 2024-12-18 | 2024-12-20 | 15 | 100 | Completed | Chinmay Deshpande | FS
TSK-00090 | PRJ-2024008 | Last Mile Tie-up | Last Mile Tie-up | 2024-12-18 | 2024-12-30 | 2025-01-03 | 12 | 100 | Completed | Karthik Subramanian | FS
TSK-00091 | PRJ-2024008 | Equipment Staging | Equipment Staging | 2024-12-30 | 2025-01-05 | 2025-01-09 | 6 | 100 | Completed | Sandeep Rao | FS
TSK-00092 | PRJ-2024008 | Installation & Commissioning | Installation & Commissioning | 2025-01-05 | 2025-01-15 | 2025-01-27 | 10 | 100 | Completed | Sandeep Rao | SS
TSK-00093 | PRJ-2024008 | UAT / Testing | UAT / Testing | 2025-01-15 | 2025-01-20 | 2025-01-25 | 5 | 100 | Completed | Farah Khan | FS
TSK-00094 | PRJ-2024008 | Go-Live & Handover | Go-Live & Handover | 2025-01-20 | 2025-01-23 | 2025-02-02 | 3 | 100 | Completed | Manish Agarwal | FS
TSK-00095 | PRJ-2024008 | Documentation & Closure | Documentation & Closure | 2025-01-23 | 2025-01-27 | 2025-01-25 | 4 | 100 | Completed | Sandeep Rao | FS
TSK-00096 | PRJ-2024008 | Hypercare Support | Hypercare Support | 2025-01-27 | 2025-02-10 | 2025-02-22 | 14 | 100 | Completed | Karthik Subramanian | FS
TSK-00097 | PRJ-2024009 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-08-15 | 2024-08-20 | 2024-08-31 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00098 | PRJ-2024009 | Site Survey Planning | Site Survey Planning | 2024-08-20 | 2024-08-27 | 2024-08-28 | 7 | 100 | Completed | Chinmay Deshpande | FS
TSK-00099 | PRJ-2024009 | BOM & Procurement | BOM & Procurement | 2024-08-27 | 2024-09-06 | 2024-09-13 | 10 | 100 | Completed | Ananya Joshi | SS
TSK-00100 | PRJ-2024009 | Vendor Coordination | Vendor Coordination | 2024-09-06 | 2024-09-14 | 2024-09-17 | 8 | 100 | Completed | Manish Agarwal | FS
TSK-00101 | PRJ-2024009 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-09-14 | 2024-09-29 | 2024-10-02 | 15 | 100 | Completed | Rahul K. Patil | FS
TSK-00102 | PRJ-2024009 | Last Mile Tie-up | Last Mile Tie-up | 2024-09-29 | 2024-10-11 | 2024-10-12 | 12 | 100 | Completed | Manish Agarwal | SS
TSK-00103 | PRJ-2024009 | Equipment Staging | Equipment Staging | 2024-10-11 | 2024-10-17 | 2024-10-15 | 6 | 100 | Completed | Farah Khan | FS
TSK-00104 | PRJ-2024009 | Installation & Commissioning | Installation & Commissioning | 2024-10-17 | 2024-10-27 | 2024-10-26 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00105 | PRJ-2024009 | UAT / Testing | UAT / Testing | 2024-10-27 | 2024-11-01 | 2024-11-06 | 5 | 100 | Completed | Ananya Joshi | SS
TSK-00106 | PRJ-2024009 | Go-Live & Handover | Go-Live & Handover | 2024-11-01 | 2024-11-04 | 2024-11-04 | 3 | 100 | Completed | Chinmay Deshpande | FS
TSK-00107 | PRJ-2024009 | Documentation & Closure | Documentation & Closure | 2024-11-04 | 2024-11-08 | 2024-11-07 | 4 | 100 | Completed | Karthik Subramanian | FS
TSK-00108 | PRJ-2024009 | Hypercare Support | Hypercare Support | 2024-11-08 | 2024-11-22 | 2024-11-30 | 14 | 100 | Completed | Sandeep Rao | FS
TSK-00109 | PRJ-2024010 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-11-11 | 2024-11-16 | 2024-11-25 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00110 | PRJ-2024010 | Site Survey Planning | Site Survey Planning | 2024-11-16 | 2024-11-23 | 2024-12-04 | 7 | 100 | Completed | Karthik Subramanian | FS
TSK-00111 | PRJ-2024010 | BOM & Procurement | BOM & Procurement | 2024-11-23 | 2024-12-03 | 2024-12-06 | 10 | 100 | Completed | Ananya Joshi | SS
TSK-00112 | PRJ-2024010 | Vendor Coordination | Vendor Coordination | 2024-12-03 | 2024-12-11 | 2024-12-23 | 8 | 100 | Completed | Rahul K. Patil | FS
TSK-00113 | PRJ-2024010 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-12-11 | 2024-12-26 | 2025-01-03 | 15 | 100 | Completed | Ananya Joshi | FS
TSK-00114 | PRJ-2024010 | Last Mile Tie-up | Last Mile Tie-up | 2024-12-26 | 2025-01-07 | 2025-01-11 | 12 | 100 | Completed | Karthik Subramanian | FS
TSK-00115 | PRJ-2024010 | Equipment Staging | Equipment Staging | 2025-01-07 | 2025-01-13 | 2025-01-24 | 6 | 100 | Completed | Sandeep Rao | FS
TSK-00116 | PRJ-2024010 | Installation & Commissioning | Installation & Commissioning | 2025-01-13 | 2025-01-23 | 2025-02-03 | 10 | 100 | Completed | Chinmay Deshpande | SS
TSK-00117 | PRJ-2024010 | UAT / Testing | UAT / Testing | 2025-01-23 | 2025-01-28 | 2025-01-26 | 5 | 100 | Completed | Ananya Joshi | FS
TSK-00118 | PRJ-2024010 | Go-Live & Handover | Go-Live & Handover | 2025-01-28 | 2025-01-31 | 2025-02-06 | 3 | 100 | Completed | Ananya Joshi | FS
TSK-00119 | PRJ-2024010 | Documentation & Closure | Documentation & Closure | 2025-01-31 | 2025-02-04 | 2025-02-16 | 4 | 100 | Completed | Deepa Nair | FS
TSK-00120 | PRJ-2024010 | Hypercare Support | Hypercare Support | 2025-02-04 | 2025-02-18 | 2025-02-26 | 14 | 100 | Completed | Manish Agarwal | FS
TSK-00121 | PRJ-2024011 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-12-16 | 2024-12-21 | 2024-12-20 | 5 | 100 | Completed | Farah Khan | FS
TSK-00122 | PRJ-2024011 | Site Survey Planning | Site Survey Planning | 2024-12-21 | 2024-12-28 | 2024-12-26 | 7 | 100 | Completed | Sandeep Rao | SS
TSK-00123 | PRJ-2024011 | BOM & Procurement | BOM & Procurement | 2024-12-28 | 2025-01-07 | 2025-01-08 | 10 | 100 | Completed | Farah Khan | FS
TSK-00124 | PRJ-2024011 | Vendor Coordination | Vendor Coordination | 2025-01-07 | 2025-01-15 | 2025-01-18 | 8 | 100 | Completed | Farah Khan | FS
TSK-00125 | PRJ-2024011 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-01-15 | 2025-01-30 | 2025-02-03 | 15 | 100 | Completed | Sandeep Rao | FS
TSK-00126 | PRJ-2024011 | Last Mile Tie-up | Last Mile Tie-up | 2025-01-30 | 2025-02-11 | 2025-02-17 | 12 | 100 | Completed | Chinmay Deshpande | FS
TSK-00127 | PRJ-2024011 | Equipment Staging | Equipment Staging | 2025-02-11 | 2025-02-17 | 2025-02-20 | 6 | 100 | Completed | Ananya Joshi | SS
TSK-00128 | PRJ-2024011 | Installation & Commissioning | Installation & Commissioning | 2025-02-17 | 2025-02-27 | 2025-03-01 | 10 | 100 | Completed | Sandeep Rao | FS
TSK-00129 | PRJ-2024011 | UAT / Testing | UAT / Testing | 2025-02-27 | 2025-03-04 | 2025-03-11 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00130 | PRJ-2024011 | Go-Live & Handover | Go-Live & Handover | 2025-03-04 | 2025-03-07 | 2025-03-18 | 3 | 100 | Completed | Chinmay Deshpande | FS
TSK-00131 | PRJ-2024011 | Documentation & Closure | Documentation & Closure | 2025-03-07 | 2025-03-11 | 2025-03-14 | 4 | 100 | Completed | Rahul K. Patil | FS
TSK-00132 | PRJ-2024011 | Hypercare Support | Hypercare Support | 2025-03-11 | 2025-03-25 | 2025-03-28 | 14 | 100 | Completed | Manish Agarwal | FS
TSK-00133 | PRJ-2024012 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-08-08 | 2024-08-13 | 2024-08-25 | 5 | 100 | Completed | Farah Khan | FS
TSK-00134 | PRJ-2024012 | Site Survey Planning | Site Survey Planning | 2024-08-13 | 2024-08-20 | 2024-08-24 | 7 | 100 | Completed | Manish Agarwal | FS
TSK-00135 | PRJ-2024012 | BOM & Procurement | BOM & Procurement | 2024-08-20 | 2024-08-30 |  | 10 | 58 | Delayed | Deepa Nair | FS
TSK-00136 | PRJ-2024012 | Vendor Coordination | Vendor Coordination | 2024-08-30 | 2024-09-07 | 2024-09-18 | 8 | 100 | Completed | Manish Agarwal | FS
TSK-00137 | PRJ-2024012 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-09-07 | 2024-09-22 | 2024-10-06 | 15 | 100 | Completed | Sandeep Rao | SS
TSK-00138 | PRJ-2024012 | Last Mile Tie-up | Last Mile Tie-up | 2024-09-22 | 2024-10-04 |  | 12 | 60 | Delayed | Sandeep Rao | SS
TSK-00139 | PRJ-2024012 | Equipment Staging | Equipment Staging | 2024-10-04 | 2024-10-10 |  | 6 | 23 | Delayed | Manish Agarwal | FS
TSK-00140 | PRJ-2024012 | Installation & Commissioning | Installation & Commissioning | 2024-10-10 | 2024-10-20 |  | 10 | 81 | In Progress | Karthik Subramanian | FS
TSK-00141 | PRJ-2024012 | UAT / Testing | UAT / Testing | 2024-10-20 | 2024-10-25 | 2024-10-30 | 5 | 100 | Completed | Ananya Joshi | FS
TSK-00142 | PRJ-2024012 | Go-Live & Handover | Go-Live & Handover | 2024-10-25 | 2024-10-28 | 2024-10-25 | 3 | 100 | Completed | Karthik Subramanian | FS
TSK-00143 | PRJ-2024012 | Documentation & Closure | Documentation & Closure | 2024-10-28 | 2024-11-01 | 2024-11-16 | 4 | 100 | Completed | Manish Agarwal | FS
TSK-00144 | PRJ-2024012 | Hypercare Support | Hypercare Support | 2024-11-01 | 2024-11-15 |  | 14 | 24 | In Progress | Manish Agarwal | FS
TSK-00145 | PRJ-2024013 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-09-22 | 2024-09-27 |  | 5 | 12 | Delayed | Karthik Subramanian | FS
TSK-00146 | PRJ-2024013 | Site Survey Planning | Site Survey Planning | 2024-09-27 | 2024-10-04 |  | 7 | 16 | Delayed | Sandeep Rao | FS
TSK-00147 | PRJ-2024013 | BOM & Procurement | BOM & Procurement | 2024-10-04 | 2024-10-14 |  | 10 | 53 | In Progress | Ananya Joshi | FS
TSK-00148 | PRJ-2024013 | Vendor Coordination | Vendor Coordination | 2024-10-14 | 2024-10-22 |  | 8 | 55 | In Progress | Rahul K. Patil | SS
TSK-00149 | PRJ-2024013 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-10-22 | 2024-11-06 |  | 15 | 59 | In Progress | Manish Agarwal | FS
TSK-00150 | PRJ-2024013 | Last Mile Tie-up | Last Mile Tie-up | 2024-11-06 | 2024-11-18 | 2024-11-23 | 12 | 100 | Completed | Sandeep Rao | SS
TSK-00151 | PRJ-2024013 | Equipment Staging | Equipment Staging | 2024-11-18 | 2024-11-24 |  | 6 | 57 | Delayed | Ananya Joshi | FS
TSK-00152 | PRJ-2024013 | Installation & Commissioning | Installation & Commissioning | 2024-11-24 | 2024-12-04 |  | 10 | 80 | In Progress | Chinmay Deshpande | FS
TSK-00153 | PRJ-2024013 | UAT / Testing | UAT / Testing | 2024-12-04 | 2024-12-09 |  | 5 | 48 | In Progress | Manish Agarwal | FS
TSK-00154 | PRJ-2024013 | Go-Live & Handover | Go-Live & Handover | 2024-12-09 | 2024-12-12 |  | 3 | 16 | Delayed | Rahul K. Patil | FS
TSK-00155 | PRJ-2024013 | Documentation & Closure | Documentation & Closure | 2024-12-12 | 2024-12-16 |  | 4 | 64 | In Progress | Deepa Nair | FS
TSK-00156 | PRJ-2024013 | Hypercare Support | Hypercare Support | 2024-12-16 | 2024-12-30 |  | 14 | 50 | Delayed | Deepa Nair | FS
TSK-00157 | PRJ-2024014 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-10-28 | 2024-11-02 | 2024-11-01 | 5 | 100 | Completed | Ananya Joshi | FS
TSK-00158 | PRJ-2024014 | Site Survey Planning | Site Survey Planning | 2024-11-02 | 2024-11-09 |  | 7 | 33 | In Progress | Ananya Joshi | FS
TSK-00159 | PRJ-2024014 | BOM & Procurement | BOM & Procurement | 2024-11-09 | 2024-11-19 | 2024-11-28 | 10 | 100 | Completed | Deepa Nair | FS
TSK-00160 | PRJ-2024014 | Vendor Coordination | Vendor Coordination | 2024-11-19 | 2024-11-27 | 2024-12-06 | 8 | 100 | Completed | Farah Khan | FS
TSK-00161 | PRJ-2024014 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-11-27 | 2024-12-12 | 2024-12-24 | 15 | 100 | Completed | Deepa Nair | FS
TSK-00162 | PRJ-2024014 | Last Mile Tie-up | Last Mile Tie-up | 2024-12-12 | 2024-12-24 | 2025-01-07 | 12 | 100 | Completed | Manish Agarwal | SS
TSK-00163 | PRJ-2024014 | Equipment Staging | Equipment Staging | 2024-12-24 | 2024-12-30 |  | 6 | 29 | Delayed | Rahul K. Patil | FS
TSK-00164 | PRJ-2024014 | Installation & Commissioning | Installation & Commissioning | 2024-12-30 | 2025-01-09 |  | 10 | 14 | Delayed | Deepa Nair | FS
TSK-00165 | PRJ-2024014 | UAT / Testing | UAT / Testing | 2025-01-09 | 2025-01-14 |  | 5 | 45 | Delayed | Chinmay Deshpande | FS
TSK-00166 | PRJ-2024014 | Go-Live & Handover | Go-Live & Handover | 2025-01-14 | 2025-01-17 |  | 3 | 58 | In Progress | Sandeep Rao | FS
TSK-00167 | PRJ-2024014 | Documentation & Closure | Documentation & Closure | 2025-01-17 | 2025-01-21 | 2025-01-22 | 4 | 100 | Completed | Ananya Joshi | FS
TSK-00168 | PRJ-2024014 | Hypercare Support | Hypercare Support | 2025-01-21 | 2025-02-04 |  | 14 | 82 | In Progress | Manish Agarwal | SS
TSK-00169 | PRJ-2024015 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-09-15 | 2024-09-20 |  | 5 | 12 | Delayed | Rahul K. Patil | SS
TSK-00170 | PRJ-2024015 | Site Survey Planning | Site Survey Planning | 2024-09-20 | 2024-09-27 | 2024-09-27 | 7 | 100 | Completed | Deepa Nair | FS
TSK-00171 | PRJ-2024015 | BOM & Procurement | BOM & Procurement | 2024-09-27 | 2024-10-07 |  | 10 | 29 | Delayed | Karthik Subramanian | SS
TSK-00172 | PRJ-2024015 | Vendor Coordination | Vendor Coordination | 2024-10-07 | 2024-10-15 | 2024-10-20 | 8 | 100 | Completed | Farah Khan | FS
TSK-00173 | PRJ-2024015 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-10-15 | 2024-10-30 |  | 15 | 53 | In Progress | Chinmay Deshpande | SS
TSK-00174 | PRJ-2024015 | Last Mile Tie-up | Last Mile Tie-up | 2024-10-30 | 2024-11-11 |  | 12 | 43 | Delayed | Manish Agarwal | SS
TSK-00175 | PRJ-2024015 | Equipment Staging | Equipment Staging | 2024-11-11 | 2024-11-17 |  | 6 | 59 | Delayed | Karthik Subramanian | FS
TSK-00176 | PRJ-2024015 | Installation & Commissioning | Installation & Commissioning | 2024-11-17 | 2024-11-27 |  | 10 | 22 | In Progress | Karthik Subramanian | FS
TSK-00177 | PRJ-2024015 | UAT / Testing | UAT / Testing | 2024-11-27 | 2024-12-02 |  | 5 | 52 | Delayed | Rahul K. Patil | FS
TSK-00178 | PRJ-2024015 | Go-Live & Handover | Go-Live & Handover | 2024-12-02 | 2024-12-05 |  | 3 | 24 | Delayed | Chinmay Deshpande | FS
TSK-00179 | PRJ-2024015 | Documentation & Closure | Documentation & Closure | 2024-12-05 | 2024-12-09 |  | 4 | 68 | In Progress | Farah Khan | FS
TSK-00180 | PRJ-2024015 | Hypercare Support | Hypercare Support | 2024-12-09 | 2024-12-23 | 2024-12-25 | 14 | 100 | Completed | Chinmay Deshpande | FS
TSK-00181 | PRJ-2024016 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-10-02 | 2024-10-07 | 2024-10-05 | 5 | 100 | Completed | Sandeep Rao | FS
TSK-00182 | PRJ-2024016 | Site Survey Planning | Site Survey Planning | 2024-10-07 | 2024-10-14 | 2024-10-24 | 7 | 100 | Completed | Karthik Subramanian | FS
TSK-00183 | PRJ-2024016 | BOM & Procurement | BOM & Procurement | 2024-10-14 | 2024-10-24 | 2024-11-01 | 10 | 100 | Completed | Manish Agarwal | FS
TSK-00184 | PRJ-2024016 | Vendor Coordination | Vendor Coordination | 2024-10-24 | 2024-11-01 | 2024-11-03 | 8 | 100 | Completed | Karthik Subramanian | FS
TSK-00185 | PRJ-2024016 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-11-01 | 2024-11-16 |  | 15 | 80 | In Progress | Rahul K. Patil | FS
TSK-00186 | PRJ-2024016 | Last Mile Tie-up | Last Mile Tie-up | 2024-11-16 | 2024-11-28 |  | 12 | 66 | In Progress | Deepa Nair | FS
TSK-00187 | PRJ-2024016 | Equipment Staging | Equipment Staging | 2024-11-28 | 2024-12-04 | 2024-12-07 | 6 | 100 | Completed | Sandeep Rao | FS
TSK-00188 | PRJ-2024016 | Installation & Commissioning | Installation & Commissioning | 2024-12-04 | 2024-12-14 | 2024-12-11 | 10 | 100 | Completed | Rahul K. Patil | SS
TSK-00189 | PRJ-2024016 | UAT / Testing | UAT / Testing | 2024-12-14 | 2024-12-19 | 2024-12-19 | 5 | 100 | Completed | Farah Khan | FS
TSK-00190 | PRJ-2024016 | Go-Live & Handover | Go-Live & Handover | 2024-12-19 | 2024-12-22 | 2024-12-24 | 3 | 100 | Completed | Manish Agarwal | SS
TSK-00191 | PRJ-2024016 | Documentation & Closure | Documentation & Closure | 2024-12-22 | 2024-12-26 |  | 4 | 37 | Delayed | Deepa Nair | FS
TSK-00192 | PRJ-2024016 | Hypercare Support | Hypercare Support | 2024-12-26 | 2025-01-09 |  | 14 | 73 | In Progress | Rahul K. Patil | SS
TSK-00193 | PRJ-2024017 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-07-24 | 2024-07-29 |  | 5 | 63 | In Progress | Farah Khan | FS
TSK-00194 | PRJ-2024017 | Site Survey Planning | Site Survey Planning | 2024-07-29 | 2024-08-05 | 2024-08-14 | 7 | 100 | Completed | Farah Khan | FS
TSK-00195 | PRJ-2024017 | BOM & Procurement | BOM & Procurement | 2024-08-05 | 2024-08-15 |  | 10 | 47 | Delayed | Karthik Subramanian | FS
TSK-00196 | PRJ-2024017 | Vendor Coordination | Vendor Coordination | 2024-08-15 | 2024-08-23 |  | 8 | 22 | Delayed | Manish Agarwal | FS
TSK-00197 | PRJ-2024017 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-08-23 | 2024-09-07 |  | 15 | 13 | Delayed | Sandeep Rao | FS
TSK-00198 | PRJ-2024017 | Last Mile Tie-up | Last Mile Tie-up | 2024-09-07 | 2024-09-19 | 2024-09-28 | 12 | 100 | Completed | Farah Khan | FS
TSK-00199 | PRJ-2024017 | Equipment Staging | Equipment Staging | 2024-09-19 | 2024-09-25 |  | 6 | 58 | Delayed | Deepa Nair | FS
TSK-00200 | PRJ-2024017 | Installation & Commissioning | Installation & Commissioning | 2024-09-25 | 2024-10-05 |  | 10 | 26 | Delayed | Deepa Nair | FS
TSK-00201 | PRJ-2024017 | UAT / Testing | UAT / Testing | 2024-10-05 | 2024-10-10 |  | 5 | 69 | In Progress | Manish Agarwal | FS
TSK-00202 | PRJ-2024017 | Go-Live & Handover | Go-Live & Handover | 2024-10-10 | 2024-10-13 |  | 3 | 50 | Delayed | Karthik Subramanian | FS
TSK-00203 | PRJ-2024017 | Documentation & Closure | Documentation & Closure | 2024-10-13 | 2024-10-17 |  | 4 | 64 | In Progress | Deepa Nair | FS
TSK-00204 | PRJ-2024017 | Hypercare Support | Hypercare Support | 2024-10-17 | 2024-10-31 |  | 14 | 25 | Delayed | Karthik Subramanian | FS
TSK-00205 | PRJ-2024018 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-08-19 | 2024-08-24 |  | 5 | 30 | Delayed | Chinmay Deshpande | FS
TSK-00206 | PRJ-2024018 | Site Survey Planning | Site Survey Planning | 2024-08-24 | 2024-08-31 | 2024-08-28 | 7 | 100 | Completed | Deepa Nair | FS
TSK-00207 | PRJ-2024018 | BOM & Procurement | BOM & Procurement | 2024-08-31 | 2024-09-10 | 2024-09-07 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00208 | PRJ-2024018 | Vendor Coordination | Vendor Coordination | 2024-09-10 | 2024-09-18 |  | 8 | 70 | In Progress | Deepa Nair | FS
TSK-00209 | PRJ-2024018 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-09-18 | 2024-10-03 |  | 15 | 53 | In Progress | Deepa Nair | FS
TSK-00210 | PRJ-2024018 | Last Mile Tie-up | Last Mile Tie-up | 2024-10-03 | 2024-10-15 | 2024-10-23 | 12 | 100 | Completed | Karthik Subramanian | FS
TSK-00211 | PRJ-2024018 | Equipment Staging | Equipment Staging | 2024-10-15 | 2024-10-21 |  | 6 | 59 | Delayed | Farah Khan | FS
TSK-00212 | PRJ-2024018 | Installation & Commissioning | Installation & Commissioning | 2024-10-21 | 2024-10-31 | 2024-11-14 | 10 | 100 | Completed | Ananya Joshi | SS
TSK-00213 | PRJ-2024018 | UAT / Testing | UAT / Testing | 2024-10-31 | 2024-11-05 |  | 5 | 71 | In Progress | Ananya Joshi | SS
TSK-00214 | PRJ-2024018 | Go-Live & Handover | Go-Live & Handover | 2024-11-05 | 2024-11-08 |  | 3 | 51 | In Progress | Manish Agarwal | FS
TSK-00215 | PRJ-2024018 | Documentation & Closure | Documentation & Closure | 2024-11-08 | 2024-11-12 | 2024-11-25 | 4 | 100 | Completed | Chinmay Deshpande | FS
TSK-00216 | PRJ-2024018 | Hypercare Support | Hypercare Support | 2024-11-12 | 2024-11-26 | 2024-11-23 | 14 | 100 | Completed | Farah Khan | FS
TSK-00217 | PRJ-2024019 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-07-01 | 2024-07-06 | 2024-07-11 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00218 | PRJ-2024019 | Site Survey Planning | Site Survey Planning | 2024-07-06 | 2024-07-13 |  | 7 | 69 | In Progress | Ananya Joshi | SS
TSK-00219 | PRJ-2024019 | BOM & Procurement | BOM & Procurement | 2024-07-13 | 2024-07-23 |  | 10 | 26 | Delayed | Chinmay Deshpande | FS
TSK-00220 | PRJ-2024019 | Vendor Coordination | Vendor Coordination | 2024-07-23 | 2024-07-31 | 2024-08-01 | 8 | 100 | Completed | Manish Agarwal | FS
TSK-00221 | PRJ-2024019 | Civil & ROW Approvals | Civil & ROW Approvals | 2024-07-31 | 2024-08-15 | 2024-08-29 | 15 | 100 | Completed | Farah Khan | FS
TSK-00222 | PRJ-2024019 | Last Mile Tie-up | Last Mile Tie-up | 2024-08-15 | 2024-08-27 | 2024-08-30 | 12 | 100 | Completed | Karthik Subramanian | FS
TSK-00223 | PRJ-2024019 | Equipment Staging | Equipment Staging | 2024-08-27 | 2024-09-02 | 2024-09-12 | 6 | 100 | Completed | Karthik Subramanian | FS
TSK-00224 | PRJ-2024019 | Installation & Commissioning | Installation & Commissioning | 2024-09-02 | 2024-09-12 |  | 10 | 35 | Delayed | Manish Agarwal | FS
TSK-00225 | PRJ-2024019 | UAT / Testing | UAT / Testing | 2024-09-12 | 2024-09-17 | 2024-09-18 | 5 | 100 | Completed | Farah Khan | SS
TSK-00226 | PRJ-2024019 | Go-Live & Handover | Go-Live & Handover | 2024-09-17 | 2024-09-20 |  | 3 | 80 | In Progress | Karthik Subramanian | SS
TSK-00227 | PRJ-2024019 | Documentation & Closure | Documentation & Closure | 2024-09-20 | 2024-09-24 |  | 4 | 26 | In Progress | Karthik Subramanian | FS
TSK-00228 | PRJ-2024019 | Hypercare Support | Hypercare Support | 2024-09-24 | 2024-10-08 | 2024-10-07 | 14 | 100 | Completed | Chinmay Deshpande | SS
TSK-00229 | PRJ-2024020 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2024-12-10 | 2024-12-15 | 2024-12-13 | 5 | 100 | Completed | Farah Khan | FS
TSK-00230 | PRJ-2024020 | Site Survey Planning | Site Survey Planning | 2024-12-15 | 2024-12-22 | 2024-12-29 | 7 | 100 | Completed | Rahul K. Patil | FS
TSK-00231 | PRJ-2024020 | BOM & Procurement | BOM & Procurement | 2024-12-22 | 2025-01-01 |  | 10 | 26 | Delayed | Farah Khan | FS
TSK-00232 | PRJ-2024020 | Vendor Coordination | Vendor Coordination | 2025-01-01 | 2025-01-09 |  | 8 | 45 | In Progress | Ananya Joshi | FS
TSK-00233 | PRJ-2024020 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-01-09 | 2025-01-24 |  | 15 | 11 | Delayed | Manish Agarwal | SS
TSK-00234 | PRJ-2024020 | Last Mile Tie-up | Last Mile Tie-up | 2025-01-24 | 2025-02-05 | 2025-02-12 | 12 | 100 | Completed | Farah Khan | FS
TSK-00235 | PRJ-2024020 | Equipment Staging | Equipment Staging | 2025-02-05 | 2025-02-11 | 2025-02-23 | 6 | 100 | Completed | Ananya Joshi | FS
TSK-00236 | PRJ-2024020 | Installation & Commissioning | Installation & Commissioning | 2025-02-11 | 2025-02-21 | 2025-03-01 | 10 | 100 | Completed | Sandeep Rao | FS
TSK-00237 | PRJ-2024020 | UAT / Testing | UAT / Testing | 2025-02-21 | 2025-02-26 | 2025-03-09 | 5 | 100 | Completed | Chinmay Deshpande | FS
TSK-00238 | PRJ-2024020 | Go-Live & Handover | Go-Live & Handover | 2025-02-26 | 2025-03-01 |  | 3 | 40 | Delayed | Deepa Nair | FS
TSK-00239 | PRJ-2024020 | Documentation & Closure | Documentation & Closure | 2025-03-01 | 2025-03-05 | 2025-03-17 | 4 | 100 | Completed | Rahul K. Patil | FS
TSK-00240 | PRJ-2024020 | Hypercare Support | Hypercare Support | 2025-03-05 | 2025-03-19 |  | 14 | 44 | Delayed | Rahul K. Patil | FS
TSK-00241 | PRJ-2024021 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-04-23 | 2025-04-28 |  | 5 | 50 | In Progress | Manish Agarwal | FS
TSK-00242 | PRJ-2024021 | Site Survey Planning | Site Survey Planning | 2025-04-28 | 2025-05-05 |  | 7 | 46 | Delayed | Rahul K. Patil | SS
TSK-00243 | PRJ-2024021 | BOM & Procurement | BOM & Procurement | 2025-05-05 | 2025-05-15 | 2025-05-20 | 10 | 100 | Completed | Deepa Nair | FS
TSK-00244 | PRJ-2024021 | Vendor Coordination | Vendor Coordination | 2025-05-15 | 2025-05-23 |  | 8 | 58 | In Progress | Rahul K. Patil | FS
TSK-00245 | PRJ-2024021 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-05-23 | 2025-06-07 |  | 15 | 25 | Delayed | Farah Khan | FS
TSK-00246 | PRJ-2024021 | Last Mile Tie-up | Last Mile Tie-up | 2025-06-07 | 2025-06-19 |  | 12 | 21 | In Progress | Deepa Nair | FS
TSK-00247 | PRJ-2024021 | Equipment Staging | Equipment Staging | 2025-06-19 | 2025-06-25 |  | 6 | 21 | In Progress | Farah Khan | FS
TSK-00248 | PRJ-2024021 | Installation & Commissioning | Installation & Commissioning | 2025-06-25 | 2025-07-05 |  | 10 | 71 | In Progress | Deepa Nair | SS
TSK-00249 | PRJ-2024021 | UAT / Testing | UAT / Testing | 2025-07-05 | 2025-07-10 | 2025-07-20 | 5 | 100 | Completed | Karthik Subramanian | SS
TSK-00250 | PRJ-2024021 | Go-Live & Handover | Go-Live & Handover | 2025-07-10 | 2025-07-13 | 2025-07-24 | 3 | 100 | Completed | Ananya Joshi | FS
TSK-00251 | PRJ-2024021 | Documentation & Closure | Documentation & Closure | 2025-07-13 | 2025-07-17 |  | 4 | 58 | In Progress | Farah Khan | FS
TSK-00252 | PRJ-2024021 | Hypercare Support | Hypercare Support | 2025-07-17 | 2025-07-31 | 2025-08-03 | 14 | 100 | Completed | Chinmay Deshpande | FS
TSK-00253 | PRJ-2024022 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-03-21 | 2025-03-26 |  | 5 | 64 | In Progress | Farah Khan | FS
TSK-00254 | PRJ-2024022 | Site Survey Planning | Site Survey Planning | 2025-03-26 | 2025-04-02 |  | 7 | 31 | Delayed | Karthik Subramanian | FS
TSK-00255 | PRJ-2024022 | BOM & Procurement | BOM & Procurement | 2025-04-02 | 2025-04-12 | 2025-04-18 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00256 | PRJ-2024022 | Vendor Coordination | Vendor Coordination | 2025-04-12 | 2025-04-20 | 2025-05-03 | 8 | 100 | Completed | Chinmay Deshpande | FS
TSK-00257 | PRJ-2024022 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-04-20 | 2025-05-05 | 2025-05-16 | 15 | 100 | Completed | Ananya Joshi | FS
TSK-00258 | PRJ-2024022 | Last Mile Tie-up | Last Mile Tie-up | 2025-05-05 | 2025-05-17 |  | 12 | 52 | In Progress | Ananya Joshi | FS
TSK-00259 | PRJ-2024022 | Equipment Staging | Equipment Staging | 2025-05-17 | 2025-05-23 | 2025-06-04 | 6 | 100 | Completed | Deepa Nair | FS
TSK-00260 | PRJ-2024022 | Installation & Commissioning | Installation & Commissioning | 2025-05-23 | 2025-06-02 |  | 10 | 54 | In Progress | Karthik Subramanian | FS
TSK-00261 | PRJ-2024022 | UAT / Testing | UAT / Testing | 2025-06-02 | 2025-06-07 |  | 5 | 45 | Delayed | Deepa Nair | FS
TSK-00262 | PRJ-2024022 | Go-Live & Handover | Go-Live & Handover | 2025-06-07 | 2025-06-10 |  | 3 | 23 | In Progress | Ananya Joshi | FS
TSK-00263 | PRJ-2024022 | Documentation & Closure | Documentation & Closure | 2025-06-10 | 2025-06-14 |  | 4 | 12 | Delayed | Farah Khan | FS
TSK-00264 | PRJ-2024022 | Hypercare Support | Hypercare Support | 2025-06-14 | 2025-06-28 | 2025-06-25 | 14 | 100 | Completed | Deepa Nair | SS
TSK-00265 | PRJ-2024023 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-06-26 | 2025-07-01 |  | 5 | 26 | In Progress | Rahul K. Patil | FS
TSK-00266 | PRJ-2024023 | Site Survey Planning | Site Survey Planning | 2025-07-01 | 2025-07-08 | 2025-07-06 | 7 | 100 | Completed | Sandeep Rao | FS
TSK-00267 | PRJ-2024023 | BOM & Procurement | BOM & Procurement | 2025-07-08 | 2025-07-18 |  | 10 | 71 | In Progress | Manish Agarwal | SS
TSK-00268 | PRJ-2024023 | Vendor Coordination | Vendor Coordination | 2025-07-18 | 2025-07-26 | 2025-07-28 | 8 | 100 | Completed | Ananya Joshi | FS
TSK-00269 | PRJ-2024023 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-07-26 | 2025-08-10 |  | 15 | 32 | Delayed | Karthik Subramanian | FS
TSK-00270 | PRJ-2024023 | Last Mile Tie-up | Last Mile Tie-up | 2025-08-10 | 2025-08-22 |  | 12 | 11 | Delayed | Farah Khan | FS
TSK-00271 | PRJ-2024023 | Equipment Staging | Equipment Staging | 2025-08-22 | 2025-08-28 |  | 6 | 65 | In Progress | Karthik Subramanian | FS
TSK-00272 | PRJ-2024023 | Installation & Commissioning | Installation & Commissioning | 2025-08-28 | 2025-09-07 |  | 10 | 21 | Delayed | Farah Khan | FS
TSK-00273 | PRJ-2024023 | UAT / Testing | UAT / Testing | 2025-09-07 | 2025-09-12 | 2025-09-12 | 5 | 100 | Completed | Sandeep Rao | FS
TSK-00274 | PRJ-2024023 | Go-Live & Handover | Go-Live & Handover | 2025-09-12 | 2025-09-15 |  | 3 | 65 | In Progress | Ananya Joshi | SS
TSK-00275 | PRJ-2024023 | Documentation & Closure | Documentation & Closure | 2025-09-15 | 2025-09-19 |  | 4 | 30 | Delayed | Chinmay Deshpande | SS
TSK-00276 | PRJ-2024023 | Hypercare Support | Hypercare Support | 2025-09-19 | 2025-10-03 | 2025-10-02 | 14 | 100 | Completed | Sandeep Rao | FS
TSK-00277 | PRJ-2024024 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-12-11 | 2025-12-16 |  | 5 | 69 | In Progress | Sandeep Rao | FS
TSK-00278 | PRJ-2024024 | Site Survey Planning | Site Survey Planning | 2025-12-16 | 2025-12-23 | 2026-01-05 | 7 | 100 | Completed | Rahul K. Patil | FS
TSK-00279 | PRJ-2024024 | BOM & Procurement | BOM & Procurement | 2025-12-23 | 2026-01-02 | 2026-01-06 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00280 | PRJ-2024024 | Vendor Coordination | Vendor Coordination | 2026-01-02 | 2026-01-10 | 2026-01-23 | 8 | 100 | Completed | Karthik Subramanian | FS
TSK-00281 | PRJ-2024024 | Civil & ROW Approvals | Civil & ROW Approvals | 2026-01-10 | 2026-01-25 | 2026-02-07 | 15 | 100 | Completed | Deepa Nair | FS
TSK-00282 | PRJ-2024024 | Last Mile Tie-up | Last Mile Tie-up | 2026-01-25 | 2026-02-06 |  | 12 | 48 | Delayed | Farah Khan | FS
TSK-00283 | PRJ-2024024 | Equipment Staging | Equipment Staging | 2026-02-06 | 2026-02-12 |  | 6 | 39 | In Progress | Karthik Subramanian | FS
TSK-00284 | PRJ-2024024 | Installation & Commissioning | Installation & Commissioning | 2026-02-12 | 2026-02-22 | 2026-03-01 | 10 | 100 | Completed | Ananya Joshi | FS
TSK-00285 | PRJ-2024024 | UAT / Testing | UAT / Testing | 2026-02-22 | 2026-02-27 | 2026-02-26 | 5 | 100 | Completed | Sandeep Rao | FS
TSK-00286 | PRJ-2024024 | Go-Live & Handover | Go-Live & Handover | 2026-02-27 | 2026-03-02 |  | 3 | 22 | Delayed | Sandeep Rao | FS
TSK-00287 | PRJ-2024024 | Documentation & Closure | Documentation & Closure | 2026-03-02 | 2026-03-06 | 2026-03-07 | 4 | 100 | Completed | Deepa Nair | FS
TSK-00288 | PRJ-2024024 | Hypercare Support | Hypercare Support | 2026-03-06 | 2026-03-20 | 2026-03-27 | 14 | 100 | Completed | Sandeep Rao | FS
TSK-00289 | PRJ-2024025 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-04-01 | 2025-04-06 | 2025-04-17 | 5 | 100 | Completed | Manish Agarwal | FS
TSK-00290 | PRJ-2024025 | Site Survey Planning | Site Survey Planning | 2025-04-06 | 2025-04-13 |  | 7 | 30 | In Progress | Deepa Nair | FS
TSK-00291 | PRJ-2024025 | BOM & Procurement | BOM & Procurement | 2025-04-13 | 2025-04-23 |  | 10 | 51 | In Progress | Chinmay Deshpande | FS
TSK-00292 | PRJ-2024025 | Vendor Coordination | Vendor Coordination | 2025-04-23 | 2025-05-01 | 2025-05-11 | 8 | 100 | Completed | Deepa Nair | FS
TSK-00293 | PRJ-2024025 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-05-01 | 2025-05-16 | 2025-05-29 | 15 | 100 | Completed | Farah Khan | FS
TSK-00294 | PRJ-2024025 | Last Mile Tie-up | Last Mile Tie-up | 2025-05-16 | 2025-05-28 |  | 12 | 63 | In Progress | Chinmay Deshpande | FS
TSK-00295 | PRJ-2024025 | Equipment Staging | Equipment Staging | 2025-05-28 | 2025-06-03 |  | 6 | 85 | In Progress | Karthik Subramanian | FS
TSK-00296 | PRJ-2024025 | Installation & Commissioning | Installation & Commissioning | 2025-06-03 | 2025-06-13 | 2025-06-20 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00297 | PRJ-2024025 | UAT / Testing | UAT / Testing | 2025-06-13 | 2025-06-18 | 2025-06-23 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00298 | PRJ-2024025 | Go-Live & Handover | Go-Live & Handover | 2025-06-18 | 2025-06-21 | 2025-06-25 | 3 | 100 | Completed | Deepa Nair | SS
TSK-00299 | PRJ-2024025 | Documentation & Closure | Documentation & Closure | 2025-06-21 | 2025-06-25 |  | 4 | 36 | Delayed | Deepa Nair | FS
TSK-00300 | PRJ-2024025 | Hypercare Support | Hypercare Support | 2025-06-25 | 2025-07-09 | 2025-07-12 | 14 | 100 | Completed | Deepa Nair | FS
TSK-00301 | PRJ-2024026 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-01-04 | 2025-01-09 |  | 5 | 29 | In Progress | Chinmay Deshpande | FS
TSK-00302 | PRJ-2024026 | Site Survey Planning | Site Survey Planning | 2025-01-09 | 2025-01-16 |  | 7 | 39 | In Progress | Farah Khan | FS
TSK-00303 | PRJ-2024026 | BOM & Procurement | BOM & Procurement | 2025-01-16 | 2025-01-26 | 2025-02-06 | 10 | 100 | Completed | Farah Khan | FS
TSK-00304 | PRJ-2024026 | Vendor Coordination | Vendor Coordination | 2025-01-26 | 2025-02-03 |  | 8 | 27 | Delayed | Deepa Nair | FS
TSK-00305 | PRJ-2024026 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-02-03 | 2025-02-18 | 2025-02-24 | 15 | 100 | Completed | Rahul K. Patil | SS
TSK-00306 | PRJ-2024026 | Last Mile Tie-up | Last Mile Tie-up | 2025-02-18 | 2025-03-02 |  | 12 | 38 | In Progress | Karthik Subramanian | FS
TSK-00307 | PRJ-2024026 | Equipment Staging | Equipment Staging | 2025-03-02 | 2025-03-08 |  | 6 | 25 | Delayed | Farah Khan | FS
TSK-00308 | PRJ-2024026 | Installation & Commissioning | Installation & Commissioning | 2025-03-08 | 2025-03-18 |  | 10 | 22 | In Progress | Farah Khan | SS
TSK-00309 | PRJ-2024026 | UAT / Testing | UAT / Testing | 2025-03-18 | 2025-03-23 | 2025-03-30 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00310 | PRJ-2024026 | Go-Live & Handover | Go-Live & Handover | 2025-03-23 | 2025-03-26 | 2025-04-01 | 3 | 100 | Completed | Manish Agarwal | FS
TSK-00311 | PRJ-2024026 | Documentation & Closure | Documentation & Closure | 2025-03-26 | 2025-03-30 | 2025-03-30 | 4 | 100 | Completed | Manish Agarwal | FS
TSK-00312 | PRJ-2024026 | Hypercare Support | Hypercare Support | 2025-03-30 | 2025-04-13 | 2025-04-28 | 14 | 100 | Completed | Deepa Nair | FS
TSK-00313 | PRJ-2024027 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-06-14 | 2025-06-19 |  | 5 | 82 | In Progress | Rahul K. Patil | SS
TSK-00314 | PRJ-2024027 | Site Survey Planning | Site Survey Planning | 2025-06-19 | 2025-06-26 | 2025-06-30 | 7 | 100 | Completed | Deepa Nair | FS
TSK-00315 | PRJ-2024027 | BOM & Procurement | BOM & Procurement | 2025-06-26 | 2025-07-06 |  | 10 | 59 | Delayed | Farah Khan | FS
TSK-00316 | PRJ-2024027 | Vendor Coordination | Vendor Coordination | 2025-07-06 | 2025-07-14 | 2025-07-11 | 8 | 100 | Completed | Manish Agarwal | FS
TSK-00317 | PRJ-2024027 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-07-14 | 2025-07-29 |  | 15 | 39 | In Progress | Farah Khan | SS
TSK-00318 | PRJ-2024027 | Last Mile Tie-up | Last Mile Tie-up | 2025-07-29 | 2025-08-10 | 2025-08-18 | 12 | 100 | Completed | Ananya Joshi | FS
TSK-00319 | PRJ-2024027 | Equipment Staging | Equipment Staging | 2025-08-10 | 2025-08-16 |  | 6 | 33 | Delayed | Rahul K. Patil | FS
TSK-00320 | PRJ-2024027 | Installation & Commissioning | Installation & Commissioning | 2025-08-16 | 2025-08-26 | 2025-08-26 | 10 | 100 | Completed | Farah Khan | FS
TSK-00321 | PRJ-2024027 | UAT / Testing | UAT / Testing | 2025-08-26 | 2025-08-31 |  | 5 | 26 | In Progress | Chinmay Deshpande | FS
TSK-00322 | PRJ-2024027 | Go-Live & Handover | Go-Live & Handover | 2025-08-31 | 2025-09-03 |  | 3 | 31 | Delayed | Ananya Joshi | FS
TSK-00323 | PRJ-2024027 | Documentation & Closure | Documentation & Closure | 2025-09-03 | 2025-09-07 | 2025-09-14 | 4 | 100 | Completed | Deepa Nair | FS
TSK-00324 | PRJ-2024027 | Hypercare Support | Hypercare Support | 2025-09-07 | 2025-09-21 |  | 14 | 17 | Delayed | Manish Agarwal | FS
TSK-00325 | PRJ-2024028 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-11-24 | 2025-11-29 |  | 5 | 52 | Delayed | Ananya Joshi | FS
TSK-00326 | PRJ-2024028 | Site Survey Planning | Site Survey Planning | 2025-11-29 | 2025-12-06 |  | 7 | 81 | In Progress | Manish Agarwal | FS
TSK-00327 | PRJ-2024028 | BOM & Procurement | BOM & Procurement | 2025-12-06 | 2025-12-16 | 2025-12-24 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00328 | PRJ-2024028 | Vendor Coordination | Vendor Coordination | 2025-12-16 | 2025-12-24 |  | 8 | 47 | Delayed | Rahul K. Patil | SS
TSK-00329 | PRJ-2024028 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-12-24 | 2026-01-08 | 2026-01-06 | 15 | 100 | Completed | Karthik Subramanian | FS
TSK-00330 | PRJ-2024028 | Last Mile Tie-up | Last Mile Tie-up | 2026-01-08 | 2026-01-20 | 2026-01-28 | 12 | 100 | Completed | Deepa Nair | FS
TSK-00331 | PRJ-2024028 | Equipment Staging | Equipment Staging | 2026-01-20 | 2026-01-26 |  | 6 | 40 | In Progress | Rahul K. Patil | FS
TSK-00332 | PRJ-2024028 | Installation & Commissioning | Installation & Commissioning | 2026-01-26 | 2026-02-05 |  | 10 | 49 | In Progress | Ananya Joshi | FS
TSK-00333 | PRJ-2024028 | UAT / Testing | UAT / Testing | 2026-02-05 | 2026-02-10 | 2026-02-08 | 5 | 100 | Completed | Ananya Joshi | FS
TSK-00334 | PRJ-2024028 | Go-Live & Handover | Go-Live & Handover | 2026-02-10 | 2026-02-13 |  | 3 | 73 | In Progress | Chinmay Deshpande | FS
TSK-00335 | PRJ-2024028 | Documentation & Closure | Documentation & Closure | 2026-02-13 | 2026-02-17 |  | 4 | 43 | Delayed | Deepa Nair | FS
TSK-00336 | PRJ-2024028 | Hypercare Support | Hypercare Support | 2026-02-17 | 2026-03-03 | 2026-03-02 | 14 | 100 | Completed | Chinmay Deshpande | FS
TSK-00337 | PRJ-2024029 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-11-03 | 2025-11-08 |  | 5 | 45 | In Progress | Rahul K. Patil | SS
TSK-00338 | PRJ-2024029 | Site Survey Planning | Site Survey Planning | 2025-11-08 | 2025-11-15 | 2025-11-18 | 7 | 100 | Completed | Sandeep Rao | SS
TSK-00339 | PRJ-2024029 | BOM & Procurement | BOM & Procurement | 2025-11-15 | 2025-11-25 | 2025-11-23 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00340 | PRJ-2024029 | Vendor Coordination | Vendor Coordination | 2025-11-25 | 2025-12-03 | 2025-12-07 | 8 | 100 | Completed | Ananya Joshi | FS
TSK-00341 | PRJ-2024029 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-12-03 | 2025-12-18 | 2025-12-30 | 15 | 100 | Completed | Chinmay Deshpande | SS
TSK-00342 | PRJ-2024029 | Last Mile Tie-up | Last Mile Tie-up | 2025-12-18 | 2025-12-30 | 2026-01-03 | 12 | 100 | Completed | Farah Khan | FS
TSK-00343 | PRJ-2024029 | Equipment Staging | Equipment Staging | 2025-12-30 | 2026-01-05 |  | 6 | 14 | Delayed | Ananya Joshi | FS
TSK-00344 | PRJ-2024029 | Installation & Commissioning | Installation & Commissioning | 2026-01-05 | 2026-01-15 | 2026-01-26 | 10 | 100 | Completed | Rahul K. Patil | FS
TSK-00345 | PRJ-2024029 | UAT / Testing | UAT / Testing | 2026-01-15 | 2026-01-20 | 2026-01-31 | 5 | 100 | Completed | Manish Agarwal | FS
TSK-00346 | PRJ-2024029 | Go-Live & Handover | Go-Live & Handover | 2026-01-20 | 2026-01-23 |  | 3 | 54 | In Progress | Sandeep Rao | FS
TSK-00347 | PRJ-2024029 | Documentation & Closure | Documentation & Closure | 2026-01-23 | 2026-01-27 |  | 4 | 58 | In Progress | Rahul K. Patil | SS
TSK-00348 | PRJ-2024029 | Hypercare Support | Hypercare Support | 2026-01-27 | 2026-02-10 | 2026-02-19 | 14 | 100 | Completed | Manish Agarwal | FS
TSK-00349 | PRJ-2024030 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-08-14 | 2025-08-19 | 2025-08-29 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00350 | PRJ-2024030 | Site Survey Planning | Site Survey Planning | 2025-08-19 | 2025-08-26 | 2025-09-06 | 7 | 100 | Completed | Ananya Joshi | FS
TSK-00351 | PRJ-2024030 | BOM & Procurement | BOM & Procurement | 2025-08-26 | 2025-09-05 |  | 10 | 83 | In Progress | Manish Agarwal | FS
TSK-00352 | PRJ-2024030 | Vendor Coordination | Vendor Coordination | 2025-09-05 | 2025-09-13 | 2025-09-20 | 8 | 100 | Completed | Rahul K. Patil | FS
TSK-00353 | PRJ-2024030 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-09-13 | 2025-09-28 |  | 15 | 76 | In Progress | Karthik Subramanian | FS
TSK-00354 | PRJ-2024030 | Last Mile Tie-up | Last Mile Tie-up | 2025-09-28 | 2025-10-10 |  | 12 | 59 | In Progress | Manish Agarwal | FS
TSK-00355 | PRJ-2024030 | Equipment Staging | Equipment Staging | 2025-10-10 | 2025-10-16 |  | 6 | 59 | In Progress | Karthik Subramanian | FS
TSK-00356 | PRJ-2024030 | Installation & Commissioning | Installation & Commissioning | 2025-10-16 | 2025-10-26 |  | 10 | 62 | In Progress | Ananya Joshi | SS
TSK-00357 | PRJ-2024030 | UAT / Testing | UAT / Testing | 2025-10-26 | 2025-10-31 | 2025-11-10 | 5 | 100 | Completed | Manish Agarwal | FS
TSK-00358 | PRJ-2024030 | Go-Live & Handover | Go-Live & Handover | 2025-10-31 | 2025-11-03 | 2025-11-08 | 3 | 100 | Completed | Chinmay Deshpande | FS
TSK-00359 | PRJ-2024030 | Documentation & Closure | Documentation & Closure | 2025-11-03 | 2025-11-07 |  | 4 | 21 | In Progress | Manish Agarwal | FS
TSK-00360 | PRJ-2024030 | Hypercare Support | Hypercare Support | 2025-11-07 | 2025-11-21 |  | 14 | 34 | Delayed | Manish Agarwal | FS
TSK-00361 | PRJ-2024031 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-09-08 | 2025-09-13 |  | 5 | 43 | Delayed | Rahul K. Patil | FS
TSK-00362 | PRJ-2024031 | Site Survey Planning | Site Survey Planning | 2025-09-13 | 2025-09-20 | 2025-10-04 | 7 | 100 | Completed | Sandeep Rao | FS
TSK-00363 | PRJ-2024031 | BOM & Procurement | BOM & Procurement | 2025-09-20 | 2025-09-30 |  | 10 | 38 | In Progress | Ananya Joshi | FS
TSK-00364 | PRJ-2024031 | Vendor Coordination | Vendor Coordination | 2025-09-30 | 2025-10-08 |  | 8 | 37 | In Progress | Karthik Subramanian | FS
TSK-00365 | PRJ-2024031 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-10-08 | 2025-10-23 | 2025-10-25 | 15 | 100 | Completed | Chinmay Deshpande | FS
TSK-00366 | PRJ-2024031 | Last Mile Tie-up | Last Mile Tie-up | 2025-10-23 | 2025-11-04 | 2025-11-16 | 12 | 100 | Completed | Karthik Subramanian | SS
TSK-00367 | PRJ-2024031 | Equipment Staging | Equipment Staging | 2025-11-04 | 2025-11-10 | 2025-11-09 | 6 | 100 | Completed | Ananya Joshi | FS
TSK-00368 | PRJ-2024031 | Installation & Commissioning | Installation & Commissioning | 2025-11-10 | 2025-11-20 | 2025-11-26 | 10 | 100 | Completed | Deepa Nair | FS
TSK-00369 | PRJ-2024031 | UAT / Testing | UAT / Testing | 2025-11-20 | 2025-11-25 | 2025-11-30 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00370 | PRJ-2024031 | Go-Live & Handover | Go-Live & Handover | 2025-11-25 | 2025-11-28 | 2025-12-05 | 3 | 100 | Completed | Farah Khan | FS
TSK-00371 | PRJ-2024031 | Documentation & Closure | Documentation & Closure | 2025-11-28 | 2025-12-02 |  | 4 | 67 | In Progress | Farah Khan | FS
TSK-00372 | PRJ-2024031 | Hypercare Support | Hypercare Support | 2025-12-02 | 2025-12-16 |  | 14 | 20 | In Progress | Chinmay Deshpande | FS
TSK-00373 | PRJ-2024032 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-08-09 | 2025-08-14 | 2025-08-15 | 5 | 100 | Completed | Manish Agarwal | FS
TSK-00374 | PRJ-2024032 | Site Survey Planning | Site Survey Planning | 2025-08-14 | 2025-08-21 | 2025-08-31 | 7 | 100 | Completed | Karthik Subramanian | FS
TSK-00375 | PRJ-2024032 | BOM & Procurement | BOM & Procurement | 2025-08-21 | 2025-08-31 |  | 10 | 26 | Delayed | Ananya Joshi | FS
TSK-00376 | PRJ-2024032 | Vendor Coordination | Vendor Coordination | 2025-08-31 | 2025-09-08 |  | 8 | 20 | Delayed | Farah Khan | SS
TSK-00377 | PRJ-2024032 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-09-08 | 2025-09-23 | 2025-09-28 | 15 | 100 | Completed | Manish Agarwal | FS
TSK-00378 | PRJ-2024032 | Last Mile Tie-up | Last Mile Tie-up | 2025-09-23 | 2025-10-05 |  | 12 | 26 | Delayed | Sandeep Rao | SS
TSK-00379 | PRJ-2024032 | Equipment Staging | Equipment Staging | 2025-10-05 | 2025-10-11 | 2025-10-10 | 6 | 100 | Completed | Manish Agarwal | FS
TSK-00380 | PRJ-2024032 | Installation & Commissioning | Installation & Commissioning | 2025-10-11 | 2025-10-21 | 2025-10-21 | 10 | 100 | Completed | Deepa Nair | SS
TSK-00381 | PRJ-2024032 | UAT / Testing | UAT / Testing | 2025-10-21 | 2025-10-26 | 2025-10-25 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00382 | PRJ-2024032 | Go-Live & Handover | Go-Live & Handover | 2025-10-26 | 2025-10-29 |  | 3 | 22 | In Progress | Deepa Nair | FS
TSK-00383 | PRJ-2024032 | Documentation & Closure | Documentation & Closure | 2025-10-29 | 2025-11-02 |  | 4 | 50 | In Progress | Ananya Joshi | FS
TSK-00384 | PRJ-2024032 | Hypercare Support | Hypercare Support | 2025-11-02 | 2025-11-16 |  | 14 | 30 | Delayed | Chinmay Deshpande | FS
TSK-00385 | PRJ-2024033 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-06-18 | 2025-06-23 |  | 5 | 44 | In Progress | Sandeep Rao | FS
TSK-00386 | PRJ-2024033 | Site Survey Planning | Site Survey Planning | 2025-06-23 | 2025-06-30 |  | 7 | 84 | In Progress | Farah Khan | FS
TSK-00387 | PRJ-2024033 | BOM & Procurement | BOM & Procurement | 2025-06-30 | 2025-07-10 | 2025-07-13 | 10 | 100 | Completed | Sandeep Rao | FS
TSK-00388 | PRJ-2024033 | Vendor Coordination | Vendor Coordination | 2025-07-10 | 2025-07-18 |  | 8 | 26 | In Progress | Karthik Subramanian | SS
TSK-00389 | PRJ-2024033 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-07-18 | 2025-08-02 | 2025-08-02 | 15 | 100 | Completed | Chinmay Deshpande | FS
TSK-00390 | PRJ-2024033 | Last Mile Tie-up | Last Mile Tie-up | 2025-08-02 | 2025-08-14 |  | 12 | 57 | Delayed | Rahul K. Patil | FS
TSK-00391 | PRJ-2024033 | Equipment Staging | Equipment Staging | 2025-08-14 | 2025-08-20 | 2025-08-18 | 6 | 100 | Completed | Deepa Nair | SS
TSK-00392 | PRJ-2024033 | Installation & Commissioning | Installation & Commissioning | 2025-08-20 | 2025-08-30 |  | 10 | 54 | In Progress | Deepa Nair | FS
TSK-00393 | PRJ-2024033 | UAT / Testing | UAT / Testing | 2025-08-30 | 2025-09-04 |  | 5 | 59 | Delayed | Karthik Subramanian | FS
TSK-00394 | PRJ-2024033 | Go-Live & Handover | Go-Live & Handover | 2025-09-04 | 2025-09-07 |  | 3 | 66 | In Progress | Chinmay Deshpande | FS
TSK-00395 | PRJ-2024033 | Documentation & Closure | Documentation & Closure | 2025-09-07 | 2025-09-11 | 2025-09-08 | 4 | 100 | Completed | Sandeep Rao | FS
TSK-00396 | PRJ-2024033 | Hypercare Support | Hypercare Support | 2025-09-11 | 2025-09-25 |  | 14 | 32 | In Progress | Rahul K. Patil | FS
TSK-00397 | PRJ-2024034 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-07-13 | 2025-07-18 | 2025-07-31 | 5 | 100 | Completed | Ananya Joshi | SS
TSK-00398 | PRJ-2024034 | Site Survey Planning | Site Survey Planning | 2025-07-18 | 2025-07-25 |  | 7 | 10 | Delayed | Farah Khan | FS
TSK-00399 | PRJ-2024034 | BOM & Procurement | BOM & Procurement | 2025-07-25 | 2025-08-04 |  | 10 | 56 | Delayed | Deepa Nair | SS
TSK-00400 | PRJ-2024034 | Vendor Coordination | Vendor Coordination | 2025-08-04 | 2025-08-12 | 2025-08-11 | 8 | 100 | Completed | Chinmay Deshpande | FS
TSK-00401 | PRJ-2024034 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-08-12 | 2025-08-27 | 2025-08-28 | 15 | 100 | Completed | Rahul K. Patil | FS
TSK-00402 | PRJ-2024034 | Last Mile Tie-up | Last Mile Tie-up | 2025-08-27 | 2025-09-08 |  | 12 | 56 | In Progress | Deepa Nair | FS
TSK-00403 | PRJ-2024034 | Equipment Staging | Equipment Staging | 2025-09-08 | 2025-09-14 | 2025-09-25 | 6 | 100 | Completed | Rahul K. Patil | FS
TSK-00404 | PRJ-2024034 | Installation & Commissioning | Installation & Commissioning | 2025-09-14 | 2025-09-24 | 2025-09-25 | 10 | 100 | Completed | Chinmay Deshpande | FS
TSK-00405 | PRJ-2024034 | UAT / Testing | UAT / Testing | 2025-09-24 | 2025-09-29 | 2025-09-30 | 5 | 100 | Completed | Farah Khan | FS
TSK-00406 | PRJ-2024034 | Go-Live & Handover | Go-Live & Handover | 2025-09-29 | 2025-10-02 |  | 3 | 42 | In Progress | Manish Agarwal | FS
TSK-00407 | PRJ-2024034 | Documentation & Closure | Documentation & Closure | 2025-10-02 | 2025-10-06 | 2025-10-04 | 4 | 100 | Completed | Sandeep Rao | FS
TSK-00408 | PRJ-2024034 | Hypercare Support | Hypercare Support | 2025-10-06 | 2025-10-20 | 2025-10-30 | 14 | 100 | Completed | Deepa Nair | FS
TSK-00409 | PRJ-2024035 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-08-01 | 2025-08-06 | 2025-08-07 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00410 | PRJ-2024035 | Site Survey Planning | Site Survey Planning | 2025-08-06 | 2025-08-13 | 2025-08-14 | 7 | 100 | Completed | Manish Agarwal | FS
TSK-00411 | PRJ-2024035 | BOM & Procurement | BOM & Procurement | 2025-08-13 | 2025-08-23 | 2025-08-21 | 10 | 100 | Completed | Ananya Joshi | FS
TSK-00412 | PRJ-2024035 | Vendor Coordination | Vendor Coordination | 2025-08-23 | 2025-08-31 |  | 8 | 57 | Delayed | Chinmay Deshpande | SS
TSK-00413 | PRJ-2024035 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-08-31 | 2025-09-15 |  | 15 | 34 | In Progress | Chinmay Deshpande | SS
TSK-00414 | PRJ-2024035 | Last Mile Tie-up | Last Mile Tie-up | 2025-09-15 | 2025-09-27 |  | 12 | 57 | Delayed | Manish Agarwal | FS
TSK-00415 | PRJ-2024035 | Equipment Staging | Equipment Staging | 2025-09-27 | 2025-10-03 | 2025-10-18 | 6 | 100 | Completed | Chinmay Deshpande | FS
TSK-00416 | PRJ-2024035 | Installation & Commissioning | Installation & Commissioning | 2025-10-03 | 2025-10-13 |  | 10 | 59 | Delayed | Rahul K. Patil | FS
TSK-00417 | PRJ-2024035 | UAT / Testing | UAT / Testing | 2025-10-13 | 2025-10-18 | 2025-10-31 | 5 | 100 | Completed | Rahul K. Patil | FS
TSK-00418 | PRJ-2024035 | Go-Live & Handover | Go-Live & Handover | 2025-10-18 | 2025-10-21 | 2025-10-24 | 3 | 100 | Completed | Sandeep Rao | FS
TSK-00419 | PRJ-2024035 | Documentation & Closure | Documentation & Closure | 2025-10-21 | 2025-10-25 | 2025-10-28 | 4 | 100 | Completed | Ananya Joshi | FS
TSK-00420 | PRJ-2024035 | Hypercare Support | Hypercare Support | 2025-10-25 | 2025-11-08 |  | 14 | 11 | Delayed | Deepa Nair | FS
TSK-00421 | PRJ-2024036 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-03-02 | 2025-03-07 | 2025-03-22 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00422 | PRJ-2024036 | Site Survey Planning | Site Survey Planning | 2025-03-07 | 2025-03-14 |  | 7 | 36 | Delayed | Deepa Nair | FS
TSK-00423 | PRJ-2024036 | BOM & Procurement | BOM & Procurement | 2025-03-14 | 2025-03-24 | 2025-04-04 | 10 | 100 | Completed | Karthik Subramanian | SS
TSK-00424 | PRJ-2024036 | Vendor Coordination | Vendor Coordination | 2025-03-24 | 2025-04-01 |  | 8 | 55 | Delayed | Ananya Joshi | SS
TSK-00425 | PRJ-2024036 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-04-01 | 2025-04-16 | 2025-04-25 | 15 | 100 | Completed | Karthik Subramanian | FS
TSK-00426 | PRJ-2024036 | Last Mile Tie-up | Last Mile Tie-up | 2025-04-16 | 2025-04-28 |  | 12 | 62 | In Progress | Deepa Nair | FS
TSK-00427 | PRJ-2024036 | Equipment Staging | Equipment Staging | 2025-04-28 | 2025-05-04 |  | 6 | 38 | In Progress | Chinmay Deshpande | FS
TSK-00428 | PRJ-2024036 | Installation & Commissioning | Installation & Commissioning | 2025-05-04 | 2025-05-14 |  | 10 | 51 | Delayed | Rahul K. Patil | FS
TSK-00429 | PRJ-2024036 | UAT / Testing | UAT / Testing | 2025-05-14 | 2025-05-19 | 2025-06-01 | 5 | 100 | Completed | Chinmay Deshpande | FS
TSK-00430 | PRJ-2024036 | Go-Live & Handover | Go-Live & Handover | 2025-05-19 | 2025-05-22 | 2025-05-26 | 3 | 100 | Completed | Ananya Joshi | FS
TSK-00431 | PRJ-2024036 | Documentation & Closure | Documentation & Closure | 2025-05-22 | 2025-05-26 |  | 4 | 51 | In Progress | Ananya Joshi | FS
TSK-00432 | PRJ-2024036 | Hypercare Support | Hypercare Support | 2025-05-26 | 2025-06-09 | 2025-06-13 | 14 | 100 | Completed | Chinmay Deshpande | FS
TSK-00433 | PRJ-2024037 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-01-12 | 2025-01-17 |  | 5 | 67 | In Progress | Karthik Subramanian | SS
TSK-00434 | PRJ-2024037 | Site Survey Planning | Site Survey Planning | 2025-01-17 | 2025-01-24 |  | 7 | 26 | In Progress | Chinmay Deshpande | FS
TSK-00435 | PRJ-2024037 | BOM & Procurement | BOM & Procurement | 2025-01-24 | 2025-02-03 |  | 10 | 56 | In Progress | Rahul K. Patil | FS
TSK-00436 | PRJ-2024037 | Vendor Coordination | Vendor Coordination | 2025-02-03 | 2025-02-11 |  | 8 | 24 | Delayed | Farah Khan | FS
TSK-00437 | PRJ-2024037 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-02-11 | 2025-02-26 | 2025-02-27 | 15 | 100 | Completed | Rahul K. Patil | FS
TSK-00438 | PRJ-2024037 | Last Mile Tie-up | Last Mile Tie-up | 2025-02-26 | 2025-03-10 | 2025-03-15 | 12 | 100 | Completed | Farah Khan | SS
TSK-00439 | PRJ-2024037 | Equipment Staging | Equipment Staging | 2025-03-10 | 2025-03-16 |  | 6 | 31 | Delayed | Sandeep Rao | FS
TSK-00440 | PRJ-2024037 | Installation & Commissioning | Installation & Commissioning | 2025-03-16 | 2025-03-26 |  | 10 | 48 | In Progress | Ananya Joshi | FS
TSK-00441 | PRJ-2024037 | UAT / Testing | UAT / Testing | 2025-03-26 | 2025-03-31 |  | 5 | 80 | In Progress | Rahul K. Patil | FS
TSK-00442 | PRJ-2024037 | Go-Live & Handover | Go-Live & Handover | 2025-03-31 | 2025-04-03 |  | 3 | 44 | Delayed | Deepa Nair | FS
TSK-00443 | PRJ-2024037 | Documentation & Closure | Documentation & Closure | 2025-04-03 | 2025-04-07 | 2025-04-16 | 4 | 100 | Completed | Farah Khan | FS
TSK-00444 | PRJ-2024037 | Hypercare Support | Hypercare Support | 2025-04-07 | 2025-04-21 | 2025-04-21 | 14 | 100 | Completed | Farah Khan | FS
TSK-00445 | PRJ-2024038 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-08-23 | 2025-08-28 | 2025-09-12 | 5 | 100 | Completed | Ananya Joshi | SS
TSK-00446 | PRJ-2024038 | Site Survey Planning | Site Survey Planning | 2025-08-28 | 2025-09-04 |  | 7 | 27 | In Progress | Deepa Nair | FS
TSK-00447 | PRJ-2024038 | BOM & Procurement | BOM & Procurement | 2025-09-04 | 2025-09-14 |  | 10 | 47 | Delayed | Rahul K. Patil | FS
TSK-00448 | PRJ-2024038 | Vendor Coordination | Vendor Coordination | 2025-09-14 | 2025-09-22 |  | 8 | 44 | In Progress | Ananya Joshi | FS
TSK-00449 | PRJ-2024038 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-09-22 | 2025-10-07 | 2025-10-22 | 15 | 100 | Completed | Ananya Joshi | FS
TSK-00450 | PRJ-2024038 | Last Mile Tie-up | Last Mile Tie-up | 2025-10-07 | 2025-10-19 | 2025-10-31 | 12 | 100 | Completed | Chinmay Deshpande | FS
TSK-00451 | PRJ-2024038 | Equipment Staging | Equipment Staging | 2025-10-19 | 2025-10-25 |  | 6 | 52 | In Progress | Karthik Subramanian | SS
TSK-00452 | PRJ-2024038 | Installation & Commissioning | Installation & Commissioning | 2025-10-25 | 2025-11-04 | 2025-11-10 | 10 | 100 | Completed | Deepa Nair | FS
TSK-00453 | PRJ-2024038 | UAT / Testing | UAT / Testing | 2025-11-04 | 2025-11-09 |  | 5 | 31 | Delayed | Ananya Joshi | FS
TSK-00454 | PRJ-2024038 | Go-Live & Handover | Go-Live & Handover | 2025-11-09 | 2025-11-12 | 2025-11-09 | 3 | 100 | Completed | Farah Khan | FS
TSK-00455 | PRJ-2024038 | Documentation & Closure | Documentation & Closure | 2025-11-12 | 2025-11-16 |  | 4 | 33 | Delayed | Chinmay Deshpande | FS
TSK-00456 | PRJ-2024038 | Hypercare Support | Hypercare Support | 2025-11-16 | 2025-11-30 | 2025-11-27 | 14 | 100 | Completed | Farah Khan | FS
TSK-00457 | PRJ-2024039 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-07-23 | 2025-07-28 |  | 5 | 0 | Not Started | Deepa Nair | FS
TSK-00458 | PRJ-2024039 | Site Survey Planning | Site Survey Planning | 2025-07-28 | 2025-08-04 |  | 7 | 0 | Not Started | Sandeep Rao | FS
TSK-00459 | PRJ-2024039 | BOM & Procurement | BOM & Procurement | 2025-08-04 | 2025-08-14 |  | 10 | 0 | Not Started | Sandeep Rao | FS
TSK-00460 | PRJ-2024039 | Vendor Coordination | Vendor Coordination | 2025-08-14 | 2025-08-22 |  | 8 | 0 | Not Started | Sandeep Rao | FS
TSK-00461 | PRJ-2024039 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-08-22 | 2025-09-06 |  | 15 | 0 | Not Started | Manish Agarwal | FS
TSK-00462 | PRJ-2024039 | Last Mile Tie-up | Last Mile Tie-up | 2025-09-06 | 2025-09-18 |  | 12 | 0 | Not Started | Rahul K. Patil | SS
TSK-00463 | PRJ-2024039 | Equipment Staging | Equipment Staging | 2025-09-18 | 2025-09-24 |  | 6 | 0 | Not Started | Manish Agarwal | FS
TSK-00464 | PRJ-2024039 | Installation & Commissioning | Installation & Commissioning | 2025-09-24 | 2025-10-04 |  | 10 | 0 | Not Started | Chinmay Deshpande | FS
TSK-00465 | PRJ-2024039 | UAT / Testing | UAT / Testing | 2025-10-04 | 2025-10-09 |  | 5 | 0 | Not Started | Chinmay Deshpande | FS
TSK-00466 | PRJ-2024039 | Go-Live & Handover | Go-Live & Handover | 2025-10-09 | 2025-10-12 |  | 3 | 0 | Not Started | Ananya Joshi | FS
TSK-00467 | PRJ-2024039 | Documentation & Closure | Documentation & Closure | 2025-10-12 | 2025-10-16 |  | 4 | 0 | Not Started | Chinmay Deshpande | FS
TSK-00468 | PRJ-2024039 | Hypercare Support | Hypercare Support | 2025-10-16 | 2025-10-30 |  | 14 | 0 | Not Started | Rahul K. Patil | FS
TSK-00469 | PRJ-2024040 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-01-28 | 2025-02-02 |  | 5 | 0 | Not Started | Chinmay Deshpande | FS
TSK-00470 | PRJ-2024040 | Site Survey Planning | Site Survey Planning | 2025-02-02 | 2025-02-09 |  | 7 | 0 | Not Started | Rahul K. Patil | FS
TSK-00471 | PRJ-2024040 | BOM & Procurement | BOM & Procurement | 2025-02-09 | 2025-02-19 |  | 10 | 0 | Not Started | Chinmay Deshpande | SS
TSK-00472 | PRJ-2024040 | Vendor Coordination | Vendor Coordination | 2025-02-19 | 2025-02-27 |  | 8 | 0 | Not Started | Ananya Joshi | FS
TSK-00473 | PRJ-2024040 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-02-27 | 2025-03-14 |  | 15 | 0 | Not Started | Farah Khan | FS
TSK-00474 | PRJ-2024040 | Last Mile Tie-up | Last Mile Tie-up | 2025-03-14 | 2025-03-26 |  | 12 | 0 | Not Started | Sandeep Rao | FS
TSK-00475 | PRJ-2024040 | Equipment Staging | Equipment Staging | 2025-03-26 | 2025-04-01 |  | 6 | 0 | Not Started | Deepa Nair | FS
TSK-00476 | PRJ-2024040 | Installation & Commissioning | Installation & Commissioning | 2025-04-01 | 2025-04-11 |  | 10 | 0 | Not Started | Farah Khan | FS
TSK-00477 | PRJ-2024040 | UAT / Testing | UAT / Testing | 2025-04-11 | 2025-04-16 |  | 5 | 0 | Not Started | Farah Khan | FS
TSK-00478 | PRJ-2024040 | Go-Live & Handover | Go-Live & Handover | 2025-04-16 | 2025-04-19 |  | 3 | 0 | Not Started | Chinmay Deshpande | SS
TSK-00479 | PRJ-2024040 | Documentation & Closure | Documentation & Closure | 2025-04-19 | 2025-04-23 |  | 4 | 0 | Not Started | Farah Khan | SS
TSK-00480 | PRJ-2024040 | Hypercare Support | Hypercare Support | 2025-04-23 | 2025-05-07 |  | 14 | 0 | Not Started | Manish Agarwal | FS
TSK-00481 | PRJ-2024041 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-08-14 | 2025-08-19 |  | 5 | 0 | Not Started | Rahul K. Patil | SS
TSK-00482 | PRJ-2024041 | Site Survey Planning | Site Survey Planning | 2025-08-19 | 2025-08-26 |  | 7 | 0 | Not Started | Deepa Nair | FS
TSK-00483 | PRJ-2024041 | BOM & Procurement | BOM & Procurement | 2025-08-26 | 2025-09-05 |  | 10 | 0 | Not Started | Manish Agarwal | FS
TSK-00484 | PRJ-2024041 | Vendor Coordination | Vendor Coordination | 2025-09-05 | 2025-09-13 |  | 8 | 0 | Not Started | Chinmay Deshpande | FS
TSK-00485 | PRJ-2024041 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-09-13 | 2025-09-28 |  | 15 | 0 | Not Started | Farah Khan | FS
TSK-00486 | PRJ-2024041 | Last Mile Tie-up | Last Mile Tie-up | 2025-09-28 | 2025-10-10 |  | 12 | 0 | Not Started | Deepa Nair | FS
TSK-00487 | PRJ-2024041 | Equipment Staging | Equipment Staging | 2025-10-10 | 2025-10-16 |  | 6 | 0 | Not Started | Deepa Nair | FS
TSK-00488 | PRJ-2024041 | Installation & Commissioning | Installation & Commissioning | 2025-10-16 | 2025-10-26 |  | 10 | 0 | Not Started | Rahul K. Patil | FS
TSK-00489 | PRJ-2024041 | UAT / Testing | UAT / Testing | 2025-10-26 | 2025-10-31 |  | 5 | 0 | Not Started | Sandeep Rao | SS
TSK-00490 | PRJ-2024041 | Go-Live & Handover | Go-Live & Handover | 2025-10-31 | 2025-11-03 |  | 3 | 0 | Not Started | Deepa Nair | FS
TSK-00491 | PRJ-2024041 | Documentation & Closure | Documentation & Closure | 2025-11-03 | 2025-11-07 |  | 4 | 0 | Not Started | Rahul K. Patil | FS
TSK-00492 | PRJ-2024041 | Hypercare Support | Hypercare Support | 2025-11-07 | 2025-11-21 |  | 14 | 0 | Not Started | Deepa Nair | FS
TSK-00493 | PRJ-2024042 | Kickoff & Requirement Gathering | Kickoff & Requirement Gathering | 2025-06-01 | 2025-06-06 | 2025-06-17 | 5 | 100 | Completed | Karthik Subramanian | FS
TSK-00494 | PRJ-2024042 | Site Survey Planning | Site Survey Planning | 2025-06-06 | 2025-06-13 | 2025-06-15 | 7 | 100 | Completed | Deepa Nair | SS
TSK-00495 | PRJ-2024042 | BOM & Procurement | BOM & Procurement | 2025-06-13 | 2025-06-23 | 2025-07-05 | 10 | 100 | Completed | Deepa Nair | SS
TSK-00496 | PRJ-2024042 | Vendor Coordination | Vendor Coordination | 2025-06-23 | 2025-07-01 | 2025-07-12 | 8 | 100 | Completed | Karthik Subramanian | FS
TSK-00497 | PRJ-2024042 | Civil & ROW Approvals | Civil & ROW Approvals | 2025-07-01 | 2025-07-16 | 2025-07-26 | 15 | 100 | Completed | Farah Khan | SS
TSK-00498 | PRJ-2024042 | Last Mile Tie-up | Last Mile Tie-up | 2025-07-16 | 2025-07-28 | 2025-07-28 | 12 | 100 | Completed | Sandeep Rao | FS
TSK-00499 | PRJ-2024042 | Equipment Staging | Equipment Staging | 2025-07-28 | 2025-08-03 | 2025-08-15 | 6 | 100 | Completed | Farah Khan | FS
TSK-00500 | PRJ-2024042 | Installation & Commissioning | Installation & Commissioning | 2025-08-03 | 2025-08-13 | 2025-08-24 | 10 | 100 | Completed | Karthik Subramanian | FS
TSK-00501 | PRJ-2024042 | UAT / Testing | UAT / Testing | 2025-08-13 | 2025-08-18 | 2025-08-22 | 5 | 100 | Completed | Deepa Nair | FS
TSK-00502 | PRJ-2024042 | Go-Live & Handover | Go-Live & Handover | 2025-08-18 | 2025-08-21 | 2025-08-28 | 3 | 100 | Completed | Karthik Subramanian | FS
TSK-00503 | PRJ-2024042 | Documentation & Closure | Documentation & Closure | 2025-08-21 | 2025-08-25 | 2025-08-29 | 4 | 100 | Completed | Deepa Nair | FS
TSK-00504 | PRJ-2024042 | Hypercare Support | Hypercare Support | 2025-08-25 | 2025-09-08 | 2025-09-20 | 14 | 100 | Completed | Rahul K. Patil | SS

## RAID_Log
RAIDID | ProjectID | Type | Category | Description | Severity | Probability | RaisedDate | Owner | Status | ClosedDate | MitigationPlan | ImpactOnSchedule_Days | ImpactOnCost_INR
RAID-0001 | PRJ-2024026 | Risk | Technical | Risk related to financial impacting client acceptance | High | Medium | 2025-01-13 | Manish Agarwal | Escalated |  | Weekly governance call instituted with client IT team | 3 | 38981
RAID-0002 | PRJ-2024005 | Risk | Regulatory/ROW | Risk related to client-side readiness impacting milestone timeline | Critical | High | 2025-03-29 | Deepa Nair | Closed | 2025-04-16 | Escalated to vendor account manager for expedited resolution | 6 | 164394
RAID-0003 | PRJ-2024004 | Risk | Technical | Risk related to resource impacting client acceptance | High | Low | 2025-03-11 | Sandeep Rao | Escalated |  | Additional field engineer deployed to region | 11 | 60854
RAID-0004 | PRJ-2024008 | Risk | Technical | Risk related to vendor/logistics impacting vendor SLA | High | Low | 2025-01-26 | Farah Khan | Closed | 2025-02-14 | Additional field engineer deployed to region | 16 | 32477
RAID-0005 | PRJ-2024029 | Risk | Resource | Risk related to financial impacting vendor SLA | High | High | 2026-03-25 | Farah Khan | Closed | 2026-04-11 | Weekly governance call instituted with client IT team | 5 | 209883
RAID-0006 | PRJ-2024031 | Risk | Financial | Risk related to client-side readiness impacting client acceptance | Low | Medium | 2026-02-03 | Chinmay Deshpande | Closed | 2026-02-21 | Weekly governance call instituted with client IT team | 20 | 72588
RAID-0007 | PRJ-2024031 | Issue | Resource | Issue related to resource impacting client acceptance | Critical |  | 2025-12-29 | Farah Khan | Closed | 2026-01-31 | Weekly governance call instituted with client IT team | 2 | 120240
RAID-0008 | PRJ-2024039 | Risk | Vendor/Logistics | Risk related to resource impacting vendor SLA | Medium | High | 2025-08-10 | Deepa Nair | Open |  | Weekly governance call instituted with client IT team | 29 | 182365
RAID-0009 | PRJ-2024026 | Risk | Technical | Risk related to schedule impacting milestone timeline | Medium | Medium | 2025-06-29 | Sandeep Rao | Closed | 2025-07-05 | Weekly governance call instituted with client IT team | 8 | 135153
RAID-0010 | PRJ-2024019 | Risk | Client-Side Readiness | Risk related to financial impacting vendor SLA | Medium | Medium | 2024-08-18 | Sandeep Rao | Closed | 2024-09-29 | Buffer added to schedule; client stakeholder aligned | 6 | 52289
RAID-0011 | PRJ-2024036 | Issue | Technical | Issue related to schedule impacting vendor SLA | Low |  | 2025-06-14 | Deepa Nair | Closed | 2025-06-18 | Additional field engineer deployed to region | 18 | 198971
RAID-0012 | PRJ-2024009 | Risk | Resource | Risk related to schedule impacting site rollout | Medium | High | 2025-03-01 | Rahul K. Patil | Open |  | Buffer added to schedule; client stakeholder aligned | 4 | 224947
RAID-0013 | PRJ-2024027 | Issue | Regulatory/ROW | Issue related to vendor/logistics impacting vendor SLA | Medium |  | 2025-12-22 | Karthik Subramanian | Escalated |  | Alternate last-mile provider engaged as backup | 3 | 241388
RAID-0014 | PRJ-2024010 | Assumption | Regulatory/ROW | Assumption related to regulatory/row impacting client acceptance | Critical |  | 2024-12-08 | Rahul K. Patil | Open |  | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0015 | PRJ-2024020 | Issue | Client-Side Readiness | Issue related to resource impacting milestone timeline | Medium |  | 2025-05-19 | Karthik Subramanian | Escalated |  | Escalated to vendor account manager for expedited resolution | 3 | 23370
RAID-0016 | PRJ-2024040 | Risk | Resource | Risk related to client-side readiness impacting vendor SLA | High | Medium | 2025-06-04 | Chinmay Deshpande | Closed | 2025-07-18 | Escalated to vendor account manager for expedited resolution | 27 | 219444
RAID-0017 | PRJ-2024038 | Risk | Resource | Risk related to schedule impacting vendor SLA | High | Medium | 2026-02-14 | Karthik Subramanian | Closed | 2026-03-15 | Alternate last-mile provider engaged as backup | 0 | 239083
RAID-0018 | PRJ-2024004 | Risk | Financial | Risk related to resource impacting client acceptance | Medium | Low | 2024-09-28 | Sandeep Rao | Open |  | Alternate last-mile provider engaged as backup | 18 | 74577
RAID-0019 | PRJ-2024029 | Risk | Financial | Risk related to resource impacting milestone timeline | High | Medium | 2025-11-24 | Manish Agarwal | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 29 | 249477
RAID-0020 | PRJ-2024022 | Dependency | Client-Side Readiness | Dependency related to financial impacting site rollout | Medium |  | 2025-06-16 | Chinmay Deshpande | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0021 | PRJ-2024042 | Issue | Technical | Issue related to client-side readiness impacting vendor SLA | Critical |  | 2025-08-03 | Rahul K. Patil | In Mitigation |  | Alternate last-mile provider engaged as backup | 10 | 34986
RAID-0022 | PRJ-2024032 | Risk | Financial | Risk related to vendor/logistics impacting site rollout | Critical | High | 2026-01-17 | Sandeep Rao | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 15 | 88592
RAID-0023 | PRJ-2024017 | Risk | Client-Side Readiness | Risk related to resource impacting site rollout | Medium | Low | 2024-10-30 | Deepa Nair | Closed | 2024-11-19 | Escalated to vendor account manager for expedited resolution | 6 | 57234
RAID-0024 | PRJ-2024017 | Issue | Vendor/Logistics | Issue related to regulatory/row impacting vendor SLA | Critical |  | 2024-11-12 | Rahul K. Patil | Closed | 2024-12-06 | Additional field engineer deployed to region | 22 | 198971
RAID-0025 | PRJ-2024015 | Dependency | Financial | Dependency related to resource impacting client acceptance | Critical |  | 2025-02-03 | Sandeep Rao | Closed | 2025-03-14 | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0026 | PRJ-2024017 | Issue | Regulatory/ROW | Issue related to vendor/logistics impacting milestone timeline | Medium |  | 2024-09-07 | Rahul K. Patil | Escalated |  | Escalated to vendor account manager for expedited resolution | 20 | 179719
RAID-0027 | PRJ-2024009 | Risk | Regulatory/ROW | Risk related to technical impacting vendor SLA | Medium | High | 2024-10-26 | Karthik Subramanian | Closed | 2024-10-29 | Escalated to vendor account manager for expedited resolution | 6 | 213796
RAID-0028 | PRJ-2024012 | Issue | Regulatory/ROW | Issue related to regulatory/row impacting milestone timeline | Low |  | 2024-11-08 | Rahul K. Patil | In Mitigation |  | Alternate last-mile provider engaged as backup | 13 | 84265
RAID-0029 | PRJ-2024010 | Risk | Technical | Risk related to client-side readiness impacting vendor SLA | Critical | High | 2024-12-11 | Sandeep Rao | Open |  | Weekly governance call instituted with client IT team | 28 | 132668
RAID-0030 | PRJ-2024009 | Issue | Client-Side Readiness | Issue related to resource impacting vendor SLA | Low |  | 2025-02-10 | Rahul K. Patil | Closed | 2025-03-19 | Alternate last-mile provider engaged as backup | 14 | 48920
RAID-0031 | PRJ-2024013 | Assumption | Client-Side Readiness | Assumption related to financial impacting vendor SLA | Low |  | 2025-02-22 | Rahul K. Patil | Closed | 2025-03-23 | Buffer added to schedule; client stakeholder aligned | 0 | 0
RAID-0032 | PRJ-2024015 | Assumption | Resource | Assumption related to vendor/logistics impacting milestone timeline | Critical |  | 2025-03-11 | Rahul K. Patil | Escalated |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0033 | PRJ-2024034 | Dependency | Vendor/Logistics | Dependency related to vendor/logistics impacting site rollout | Medium |  | 2025-08-07 | Deepa Nair | Closed | 2025-09-04 | Weekly governance call instituted with client IT team | 0 | 0
RAID-0034 | PRJ-2024013 | Issue | Financial | Issue related to technical impacting milestone timeline | Medium |  | 2024-11-21 | Sandeep Rao | Closed | 2024-12-10 | Additional field engineer deployed to region | 5 | 247115
RAID-0035 | PRJ-2024013 | Risk | Technical | Risk related to vendor/logistics impacting vendor SLA | High | High | 2024-10-12 | Karthik Subramanian | Open |  | Alternate last-mile provider engaged as backup | 17 | 111125
RAID-0036 | PRJ-2024032 | Risk | Client-Side Readiness | Risk related to technical impacting vendor SLA | Low | High | 2025-08-19 | Ananya Joshi | Escalated |  | Weekly governance call instituted with client IT team | 24 | 140315
RAID-0037 | PRJ-2024028 | Issue | Financial | Issue related to client-side readiness impacting client acceptance | Low |  | 2026-05-23 | Karthik Subramanian | Open |  | Weekly governance call instituted with client IT team | 22 | 229772
RAID-0038 | PRJ-2024007 | Dependency | Technical | Dependency related to technical impacting client acceptance | High |  | 2025-04-25 | Deepa Nair | Closed | 2025-05-09 | Buffer added to schedule; client stakeholder aligned | 0 | 0
RAID-0039 | PRJ-2024023 | Dependency | Financial | Dependency related to technical impacting vendor SLA | High |  | 2025-07-09 | Rahul K. Patil | Closed | 2025-07-13 | Weekly governance call instituted with client IT team | 0 | 0
RAID-0040 | PRJ-2024022 | Issue | Resource | Issue related to schedule impacting client acceptance | High |  | 2025-07-25 | Sandeep Rao | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 5 | 113314
RAID-0041 | PRJ-2024005 | Risk | Regulatory/ROW | Risk related to vendor/logistics impacting client acceptance | High | Medium | 2024-12-10 | Ananya Joshi | Closed | 2025-01-19 | Weekly governance call instituted with client IT team | 10 | 183321
RAID-0042 | PRJ-2024011 | Risk | Schedule | Risk related to regulatory/row impacting milestone timeline | High | Medium | 2025-05-07 | Ananya Joshi | Escalated |  | Alternate last-mile provider engaged as backup | 24 | 218680
RAID-0043 | PRJ-2024037 | Issue | Client-Side Readiness | Issue related to financial impacting site rollout | Critical |  | 2025-06-27 | Karthik Subramanian | Closed | 2025-07-11 | Alternate last-mile provider engaged as backup | 11 | 236922
RAID-0044 | PRJ-2024005 | Dependency | Regulatory/ROW | Dependency related to regulatory/row impacting vendor SLA | Critical |  | 2025-06-09 | Ananya Joshi | Open |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0045 | PRJ-2024027 | Issue | Financial | Issue related to technical impacting milestone timeline | High |  | 2025-12-05 | Deepa Nair | Open |  | Buffer added to schedule; client stakeholder aligned | 22 | 122573
RAID-0046 | PRJ-2024040 | Issue | Schedule | Issue related to financial impacting site rollout | Low |  | 2025-04-26 | Farah Khan | Closed | 2025-05-29 | Buffer added to schedule; client stakeholder aligned | 0 | 189586
RAID-0047 | PRJ-2024020 | Issue | Financial | Issue related to regulatory/row impacting client acceptance | Medium |  | 2025-06-26 | Ananya Joshi | In Mitigation |  | Additional field engineer deployed to region | 12 | 132269
RAID-0048 | PRJ-2024042 | Risk | Vendor/Logistics | Risk related to regulatory/row impacting site rollout | Critical | Medium | 2025-09-15 | Deepa Nair | Closed | 2025-09-22 | Weekly governance call instituted with client IT team | 24 | 215798
RAID-0049 | PRJ-2024016 | Risk | Financial | Risk related to vendor/logistics impacting milestone timeline | Medium | Medium | 2024-12-12 | Deepa Nair | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 6 | 214206
RAID-0050 | PRJ-2024023 | Dependency | Regulatory/ROW | Dependency related to technical impacting vendor SLA | Medium |  | 2025-08-13 | Karthik Subramanian | Open |  | Weekly governance call instituted with client IT team | 0 | 0
RAID-0051 | PRJ-2024036 | Risk | Financial | Risk related to financial impacting site rollout | Critical | High | 2025-08-17 | Manish Agarwal | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 10 | 28116
RAID-0052 | PRJ-2024001 | Issue | Financial | Issue related to regulatory/row impacting site rollout | Medium |  | 2024-11-25 | Deepa Nair | Closed | 2024-11-29 | Buffer added to schedule; client stakeholder aligned | 2 | 128774
RAID-0053 | PRJ-2024042 | Risk | Vendor/Logistics | Risk related to client-side readiness impacting client acceptance | Medium | Low | 2025-07-07 | Farah Khan | Closed | 2025-07-12 | Alternate last-mile provider engaged as backup | 28 | 216546
RAID-0054 | PRJ-2024011 | Issue | Vendor/Logistics | Issue related to regulatory/row impacting site rollout | Critical |  | 2025-02-09 | Farah Khan | Open |  | Weekly governance call instituted with client IT team | 26 | 163076
RAID-0055 | PRJ-2024016 | Issue | Schedule | Issue related to resource impacting client acceptance | Medium |  | 2025-02-24 | Deepa Nair | Open |  | Escalated to vendor account manager for expedited resolution | 2 | 236757
RAID-0056 | PRJ-2024011 | Risk | Vendor/Logistics | Risk related to schedule impacting client acceptance | Low | High | 2025-06-25 | Rahul K. Patil | Closed | 2025-07-03 | Buffer added to schedule; client stakeholder aligned | 19 | 220531
RAID-0057 | PRJ-2024030 | Assumption | Technical | Assumption related to regulatory/row impacting client acceptance | Critical |  | 2025-10-14 | Sandeep Rao | Open |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0058 | PRJ-2024022 | Dependency | Financial | Dependency related to schedule impacting site rollout | Medium |  | 2025-09-24 | Chinmay Deshpande | Open |  | Weekly governance call instituted with client IT team | 0 | 0
RAID-0059 | PRJ-2024027 | Risk | Resource | Risk related to regulatory/row impacting vendor SLA | Low | Low | 2025-06-18 | Rahul K. Patil | Closed | 2025-06-23 | Escalated to vendor account manager for expedited resolution | 4 | 17752
RAID-0060 | PRJ-2024025 | Issue | Technical | Issue related to regulatory/row impacting site rollout | Medium |  | 2025-06-17 | Farah Khan | Closed | 2025-06-22 | Alternate last-mile provider engaged as backup | 16 | 68626
RAID-0061 | PRJ-2024015 | Assumption | Regulatory/ROW | Assumption related to client-side readiness impacting milestone timeline | Low |  | 2024-10-01 | Sandeep Rao | Closed | 2024-10-08 | Buffer added to schedule; client stakeholder aligned | 0 | 0
RAID-0062 | PRJ-2024028 | Issue | Vendor/Logistics | Issue related to financial impacting milestone timeline | Critical |  | 2026-04-19 | Chinmay Deshpande | Closed | 2026-05-09 | Alternate last-mile provider engaged as backup | 20 | 81628
RAID-0063 | PRJ-2024006 | Issue | Resource | Issue related to resource impacting milestone timeline | High |  | 2024-09-10 | Rahul K. Patil | Closed | 2024-09-15 | Additional field engineer deployed to region | 11 | 17391
RAID-0064 | PRJ-2024024 | Dependency | Technical | Dependency related to technical impacting site rollout | Low |  | 2025-12-16 | Karthik Subramanian | Closed | 2025-12-26 | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0065 | PRJ-2024019 | Risk | Regulatory/ROW | Risk related to resource impacting milestone timeline | Low | High | 2024-09-25 | Farah Khan | Closed | 2024-10-07 | Alternate last-mile provider engaged as backup | 21 | 60823
RAID-0066 | PRJ-2024011 | Issue | Vendor/Logistics | Issue related to financial impacting site rollout | Low |  | 2025-03-17 | Farah Khan | Closed | 2025-04-13 | Escalated to vendor account manager for expedited resolution | 22 | 137031
RAID-0067 | PRJ-2024025 | Dependency | Financial | Dependency related to regulatory/row impacting client acceptance | Low |  | 2025-09-01 | Farah Khan | In Mitigation |  | Additional field engineer deployed to region | 0 | 0
RAID-0068 | PRJ-2024011 | Issue | Regulatory/ROW | Issue related to client-side readiness impacting client acceptance | High |  | 2025-03-20 | Rahul K. Patil | Open |  | Alternate last-mile provider engaged as backup | 19 | 140783
RAID-0069 | PRJ-2024037 | Risk | Financial | Risk related to financial impacting milestone timeline | Low | High | 2025-06-07 | Karthik Subramanian | Closed | 2025-07-12 | Additional field engineer deployed to region | 7 | 10180
RAID-0070 | PRJ-2024037 | Risk | Resource | Risk related to financial impacting client acceptance | Medium | Low | 2025-02-10 | Rahul K. Patil | Escalated |  | Additional field engineer deployed to region | 26 | 189842
RAID-0071 | PRJ-2024035 | Risk | Client-Side Readiness | Risk related to regulatory/row impacting client acceptance | Critical | Medium | 2025-08-30 | Chinmay Deshpande | Closed | 2025-09-17 | Escalated to vendor account manager for expedited resolution | 11 | 229735
RAID-0072 | PRJ-2024036 | Issue | Regulatory/ROW | Issue related to technical impacting vendor SLA | High |  | 2025-05-22 | Ananya Joshi | Closed | 2025-07-06 | Additional field engineer deployed to region | 23 | 36754
RAID-0073 | PRJ-2024014 | Risk | Schedule | Risk related to vendor/logistics impacting milestone timeline | High | Medium | 2025-01-07 | Rahul K. Patil | Escalated |  | Weekly governance call instituted with client IT team | 10 | 65971
RAID-0074 | PRJ-2024010 | Risk | Schedule | Risk related to client-side readiness impacting client acceptance | Medium | High | 2025-02-24 | Sandeep Rao | Closed | 2025-03-02 | Additional field engineer deployed to region | 30 | 166431
RAID-0075 | PRJ-2024021 | Risk | Vendor/Logistics | Risk related to technical impacting vendor SLA | Medium | Medium | 2025-07-22 | Deepa Nair | Closed | 2025-08-15 | Alternate last-mile provider engaged as backup | 21 | 83783
RAID-0076 | PRJ-2024012 | Risk | Schedule | Risk related to regulatory/row impacting client acceptance | Low | Medium | 2025-02-18 | Farah Khan | Escalated |  | Weekly governance call instituted with client IT team | 27 | 137791
RAID-0077 | PRJ-2024030 | Issue | Financial | Issue related to financial impacting milestone timeline | High |  | 2026-01-11 | Rahul K. Patil | Open |  | Escalated to vendor account manager for expedited resolution | 14 | 204374
RAID-0078 | PRJ-2024034 | Risk | Technical | Risk related to schedule impacting vendor SLA | Medium | Medium | 2025-12-30 | Rahul K. Patil | Closed | 2026-01-09 | Alternate last-mile provider engaged as backup | 9 | 105521
RAID-0079 | PRJ-2024041 | Risk | Regulatory/ROW | Risk related to financial impacting site rollout | Low | Medium | 2025-12-05 | Rahul K. Patil | Closed | 2025-12-09 | Buffer added to schedule; client stakeholder aligned | 17 | 112072
RAID-0080 | PRJ-2024032 | Risk | Resource | Risk related to vendor/logistics impacting client acceptance | Medium | High | 2025-08-29 | Karthik Subramanian | Closed | 2025-09-20 | Additional field engineer deployed to region | 1 | 182374
RAID-0081 | PRJ-2024014 | Risk | Technical | Risk related to schedule impacting site rollout | Critical | High | 2025-03-17 | Farah Khan | Closed | 2025-04-18 | Escalated to vendor account manager for expedited resolution | 7 | 63488
RAID-0082 | PRJ-2024042 | Risk | Financial | Risk related to resource impacting milestone timeline | Medium | High | 2025-09-27 | Farah Khan | Open |  | Alternate last-mile provider engaged as backup | 9 | 220229
RAID-0083 | PRJ-2024021 | Risk | Financial | Risk related to resource impacting site rollout | Low | High | 2025-08-09 | Chinmay Deshpande | In Mitigation |  | Alternate last-mile provider engaged as backup | 16 | 26502
RAID-0084 | PRJ-2024041 | Dependency | Resource | Dependency related to client-side readiness impacting milestone timeline | High |  | 2025-12-05 | Karthik Subramanian | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0085 | PRJ-2024010 | Risk | Technical | Risk related to technical impacting client acceptance | High | Medium | 2025-03-26 | Ananya Joshi | Closed | 2025-04-06 | Alternate last-mile provider engaged as backup | 2 | 213403
RAID-0086 | PRJ-2024041 | Risk | Technical | Risk related to regulatory/row impacting site rollout | Medium | High | 2025-11-13 | Farah Khan | In Mitigation |  | Weekly governance call instituted with client IT team | 2 | 235283
RAID-0087 | PRJ-2024015 | Dependency | Vendor/Logistics | Dependency related to schedule impacting client acceptance | Medium |  | 2024-09-29 | Karthik Subramanian | Closed | 2024-10-14 | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0088 | PRJ-2024003 | Risk | Resource | Risk related to technical impacting vendor SLA | Low | High | 2025-02-14 | Manish Agarwal | Open |  | Buffer added to schedule; client stakeholder aligned | 2 | 229464
RAID-0089 | PRJ-2024028 | Issue | Schedule | Issue related to resource impacting vendor SLA | Critical |  | 2026-01-02 | Rahul K. Patil | Closed | 2026-02-14 | Escalated to vendor account manager for expedited resolution | 3 | 155155
RAID-0090 | PRJ-2024028 | Dependency | Client-Side Readiness | Dependency related to technical impacting client acceptance | Critical |  | 2025-11-30 | Rahul K. Patil | Open |  | Additional field engineer deployed to region | 0 | 0
RAID-0091 | PRJ-2024035 | Issue | Resource | Issue related to schedule impacting milestone timeline | Critical |  | 2025-09-22 | Sandeep Rao | Closed | 2025-09-29 | Buffer added to schedule; client stakeholder aligned | 8 | 42978
RAID-0092 | PRJ-2024007 | Issue | Financial | Issue related to vendor/logistics impacting vendor SLA | Low |  | 2025-04-06 | Ananya Joshi | Escalated |  | Buffer added to schedule; client stakeholder aligned | 21 | 35674
RAID-0093 | PRJ-2024006 | Risk | Technical | Risk related to financial impacting vendor SLA | Low | Low | 2024-10-23 | Karthik Subramanian | Closed | 2024-11-12 | Alternate last-mile provider engaged as backup | 13 | 207645
RAID-0094 | PRJ-2024037 | Issue | Resource | Issue related to vendor/logistics impacting client acceptance | Medium |  | 2025-05-28 | Deepa Nair | Closed | 2025-07-04 | Alternate last-mile provider engaged as backup | 12 | 138927
RAID-0095 | PRJ-2024035 | Risk | Regulatory/ROW | Risk related to technical impacting vendor SLA | Critical | Low | 2026-01-12 | Karthik Subramanian | Open |  | Alternate last-mile provider engaged as backup | 25 | 50201
RAID-0096 | PRJ-2024003 | Risk | Schedule | Risk related to resource impacting site rollout | High | Low | 2025-02-05 | Ananya Joshi | Escalated |  | Buffer added to schedule; client stakeholder aligned | 28 | 169040
RAID-0097 | PRJ-2024035 | Risk | Schedule | Risk related to client-side readiness impacting vendor SLA | Critical | High | 2025-12-11 | Farah Khan | Closed | 2026-01-25 | Weekly governance call instituted with client IT team | 2 | 153592
RAID-0098 | PRJ-2024007 | Issue | Resource | Issue related to resource impacting vendor SLA | High |  | 2025-05-29 | Sandeep Rao | In Mitigation |  | Alternate last-mile provider engaged as backup | 8 | 184482
RAID-0099 | PRJ-2024022 | Issue | Resource | Issue related to schedule impacting vendor SLA | Medium |  | 2025-07-25 | Manish Agarwal | Closed | 2025-08-13 | Weekly governance call instituted with client IT team | 7 | 8892
RAID-0100 | PRJ-2024006 | Risk | Client-Side Readiness | Risk related to technical impacting client acceptance | Critical | Low | 2024-09-17 | Sandeep Rao | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 17 | 113872
RAID-0101 | PRJ-2024005 | Risk | Schedule | Risk related to resource impacting milestone timeline | Medium | Medium | 2025-06-01 | Farah Khan | Escalated |  | Alternate last-mile provider engaged as backup | 25 | 232251
RAID-0102 | PRJ-2024020 | Dependency | Financial | Dependency related to schedule impacting client acceptance | Medium |  | 2025-05-02 | Chinmay Deshpande | Closed | 2025-06-11 | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0103 | PRJ-2024021 | Risk | Technical | Risk related to client-side readiness impacting milestone timeline | Medium | Medium | 2025-04-28 | Karthik Subramanian | In Mitigation |  | Alternate last-mile provider engaged as backup | 19 | 114049
RAID-0104 | PRJ-2024004 | Risk | Vendor/Logistics | Risk related to schedule impacting vendor SLA | High | Medium | 2025-03-09 | Chinmay Deshpande | Closed | 2025-04-09 | Weekly governance call instituted with client IT team | 4 | 104107
RAID-0105 | PRJ-2024012 | Assumption | Financial | Assumption related to client-side readiness impacting vendor SLA | Critical |  | 2024-11-08 | Ananya Joshi | Open |  | Additional field engineer deployed to region | 0 | 0
RAID-0106 | PRJ-2024024 | Issue | Financial | Issue related to schedule impacting milestone timeline | Critical |  | 2026-02-04 | Karthik Subramanian | Closed | 2026-02-22 | Weekly governance call instituted with client IT team | 16 | 244953
RAID-0107 | PRJ-2024017 | Issue | Regulatory/ROW | Issue related to regulatory/row impacting vendor SLA | Low |  | 2024-09-30 | Sandeep Rao | Escalated |  | Alternate last-mile provider engaged as backup | 13 | 23804
RAID-0108 | PRJ-2024012 | Issue | Regulatory/ROW | Issue related to client-side readiness impacting vendor SLA | Medium |  | 2024-12-13 | Deepa Nair | In Mitigation |  | Weekly governance call instituted with client IT team | 22 | 196203
RAID-0109 | PRJ-2024015 | Dependency | Financial | Dependency related to regulatory/row impacting site rollout | Low |  | 2025-03-16 | Sandeep Rao | In Mitigation |  | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0110 | PRJ-2024019 | Issue | Financial | Issue related to financial impacting milestone timeline | Medium |  | 2024-11-04 | Farah Khan | Escalated |  | Escalated to vendor account manager for expedited resolution | 16 | 59921
RAID-0111 | PRJ-2024006 | Risk | Technical | Risk related to vendor/logistics impacting milestone timeline | Medium | Low | 2024-08-13 | Ananya Joshi | In Mitigation |  | Alternate last-mile provider engaged as backup | 15 | 101571
RAID-0112 | PRJ-2024040 | Risk | Financial | Risk related to technical impacting vendor SLA | Medium | High | 2025-05-12 | Karthik Subramanian | Escalated |  | Additional field engineer deployed to region | 10 | 174005
RAID-0113 | PRJ-2024024 | Risk | Vendor/Logistics | Risk related to regulatory/row impacting site rollout | Low | High | 2025-12-31 | Chinmay Deshpande | Closed | 2026-01-25 | Escalated to vendor account manager for expedited resolution | 30 | 35614
RAID-0114 | PRJ-2024027 | Issue | Technical | Issue related to client-side readiness impacting vendor SLA | High |  | 2025-07-17 | Deepa Nair | Closed | 2025-08-26 | Buffer added to schedule; client stakeholder aligned | 5 | 207917
RAID-0115 | PRJ-2024039 | Assumption | Client-Side Readiness | Assumption related to schedule impacting client acceptance | High |  | 2025-12-04 | Farah Khan | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 0 | 0
RAID-0116 | PRJ-2024027 | Risk | Vendor/Logistics | Risk related to schedule impacting milestone timeline | Medium | Low | 2025-11-20 | Farah Khan | Closed | 2025-12-05 | Alternate last-mile provider engaged as backup | 22 | 115465
RAID-0117 | PRJ-2024030 | Issue | Technical | Issue related to schedule impacting vendor SLA | High |  | 2025-10-08 | Rahul K. Patil | Open |  | Escalated to vendor account manager for expedited resolution | 4 | 99445
RAID-0118 | PRJ-2024020 | Risk | Resource | Risk related to vendor/logistics impacting vendor SLA | Critical | Low | 2025-04-01 | Manish Agarwal | Escalated |  | Additional field engineer deployed to region | 25 | 242861
RAID-0119 | PRJ-2024032 | Dependency | Resource | Dependency related to resource impacting client acceptance | Critical |  | 2025-10-03 | Ananya Joshi | Open |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0120 | PRJ-2024038 | Risk | Technical | Risk related to regulatory/row impacting client acceptance | High | High | 2025-08-24 | Chinmay Deshpande | Escalated |  | Weekly governance call instituted with client IT team | 11 | 13563
RAID-0121 | PRJ-2024017 | Issue | Client-Side Readiness | Issue related to schedule impacting milestone timeline | Low |  | 2024-09-15 | Rahul K. Patil | Open |  | Weekly governance call instituted with client IT team | 15 | 50533
RAID-0122 | PRJ-2024034 | Dependency | Regulatory/ROW | Dependency related to resource impacting site rollout | Medium |  | 2025-09-21 | Sandeep Rao | Escalated |  | Additional field engineer deployed to region | 0 | 0
RAID-0123 | PRJ-2024009 | Issue | Regulatory/ROW | Issue related to vendor/logistics impacting client acceptance | Critical |  | 2024-11-18 | Chinmay Deshpande | Open |  | Weekly governance call instituted with client IT team | 1 | 123750
RAID-0124 | PRJ-2024041 | Risk | Technical | Risk related to schedule impacting milestone timeline | Low | High | 2025-08-21 | Karthik Subramanian | In Mitigation |  | Alternate last-mile provider engaged as backup | 7 | 156292
RAID-0125 | PRJ-2024005 | Assumption | Schedule | Assumption related to technical impacting milestone timeline | Low |  | 2025-05-22 | Ananya Joshi | Closed | 2025-06-07 | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0126 | PRJ-2024036 | Dependency | Resource | Dependency related to technical impacting client acceptance | Low |  | 2025-08-07 | Deepa Nair | In Mitigation |  | Weekly governance call instituted with client IT team | 0 | 0
RAID-0127 | PRJ-2024037 | Risk | Schedule | Risk related to client-side readiness impacting site rollout | Critical | Low | 2025-02-23 | Karthik Subramanian | Closed | 2025-03-02 | Additional field engineer deployed to region | 10 | 3089
RAID-0128 | PRJ-2024011 | Risk | Technical | Risk related to technical impacting client acceptance | High | Low | 2025-06-21 | Manish Agarwal | Closed | 2025-07-25 | Buffer added to schedule; client stakeholder aligned | 16 | 183675
RAID-0129 | PRJ-2024015 | Issue | Technical | Issue related to regulatory/row impacting vendor SLA | Medium |  | 2024-12-07 | Rahul K. Patil | Closed | 2024-12-29 | Buffer added to schedule; client stakeholder aligned | 1 | 77771
RAID-0130 | PRJ-2024004 | Issue | Client-Side Readiness | Issue related to client-side readiness impacting vendor SLA | High |  | 2024-12-18 | Manish Agarwal | Closed | 2024-12-29 | Additional field engineer deployed to region | 5 | 131518
RAID-0131 | PRJ-2024040 | Risk | Resource | Risk related to schedule impacting milestone timeline | Critical | High | 2025-04-24 | Karthik Subramanian | Closed | 2025-05-11 | Weekly governance call instituted with client IT team | 8 | 200653
RAID-0132 | PRJ-2024039 | Issue | Client-Side Readiness | Issue related to vendor/logistics impacting site rollout | Medium |  | 2025-08-03 | Farah Khan | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 21 | 50693
RAID-0133 | PRJ-2024022 | Assumption | Technical | Assumption related to client-side readiness impacting client acceptance | Medium |  | 2025-08-22 | Farah Khan | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0134 | PRJ-2024006 | Risk | Regulatory/ROW | Risk related to regulatory/row impacting vendor SLA | Low | Low | 2024-12-27 | Deepa Nair | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 19 | 19759
RAID-0135 | PRJ-2024032 | Assumption | Client-Side Readiness | Assumption related to financial impacting milestone timeline | Low |  | 2025-08-31 | Manish Agarwal | Closed | 2025-09-21 | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0136 | PRJ-2024006 | Issue | Regulatory/ROW | Issue related to regulatory/row impacting vendor SLA | Low |  | 2024-12-13 | Ananya Joshi | Closed | 2025-01-14 | Additional field engineer deployed to region | 1 | 19000
RAID-0137 | PRJ-2024003 | Assumption | Client-Side Readiness | Assumption related to financial impacting vendor SLA | Critical |  | 2025-01-19 | Deepa Nair | Escalated |  | Weekly governance call instituted with client IT team | 0 | 0
RAID-0138 | PRJ-2024006 | Issue | Vendor/Logistics | Issue related to client-side readiness impacting site rollout | Medium |  | 2024-08-13 | Karthik Subramanian | In Mitigation |  | Escalated to vendor account manager for expedited resolution | 9 | 10296
RAID-0139 | PRJ-2024042 | Issue | Technical | Issue related to schedule impacting client acceptance | Medium |  | 2025-10-29 | Deepa Nair | Closed | 2025-11-26 | Weekly governance call instituted with client IT team | 5 | 113274
RAID-0140 | PRJ-2024031 | Dependency | Schedule | Dependency related to schedule impacting milestone timeline | Critical |  | 2026-02-05 | Sandeep Rao | Closed | 2026-03-10 | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0141 | PRJ-2024026 | Assumption | Resource | Assumption related to client-side readiness impacting client acceptance | High |  | 2025-07-21 | Sandeep Rao | Closed | 2025-07-28 | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0142 | PRJ-2024029 | Dependency | Client-Side Readiness | Dependency related to financial impacting vendor SLA | Medium |  | 2025-11-04 | Rahul K. Patil | Closed | 2025-11-30 | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0143 | PRJ-2024042 | Risk | Client-Side Readiness | Risk related to technical impacting site rollout | Low | Low | 2025-08-18 | Chinmay Deshpande | Closed | 2025-09-11 | Additional field engineer deployed to region | 25 | 140952
RAID-0144 | PRJ-2024038 | Risk | Technical | Risk related to vendor/logistics impacting vendor SLA | High | High | 2026-02-06 | Ananya Joshi | Escalated |  | Additional field engineer deployed to region | 10 | 171504
RAID-0145 | PRJ-2024005 | Risk | Financial | Risk related to regulatory/row impacting vendor SLA | Low | Low | 2025-04-23 | Farah Khan | Closed | 2025-05-24 | Escalated to vendor account manager for expedited resolution | 23 | 130635
RAID-0146 | PRJ-2024031 | Dependency | Resource | Dependency related to client-side readiness impacting site rollout | Low |  | 2025-12-26 | Karthik Subramanian | Closed | 2026-01-13 | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0147 | PRJ-2024015 | Dependency | Financial | Dependency related to regulatory/row impacting site rollout | Medium |  | 2024-09-23 | Farah Khan | In Mitigation |  | Buffer added to schedule; client stakeholder aligned | 0 | 0
RAID-0148 | PRJ-2024008 | Risk | Vendor/Logistics | Risk related to regulatory/row impacting client acceptance | Low | Medium | 2025-03-26 | Sandeep Rao | Closed | 2025-04-03 | Buffer added to schedule; client stakeholder aligned | 28 | 125307
RAID-0149 | PRJ-2024001 | Issue | Resource | Issue related to resource impacting client acceptance | Medium |  | 2024-10-24 | Manish Agarwal | Open |  | Weekly governance call instituted with client IT team | 4 | 76144
RAID-0150 | PRJ-2024024 | Issue | Resource | Issue related to vendor/logistics impacting client acceptance | Critical |  | 2026-06-14 | Deepa Nair | Closed | 2026-07-01 | Escalated to vendor account manager for expedited resolution | 8 | 28528
RAID-0151 | PRJ-2024011 | Issue | Vendor/Logistics | Issue related to client-side readiness impacting milestone timeline | Low |  | 2025-05-19 | Karthik Subramanian | Closed | 2025-06-27 | Alternate last-mile provider engaged as backup | 2 | 165935
RAID-0152 | PRJ-2024025 | Risk | Technical | Risk related to resource impacting site rollout | High | High | 2025-05-23 | Farah Khan | Escalated |  | Escalated to vendor account manager for expedited resolution | 6 | 225749
RAID-0153 | PRJ-2024024 | Assumption | Financial | Assumption related to resource impacting vendor SLA | Medium |  | 2026-05-29 | Deepa Nair | In Mitigation |  | Additional field engineer deployed to region | 0 | 0
RAID-0154 | PRJ-2024026 | Assumption | Technical | Assumption related to financial impacting client acceptance | Medium |  | 2025-05-07 | Manish Agarwal | Closed | 2025-06-03 | Escalated to vendor account manager for expedited resolution | 0 | 0
RAID-0155 | PRJ-2024003 | Risk | Regulatory/ROW | Risk related to technical impacting site rollout | High | Medium | 2025-02-23 | Karthik Subramanian | Closed | 2025-03-21 | Additional field engineer deployed to region | 20 | 105033
RAID-0156 | PRJ-2024019 | Issue | Resource | Issue related to schedule impacting client acceptance | Low |  | 2024-12-18 | Manish Agarwal | In Mitigation |  | Additional field engineer deployed to region | 27 | 65983
RAID-0157 | PRJ-2024037 | Issue | Vendor/Logistics | Issue related to technical impacting vendor SLA | Medium |  | 2025-04-22 | Sandeep Rao | Closed | 2025-06-01 | Additional field engineer deployed to region | 9 | 86384
RAID-0158 | PRJ-2024011 | Dependency | Technical | Dependency related to resource impacting client acceptance | Medium |  | 2025-02-01 | Sandeep Rao | Closed | 2025-03-13 | Weekly governance call instituted with client IT team | 0 | 0
RAID-0159 | PRJ-2024040 | Issue | Financial | Issue related to resource impacting milestone timeline | Medium |  | 2025-03-05 | Sandeep Rao | Closed | 2025-03-08 | Additional field engineer deployed to region | 2 | 180076
RAID-0160 | PRJ-2024011 | Issue | Regulatory/ROW | Issue related to vendor/logistics impacting client acceptance | Low |  | 2025-03-18 | Ananya Joshi | Escalated |  | Weekly governance call instituted with client IT team | 13 | 205815
RAID-0161 | PRJ-2024030 | Issue | Vendor/Logistics | Issue related to resource impacting client acceptance | Low |  | 2025-08-22 | Manish Agarwal | Closed | 2025-09-06 | Weekly governance call instituted with client IT team | 1 | 64422
RAID-0162 | PRJ-2024039 | Risk | Vendor/Logistics | Risk related to technical impacting milestone timeline | Critical | Low | 2025-08-14 | Ananya Joshi | Closed | 2025-09-01 | Escalated to vendor account manager for expedited resolution | 28 | 20704
RAID-0163 | PRJ-2024027 | Risk | Financial | Risk related to technical impacting client acceptance | Medium | Medium | 2025-07-12 | Karthik Subramanian | Escalated |  | Weekly governance call instituted with client IT team | 10 | 89951
RAID-0164 | PRJ-2024028 | Issue | Resource | Issue related to vendor/logistics impacting client acceptance | Medium |  | 2026-02-13 | Rahul K. Patil | Closed | 2026-03-09 | Escalated to vendor account manager for expedited resolution | 8 | 50556
RAID-0165 | PRJ-2024018 | Risk | Client-Side Readiness | Risk related to financial impacting milestone timeline | Medium | Medium | 2024-12-14 | Rahul K. Patil | In Mitigation |  | Weekly governance call instituted with client IT team | 28 | 143184
RAID-0166 | PRJ-2024008 | Risk | Financial | Risk related to vendor/logistics impacting vendor SLA | Critical | Medium | 2025-03-11 | Manish Agarwal | Closed | 2025-04-10 | Weekly governance call instituted with client IT team | 13 | 229839
RAID-0167 | PRJ-2024037 | Risk | Financial | Risk related to financial impacting client acceptance | Medium | Low | 2025-03-05 | Karthik Subramanian | Open |  | Additional field engineer deployed to region | 20 | 139954
RAID-0168 | PRJ-2024007 | Assumption | Technical | Assumption related to financial impacting site rollout | Low |  | 2025-03-12 | Rahul K. Patil | Escalated |  | Additional field engineer deployed to region | 0 | 0
RAID-0169 | PRJ-2024020 | Risk | Financial | Risk related to client-side readiness impacting client acceptance | Medium | Low | 2025-03-28 | Sandeep Rao | Escalated |  | Alternate last-mile provider engaged as backup | 12 | 210162
RAID-0170 | PRJ-2024018 | Dependency | Regulatory/ROW | Dependency related to schedule impacting vendor SLA | Low |  | 2025-01-03 | Rahul K. Patil | Closed | 2025-02-06 | Weekly governance call instituted with client IT team | 0 | 0
RAID-0171 | PRJ-2024001 | Issue | Technical | Issue related to schedule impacting site rollout | Critical |  | 2024-11-27 | Sandeep Rao | Closed | 2025-01-10 | Additional field engineer deployed to region | 26 | 20205
RAID-0172 | PRJ-2024004 | Issue | Schedule | Issue related to financial impacting milestone timeline | Medium |  | 2024-09-11 | Chinmay Deshpande | Open |  | Weekly governance call instituted with client IT team | 30 | 173122
RAID-0173 | PRJ-2024042 | Issue | Schedule | Issue related to schedule impacting vendor SLA | Critical |  | 2025-06-26 | Rahul K. Patil | Escalated |  | Escalated to vendor account manager for expedited resolution | 20 | 71831
RAID-0174 | PRJ-2024038 | Dependency | Schedule | Dependency related to resource impacting vendor SLA | High |  | 2026-02-26 | Manish Agarwal | Escalated |  | Alternate last-mile provider engaged as backup | 0 | 0
RAID-0175 | PRJ-2024009 | Risk | Client-Side Readiness | Risk related to vendor/logistics impacting milestone timeline | Low | Low | 2024-09-08 | Ananya Joshi | Closed | 2024-10-03 | Escalated to vendor account manager for expedited resolution | 16 | 40805
RAID-0176 | PRJ-2024029 | Risk | Resource | Risk related to vendor/logistics impacting site rollout | High | Medium | 2026-05-09 | Chinmay Deshpande | Closed | 2026-05-27 | Escalated to vendor account manager for expedited resolution | 20 | 129634
RAID-0177 | PRJ-2024017 | Risk | Technical | Risk related to financial impacting vendor SLA | Medium | High | 2024-12-23 | Chinmay Deshpande | Open |  | Buffer added to schedule; client stakeholder aligned | 16 | 77994
RAID-0178 | PRJ-2024027 | Risk | Resource | Risk related to technical impacting milestone timeline | Medium | Low | 2025-09-10 | Ananya Joshi | Closed | 2025-09-24 | Weekly governance call instituted with client IT team | 1 | 224124
RAID-0179 | PRJ-2024026 | Issue | Technical | Issue related to vendor/logistics impacting vendor SLA | Low |  | 2025-05-28 | Karthik Subramanian | Open |  | Buffer added to schedule; client stakeholder aligned | 29 | 206499
RAID-0180 | PRJ-2024005 | Risk | Client-Side Readiness | Risk related to client-side readiness impacting site rollout | Critical | Low | 2024-11-30 | Sandeep Rao | Open |  | Buffer added to schedule; client stakeholder aligned | 22 | 180737

## Resources
ResourceID | ResourceName | Role | ProjectID | Region | AllocationPercent | BillRateINRPerDay | StartDate | Status | Certification
EMP-1001 | Sandeep Mehta | Solution Architect | PRJ-2024008 | West | 50 | 10277 | 2024-11-03 | Active | CCNP
EMP-1002 | Anjali Nair | Quality/UAT Lead | PRJ-2024040 | East | 75 | 9722 | 2025-01-28 | Rolled Off | PMP
EMP-1003 | Meera Gupta | Service Delivery Manager | PRJ-2024027 | South | 50 | 10295 | 2025-06-14 | Active | CCNA
EMP-1004 | Karan Patil | Vendor Coordinator | PRJ-2024040 | East | 75 | 7220 | 2025-01-28 | Rolled Off | PMP
EMP-1005 | Suresh Joshi | Network Engineer | PRJ-2024008 | West | 100 | 4232 | 2024-11-03 | Active | None
EMP-1006 | Sandeep Kulkarni | Solution Architect | PRJ-2024022 | East | 50 | 4589 | 2025-03-21 | Active | CSM
EMP-1007 | Kavita Iyer | Service Delivery Manager | PRJ-2024011 | South | 25 | 3630 | 2024-12-16 | Active | PMP
EMP-1008 | Arjun Nair | Field Engineer | PRJ-2024018 | Central | 50 | 3200 | 2024-08-19 | Active | None
EMP-1009 | Suresh Iyer | Solution Architect | PRJ-2024021 | Central | 25 | 10242 | 2025-04-23 | Active | ITIL
EMP-1010 | Sandeep Mehta | Network Engineer | PRJ-2024028 | West | 75 | 10252 | 2025-11-24 | Active | CSM
EMP-1011 | Divya Kulkarni | Field Engineer | PRJ-2024042 | West | 50 | 3270 | 2025-06-01 | Active | CSM
EMP-1012 | Neha Kulkarni | Service Delivery Manager | PRJ-2024029 | South | 25 | 4296 | 2025-11-03 | Active | CCNP
EMP-1013 | Divya Gupta | Vendor Coordinator | PRJ-2024018 | Central | 50 | 7661 | 2024-08-19 | Rolled Off | None
EMP-1014 | Sandeep Iyer | Field Engineer | PRJ-2024018 | Central | 75 | 1672 | 2024-08-19 | Active | CCNP
EMP-1015 | Amit Joshi | Network Engineer | PRJ-2024008 | West | 50 | 7828 | 2024-11-03 | Active | PMP
EMP-1016 | Kavita Nair | Project Manager | PRJ-2024023 | East | 75 | 5606 | 2025-06-26 | Rolled Off | CCNA
EMP-1017 | Vikram Nair | Solution Architect | PRJ-2024008 | West | 100 | 6612 | 2024-11-03 | Active | PMP+CCNA
EMP-1018 | Divya Patil | Network Engineer | PRJ-2024038 | South | 100 | 6643 | 2025-08-23 | Active | CSM
EMP-1019 | Meera Iyer | Project Manager | PRJ-2024022 | East | 25 | 5205 | 2025-03-21 | Rolled Off | CCNP
EMP-1020 | Rahul Mehta | Solution Architect | PRJ-2024015 | South | 75 | 10833 | 2024-09-15 | Active | PMP+CCNA
EMP-1021 | Rohan Mehta | Service Delivery Manager | PRJ-2024019 | East | 75 | 4243 | 2024-07-01 | Active | ITIL
EMP-1022 | Karan Gupta | Solution Architect | PRJ-2024004 | North | 50 | 6072 | 2024-08-28 | Active | PMP
EMP-1023 | Arjun Sharma | Project Manager | PRJ-2024005 | South | 25 | 9430 | 2024-11-24 | Active | None
EMP-1024 | Karan Joshi | Network Engineer | PRJ-2024008 | West | 75 | 10296 | 2024-11-03 | Rolled Off | CCNA
EMP-1025 | Anjali Rao | Procurement Specialist | PRJ-2024004 | North | 100 | 9269 | 2024-08-28 | Active | CCNP
EMP-1026 | Meera Sharma | Network Engineer | PRJ-2024004 | North | 75 | 6453 | 2024-08-28 | Active | CCNA
EMP-1027 | Pooja Iyer | Quality/UAT Lead | PRJ-2024011 | South | 50 | 7202 | 2024-12-16 | Rolled Off | CCNA
EMP-1028 | Kavita Patil | Quality/UAT Lead | PRJ-2024011 | South | 75 | 7975 | 2024-12-16 | Active | None
EMP-1029 | Anjali Patil | Quality/UAT Lead | PRJ-2024026 | East | 50 | 10127 | 2025-01-04 | Active | CCNP
EMP-1030 | Sandeep Patil | Solution Architect | PRJ-2024016 | South | 75 | 10932 | 2024-10-02 | Active | PMP
EMP-1031 | Divya Joshi | Service Delivery Manager | PRJ-2024001 | East | 100 | 8381 | 2024-08-08 | Active | ITIL
EMP-1032 | Sandeep Joshi | Quality/UAT Lead | PRJ-2024013 | South | 75 | 2706 | 2024-09-22 | Active | PMP+CCNA
EMP-1033 | Meera Gupta | Solution Architect | PRJ-2024027 | South | 50 | 5014 | 2025-06-14 | Active | ITIL
EMP-1034 | Karan Nair | Quality/UAT Lead | PRJ-2024027 | South | 75 | 4788 | 2025-06-14 | Active | PMP
EMP-1035 | Arjun Iyer | Network Engineer | PRJ-2024022 | East | 50 | 7842 | 2025-03-21 | Active | None
EMP-1036 | Anjali Mehta | Procurement Specialist | PRJ-2024032 | West | 75 | 8533 | 2025-08-09 | Active | CCNP
EMP-1037 | Meera Joshi | Network Engineer | PRJ-2024011 | South | 50 | 9270 | 2024-12-16 | Active | CCNA
EMP-1038 | Rahul Joshi | Field Engineer | PRJ-2024030 | North | 75 | 2128 | 2025-08-14 | Active | PMP
EMP-1039 | Amit Rao | Network Engineer | PRJ-2024005 | South | 100 | 3769 | 2024-11-24 | Active | PMP+CCNA
EMP-1040 | Rahul Kulkarni | Service Delivery Manager | PRJ-2024032 | West | 50 | 11667 | 2025-08-09 | Active | PMP
EMP-1041 | Anjali Iyer | Project Manager | PRJ-2024037 | Central | 50 | 7601 | 2025-01-12 | Active | ITIL
EMP-1042 | Divya Gupta | Network Engineer | PRJ-2024013 | South | 50 | 3039 | 2024-09-22 | Active | None
EMP-1043 | Arjun Iyer | Procurement Specialist | PRJ-2024022 | East | 100 | 11625 | 2025-03-21 | Active | PMP
EMP-1044 | Rohan Kulkarni | Service Delivery Manager | PRJ-2024039 | West | 100 | 7880 | 2025-07-23 | Active | ITIL
EMP-1045 | Karan Reddy | Project Manager | PRJ-2024023 | East | 100 | 7317 | 2025-06-26 | Rolled Off | CCNP
EMP-1046 | Amit Mehta | Service Delivery Manager | PRJ-2024031 | North | 25 | 10786 | 2025-09-08 | Active | CCNA
EMP-1047 | Suresh Joshi | Procurement Specialist | PRJ-2024034 | South | 100 | 8681 | 2025-07-13 | Active | None
EMP-1048 | Arjun Sharma | Solution Architect | PRJ-2024042 | West | 100 | 11758 | 2025-06-01 | Active | CSM
EMP-1049 | Arjun Gupta | Quality/UAT Lead | PRJ-2024017 | Central | 50 | 2768 | 2024-07-24 | Active | CCNA
EMP-1050 | Sandeep Joshi | Network Engineer | PRJ-2024009 | West | 75 | 5206 | 2024-08-15 | Rolled Off | PMP+CCNA
EMP-1051 | Suresh Kulkarni | Network Engineer | PRJ-2024022 | East | 100 | 4897 | 2025-03-21 | Active | PMP+CCNA
EMP-1052 | Meera Iyer | Network Engineer | PRJ-2024041 | West | 75 | 10492 | 2025-08-14 | Active | None
EMP-1053 | Arjun Rao | Procurement Specialist | PRJ-2024020 | Central | 100 | 5213 | 2024-12-10 | Rolled Off | PMP
EMP-1054 | Rahul Reddy | Procurement Specialist | PRJ-2024031 | North | 100 | 6447 | 2025-09-08 | Active | None
EMP-1055 | Suresh Joshi | Procurement Specialist | PRJ-2024019 | East | 100 | 4226 | 2024-07-01 | Active | CCNA
EMP-1056 | Divya Joshi | Field Engineer | PRJ-2024025 | South | 75 | 1678 | 2025-04-01 | Active | CCNP
EMP-1057 | Karan Rao | Quality/UAT Lead | PRJ-2024036 | West | 50 | 8826 | 2025-03-02 | Rolled Off | ITIL
EMP-1058 | Vikram Kulkarni | Network Engineer | PRJ-2024007 | East | 75 | 6674 | 2024-12-19 | Active | PMP+CCNA
EMP-1059 | Sneha Rao | Solution Architect | PRJ-2024018 | Central | 75 | 9499 | 2024-08-19 | Active | CCNP
EMP-1060 | Rohan Nair | Field Engineer | PRJ-2024023 | East | 50 | 2059 | 2025-06-26 | Active | PMP+CCNA
EMP-1061 | Kavita Patil | Solution Architect | PRJ-2024010 | North | 50 | 11420 | 2024-11-11 | Active | ITIL
EMP-1062 | Suresh Kulkarni | Project Manager | PRJ-2024016 | South | 25 | 5623 | 2024-10-02 | Active | CCNP
EMP-1063 | Sandeep Iyer | Quality/UAT Lead | PRJ-2024007 | East | 25 | 5833 | 2024-12-19 | Rolled Off | CCNP
EMP-1064 | Sneha Iyer | Solution Architect | PRJ-2024011 | South | 25 | 5120 | 2024-12-16 | Active | PMP
EMP-1065 | Sneha Rao | Quality/UAT Lead | PRJ-2024004 | North | 50 | 8513 | 2024-08-28 | Active | PMP

## Budget_Costs
ProjectID | Month | CostCategory | PlannedCostINR | ActualCostINR
PRJ-2024001 | 2024-08 | Equipment/CapEx | 847595 | 596569
PRJ-2024001 | 2024-08 | Last Mile Circuit Cost | 484340 | 387297
PRJ-2024001 | 2024-08 | Installation Labor | 363255 | 391212
PRJ-2024001 | 2024-08 | Vendor Management Fee | 242170 | 226787
PRJ-2024001 | 2024-08 | Travel & Logistics | 193736 | 162847
PRJ-2024001 | 2024-08 | Project Management Overhead | 169519 | 220937
PRJ-2024001 | 2024-08 | Contingency | 121085 | 103835
PRJ-2024001 | 2024-09 | Equipment/CapEx | 847595 | 1048374
PRJ-2024001 | 2024-09 | Last Mile Circuit Cost | 484340 | 539629
PRJ-2024001 | 2024-09 | Installation Labor | 363255 | 416191
PRJ-2024001 | 2024-09 | Vendor Management Fee | 242170 | 276383
PRJ-2024001 | 2024-09 | Travel & Logistics | 193736 | 172272
PRJ-2024001 | 2024-09 | Project Management Overhead | 169519 | 119200
PRJ-2024001 | 2024-09 | Contingency | 121085 | 128308
PRJ-2024001 | 2024-10 | Equipment/CapEx | 847595 | 637143
PRJ-2024001 | 2024-10 | Last Mile Circuit Cost | 484340 | 491737
PRJ-2024001 | 2024-10 | Installation Labor | 363255 | 297627
PRJ-2024001 | 2024-10 | Vendor Management Fee | 242170 | 188753
PRJ-2024001 | 2024-10 | Travel & Logistics | 193736 | 210518
PRJ-2024001 | 2024-10 | Project Management Overhead | 169519 | 165652
PRJ-2024001 | 2024-10 | Contingency | 121085 | 99501
PRJ-2024002 | 2024-10 | Equipment/CapEx | 627392 | 779180
PRJ-2024002 | 2024-10 | Last Mile Circuit Cost | 358510 | 293586
PRJ-2024002 | 2024-10 | Installation Labor | 268882 | 248984
PRJ-2024002 | 2024-10 | Vendor Management Fee | 179255 | 127595
PRJ-2024002 | 2024-10 | Travel & Logistics | 143404 | 179443
PRJ-2024002 | 2024-10 | Project Management Overhead | 125479 | 107808
PRJ-2024002 | 2024-10 | Contingency | 89628 | 101369
PRJ-2024002 | 2024-11 | Equipment/CapEx | 627392 | 625338
PRJ-2024002 | 2024-11 | Last Mile Circuit Cost | 358510 | 399073
PRJ-2024002 | 2024-11 | Installation Labor | 268882 | 257927
PRJ-2024002 | 2024-11 | Vendor Management Fee | 179255 | 192509
PRJ-2024002 | 2024-11 | Travel & Logistics | 143404 | 164630
PRJ-2024002 | 2024-11 | Project Management Overhead | 125479 | 88471
PRJ-2024002 | 2024-11 | Contingency | 89628 | 63072
PRJ-2024002 | 2024-12 | Equipment/CapEx | 627392 | 482075
PRJ-2024002 | 2024-12 | Last Mile Circuit Cost | 358510 | 386543
PRJ-2024002 | 2024-12 | Installation Labor | 268882 | 362587
PRJ-2024002 | 2024-12 | Vendor Management Fee | 179255 | 212712
PRJ-2024002 | 2024-12 | Travel & Logistics | 143404 | 189048
PRJ-2024002 | 2024-12 | Project Management Overhead | 125479 | 118520
PRJ-2024002 | 2024-12 | Contingency | 89628 | 82707
PRJ-2024002 | 2025-01 | Equipment/CapEx | 627392 | 830457
PRJ-2024002 | 2025-01 | Last Mile Circuit Cost | 358510 | 300491
PRJ-2024002 | 2025-01 | Installation Labor | 268882 | 320654
PRJ-2024002 | 2025-01 | Vendor Management Fee | 179255 | 234888
PRJ-2024002 | 2025-01 | Travel & Logistics | 143404 | 179608
PRJ-2024002 | 2025-01 | Project Management Overhead | 125479 | 131030
PRJ-2024002 | 2025-01 | Contingency | 89628 | 77722
PRJ-2024003 | 2024-11 | Equipment/CapEx | 20829 | 17541
PRJ-2024003 | 2024-11 | Last Mile Circuit Cost | 11902 | 15015
PRJ-2024003 | 2024-11 | Installation Labor | 8927 | 11527
PRJ-2024003 | 2024-11 | Vendor Management Fee | 5951 | 6026
PRJ-2024003 | 2024-11 | Travel & Logistics | 4761 | 4486
PRJ-2024003 | 2024-11 | Project Management Overhead | 4166 | 3113
PRJ-2024003 | 2024-11 | Contingency | 2976 | 2633
PRJ-2024003 | 2024-12 | Equipment/CapEx | 20829 | 21252
PRJ-2024003 | 2024-12 | Last Mile Circuit Cost | 11902 | 11700
PRJ-2024003 | 2024-12 | Installation Labor | 8927 | 6917
PRJ-2024003 | 2024-12 | Vendor Management Fee | 5951 | 5965
PRJ-2024003 | 2024-12 | Travel & Logistics | 4761 | 5271
PRJ-2024003 | 2024-12 | Project Management Overhead | 4166 | 5347
PRJ-2024003 | 2024-12 | Contingency | 2976 | 3417
PRJ-2024003 | 2025-01 | Equipment/CapEx | 20829 | 20702
PRJ-2024003 | 2025-01 | Last Mile Circuit Cost | 11902 | 9363
PRJ-2024003 | 2025-01 | Installation Labor | 8927 | 7065
PRJ-2024003 | 2025-01 | Vendor Management Fee | 5951 | 7908
PRJ-2024003 | 2025-01 | Travel & Logistics | 4761 | 6137
PRJ-2024003 | 2025-01 | Project Management Overhead | 4166 | 5201
PRJ-2024003 | 2025-01 | Contingency | 2976 | 2186
PRJ-2024003 | 2025-02 | Equipment/CapEx | 20829 | 23018
PRJ-2024003 | 2025-02 | Last Mile Circuit Cost | 11902 | 13413
PRJ-2024003 | 2025-02 | Installation Labor | 8927 | 10500
PRJ-2024003 | 2025-02 | Vendor Management Fee | 5951 | 6176
PRJ-2024003 | 2025-02 | Travel & Logistics | 4761 | 5997
PRJ-2024003 | 2025-02 | Project Management Overhead | 4166 | 4393
PRJ-2024003 | 2025-02 | Contingency | 2976 | 3489
PRJ-2024003 | 2025-03 | Equipment/CapEx | 20829 | 18412
PRJ-2024003 | 2025-03 | Last Mile Circuit Cost | 11902 | 13851
PRJ-2024003 | 2025-03 | Installation Labor | 8927 | 9971
PRJ-2024003 | 2025-03 | Vendor Management Fee | 5951 | 4857
PRJ-2024003 | 2025-03 | Travel & Logistics | 4761 | 3967
PRJ-2024003 | 2025-03 | Project Management Overhead | 4166 | 3223
PRJ-2024003 | 2025-03 | Contingency | 2976 | 3371
PRJ-2024003 | 2025-04 | Equipment/CapEx | 20829 | 14751
PRJ-2024003 | 2025-04 | Last Mile Circuit Cost | 11902 | 11230
PRJ-2024003 | 2025-04 | Installation Labor | 8927 | 9732
PRJ-2024003 | 2025-04 | Vendor Management Fee | 5951 | 6913
PRJ-2024003 | 2025-04 | Travel & Logistics | 4761 | 3883
PRJ-2024003 | 2025-04 | Project Management Overhead | 4166 | 4806
PRJ-2024003 | 2025-04 | Contingency | 2976 | 3140
PRJ-2024003 | 2025-05 | Equipment/CapEx | 20829 | 16460
PRJ-2024003 | 2025-05 | Last Mile Circuit Cost | 11902 | 14026
PRJ-2024003 | 2025-05 | Installation Labor | 8927 | 8281
PRJ-2024003 | 2025-05 | Vendor Management Fee | 5951 | 6918
PRJ-2024003 | 2025-05 | Travel & Logistics | 4761 | 4522
PRJ-2024003 | 2025-05 | Project Management Overhead | 4166 | 3893
PRJ-2024003 | 2025-05 | Contingency | 2976 | 3351
PRJ-2024003 | 2025-06 | Equipment/CapEx | 20829 | 15161
PRJ-2024003 | 2025-06 | Last Mile Circuit Cost | 11902 | 9600
PRJ-2024003 | 2025-06 | Installation Labor | 8927 | 7527
PRJ-2024003 | 2025-06 | Vendor Management Fee | 5951 | 4548
PRJ-2024003 | 2025-06 | Travel & Logistics | 4761 | 4779
PRJ-2024003 | 2025-06 | Project Management Overhead | 4166 | 3854
PRJ-2024003 | 2025-06 | Contingency | 2976 | 2644
PRJ-2024004 | 2024-08 | Equipment/CapEx | 375028 | 391506
PRJ-2024004 | 2024-08 | Last Mile Circuit Cost | 214302 | 276124
PRJ-2024004 | 2024-08 | Installation Labor | 160726 | 134981
PRJ-2024004 | 2024-08 | Vendor Management Fee | 107151 | 137030
PRJ-2024004 | 2024-08 | Travel & Logistics | 85721 | 87535
PRJ-2024004 | 2024-08 | Project Management Overhead | 75006 | 53799
PRJ-2024004 | 2024-08 | Contingency | 53576 | 63597
PRJ-2024004 | 2024-09 | Equipment/CapEx | 375028 | 282860
PRJ-2024004 | 2024-09 | Last Mile Circuit Cost | 214302 | 212128
PRJ-2024004 | 2024-09 | Installation Labor | 160726 | 124086
PRJ-2024004 | 2024-09 | Vendor Management Fee | 107151 | 130947
PRJ-2024004 | 2024-09 | Travel & Logistics | 85721 | 115011
PRJ-2024004 | 2024-09 | Project Management Overhead | 75006 | 75334
PRJ-2024004 | 2024-09 | Contingency | 53576 | 66384
PRJ-2024005 | 2024-11 | Equipment/CapEx | 83640 | 87744
PRJ-2024005 | 2024-11 | Last Mile Circuit Cost | 47794 | 56348
PRJ-2024005 | 2024-11 | Installation Labor | 35846 | 47299
PRJ-2024005 | 2024-11 | Vendor Management Fee | 23897 | 16838
PRJ-2024005 | 2024-11 | Travel & Logistics | 19118 | 17357
PRJ-2024005 | 2024-11 | Project Management Overhead | 16728 | 15331
PRJ-2024005 | 2024-11 | Contingency | 11949 | 12303
PRJ-2024005 | 2024-12 | Equipment/CapEx | 83640 | 106101
PRJ-2024005 | 2024-12 | Last Mile Circuit Cost | 47794 | 56881
PRJ-2024005 | 2024-12 | Installation Labor | 35846 | 35165
PRJ-2024005 | 2024-12 | Vendor Management Fee | 23897 | 20361
PRJ-2024005 | 2024-12 | Travel & Logistics | 19118 | 13578
PRJ-2024005 | 2024-12 | Project Management Overhead | 16728 | 13570
PRJ-2024005 | 2024-12 | Contingency | 11949 | 13139
PRJ-2024005 | 2025-01 | Equipment/CapEx | 83640 | 74797
PRJ-2024005 | 2025-01 | Last Mile Circuit Cost | 47794 | 48471
PRJ-2024005 | 2025-01 | Installation Labor | 35846 | 43893
PRJ-2024005 | 2025-01 | Vendor Management Fee | 23897 | 31373
PRJ-2024005 | 2025-01 | Travel & Logistics | 19118 | 15976
PRJ-2024005 | 2025-01 | Project Management Overhead | 16728 | 21029
PRJ-2024005 | 2025-01 | Contingency | 11949 | 10561
PRJ-2024005 | 2025-02 | Equipment/CapEx | 83640 | 95175
PRJ-2024005 | 2025-02 | Last Mile Circuit Cost | 47794 | 44672
PRJ-2024005 | 2025-02 | Installation Labor | 35846 | 29691
PRJ-2024005 | 2025-02 | Vendor Management Fee | 23897 | 26177
PRJ-2024005 | 2025-02 | Travel & Logistics | 19118 | 16874
PRJ-2024005 | 2025-02 | Project Management Overhead | 16728 | 12517
PRJ-2024005 | 2025-02 | Contingency | 11949 | 13527
PRJ-2024006 | 2024-07 | Equipment/CapEx | 1334288 | 957824
PRJ-2024006 | 2024-07 | Last Mile Circuit Cost | 762450 | 693470
PRJ-2024006 | 2024-07 | Installation Labor | 571838 | 519128
PRJ-2024006 | 2024-07 | Vendor Management Fee | 381225 | 397599
PRJ-2024006 | 2024-07 | Travel & Logistics | 304980 | 312961
PRJ-2024006 | 2024-07 | Project Management Overhead | 266858 | 215215
PRJ-2024006 | 2024-07 | Contingency | 190612 | 169510
PRJ-2024006 | 2024-08 | Equipment/CapEx | 1334288 | 1739786
PRJ-2024006 | 2024-08 | Last Mile Circuit Cost | 762450 | 755037
PRJ-2024006 | 2024-08 | Installation Labor | 571838 | 486774
PRJ-2024006 | 2024-08 | Vendor Management Fee | 381225 | 389907
PRJ-2024006 | 2024-08 | Travel & Logistics | 304980 | 263145
PRJ-2024006 | 2024-08 | Project Management Overhead | 266858 | 265218
PRJ-2024006 | 2024-08 | Contingency | 190612 | 194404
PRJ-2024006 | 2024-09 | Equipment/CapEx | 1334288 | 1570448
PRJ-2024006 | 2024-09 | Last Mile Circuit Cost | 762450 | 810817
PRJ-2024006 | 2024-09 | Installation Labor | 571838 | 670165
PRJ-2024006 | 2024-09 | Vendor Management Fee | 381225 | 513709
PRJ-2024006 | 2024-09 | Travel & Logistics | 304980 | 342422
PRJ-2024006 | 2024-09 | Project Management Overhead | 266858 | 254918
PRJ-2024006 | 2024-09 | Contingency | 190612 | 215187
PRJ-2024006 | 2024-10 | Equipment/CapEx | 1334288 | 1654524
PRJ-2024006 | 2024-10 | Last Mile Circuit Cost | 762450 | 702089
PRJ-2024006 | 2024-10 | Installation Labor | 571838 | 589827
PRJ-2024006 | 2024-10 | Vendor Management Fee | 381225 | 346631
PRJ-2024006 | 2024-10 | Travel & Logistics | 304980 | 355798
PRJ-2024006 | 2024-10 | Project Management Overhead | 266858 | 188149
PRJ-2024006 | 2024-10 | Contingency | 190612 | 195074
PRJ-2024006 | 2024-11 | Equipment/CapEx | 1334288 | 1075734
PRJ-2024006 | 2024-11 | Last Mile Circuit Cost | 762450 | 616478
PRJ-2024006 | 2024-11 | Installation Labor | 571838 | 638632
PRJ-2024006 | 2024-11 | Vendor Management Fee | 381225 | 510169
PRJ-2024006 | 2024-11 | Travel & Logistics | 304980 | 261534
PRJ-2024006 | 2024-11 | Project Management Overhead | 266858 | 312571
PRJ-2024006 | 2024-11 | Contingency | 190612 | 201387
PRJ-2024006 | 2024-12 | Equipment/CapEx | 1334288 | 1423765
PRJ-2024006 | 2024-12 | Last Mile Circuit Cost | 762450 | 592098
PRJ-2024006 | 2024-12 | Installation Labor | 571838 | 656608
PRJ-2024006 | 2024-12 | Vendor Management Fee | 381225 | 491801
PRJ-2024006 | 2024-12 | Travel & Logistics | 304980 | 239343
PRJ-2024006 | 2024-12 | Project Management Overhead | 266858 | 249419
PRJ-2024006 | 2024-12 | Contingency | 190612 | 144578
PRJ-2024007 | 2024-12 | Equipment/CapEx | 2341164 | 1878720
PRJ-2024007 | 2024-12 | Last Mile Circuit Cost | 1337808 | 1655097
PRJ-2024007 | 2024-12 | Installation Labor | 1003356 | 869059
PRJ-2024007 | 2024-12 | Vendor Management Fee | 668904 | 653964
PRJ-2024007 | 2024-12 | Travel & Logistics | 535123 | 442569
PRJ-2024007 | 2024-12 | Project Management Overhead | 468233 | 444437
PRJ-2024007 | 2024-12 | Contingency | 334452 | 240863
PRJ-2024007 | 2025-01 | Equipment/CapEx | 2341164 | 2986779
PRJ-2024007 | 2025-01 | Last Mile Circuit Cost | 1337808 | 1455200
PRJ-2024007 | 2025-01 | Installation Labor | 1003356 | 939663
PRJ-2024007 | 2025-01 | Vendor Management Fee | 668904 | 545960
PRJ-2024007 | 2025-01 | Travel & Logistics | 535123 | 389006
PRJ-2024007 | 2025-01 | Project Management Overhead | 468233 | 423572
PRJ-2024007 | 2025-01 | Contingency | 334452 | 248496
PRJ-2024007 | 2025-02 | Equipment/CapEx | 2341164 | 2352616
PRJ-2024007 | 2025-02 | Last Mile Circuit Cost | 1337808 | 1556696
PRJ-2024007 | 2025-02 | Installation Labor | 1003356 | 880502
PRJ-2024007 | 2025-02 | Vendor Management Fee | 668904 | 881700
PRJ-2024007 | 2025-02 | Travel & Logistics | 535123 | 653536
PRJ-2024007 | 2025-02 | Project Management Overhead | 468233 | 546596
PRJ-2024007 | 2025-02 | Contingency | 334452 | 334311
PRJ-2024007 | 2025-03 | Equipment/CapEx | 2341164 | 2655795
PRJ-2024007 | 2025-03 | Last Mile Circuit Cost | 1337808 | 1172570
PRJ-2024007 | 2025-03 | Installation Labor | 1003356 | 931685
PRJ-2024007 | 2025-03 | Vendor Management Fee | 668904 | 821279
PRJ-2024007 | 2025-03 | Travel & Logistics | 535123 | 527608
PRJ-2024007 | 2025-03 | Project Management Overhead | 468233 | 460348
PRJ-2024007 | 2025-03 | Contingency | 334452 | 345034
PRJ-2024007 | 2025-04 | Equipment/CapEx | 2341164 | 2255946
PRJ-2024007 | 2025-04 | Last Mile Circuit Cost | 1337808 | 1106244
PRJ-2024007 | 2025-04 | Installation Labor | 1003356 | 1131070
PRJ-2024007 | 2025-04 | Vendor Management Fee | 668904 | 539333
PRJ-2024007 | 2025-04 | Travel & Logistics | 535123 | 706878
PRJ-2024007 | 2025-04 | Project Management Overhead | 468233 | 569164
PRJ-2024007 | 2025-04 | Contingency | 334452 | 414436
PRJ-2024008 | 2024-11 | Equipment/CapEx | 237518 | 235402
PRJ-2024008 | 2024-11 | Last Mile Circuit Cost | 135725 | 153255
PRJ-2024008 | 2024-11 | Installation Labor | 101794 | 72926
PRJ-2024008 | 2024-11 | Vendor Management Fee | 67862 | 75502
PRJ-2024008 | 2024-11 | Travel & Logistics | 54290 | 57165
PRJ-2024008 | 2024-11 | Project Management Overhead | 47504 | 35730
PRJ-2024008 | 2024-11 | Contingency | 33931 | 29187
PRJ-2024008 | 2024-12 | Equipment/CapEx | 237518 | 317973
PRJ-2024008 | 2024-12 | Last Mile Circuit Cost | 135725 | 140990
PRJ-2024008 | 2024-12 | Installation Labor | 101794 | 109470
PRJ-2024008 | 2024-12 | Vendor Management Fee | 67862 | 87817
PRJ-2024008 | 2024-12 | Travel & Logistics | 54290 | 41525
PRJ-2024008 | 2024-12 | Project Management Overhead | 47504 | 56505
PRJ-2024008 | 2024-12 | Contingency | 33931 | 42378
PRJ-2024008 | 2025-01 | Equipment/CapEx | 237518 | 293006
PRJ-2024008 | 2025-01 | Last Mile Circuit Cost | 135725 | 124585
PRJ-2024008 | 2025-01 | Installation Labor | 101794 | 98177
PRJ-2024008 | 2025-01 | Vendor Management Fee | 67862 | 82604
PRJ-2024008 | 2025-01 | Travel & Logistics | 54290 | 52193
PRJ-2024008 | 2025-01 | Project Management Overhead | 47504 | 46807
PRJ-2024008 | 2025-01 | Contingency | 33931 | 43648
PRJ-2024008 | 2025-02 | Equipment/CapEx | 237518 | 256498
PRJ-2024008 | 2025-02 | Last Mile Circuit Cost | 135725 | 124855
PRJ-2024008 | 2025-02 | Installation Labor | 101794 | 88986
PRJ-2024008 | 2025-02 | Vendor Management Fee | 67862 | 65108
PRJ-2024008 | 2025-02 | Travel & Logistics | 54290 | 39026
PRJ-2024008 | 2025-02 | Project Management Overhead | 47504 | 48195
PRJ-2024008 | 2025-02 | Contingency | 33931 | 36285
PRJ-2024008 | 2025-03 | Equipment/CapEx | 237518 | 288251
PRJ-2024008 | 2025-03 | Last Mile Circuit Cost | 135725 | 134694
PRJ-2024008 | 2025-03 | Installation Labor | 101794 | 91530
PRJ-2024008 | 2025-03 | Vendor Management Fee | 67862 | 50816
PRJ-2024008 | 2025-03 | Travel & Logistics | 54290 | 69745
PRJ-2024008 | 2025-03 | Project Management Overhead | 47504 | 60116
PRJ-2024008 | 2025-03 | Contingency | 33931 | 34045
PRJ-2024009 | 2024-08 | Equipment/CapEx | 1824952 | 2224703
PRJ-2024009 | 2024-08 | Last Mile Circuit Cost | 1042830 | 817379
PRJ-2024009 | 2024-08 | Installation Labor | 782122 | 625049
PRJ-2024009 | 2024-08 | Vendor Management Fee | 521415 | 434685
PRJ-2024009 | 2024-08 | Travel & Logistics | 417132 | 293130
PRJ-2024009 | 2024-08 | Project Management Overhead | 364991 | 422506
PRJ-2024009 | 2024-08 | Contingency | 260708 | 241807
PRJ-2024009 | 2024-09 | Equipment/CapEx | 1824952 | 1550301
PRJ-2024009 | 2024-09 | Last Mile Circuit Cost | 1042830 | 1036443
PRJ-2024009 | 2024-09 | Installation Labor | 782122 | 991797
PRJ-2024009 | 2024-09 | Vendor Management Fee | 521415 | 514260
PRJ-2024009 | 2024-09 | Travel & Logistics | 417132 | 470161
PRJ-2024009 | 2024-09 | Project Management Overhead | 364991 | 332027
PRJ-2024009 | 2024-09 | Contingency | 260708 | 214624
PRJ-2024010 | 2024-11 | Equipment/CapEx | 14485 | 11540
PRJ-2024010 | 2024-11 | Last Mile Circuit Cost | 8277 | 9115
PRJ-2024010 | 2024-11 | Installation Labor | 6208 | 5771
PRJ-2024010 | 2024-11 | Vendor Management Fee | 4138 | 4479
PRJ-2024010 | 2024-11 | Travel & Logistics | 3311 | 3802
PRJ-2024010 | 2024-11 | Project Management Overhead | 2897 | 3030
PRJ-2024010 | 2024-11 | Contingency | 2069 | 2153
PRJ-2024010 | 2024-12 | Equipment/CapEx | 14485 | 15371
PRJ-2024010 | 2024-12 | Last Mile Circuit Cost | 8277 | 10011
PRJ-2024010 | 2024-12 | Installation Labor | 6208 | 5801
PRJ-2024010 | 2024-12 | Vendor Management Fee | 4138 | 4247
PRJ-2024010 | 2024-12 | Travel & Logistics | 3311 | 2693
PRJ-2024010 | 2024-12 | Project Management Overhead | 2897 | 2891
PRJ-2024010 | 2024-12 | Contingency | 2069 | 1679
PRJ-2024010 | 2025-01 | Equipment/CapEx | 14485 | 15861
PRJ-2024010 | 2025-01 | Last Mile Circuit Cost | 8277 | 10903
PRJ-2024010 | 2025-01 | Installation Labor | 6208 | 5213
PRJ-2024010 | 2025-01 | Vendor Management Fee | 4138 | 4847
PRJ-2024010 | 2025-01 | Travel & Logistics | 3311 | 3825
PRJ-2024010 | 2025-01 | Project Management Overhead | 2897 | 3707
PRJ-2024010 | 2025-01 | Contingency | 2069 | 2292
PRJ-2024010 | 2025-02 | Equipment/CapEx | 14485 | 11678
PRJ-2024010 | 2025-02 | Last Mile Circuit Cost | 8277 | 10642
PRJ-2024010 | 2025-02 | Installation Labor | 6208 | 4467
PRJ-2024010 | 2025-02 | Vendor Management Fee | 4138 | 5091
PRJ-2024010 | 2025-02 | Travel & Logistics | 3311 | 2840
PRJ-2024010 | 2025-02 | Project Management Overhead | 2897 | 2975
PRJ-2024010 | 2025-02 | Contingency | 2069 | 2344
PRJ-2024010 | 2025-03 | Equipment/CapEx | 14485 | 11979
PRJ-2024010 | 2025-03 | Last Mile Circuit Cost | 8277 | 9057
PRJ-2024010 | 2025-03 | Installation Labor | 6208 | 6478
PRJ-2024010 | 2025-03 | Vendor Management Fee | 4138 | 4957
PRJ-2024010 | 2025-03 | Travel & Logistics | 3311 | 2933
PRJ-2024010 | 2025-03 | Project Management Overhead | 2897 | 2566
PRJ-2024010 | 2025-03 | Contingency | 2069 | 1630
PRJ-2024010 | 2025-04 | Equipment/CapEx | 14485 | 14422
PRJ-2024010 | 2025-04 | Last Mile Circuit Cost | 8277 | 8944
PRJ-2024010 | 2025-04 | Installation Labor | 6208 | 5284
PRJ-2024010 | 2025-04 | Vendor Management Fee | 4138 | 4841
PRJ-2024010 | 2025-04 | Travel & Logistics | 3311 | 3163
PRJ-2024010 | 2025-04 | Project Management Overhead | 2897 | 3303
PRJ-2024010 | 2025-04 | Contingency | 2069 | 1624
PRJ-2024011 | 2024-12 | Equipment/CapEx | 40682 | 34817
PRJ-2024011 | 2024-12 | Last Mile Circuit Cost | 23247 | 17443
PRJ-2024011 | 2024-12 | Installation Labor | 17435 | 20512
PRJ-2024011 | 2024-12 | Vendor Management Fee | 11624 | 11282
PRJ-2024011 | 2024-12 | Travel & Logistics | 9299 | 9253
PRJ-2024011 | 2024-12 | Project Management Overhead | 8136 | 6574
PRJ-2024011 | 2024-12 | Contingency | 5812 | 7737
PRJ-2024011 | 2025-01 | Equipment/CapEx | 40682 | 40994
PRJ-2024011 | 2025-01 | Last Mile Circuit Cost | 23247 | 21312
PRJ-2024011 | 2025-01 | Installation Labor | 17435 | 23318
PRJ-2024011 | 2025-01 | Vendor Management Fee | 11624 | 9842
PRJ-2024011 | 2025-01 | Travel & Logistics | 9299 | 7928
PRJ-2024011 | 2025-01 | Project Management Overhead | 8136 | 7344
PRJ-2024011 | 2025-01 | Contingency | 5812 | 4079
PRJ-2024011 | 2025-02 | Equipment/CapEx | 40682 | 38802
PRJ-2024011 | 2025-02 | Last Mile Circuit Cost | 23247 | 18661
PRJ-2024011 | 2025-02 | Installation Labor | 17435 | 21861
PRJ-2024011 | 2025-02 | Vendor Management Fee | 11624 | 11242
PRJ-2024011 | 2025-02 | Travel & Logistics | 9299 | 7684
PRJ-2024011 | 2025-02 | Project Management Overhead | 8136 | 7124
PRJ-2024011 | 2025-02 | Contingency | 5812 | 4291
PRJ-2024011 | 2025-03 | Equipment/CapEx | 40682 | 35401
PRJ-2024011 | 2025-03 | Last Mile Circuit Cost | 23247 | 29533
PRJ-2024011 | 2025-03 | Installation Labor | 17435 | 13246
PRJ-2024011 | 2025-03 | Vendor Management Fee | 11624 | 11146
PRJ-2024011 | 2025-03 | Travel & Logistics | 9299 | 7695
PRJ-2024011 | 2025-03 | Project Management Overhead | 8136 | 10361
PRJ-2024011 | 2025-03 | Contingency | 5812 | 7789
PRJ-2024011 | 2025-04 | Equipment/CapEx | 40682 | 33159
PRJ-2024011 | 2025-04 | Last Mile Circuit Cost | 23247 | 29474
PRJ-2024011 | 2025-04 | Installation Labor | 17435 | 14605
PRJ-2024011 | 2025-04 | Vendor Management Fee | 11624 | 9431
PRJ-2024011 | 2025-04 | Travel & Logistics | 9299 | 11760
PRJ-2024011 | 2025-04 | Project Management Overhead | 8136 | 8639
PRJ-2024011 | 2025-04 | Contingency | 5812 | 4756
PRJ-2024011 | 2025-05 | Equipment/CapEx | 40682 | 34220
PRJ-2024011 | 2025-05 | Last Mile Circuit Cost | 23247 | 21780
PRJ-2024011 | 2025-05 | Installation Labor | 17435 | 12569
PRJ-2024011 | 2025-05 | Vendor Management Fee | 11624 | 10221
PRJ-2024011 | 2025-05 | Travel & Logistics | 9299 | 8708
PRJ-2024011 | 2025-05 | Project Management Overhead | 8136 | 9922
PRJ-2024011 | 2025-05 | Contingency | 5812 | 4511
PRJ-2024012 | 2024-08 | Equipment/CapEx | 165187 | 213098
PRJ-2024012 | 2024-08 | Last Mile Circuit Cost | 94392 | 106103
PRJ-2024012 | 2024-08 | Installation Labor | 70794 | 63659
PRJ-2024012 | 2024-08 | Vendor Management Fee | 47196 | 41348
PRJ-2024012 | 2024-08 | Travel & Logistics | 37757 | 33559
PRJ-2024012 | 2024-08 | Project Management Overhead | 33037 | 26289
PRJ-2024012 | 2024-08 | Contingency | 23598 | 17707
PRJ-2024012 | 2024-09 | Equipment/CapEx | 165187 | 165794
PRJ-2024012 | 2024-09 | Last Mile Circuit Cost | 94392 | 82342
PRJ-2024012 | 2024-09 | Installation Labor | 70794 | 76055
PRJ-2024012 | 2024-09 | Vendor Management Fee | 47196 | 42027
PRJ-2024012 | 2024-09 | Travel & Logistics | 37757 | 40361
PRJ-2024012 | 2024-09 | Project Management Overhead | 33037 | 33392
PRJ-2024012 | 2024-09 | Contingency | 23598 | 20949
PRJ-2024013 | 2024-09 | Equipment/CapEx | 92468 | 110726
PRJ-2024013 | 2024-09 | Last Mile Circuit Cost | 52839 | 39771
PRJ-2024013 | 2024-09 | Installation Labor | 39629 | 42016
PRJ-2024013 | 2024-09 | Vendor Management Fee | 26420 | 30834
PRJ-2024013 | 2024-09 | Travel & Logistics | 21136 | 17263
PRJ-2024013 | 2024-09 | Project Management Overhead | 18494 | 20464
PRJ-2024013 | 2024-09 | Contingency | 13210 | 11825
PRJ-2024013 | 2024-10 | Equipment/CapEx | 92468 | 79011
PRJ-2024013 | 2024-10 | Last Mile Circuit Cost | 52839 | 40754
PRJ-2024013 | 2024-10 | Installation Labor | 39629 | 37196
PRJ-2024013 | 2024-10 | Vendor Management Fee | 26420 | 21266
PRJ-2024013 | 2024-10 | Travel & Logistics | 21136 | 16323
PRJ-2024013 | 2024-10 | Project Management Overhead | 18494 | 24710
PRJ-2024013 | 2024-10 | Contingency | 13210 | 12749
PRJ-2024013 | 2024-11 | Equipment/CapEx | 92468 | 109952
PRJ-2024013 | 2024-11 | Last Mile Circuit Cost | 52839 | 59026
PRJ-2024013 | 2024-11 | Installation Labor | 39629 | 32213
PRJ-2024013 | 2024-11 | Vendor Management Fee | 26420 | 22816
PRJ-2024013 | 2024-11 | Travel & Logistics | 21136 | 20117
PRJ-2024013 | 2024-11 | Project Management Overhead | 18494 | 15086
PRJ-2024013 | 2024-11 | Contingency | 13210 | 14366
PRJ-2024013 | 2024-12 | Equipment/CapEx | 92468 | 94847
PRJ-2024013 | 2024-12 | Last Mile Circuit Cost | 52839 | 52173
PRJ-2024013 | 2024-12 | Installation Labor | 39629 | 34262
PRJ-2024013 | 2024-12 | Vendor Management Fee | 26420 | 31003
PRJ-2024013 | 2024-12 | Travel & Logistics | 21136 | 19235
PRJ-2024013 | 2024-12 | Project Management Overhead | 18494 | 20781
PRJ-2024013 | 2024-12 | Contingency | 13210 | 14586
PRJ-2024013 | 2025-01 | Equipment/CapEx | 92468 | 96482
PRJ-2024013 | 2025-01 | Last Mile Circuit Cost | 52839 | 54017
PRJ-2024013 | 2025-01 | Installation Labor | 39629 | 47438
PRJ-2024013 | 2025-01 | Vendor Management Fee | 26420 | 28281
PRJ-2024013 | 2025-01 | Travel & Logistics | 21136 | 16420
PRJ-2024013 | 2025-01 | Project Management Overhead | 18494 | 15829
PRJ-2024013 | 2025-01 | Contingency | 13210 | 9265
PRJ-2024013 | 2025-02 | Equipment/CapEx | 92468 | 92659
PRJ-2024013 | 2025-02 | Last Mile Circuit Cost | 52839 | 64791
PRJ-2024013 | 2025-02 | Installation Labor | 39629 | 34466
PRJ-2024013 | 2025-02 | Vendor Management Fee | 26420 | 35350
PRJ-2024013 | 2025-02 | Travel & Logistics | 21136 | 23737
PRJ-2024013 | 2025-02 | Project Management Overhead | 18494 | 22525
PRJ-2024013 | 2025-02 | Contingency | 13210 | 11138
PRJ-2024014 | 2024-10 | Equipment/CapEx | 26184 | 23059
PRJ-2024014 | 2024-10 | Last Mile Circuit Cost | 14962 | 19065
PRJ-2024014 | 2024-10 | Installation Labor | 11222 | 9149
PRJ-2024014 | 2024-10 | Vendor Management Fee | 7481 | 8579
PRJ-2024014 | 2024-10 | Travel & Logistics | 5985 | 5102
PRJ-2024014 | 2024-10 | Project Management Overhead | 5237 | 4822
PRJ-2024014 | 2024-10 | Contingency | 3740 | 3750
PRJ-2024014 | 2024-11 | Equipment/CapEx | 26184 | 33453
PRJ-2024014 | 2024-11 | Last Mile Circuit Cost | 14962 | 12141
PRJ-2024014 | 2024-11 | Installation Labor | 11222 | 10220
PRJ-2024014 | 2024-11 | Vendor Management Fee | 7481 | 6193
PRJ-2024014 | 2024-11 | Travel & Logistics | 5985 | 4486
PRJ-2024014 | 2024-11 | Project Management Overhead | 5237 | 6131
PRJ-2024014 | 2024-11 | Contingency | 3740 | 2842
PRJ-2024014 | 2024-12 | Equipment/CapEx | 26184 | 22600
PRJ-2024014 | 2024-12 | Last Mile Circuit Cost | 14962 | 20001
PRJ-2024014 | 2024-12 | Installation Labor | 11222 | 14449
PRJ-2024014 | 2024-12 | Vendor Management Fee | 7481 | 6397
PRJ-2024014 | 2024-12 | Travel & Logistics | 5985 | 6050
PRJ-2024014 | 2024-12 | Project Management Overhead | 5237 | 5844
PRJ-2024014 | 2024-12 | Contingency | 3740 | 4626
PRJ-2024014 | 2025-01 | Equipment/CapEx | 26184 | 24863
PRJ-2024014 | 2025-01 | Last Mile Circuit Cost | 14962 | 12107
PRJ-2024014 | 2025-01 | Installation Labor | 11222 | 9355
PRJ-2024014 | 2025-01 | Vendor Management Fee | 7481 | 5467
PRJ-2024014 | 2025-01 | Travel & Logistics | 5985 | 7371
PRJ-2024014 | 2025-01 | Project Management Overhead | 5237 | 3907
PRJ-2024014 | 2025-01 | Contingency | 3740 | 3272
PRJ-2024014 | 2025-02 | Equipment/CapEx | 26184 | 25404
PRJ-2024014 | 2025-02 | Last Mile Circuit Cost | 14962 | 14614
PRJ-2024014 | 2025-02 | Installation Labor | 11222 | 13226
PRJ-2024014 | 2025-02 | Vendor Management Fee | 7481 | 8107
PRJ-2024014 | 2025-02 | Travel & Logistics | 5985 | 4634
PRJ-2024014 | 2025-02 | Project Management Overhead | 5237 | 3756
PRJ-2024014 | 2025-02 | Contingency | 3740 | 4585
PRJ-2024014 | 2025-03 | Equipment/CapEx | 26184 | 28454
PRJ-2024014 | 2025-03 | Last Mile Circuit Cost | 14962 | 14492
PRJ-2024014 | 2025-03 | Installation Labor | 11222 | 13325
PRJ-2024014 | 2025-03 | Vendor Management Fee | 7481 | 9677
PRJ-2024014 | 2025-03 | Travel & Logistics | 5985 | 6551
PRJ-2024014 | 2025-03 | Project Management Overhead | 5237 | 6664
PRJ-2024014 | 2025-03 | Contingency | 3740 | 2976
PRJ-2024014 | 2025-04 | Equipment/CapEx | 26184 | 32936
PRJ-2024014 | 2025-04 | Last Mile Circuit Cost | 14962 | 11094
PRJ-2024014 | 2025-04 | Installation Labor | 11222 | 14513
PRJ-2024014 | 2025-04 | Vendor Management Fee | 7481 | 8143
PRJ-2024014 | 2025-04 | Travel & Logistics | 5985 | 6913
PRJ-2024014 | 2025-04 | Project Management Overhead | 5237 | 3792
PRJ-2024014 | 2025-04 | Contingency | 3740 | 3441
PRJ-2024014 | 2025-05 | Equipment/CapEx | 26184 | 25557
PRJ-2024014 | 2025-05 | Last Mile Circuit Cost | 14962 | 18735
PRJ-2024014 | 2025-05 | Installation Labor | 11222 | 9797
PRJ-2024014 | 2025-05 | Vendor Management Fee | 7481 | 5643
PRJ-2024014 | 2025-05 | Travel & Logistics | 5985 | 6451
PRJ-2024014 | 2025-05 | Project Management Overhead | 5237 | 4014
PRJ-2024014 | 2025-05 | Contingency | 3740 | 4807
PRJ-2024015 | 2024-09 | Equipment/CapEx | 981750 | 890421
PRJ-2024015 | 2024-09 | Last Mile Circuit Cost | 561000 | 443311
PRJ-2024015 | 2024-09 | Installation Labor | 420750 | 565534
PRJ-2024015 | 2024-09 | Vendor Management Fee | 280500 | 211191
PRJ-2024015 | 2024-09 | Travel & Logistics | 224400 | 163512
PRJ-2024015 | 2024-09 | Project Management Overhead | 196350 | 253557
PRJ-2024015 | 2024-09 | Contingency | 140250 | 167599
PRJ-2024015 | 2024-10 | Equipment/CapEx | 981750 | 806714
PRJ-2024015 | 2024-10 | Last Mile Circuit Cost | 561000 | 751094
PRJ-2024015 | 2024-10 | Installation Labor | 420750 | 339666
PRJ-2024015 | 2024-10 | Vendor Management Fee | 280500 | 365612
PRJ-2024015 | 2024-10 | Travel & Logistics | 224400 | 247657
PRJ-2024015 | 2024-10 | Project Management Overhead | 196350 | 190490
PRJ-2024015 | 2024-10 | Contingency | 140250 | 188884
PRJ-2024015 | 2024-11 | Equipment/CapEx | 981750 | 1236056
PRJ-2024015 | 2024-11 | Last Mile Circuit Cost | 561000 | 743466
PRJ-2024015 | 2024-11 | Installation Labor | 420750 | 469248
PRJ-2024015 | 2024-11 | Vendor Management Fee | 280500 | 216920
PRJ-2024015 | 2024-11 | Travel & Logistics | 224400 | 182263
PRJ-2024015 | 2024-11 | Project Management Overhead | 196350 | 208174
PRJ-2024015 | 2024-11 | Contingency | 140250 | 179179
PRJ-2024015 | 2024-12 | Equipment/CapEx | 981750 | 855868
PRJ-2024015 | 2024-12 | Last Mile Circuit Cost | 561000 | 648690
PRJ-2024015 | 2024-12 | Installation Labor | 420750 | 444395
PRJ-2024015 | 2024-12 | Vendor Management Fee | 280500 | 222060
PRJ-2024015 | 2024-12 | Travel & Logistics | 224400 | 162431
PRJ-2024015 | 2024-12 | Project Management Overhead | 196350 | 196421
PRJ-2024015 | 2024-12 | Contingency | 140250 | 134187
PRJ-2024016 | 2024-10 | Equipment/CapEx | 123487 | 117001
PRJ-2024016 | 2024-10 | Last Mile Circuit Cost | 70564 | 77122
PRJ-2024016 | 2024-10 | Installation Labor | 52923 | 58947
PRJ-2024016 | 2024-10 | Vendor Management Fee | 35282 | 46826
PRJ-2024016 | 2024-10 | Travel & Logistics | 28226 | 29028
PRJ-2024016 | 2024-10 | Project Management Overhead | 24697 | 21482
PRJ-2024016 | 2024-10 | Contingency | 17641 | 12720
PRJ-2024016 | 2024-11 | Equipment/CapEx | 123487 | 91390
PRJ-2024016 | 2024-11 | Last Mile Circuit Cost | 70564 | 52488
PRJ-2024016 | 2024-11 | Installation Labor | 52923 | 39962
PRJ-2024016 | 2024-11 | Vendor Management Fee | 35282 | 43919
PRJ-2024016 | 2024-11 | Travel & Logistics | 28226 | 22261
PRJ-2024016 | 2024-11 | Project Management Overhead | 24697 | 23585
PRJ-2024016 | 2024-11 | Contingency | 17641 | 19706
PRJ-2024016 | 2024-12 | Equipment/CapEx | 123487 | 104327
PRJ-2024016 | 2024-12 | Last Mile Circuit Cost | 70564 | 71793
PRJ-2024016 | 2024-12 | Installation Labor | 52923 | 45532
PRJ-2024016 | 2024-12 | Vendor Management Fee | 35282 | 44052
PRJ-2024016 | 2024-12 | Travel & Logistics | 28226 | 36588
PRJ-2024016 | 2024-12 | Project Management Overhead | 24697 | 18375
PRJ-2024016 | 2024-12 | Contingency | 17641 | 23583
PRJ-2024017 | 2024-07 | Equipment/CapEx | 18188 | 19574
PRJ-2024017 | 2024-07 | Last Mile Circuit Cost | 10393 | 8421
PRJ-2024017 | 2024-07 | Installation Labor | 7795 | 9026
PRJ-2024017 | 2024-07 | Vendor Management Fee | 5196 | 6485
PRJ-2024017 | 2024-07 | Travel & Logistics | 4157 | 4909
PRJ-2024017 | 2024-07 | Project Management Overhead | 3638 | 4222
PRJ-2024017 | 2024-07 | Contingency | 2598 | 2831
PRJ-2024017 | 2024-08 | Equipment/CapEx | 18188 | 18134
PRJ-2024017 | 2024-08 | Last Mile Circuit Cost | 10393 | 9462
PRJ-2024017 | 2024-08 | Installation Labor | 7795 | 7840
PRJ-2024017 | 2024-08 | Vendor Management Fee | 5196 | 5113
PRJ-2024017 | 2024-08 | Travel & Logistics | 4157 | 5330
PRJ-2024017 | 2024-08 | Project Management Overhead | 3638 | 4669
PRJ-2024017 | 2024-08 | Contingency | 2598 | 3005
PRJ-2024017 | 2024-09 | Equipment/CapEx | 18188 | 19929
PRJ-2024017 | 2024-09 | Last Mile Circuit Cost | 10393 | 8426
PRJ-2024017 | 2024-09 | Installation Labor | 7795 | 6620
PRJ-2024017 | 2024-09 | Vendor Management Fee | 5196 | 4786
PRJ-2024017 | 2024-09 | Travel & Logistics | 4157 | 4258
PRJ-2024017 | 2024-09 | Project Management Overhead | 3638 | 3905
PRJ-2024017 | 2024-09 | Contingency | 2598 | 2934
PRJ-2024017 | 2024-10 | Equipment/CapEx | 18188 | 19834
PRJ-2024017 | 2024-10 | Last Mile Circuit Cost | 10393 | 10887
PRJ-2024017 | 2024-10 | Installation Labor | 7795 | 9671
PRJ-2024017 | 2024-10 | Vendor Management Fee | 5196 | 4955
PRJ-2024017 | 2024-10 | Travel & Logistics | 4157 | 4084
PRJ-2024017 | 2024-10 | Project Management Overhead | 3638 | 3655
PRJ-2024017 | 2024-10 | Contingency | 2598 | 3035
PRJ-2024018 | 2024-08 | Equipment/CapEx | 29046 | 22214
PRJ-2024018 | 2024-08 | Last Mile Circuit Cost | 16598 | 15599
PRJ-2024018 | 2024-08 | Installation Labor | 12448 | 10481
PRJ-2024018 | 2024-08 | Vendor Management Fee | 8299 | 7280
PRJ-2024018 | 2024-08 | Travel & Logistics | 6639 | 7550
PRJ-2024018 | 2024-08 | Project Management Overhead | 5809 | 4457
PRJ-2024018 | 2024-08 | Contingency | 4149 | 2917
PRJ-2024018 | 2024-09 | Equipment/CapEx | 29046 | 25632
PRJ-2024018 | 2024-09 | Last Mile Circuit Cost | 16598 | 20756
PRJ-2024018 | 2024-09 | Installation Labor | 12448 | 13324
PRJ-2024018 | 2024-09 | Vendor Management Fee | 8299 | 11070
PRJ-2024018 | 2024-09 | Travel & Logistics | 6639 | 6119
PRJ-2024018 | 2024-09 | Project Management Overhead | 5809 | 7119
PRJ-2024018 | 2024-09 | Contingency | 4149 | 4906
PRJ-2024018 | 2024-10 | Equipment/CapEx | 29046 | 36844
PRJ-2024018 | 2024-10 | Last Mile Circuit Cost | 16598 | 17344
PRJ-2024018 | 2024-10 | Installation Labor | 12448 | 14924
PRJ-2024018 | 2024-10 | Vendor Management Fee | 8299 | 9222
PRJ-2024018 | 2024-10 | Travel & Logistics | 6639 | 7318
PRJ-2024018 | 2024-10 | Project Management Overhead | 5809 | 7706
PRJ-2024018 | 2024-10 | Contingency | 4149 | 4052
PRJ-2024018 | 2024-11 | Equipment/CapEx | 29046 | 20617
PRJ-2024018 | 2024-11 | Last Mile Circuit Cost | 16598 | 18279
PRJ-2024018 | 2024-11 | Installation Labor | 12448 | 10425
PRJ-2024018 | 2024-11 | Vendor Management Fee | 8299 | 7467
PRJ-2024018 | 2024-11 | Travel & Logistics | 6639 | 6667
PRJ-2024018 | 2024-11 | Project Management Overhead | 5809 | 7530
PRJ-2024018 | 2024-11 | Contingency | 4149 | 2951
PRJ-2024018 | 2024-12 | Equipment/CapEx | 29046 | 29511
PRJ-2024018 | 2024-12 | Last Mile Circuit Cost | 16598 | 20737
PRJ-2024018 | 2024-12 | Installation Labor | 12448 | 15164
PRJ-2024018 | 2024-12 | Vendor Management Fee | 8299 | 6279
PRJ-2024018 | 2024-12 | Travel & Logistics | 6639 | 5030
PRJ-2024018 | 2024-12 | Project Management Overhead | 5809 | 5165
PRJ-2024018 | 2024-12 | Contingency | 4149 | 3955
PRJ-2024018 | 2025-01 | Equipment/CapEx | 29046 | 32855
PRJ-2024018 | 2025-01 | Last Mile Circuit Cost | 16598 | 15715
PRJ-2024018 | 2025-01 | Installation Labor | 12448 | 15498
PRJ-2024018 | 2025-01 | Vendor Management Fee | 8299 | 7350
PRJ-2024018 | 2025-01 | Travel & Logistics | 6639 | 5095
PRJ-2024018 | 2025-01 | Project Management Overhead | 5809 | 4155
PRJ-2024018 | 2025-01 | Contingency | 4149 | 5022
PRJ-2024018 | 2025-02 | Equipment/CapEx | 29046 | 36467
PRJ-2024018 | 2025-02 | Last Mile Circuit Cost | 16598 | 15343
PRJ-2024018 | 2025-02 | Installation Labor | 12448 | 11088
PRJ-2024018 | 2025-02 | Vendor Management Fee | 8299 | 8515
PRJ-2024018 | 2025-02 | Travel & Logistics | 6639 | 8888
PRJ-2024018 | 2025-02 | Project Management Overhead | 5809 | 6357
PRJ-2024018 | 2025-02 | Contingency | 4149 | 3536
PRJ-2024019 | 2024-07 | Equipment/CapEx | 571158 | 550272
PRJ-2024019 | 2024-07 | Last Mile Circuit Cost | 326376 | 279463
PRJ-2024019 | 2024-07 | Installation Labor | 244782 | 196403
PRJ-2024019 | 2024-07 | Vendor Management Fee | 163188 | 143552
PRJ-2024019 | 2024-07 | Travel & Logistics | 130550 | 112105
PRJ-2024019 | 2024-07 | Project Management Overhead | 114232 | 137349
PRJ-2024019 | 2024-07 | Contingency | 81594 | 97624
PRJ-2024019 | 2024-07 | Equipment/CapEx | 571158 | 750724
PRJ-2024019 | 2024-07 | Last Mile Circuit Cost | 326376 | 298652
PRJ-2024019 | 2024-07 | Installation Labor | 244782 | 302287
PRJ-2024019 | 2024-07 | Vendor Management Fee | 163188 | 190894
PRJ-2024019 | 2024-07 | Travel & Logistics | 130550 | 126801
PRJ-2024019 | 2024-07 | Project Management Overhead | 114232 | 130586
PRJ-2024019 | 2024-07 | Contingency | 81594 | 76343
PRJ-2024019 | 2024-08 | Equipment/CapEx | 571158 | 687186
PRJ-2024019 | 2024-08 | Last Mile Circuit Cost | 326376 | 325784
PRJ-2024019 | 2024-08 | Installation Labor | 244782 | 206910
PRJ-2024019 | 2024-08 | Vendor Management Fee | 163188 | 207096
PRJ-2024019 | 2024-08 | Travel & Logistics | 130550 | 112770
PRJ-2024019 | 2024-08 | Project Management Overhead | 114232 | 140285
PRJ-2024019 | 2024-08 | Contingency | 81594 | 99486
PRJ-2024019 | 2024-09 | Equipment/CapEx | 571158 | 530722
PRJ-2024019 | 2024-09 | Last Mile Circuit Cost | 326376 | 423739
PRJ-2024019 | 2024-09 | Installation Labor | 244782 | 195963
PRJ-2024019 | 2024-09 | Vendor Management Fee | 163188 | 122298
PRJ-2024019 | 2024-09 | Travel & Logistics | 130550 | 105856
PRJ-2024019 | 2024-09 | Project Management Overhead | 114232 | 104536
PRJ-2024019 | 2024-09 | Contingency | 81594 | 100487
PRJ-2024019 | 2024-10 | Equipment/CapEx | 571158 | 604300
PRJ-2024019 | 2024-10 | Last Mile Circuit Cost | 326376 | 290078
PRJ-2024019 | 2024-10 | Installation Labor | 244782 | 244213
PRJ-2024019 | 2024-10 | Vendor Management Fee | 163188 | 177087
PRJ-2024019 | 2024-10 | Travel & Logistics | 130550 | 145713
PRJ-2024019 | 2024-10 | Project Management Overhead | 114232 | 86072
PRJ-2024019 | 2024-10 | Contingency | 81594 | 83198
PRJ-2024020 | 2024-12 | Equipment/CapEx | 1043290 | 950441
PRJ-2024020 | 2024-12 | Last Mile Circuit Cost | 596166 | 483153
PRJ-2024020 | 2024-12 | Installation Labor | 447124 | 358848
PRJ-2024020 | 2024-12 | Vendor Management Fee | 298083 | 301717
PRJ-2024020 | 2024-12 | Travel & Logistics | 238466 | 283413
PRJ-2024020 | 2024-12 | Project Management Overhead | 208658 | 269181
PRJ-2024020 | 2024-12 | Contingency | 149041 | 164506
PRJ-2024020 | 2025-01 | Equipment/CapEx | 1043290 | 1111829
PRJ-2024020 | 2025-01 | Last Mile Circuit Cost | 596166 | 712126
PRJ-2024020 | 2025-01 | Installation Labor | 447124 | 601312
PRJ-2024020 | 2025-01 | Vendor Management Fee | 298083 | 272162
PRJ-2024020 | 2025-01 | Travel & Logistics | 238466 | 192054
PRJ-2024020 | 2025-01 | Project Management Overhead | 208658 | 252737
PRJ-2024020 | 2025-01 | Contingency | 149041 | 142829
PRJ-2024020 | 2025-02 | Equipment/CapEx | 1043290 | 903089
PRJ-2024020 | 2025-02 | Last Mile Circuit Cost | 596166 | 755775
PRJ-2024020 | 2025-02 | Installation Labor | 447124 | 589147
PRJ-2024020 | 2025-02 | Vendor Management Fee | 298083 | 317885
PRJ-2024020 | 2025-02 | Travel & Logistics | 238466 | 175101
PRJ-2024020 | 2025-02 | Project Management Overhead | 208658 | 154228
PRJ-2024020 | 2025-02 | Contingency | 149041 | 126036
PRJ-2024020 | 2025-03 | Equipment/CapEx | 1043290 | 1080905
PRJ-2024020 | 2025-03 | Last Mile Circuit Cost | 596166 | 521635
PRJ-2024020 | 2025-03 | Installation Labor | 447124 | 440183
PRJ-2024020 | 2025-03 | Vendor Management Fee | 298083 | 220060
PRJ-2024020 | 2025-03 | Travel & Logistics | 238466 | 207573
PRJ-2024020 | 2025-03 | Project Management Overhead | 208658 | 158223
PRJ-2024020 | 2025-03 | Contingency | 149041 | 159583
PRJ-2024020 | 2025-04 | Equipment/CapEx | 1043290 | 786011
PRJ-2024020 | 2025-04 | Last Mile Circuit Cost | 596166 | 467267
PRJ-2024020 | 2025-04 | Installation Labor | 447124 | 354693
PRJ-2024020 | 2025-04 | Vendor Management Fee | 298083 | 317980
PRJ-2024020 | 2025-04 | Travel & Logistics | 238466 | 216509
PRJ-2024020 | 2025-04 | Project Management Overhead | 208658 | 266626
PRJ-2024020 | 2025-04 | Contingency | 149041 | 125775
PRJ-2024020 | 2025-05 | Equipment/CapEx | 1043290 | 1201426
PRJ-2024020 | 2025-05 | Last Mile Circuit Cost | 596166 | 549343
PRJ-2024020 | 2025-05 | Installation Labor | 447124 | 518511
PRJ-2024020 | 2025-05 | Vendor Management Fee | 298083 | 247741
PRJ-2024020 | 2025-05 | Travel & Logistics | 238466 | 312876
PRJ-2024020 | 2025-05 | Project Management Overhead | 208658 | 264158
PRJ-2024020 | 2025-05 | Contingency | 149041 | 140669
PRJ-2024020 | 2025-06 | Equipment/CapEx | 1043290 | 898249
PRJ-2024020 | 2025-06 | Last Mile Circuit Cost | 596166 | 479714
PRJ-2024020 | 2025-06 | Installation Labor | 447124 | 395619
PRJ-2024020 | 2025-06 | Vendor Management Fee | 298083 | 222283
PRJ-2024020 | 2025-06 | Travel & Logistics | 238466 | 187207
PRJ-2024020 | 2025-06 | Project Management Overhead | 208658 | 204975
PRJ-2024020 | 2025-06 | Contingency | 149041 | 120564
PRJ-2024021 | 2025-04 | Equipment/CapEx | 155046 | 135855
PRJ-2024021 | 2025-04 | Last Mile Circuit Cost | 88598 | 91453
PRJ-2024021 | 2025-04 | Installation Labor | 66448 | 52592
PRJ-2024021 | 2025-04 | Vendor Management Fee | 44299 | 42466
PRJ-2024021 | 2025-04 | Travel & Logistics | 35439 | 30476
PRJ-2024021 | 2025-04 | Project Management Overhead | 31009 | 27017
PRJ-2024021 | 2025-04 | Contingency | 22149 | 21373
PRJ-2024021 | 2025-05 | Equipment/CapEx | 155046 | 115480
PRJ-2024021 | 2025-05 | Last Mile Circuit Cost | 88598 | 96503
PRJ-2024021 | 2025-05 | Installation Labor | 66448 | 69214
PRJ-2024021 | 2025-05 | Vendor Management Fee | 44299 | 36447
PRJ-2024021 | 2025-05 | Travel & Logistics | 35439 | 28123
PRJ-2024021 | 2025-05 | Project Management Overhead | 31009 | 25326
PRJ-2024021 | 2025-05 | Contingency | 22149 | 21010
PRJ-2024021 | 2025-06 | Equipment/CapEx | 155046 | 143737
PRJ-2024021 | 2025-06 | Last Mile Circuit Cost | 88598 | 96757
PRJ-2024021 | 2025-06 | Installation Labor | 66448 | 82378
PRJ-2024021 | 2025-06 | Vendor Management Fee | 44299 | 49985
PRJ-2024021 | 2025-06 | Travel & Logistics | 35439 | 40737
PRJ-2024021 | 2025-06 | Project Management Overhead | 31009 | 22534
PRJ-2024021 | 2025-06 | Contingency | 22149 | 16979
PRJ-2024021 | 2025-07 | Equipment/CapEx | 155046 | 204721
PRJ-2024021 | 2025-07 | Last Mile Circuit Cost | 88598 | 65817
PRJ-2024021 | 2025-07 | Installation Labor | 66448 | 50186
PRJ-2024021 | 2025-07 | Vendor Management Fee | 44299 | 56472
PRJ-2024021 | 2025-07 | Travel & Logistics | 35439 | 33667
PRJ-2024021 | 2025-07 | Project Management Overhead | 31009 | 41709
PRJ-2024021 | 2025-07 | Contingency | 22149 | 18418
PRJ-2024022 | 2025-03 | Equipment/CapEx | 81298 | 100678
PRJ-2024022 | 2025-03 | Last Mile Circuit Cost | 46456 | 56778
PRJ-2024022 | 2025-03 | Installation Labor | 34842 | 29630
PRJ-2024022 | 2025-03 | Vendor Management Fee | 23228 | 23878
PRJ-2024022 | 2025-03 | Travel & Logistics | 18582 | 17521
PRJ-2024022 | 2025-03 | Project Management Overhead | 16260 | 14355
PRJ-2024022 | 2025-03 | Contingency | 11614 | 12124
PRJ-2024022 | 2025-04 | Equipment/CapEx | 81298 | 72834
PRJ-2024022 | 2025-04 | Last Mile Circuit Cost | 46456 | 45191
PRJ-2024022 | 2025-04 | Installation Labor | 34842 | 42606
PRJ-2024022 | 2025-04 | Vendor Management Fee | 23228 | 22750
PRJ-2024022 | 2025-04 | Travel & Logistics | 18582 | 21040
PRJ-2024022 | 2025-04 | Project Management Overhead | 16260 | 18537
PRJ-2024022 | 2025-04 | Contingency | 11614 | 12889
PRJ-2024022 | 2025-05 | Equipment/CapEx | 81298 | 105421
PRJ-2024022 | 2025-05 | Last Mile Circuit Cost | 46456 | 35151
PRJ-2024022 | 2025-05 | Installation Labor | 34842 | 35061
PRJ-2024022 | 2025-05 | Vendor Management Fee | 23228 | 24614
PRJ-2024022 | 2025-05 | Travel & Logistics | 18582 | 13591
PRJ-2024022 | 2025-05 | Project Management Overhead | 16260 | 13055
PRJ-2024022 | 2025-05 | Contingency | 11614 | 14988
PRJ-2024022 | 2025-06 | Equipment/CapEx | 81298 | 58569
PRJ-2024022 | 2025-06 | Last Mile Circuit Cost | 46456 | 39775
PRJ-2024022 | 2025-06 | Installation Labor | 34842 | 33799
PRJ-2024022 | 2025-06 | Vendor Management Fee | 23228 | 27204
PRJ-2024022 | 2025-06 | Travel & Logistics | 18582 | 21743
PRJ-2024022 | 2025-06 | Project Management Overhead | 16260 | 15749
PRJ-2024022 | 2025-06 | Contingency | 11614 | 15223
PRJ-2024023 | 2025-06 | Equipment/CapEx | 4299645 | 5198398
PRJ-2024023 | 2025-06 | Last Mile Circuit Cost | 2456940 | 2446369
PRJ-2024023 | 2025-06 | Installation Labor | 1842705 | 2311955
PRJ-2024023 | 2025-06 | Vendor Management Fee | 1228470 | 1133072
PRJ-2024023 | 2025-06 | Travel & Logistics | 982776 | 1297447
PRJ-2024023 | 2025-06 | Project Management Overhead | 859929 | 812941
PRJ-2024023 | 2025-06 | Contingency | 614235 | 572530
PRJ-2024023 | 2025-07 | Equipment/CapEx | 4299645 | 3844815
PRJ-2024023 | 2025-07 | Last Mile Circuit Cost | 2456940 | 2705980
PRJ-2024023 | 2025-07 | Installation Labor | 1842705 | 1359570
PRJ-2024023 | 2025-07 | Vendor Management Fee | 1228470 | 1059710
PRJ-2024023 | 2025-07 | Travel & Logistics | 982776 | 1302945
PRJ-2024023 | 2025-07 | Project Management Overhead | 859929 | 663897
PRJ-2024023 | 2025-07 | Contingency | 614235 | 562047
PRJ-2024024 | 2025-12 | Equipment/CapEx | 1167652 | 1470733
PRJ-2024024 | 2025-12 | Last Mile Circuit Cost | 667230 | 575537
PRJ-2024024 | 2025-12 | Installation Labor | 500422 | 466818
PRJ-2024024 | 2025-12 | Vendor Management Fee | 333615 | 393800
PRJ-2024024 | 2025-12 | Travel & Logistics | 266892 | 206087
PRJ-2024024 | 2025-12 | Project Management Overhead | 233531 | 300351
PRJ-2024024 | 2025-12 | Contingency | 166808 | 131913
PRJ-2024024 | 2026-01 | Equipment/CapEx | 1167652 | 1291155
PRJ-2024024 | 2026-01 | Last Mile Circuit Cost | 667230 | 716091
PRJ-2024024 | 2026-01 | Installation Labor | 500422 | 471124
PRJ-2024024 | 2026-01 | Vendor Management Fee | 333615 | 284499
PRJ-2024024 | 2026-01 | Travel & Logistics | 266892 | 195380
PRJ-2024024 | 2026-01 | Project Management Overhead | 233531 | 257321
PRJ-2024024 | 2026-01 | Contingency | 166808 | 198204
PRJ-2024024 | 2026-02 | Equipment/CapEx | 1167652 | 963187
PRJ-2024024 | 2026-02 | Last Mile Circuit Cost | 667230 | 575264
PRJ-2024024 | 2026-02 | Installation Labor | 500422 | 562635
PRJ-2024024 | 2026-02 | Vendor Management Fee | 333615 | 424093
PRJ-2024024 | 2026-02 | Travel & Logistics | 266892 | 222522
PRJ-2024024 | 2026-02 | Project Management Overhead | 233531 | 266497
PRJ-2024024 | 2026-02 | Contingency | 166808 | 223390
PRJ-2024024 | 2026-03 | Equipment/CapEx | 1167652 | 1053645
PRJ-2024024 | 2026-03 | Last Mile Circuit Cost | 667230 | 751058
PRJ-2024024 | 2026-03 | Installation Labor | 500422 | 452725
PRJ-2024024 | 2026-03 | Vendor Management Fee | 333615 | 395455
PRJ-2024024 | 2026-03 | Travel & Logistics | 266892 | 191767
PRJ-2024024 | 2026-03 | Project Management Overhead | 233531 | 166938
PRJ-2024024 | 2026-03 | Contingency | 166808 | 157589
PRJ-2024024 | 2026-04 | Equipment/CapEx | 1167652 | 830536
PRJ-2024024 | 2026-04 | Last Mile Circuit Cost | 667230 | 527178
PRJ-2024024 | 2026-04 | Installation Labor | 500422 | 609098
PRJ-2024024 | 2026-04 | Vendor Management Fee | 333615 | 236611
PRJ-2024024 | 2026-04 | Travel & Logistics | 266892 | 263158
PRJ-2024024 | 2026-04 | Project Management Overhead | 233531 | 272354
PRJ-2024024 | 2026-04 | Contingency | 166808 | 151442
PRJ-2024024 | 2026-05 | Equipment/CapEx | 1167652 | 1575629
PRJ-2024024 | 2026-05 | Last Mile Circuit Cost | 667230 | 790753
PRJ-2024024 | 2026-05 | Installation Labor | 500422 | 446887
PRJ-2024024 | 2026-05 | Vendor Management Fee | 333615 | 410256
PRJ-2024024 | 2026-05 | Travel & Logistics | 266892 | 269663
PRJ-2024024 | 2026-05 | Project Management Overhead | 233531 | 187331
PRJ-2024024 | 2026-05 | Contingency | 166808 | 217876
PRJ-2024024 | 2026-06 | Equipment/CapEx | 1167652 | 1503825
PRJ-2024024 | 2026-06 | Last Mile Circuit Cost | 667230 | 649243
PRJ-2024024 | 2026-06 | Installation Labor | 500422 | 443210
PRJ-2024024 | 2026-06 | Vendor Management Fee | 333615 | 446926
PRJ-2024024 | 2026-06 | Travel & Logistics | 266892 | 314291
PRJ-2024024 | 2026-06 | Project Management Overhead | 233531 | 202175
PRJ-2024024 | 2026-06 | Contingency | 166808 | 131490
PRJ-2024024 | 2026-07 | Equipment/CapEx | 1167652 | 1346562
PRJ-2024024 | 2026-07 | Last Mile Circuit Cost | 667230 | 829321
PRJ-2024024 | 2026-07 | Installation Labor | 500422 | 538597
PRJ-2024024 | 2026-07 | Vendor Management Fee | 333615 | 287580
PRJ-2024024 | 2026-07 | Travel & Logistics | 266892 | 217056
PRJ-2024024 | 2026-07 | Project Management Overhead | 233531 | 206258
PRJ-2024024 | 2026-07 | Contingency | 166808 | 164123
PRJ-2024025 | 2025-04 | Equipment/CapEx | 65420 | 59707
PRJ-2024025 | 2025-04 | Last Mile Circuit Cost | 37383 | 37783
PRJ-2024025 | 2025-04 | Installation Labor | 28037 | 22704
PRJ-2024025 | 2025-04 | Vendor Management Fee | 18692 | 15122
PRJ-2024025 | 2025-04 | Travel & Logistics | 14953 | 10794
PRJ-2024025 | 2025-04 | Project Management Overhead | 13084 | 11105
PRJ-2024025 | 2025-04 | Contingency | 9346 | 11387
PRJ-2024025 | 2025-05 | Equipment/CapEx | 65420 | 86522
PRJ-2024025 | 2025-05 | Last Mile Circuit Cost | 37383 | 38494
PRJ-2024025 | 2025-05 | Installation Labor | 28037 | 23385
PRJ-2024025 | 2025-05 | Vendor Management Fee | 18692 | 18698
PRJ-2024025 | 2025-05 | Travel & Logistics | 14953 | 11552
PRJ-2024025 | 2025-05 | Project Management Overhead | 13084 | 12342
PRJ-2024025 | 2025-05 | Contingency | 9346 | 7640
PRJ-2024025 | 2025-05 | Equipment/CapEx | 65420 | 57040
PRJ-2024025 | 2025-05 | Last Mile Circuit Cost | 37383 | 50136
PRJ-2024025 | 2025-05 | Installation Labor | 28037 | 29820
PRJ-2024025 | 2025-05 | Vendor Management Fee | 18692 | 23946
PRJ-2024025 | 2025-05 | Travel & Logistics | 14953 | 16219
PRJ-2024025 | 2025-05 | Project Management Overhead | 13084 | 16731
PRJ-2024025 | 2025-05 | Contingency | 9346 | 10906
PRJ-2024025 | 2025-06 | Equipment/CapEx | 65420 | 86349
PRJ-2024025 | 2025-06 | Last Mile Circuit Cost | 37383 | 33462
PRJ-2024025 | 2025-06 | Installation Labor | 28037 | 30622
PRJ-2024025 | 2025-06 | Vendor Management Fee | 18692 | 24647
PRJ-2024025 | 2025-06 | Travel & Logistics | 14953 | 14200
PRJ-2024025 | 2025-06 | Project Management Overhead | 13084 | 15327
PRJ-2024025 | 2025-06 | Contingency | 9346 | 10338
PRJ-2024025 | 2025-07 | Equipment/CapEx | 65420 | 48653
PRJ-2024025 | 2025-07 | Last Mile Circuit Cost | 37383 | 43344
PRJ-2024025 | 2025-07 | Installation Labor | 28037 | 30269
PRJ-2024025 | 2025-07 | Vendor Management Fee | 18692 | 16894
PRJ-2024025 | 2025-07 | Travel & Logistics | 14953 | 18403
PRJ-2024025 | 2025-07 | Project Management Overhead | 13084 | 14745
PRJ-2024025 | 2025-07 | Contingency | 9346 | 8323
PRJ-2024025 | 2025-08 | Equipment/CapEx | 65420 | 58488
PRJ-2024025 | 2025-08 | Last Mile Circuit Cost | 37383 | 32277
PRJ-2024025 | 2025-08 | Installation Labor | 28037 | 25484
PRJ-2024025 | 2025-08 | Vendor Management Fee | 18692 | 15979
PRJ-2024025 | 2025-08 | Travel & Logistics | 14953 | 16145
PRJ-2024025 | 2025-08 | Project Management Overhead | 13084 | 9415
PRJ-2024025 | 2025-08 | Contingency | 9346 | 6983
PRJ-2024025 | 2025-09 | Equipment/CapEx | 65420 | 61545
PRJ-2024025 | 2025-09 | Last Mile Circuit Cost | 37383 | 33535
PRJ-2024025 | 2025-09 | Installation Labor | 28037 | 22473
PRJ-2024025 | 2025-09 | Vendor Management Fee | 18692 | 23728
PRJ-2024025 | 2025-09 | Travel & Logistics | 14953 | 18766
PRJ-2024025 | 2025-09 | Project Management Overhead | 13084 | 13635
PRJ-2024025 | 2025-09 | Contingency | 9346 | 9552
PRJ-2024026 | 2025-01 | Equipment/CapEx | 120464 | 112942
PRJ-2024026 | 2025-01 | Last Mile Circuit Cost | 68836 | 59624
PRJ-2024026 | 2025-01 | Installation Labor | 51627 | 66025
PRJ-2024026 | 2025-01 | Vendor Management Fee | 34418 | 41710
PRJ-2024026 | 2025-01 | Travel & Logistics | 27535 | 28261
PRJ-2024026 | 2025-01 | Project Management Overhead | 24093 | 24224
PRJ-2024026 | 2025-01 | Contingency | 17209 | 17506
PRJ-2024026 | 2025-02 | Equipment/CapEx | 120464 | 138156
PRJ-2024026 | 2025-02 | Last Mile Circuit Cost | 68836 | 82392
PRJ-2024026 | 2025-02 | Installation Labor | 51627 | 40332
PRJ-2024026 | 2025-02 | Vendor Management Fee | 34418 | 39414
PRJ-2024026 | 2025-02 | Travel & Logistics | 27535 | 25999
PRJ-2024026 | 2025-02 | Project Management Overhead | 24093 | 31568
PRJ-2024026 | 2025-02 | Contingency | 17209 | 20420
PRJ-2024026 | 2025-03 | Equipment/CapEx | 120464 | 132563
PRJ-2024026 | 2025-03 | Last Mile Circuit Cost | 68836 | 81896
PRJ-2024026 | 2025-03 | Installation Labor | 51627 | 50351
PRJ-2024026 | 2025-03 | Vendor Management Fee | 34418 | 27298
PRJ-2024026 | 2025-03 | Travel & Logistics | 27535 | 30759
PRJ-2024026 | 2025-03 | Project Management Overhead | 24093 | 22248
PRJ-2024026 | 2025-03 | Contingency | 17209 | 12544
PRJ-2024026 | 2025-04 | Equipment/CapEx | 120464 | 94361
PRJ-2024026 | 2025-04 | Last Mile Circuit Cost | 68836 | 70714
PRJ-2024026 | 2025-04 | Installation Labor | 51627 | 37074
PRJ-2024026 | 2025-04 | Vendor Management Fee | 34418 | 41933
PRJ-2024026 | 2025-04 | Travel & Logistics | 27535 | 24815
PRJ-2024026 | 2025-04 | Project Management Overhead | 24093 | 18066
PRJ-2024026 | 2025-04 | Contingency | 17209 | 17455
PRJ-2024026 | 2025-05 | Equipment/CapEx | 120464 | 140003
PRJ-2024026 | 2025-05 | Last Mile Circuit Cost | 68836 | 85262
PRJ-2024026 | 2025-05 | Installation Labor | 51627 | 52760
PRJ-2024026 | 2025-05 | Vendor Management Fee | 34418 | 30130
PRJ-2024026 | 2025-05 | Travel & Logistics | 27535 | 34498
PRJ-2024026 | 2025-05 | Project Management Overhead | 24093 | 17537
PRJ-2024026 | 2025-05 | Contingency | 17209 | 14823
PRJ-2024026 | 2025-06 | Equipment/CapEx | 120464 | 116710
PRJ-2024026 | 2025-06 | Last Mile Circuit Cost | 68836 | 58099
PRJ-2024026 | 2025-06 | Installation Labor | 51627 | 46142
PRJ-2024026 | 2025-06 | Vendor Management Fee | 34418 | 40794
PRJ-2024026 | 2025-06 | Travel & Logistics | 27535 | 29787
PRJ-2024026 | 2025-06 | Project Management Overhead | 24093 | 18862
PRJ-2024026 | 2025-06 | Contingency | 17209 | 19711
PRJ-2024026 | 2025-07 | Equipment/CapEx | 120464 | 91200
PRJ-2024026 | 2025-07 | Last Mile Circuit Cost | 68836 | 87794
PRJ-2024026 | 2025-07 | Installation Labor | 51627 | 47886
PRJ-2024026 | 2025-07 | Vendor Management Fee | 34418 | 31333
PRJ-2024026 | 2025-07 | Travel & Logistics | 27535 | 22451
PRJ-2024026 | 2025-07 | Project Management Overhead | 24093 | 22273
PRJ-2024026 | 2025-07 | Contingency | 17209 | 19290
PRJ-2024027 | 2025-06 | Equipment/CapEx | 1369882 | 1597848
PRJ-2024027 | 2025-06 | Last Mile Circuit Cost | 782790 | 910040
PRJ-2024027 | 2025-06 | Installation Labor | 587092 | 665361
PRJ-2024027 | 2025-06 | Vendor Management Fee | 391395 | 325168
PRJ-2024027 | 2025-06 | Travel & Logistics | 313116 | 244724
PRJ-2024027 | 2025-06 | Project Management Overhead | 273976 | 291787
PRJ-2024027 | 2025-06 | Contingency | 195698 | 187820
PRJ-2024027 | 2025-07 | Equipment/CapEx | 1369882 | 1570876
PRJ-2024027 | 2025-07 | Last Mile Circuit Cost | 782790 | 803440
PRJ-2024027 | 2025-07 | Installation Labor | 587092 | 762209
PRJ-2024027 | 2025-07 | Vendor Management Fee | 391395 | 518073
PRJ-2024027 | 2025-07 | Travel & Logistics | 313116 | 357590
PRJ-2024027 | 2025-07 | Project Management Overhead | 273976 | 267096
PRJ-2024027 | 2025-07 | Contingency | 195698 | 249501
PRJ-2024028 | 2025-11 | Equipment/CapEx | 958939 | 996045
PRJ-2024028 | 2025-11 | Last Mile Circuit Cost | 547965 | 564546
PRJ-2024028 | 2025-11 | Installation Labor | 410974 | 380517
PRJ-2024028 | 2025-11 | Vendor Management Fee | 273982 | 324057
PRJ-2024028 | 2025-11 | Travel & Logistics | 219186 | 169075
PRJ-2024028 | 2025-11 | Project Management Overhead | 191788 | 174779
PRJ-2024028 | 2025-11 | Contingency | 136991 | 170322
PRJ-2024028 | 2025-12 | Equipment/CapEx | 958939 | 1093452
PRJ-2024028 | 2025-12 | Last Mile Circuit Cost | 547965 | 412408
PRJ-2024028 | 2025-12 | Installation Labor | 410974 | 400243
PRJ-2024028 | 2025-12 | Vendor Management Fee | 273982 | 291460
PRJ-2024028 | 2025-12 | Travel & Logistics | 219186 | 236386
PRJ-2024028 | 2025-12 | Project Management Overhead | 191788 | 171839
PRJ-2024028 | 2025-12 | Contingency | 136991 | 99736
PRJ-2024028 | 2026-01 | Equipment/CapEx | 958939 | 820549
PRJ-2024028 | 2026-01 | Last Mile Circuit Cost | 547965 | 716324
PRJ-2024028 | 2026-01 | Installation Labor | 410974 | 351522
PRJ-2024028 | 2026-01 | Vendor Management Fee | 273982 | 236467
PRJ-2024028 | 2026-01 | Travel & Logistics | 219186 | 244501
PRJ-2024028 | 2026-01 | Project Management Overhead | 191788 | 176840
PRJ-2024028 | 2026-01 | Contingency | 136991 | 174485
PRJ-2024029 | 2025-11 | Equipment/CapEx | 516075 | 466444
PRJ-2024029 | 2025-11 | Last Mile Circuit Cost | 294900 | 339767
PRJ-2024029 | 2025-11 | Installation Labor | 221175 | 171581
PRJ-2024029 | 2025-11 | Vendor Management Fee | 147450 | 190097
PRJ-2024029 | 2025-11 | Travel & Logistics | 117960 | 99370
PRJ-2024029 | 2025-11 | Project Management Overhead | 103215 | 111633
PRJ-2024029 | 2025-11 | Contingency | 73725 | 71510
PRJ-2024029 | 2025-12 | Equipment/CapEx | 516075 | 424277
PRJ-2024029 | 2025-12 | Last Mile Circuit Cost | 294900 | 231675
PRJ-2024029 | 2025-12 | Installation Labor | 221175 | 285115
PRJ-2024029 | 2025-12 | Vendor Management Fee | 147450 | 192455
PRJ-2024029 | 2025-12 | Travel & Logistics | 117960 | 121734
PRJ-2024029 | 2025-12 | Project Management Overhead | 103215 | 97288
PRJ-2024029 | 2025-12 | Contingency | 73725 | 80695
PRJ-2024029 | 2026-01 | Equipment/CapEx | 516075 | 383854
PRJ-2024029 | 2026-01 | Last Mile Circuit Cost | 294900 | 231092
PRJ-2024029 | 2026-01 | Installation Labor | 221175 | 291225
PRJ-2024029 | 2026-01 | Vendor Management Fee | 147450 | 164673
PRJ-2024029 | 2026-01 | Travel & Logistics | 117960 | 115515
PRJ-2024029 | 2026-01 | Project Management Overhead | 103215 | 110324
PRJ-2024029 | 2026-01 | Contingency | 73725 | 92133
PRJ-2024029 | 2026-02 | Equipment/CapEx | 516075 | 660467
PRJ-2024029 | 2026-02 | Last Mile Circuit Cost | 294900 | 313398
PRJ-2024029 | 2026-02 | Installation Labor | 221175 | 264056
PRJ-2024029 | 2026-02 | Vendor Management Fee | 147450 | 187303
PRJ-2024029 | 2026-02 | Travel & Logistics | 117960 | 127023
PRJ-2024029 | 2026-02 | Project Management Overhead | 103215 | 109381
PRJ-2024029 | 2026-02 | Contingency | 73725 | 76795
PRJ-2024030 | 2025-08 | Equipment/CapEx | 226819 | 242967
PRJ-2024030 | 2025-08 | Last Mile Circuit Cost | 129611 | 160423
PRJ-2024030 | 2025-08 | Installation Labor | 97208 | 107693
PRJ-2024030 | 2025-08 | Vendor Management Fee | 64805 | 87083
PRJ-2024030 | 2025-08 | Travel & Logistics | 51844 | 61212
PRJ-2024030 | 2025-08 | Project Management Overhead | 45364 | 34269
PRJ-2024030 | 2025-08 | Contingency | 32403 | 31630
PRJ-2024030 | 2025-09 | Equipment/CapEx | 226819 | 191867
PRJ-2024030 | 2025-09 | Last Mile Circuit Cost | 129611 | 120004
PRJ-2024030 | 2025-09 | Installation Labor | 97208 | 99301
PRJ-2024030 | 2025-09 | Vendor Management Fee | 64805 | 47510
PRJ-2024030 | 2025-09 | Travel & Logistics | 51844 | 60171
PRJ-2024030 | 2025-09 | Project Management Overhead | 45364 | 43215
PRJ-2024030 | 2025-09 | Contingency | 32403 | 41112
PRJ-2024030 | 2025-10 | Equipment/CapEx | 226819 | 304617
PRJ-2024030 | 2025-10 | Last Mile Circuit Cost | 129611 | 105928
PRJ-2024030 | 2025-10 | Installation Labor | 97208 | 90005
PRJ-2024030 | 2025-10 | Vendor Management Fee | 64805 | 69096
PRJ-2024030 | 2025-10 | Travel & Logistics | 51844 | 38939
PRJ-2024030 | 2025-10 | Project Management Overhead | 45364 | 39139
PRJ-2024030 | 2025-10 | Contingency | 32403 | 27633
PRJ-2024030 | 2025-11 | Equipment/CapEx | 226819 | 297550
PRJ-2024030 | 2025-11 | Last Mile Circuit Cost | 129611 | 102029
PRJ-2024030 | 2025-11 | Installation Labor | 97208 | 85837
PRJ-2024030 | 2025-11 | Vendor Management Fee | 64805 | 70065
PRJ-2024030 | 2025-11 | Travel & Logistics | 51844 | 60503
PRJ-2024030 | 2025-11 | Project Management Overhead | 45364 | 32049
PRJ-2024030 | 2025-11 | Contingency | 32403 | 32957
PRJ-2024030 | 2025-12 | Equipment/CapEx | 226819 | 188820
PRJ-2024030 | 2025-12 | Last Mile Circuit Cost | 129611 | 99819
PRJ-2024030 | 2025-12 | Installation Labor | 97208 | 106332
PRJ-2024030 | 2025-12 | Vendor Management Fee | 64805 | 69402
PRJ-2024030 | 2025-12 | Travel & Logistics | 51844 | 53222
PRJ-2024030 | 2025-12 | Project Management Overhead | 45364 | 44294
PRJ-2024030 | 2025-12 | Contingency | 32403 | 32511
PRJ-2024030 | 2026-01 | Equipment/CapEx | 226819 | 259348
PRJ-2024030 | 2026-01 | Last Mile Circuit Cost | 129611 | 92158
PRJ-2024030 | 2026-01 | Installation Labor | 97208 | 101165
PRJ-2024030 | 2026-01 | Vendor Management Fee | 64805 | 73475
PRJ-2024030 | 2026-01 | Travel & Logistics | 51844 | 43914
PRJ-2024030 | 2026-01 | Project Management Overhead | 45364 | 43204
PRJ-2024030 | 2026-01 | Contingency | 32403 | 31529
PRJ-2024030 | 2026-02 | Equipment/CapEx | 226819 | 180874
PRJ-2024030 | 2026-02 | Last Mile Circuit Cost | 129611 | 106958
PRJ-2024030 | 2026-02 | Installation Labor | 97208 | 94156
PRJ-2024030 | 2026-02 | Vendor Management Fee | 64805 | 60035
PRJ-2024030 | 2026-02 | Travel & Logistics | 51844 | 52145
PRJ-2024030 | 2026-02 | Project Management Overhead | 45364 | 50661
PRJ-2024030 | 2026-02 | Contingency | 32403 | 30112
PRJ-2024031 | 2025-09 | Equipment/CapEx | 244893 | 243816
PRJ-2024031 | 2025-09 | Last Mile Circuit Cost | 139939 | 133576
PRJ-2024031 | 2025-09 | Installation Labor | 104954 | 123365
PRJ-2024031 | 2025-09 | Vendor Management Fee | 69969 | 56537
PRJ-2024031 | 2025-09 | Travel & Logistics | 55975 | 61304
PRJ-2024031 | 2025-09 | Project Management Overhead | 48979 | 44135
PRJ-2024031 | 2025-09 | Contingency | 34985 | 25965
PRJ-2024031 | 2025-10 | Equipment/CapEx | 244893 | 298651
PRJ-2024031 | 2025-10 | Last Mile Circuit Cost | 139939 | 177990
PRJ-2024031 | 2025-10 | Installation Labor | 104954 | 130643
PRJ-2024031 | 2025-10 | Vendor Management Fee | 69969 | 81266
PRJ-2024031 | 2025-10 | Travel & Logistics | 55975 | 47081
PRJ-2024031 | 2025-10 | Project Management Overhead | 48979 | 57987
PRJ-2024031 | 2025-10 | Contingency | 34985 | 35149
PRJ-2024031 | 2025-11 | Equipment/CapEx | 244893 | 174364
PRJ-2024031 | 2025-11 | Last Mile Circuit Cost | 139939 | 166395
PRJ-2024031 | 2025-11 | Installation Labor | 104954 | 94516
PRJ-2024031 | 2025-11 | Vendor Management Fee | 69969 | 72799
PRJ-2024031 | 2025-11 | Travel & Logistics | 55975 | 64995
PRJ-2024031 | 2025-11 | Project Management Overhead | 48979 | 43982
PRJ-2024031 | 2025-11 | Contingency | 34985 | 40288
PRJ-2024032 | 2025-08 | Equipment/CapEx | 77817 | 73741
PRJ-2024032 | 2025-08 | Last Mile Circuit Cost | 44467 | 52751
PRJ-2024032 | 2025-08 | Installation Labor | 33350 | 30388
PRJ-2024032 | 2025-08 | Vendor Management Fee | 22234 | 25441
PRJ-2024032 | 2025-08 | Travel & Logistics | 17787 | 15101
PRJ-2024032 | 2025-08 | Project Management Overhead | 15563 | 14350
PRJ-2024032 | 2025-08 | Contingency | 11117 | 10767
PRJ-2024032 | 2025-09 | Equipment/CapEx | 77817 | 60336
PRJ-2024032 | 2025-09 | Last Mile Circuit Cost | 44467 | 46008
PRJ-2024032 | 2025-09 | Installation Labor | 33350 | 39664
PRJ-2024032 | 2025-09 | Vendor Management Fee | 22234 | 15749
PRJ-2024032 | 2025-09 | Travel & Logistics | 17787 | 15258
PRJ-2024032 | 2025-09 | Project Management Overhead | 15563 | 20764
PRJ-2024032 | 2025-09 | Contingency | 11117 | 7806
PRJ-2024032 | 2025-10 | Equipment/CapEx | 77817 | 97116
PRJ-2024032 | 2025-10 | Last Mile Circuit Cost | 44467 | 55896
PRJ-2024032 | 2025-10 | Installation Labor | 33350 | 37926
PRJ-2024032 | 2025-10 | Vendor Management Fee | 22234 | 25967
PRJ-2024032 | 2025-10 | Travel & Logistics | 17787 | 16260
PRJ-2024032 | 2025-10 | Project Management Overhead | 15563 | 17634
PRJ-2024032 | 2025-10 | Contingency | 11117 | 10767
PRJ-2024032 | 2025-11 | Equipment/CapEx | 77817 | 61490
PRJ-2024032 | 2025-11 | Last Mile Circuit Cost | 44467 | 33067
PRJ-2024032 | 2025-11 | Installation Labor | 33350 | 30604
PRJ-2024032 | 2025-11 | Vendor Management Fee | 22234 | 28837
PRJ-2024032 | 2025-11 | Travel & Logistics | 17787 | 23640
PRJ-2024032 | 2025-11 | Project Management Overhead | 15563 | 19742
PRJ-2024032 | 2025-11 | Contingency | 11117 | 12913
PRJ-2024032 | 2025-12 | Equipment/CapEx | 77817 | 59221
PRJ-2024032 | 2025-12 | Last Mile Circuit Cost | 44467 | 58011
PRJ-2024032 | 2025-12 | Installation Labor | 33350 | 34239
PRJ-2024032 | 2025-12 | Vendor Management Fee | 22234 | 16699
PRJ-2024032 | 2025-12 | Travel & Logistics | 17787 | 18051
PRJ-2024032 | 2025-12 | Project Management Overhead | 15563 | 16994
PRJ-2024032 | 2025-12 | Contingency | 11117 | 13631
PRJ-2024032 | 2026-01 | Equipment/CapEx | 77817 | 65049
PRJ-2024032 | 2026-01 | Last Mile Circuit Cost | 44467 | 42437
PRJ-2024032 | 2026-01 | Installation Labor | 33350 | 31690
PRJ-2024032 | 2026-01 | Vendor Management Fee | 22234 | 18866
PRJ-2024032 | 2026-01 | Travel & Logistics | 17787 | 19977
PRJ-2024032 | 2026-01 | Project Management Overhead | 15563 | 20389
PRJ-2024032 | 2026-01 | Contingency | 11117 | 9976
PRJ-2024032 | 2026-02 | Equipment/CapEx | 77817 | 63333
PRJ-2024032 | 2026-02 | Last Mile Circuit Cost | 44467 | 33255
PRJ-2024032 | 2026-02 | Installation Labor | 33350 | 28684
PRJ-2024032 | 2026-02 | Vendor Management Fee | 22234 | 21549
PRJ-2024032 | 2026-02 | Travel & Logistics | 17787 | 22267
PRJ-2024032 | 2026-02 | Project Management Overhead | 15563 | 16777
PRJ-2024032 | 2026-02 | Contingency | 11117 | 9804
PRJ-2024032 | 2026-03 | Equipment/CapEx | 77817 | 54987
PRJ-2024032 | 2026-03 | Last Mile Circuit Cost | 44467 | 36938
PRJ-2024032 | 2026-03 | Installation Labor | 33350 | 38170
PRJ-2024032 | 2026-03 | Vendor Management Fee | 22234 | 24395
PRJ-2024032 | 2026-03 | Travel & Logistics | 17787 | 20742
PRJ-2024032 | 2026-03 | Project Management Overhead | 15563 | 17651
PRJ-2024032 | 2026-03 | Contingency | 11117 | 12126
PRJ-2024033 | 2025-06 | Equipment/CapEx | 95846 | 128637
PRJ-2024033 | 2025-06 | Last Mile Circuit Cost | 54769 | 39437
PRJ-2024033 | 2025-06 | Installation Labor | 41077 | 34759
PRJ-2024033 | 2025-06 | Vendor Management Fee | 27384 | 25599
PRJ-2024033 | 2025-06 | Travel & Logistics | 21908 | 20249
PRJ-2024033 | 2025-06 | Project Management Overhead | 19169 | 21997
PRJ-2024033 | 2025-06 | Contingency | 13692 | 15515
PRJ-2024033 | 2025-07 | Equipment/CapEx | 95846 | 73799
PRJ-2024033 | 2025-07 | Last Mile Circuit Cost | 54769 | 45489
PRJ-2024033 | 2025-07 | Installation Labor | 41077 | 47724
PRJ-2024033 | 2025-07 | Vendor Management Fee | 27384 | 32335
PRJ-2024033 | 2025-07 | Travel & Logistics | 21908 | 17132
PRJ-2024033 | 2025-07 | Project Management Overhead | 19169 | 22007
PRJ-2024033 | 2025-07 | Contingency | 13692 | 18065
PRJ-2024034 | 2025-07 | Equipment/CapEx | 123244 | 112708
PRJ-2024034 | 2025-07 | Last Mile Circuit Cost | 70425 | 69971
PRJ-2024034 | 2025-07 | Installation Labor | 52819 | 40343
PRJ-2024034 | 2025-07 | Vendor Management Fee | 35212 | 39099
PRJ-2024034 | 2025-07 | Travel & Logistics | 28170 | 20588
PRJ-2024034 | 2025-07 | Project Management Overhead | 24649 | 30171
PRJ-2024034 | 2025-07 | Contingency | 17606 | 21293
PRJ-2024034 | 2025-08 | Equipment/CapEx | 123244 | 106260
PRJ-2024034 | 2025-08 | Last Mile Circuit Cost | 70425 | 66196
PRJ-2024034 | 2025-08 | Installation Labor | 52819 | 54185
PRJ-2024034 | 2025-08 | Vendor Management Fee | 35212 | 37362
PRJ-2024034 | 2025-08 | Travel & Logistics | 28170 | 28070
PRJ-2024034 | 2025-08 | Project Management Overhead | 24649 | 18329
PRJ-2024034 | 2025-08 | Contingency | 17606 | 20347
PRJ-2024034 | 2025-09 | Equipment/CapEx | 123244 | 148184
PRJ-2024034 | 2025-09 | Last Mile Circuit Cost | 70425 | 64393
PRJ-2024034 | 2025-09 | Installation Labor | 52819 | 46725
PRJ-2024034 | 2025-09 | Vendor Management Fee | 35212 | 44202
PRJ-2024034 | 2025-09 | Travel & Logistics | 28170 | 25068
PRJ-2024034 | 2025-09 | Project Management Overhead | 24649 | 25935
PRJ-2024034 | 2025-09 | Contingency | 17606 | 13151
PRJ-2024034 | 2025-10 | Equipment/CapEx | 123244 | 114752
PRJ-2024034 | 2025-10 | Last Mile Circuit Cost | 70425 | 85887
PRJ-2024034 | 2025-10 | Installation Labor | 52819 | 57552
PRJ-2024034 | 2025-10 | Vendor Management Fee | 35212 | 36215
PRJ-2024034 | 2025-10 | Travel & Logistics | 28170 | 29015
PRJ-2024034 | 2025-10 | Project Management Overhead | 24649 | 31665
PRJ-2024034 | 2025-10 | Contingency | 17606 | 22731
PRJ-2024034 | 2025-11 | Equipment/CapEx | 123244 | 158924
PRJ-2024034 | 2025-11 | Last Mile Circuit Cost | 70425 | 52677
PRJ-2024034 | 2025-11 | Installation Labor | 52819 | 41121
PRJ-2024034 | 2025-11 | Vendor Management Fee | 35212 | 38086
PRJ-2024034 | 2025-11 | Travel & Logistics | 28170 | 27807
PRJ-2024034 | 2025-11 | Project Management Overhead | 24649 | 23882
PRJ-2024034 | 2025-11 | Contingency | 17606 | 18897
PRJ-2024034 | 2025-12 | Equipment/CapEx | 123244 | 105985
PRJ-2024034 | 2025-12 | Last Mile Circuit Cost | 70425 | 82526
PRJ-2024034 | 2025-12 | Installation Labor | 52819 | 50988
PRJ-2024034 | 2025-12 | Vendor Management Fee | 35212 | 32706
PRJ-2024034 | 2025-12 | Travel & Logistics | 28170 | 27298
PRJ-2024034 | 2025-12 | Project Management Overhead | 24649 | 22804
PRJ-2024034 | 2025-12 | Contingency | 17606 | 18140
PRJ-2024034 | 2026-01 | Equipment/CapEx | 123244 | 165988
PRJ-2024034 | 2026-01 | Last Mile Circuit Cost | 70425 | 93188
PRJ-2024034 | 2026-01 | Installation Labor | 52819 | 61113
PRJ-2024034 | 2026-01 | Vendor Management Fee | 35212 | 43073
PRJ-2024034 | 2026-01 | Travel & Logistics | 28170 | 26800
PRJ-2024034 | 2026-01 | Project Management Overhead | 24649 | 30707
PRJ-2024034 | 2026-01 | Contingency | 17606 | 19826
PRJ-2024034 | 2026-02 | Equipment/CapEx | 123244 | 138866
PRJ-2024034 | 2026-02 | Last Mile Circuit Cost | 70425 | 81727
PRJ-2024034 | 2026-02 | Installation Labor | 52819 | 56321
PRJ-2024034 | 2026-02 | Vendor Management Fee | 35212 | 43294
PRJ-2024034 | 2026-02 | Travel & Logistics | 28170 | 36004
PRJ-2024034 | 2026-02 | Project Management Overhead | 24649 | 32587
PRJ-2024034 | 2026-02 | Contingency | 17606 | 18764
PRJ-2024035 | 2025-08 | Equipment/CapEx | 153990 | 164035
PRJ-2024035 | 2025-08 | Last Mile Circuit Cost | 87994 | 76669
PRJ-2024035 | 2025-08 | Installation Labor | 65996 | 79601
PRJ-2024035 | 2025-08 | Vendor Management Fee | 43997 | 36223
PRJ-2024035 | 2025-08 | Travel & Logistics | 35198 | 44141
PRJ-2024035 | 2025-08 | Project Management Overhead | 30798 | 37862
PRJ-2024035 | 2025-08 | Contingency | 21998 | 25985
PRJ-2024035 | 2025-08 | Equipment/CapEx | 153990 | 139806
PRJ-2024035 | 2025-08 | Last Mile Circuit Cost | 87994 | 89065
PRJ-2024035 | 2025-08 | Installation Labor | 65996 | 80891
PRJ-2024035 | 2025-08 | Vendor Management Fee | 43997 | 42502
PRJ-2024035 | 2025-08 | Travel & Logistics | 35198 | 33677
PRJ-2024035 | 2025-08 | Project Management Overhead | 30798 | 36009
PRJ-2024035 | 2025-08 | Contingency | 21998 | 18798
PRJ-2024035 | 2025-09 | Equipment/CapEx | 153990 | 162076
PRJ-2024035 | 2025-09 | Last Mile Circuit Cost | 87994 | 109883
PRJ-2024035 | 2025-09 | Installation Labor | 65996 | 60922
PRJ-2024035 | 2025-09 | Vendor Management Fee | 43997 | 40519
PRJ-2024035 | 2025-09 | Travel & Logistics | 35198 | 42414
PRJ-2024035 | 2025-09 | Project Management Overhead | 30798 | 40709
PRJ-2024035 | 2025-09 | Contingency | 21998 | 28492
PRJ-2024035 | 2025-10 | Equipment/CapEx | 153990 | 178562
PRJ-2024035 | 2025-10 | Last Mile Circuit Cost | 87994 | 94919
PRJ-2024035 | 2025-10 | Installation Labor | 65996 | 50075
PRJ-2024035 | 2025-10 | Vendor Management Fee | 43997 | 41308
PRJ-2024035 | 2025-10 | Travel & Logistics | 35198 | 32570
PRJ-2024035 | 2025-10 | Project Management Overhead | 30798 | 29572
PRJ-2024035 | 2025-10 | Contingency | 21998 | 21742
PRJ-2024035 | 2025-11 | Equipment/CapEx | 153990 | 126561
PRJ-2024035 | 2025-11 | Last Mile Circuit Cost | 87994 | 115708
PRJ-2024035 | 2025-11 | Installation Labor | 65996 | 70405
PRJ-2024035 | 2025-11 | Vendor Management Fee | 43997 | 49420
PRJ-2024035 | 2025-11 | Travel & Logistics | 35198 | 41597
PRJ-2024035 | 2025-11 | Project Management Overhead | 30798 | 36853
PRJ-2024035 | 2025-11 | Contingency | 21998 | 29116
PRJ-2024036 | 2025-03 | Equipment/CapEx | 204503 | 243751
PRJ-2024036 | 2025-03 | Last Mile Circuit Cost | 116859 | 139273
PRJ-2024036 | 2025-03 | Installation Labor | 87644 | 83206
PRJ-2024036 | 2025-03 | Vendor Management Fee | 58430 | 41480
PRJ-2024036 | 2025-03 | Travel & Logistics | 46744 | 36276
PRJ-2024036 | 2025-03 | Project Management Overhead | 40901 | 49372
PRJ-2024036 | 2025-03 | Contingency | 29215 | 22102
PRJ-2024036 | 2025-04 | Equipment/CapEx | 204503 | 227842
PRJ-2024036 | 2025-04 | Last Mile Circuit Cost | 116859 | 84133
PRJ-2024036 | 2025-04 | Installation Labor | 87644 | 83162
PRJ-2024036 | 2025-04 | Vendor Management Fee | 58430 | 62242
PRJ-2024036 | 2025-04 | Travel & Logistics | 46744 | 42661
PRJ-2024036 | 2025-04 | Project Management Overhead | 40901 | 34738
PRJ-2024036 | 2025-04 | Contingency | 29215 | 21102
PRJ-2024036 | 2025-05 | Equipment/CapEx | 204503 | 213744
PRJ-2024036 | 2025-05 | Last Mile Circuit Cost | 116859 | 122432
PRJ-2024036 | 2025-05 | Installation Labor | 87644 | 118049
PRJ-2024036 | 2025-05 | Vendor Management Fee | 58430 | 57548
PRJ-2024036 | 2025-05 | Travel & Logistics | 46744 | 32742
PRJ-2024036 | 2025-05 | Project Management Overhead | 40901 | 32349
PRJ-2024036 | 2025-05 | Contingency | 29215 | 37586
PRJ-2024036 | 2025-05 | Equipment/CapEx | 204503 | 263210
PRJ-2024036 | 2025-05 | Last Mile Circuit Cost | 116859 | 152170
PRJ-2024036 | 2025-05 | Installation Labor | 87644 | 101910
PRJ-2024036 | 2025-05 | Vendor Management Fee | 58430 | 61811
PRJ-2024036 | 2025-05 | Travel & Logistics | 46744 | 49405
PRJ-2024036 | 2025-05 | Project Management Overhead | 40901 | 53714
PRJ-2024036 | 2025-05 | Contingency | 29215 | 23450
PRJ-2024037 | 2025-01 | Equipment/CapEx | 513252 | 612273
PRJ-2024037 | 2025-01 | Last Mile Circuit Cost | 293287 | 315458
PRJ-2024037 | 2025-01 | Installation Labor | 219965 | 215016
PRJ-2024037 | 2025-01 | Vendor Management Fee | 146643 | 183902
PRJ-2024037 | 2025-01 | Travel & Logistics | 117315 | 114804
PRJ-2024037 | 2025-01 | Project Management Overhead | 102650 | 86524
PRJ-2024037 | 2025-01 | Contingency | 73322 | 59136
PRJ-2024037 | 2025-02 | Equipment/CapEx | 513252 | 365098
PRJ-2024037 | 2025-02 | Last Mile Circuit Cost | 293287 | 328617
PRJ-2024037 | 2025-02 | Installation Labor | 219965 | 185937
PRJ-2024037 | 2025-02 | Vendor Management Fee | 146643 | 176459
PRJ-2024037 | 2025-02 | Travel & Logistics | 117315 | 120498
PRJ-2024037 | 2025-02 | Project Management Overhead | 102650 | 137706
PRJ-2024037 | 2025-02 | Contingency | 73322 | 69213
PRJ-2024037 | 2025-03 | Equipment/CapEx | 513252 | 499570
PRJ-2024037 | 2025-03 | Last Mile Circuit Cost | 293287 | 205484
PRJ-2024037 | 2025-03 | Installation Labor | 219965 | 245567
PRJ-2024037 | 2025-03 | Vendor Management Fee | 146643 | 157869
PRJ-2024037 | 2025-03 | Travel & Logistics | 117315 | 135233
PRJ-2024037 | 2025-03 | Project Management Overhead | 102650 | 95042
PRJ-2024037 | 2025-03 | Contingency | 73322 | 82749
PRJ-2024038 | 2025-08 | Equipment/CapEx | 1458642 | 1330114
PRJ-2024038 | 2025-08 | Last Mile Circuit Cost | 833510 | 1019878
PRJ-2024038 | 2025-08 | Installation Labor | 625132 | 778506
PRJ-2024038 | 2025-08 | Vendor Management Fee | 416755 | 521041
PRJ-2024038 | 2025-08 | Travel & Logistics | 333404 | 361016
PRJ-2024038 | 2025-08 | Project Management Overhead | 291728 | 296958
PRJ-2024038 | 2025-08 | Contingency | 208378 | 150465
PRJ-2024038 | 2025-09 | Equipment/CapEx | 1458642 | 1268167
PRJ-2024038 | 2025-09 | Last Mile Circuit Cost | 833510 | 1027014
PRJ-2024038 | 2025-09 | Installation Labor | 625132 | 519358
PRJ-2024038 | 2025-09 | Vendor Management Fee | 416755 | 357823
PRJ-2024038 | 2025-09 | Travel & Logistics | 333404 | 318436
PRJ-2024038 | 2025-09 | Project Management Overhead | 291728 | 341839
PRJ-2024038 | 2025-09 | Contingency | 208378 | 146628
PRJ-2024038 | 2025-10 | Equipment/CapEx | 1458642 | 1918228
PRJ-2024038 | 2025-10 | Last Mile Circuit Cost | 833510 | 1122295
PRJ-2024038 | 2025-10 | Installation Labor | 625132 | 547525
PRJ-2024038 | 2025-10 | Vendor Management Fee | 416755 | 407049
PRJ-2024038 | 2025-10 | Travel & Logistics | 333404 | 352521
PRJ-2024038 | 2025-10 | Project Management Overhead | 291728 | 305219
PRJ-2024038 | 2025-10 | Contingency | 208378 | 246942
PRJ-2024038 | 2025-11 | Equipment/CapEx | 1458642 | 1249628
PRJ-2024038 | 2025-11 | Last Mile Circuit Cost | 833510 | 941619
PRJ-2024038 | 2025-11 | Installation Labor | 625132 | 744398
PRJ-2024038 | 2025-11 | Vendor Management Fee | 416755 | 431910
PRJ-2024038 | 2025-11 | Travel & Logistics | 333404 | 342306
PRJ-2024038 | 2025-11 | Project Management Overhead | 291728 | 305431
PRJ-2024038 | 2025-11 | Contingency | 208378 | 153738
PRJ-2024039 | 2025-07 | Equipment/CapEx | 105100 | 84557
PRJ-2024039 | 2025-07 | Last Mile Circuit Cost | 60057 | 50329
PRJ-2024039 | 2025-07 | Installation Labor | 45043 | 34297
PRJ-2024039 | 2025-07 | Vendor Management Fee | 30029 | 39906
PRJ-2024039 | 2025-07 | Travel & Logistics | 24023 | 29320
PRJ-2024039 | 2025-07 | Project Management Overhead | 21020 | 20486
PRJ-2024039 | 2025-07 | Contingency | 15014 | 19120
PRJ-2024039 | 2025-08 | Equipment/CapEx | 105100 | 82299
PRJ-2024039 | 2025-08 | Last Mile Circuit Cost | 60057 | 52663
PRJ-2024039 | 2025-08 | Installation Labor | 45043 | 46032
PRJ-2024039 | 2025-08 | Vendor Management Fee | 30029 | 30943
PRJ-2024039 | 2025-08 | Travel & Logistics | 24023 | 17576
PRJ-2024039 | 2025-08 | Project Management Overhead | 21020 | 15160
PRJ-2024039 | 2025-08 | Contingency | 15014 | 13709
PRJ-2024039 | 2025-09 | Equipment/CapEx | 105100 | 77105
PRJ-2024039 | 2025-09 | Last Mile Circuit Cost | 60057 | 42592
PRJ-2024039 | 2025-09 | Installation Labor | 45043 | 34183
PRJ-2024039 | 2025-09 | Vendor Management Fee | 30029 | 26756
PRJ-2024039 | 2025-09 | Travel & Logistics | 24023 | 18723
PRJ-2024039 | 2025-09 | Project Management Overhead | 21020 | 19024
PRJ-2024039 | 2025-09 | Contingency | 15014 | 18195
PRJ-2024040 | 2025-01 | Equipment/CapEx | 1736892 | 2083521
PRJ-2024040 | 2025-01 | Last Mile Circuit Cost | 992510 | 703141
PRJ-2024040 | 2025-01 | Installation Labor | 744382 | 533442
PRJ-2024040 | 2025-01 | Vendor Management Fee | 496255 | 642966
PRJ-2024040 | 2025-01 | Travel & Logistics | 397004 | 451191
PRJ-2024040 | 2025-01 | Project Management Overhead | 347379 | 461324
PRJ-2024040 | 2025-01 | Contingency | 248128 | 322911
PRJ-2024040 | 2025-02 | Equipment/CapEx | 1736892 | 1724707
PRJ-2024040 | 2025-02 | Last Mile Circuit Cost | 992510 | 1029614
PRJ-2024040 | 2025-02 | Installation Labor | 744382 | 975007
PRJ-2024040 | 2025-02 | Vendor Management Fee | 496255 | 430482
PRJ-2024040 | 2025-02 | Travel & Logistics | 397004 | 391711
PRJ-2024040 | 2025-02 | Project Management Overhead | 347379 | 414381
PRJ-2024040 | 2025-02 | Contingency | 248128 | 211073
PRJ-2024040 | 2025-03 | Equipment/CapEx | 1736892 | 1564714
PRJ-2024040 | 2025-03 | Last Mile Circuit Cost | 992510 | 1014837
PRJ-2024040 | 2025-03 | Installation Labor | 744382 | 639132
PRJ-2024040 | 2025-03 | Vendor Management Fee | 496255 | 477013
PRJ-2024040 | 2025-03 | Travel & Logistics | 397004 | 425626
PRJ-2024040 | 2025-03 | Project Management Overhead | 347379 | 428381
PRJ-2024040 | 2025-03 | Contingency | 248128 | 276302
PRJ-2024040 | 2025-04 | Equipment/CapEx | 1736892 | 1252441
PRJ-2024040 | 2025-04 | Last Mile Circuit Cost | 992510 | 1084663
PRJ-2024040 | 2025-04 | Installation Labor | 744382 | 571695
PRJ-2024040 | 2025-04 | Vendor Management Fee | 496255 | 381994
PRJ-2024040 | 2025-04 | Travel & Logistics | 397004 | 414962
PRJ-2024040 | 2025-04 | Project Management Overhead | 347379 | 456839
PRJ-2024040 | 2025-04 | Contingency | 248128 | 234648
PRJ-2024040 | 2025-05 | Equipment/CapEx | 1736892 | 1292238
PRJ-2024040 | 2025-05 | Last Mile Circuit Cost | 992510 | 836063
PRJ-2024040 | 2025-05 | Installation Labor | 744382 | 573909
PRJ-2024040 | 2025-05 | Vendor Management Fee | 496255 | 656737
PRJ-2024040 | 2025-05 | Travel & Logistics | 397004 | 368261
PRJ-2024040 | 2025-05 | Project Management Overhead | 347379 | 271582
PRJ-2024040 | 2025-05 | Contingency | 248128 | 280184
PRJ-2024041 | 2025-08 | Equipment/CapEx | 230275 | 256598
PRJ-2024041 | 2025-08 | Last Mile Circuit Cost | 131586 | 148111
PRJ-2024041 | 2025-08 | Installation Labor | 98689 | 114610
PRJ-2024041 | 2025-08 | Vendor Management Fee | 65793 | 61385
PRJ-2024041 | 2025-08 | Travel & Logistics | 52634 | 39162
PRJ-2024041 | 2025-08 | Project Management Overhead | 46055 | 34831
PRJ-2024041 | 2025-08 | Contingency | 32896 | 42336
PRJ-2024041 | 2025-09 | Equipment/CapEx | 230275 | 259414
PRJ-2024041 | 2025-09 | Last Mile Circuit Cost | 131586 | 108901
PRJ-2024041 | 2025-09 | Installation Labor | 98689 | 91751
PRJ-2024041 | 2025-09 | Vendor Management Fee | 65793 | 58894
PRJ-2024041 | 2025-09 | Travel & Logistics | 52634 | 62434
PRJ-2024041 | 2025-09 | Project Management Overhead | 46055 | 49536
PRJ-2024041 | 2025-09 | Contingency | 32896 | 26578
PRJ-2024041 | 2025-10 | Equipment/CapEx | 230275 | 247619
PRJ-2024041 | 2025-10 | Last Mile Circuit Cost | 131586 | 97503
PRJ-2024041 | 2025-10 | Installation Labor | 98689 | 80722
PRJ-2024041 | 2025-10 | Vendor Management Fee | 65793 | 70205
PRJ-2024041 | 2025-10 | Travel & Logistics | 52634 | 58105
PRJ-2024041 | 2025-10 | Project Management Overhead | 46055 | 54341
PRJ-2024041 | 2025-10 | Contingency | 32896 | 35635
PRJ-2024041 | 2025-11 | Equipment/CapEx | 230275 | 270263
PRJ-2024041 | 2025-11 | Last Mile Circuit Cost | 131586 | 111634
PRJ-2024041 | 2025-11 | Installation Labor | 98689 | 118579
PRJ-2024041 | 2025-11 | Vendor Management Fee | 65793 | 56614
PRJ-2024041 | 2025-11 | Travel & Logistics | 52634 | 55395
PRJ-2024041 | 2025-11 | Project Management Overhead | 46055 | 45639
PRJ-2024041 | 2025-11 | Contingency | 32896 | 31981
PRJ-2024041 | 2025-12 | Equipment/CapEx | 230275 | 231281
PRJ-2024041 | 2025-12 | Last Mile Circuit Cost | 131586 | 165032
PRJ-2024041 | 2025-12 | Installation Labor | 98689 | 71409
PRJ-2024041 | 2025-12 | Vendor Management Fee | 65793 | 73115
PRJ-2024041 | 2025-12 | Travel & Logistics | 52634 | 65288
PRJ-2024041 | 2025-12 | Project Management Overhead | 46055 | 57431
PRJ-2024041 | 2025-12 | Contingency | 32896 | 34223
PRJ-2024041 | 2026-01 | Equipment/CapEx | 230275 | 301579
PRJ-2024041 | 2026-01 | Last Mile Circuit Cost | 131586 | 168769
PRJ-2024041 | 2026-01 | Installation Labor | 98689 | 122808
PRJ-2024041 | 2026-01 | Vendor Management Fee | 65793 | 84298
PRJ-2024041 | 2026-01 | Travel & Logistics | 52634 | 63567
PRJ-2024041 | 2026-01 | Project Management Overhead | 46055 | 57128
PRJ-2024041 | 2026-01 | Contingency | 32896 | 23384
PRJ-2024041 | 2026-02 | Equipment/CapEx | 230275 | 192992
PRJ-2024041 | 2026-02 | Last Mile Circuit Cost | 131586 | 144446
PRJ-2024041 | 2026-02 | Installation Labor | 98689 | 131548
PRJ-2024041 | 2026-02 | Vendor Management Fee | 65793 | 69581
PRJ-2024041 | 2026-02 | Travel & Logistics | 52634 | 55105
PRJ-2024041 | 2026-02 | Project Management Overhead | 46055 | 40823
PRJ-2024041 | 2026-02 | Contingency | 32896 | 37335
PRJ-2024041 | 2026-03 | Equipment/CapEx | 230275 | 258854
PRJ-2024041 | 2026-03 | Last Mile Circuit Cost | 131586 | 93936
PRJ-2024041 | 2026-03 | Installation Labor | 98689 | 75492
PRJ-2024041 | 2026-03 | Vendor Management Fee | 65793 | 54461
PRJ-2024041 | 2026-03 | Travel & Logistics | 52634 | 45014
PRJ-2024041 | 2026-03 | Project Management Overhead | 46055 | 52912
PRJ-2024041 | 2026-03 | Contingency | 32896 | 35183
PRJ-2024042 | 2025-06 | Equipment/CapEx | 1131667 | 942614
PRJ-2024042 | 2025-06 | Last Mile Circuit Cost | 646667 | 714738
PRJ-2024042 | 2025-06 | Installation Labor | 485000 | 555157
PRJ-2024042 | 2025-06 | Vendor Management Fee | 323333 | 320428
PRJ-2024042 | 2025-06 | Travel & Logistics | 258667 | 182500
PRJ-2024042 | 2025-06 | Project Management Overhead | 226333 | 215048
PRJ-2024042 | 2025-06 | Contingency | 161667 | 153296
PRJ-2024042 | 2025-07 | Equipment/CapEx | 1131667 | 1167167
PRJ-2024042 | 2025-07 | Last Mile Circuit Cost | 646667 | 821491
PRJ-2024042 | 2025-07 | Installation Labor | 485000 | 488274
PRJ-2024042 | 2025-07 | Vendor Management Fee | 323333 | 299524
PRJ-2024042 | 2025-07 | Travel & Logistics | 258667 | 233006
PRJ-2024042 | 2025-07 | Project Management Overhead | 226333 | 170180
PRJ-2024042 | 2025-07 | Contingency | 161667 | 147393
PRJ-2024042 | 2025-07 | Equipment/CapEx | 1131667 | 955806
PRJ-2024042 | 2025-07 | Last Mile Circuit Cost | 646667 | 799401
PRJ-2024042 | 2025-07 | Installation Labor | 485000 | 372740
PRJ-2024042 | 2025-07 | Vendor Management Fee | 323333 | 397137
PRJ-2024042 | 2025-07 | Travel & Logistics | 258667 | 266706
PRJ-2024042 | 2025-07 | Project Management Overhead | 226333 | 166743
PRJ-2024042 | 2025-07 | Contingency | 161667 | 159163
PRJ-2024042 | 2025-08 | Equipment/CapEx | 1131667 | 1122500
PRJ-2024042 | 2025-08 | Last Mile Circuit Cost | 646667 | 806678
PRJ-2024042 | 2025-08 | Installation Labor | 485000 | 495011
PRJ-2024042 | 2025-08 | Vendor Management Fee | 323333 | 350944
PRJ-2024042 | 2025-08 | Travel & Logistics | 258667 | 347105
PRJ-2024042 | 2025-08 | Project Management Overhead | 226333 | 273513
PRJ-2024042 | 2025-08 | Contingency | 161667 | 198578
PRJ-2024042 | 2025-09 | Equipment/CapEx | 1131667 | 1203124
PRJ-2024042 | 2025-09 | Last Mile Circuit Cost | 646667 | 707714
PRJ-2024042 | 2025-09 | Installation Labor | 485000 | 580111
PRJ-2024042 | 2025-09 | Vendor Management Fee | 323333 | 410139
PRJ-2024042 | 2025-09 | Travel & Logistics | 258667 | 190999
PRJ-2024042 | 2025-09 | Project Management Overhead | 226333 | 181396
PRJ-2024042 | 2025-09 | Contingency | 161667 | 215110
PRJ-2024042 | 2025-10 | Equipment/CapEx | 1131667 | 1521109
PRJ-2024042 | 2025-10 | Last Mile Circuit Cost | 646667 | 587001
PRJ-2024042 | 2025-10 | Installation Labor | 485000 | 477533
PRJ-2024042 | 2025-10 | Vendor Management Fee | 323333 | 233373
PRJ-2024042 | 2025-10 | Travel & Logistics | 258667 | 265719
PRJ-2024042 | 2025-10 | Project Management Overhead | 226333 | 269124
PRJ-2024042 | 2025-10 | Contingency | 161667 | 132681

## SLA_Governance
ProjectID | ClientID | SLAMetric | Target | AchievedPercent | ComplianceStatus | PenaltyApplicableINR | ReportingPeriod
PRJ-2024001 | CL002 | Site Installation TAT | ≤ 21 days | 92.8 | Marginal | 13391 | Q2 2026
PRJ-2024001 | CL002 | Fault Resolution Time | ≤ 4 hours | 82.6 | Breached | 13397 | Q2 2026
PRJ-2024001 | CL002 | Uptime % | ≥ 99.5% | 86.2 | Breached | 138136 | Q2 2026
PRJ-2024001 | CL002 | Change Request Turnaround | ≤ 5 days | 89.6 | Marginal | 39036 | Q2 2026
PRJ-2024001 | CL002 | Escalation Response Time | ≤ 2 hours | 91 | Marginal | 178665 | Q2 2026
PRJ-2024002 | CL004 | Site Installation TAT | ≤ 21 days | 81.7 | Breached | 166525 | Q2 2026
PRJ-2024002 | CL004 | Fault Resolution Time | ≤ 4 hours | 88.3 | Marginal | 55866 | Q2 2026
PRJ-2024002 | CL004 | Uptime % | ≥ 99.5% | 86.2 | Breached | 99549 | Q2 2026
PRJ-2024002 | CL004 | Change Request Turnaround | ≤ 5 days | 94.4 | Marginal | 131984 | Q2 2026
PRJ-2024002 | CL004 | Escalation Response Time | ≤ 2 hours | 79.4 | Breached | 116135 | Q2 2026
PRJ-2024003 | CL007 | Site Installation TAT | ≤ 21 days | 84.1 | Breached | 118581 | Q2 2026
PRJ-2024003 | CL007 | Fault Resolution Time | ≤ 4 hours | 88.4 | Marginal | 77833 | Q2 2026
PRJ-2024003 | CL007 | Uptime % | ≥ 99.5% | 93.2 | Marginal | 34836 | Q2 2026
PRJ-2024003 | CL007 | Change Request Turnaround | ≤ 5 days | 93.1 | Marginal | 91048 | Q2 2026
PRJ-2024003 | CL007 | Escalation Response Time | ≤ 2 hours | 84.9 | Breached | 128648 | Q2 2026
PRJ-2024004 | CL001 | Site Installation TAT | ≤ 21 days | 85.8 | Breached | 56582 | Q2 2026
PRJ-2024004 | CL001 | Fault Resolution Time | ≤ 4 hours | 85.7 | Breached | 198527 | Q2 2026
PRJ-2024004 | CL001 | Uptime % | ≥ 99.5% | 84.5 | Breached | 87901 | Q2 2026
PRJ-2024004 | CL001 | Change Request Turnaround | ≤ 5 days | 92.8 | Marginal | 145845 | Q2 2026
PRJ-2024004 | CL001 | Escalation Response Time | ≤ 2 hours | 89.6 | Marginal | 94708 | Q2 2026
PRJ-2024005 | CL002 | Site Installation TAT | ≤ 21 days | 81 | Breached | 119906 | Q2 2026
PRJ-2024005 | CL002 | Fault Resolution Time | ≤ 4 hours | 92.3 | Marginal | 168215 | Q2 2026
PRJ-2024005 | CL002 | Uptime % | ≥ 99.5% | 90.5 | Marginal | 22722 | Q2 2026
PRJ-2024005 | CL002 | Change Request Turnaround | ≤ 5 days | 93.4 | Marginal | 146478 | Q2 2026
PRJ-2024005 | CL002 | Escalation Response Time | ≤ 2 hours | 86 | Breached | 37322 | Q2 2026
PRJ-2024006 | CL001 | Site Installation TAT | ≤ 21 days | 94.6 | Marginal | 37007 | Q2 2026
PRJ-2024006 | CL001 | Fault Resolution Time | ≤ 4 hours | 95.9 | Met | 0 | Q2 2026
PRJ-2024006 | CL001 | Uptime % | ≥ 99.5% | 84.9 | Breached | 123450 | Q2 2026
PRJ-2024006 | CL001 | Change Request Turnaround | ≤ 5 days | 88.4 | Marginal | 75445 | Q2 2026
PRJ-2024006 | CL001 | Escalation Response Time | ≤ 2 hours | 95.2 | Met | 0 | Q2 2026
PRJ-2024007 | CL004 | Site Installation TAT | ≤ 21 days | 89.8 | Marginal | 100261 | Q2 2026
PRJ-2024007 | CL004 | Fault Resolution Time | ≤ 4 hours | 79.6 | Breached | 130572 | Q2 2026
PRJ-2024007 | CL004 | Uptime % | ≥ 99.5% | 87.3 | Breached | 120221 | Q2 2026
PRJ-2024007 | CL004 | Change Request Turnaround | ≤ 5 days | 88.8 | Marginal | 19719 | Q2 2026
PRJ-2024007 | CL004 | Escalation Response Time | ≤ 2 hours | 92.1 | Marginal | 25803 | Q2 2026
PRJ-2024008 | CL003 | Site Installation TAT | ≤ 21 days | 92.4 | Marginal | 149475 | Q2 2026
PRJ-2024008 | CL003 | Fault Resolution Time | ≤ 4 hours | 78.2 | Breached | 169519 | Q2 2026
PRJ-2024008 | CL003 | Uptime % | ≥ 99.5% | 89.9 | Marginal | 142121 | Q2 2026
PRJ-2024008 | CL003 | Change Request Turnaround | ≤ 5 days | 94 | Marginal | 27750 | Q2 2026
PRJ-2024008 | CL003 | Escalation Response Time | ≤ 2 hours | 96.7 | Met | 0 | Q2 2026
PRJ-2024009 | CL006 | Site Installation TAT | ≤ 21 days | 82.9 | Breached | 123748 | Q2 2026
PRJ-2024009 | CL006 | Fault Resolution Time | ≤ 4 hours | 85.1 | Breached | 25868 | Q2 2026
PRJ-2024009 | CL006 | Uptime % | ≥ 99.5% | 81.9 | Breached | 137105 | Q2 2026
PRJ-2024009 | CL006 | Change Request Turnaround | ≤ 5 days | 85 | Breached | 122283 | Q2 2026
PRJ-2024009 | CL006 | Escalation Response Time | ≤ 2 hours | 79.1 | Breached | 173998 | Q2 2026
PRJ-2024010 | CL003 | Site Installation TAT | ≤ 21 days | 84.5 | Breached | 100204 | Q2 2026
PRJ-2024010 | CL003 | Fault Resolution Time | ≤ 4 hours | 86.2 | Breached | 190394 | Q2 2026
PRJ-2024010 | CL003 | Uptime % | ≥ 99.5% | 83.3 | Breached | 64150 | Q2 2026
PRJ-2024010 | CL003 | Change Request Turnaround | ≤ 5 days | 94.9 | Marginal | 161541 | Q2 2026
PRJ-2024010 | CL003 | Escalation Response Time | ≤ 2 hours | 81.3 | Breached | 88814 | Q2 2026
PRJ-2024011 | CL002 | Site Installation TAT | ≤ 21 days | 91.6 | Marginal | 104257 | Q2 2026
PRJ-2024011 | CL002 | Fault Resolution Time | ≤ 4 hours | 81 | Breached | 94154 | Q2 2026
PRJ-2024011 | CL002 | Uptime % | ≥ 99.5% | 87.9 | Breached | 98867 | Q2 2026
PRJ-2024011 | CL002 | Change Request Turnaround | ≤ 5 days | 79.7 | Breached | 98406 | Q2 2026
PRJ-2024011 | CL002 | Escalation Response Time | ≤ 2 hours | 93.7 | Marginal | 149058 | Q2 2026
PRJ-2024012 | CL008 | Site Installation TAT | ≤ 21 days | 98.5 | Met | 0 | Q2 2026
PRJ-2024012 | CL008 | Fault Resolution Time | ≤ 4 hours | 91.9 | Marginal | 115494 | Q2 2026
PRJ-2024012 | CL008 | Uptime % | ≥ 99.5% | 82.2 | Breached | 152584 | Q2 2026
PRJ-2024012 | CL008 | Change Request Turnaround | ≤ 5 days | 78.2 | Breached | 177729 | Q2 2026
PRJ-2024012 | CL008 | Escalation Response Time | ≤ 2 hours | 82.4 | Breached | 53565 | Q2 2026
PRJ-2024013 | CL006 | Site Installation TAT | ≤ 21 days | 99 | Met | 0 | Q2 2026
PRJ-2024013 | CL006 | Fault Resolution Time | ≤ 4 hours | 99.7 | Met | 0 | Q2 2026
PRJ-2024013 | CL006 | Uptime % | ≥ 99.5% | 94.1 | Marginal | 48101 | Q2 2026
PRJ-2024013 | CL006 | Change Request Turnaround | ≤ 5 days | 88.1 | Marginal | 108968 | Q2 2026
PRJ-2024013 | CL006 | Escalation Response Time | ≤ 2 hours | 80.4 | Breached | 147713 | Q2 2026
PRJ-2024014 | CL007 | Site Installation TAT | ≤ 21 days | 94.3 | Marginal | 112153 | Q2 2026
PRJ-2024014 | CL007 | Fault Resolution Time | ≤ 4 hours | 94.8 | Marginal | 197500 | Q2 2026
PRJ-2024014 | CL007 | Uptime % | ≥ 99.5% | 98.3 | Met | 0 | Q2 2026
PRJ-2024014 | CL007 | Change Request Turnaround | ≤ 5 days | 89.1 | Marginal | 175658 | Q2 2026
PRJ-2024014 | CL007 | Escalation Response Time | ≤ 2 hours | 86.2 | Breached | 131292 | Q2 2026
PRJ-2024015 | CL008 | Site Installation TAT | ≤ 21 days | 98.9 | Met | 0 | Q2 2026
PRJ-2024015 | CL008 | Fault Resolution Time | ≤ 4 hours | 83.5 | Breached | 119567 | Q2 2026
PRJ-2024015 | CL008 | Uptime % | ≥ 99.5% | 93.8 | Marginal | 57150 | Q2 2026
PRJ-2024015 | CL008 | Change Request Turnaround | ≤ 5 days | 98.8 | Met | 0 | Q2 2026
PRJ-2024015 | CL008 | Escalation Response Time | ≤ 2 hours | 99.7 | Met | 0 | Q2 2026
PRJ-2024016 | CL007 | Site Installation TAT | ≤ 21 days | 91.8 | Marginal | 16444 | Q2 2026
PRJ-2024016 | CL007 | Fault Resolution Time | ≤ 4 hours | 82.6 | Breached | 155885 | Q2 2026
PRJ-2024016 | CL007 | Uptime % | ≥ 99.5% | 85.5 | Breached | 83166 | Q2 2026
PRJ-2024016 | CL007 | Change Request Turnaround | ≤ 5 days | 88.2 | Marginal | 126365 | Q2 2026
PRJ-2024016 | CL007 | Escalation Response Time | ≤ 2 hours | 94.4 | Marginal | 192206 | Q2 2026
PRJ-2024017 | CL004 | Site Installation TAT | ≤ 21 days | 82 | Breached | 148047 | Q2 2026
PRJ-2024017 | CL004 | Fault Resolution Time | ≤ 4 hours | 80.1 | Breached | 59600 | Q2 2026
PRJ-2024017 | CL004 | Uptime % | ≥ 99.5% | 98 | Met | 0 | Q2 2026
PRJ-2024017 | CL004 | Change Request Turnaround | ≤ 5 days | 95.4 | Met | 0 | Q2 2026
PRJ-2024017 | CL004 | Escalation Response Time | ≤ 2 hours | 81.4 | Breached | 199767 | Q2 2026
PRJ-2024018 | CL004 | Site Installation TAT | ≤ 21 days | 90.5 | Marginal | 83536 | Q2 2026
PRJ-2024018 | CL004 | Fault Resolution Time | ≤ 4 hours | 80 | Breached | 196836 | Q2 2026
PRJ-2024018 | CL004 | Uptime % | ≥ 99.5% | 99 | Met | 0 | Q2 2026
PRJ-2024018 | CL004 | Change Request Turnaround | ≤ 5 days | 98.3 | Met | 0 | Q2 2026
PRJ-2024018 | CL004 | Escalation Response Time | ≤ 2 hours | 93.3 | Marginal | 46568 | Q2 2026
PRJ-2024019 | CL003 | Site Installation TAT | ≤ 21 days | 89.1 | Marginal | 192768 | Q2 2026
PRJ-2024019 | CL003 | Fault Resolution Time | ≤ 4 hours | 78 | Breached | 112696 | Q2 2026
PRJ-2024019 | CL003 | Uptime % | ≥ 99.5% | 82 | Breached | 73085 | Q2 2026
PRJ-2024019 | CL003 | Change Request Turnaround | ≤ 5 days | 92.9 | Marginal | 75721 | Q2 2026
PRJ-2024019 | CL003 | Escalation Response Time | ≤ 2 hours | 96.9 | Met | 0 | Q2 2026
PRJ-2024020 | CL005 | Site Installation TAT | ≤ 21 days | 80.1 | Breached | 141543 | Q2 2026
PRJ-2024020 | CL005 | Fault Resolution Time | ≤ 4 hours | 85.9 | Breached | 99581 | Q2 2026
PRJ-2024020 | CL005 | Uptime % | ≥ 99.5% | 86 | Breached | 26888 | Q2 2026
PRJ-2024020 | CL005 | Change Request Turnaround | ≤ 5 days | 96.4 | Met | 0 | Q2 2026
PRJ-2024020 | CL005 | Escalation Response Time | ≤ 2 hours | 91.4 | Marginal | 93439 | Q2 2026
PRJ-2024021 | CL003 | Site Installation TAT | ≤ 21 days | 89.7 | Marginal | 148893 | Q2 2026
PRJ-2024021 | CL003 | Fault Resolution Time | ≤ 4 hours | 97.4 | Met | 0 | Q2 2026
PRJ-2024021 | CL003 | Uptime % | ≥ 99.5% | 98 | Met | 0 | Q2 2026
PRJ-2024021 | CL003 | Change Request Turnaround | ≤ 5 days | 79.9 | Breached | 10943 | Q2 2026
PRJ-2024021 | CL003 | Escalation Response Time | ≤ 2 hours | 79.1 | Breached | 70880 | Q2 2026
PRJ-2024022 | CL005 | Site Installation TAT | ≤ 21 days | 85.6 | Breached | 68892 | Q2 2026
PRJ-2024022 | CL005 | Fault Resolution Time | ≤ 4 hours | 78.6 | Breached | 51553 | Q2 2026
PRJ-2024022 | CL005 | Uptime % | ≥ 99.5% | 89 | Marginal | 123008 | Q2 2026
PRJ-2024022 | CL005 | Change Request Turnaround | ≤ 5 days | 88.4 | Marginal | 95559 | Q2 2026
PRJ-2024022 | CL005 | Escalation Response Time | ≤ 2 hours | 92.6 | Marginal | 170529 | Q2 2026
PRJ-2024023 | CL007 | Site Installation TAT | ≤ 21 days | 78.2 | Breached | 127119 | Q2 2026
PRJ-2024023 | CL007 | Fault Resolution Time | ≤ 4 hours | 90.6 | Marginal | 153304 | Q2 2026
PRJ-2024023 | CL007 | Uptime % | ≥ 99.5% | 98.7 | Met | 0 | Q2 2026
PRJ-2024023 | CL007 | Change Request Turnaround | ≤ 5 days | 85.9 | Breached | 36283 | Q2 2026
PRJ-2024023 | CL007 | Escalation Response Time | ≤ 2 hours | 87.3 | Breached | 142053 | Q2 2026
PRJ-2024024 | CL003 | Site Installation TAT | ≤ 21 days | 90.7 | Marginal | 124474 | Q2 2026
PRJ-2024024 | CL003 | Fault Resolution Time | ≤ 4 hours | 92.3 | Marginal | 34216 | Q2 2026
PRJ-2024024 | CL003 | Uptime % | ≥ 99.5% | 82.2 | Breached | 106124 | Q2 2026
PRJ-2024024 | CL003 | Change Request Turnaround | ≤ 5 days | 79.3 | Breached | 119530 | Q2 2026
PRJ-2024024 | CL003 | Escalation Response Time | ≤ 2 hours | 81.8 | Breached | 151530 | Q2 2026
PRJ-2024025 | CL008 | Site Installation TAT | ≤ 21 days | 86.9 | Breached | 150573 | Q2 2026
PRJ-2024025 | CL008 | Fault Resolution Time | ≤ 4 hours | 84.8 | Breached | 86591 | Q2 2026
PRJ-2024025 | CL008 | Uptime % | ≥ 99.5% | 98.9 | Met | 0 | Q2 2026
PRJ-2024025 | CL008 | Change Request Turnaround | ≤ 5 days | 82.6 | Breached | 124885 | Q2 2026
PRJ-2024025 | CL008 | Escalation Response Time | ≤ 2 hours | 86.4 | Breached | 189626 | Q2 2026
PRJ-2024026 | CL005 | Site Installation TAT | ≤ 21 days | 92.8 | Marginal | 151103 | Q2 2026
PRJ-2024026 | CL005 | Fault Resolution Time | ≤ 4 hours | 81.8 | Breached | 15317 | Q2 2026
PRJ-2024026 | CL005 | Uptime % | ≥ 99.5% | 90.6 | Marginal | 104765 | Q2 2026
PRJ-2024026 | CL005 | Change Request Turnaround | ≤ 5 days | 89.9 | Marginal | 56423 | Q2 2026
PRJ-2024026 | CL005 | Escalation Response Time | ≤ 2 hours | 89.4 | Marginal | 180673 | Q2 2026
PRJ-2024027 | CL001 | Site Installation TAT | ≤ 21 days | 91.9 | Marginal | 113562 | Q2 2026
PRJ-2024027 | CL001 | Fault Resolution Time | ≤ 4 hours | 88.2 | Marginal | 184163 | Q2 2026
PRJ-2024027 | CL001 | Uptime % | ≥ 99.5% | 82.7 | Breached | 64876 | Q2 2026
PRJ-2024027 | CL001 | Change Request Turnaround | ≤ 5 days | 79.7 | Breached | 63046 | Q2 2026
PRJ-2024027 | CL001 | Escalation Response Time | ≤ 2 hours | 83.3 | Breached | 155256 | Q2 2026
PRJ-2024028 | CL003 | Site Installation TAT | ≤ 21 days | 84.4 | Breached | 20978 | Q2 2026
PRJ-2024028 | CL003 | Fault Resolution Time | ≤ 4 hours | 80.2 | Breached | 51339 | Q2 2026
PRJ-2024028 | CL003 | Uptime % | ≥ 99.5% | 94.2 | Marginal | 49911 | Q2 2026
PRJ-2024028 | CL003 | Change Request Turnaround | ≤ 5 days | 89.2 | Marginal | 13743 | Q2 2026
PRJ-2024028 | CL003 | Escalation Response Time | ≤ 2 hours | 83.1 | Breached | 64390 | Q2 2026
PRJ-2024029 | CL004 | Site Installation TAT | ≤ 21 days | 93.3 | Marginal | 116227 | Q2 2026
PRJ-2024029 | CL004 | Fault Resolution Time | ≤ 4 hours | 84.8 | Breached | 22871 | Q2 2026
PRJ-2024029 | CL004 | Uptime % | ≥ 99.5% | 89.2 | Marginal | 84444 | Q2 2026
PRJ-2024029 | CL004 | Change Request Turnaround | ≤ 5 days | 95.1 | Met | 0 | Q2 2026
PRJ-2024029 | CL004 | Escalation Response Time | ≤ 2 hours | 92.6 | Marginal | 83737 | Q2 2026
PRJ-2024030 | CL004 | Site Installation TAT | ≤ 21 days | 90.4 | Marginal | 175593 | Q2 2026
PRJ-2024030 | CL004 | Fault Resolution Time | ≤ 4 hours | 80 | Breached | 72794 | Q2 2026
PRJ-2024030 | CL004 | Uptime % | ≥ 99.5% | 83.5 | Breached | 180917 | Q2 2026
PRJ-2024030 | CL004 | Change Request Turnaround | ≤ 5 days | 93.4 | Marginal | 188208 | Q2 2026
PRJ-2024030 | CL004 | Escalation Response Time | ≤ 2 hours | 78.8 | Breached | 34908 | Q2 2026
PRJ-2024031 | CL003 | Site Installation TAT | ≤ 21 days | 79.3 | Breached | 190793 | Q2 2026
PRJ-2024031 | CL003 | Fault Resolution Time | ≤ 4 hours | 80.1 | Breached | 118016 | Q2 2026
PRJ-2024031 | CL003 | Uptime % | ≥ 99.5% | 83.1 | Breached | 108394 | Q2 2026
PRJ-2024031 | CL003 | Change Request Turnaround | ≤ 5 days | 87.4 | Breached | 47664 | Q2 2026
PRJ-2024031 | CL003 | Escalation Response Time | ≤ 2 hours | 89.4 | Marginal | 105114 | Q2 2026
PRJ-2024032 | CL008 | Site Installation TAT | ≤ 21 days | 96.2 | Met | 0 | Q2 2026
PRJ-2024032 | CL008 | Fault Resolution Time | ≤ 4 hours | 84.7 | Breached | 86049 | Q2 2026
PRJ-2024032 | CL008 | Uptime % | ≥ 99.5% | 94.4 | Marginal | 149833 | Q2 2026
PRJ-2024032 | CL008 | Change Request Turnaround | ≤ 5 days | 91.9 | Marginal | 128938 | Q2 2026
PRJ-2024032 | CL008 | Escalation Response Time | ≤ 2 hours | 91.4 | Marginal | 109185 | Q2 2026
PRJ-2024033 | CL005 | Site Installation TAT | ≤ 21 days | 81.3 | Breached | 160716 | Q2 2026
PRJ-2024033 | CL005 | Fault Resolution Time | ≤ 4 hours | 85.7 | Breached | 37287 | Q2 2026
PRJ-2024033 | CL005 | Uptime % | ≥ 99.5% | 91.8 | Marginal | 144073 | Q2 2026
PRJ-2024033 | CL005 | Change Request Turnaround | ≤ 5 days | 84.8 | Breached | 121932 | Q2 2026
PRJ-2024033 | CL005 | Escalation Response Time | ≤ 2 hours | 79.7 | Breached | 110309 | Q2 2026
PRJ-2024034 | CL008 | Site Installation TAT | ≤ 21 days | 93.9 | Marginal | 118677 | Q2 2026
PRJ-2024034 | CL008 | Fault Resolution Time | ≤ 4 hours | 94.3 | Marginal | 182968 | Q2 2026
PRJ-2024034 | CL008 | Uptime % | ≥ 99.5% | 95.2 | Met | 0 | Q2 2026
PRJ-2024034 | CL008 | Change Request Turnaround | ≤ 5 days | 82 | Breached | 112096 | Q2 2026
PRJ-2024034 | CL008 | Escalation Response Time | ≤ 2 hours | 97.4 | Met | 0 | Q2 2026
PRJ-2024035 | CL008 | Site Installation TAT | ≤ 21 days | 84.5 | Breached | 164963 | Q2 2026
PRJ-2024035 | CL008 | Fault Resolution Time | ≤ 4 hours | 78.4 | Breached | 37237 | Q2 2026
PRJ-2024035 | CL008 | Uptime % | ≥ 99.5% | 87.6 | Breached | 170558 | Q2 2026
PRJ-2024035 | CL008 | Change Request Turnaround | ≤ 5 days | 92.4 | Marginal | 62232 | Q2 2026
PRJ-2024035 | CL008 | Escalation Response Time | ≤ 2 hours | 89.1 | Marginal | 176252 | Q2 2026
PRJ-2024036 | CL002 | Site Installation TAT | ≤ 21 days | 91.6 | Marginal | 198496 | Q2 2026
PRJ-2024036 | CL002 | Fault Resolution Time | ≤ 4 hours | 86.3 | Breached | 45152 | Q2 2026
PRJ-2024036 | CL002 | Uptime % | ≥ 99.5% | 97.7 | Met | 0 | Q2 2026
PRJ-2024036 | CL002 | Change Request Turnaround | ≤ 5 days | 84 | Breached | 16266 | Q2 2026
PRJ-2024036 | CL002 | Escalation Response Time | ≤ 2 hours | 87.1 | Breached | 174229 | Q2 2026
PRJ-2024037 | CL002 | Site Installation TAT | ≤ 21 days | 88.7 | Marginal | 152697 | Q2 2026
PRJ-2024037 | CL002 | Fault Resolution Time | ≤ 4 hours | 84.3 | Breached | 133375 | Q2 2026
PRJ-2024037 | CL002 | Uptime % | ≥ 99.5% | 97 | Met | 0 | Q2 2026
PRJ-2024037 | CL002 | Change Request Turnaround | ≤ 5 days | 82.8 | Breached | 48666 | Q2 2026
PRJ-2024037 | CL002 | Escalation Response Time | ≤ 2 hours | 97.8 | Met | 0 | Q2 2026
PRJ-2024038 | CL008 | Site Installation TAT | ≤ 21 days | 87.4 | Breached | 24674 | Q2 2026
PRJ-2024038 | CL008 | Fault Resolution Time | ≤ 4 hours | 97.1 | Met | 0 | Q2 2026
PRJ-2024038 | CL008 | Uptime % | ≥ 99.5% | 97.9 | Met | 0 | Q2 2026
PRJ-2024038 | CL008 | Change Request Turnaround | ≤ 5 days | 84 | Breached | 65432 | Q2 2026
PRJ-2024038 | CL008 | Escalation Response Time | ≤ 2 hours | 94.9 | Marginal | 160008 | Q2 2026
PRJ-2024039 | CL001 | Site Installation TAT | ≤ 21 days | 82.3 | Breached | 79750 | Q2 2026
PRJ-2024039 | CL001 | Fault Resolution Time | ≤ 4 hours | 94.2 | Marginal | 13666 | Q2 2026
PRJ-2024039 | CL001 | Uptime % | ≥ 99.5% | 88 | Marginal | 27739 | Q2 2026
PRJ-2024039 | CL001 | Change Request Turnaround | ≤ 5 days | 92 | Marginal | 14013 | Q2 2026
PRJ-2024039 | CL001 | Escalation Response Time | ≤ 2 hours | 93 | Marginal | 54967 | Q2 2026
PRJ-2024040 | CL006 | Site Installation TAT | ≤ 21 days | 91.4 | Marginal | 108267 | Q2 2026
PRJ-2024040 | CL006 | Fault Resolution Time | ≤ 4 hours | 78.5 | Breached | 73932 | Q2 2026
PRJ-2024040 | CL006 | Uptime % | ≥ 99.5% | 92.4 | Marginal | 16693 | Q2 2026
PRJ-2024040 | CL006 | Change Request Turnaround | ≤ 5 days | 99.6 | Met | 0 | Q2 2026
PRJ-2024040 | CL006 | Escalation Response Time | ≤ 2 hours | 91.9 | Marginal | 17977 | Q2 2026
PRJ-2024041 | CL005 | Site Installation TAT | ≤ 21 days | 96.3 | Met | 0 | Q2 2026
PRJ-2024041 | CL005 | Fault Resolution Time | ≤ 4 hours | 87.5 | Breached | 34716 | Q2 2026
PRJ-2024041 | CL005 | Uptime % | ≥ 99.5% | 83.5 | Breached | 99081 | Q2 2026
PRJ-2024041 | CL005 | Change Request Turnaround | ≤ 5 days | 83.1 | Breached | 68294 | Q2 2026
PRJ-2024041 | CL005 | Escalation Response Time | ≤ 2 hours | 92.3 | Marginal | 41996 | Q2 2026
PRJ-2024042 | CL008 | Site Installation TAT | ≤ 21 days | 88.9 | Marginal | 31123 | Q2 2026
PRJ-2024042 | CL008 | Fault Resolution Time | ≤ 4 hours | 83.6 | Breached | 160709 | Q2 2026
PRJ-2024042 | CL008 | Uptime % | ≥ 99.5% | 94.6 | Marginal | 103541 | Q2 2026
PRJ-2024042 | CL008 | Change Request Turnaround | ≤ 5 days | 83.6 | Breached | 27298 | Q2 2026
PRJ-2024042 | CL008 | Escalation Response Time | ≤ 2 hours | 81.7 | Breached | 154809 | Q2 2026

## Client_Master
ClientID | ClientName | Industry | Tier | RelationshipOwner | ContractType
CL001 | Hitachi Payments Services | BFSI - Payments/ATM | Tier 1 | Rahul Mehta | Managed Services + Rollout
CL002 | Axis Bank Ltd | BFSI - Banking | Tier 1 | Priya Sharma | MPLS + SD-WAN
CL003 | State Bank of India | BFSI - Banking | Tier 1 | Anil Kapoor | Pan-India MPLS
CL004 | Bajaj Finance Ltd | BFSI - NBFC | Tier 1 | Sneha Iyer | SD-WAN Rollout
CL005 | HDFC Bank Ltd | BFSI - Banking | Tier 1 | Vikram Singh | VSAT + MPLS Hybrid
CL006 | ICICI Bank Ltd | BFSI - Banking | Tier 1 | Rohit Verma | SD-WAN Migration
CL007 | Muthoot Finance | BFSI - NBFC | Tier 2 | Sneha Iyer | VSAT Rollout
CL008 | Aditya Birla Finance | BFSI - NBFC | Tier 2 | Anil Kapoor | MPLS Rollout

## Weekly_Status_Log
LogID | ProjectID | WeekEndingDate | SitesCompletedCumulative | PercentCompleteSnapshot | WeeklyRAGStatus | KeyUpdate | OpenIssuesCount | PreparedBy
LOG-000001 | PRJ-2024001 | 2024-08-08 | 9 | 6 | Green | Equipment dispatch completed; installation team mobilized | 2 | Rahul K. Patil
LOG-000002 | PRJ-2024001 | 2024-08-15 | 12 | 8 | Green | Resource constraint flagged; additional field engineer requested | 2 | Rahul K. Patil
LOG-000003 | PRJ-2024001 | 2024-08-22 | 19 | 13 | Red | Survey activities progressing as per plan across allocated sites | 5 | Rahul K. Patil
LOG-000004 | PRJ-2024001 | 2024-08-29 | 28 | 19 | Green | Survey activities progressing as per plan across allocated sites | 8 | Rahul K. Patil
LOG-000005 | PRJ-2024001 | 2024-09-05 | 36 | 24 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Rahul K. Patil
LOG-000006 | PRJ-2024001 | 2024-09-12 | 42 | 28 | Amber | Vendor escalation raised for delayed circuit provisioning | 0 | Rahul K. Patil
LOG-000007 | PRJ-2024001 | 2024-09-19 | 43 | 29 | Green | Client UAT sign-off received for batch of completed sites | 6 | Rahul K. Patil
LOG-000008 | PRJ-2024001 | 2024-09-26 | 46 | 31 | Green | Survey activities progressing as per plan across allocated sites | 5 | Rahul K. Patil
LOG-000009 | PRJ-2024001 | 2024-10-03 | 48 | 32 | Amber | Weekly governance call held with client stakeholders | 3 | Rahul K. Patil
LOG-000010 | PRJ-2024001 | 2024-10-10 | 57 | 38 | Green | Equipment dispatch completed; installation team mobilized | 1 | Rahul K. Patil
LOG-000011 | PRJ-2024001 | 2024-10-17 | 60 | 40 | Red | Equipment dispatch completed; installation team mobilized | 3 | Rahul K. Patil
LOG-000012 | PRJ-2024001 | 2024-10-24 | 61 | 41 | Green | Resource constraint flagged; additional field engineer requested | 2 | Rahul K. Patil
LOG-000013 | PRJ-2024001 | 2024-10-31 | 66 | 44 | Green | Weekly governance call held with client stakeholders | 2 | Rahul K. Patil
LOG-000014 | PRJ-2024001 | 2024-11-07 | 72 | 48 | Green | Vendor escalation raised for delayed circuit provisioning | 6 | Rahul K. Patil
LOG-000015 | PRJ-2024001 | 2024-11-14 | 75 | 50 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Rahul K. Patil
LOG-000016 | PRJ-2024001 | 2024-11-21 | 82 | 55 | Green | Equipment dispatch completed; installation team mobilized | 0 | Rahul K. Patil
LOG-000017 | PRJ-2024001 | 2024-11-28 | 91 | 61 | Green | Client UAT sign-off received for batch of completed sites | 6 | Rahul K. Patil
LOG-000018 | PRJ-2024001 | 2024-12-05 | 96 | 64 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Rahul K. Patil
LOG-000019 | PRJ-2024001 | 2024-12-12 | 99 | 66 | Red | Resource constraint flagged; additional field engineer requested | 5 | Rahul K. Patil
LOG-000020 | PRJ-2024001 | 2024-12-19 | 108 | 72 | Red | Survey activities progressing as per plan across allocated sites | 3 | Rahul K. Patil
LOG-000021 | PRJ-2024001 | 2024-12-26 | 111 | 74 | Green | Vendor escalation raised for delayed circuit provisioning | 6 | Rahul K. Patil
LOG-000022 | PRJ-2024001 | 2025-01-02 | 120 | 80 | Green | Resource constraint flagged; additional field engineer requested | 1 | Rahul K. Patil
LOG-000023 | PRJ-2024001 | 2025-01-09 | 124 | 83 | Red | Client UAT sign-off received for batch of completed sites | 3 | Rahul K. Patil
LOG-000024 | PRJ-2024001 | 2025-01-16 | 127 | 85 | Red | Weekly governance call held with client stakeholders | 0 | Rahul K. Patil
LOG-000025 | PRJ-2024001 | 2025-01-23 | 135 | 90 | Green | Resource constraint flagged; additional field engineer requested | 0 | Rahul K. Patil
LOG-000026 | PRJ-2024001 | 2025-01-30 | 139 | 93 | Green | Resource constraint flagged; additional field engineer requested | 4 | Rahul K. Patil
LOG-000027 | PRJ-2024001 | 2025-02-06 | 148 | 99 | Red | Resource constraint flagged; additional field engineer requested | 7 | Rahul K. Patil
LOG-000028 | PRJ-2024001 | 2025-02-13 | 150 | 100 | Green | Equipment dispatch completed; installation team mobilized | 0 | Rahul K. Patil
LOG-000029 | PRJ-2024002 | 2024-10-19 | 6 | 3 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Sandeep Rao
LOG-000030 | PRJ-2024002 | 2024-10-26 | 10 | 5 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Sandeep Rao
LOG-000031 | PRJ-2024002 | 2024-11-02 | 12 | 6 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Sandeep Rao
LOG-000032 | PRJ-2024002 | 2024-11-09 | 20 | 10 | Green | Equipment dispatch completed; installation team mobilized | 4 | Sandeep Rao
LOG-000033 | PRJ-2024002 | 2024-11-16 | 28 | 14 | Red | Weekly governance call held with client stakeholders | 3 | Sandeep Rao
LOG-000034 | PRJ-2024002 | 2024-11-23 | 38 | 19 | Green | Weekly governance call held with client stakeholders | 1 | Sandeep Rao
LOG-000035 | PRJ-2024002 | 2024-11-30 | 46 | 23 | Green | Client UAT sign-off received for batch of completed sites | 4 | Sandeep Rao
LOG-000036 | PRJ-2024002 | 2024-12-07 | 58 | 29 | Green | Survey activities progressing as per plan across allocated sites | 3 | Sandeep Rao
LOG-000037 | PRJ-2024002 | 2024-12-14 | 70 | 35 | Green | Equipment dispatch completed; installation team mobilized | 6 | Sandeep Rao
LOG-000038 | PRJ-2024002 | 2024-12-21 | 80 | 40 | Red | Weekly governance call held with client stakeholders | 4 | Sandeep Rao
LOG-000039 | PRJ-2024002 | 2024-12-28 | 90 | 45 | Amber | Equipment dispatch completed; installation team mobilized | 7 | Sandeep Rao
LOG-000040 | PRJ-2024002 | 2025-01-04 | 94 | 47 | Amber | Equipment dispatch completed; installation team mobilized | 4 | Sandeep Rao
LOG-000041 | PRJ-2024002 | 2025-01-11 | 104 | 52 | Amber | Client UAT sign-off received for batch of completed sites | 6 | Sandeep Rao
LOG-000042 | PRJ-2024002 | 2025-01-18 | 106 | 53 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Sandeep Rao
LOG-000043 | PRJ-2024002 | 2025-01-25 | 114 | 57 | Amber | Weekly governance call held with client stakeholders | 0 | Sandeep Rao
LOG-000044 | PRJ-2024002 | 2025-02-01 | 120 | 60 | Amber | Equipment dispatch completed; installation team mobilized | 1 | Sandeep Rao
LOG-000045 | PRJ-2024002 | 2025-02-08 | 124 | 62 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Sandeep Rao
LOG-000046 | PRJ-2024002 | 2025-02-15 | 134 | 67 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Sandeep Rao
LOG-000047 | PRJ-2024002 | 2025-02-22 | 144 | 72 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Sandeep Rao
LOG-000048 | PRJ-2024002 | 2025-03-01 | 156 | 78 | Green | Equipment dispatch completed; installation team mobilized | 2 | Sandeep Rao
LOG-000049 | PRJ-2024002 | 2025-03-08 | 166 | 83 | Red | Weekly governance call held with client stakeholders | 4 | Sandeep Rao
LOG-000050 | PRJ-2024002 | 2025-03-15 | 168 | 84 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Sandeep Rao
LOG-000051 | PRJ-2024002 | 2025-03-22 | 174 | 87 | Green | Client UAT sign-off received for batch of completed sites | 0 | Sandeep Rao
LOG-000052 | PRJ-2024002 | 2025-03-29 | 178 | 89 | Amber | Vendor escalation raised for delayed circuit provisioning | 5 | Sandeep Rao
LOG-000053 | PRJ-2024002 | 2025-04-05 | 186 | 93 | Amber | Equipment dispatch completed; installation team mobilized | 2 | Sandeep Rao
LOG-000054 | PRJ-2024002 | 2025-04-12 | 198 | 99 | Amber | Client UAT sign-off received for batch of completed sites | 8 | Sandeep Rao
LOG-000055 | PRJ-2024002 | 2025-04-19 | 200 | 100 | Red | Survey activities progressing as per plan across allocated sites | 3 | Sandeep Rao
LOG-000056 | PRJ-2024002 | 2025-04-26 | 200 | 100 | Green | Client UAT sign-off received for batch of completed sites | 3 | Sandeep Rao
LOG-000057 | PRJ-2024003 | 2024-11-09 | 0 | 4 | Amber | Vendor escalation raised for delayed circuit provisioning | 1 | Rahul K. Patil
LOG-000058 | PRJ-2024003 | 2024-11-16 | 0 | 8 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Rahul K. Patil
LOG-000059 | PRJ-2024003 | 2024-11-23 | 0 | 14 | Red | Survey activities progressing as per plan across allocated sites | 3 | Rahul K. Patil
LOG-000060 | PRJ-2024003 | 2024-11-30 | 0 | 17 | Green | Client UAT sign-off received for batch of completed sites | 6 | Rahul K. Patil
LOG-000061 | PRJ-2024003 | 2024-12-07 | 1 | 20 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Rahul K. Patil
LOG-000062 | PRJ-2024003 | 2024-12-14 | 1 | 22 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Rahul K. Patil
LOG-000063 | PRJ-2024003 | 2024-12-21 | 1 | 24 | Red | Resource constraint flagged; additional field engineer requested | 5 | Rahul K. Patil
LOG-000064 | PRJ-2024003 | 2024-12-28 | 1 | 26 | Red | Equipment dispatch completed; installation team mobilized | 2 | Rahul K. Patil
LOG-000065 | PRJ-2024003 | 2025-01-04 | 1 | 32 | Amber | Survey activities progressing as per plan across allocated sites | 8 | Rahul K. Patil
LOG-000066 | PRJ-2024003 | 2025-01-11 | 1 | 38 | Red | Equipment dispatch completed; installation team mobilized | 3 | Rahul K. Patil
LOG-000067 | PRJ-2024003 | 2025-01-18 | 2 | 40 | Red | Resource constraint flagged; additional field engineer requested | 8 | Rahul K. Patil
LOG-000068 | PRJ-2024003 | 2025-01-25 | 2 | 44 | Green | Equipment dispatch completed; installation team mobilized | 0 | Rahul K. Patil
LOG-000069 | PRJ-2024003 | 2025-02-01 | 2 | 45 | Green | Equipment dispatch completed; installation team mobilized | 7 | Rahul K. Patil
LOG-000070 | PRJ-2024003 | 2025-02-08 | 2 | 51 | Green | Client UAT sign-off received for batch of completed sites | 5 | Rahul K. Patil
LOG-000071 | PRJ-2024003 | 2025-02-15 | 2 | 54 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Rahul K. Patil
LOG-000072 | PRJ-2024003 | 2025-02-22 | 2 | 58 | Green | Equipment dispatch completed; installation team mobilized | 0 | Rahul K. Patil
LOG-000073 | PRJ-2024003 | 2025-03-01 | 3 | 63 | Amber | Client UAT sign-off received for batch of completed sites | 8 | Rahul K. Patil
LOG-000074 | PRJ-2024003 | 2025-03-08 | 3 | 64 | Red | Equipment dispatch completed; installation team mobilized | 5 | Rahul K. Patil
LOG-000075 | PRJ-2024003 | 2025-03-15 | 3 | 68 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Rahul K. Patil
LOG-000076 | PRJ-2024003 | 2025-03-22 | 3 | 72 | Green | Vendor escalation raised for delayed circuit provisioning | 6 | Rahul K. Patil
LOG-000077 | PRJ-2024003 | 2025-03-29 | 3 | 73 | Green | Weekly governance call held with client stakeholders | 3 | Rahul K. Patil
LOG-000078 | PRJ-2024003 | 2025-04-05 | 3 | 79 | Green | Survey activities progressing as per plan across allocated sites | 5 | Rahul K. Patil
LOG-000079 | PRJ-2024003 | 2025-04-12 | 4 | 83 | Green | Client UAT sign-off received for batch of completed sites | 8 | Rahul K. Patil
LOG-000080 | PRJ-2024003 | 2025-04-19 | 4 | 89 | Red | Survey activities progressing as per plan across allocated sites | 0 | Rahul K. Patil
LOG-000081 | PRJ-2024003 | 2025-04-26 | 4 | 94 | Green | Equipment dispatch completed; installation team mobilized | 1 | Rahul K. Patil
LOG-000082 | PRJ-2024003 | 2025-05-03 | 5 | 100 | Amber | Equipment dispatch completed; installation team mobilized | 6 | Rahul K. Patil
LOG-000083 | PRJ-2024003 | 2025-05-10 | 5 | 100 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Rahul K. Patil
LOG-000084 | PRJ-2024003 | 2025-05-17 | 5 | 100 | Green | Resource constraint flagged; additional field engineer requested | 1 | Rahul K. Patil
LOG-000085 | PRJ-2024004 | 2024-08-28 | 1 | 6 | Red | Weekly governance call held with client stakeholders | 8 | Farah Khan
LOG-000086 | PRJ-2024004 | 2024-09-04 | 3 | 10 | Amber | Resource constraint flagged; additional field engineer requested | 1 | Farah Khan
LOG-000087 | PRJ-2024004 | 2024-09-11 | 4 | 16 | Amber | Vendor escalation raised for delayed circuit provisioning | 1 | Farah Khan
LOG-000088 | PRJ-2024004 | 2024-09-18 | 6 | 20 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Farah Khan
LOG-000089 | PRJ-2024004 | 2024-09-25 | 6 | 22 | Green | Client UAT sign-off received for batch of completed sites | 3 | Farah Khan
LOG-000090 | PRJ-2024004 | 2024-10-02 | 7 | 25 | Green | Survey activities progressing as per plan across allocated sites | 0 | Farah Khan
LOG-000091 | PRJ-2024004 | 2024-10-09 | 8 | 28 | Red | Resource constraint flagged; additional field engineer requested | 5 | Farah Khan
LOG-000092 | PRJ-2024004 | 2024-10-16 | 9 | 32 | Red | Weekly governance call held with client stakeholders | 6 | Farah Khan
LOG-000093 | PRJ-2024004 | 2024-10-23 | 10 | 36 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Farah Khan
LOG-000094 | PRJ-2024004 | 2024-10-30 | 11 | 39 | Amber | Weekly governance call held with client stakeholders | 2 | Farah Khan
LOG-000095 | PRJ-2024004 | 2024-11-06 | 13 | 44 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Farah Khan
LOG-000096 | PRJ-2024004 | 2024-11-13 | 14 | 49 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Farah Khan
LOG-000097 | PRJ-2024004 | 2024-11-20 | 16 | 54 | Red | Weekly governance call held with client stakeholders | 8 | Farah Khan
LOG-000098 | PRJ-2024004 | 2024-11-27 | 17 | 59 | Green | Weekly governance call held with client stakeholders | 2 | Farah Khan
LOG-000099 | PRJ-2024004 | 2024-12-04 | 18 | 62 | Red | Weekly governance call held with client stakeholders | 1 | Farah Khan
LOG-000100 | PRJ-2024004 | 2024-12-11 | 20 | 67 | Amber | Survey activities progressing as per plan across allocated sites | 8 | Farah Khan
LOG-000101 | PRJ-2024004 | 2024-12-18 | 21 | 70 | Green | Weekly governance call held with client stakeholders | 5 | Farah Khan
LOG-000102 | PRJ-2024004 | 2024-12-25 | 22 | 76 | Red | Resource constraint flagged; additional field engineer requested | 5 | Farah Khan
LOG-000103 | PRJ-2024004 | 2025-01-01 | 23 | 79 | Green | Client UAT sign-off received for batch of completed sites | 3 | Farah Khan
LOG-000104 | PRJ-2024004 | 2025-01-08 | 24 | 80 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Farah Khan
LOG-000105 | PRJ-2024004 | 2025-01-15 | 25 | 84 | Green | Survey activities progressing as per plan across allocated sites | 8 | Farah Khan
LOG-000106 | PRJ-2024004 | 2025-01-22 | 26 | 87 | Green | Vendor escalation raised for delayed circuit provisioning | 6 | Farah Khan
LOG-000107 | PRJ-2024004 | 2025-01-29 | 27 | 91 | Green | Client UAT sign-off received for batch of completed sites | 1 | Farah Khan
LOG-000108 | PRJ-2024004 | 2025-02-05 | 28 | 95 | Red | Resource constraint flagged; additional field engineer requested | 4 | Farah Khan
LOG-000109 | PRJ-2024004 | 2025-02-12 | 29 | 98 | Red | Weekly governance call held with client stakeholders | 1 | Farah Khan
LOG-000110 | PRJ-2024004 | 2025-02-19 | 30 | 100 | Green | Survey activities progressing as per plan across allocated sites | 0 | Farah Khan
LOG-000111 | PRJ-2024004 | 2025-02-26 | 30 | 100 | Green | Survey activities progressing as per plan across allocated sites | 7 | Farah Khan
LOG-000112 | PRJ-2024004 | 2025-03-05 | 30 | 100 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Farah Khan
LOG-000113 | PRJ-2024005 | 2024-11-24 | 0 | 2 | Green | Survey activities progressing as per plan across allocated sites | 6 | Manish Agarwal
LOG-000114 | PRJ-2024005 | 2024-12-01 | 0 | 5 | Green | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000115 | PRJ-2024005 | 2024-12-08 | 0 | 7 | Red | Client UAT sign-off received for batch of completed sites | 8 | Manish Agarwal
LOG-000116 | PRJ-2024005 | 2024-12-15 | 1 | 13 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Manish Agarwal
LOG-000117 | PRJ-2024005 | 2024-12-22 | 1 | 18 | Green | Weekly governance call held with client stakeholders | 4 | Manish Agarwal
LOG-000118 | PRJ-2024005 | 2024-12-29 | 2 | 20 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Manish Agarwal
LOG-000119 | PRJ-2024005 | 2025-01-05 | 2 | 23 | Red | Weekly governance call held with client stakeholders | 7 | Manish Agarwal
LOG-000120 | PRJ-2024005 | 2025-01-12 | 2 | 28 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Manish Agarwal
LOG-000121 | PRJ-2024005 | 2025-01-19 | 2 | 29 | Red | Client UAT sign-off received for batch of completed sites | 3 | Manish Agarwal
LOG-000122 | PRJ-2024005 | 2025-01-26 | 3 | 33 | Amber | Weekly governance call held with client stakeholders | 5 | Manish Agarwal
LOG-000123 | PRJ-2024005 | 2025-02-02 | 3 | 36 | Amber | Weekly governance call held with client stakeholders | 5 | Manish Agarwal
LOG-000124 | PRJ-2024005 | 2025-02-09 | 4 | 41 | Amber | Resource constraint flagged; additional field engineer requested | 8 | Manish Agarwal
LOG-000125 | PRJ-2024005 | 2025-02-16 | 4 | 47 | Green | Weekly governance call held with client stakeholders | 7 | Manish Agarwal
LOG-000126 | PRJ-2024005 | 2025-02-23 | 4 | 48 | Green | Resource constraint flagged; additional field engineer requested | 5 | Manish Agarwal
LOG-000127 | PRJ-2024005 | 2025-03-02 | 5 | 50 | Red | Weekly governance call held with client stakeholders | 2 | Manish Agarwal
LOG-000128 | PRJ-2024005 | 2025-03-09 | 5 | 53 | Red | Survey activities progressing as per plan across allocated sites | 6 | Manish Agarwal
LOG-000129 | PRJ-2024005 | 2025-03-16 | 5 | 59 | Amber | Client UAT sign-off received for batch of completed sites | 1 | Manish Agarwal
LOG-000130 | PRJ-2024005 | 2025-03-23 | 6 | 64 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Manish Agarwal
LOG-000131 | PRJ-2024005 | 2025-03-30 | 6 | 65 | Green | Client UAT sign-off received for batch of completed sites | 4 | Manish Agarwal
LOG-000132 | PRJ-2024005 | 2025-04-06 | 6 | 67 | Green | Equipment dispatch completed; installation team mobilized | 0 | Manish Agarwal
LOG-000133 | PRJ-2024005 | 2025-04-13 | 6 | 69 | Green | Client UAT sign-off received for batch of completed sites | 0 | Manish Agarwal
LOG-000134 | PRJ-2024005 | 2025-04-20 | 7 | 70 | Green | Survey activities progressing as per plan across allocated sites | 3 | Manish Agarwal
LOG-000135 | PRJ-2024005 | 2025-04-27 | 7 | 71 | Amber | Weekly governance call held with client stakeholders | 6 | Manish Agarwal
LOG-000136 | PRJ-2024005 | 2025-05-04 | 7 | 75 | Amber | Equipment dispatch completed; installation team mobilized | 2 | Manish Agarwal
LOG-000137 | PRJ-2024005 | 2025-05-11 | 7 | 79 | Green | Client UAT sign-off received for batch of completed sites | 1 | Manish Agarwal
LOG-000138 | PRJ-2024005 | 2025-05-18 | 8 | 81 | Amber | Vendor escalation raised for delayed circuit provisioning | 7 | Manish Agarwal
LOG-000139 | PRJ-2024005 | 2025-05-25 | 8 | 82 | Amber | Client UAT sign-off received for batch of completed sites | 3 | Manish Agarwal
LOG-000140 | PRJ-2024005 | 2025-06-01 | 8 | 88 | Green | Survey activities progressing as per plan across allocated sites | 6 | Manish Agarwal
LOG-000141 | PRJ-2024006 | 2024-07-07 | 9 | 3 | Green | Weekly governance call held with client stakeholders | 7 | Ananya Joshi
LOG-000142 | PRJ-2024006 | 2024-07-14 | 15 | 5 | Red | Weekly governance call held with client stakeholders | 0 | Ananya Joshi
LOG-000143 | PRJ-2024006 | 2024-07-21 | 33 | 11 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Ananya Joshi
LOG-000144 | PRJ-2024006 | 2024-07-28 | 48 | 16 | Green | Client UAT sign-off received for batch of completed sites | 6 | Ananya Joshi
LOG-000145 | PRJ-2024006 | 2024-08-04 | 60 | 20 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Ananya Joshi
LOG-000146 | PRJ-2024006 | 2024-08-11 | 72 | 24 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Ananya Joshi
LOG-000147 | PRJ-2024006 | 2024-08-18 | 81 | 27 | Green | Survey activities progressing as per plan across allocated sites | 6 | Ananya Joshi
LOG-000148 | PRJ-2024006 | 2024-08-25 | 99 | 33 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Ananya Joshi
LOG-000149 | PRJ-2024006 | 2024-09-01 | 108 | 36 | Red | Equipment dispatch completed; installation team mobilized | 6 | Ananya Joshi
LOG-000150 | PRJ-2024006 | 2024-09-08 | 117 | 39 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Ananya Joshi
LOG-000151 | PRJ-2024006 | 2024-09-15 | 129 | 43 | Green | Resource constraint flagged; additional field engineer requested | 4 | Ananya Joshi
LOG-000152 | PRJ-2024006 | 2024-09-22 | 141 | 47 | Amber | Vendor escalation raised for delayed circuit provisioning | 2 | Ananya Joshi
LOG-000153 | PRJ-2024006 | 2024-09-29 | 159 | 53 | Green | Weekly governance call held with client stakeholders | 3 | Ananya Joshi
LOG-000154 | PRJ-2024006 | 2024-10-06 | 171 | 57 | Red | Survey activities progressing as per plan across allocated sites | 6 | Ananya Joshi
LOG-000155 | PRJ-2024006 | 2024-10-13 | 189 | 63 | Green | Equipment dispatch completed; installation team mobilized | 5 | Ananya Joshi
LOG-000156 | PRJ-2024006 | 2024-10-20 | 192 | 64 | Green | Client UAT sign-off received for batch of completed sites | 1 | Ananya Joshi
LOG-000157 | PRJ-2024006 | 2024-10-27 | 198 | 66 | Green | Survey activities progressing as per plan across allocated sites | 7 | Ananya Joshi
LOG-000158 | PRJ-2024006 | 2024-11-03 | 204 | 68 | Green | Resource constraint flagged; additional field engineer requested | 2 | Ananya Joshi
LOG-000159 | PRJ-2024006 | 2024-11-10 | 210 | 70 | Green | Resource constraint flagged; additional field engineer requested | 6 | Ananya Joshi
LOG-000160 | PRJ-2024006 | 2024-11-17 | 222 | 74 | Amber | Client UAT sign-off received for batch of completed sites | 6 | Ananya Joshi
LOG-000161 | PRJ-2024006 | 2024-11-24 | 231 | 77 | Green | Weekly governance call held with client stakeholders | 0 | Ananya Joshi
LOG-000162 | PRJ-2024006 | 2024-12-01 | 240 | 80 | Green | Weekly governance call held with client stakeholders | 2 | Ananya Joshi
LOG-000163 | PRJ-2024006 | 2024-12-08 | 249 | 83 | Green | Weekly governance call held with client stakeholders | 1 | Ananya Joshi
LOG-000164 | PRJ-2024006 | 2024-12-15 | 267 | 89 | Amber | Vendor escalation raised for delayed circuit provisioning | 4 | Ananya Joshi
LOG-000165 | PRJ-2024006 | 2024-12-22 | 273 | 91 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Ananya Joshi
LOG-000166 | PRJ-2024006 | 2024-12-29 | 288 | 96 | Amber | Survey activities progressing as per plan across allocated sites | 7 | Ananya Joshi
LOG-000167 | PRJ-2024006 | 2025-01-05 | 300 | 100 | Green | Equipment dispatch completed; installation team mobilized | 8 | Ananya Joshi
LOG-000168 | PRJ-2024006 | 2025-01-12 | 300 | 100 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Ananya Joshi
LOG-000169 | PRJ-2024007 | 2024-12-19 | 9 | 3 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Manish Agarwal
LOG-000170 | PRJ-2024007 | 2024-12-26 | 12 | 4 | Green | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000171 | PRJ-2024007 | 2025-01-02 | 27 | 9 | Red | Client UAT sign-off received for batch of completed sites | 4 | Manish Agarwal
LOG-000172 | PRJ-2024007 | 2025-01-09 | 36 | 12 | Green | Resource constraint flagged; additional field engineer requested | 5 | Manish Agarwal
LOG-000173 | PRJ-2024007 | 2025-01-16 | 42 | 14 | Amber | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000174 | PRJ-2024007 | 2025-01-23 | 45 | 15 | Green | Client UAT sign-off received for batch of completed sites | 0 | Manish Agarwal
LOG-000175 | PRJ-2024007 | 2025-01-30 | 63 | 21 | Green | Weekly governance call held with client stakeholders | 5 | Manish Agarwal
LOG-000176 | PRJ-2024007 | 2025-02-06 | 75 | 25 | Green | Equipment dispatch completed; installation team mobilized | 2 | Manish Agarwal
LOG-000177 | PRJ-2024007 | 2025-02-13 | 90 | 30 | Green | Survey activities progressing as per plan across allocated sites | 8 | Manish Agarwal
LOG-000178 | PRJ-2024007 | 2025-02-20 | 102 | 34 | Red | Client UAT sign-off received for batch of completed sites | 4 | Manish Agarwal
LOG-000179 | PRJ-2024007 | 2025-02-27 | 111 | 37 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Manish Agarwal
LOG-000180 | PRJ-2024007 | 2025-03-06 | 120 | 40 | Red | Vendor escalation raised for delayed circuit provisioning | 8 | Manish Agarwal
LOG-000181 | PRJ-2024007 | 2025-03-13 | 135 | 45 | Amber | Weekly governance call held with client stakeholders | 2 | Manish Agarwal
LOG-000182 | PRJ-2024007 | 2025-03-20 | 144 | 48 | Red | Client UAT sign-off received for batch of completed sites | 2 | Manish Agarwal
LOG-000183 | PRJ-2024007 | 2025-03-27 | 156 | 52 | Green | Equipment dispatch completed; installation team mobilized | 6 | Manish Agarwal
LOG-000184 | PRJ-2024007 | 2025-04-03 | 159 | 53 | Green | Client UAT sign-off received for batch of completed sites | 2 | Manish Agarwal
LOG-000185 | PRJ-2024007 | 2025-04-10 | 168 | 56 | Green | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000186 | PRJ-2024007 | 2025-04-17 | 171 | 57 | Amber | Resource constraint flagged; additional field engineer requested | 7 | Manish Agarwal
LOG-000187 | PRJ-2024007 | 2025-04-24 | 189 | 63 | Green | Survey activities progressing as per plan across allocated sites | 3 | Manish Agarwal
LOG-000188 | PRJ-2024007 | 2025-05-01 | 201 | 67 | Red | Equipment dispatch completed; installation team mobilized | 5 | Manish Agarwal
LOG-000189 | PRJ-2024007 | 2025-05-08 | 207 | 69 | Green | Resource constraint flagged; additional field engineer requested | 2 | Manish Agarwal
LOG-000190 | PRJ-2024007 | 2025-05-15 | 219 | 73 | Green | Equipment dispatch completed; installation team mobilized | 4 | Manish Agarwal
LOG-000191 | PRJ-2024007 | 2025-05-22 | 228 | 76 | Red | Weekly governance call held with client stakeholders | 0 | Manish Agarwal
LOG-000192 | PRJ-2024007 | 2025-05-29 | 246 | 82 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Manish Agarwal
LOG-000193 | PRJ-2024007 | 2025-06-05 | 258 | 86 | Green | Survey activities progressing as per plan across allocated sites | 3 | Manish Agarwal
LOG-000194 | PRJ-2024007 | 2025-06-12 | 267 | 89 | Amber | Resource constraint flagged; additional field engineer requested | 1 | Manish Agarwal
LOG-000195 | PRJ-2024007 | 2025-06-19 | 279 | 93 | Green | Weekly governance call held with client stakeholders | 6 | Manish Agarwal
LOG-000196 | PRJ-2024007 | 2025-06-26 | 282 | 94 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Manish Agarwal
LOG-000197 | PRJ-2024008 | 2024-11-03 | 0 | 3 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Farah Khan
LOG-000198 | PRJ-2024008 | 2024-11-10 | 1 | 5 | Green | Resource constraint flagged; additional field engineer requested | 7 | Farah Khan
LOG-000199 | PRJ-2024008 | 2024-11-17 | 1 | 6 | Red | Survey activities progressing as per plan across allocated sites | 0 | Farah Khan
LOG-000200 | PRJ-2024008 | 2024-11-24 | 2 | 7 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Farah Khan
LOG-000201 | PRJ-2024008 | 2024-12-01 | 2 | 9 | Red | Weekly governance call held with client stakeholders | 7 | Farah Khan
LOG-000202 | PRJ-2024008 | 2024-12-08 | 3 | 10 | Red | Vendor escalation raised for delayed circuit provisioning | 8 | Farah Khan
LOG-000203 | PRJ-2024008 | 2024-12-15 | 3 | 13 | Green | Resource constraint flagged; additional field engineer requested | 8 | Farah Khan
LOG-000204 | PRJ-2024008 | 2024-12-22 | 5 | 18 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Farah Khan
LOG-000205 | PRJ-2024008 | 2024-12-29 | 6 | 21 | Red | Weekly governance call held with client stakeholders | 1 | Farah Khan
LOG-000206 | PRJ-2024008 | 2025-01-05 | 6 | 23 | Amber | Vendor escalation raised for delayed circuit provisioning | 1 | Farah Khan
LOG-000207 | PRJ-2024008 | 2025-01-12 | 8 | 27 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Farah Khan
LOG-000208 | PRJ-2024008 | 2025-01-19 | 9 | 33 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Farah Khan
LOG-000209 | PRJ-2024008 | 2025-01-26 | 10 | 36 | Red | Vendor escalation raised for delayed circuit provisioning | 0 | Farah Khan
LOG-000210 | PRJ-2024008 | 2025-02-02 | 11 | 39 | Red | Survey activities progressing as per plan across allocated sites | 8 | Farah Khan
LOG-000211 | PRJ-2024008 | 2025-02-09 | 12 | 40 | Green | Survey activities progressing as per plan across allocated sites | 3 | Farah Khan
LOG-000212 | PRJ-2024008 | 2025-02-16 | 12 | 42 | Green | Weekly governance call held with client stakeholders | 0 | Farah Khan
LOG-000213 | PRJ-2024008 | 2025-02-23 | 13 | 45 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Farah Khan
LOG-000214 | PRJ-2024008 | 2025-03-02 | 15 | 51 | Green | Equipment dispatch completed; installation team mobilized | 6 | Farah Khan
LOG-000215 | PRJ-2024008 | 2025-03-09 | 17 | 57 | Green | Equipment dispatch completed; installation team mobilized | 8 | Farah Khan
LOG-000216 | PRJ-2024008 | 2025-03-16 | 18 | 63 | Amber | Resource constraint flagged; additional field engineer requested | 0 | Farah Khan
LOG-000217 | PRJ-2024008 | 2025-03-23 | 20 | 69 | Green | Survey activities progressing as per plan across allocated sites | 3 | Farah Khan
LOG-000218 | PRJ-2024008 | 2025-03-30 | 21 | 70 | Green | Client UAT sign-off received for batch of completed sites | 6 | Farah Khan
LOG-000219 | PRJ-2024008 | 2025-04-06 | 22 | 75 | Green | Client UAT sign-off received for batch of completed sites | 0 | Farah Khan
LOG-000220 | PRJ-2024008 | 2025-04-13 | 23 | 77 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Farah Khan
LOG-000221 | PRJ-2024008 | 2025-04-20 | 24 | 81 | Amber | Resource constraint flagged; additional field engineer requested | 6 | Farah Khan
LOG-000222 | PRJ-2024008 | 2025-04-27 | 25 | 84 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Farah Khan
LOG-000223 | PRJ-2024008 | 2025-05-04 | 25 | 86 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Farah Khan
LOG-000224 | PRJ-2024008 | 2025-05-11 | 26 | 88 | Amber | Resource constraint flagged; additional field engineer requested | 2 | Farah Khan
LOG-000225 | PRJ-2024009 | 2024-08-15 | 1 | 1 | Amber | Resource constraint flagged; additional field engineer requested | 4 | Sandeep Rao
LOG-000226 | PRJ-2024009 | 2024-08-22 | 9 | 6 | Red | Resource constraint flagged; additional field engineer requested | 8 | Sandeep Rao
LOG-000227 | PRJ-2024009 | 2024-08-29 | 13 | 9 | Red | Weekly governance call held with client stakeholders | 5 | Sandeep Rao
LOG-000228 | PRJ-2024009 | 2024-09-05 | 21 | 14 | Green | Resource constraint flagged; additional field engineer requested | 2 | Sandeep Rao
LOG-000229 | PRJ-2024009 | 2024-09-12 | 27 | 18 | Green | Resource constraint flagged; additional field engineer requested | 2 | Sandeep Rao
LOG-000230 | PRJ-2024009 | 2024-09-19 | 28 | 19 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Sandeep Rao
LOG-000231 | PRJ-2024009 | 2024-09-26 | 37 | 25 | Green | Weekly governance call held with client stakeholders | 6 | Sandeep Rao
LOG-000232 | PRJ-2024009 | 2024-10-03 | 42 | 28 | Amber | Weekly governance call held with client stakeholders | 5 | Sandeep Rao
LOG-000233 | PRJ-2024009 | 2024-10-10 | 48 | 32 | Green | Resource constraint flagged; additional field engineer requested | 6 | Sandeep Rao
LOG-000234 | PRJ-2024009 | 2024-10-17 | 54 | 36 | Green | Client UAT sign-off received for batch of completed sites | 8 | Sandeep Rao
LOG-000235 | PRJ-2024009 | 2024-10-24 | 63 | 42 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Sandeep Rao
LOG-000236 | PRJ-2024009 | 2024-10-31 | 67 | 45 | Red | Vendor escalation raised for delayed circuit provisioning | 5 | Sandeep Rao
LOG-000237 | PRJ-2024009 | 2024-11-07 | 69 | 46 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Sandeep Rao
LOG-000238 | PRJ-2024009 | 2024-11-14 | 76 | 51 | Amber | Equipment dispatch completed; installation team mobilized | 1 | Sandeep Rao
LOG-000239 | PRJ-2024009 | 2024-11-21 | 82 | 55 | Green | Equipment dispatch completed; installation team mobilized | 0 | Sandeep Rao
LOG-000240 | PRJ-2024009 | 2024-11-28 | 90 | 60 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Sandeep Rao
LOG-000241 | PRJ-2024009 | 2024-12-05 | 93 | 62 | Green | Resource constraint flagged; additional field engineer requested | 2 | Sandeep Rao
LOG-000242 | PRJ-2024009 | 2024-12-12 | 96 | 64 | Green | Client UAT sign-off received for batch of completed sites | 2 | Sandeep Rao
LOG-000243 | PRJ-2024009 | 2024-12-19 | 100 | 67 | Red | Client UAT sign-off received for batch of completed sites | 6 | Sandeep Rao
LOG-000244 | PRJ-2024009 | 2024-12-26 | 105 | 70 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Sandeep Rao
LOG-000245 | PRJ-2024009 | 2025-01-02 | 106 | 71 | Green | Weekly governance call held with client stakeholders | 5 | Sandeep Rao
LOG-000246 | PRJ-2024009 | 2025-01-09 | 111 | 74 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Sandeep Rao
LOG-000247 | PRJ-2024009 | 2025-01-16 | 118 | 79 | Amber | Survey activities progressing as per plan across allocated sites | 8 | Sandeep Rao
LOG-000248 | PRJ-2024009 | 2025-01-23 | 127 | 85 | Green | Weekly governance call held with client stakeholders | 5 | Sandeep Rao
LOG-000249 | PRJ-2024009 | 2025-01-30 | 135 | 90 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Sandeep Rao
LOG-000250 | PRJ-2024009 | 2025-02-06 | 139 | 93 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Sandeep Rao
LOG-000251 | PRJ-2024009 | 2025-02-13 | 144 | 96 | Green | Weekly governance call held with client stakeholders | 4 | Sandeep Rao
LOG-000252 | PRJ-2024009 | 2025-02-20 | 147 | 98 | Amber | Vendor escalation raised for delayed circuit provisioning | 8 | Sandeep Rao
LOG-000253 | PRJ-2024010 | 2024-11-11 | 0 | 3 | Red | Vendor escalation raised for delayed circuit provisioning | 8 | Deepa Nair
LOG-000254 | PRJ-2024010 | 2024-11-18 | 0 | 4 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Deepa Nair
LOG-000255 | PRJ-2024010 | 2024-11-25 | 0 | 8 | Red | Client UAT sign-off received for batch of completed sites | 5 | Deepa Nair
LOG-000256 | PRJ-2024010 | 2024-12-02 | 0 | 12 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Deepa Nair
LOG-000257 | PRJ-2024010 | 2024-12-09 | 0 | 15 | Red | Client UAT sign-off received for batch of completed sites | 2 | Deepa Nair
LOG-000258 | PRJ-2024010 | 2024-12-16 | 0 | 19 | Amber | Weekly governance call held with client stakeholders | 2 | Deepa Nair
LOG-000259 | PRJ-2024010 | 2024-12-23 | 1 | 21 | Green | Client UAT sign-off received for batch of completed sites | 8 | Deepa Nair
LOG-000260 | PRJ-2024010 | 2024-12-30 | 1 | 23 | Green | Resource constraint flagged; additional field engineer requested | 2 | Deepa Nair
LOG-000261 | PRJ-2024010 | 2025-01-06 | 1 | 27 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Deepa Nair
LOG-000262 | PRJ-2024010 | 2025-01-13 | 1 | 28 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Deepa Nair
LOG-000263 | PRJ-2024010 | 2025-01-20 | 1 | 31 | Amber | Resource constraint flagged; additional field engineer requested | 8 | Deepa Nair
LOG-000264 | PRJ-2024010 | 2025-01-27 | 1 | 37 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Deepa Nair
LOG-000265 | PRJ-2024010 | 2025-02-03 | 2 | 42 | Green | Survey activities progressing as per plan across allocated sites | 7 | Deepa Nair
LOG-000266 | PRJ-2024010 | 2025-02-10 | 2 | 46 | Green | Weekly governance call held with client stakeholders | 0 | Deepa Nair
LOG-000267 | PRJ-2024010 | 2025-02-17 | 2 | 50 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Deepa Nair
LOG-000268 | PRJ-2024010 | 2025-02-24 | 2 | 53 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000269 | PRJ-2024010 | 2025-03-03 | 2 | 59 | Red | Equipment dispatch completed; installation team mobilized | 4 | Deepa Nair
LOG-000270 | PRJ-2024010 | 2025-03-10 | 3 | 63 | Green | Resource constraint flagged; additional field engineer requested | 5 | Deepa Nair
LOG-000271 | PRJ-2024010 | 2025-03-17 | 3 | 69 | Green | Equipment dispatch completed; installation team mobilized | 1 | Deepa Nair
LOG-000272 | PRJ-2024010 | 2025-03-24 | 3 | 75 | Green | Weekly governance call held with client stakeholders | 3 | Deepa Nair
LOG-000273 | PRJ-2024010 | 2025-03-31 | 4 | 80 | Green | Survey activities progressing as per plan across allocated sites | 3 | Deepa Nair
LOG-000274 | PRJ-2024010 | 2025-04-07 | 4 | 82 | Green | Weekly governance call held with client stakeholders | 1 | Deepa Nair
LOG-000275 | PRJ-2024010 | 2025-04-14 | 4 | 87 | Amber | Resource constraint flagged; additional field engineer requested | 6 | Deepa Nair
LOG-000276 | PRJ-2024010 | 2025-04-21 | 4 | 91 | Red | Weekly governance call held with client stakeholders | 0 | Deepa Nair
LOG-000277 | PRJ-2024010 | 2025-04-28 | 4 | 95 | Amber | Weekly governance call held with client stakeholders | 7 | Deepa Nair
LOG-000278 | PRJ-2024010 | 2025-05-05 | 5 | 100 | Green | Client UAT sign-off received for batch of completed sites | 7 | Deepa Nair
LOG-000279 | PRJ-2024010 | 2025-05-12 | 5 | 100 | Green | Resource constraint flagged; additional field engineer requested | 0 | Deepa Nair
LOG-000280 | PRJ-2024010 | 2025-05-19 | 5 | 100 | Green | Survey activities progressing as per plan across allocated sites | 0 | Deepa Nair
LOG-000281 | PRJ-2024011 | 2024-12-16 | 0 | 3 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Manish Agarwal
LOG-000282 | PRJ-2024011 | 2024-12-23 | 0 | 8 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Manish Agarwal
LOG-000283 | PRJ-2024011 | 2024-12-30 | 1 | 13 | Green | Client UAT sign-off received for batch of completed sites | 0 | Manish Agarwal
LOG-000284 | PRJ-2024011 | 2025-01-06 | 1 | 14 | Red | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000285 | PRJ-2024011 | 2025-01-13 | 2 | 20 | Amber | Resource constraint flagged; additional field engineer requested | 5 | Manish Agarwal
LOG-000286 | PRJ-2024011 | 2025-01-20 | 2 | 26 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Manish Agarwal
LOG-000287 | PRJ-2024011 | 2025-01-27 | 2 | 28 | Green | Equipment dispatch completed; installation team mobilized | 3 | Manish Agarwal
LOG-000288 | PRJ-2024011 | 2025-02-03 | 3 | 33 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Manish Agarwal
LOG-000289 | PRJ-2024011 | 2025-02-10 | 3 | 35 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Manish Agarwal
LOG-000290 | PRJ-2024011 | 2025-02-17 | 3 | 39 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Manish Agarwal
LOG-000291 | PRJ-2024011 | 2025-02-24 | 4 | 43 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Manish Agarwal
LOG-000292 | PRJ-2024011 | 2025-03-03 | 4 | 47 | Green | Survey activities progressing as per plan across allocated sites | 2 | Manish Agarwal
LOG-000293 | PRJ-2024011 | 2025-03-10 | 4 | 48 | Red | Vendor escalation raised for delayed circuit provisioning | 5 | Manish Agarwal
LOG-000294 | PRJ-2024011 | 2025-03-17 | 5 | 50 | Green | Survey activities progressing as per plan across allocated sites | 4 | Manish Agarwal
LOG-000295 | PRJ-2024011 | 2025-03-24 | 5 | 55 | Green | Client UAT sign-off received for batch of completed sites | 0 | Manish Agarwal
LOG-000296 | PRJ-2024011 | 2025-03-31 | 5 | 57 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Manish Agarwal
LOG-000297 | PRJ-2024011 | 2025-04-07 | 5 | 59 | Red | Resource constraint flagged; additional field engineer requested | 6 | Manish Agarwal
LOG-000298 | PRJ-2024011 | 2025-04-14 | 6 | 65 | Red | Client UAT sign-off received for batch of completed sites | 8 | Manish Agarwal
LOG-000299 | PRJ-2024011 | 2025-04-21 | 7 | 70 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Manish Agarwal
LOG-000300 | PRJ-2024011 | 2025-04-28 | 7 | 76 | Green | Client UAT sign-off received for batch of completed sites | 5 | Manish Agarwal
LOG-000301 | PRJ-2024011 | 2025-05-05 | 8 | 82 | Red | Resource constraint flagged; additional field engineer requested | 8 | Manish Agarwal
LOG-000302 | PRJ-2024011 | 2025-05-12 | 8 | 84 | Green | Weekly governance call held with client stakeholders | 8 | Manish Agarwal
LOG-000303 | PRJ-2024011 | 2025-05-19 | 8 | 89 | Green | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000304 | PRJ-2024011 | 2025-05-26 | 9 | 90 | Amber | Vendor escalation raised for delayed circuit provisioning | 3 | Manish Agarwal
LOG-000305 | PRJ-2024011 | 2025-06-02 | 9 | 96 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Manish Agarwal
LOG-000306 | PRJ-2024011 | 2025-06-09 | 9 | 99 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Manish Agarwal
LOG-000307 | PRJ-2024011 | 2025-06-16 | 10 | 100 | Green | Equipment dispatch completed; installation team mobilized | 6 | Manish Agarwal
LOG-000308 | PRJ-2024011 | 2025-06-23 | 10 | 100 | Amber | Weekly governance call held with client stakeholders | 7 | Manish Agarwal
LOG-000309 | PRJ-2024012 | 2024-08-08 | 1 | 5 | Green | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-000310 | PRJ-2024012 | 2024-08-15 | 2 | 11 | Amber | Vendor escalation raised for delayed circuit provisioning | 1 | Ananya Joshi
LOG-000311 | PRJ-2024012 | 2024-08-22 | 4 | 16 | Red | Vendor escalation raised for delayed circuit provisioning | 6 | Ananya Joshi
LOG-000312 | PRJ-2024012 | 2024-08-29 | 4 | 18 | Amber | Weekly governance call held with client stakeholders | 1 | Ananya Joshi
LOG-000313 | PRJ-2024012 | 2024-09-05 | 5 | 20 | Red | Equipment dispatch completed; installation team mobilized | 4 | Ananya Joshi
LOG-000314 | PRJ-2024012 | 2024-09-12 | 6 | 26 | Green | Resource constraint flagged; additional field engineer requested | 2 | Ananya Joshi
LOG-000315 | PRJ-2024012 | 2024-09-19 | 8 | 32 | Green | Survey activities progressing as per plan across allocated sites | 8 | Ananya Joshi
LOG-000316 | PRJ-2024012 | 2024-09-26 | 8 | 35 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Ananya Joshi
LOG-000317 | PRJ-2024012 | 2024-10-03 | 10 | 41 | Green | Weekly governance call held with client stakeholders | 0 | Ananya Joshi
LOG-000318 | PRJ-2024012 | 2024-10-10 | 10 | 42 | Red | Equipment dispatch completed; installation team mobilized | 7 | Ananya Joshi
LOG-000319 | PRJ-2024012 | 2024-10-17 | 11 | 44 | Amber | Client UAT sign-off received for batch of completed sites | 6 | Ananya Joshi
LOG-000320 | PRJ-2024012 | 2024-10-24 | 11 | 46 | Amber | Weekly governance call held with client stakeholders | 3 | Ananya Joshi
LOG-000321 | PRJ-2024012 | 2024-10-31 | 12 | 51 | Red | Client UAT sign-off received for batch of completed sites | 5 | Ananya Joshi
LOG-000322 | PRJ-2024012 | 2024-11-07 | 13 | 54 | Red | Vendor escalation raised for delayed circuit provisioning | 7 | Ananya Joshi
LOG-000323 | PRJ-2024012 | 2024-11-14 | 15 | 60 | Amber | Vendor escalation raised for delayed circuit provisioning | 1 | Ananya Joshi
LOG-000324 | PRJ-2024012 | 2024-11-21 | 16 | 66 | Amber | Vendor escalation raised for delayed circuit provisioning | 2 | Ananya Joshi
LOG-000325 | PRJ-2024012 | 2024-11-28 | 17 | 68 | Green | Survey activities progressing as per plan across allocated sites | 8 | Ananya Joshi
LOG-000326 | PRJ-2024012 | 2024-12-05 | 18 | 74 | Green | Survey activities progressing as per plan across allocated sites | 0 | Ananya Joshi
LOG-000327 | PRJ-2024012 | 2024-12-12 | 18 | 75 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Ananya Joshi
LOG-000328 | PRJ-2024012 | 2024-12-19 | 19 | 79 | Amber | Vendor escalation raised for delayed circuit provisioning | 0 | Ananya Joshi
LOG-000329 | PRJ-2024012 | 2024-12-26 | 20 | 83 | Green | Equipment dispatch completed; installation team mobilized | 1 | Ananya Joshi
LOG-000330 | PRJ-2024012 | 2025-01-02 | 21 | 86 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Ananya Joshi
LOG-000331 | PRJ-2024012 | 2025-01-09 | 21 | 87 | Green | Resource constraint flagged; additional field engineer requested | 0 | Ananya Joshi
LOG-000332 | PRJ-2024012 | 2025-01-16 | 23 | 92 | Amber | Client UAT sign-off received for batch of completed sites | 1 | Ananya Joshi
LOG-000333 | PRJ-2024012 | 2025-01-23 | 24 | 98 | Green | Weekly governance call held with client stakeholders | 8 | Ananya Joshi
LOG-000334 | PRJ-2024012 | 2025-01-30 | 24 | 99 | Green | Weekly governance call held with client stakeholders | 4 | Ananya Joshi
LOG-000335 | PRJ-2024012 | 2025-02-06 | 25 | 100 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Ananya Joshi
LOG-000336 | PRJ-2024012 | 2025-02-13 | 25 | 100 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Ananya Joshi
LOG-000337 | PRJ-2024013 | 2024-09-22 | 0 | 4 | Green | Weekly governance call held with client stakeholders | 6 | Sandeep Rao
LOG-000338 | PRJ-2024013 | 2024-09-29 | 1 | 8 | Green | Weekly governance call held with client stakeholders | 2 | Sandeep Rao
LOG-000339 | PRJ-2024013 | 2024-10-06 | 1 | 13 | Green | Resource constraint flagged; additional field engineer requested | 8 | Sandeep Rao
LOG-000340 | PRJ-2024013 | 2024-10-13 | 2 | 15 | Green | Equipment dispatch completed; installation team mobilized | 1 | Sandeep Rao
LOG-000341 | PRJ-2024013 | 2024-10-20 | 2 | 19 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Sandeep Rao
LOG-000342 | PRJ-2024013 | 2024-10-27 | 3 | 21 | Green | Survey activities progressing as per plan across allocated sites | 2 | Sandeep Rao
LOG-000343 | PRJ-2024013 | 2024-11-03 | 4 | 27 | Green | Resource constraint flagged; additional field engineer requested | 4 | Sandeep Rao
LOG-000344 | PRJ-2024013 | 2024-11-10 | 4 | 29 | Green | Equipment dispatch completed; installation team mobilized | 3 | Sandeep Rao
LOG-000345 | PRJ-2024013 | 2024-11-17 | 4 | 33 | Amber | Equipment dispatch completed; installation team mobilized | 7 | Sandeep Rao
LOG-000346 | PRJ-2024013 | 2024-11-24 | 5 | 39 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Sandeep Rao
LOG-000347 | PRJ-2024013 | 2024-12-01 | 6 | 41 | Green | Weekly governance call held with client stakeholders | 2 | Sandeep Rao
LOG-000348 | PRJ-2024013 | 2024-12-08 | 6 | 45 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Sandeep Rao
LOG-000349 | PRJ-2024013 | 2024-12-15 | 7 | 48 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Sandeep Rao
LOG-000350 | PRJ-2024013 | 2024-12-22 | 7 | 49 | Green | Weekly governance call held with client stakeholders | 7 | Sandeep Rao
LOG-000351 | PRJ-2024013 | 2024-12-29 | 8 | 54 | Green | Equipment dispatch completed; installation team mobilized | 0 | Sandeep Rao
LOG-000352 | PRJ-2024013 | 2025-01-05 | 8 | 58 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Sandeep Rao
LOG-000353 | PRJ-2024013 | 2025-01-12 | 9 | 63 | Green | Resource constraint flagged; additional field engineer requested | 6 | Sandeep Rao
LOG-000354 | PRJ-2024013 | 2025-01-19 | 9 | 64 | Red | Vendor escalation raised for delayed circuit provisioning | 0 | Sandeep Rao
LOG-000355 | PRJ-2024013 | 2025-01-26 | 10 | 68 | Green | Client UAT sign-off received for batch of completed sites | 6 | Sandeep Rao
LOG-000356 | PRJ-2024013 | 2025-02-02 | 11 | 74 | Amber | Vendor escalation raised for delayed circuit provisioning | 7 | Sandeep Rao
LOG-000357 | PRJ-2024013 | 2025-02-09 | 12 | 80 | Green | Client UAT sign-off received for batch of completed sites | 2 | Sandeep Rao
LOG-000358 | PRJ-2024013 | 2025-02-16 | 12 | 86 | Green | Client UAT sign-off received for batch of completed sites | 1 | Sandeep Rao
LOG-000359 | PRJ-2024013 | 2025-02-23 | 13 | 88 | Green | Resource constraint flagged; additional field engineer requested | 3 | Sandeep Rao
LOG-000360 | PRJ-2024013 | 2025-03-02 | 13 | 91 | Amber | Client UAT sign-off received for batch of completed sites | 8 | Sandeep Rao
LOG-000361 | PRJ-2024013 | 2025-03-09 | 14 | 97 | Green | Resource constraint flagged; additional field engineer requested | 0 | Sandeep Rao
LOG-000362 | PRJ-2024013 | 2025-03-16 | 14 | 99 | Green | Equipment dispatch completed; installation team mobilized | 3 | Sandeep Rao
LOG-000363 | PRJ-2024013 | 2025-03-23 | 15 | 100 | Red | Equipment dispatch completed; installation team mobilized | 2 | Sandeep Rao
LOG-000364 | PRJ-2024013 | 2025-03-30 | 15 | 100 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Sandeep Rao
LOG-000365 | PRJ-2024014 | 2024-10-28 | 0 | 6 | Amber | Client UAT sign-off received for batch of completed sites | 3 | Rahul K. Patil
LOG-000366 | PRJ-2024014 | 2024-11-04 | 0 | 9 | Green | Client UAT sign-off received for batch of completed sites | 8 | Rahul K. Patil
LOG-000367 | PRJ-2024014 | 2024-11-11 | 0 | 10 | Green | Weekly governance call held with client stakeholders | 7 | Rahul K. Patil
LOG-000368 | PRJ-2024014 | 2024-11-18 | 0 | 12 | Red | Weekly governance call held with client stakeholders | 3 | Rahul K. Patil
LOG-000369 | PRJ-2024014 | 2024-11-25 | 0 | 18 | Red | Equipment dispatch completed; installation team mobilized | 7 | Rahul K. Patil
LOG-000370 | PRJ-2024014 | 2024-12-02 | 1 | 22 | Green | Weekly governance call held with client stakeholders | 6 | Rahul K. Patil
LOG-000371 | PRJ-2024014 | 2024-12-09 | 1 | 28 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Rahul K. Patil
LOG-000372 | PRJ-2024014 | 2024-12-16 | 1 | 29 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Rahul K. Patil
LOG-000373 | PRJ-2024014 | 2024-12-23 | 1 | 35 | Amber | Weekly governance call held with client stakeholders | 3 | Rahul K. Patil
LOG-000374 | PRJ-2024014 | 2024-12-30 | 1 | 36 | Red | Client UAT sign-off received for batch of completed sites | 2 | Rahul K. Patil
LOG-000375 | PRJ-2024014 | 2025-01-06 | 2 | 40 | Green | Client UAT sign-off received for batch of completed sites | 4 | Rahul K. Patil
LOG-000376 | PRJ-2024014 | 2025-01-13 | 2 | 43 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Rahul K. Patil
LOG-000377 | PRJ-2024014 | 2025-01-20 | 2 | 48 | Green | Survey activities progressing as per plan across allocated sites | 5 | Rahul K. Patil
LOG-000378 | PRJ-2024014 | 2025-01-27 | 2 | 52 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Rahul K. Patil
LOG-000379 | PRJ-2024014 | 2025-02-03 | 2 | 53 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Rahul K. Patil
LOG-000380 | PRJ-2024014 | 2025-02-10 | 2 | 55 | Green | Resource constraint flagged; additional field engineer requested | 0 | Rahul K. Patil
LOG-000381 | PRJ-2024014 | 2025-02-17 | 2 | 58 | Green | Client UAT sign-off received for batch of completed sites | 4 | Rahul K. Patil
LOG-000382 | PRJ-2024014 | 2025-02-24 | 2 | 59 | Amber | Vendor escalation raised for delayed circuit provisioning | 7 | Rahul K. Patil
LOG-000383 | PRJ-2024014 | 2025-03-03 | 3 | 65 | Green | Resource constraint flagged; additional field engineer requested | 4 | Rahul K. Patil
LOG-000384 | PRJ-2024014 | 2025-03-10 | 3 | 70 | Green | Survey activities progressing as per plan across allocated sites | 3 | Rahul K. Patil
LOG-000385 | PRJ-2024014 | 2025-03-17 | 3 | 76 | Green | Resource constraint flagged; additional field engineer requested | 3 | Rahul K. Patil
LOG-000386 | PRJ-2024014 | 2025-03-24 | 4 | 82 | Amber | Weekly governance call held with client stakeholders | 3 | Rahul K. Patil
LOG-000387 | PRJ-2024014 | 2025-03-31 | 4 | 87 | Amber | Equipment dispatch completed; installation team mobilized | 2 | Rahul K. Patil
LOG-000388 | PRJ-2024014 | 2025-04-07 | 4 | 91 | Green | Resource constraint flagged; additional field engineer requested | 5 | Rahul K. Patil
LOG-000389 | PRJ-2024014 | 2025-04-14 | 4 | 96 | Red | Client UAT sign-off received for batch of completed sites | 7 | Rahul K. Patil
LOG-000390 | PRJ-2024014 | 2025-04-21 | 5 | 100 | Amber | Weekly governance call held with client stakeholders | 0 | Rahul K. Patil
LOG-000391 | PRJ-2024014 | 2025-04-28 | 5 | 100 | Green | Equipment dispatch completed; installation team mobilized | 8 | Rahul K. Patil
LOG-000392 | PRJ-2024014 | 2025-05-05 | 5 | 100 | Red | Weekly governance call held with client stakeholders | 0 | Rahul K. Patil
LOG-000393 | PRJ-2024015 | 2024-09-15 | 10 | 4 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Farah Khan
LOG-000394 | PRJ-2024015 | 2024-09-22 | 22 | 9 | Red | Survey activities progressing as per plan across allocated sites | 5 | Farah Khan
LOG-000395 | PRJ-2024015 | 2024-09-29 | 30 | 12 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Farah Khan
LOG-000396 | PRJ-2024015 | 2024-10-06 | 32 | 13 | Green | Weekly governance call held with client stakeholders | 2 | Farah Khan
LOG-000397 | PRJ-2024015 | 2024-10-13 | 45 | 18 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Farah Khan
LOG-000398 | PRJ-2024015 | 2024-10-20 | 50 | 20 | Green | Client UAT sign-off received for batch of completed sites | 8 | Farah Khan
LOG-000399 | PRJ-2024015 | 2024-10-27 | 62 | 25 | Green | Client UAT sign-off received for batch of completed sites | 4 | Farah Khan
LOG-000400 | PRJ-2024015 | 2024-11-03 | 72 | 29 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Farah Khan
LOG-000401 | PRJ-2024015 | 2024-11-10 | 77 | 31 | Amber | Resource constraint flagged; additional field engineer requested | 8 | Farah Khan
LOG-000402 | PRJ-2024015 | 2024-11-17 | 90 | 36 | Green | Survey activities progressing as per plan across allocated sites | 5 | Farah Khan
LOG-000403 | PRJ-2024015 | 2024-11-24 | 100 | 40 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Farah Khan
LOG-000404 | PRJ-2024015 | 2024-12-01 | 115 | 46 | Red | Survey activities progressing as per plan across allocated sites | 8 | Farah Khan
LOG-000405 | PRJ-2024015 | 2024-12-08 | 122 | 49 | Green | Weekly governance call held with client stakeholders | 5 | Farah Khan
LOG-000406 | PRJ-2024015 | 2024-12-15 | 125 | 50 | Red | Equipment dispatch completed; installation team mobilized | 6 | Farah Khan
LOG-000407 | PRJ-2024015 | 2024-12-22 | 127 | 51 | Amber | Client UAT sign-off received for batch of completed sites | 5 | Farah Khan
LOG-000408 | PRJ-2024015 | 2024-12-29 | 135 | 54 | Red | Vendor escalation raised for delayed circuit provisioning | 2 | Farah Khan
LOG-000409 | PRJ-2024015 | 2025-01-05 | 140 | 56 | Green | Weekly governance call held with client stakeholders | 5 | Farah Khan
LOG-000410 | PRJ-2024015 | 2025-01-12 | 147 | 59 | Green | Weekly governance call held with client stakeholders | 8 | Farah Khan
LOG-000411 | PRJ-2024015 | 2025-01-19 | 155 | 62 | Red | Client UAT sign-off received for batch of completed sites | 0 | Farah Khan
LOG-000412 | PRJ-2024015 | 2025-01-26 | 165 | 66 | Green | Survey activities progressing as per plan across allocated sites | 2 | Farah Khan
LOG-000413 | PRJ-2024015 | 2025-02-02 | 170 | 68 | Red | Resource constraint flagged; additional field engineer requested | 2 | Farah Khan
LOG-000414 | PRJ-2024015 | 2025-02-09 | 182 | 73 | Green | Resource constraint flagged; additional field engineer requested | 3 | Farah Khan
LOG-000415 | PRJ-2024015 | 2025-02-16 | 190 | 76 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Farah Khan
LOG-000416 | PRJ-2024015 | 2025-02-23 | 202 | 81 | Red | Client UAT sign-off received for batch of completed sites | 1 | Farah Khan
LOG-000417 | PRJ-2024015 | 2025-03-02 | 210 | 84 | Green | Equipment dispatch completed; installation team mobilized | 6 | Farah Khan
LOG-000418 | PRJ-2024015 | 2025-03-09 | 217 | 87 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Farah Khan
LOG-000419 | PRJ-2024015 | 2025-03-16 | 230 | 92 | Green | Resource constraint flagged; additional field engineer requested | 7 | Farah Khan
LOG-000420 | PRJ-2024015 | 2025-03-23 | 237 | 95 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Farah Khan
LOG-000421 | PRJ-2024016 | 2024-10-02 | 0 | 3 | Green | Client UAT sign-off received for batch of completed sites | 2 | Manish Agarwal
LOG-000422 | PRJ-2024016 | 2024-10-09 | 2 | 8 | Green | Survey activities progressing as per plan across allocated sites | 0 | Manish Agarwal
LOG-000423 | PRJ-2024016 | 2024-10-16 | 2 | 9 | Red | Equipment dispatch completed; installation team mobilized | 0 | Manish Agarwal
LOG-000424 | PRJ-2024016 | 2024-10-23 | 4 | 14 | Red | Survey activities progressing as per plan across allocated sites | 8 | Manish Agarwal
LOG-000425 | PRJ-2024016 | 2024-10-30 | 5 | 18 | Green | Client UAT sign-off received for batch of completed sites | 4 | Manish Agarwal
LOG-000426 | PRJ-2024016 | 2024-11-06 | 6 | 21 | Green | Weekly governance call held with client stakeholders | 5 | Manish Agarwal
LOG-000427 | PRJ-2024016 | 2024-11-13 | 7 | 26 | Green | Weekly governance call held with client stakeholders | 0 | Manish Agarwal
LOG-000428 | PRJ-2024016 | 2024-11-20 | 8 | 29 | Red | Survey activities progressing as per plan across allocated sites | 1 | Manish Agarwal
LOG-000429 | PRJ-2024016 | 2024-11-27 | 9 | 30 | Red | Weekly governance call held with client stakeholders | 8 | Manish Agarwal
LOG-000430 | PRJ-2024016 | 2024-12-04 | 10 | 36 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000431 | PRJ-2024016 | 2024-12-11 | 11 | 39 | Green | Client UAT sign-off received for batch of completed sites | 6 | Manish Agarwal
LOG-000432 | PRJ-2024016 | 2024-12-18 | 12 | 40 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Manish Agarwal
LOG-000433 | PRJ-2024016 | 2024-12-25 | 13 | 45 | Red | Client UAT sign-off received for batch of completed sites | 6 | Manish Agarwal
LOG-000434 | PRJ-2024016 | 2025-01-01 | 14 | 47 | Amber | Resource constraint flagged; additional field engineer requested | 4 | Manish Agarwal
LOG-000435 | PRJ-2024016 | 2025-01-08 | 15 | 51 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Manish Agarwal
LOG-000436 | PRJ-2024016 | 2025-01-15 | 15 | 53 | Green | Resource constraint flagged; additional field engineer requested | 7 | Manish Agarwal
LOG-000437 | PRJ-2024016 | 2025-01-22 | 17 | 57 | Green | Weekly governance call held with client stakeholders | 6 | Manish Agarwal
LOG-000438 | PRJ-2024016 | 2025-01-29 | 17 | 59 | Green | Client UAT sign-off received for batch of completed sites | 2 | Manish Agarwal
LOG-000439 | PRJ-2024016 | 2025-02-05 | 18 | 61 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Manish Agarwal
LOG-000440 | PRJ-2024016 | 2025-02-12 | 18 | 62 | Red | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000441 | PRJ-2024016 | 2025-02-19 | 18 | 63 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Manish Agarwal
LOG-000442 | PRJ-2024016 | 2025-02-26 | 19 | 66 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Manish Agarwal
LOG-000443 | PRJ-2024016 | 2025-03-05 | 20 | 68 | Green | Equipment dispatch completed; installation team mobilized | 0 | Manish Agarwal
LOG-000444 | PRJ-2024016 | 2025-03-12 | 21 | 71 | Green | Survey activities progressing as per plan across allocated sites | 4 | Manish Agarwal
LOG-000445 | PRJ-2024016 | 2025-03-19 | 21 | 72 | Green | Weekly governance call held with client stakeholders | 0 | Manish Agarwal
LOG-000446 | PRJ-2024016 | 2025-03-26 | 22 | 75 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Manish Agarwal
LOG-000447 | PRJ-2024016 | 2025-04-02 | 22 | 76 | Red | Client UAT sign-off received for batch of completed sites | 6 | Manish Agarwal
LOG-000448 | PRJ-2024016 | 2025-04-09 | 23 | 78 | Red | Survey activities progressing as per plan across allocated sites | 4 | Manish Agarwal
LOG-000449 | PRJ-2024017 | 2024-07-24 | 0 | 3 | Red | Client UAT sign-off received for batch of completed sites | 7 | Farah Khan
LOG-000450 | PRJ-2024017 | 2024-07-31 | 0 | 5 | Amber | Client UAT sign-off received for batch of completed sites | 0 | Farah Khan
LOG-000451 | PRJ-2024017 | 2024-08-07 | 0 | 10 | Red | Resource constraint flagged; additional field engineer requested | 5 | Farah Khan
LOG-000452 | PRJ-2024017 | 2024-08-14 | 0 | 15 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Farah Khan
LOG-000453 | PRJ-2024017 | 2024-08-21 | 0 | 16 | Amber | Resource constraint flagged; additional field engineer requested | 4 | Farah Khan
LOG-000454 | PRJ-2024017 | 2024-08-28 | 1 | 20 | Green | Client UAT sign-off received for batch of completed sites | 6 | Farah Khan
LOG-000455 | PRJ-2024017 | 2024-09-04 | 1 | 23 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Farah Khan
LOG-000456 | PRJ-2024017 | 2024-09-11 | 1 | 29 | Red | Vendor escalation raised for delayed circuit provisioning | 5 | Farah Khan
LOG-000457 | PRJ-2024017 | 2024-09-18 | 1 | 34 | Amber | Resource constraint flagged; additional field engineer requested | 4 | Farah Khan
LOG-000458 | PRJ-2024017 | 2024-09-25 | 1 | 39 | Red | Weekly governance call held with client stakeholders | 5 | Farah Khan
LOG-000459 | PRJ-2024017 | 2024-10-02 | 2 | 45 | Green | Client UAT sign-off received for batch of completed sites | 1 | Farah Khan
LOG-000460 | PRJ-2024017 | 2024-10-09 | 2 | 47 | Green | Resource constraint flagged; additional field engineer requested | 8 | Farah Khan
LOG-000461 | PRJ-2024017 | 2024-10-16 | 2 | 50 | Green | Equipment dispatch completed; installation team mobilized | 6 | Farah Khan
LOG-000462 | PRJ-2024017 | 2024-10-23 | 2 | 51 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Farah Khan
LOG-000463 | PRJ-2024017 | 2024-10-30 | 2 | 53 | Green | Client UAT sign-off received for batch of completed sites | 4 | Farah Khan
LOG-000464 | PRJ-2024017 | 2024-11-06 | 2 | 57 | Amber | Client UAT sign-off received for batch of completed sites | 4 | Farah Khan
LOG-000465 | PRJ-2024017 | 2024-11-13 | 2 | 59 | Amber | Weekly governance call held with client stakeholders | 2 | Farah Khan
LOG-000466 | PRJ-2024017 | 2024-11-20 | 3 | 60 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Farah Khan
LOG-000467 | PRJ-2024017 | 2024-11-27 | 3 | 63 | Red | Client UAT sign-off received for batch of completed sites | 7 | Farah Khan
LOG-000468 | PRJ-2024017 | 2024-12-04 | 3 | 66 | Amber | Resource constraint flagged; additional field engineer requested | 1 | Farah Khan
LOG-000469 | PRJ-2024017 | 2024-12-11 | 3 | 71 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Farah Khan
LOG-000470 | PRJ-2024017 | 2024-12-18 | 3 | 75 | Green | Equipment dispatch completed; installation team mobilized | 7 | Farah Khan
LOG-000471 | PRJ-2024017 | 2024-12-25 | 4 | 80 | Red | Resource constraint flagged; additional field engineer requested | 3 | Farah Khan
LOG-000472 | PRJ-2024017 | 2025-01-01 | 4 | 82 | Green | Resource constraint flagged; additional field engineer requested | 0 | Farah Khan
LOG-000473 | PRJ-2024017 | 2025-01-08 | 4 | 88 | Green | Survey activities progressing as per plan across allocated sites | 5 | Farah Khan
LOG-000474 | PRJ-2024017 | 2025-01-15 | 4 | 93 | Green | Equipment dispatch completed; installation team mobilized | 4 | Farah Khan
LOG-000475 | PRJ-2024017 | 2025-01-22 | 4 | 96 | Green | Client UAT sign-off received for batch of completed sites | 3 | Farah Khan
LOG-000476 | PRJ-2024017 | 2025-01-29 | 5 | 100 | Green | Vendor escalation raised for delayed circuit provisioning | 5 | Farah Khan
LOG-000477 | PRJ-2024018 | 2024-08-19 | 0 | 3 | Green | Equipment dispatch completed; installation team mobilized | 1 | Rahul K. Patil
LOG-000478 | PRJ-2024018 | 2024-08-26 | 0 | 8 | Green | Equipment dispatch completed; installation team mobilized | 4 | Rahul K. Patil
LOG-000479 | PRJ-2024018 | 2024-09-02 | 0 | 10 | Green | Client UAT sign-off received for batch of completed sites | 2 | Rahul K. Patil
LOG-000480 | PRJ-2024018 | 2024-09-09 | 0 | 16 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Rahul K. Patil
LOG-000481 | PRJ-2024018 | 2024-09-16 | 0 | 18 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Rahul K. Patil
LOG-000482 | PRJ-2024018 | 2024-09-23 | 0 | 19 | Amber | Equipment dispatch completed; installation team mobilized | 3 | Rahul K. Patil
LOG-000483 | PRJ-2024018 | 2024-09-30 | 1 | 21 | Green | Resource constraint flagged; additional field engineer requested | 3 | Rahul K. Patil
LOG-000484 | PRJ-2024018 | 2024-10-07 | 1 | 27 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Rahul K. Patil
LOG-000485 | PRJ-2024018 | 2024-10-14 | 1 | 30 | Red | Weekly governance call held with client stakeholders | 8 | Rahul K. Patil
LOG-000486 | PRJ-2024018 | 2024-10-21 | 1 | 31 | Red | Client UAT sign-off received for batch of completed sites | 2 | Rahul K. Patil
LOG-000487 | PRJ-2024018 | 2024-10-28 | 1 | 36 | Green | Weekly governance call held with client stakeholders | 1 | Rahul K. Patil
LOG-000488 | PRJ-2024018 | 2024-11-04 | 2 | 41 | Amber | Survey activities progressing as per plan across allocated sites | 8 | Rahul K. Patil
LOG-000489 | PRJ-2024018 | 2024-11-11 | 2 | 45 | Red | Client UAT sign-off received for batch of completed sites | 5 | Rahul K. Patil
LOG-000490 | PRJ-2024018 | 2024-11-18 | 2 | 51 | Amber | Vendor escalation raised for delayed circuit provisioning | 8 | Rahul K. Patil
LOG-000491 | PRJ-2024018 | 2024-11-25 | 2 | 53 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Rahul K. Patil
LOG-000492 | PRJ-2024018 | 2024-12-02 | 2 | 57 | Green | Survey activities progressing as per plan across allocated sites | 7 | Rahul K. Patil
LOG-000493 | PRJ-2024018 | 2024-12-09 | 3 | 61 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Rahul K. Patil
LOG-000494 | PRJ-2024018 | 2024-12-16 | 3 | 67 | Green | Resource constraint flagged; additional field engineer requested | 6 | Rahul K. Patil
LOG-000495 | PRJ-2024018 | 2024-12-23 | 3 | 71 | Amber | Survey activities progressing as per plan across allocated sites | 7 | Rahul K. Patil
LOG-000496 | PRJ-2024018 | 2024-12-30 | 3 | 77 | Red | Client UAT sign-off received for batch of completed sites | 8 | Rahul K. Patil
LOG-000497 | PRJ-2024018 | 2025-01-06 | 4 | 80 | Green | Survey activities progressing as per plan across allocated sites | 0 | Rahul K. Patil
LOG-000498 | PRJ-2024018 | 2025-01-13 | 4 | 86 | Green | Equipment dispatch completed; installation team mobilized | 5 | Rahul K. Patil
LOG-000499 | PRJ-2024018 | 2025-01-20 | 4 | 92 | Green | Client UAT sign-off received for batch of completed sites | 2 | Rahul K. Patil
LOG-000500 | PRJ-2024018 | 2025-01-27 | 4 | 97 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Rahul K. Patil
LOG-000501 | PRJ-2024018 | 2025-02-03 | 5 | 100 | Green | Survey activities progressing as per plan across allocated sites | 7 | Rahul K. Patil
LOG-000502 | PRJ-2024018 | 2025-02-10 | 5 | 100 | Green | Weekly governance call held with client stakeholders | 2 | Rahul K. Patil
LOG-000503 | PRJ-2024018 | 2025-02-17 | 5 | 100 | Green | Client UAT sign-off received for batch of completed sites | 5 | Rahul K. Patil
LOG-000504 | PRJ-2024018 | 2025-02-24 | 5 | 100 | Amber | Vendor escalation raised for delayed circuit provisioning | 2 | Rahul K. Patil
LOG-000505 | PRJ-2024019 | 2024-07-01 | 2 | 3 | Green | Client UAT sign-off received for batch of completed sites | 3 | Rahul K. Patil
LOG-000506 | PRJ-2024019 | 2024-07-08 | 3 | 4 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Rahul K. Patil
LOG-000507 | PRJ-2024019 | 2024-07-15 | 7 | 10 | Green | Weekly governance call held with client stakeholders | 5 | Rahul K. Patil
LOG-000508 | PRJ-2024019 | 2024-07-22 | 10 | 14 | Amber | Survey activities progressing as per plan across allocated sites | 1 | Rahul K. Patil
LOG-000509 | PRJ-2024019 | 2024-07-29 | 13 | 18 | Amber | Equipment dispatch completed; installation team mobilized | 3 | Rahul K. Patil
LOG-000510 | PRJ-2024019 | 2024-08-05 | 17 | 23 | Red | Resource constraint flagged; additional field engineer requested | 7 | Rahul K. Patil
LOG-000511 | PRJ-2024019 | 2024-08-12 | 18 | 25 | Green | Resource constraint flagged; additional field engineer requested | 5 | Rahul K. Patil
LOG-000512 | PRJ-2024019 | 2024-08-19 | 22 | 30 | Green | Weekly governance call held with client stakeholders | 8 | Rahul K. Patil
LOG-000513 | PRJ-2024019 | 2024-08-26 | 25 | 34 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Rahul K. Patil
LOG-000514 | PRJ-2024019 | 2024-09-02 | 27 | 37 | Green | Client UAT sign-off received for batch of completed sites | 5 | Rahul K. Patil
LOG-000515 | PRJ-2024019 | 2024-09-09 | 32 | 43 | Green | Resource constraint flagged; additional field engineer requested | 3 | Rahul K. Patil
LOG-000516 | PRJ-2024019 | 2024-09-16 | 36 | 49 | Red | Resource constraint flagged; additional field engineer requested | 0 | Rahul K. Patil
LOG-000517 | PRJ-2024019 | 2024-09-23 | 39 | 52 | Green | Weekly governance call held with client stakeholders | 6 | Rahul K. Patil
LOG-000518 | PRJ-2024019 | 2024-09-30 | 41 | 55 | Red | Weekly governance call held with client stakeholders | 7 | Rahul K. Patil
LOG-000519 | PRJ-2024019 | 2024-10-07 | 42 | 57 | Amber | Vendor escalation raised for delayed circuit provisioning | 3 | Rahul K. Patil
LOG-000520 | PRJ-2024019 | 2024-10-14 | 46 | 62 | Green | Survey activities progressing as per plan across allocated sites | 7 | Rahul K. Patil
LOG-000521 | PRJ-2024019 | 2024-10-21 | 51 | 68 | Green | Equipment dispatch completed; installation team mobilized | 1 | Rahul K. Patil
LOG-000522 | PRJ-2024019 | 2024-10-28 | 52 | 70 | Green | Client UAT sign-off received for batch of completed sites | 6 | Rahul K. Patil
LOG-000523 | PRJ-2024019 | 2024-11-04 | 55 | 74 | Green | Survey activities progressing as per plan across allocated sites | 2 | Rahul K. Patil
LOG-000524 | PRJ-2024019 | 2024-11-11 | 59 | 79 | Green | Equipment dispatch completed; installation team mobilized | 6 | Rahul K. Patil
LOG-000525 | PRJ-2024019 | 2024-11-18 | 63 | 84 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Rahul K. Patil
LOG-000526 | PRJ-2024019 | 2024-11-25 | 63 | 85 | Green | Client UAT sign-off received for batch of completed sites | 8 | Rahul K. Patil
LOG-000527 | PRJ-2024019 | 2024-12-02 | 66 | 88 | Green | Client UAT sign-off received for batch of completed sites | 8 | Rahul K. Patil
LOG-000528 | PRJ-2024019 | 2024-12-09 | 67 | 90 | Green | Equipment dispatch completed; installation team mobilized | 2 | Rahul K. Patil
LOG-000529 | PRJ-2024019 | 2024-12-16 | 69 | 93 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Rahul K. Patil
LOG-000530 | PRJ-2024019 | 2024-12-23 | 70 | 94 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Rahul K. Patil
LOG-000531 | PRJ-2024019 | 2024-12-30 | 73 | 98 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Rahul K. Patil
LOG-000532 | PRJ-2024019 | 2025-01-06 | 75 | 100 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Rahul K. Patil
LOG-000533 | PRJ-2024020 | 2024-12-10 | 2 | 1 | Amber | Vendor escalation raised for delayed circuit provisioning | 4 | Chinmay Deshpande
LOG-000534 | PRJ-2024020 | 2024-12-17 | 14 | 7 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Chinmay Deshpande
LOG-000535 | PRJ-2024020 | 2024-12-24 | 24 | 12 | Green | Client UAT sign-off received for batch of completed sites | 7 | Chinmay Deshpande
LOG-000536 | PRJ-2024020 | 2024-12-31 | 28 | 14 | Green | Vendor escalation raised for delayed circuit provisioning | 6 | Chinmay Deshpande
LOG-000537 | PRJ-2024020 | 2025-01-07 | 36 | 18 | Green | Weekly governance call held with client stakeholders | 6 | Chinmay Deshpande
LOG-000538 | PRJ-2024020 | 2025-01-14 | 38 | 19 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Chinmay Deshpande
LOG-000539 | PRJ-2024020 | 2025-01-21 | 44 | 22 | Green | Vendor escalation raised for delayed circuit provisioning | 5 | Chinmay Deshpande
LOG-000540 | PRJ-2024020 | 2025-01-28 | 52 | 26 | Green | Weekly governance call held with client stakeholders | 5 | Chinmay Deshpande
LOG-000541 | PRJ-2024020 | 2025-02-04 | 58 | 29 | Green | Resource constraint flagged; additional field engineer requested | 0 | Chinmay Deshpande
LOG-000542 | PRJ-2024020 | 2025-02-11 | 64 | 32 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Chinmay Deshpande
LOG-000543 | PRJ-2024020 | 2025-02-18 | 70 | 35 | Green | Equipment dispatch completed; installation team mobilized | 0 | Chinmay Deshpande
LOG-000544 | PRJ-2024020 | 2025-02-25 | 74 | 37 | Green | Weekly governance call held with client stakeholders | 8 | Chinmay Deshpande
LOG-000545 | PRJ-2024020 | 2025-03-04 | 86 | 43 | Red | Weekly governance call held with client stakeholders | 8 | Chinmay Deshpande
LOG-000546 | PRJ-2024020 | 2025-03-11 | 96 | 48 | Green | Survey activities progressing as per plan across allocated sites | 8 | Chinmay Deshpande
LOG-000547 | PRJ-2024020 | 2025-03-18 | 102 | 51 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Chinmay Deshpande
LOG-000548 | PRJ-2024020 | 2025-03-25 | 106 | 53 | Green | Equipment dispatch completed; installation team mobilized | 7 | Chinmay Deshpande
LOG-000549 | PRJ-2024020 | 2025-04-01 | 116 | 58 | Green | Resource constraint flagged; additional field engineer requested | 5 | Chinmay Deshpande
LOG-000550 | PRJ-2024020 | 2025-04-08 | 124 | 62 | Green | Survey activities progressing as per plan across allocated sites | 8 | Chinmay Deshpande
LOG-000551 | PRJ-2024020 | 2025-04-15 | 126 | 63 | Green | Equipment dispatch completed; installation team mobilized | 1 | Chinmay Deshpande
LOG-000552 | PRJ-2024020 | 2025-04-22 | 128 | 64 | Green | Survey activities progressing as per plan across allocated sites | 5 | Chinmay Deshpande
LOG-000553 | PRJ-2024020 | 2025-04-29 | 130 | 65 | Amber | Weekly governance call held with client stakeholders | 4 | Chinmay Deshpande
LOG-000554 | PRJ-2024020 | 2025-05-06 | 140 | 70 | Green | Survey activities progressing as per plan across allocated sites | 6 | Chinmay Deshpande
LOG-000555 | PRJ-2024020 | 2025-05-13 | 148 | 74 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Chinmay Deshpande
LOG-000556 | PRJ-2024020 | 2025-05-20 | 156 | 78 | Green | Survey activities progressing as per plan across allocated sites | 5 | Chinmay Deshpande
LOG-000557 | PRJ-2024020 | 2025-05-27 | 168 | 84 | Green | Weekly governance call held with client stakeholders | 6 | Chinmay Deshpande
LOG-000558 | PRJ-2024020 | 2025-06-03 | 176 | 88 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Chinmay Deshpande
LOG-000559 | PRJ-2024020 | 2025-06-10 | 178 | 89 | Green | Client UAT sign-off received for batch of completed sites | 5 | Chinmay Deshpande
LOG-000560 | PRJ-2024020 | 2025-06-17 | 180 | 90 | Green | Survey activities progressing as per plan across allocated sites | 4 | Chinmay Deshpande
LOG-000561 | PRJ-2024021 | 2025-04-23 | 0 | 3 | Red | Equipment dispatch completed; installation team mobilized | 0 | Karthik Subramanian
LOG-000562 | PRJ-2024021 | 2025-04-30 | 1 | 9 | Red | Vendor escalation raised for delayed circuit provisioning | 2 | Karthik Subramanian
LOG-000563 | PRJ-2024021 | 2025-05-07 | 1 | 11 | Amber | Survey activities progressing as per plan across allocated sites | 6 | Karthik Subramanian
LOG-000564 | PRJ-2024021 | 2025-05-14 | 2 | 16 | Red | Weekly governance call held with client stakeholders | 0 | Karthik Subramanian
LOG-000565 | PRJ-2024021 | 2025-05-21 | 3 | 22 | Amber | Equipment dispatch completed; installation team mobilized | 4 | Karthik Subramanian
LOG-000566 | PRJ-2024021 | 2025-05-28 | 4 | 27 | Green | Equipment dispatch completed; installation team mobilized | 6 | Karthik Subramanian
LOG-000567 | PRJ-2024021 | 2025-06-04 | 4 | 33 | Green | Weekly governance call held with client stakeholders | 8 | Karthik Subramanian
LOG-000568 | PRJ-2024021 | 2025-06-11 | 5 | 34 | Green | Resource constraint flagged; additional field engineer requested | 6 | Karthik Subramanian
LOG-000569 | PRJ-2024021 | 2025-06-18 | 5 | 36 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Karthik Subramanian
LOG-000570 | PRJ-2024021 | 2025-06-25 | 5 | 39 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Karthik Subramanian
LOG-000571 | PRJ-2024021 | 2025-07-02 | 6 | 42 | Green | Equipment dispatch completed; installation team mobilized | 8 | Karthik Subramanian
LOG-000572 | PRJ-2024021 | 2025-07-09 | 7 | 48 | Green | Client UAT sign-off received for batch of completed sites | 0 | Karthik Subramanian
LOG-000573 | PRJ-2024021 | 2025-07-16 | 7 | 53 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Karthik Subramanian
LOG-000574 | PRJ-2024021 | 2025-07-23 | 8 | 54 | Green | Resource constraint flagged; additional field engineer requested | 2 | Karthik Subramanian
LOG-000575 | PRJ-2024021 | 2025-07-30 | 8 | 57 | Green | Weekly governance call held with client stakeholders | 6 | Karthik Subramanian
LOG-000576 | PRJ-2024021 | 2025-08-06 | 9 | 61 | Green | Weekly governance call held with client stakeholders | 0 | Karthik Subramanian
LOG-000577 | PRJ-2024021 | 2025-08-13 | 9 | 62 | Green | Equipment dispatch completed; installation team mobilized | 5 | Karthik Subramanian
LOG-000578 | PRJ-2024021 | 2025-08-20 | 9 | 64 | Red | Weekly governance call held with client stakeholders | 8 | Karthik Subramanian
LOG-000579 | PRJ-2024021 | 2025-08-27 | 9 | 65 | Green | Weekly governance call held with client stakeholders | 8 | Karthik Subramanian
LOG-000580 | PRJ-2024021 | 2025-09-03 | 10 | 70 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Karthik Subramanian
LOG-000581 | PRJ-2024021 | 2025-09-10 | 10 | 73 | Green | Equipment dispatch completed; installation team mobilized | 0 | Karthik Subramanian
LOG-000582 | PRJ-2024021 | 2025-09-17 | 11 | 79 | Red | Client UAT sign-off received for batch of completed sites | 1 | Karthik Subramanian
LOG-000583 | PRJ-2024021 | 2025-09-24 | 12 | 85 | Amber | Survey activities progressing as per plan across allocated sites | 8 | Karthik Subramanian
LOG-000584 | PRJ-2024021 | 2025-10-01 | 13 | 89 | Green | Survey activities progressing as per plan across allocated sites | 7 | Karthik Subramanian
LOG-000585 | PRJ-2024021 | 2025-10-08 | 13 | 90 | Red | Vendor escalation raised for delayed circuit provisioning | 1 | Karthik Subramanian
LOG-000586 | PRJ-2024021 | 2025-10-15 | 14 | 94 | Amber | Vendor escalation raised for delayed circuit provisioning | 8 | Karthik Subramanian
LOG-000587 | PRJ-2024021 | 2025-10-22 | 14 | 95 | Green | Survey activities progressing as per plan across allocated sites | 3 | Karthik Subramanian
LOG-000588 | PRJ-2024021 | 2025-10-29 | 15 | 100 | Red | Equipment dispatch completed; installation team mobilized | 6 | Karthik Subramanian
LOG-000589 | PRJ-2024022 | 2025-03-21 | 0 | 5 | Green | Weekly governance call held with client stakeholders | 2 | Manish Agarwal
LOG-000590 | PRJ-2024022 | 2025-03-28 | 1 | 10 | Green | Equipment dispatch completed; installation team mobilized | 0 | Manish Agarwal
LOG-000591 | PRJ-2024022 | 2025-04-04 | 1 | 11 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Manish Agarwal
LOG-000592 | PRJ-2024022 | 2025-04-11 | 1 | 14 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Manish Agarwal
LOG-000593 | PRJ-2024022 | 2025-04-18 | 1 | 17 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Manish Agarwal
LOG-000594 | PRJ-2024022 | 2025-04-25 | 1 | 19 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Manish Agarwal
LOG-000595 | PRJ-2024022 | 2025-05-02 | 2 | 20 | Green | Client UAT sign-off received for batch of completed sites | 6 | Manish Agarwal
LOG-000596 | PRJ-2024022 | 2025-05-09 | 2 | 25 | Red | Client UAT sign-off received for batch of completed sites | 6 | Manish Agarwal
LOG-000597 | PRJ-2024022 | 2025-05-16 | 2 | 27 | Green | Resource constraint flagged; additional field engineer requested | 5 | Manish Agarwal
LOG-000598 | PRJ-2024022 | 2025-05-23 | 3 | 31 | Red | Equipment dispatch completed; installation team mobilized | 7 | Manish Agarwal
LOG-000599 | PRJ-2024022 | 2025-05-30 | 3 | 34 | Green | Survey activities progressing as per plan across allocated sites | 8 | Manish Agarwal
LOG-000600 | PRJ-2024022 | 2025-06-06 | 3 | 35 | Red | Weekly governance call held with client stakeholders | 8 | Manish Agarwal
LOG-000601 | PRJ-2024022 | 2025-06-13 | 4 | 40 | Amber | Survey activities progressing as per plan across allocated sites | 7 | Manish Agarwal
LOG-000602 | PRJ-2024022 | 2025-06-20 | 4 | 42 | Green | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000603 | PRJ-2024022 | 2025-06-27 | 4 | 46 | Green | Client UAT sign-off received for batch of completed sites | 0 | Manish Agarwal
LOG-000604 | PRJ-2024022 | 2025-07-04 | 4 | 49 | Green | Client UAT sign-off received for batch of completed sites | 1 | Manish Agarwal
LOG-000605 | PRJ-2024022 | 2025-07-11 | 5 | 52 | Green | Client UAT sign-off received for batch of completed sites | 1 | Manish Agarwal
LOG-000606 | PRJ-2024022 | 2025-07-18 | 5 | 56 | Green | Survey activities progressing as per plan across allocated sites | 4 | Manish Agarwal
LOG-000607 | PRJ-2024022 | 2025-07-25 | 5 | 59 | Green | Equipment dispatch completed; installation team mobilized | 2 | Manish Agarwal
LOG-000608 | PRJ-2024022 | 2025-08-01 | 6 | 63 | Green | Equipment dispatch completed; installation team mobilized | 5 | Manish Agarwal
LOG-000609 | PRJ-2024022 | 2025-08-08 | 6 | 69 | Red | Weekly governance call held with client stakeholders | 2 | Manish Agarwal
LOG-000610 | PRJ-2024022 | 2025-08-15 | 7 | 74 | Amber | Weekly governance call held with client stakeholders | 4 | Manish Agarwal
LOG-000611 | PRJ-2024022 | 2025-08-22 | 8 | 80 | Green | Equipment dispatch completed; installation team mobilized | 1 | Manish Agarwal
LOG-000612 | PRJ-2024022 | 2025-08-29 | 8 | 86 | Red | Resource constraint flagged; additional field engineer requested | 1 | Manish Agarwal
LOG-000613 | PRJ-2024022 | 2025-09-05 | 8 | 88 | Amber | Vendor escalation raised for delayed circuit provisioning | 0 | Manish Agarwal
LOG-000614 | PRJ-2024022 | 2025-09-12 | 9 | 91 | Red | Vendor escalation raised for delayed circuit provisioning | 7 | Manish Agarwal
LOG-000615 | PRJ-2024022 | 2025-09-19 | 9 | 95 | Green | Survey activities progressing as per plan across allocated sites | 3 | Manish Agarwal
LOG-000616 | PRJ-2024022 | 2025-09-26 | 10 | 100 | Green | Client UAT sign-off received for batch of completed sites | 3 | Manish Agarwal
LOG-000617 | PRJ-2024023 | 2025-06-26 | 15 | 5 | Amber | Equipment dispatch completed; installation team mobilized | 2 | Ananya Joshi
LOG-000618 | PRJ-2024023 | 2025-07-03 | 24 | 8 | Green | Resource constraint flagged; additional field engineer requested | 7 | Ananya Joshi
LOG-000619 | PRJ-2024023 | 2025-07-10 | 42 | 14 | Amber | Survey activities progressing as per plan across allocated sites | 7 | Ananya Joshi
LOG-000620 | PRJ-2024023 | 2025-07-17 | 51 | 17 | Green | Equipment dispatch completed; installation team mobilized | 6 | Ananya Joshi
LOG-000621 | PRJ-2024023 | 2025-07-24 | 60 | 20 | Green | Survey activities progressing as per plan across allocated sites | 2 | Ananya Joshi
LOG-000622 | PRJ-2024023 | 2025-07-31 | 72 | 24 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Ananya Joshi
LOG-000623 | PRJ-2024023 | 2025-08-07 | 78 | 26 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Ananya Joshi
LOG-000624 | PRJ-2024023 | 2025-08-14 | 87 | 29 | Green | Client UAT sign-off received for batch of completed sites | 1 | Ananya Joshi
LOG-000625 | PRJ-2024023 | 2025-08-21 | 102 | 34 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Ananya Joshi
LOG-000626 | PRJ-2024023 | 2025-08-28 | 120 | 40 | Green | Resource constraint flagged; additional field engineer requested | 1 | Ananya Joshi
LOG-000627 | PRJ-2024023 | 2025-09-04 | 126 | 42 | Red | Equipment dispatch completed; installation team mobilized | 1 | Ananya Joshi
LOG-000628 | PRJ-2024023 | 2025-09-11 | 144 | 48 | Green | Equipment dispatch completed; installation team mobilized | 1 | Ananya Joshi
LOG-000629 | PRJ-2024023 | 2025-09-18 | 147 | 49 | Red | Weekly governance call held with client stakeholders | 5 | Ananya Joshi
LOG-000630 | PRJ-2024023 | 2025-09-25 | 156 | 52 | Green | Resource constraint flagged; additional field engineer requested | 5 | Ananya Joshi
LOG-000631 | PRJ-2024023 | 2025-10-02 | 162 | 54 | Amber | Equipment dispatch completed; installation team mobilized | 0 | Ananya Joshi
LOG-000632 | PRJ-2024023 | 2025-10-09 | 171 | 57 | Amber | Vendor escalation raised for delayed circuit provisioning | 8 | Ananya Joshi
LOG-000633 | PRJ-2024023 | 2025-10-16 | 189 | 63 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Ananya Joshi
LOG-000634 | PRJ-2024023 | 2025-10-23 | 207 | 69 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Ananya Joshi
LOG-000635 | PRJ-2024023 | 2025-10-30 | 219 | 73 | Green | Client UAT sign-off received for batch of completed sites | 1 | Ananya Joshi
LOG-000636 | PRJ-2024023 | 2025-11-06 | 225 | 75 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Ananya Joshi
LOG-000637 | PRJ-2024023 | 2025-11-13 | 234 | 78 | Green | Weekly governance call held with client stakeholders | 2 | Ananya Joshi
LOG-000638 | PRJ-2024023 | 2025-11-20 | 252 | 84 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Ananya Joshi
LOG-000639 | PRJ-2024023 | 2025-11-27 | 267 | 89 | Green | Weekly governance call held with client stakeholders | 3 | Ananya Joshi
LOG-000640 | PRJ-2024023 | 2025-12-04 | 273 | 91 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Ananya Joshi
LOG-000641 | PRJ-2024023 | 2025-12-11 | 285 | 95 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Ananya Joshi
LOG-000642 | PRJ-2024023 | 2025-12-18 | 297 | 99 | Green | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-000643 | PRJ-2024023 | 2025-12-25 | 300 | 100 | Amber | Client UAT sign-off received for batch of completed sites | 4 | Ananya Joshi
LOG-000644 | PRJ-2024023 | 2026-01-01 | 300 | 100 | Red | Equipment dispatch completed; installation team mobilized | 8 | Ananya Joshi
LOG-000645 | PRJ-2024024 | 2025-12-11 | 15 | 5 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Ananya Joshi
LOG-000646 | PRJ-2024024 | 2025-12-18 | 27 | 9 | Red | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-000647 | PRJ-2024024 | 2025-12-25 | 36 | 12 | Red | Weekly governance call held with client stakeholders | 2 | Ananya Joshi
LOG-000648 | PRJ-2024024 | 2026-01-01 | 51 | 17 | Green | Equipment dispatch completed; installation team mobilized | 3 | Ananya Joshi
LOG-000649 | PRJ-2024024 | 2026-01-08 | 54 | 18 | Green | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-000650 | PRJ-2024024 | 2026-01-15 | 63 | 21 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Ananya Joshi
LOG-000651 | PRJ-2024024 | 2026-01-22 | 75 | 25 | Red | Equipment dispatch completed; installation team mobilized | 0 | Ananya Joshi
LOG-000652 | PRJ-2024024 | 2026-01-29 | 93 | 31 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Ananya Joshi
LOG-000653 | PRJ-2024024 | 2026-02-05 | 111 | 37 | Amber | Client UAT sign-off received for batch of completed sites | 8 | Ananya Joshi
LOG-000654 | PRJ-2024024 | 2026-02-12 | 117 | 39 | Green | Survey activities progressing as per plan across allocated sites | 3 | Ananya Joshi
LOG-000655 | PRJ-2024024 | 2026-02-19 | 120 | 40 | Amber | Survey activities progressing as per plan across allocated sites | 3 | Ananya Joshi
LOG-000656 | PRJ-2024024 | 2026-02-26 | 123 | 41 | Amber | Client UAT sign-off received for batch of completed sites | 0 | Ananya Joshi
LOG-000657 | PRJ-2024024 | 2026-03-05 | 132 | 44 | Green | Equipment dispatch completed; installation team mobilized | 0 | Ananya Joshi
LOG-000658 | PRJ-2024024 | 2026-03-12 | 138 | 46 | Red | Weekly governance call held with client stakeholders | 8 | Ananya Joshi
LOG-000659 | PRJ-2024024 | 2026-03-19 | 144 | 48 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Ananya Joshi
LOG-000660 | PRJ-2024024 | 2026-03-26 | 162 | 54 | Green | Resource constraint flagged; additional field engineer requested | 1 | Ananya Joshi
LOG-000661 | PRJ-2024024 | 2026-04-02 | 177 | 59 | Green | Survey activities progressing as per plan across allocated sites | 6 | Ananya Joshi
LOG-000662 | PRJ-2024024 | 2026-04-09 | 189 | 63 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Ananya Joshi
LOG-000663 | PRJ-2024024 | 2026-04-16 | 195 | 65 | Green | Client UAT sign-off received for batch of completed sites | 2 | Ananya Joshi
LOG-000664 | PRJ-2024024 | 2026-04-23 | 210 | 70 | Green | Resource constraint flagged; additional field engineer requested | 1 | Ananya Joshi
LOG-000665 | PRJ-2024024 | 2026-04-30 | 225 | 75 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Ananya Joshi
LOG-000666 | PRJ-2024024 | 2026-05-07 | 243 | 81 | Red | Weekly governance call held with client stakeholders | 5 | Ananya Joshi
LOG-000667 | PRJ-2024024 | 2026-05-14 | 249 | 83 | Green | Survey activities progressing as per plan across allocated sites | 5 | Ananya Joshi
LOG-000668 | PRJ-2024024 | 2026-05-21 | 258 | 86 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Ananya Joshi
LOG-000669 | PRJ-2024024 | 2026-05-28 | 273 | 91 | Green | Equipment dispatch completed; installation team mobilized | 7 | Ananya Joshi
LOG-000670 | PRJ-2024024 | 2026-06-04 | 279 | 93 | Green | Resource constraint flagged; additional field engineer requested | 1 | Ananya Joshi
LOG-000671 | PRJ-2024024 | 2026-06-11 | 288 | 96 | Red | Resource constraint flagged; additional field engineer requested | 1 | Ananya Joshi
LOG-000672 | PRJ-2024024 | 2026-06-18 | 291 | 97 | Amber | Resource constraint flagged; additional field engineer requested | 6 | Ananya Joshi
LOG-000673 | PRJ-2024025 | 2025-04-01 | 0 | 1 | Red | Client UAT sign-off received for batch of completed sites | 2 | Deepa Nair
LOG-000674 | PRJ-2024025 | 2025-04-08 | 0 | 3 | Amber | Equipment dispatch completed; installation team mobilized | 0 | Deepa Nair
LOG-000675 | PRJ-2024025 | 2025-04-15 | 0 | 6 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Deepa Nair
LOG-000676 | PRJ-2024025 | 2025-04-22 | 1 | 10 | Green | Resource constraint flagged; additional field engineer requested | 2 | Deepa Nair
LOG-000677 | PRJ-2024025 | 2025-04-29 | 1 | 13 | Amber | Vendor escalation raised for delayed circuit provisioning | 2 | Deepa Nair
LOG-000678 | PRJ-2024025 | 2025-05-06 | 2 | 15 | Green | Survey activities progressing as per plan across allocated sites | 8 | Deepa Nair
LOG-000679 | PRJ-2024025 | 2025-05-13 | 3 | 21 | Green | Resource constraint flagged; additional field engineer requested | 6 | Deepa Nair
LOG-000680 | PRJ-2024025 | 2025-05-20 | 4 | 27 | Green | Resource constraint flagged; additional field engineer requested | 3 | Deepa Nair
LOG-000681 | PRJ-2024025 | 2025-05-27 | 4 | 30 | Green | Client UAT sign-off received for batch of completed sites | 2 | Deepa Nair
LOG-000682 | PRJ-2024025 | 2025-06-03 | 4 | 31 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Deepa Nair
LOG-000683 | PRJ-2024025 | 2025-06-10 | 4 | 32 | Green | Equipment dispatch completed; installation team mobilized | 7 | Deepa Nair
LOG-000684 | PRJ-2024025 | 2025-06-17 | 5 | 37 | Red | Client UAT sign-off received for batch of completed sites | 0 | Deepa Nair
LOG-000685 | PRJ-2024025 | 2025-06-24 | 6 | 41 | Green | Weekly governance call held with client stakeholders | 8 | Deepa Nair
LOG-000686 | PRJ-2024025 | 2025-07-01 | 6 | 42 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Deepa Nair
LOG-000687 | PRJ-2024025 | 2025-07-08 | 7 | 48 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000688 | PRJ-2024025 | 2025-07-15 | 7 | 53 | Amber | Client UAT sign-off received for batch of completed sites | 5 | Deepa Nair
LOG-000689 | PRJ-2024025 | 2025-07-22 | 8 | 54 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000690 | PRJ-2024025 | 2025-07-29 | 8 | 59 | Green | Resource constraint flagged; additional field engineer requested | 6 | Deepa Nair
LOG-000691 | PRJ-2024025 | 2025-08-05 | 9 | 64 | Green | Survey activities progressing as per plan across allocated sites | 4 | Deepa Nair
LOG-000692 | PRJ-2024025 | 2025-08-12 | 9 | 65 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Deepa Nair
LOG-000693 | PRJ-2024025 | 2025-08-19 | 10 | 67 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Deepa Nair
LOG-000694 | PRJ-2024025 | 2025-08-26 | 10 | 68 | Green | Resource constraint flagged; additional field engineer requested | 3 | Deepa Nair
LOG-000695 | PRJ-2024025 | 2025-09-02 | 10 | 73 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Deepa Nair
LOG-000696 | PRJ-2024025 | 2025-09-09 | 11 | 78 | Green | Survey activities progressing as per plan across allocated sites | 0 | Deepa Nair
LOG-000697 | PRJ-2024025 | 2025-09-16 | 12 | 81 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000698 | PRJ-2024025 | 2025-09-23 | 12 | 82 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Deepa Nair
LOG-000699 | PRJ-2024025 | 2025-09-30 | 13 | 88 | Green | Client UAT sign-off received for batch of completed sites | 4 | Deepa Nair
LOG-000700 | PRJ-2024025 | 2025-10-07 | 13 | 93 | Green | Weekly governance call held with client stakeholders | 7 | Deepa Nair
LOG-000701 | PRJ-2024026 | 2025-01-04 | 1 | 5 | Red | Weekly governance call held with client stakeholders | 8 | Deepa Nair
LOG-000702 | PRJ-2024026 | 2025-01-11 | 3 | 10 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Deepa Nair
LOG-000703 | PRJ-2024026 | 2025-01-18 | 3 | 12 | Green | Client UAT sign-off received for batch of completed sites | 3 | Deepa Nair
LOG-000704 | PRJ-2024026 | 2025-01-25 | 5 | 17 | Green | Equipment dispatch completed; installation team mobilized | 2 | Deepa Nair
LOG-000705 | PRJ-2024026 | 2025-02-01 | 5 | 19 | Red | Resource constraint flagged; additional field engineer requested | 3 | Deepa Nair
LOG-000706 | PRJ-2024026 | 2025-02-08 | 6 | 21 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Deepa Nair
LOG-000707 | PRJ-2024026 | 2025-02-15 | 8 | 27 | Green | Resource constraint flagged; additional field engineer requested | 5 | Deepa Nair
LOG-000708 | PRJ-2024026 | 2025-02-22 | 9 | 30 | Green | Survey activities progressing as per plan across allocated sites | 4 | Deepa Nair
LOG-000709 | PRJ-2024026 | 2025-03-01 | 10 | 35 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Deepa Nair
LOG-000710 | PRJ-2024026 | 2025-03-08 | 11 | 39 | Green | Equipment dispatch completed; installation team mobilized | 3 | Deepa Nair
LOG-000711 | PRJ-2024026 | 2025-03-15 | 13 | 45 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Deepa Nair
LOG-000712 | PRJ-2024026 | 2025-03-22 | 14 | 49 | Green | Equipment dispatch completed; installation team mobilized | 4 | Deepa Nair
LOG-000713 | PRJ-2024026 | 2025-03-29 | 15 | 53 | Red | Survey activities progressing as per plan across allocated sites | 0 | Deepa Nair
LOG-000714 | PRJ-2024026 | 2025-04-05 | 17 | 57 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Deepa Nair
LOG-000715 | PRJ-2024026 | 2025-04-12 | 18 | 61 | Green | Client UAT sign-off received for batch of completed sites | 6 | Deepa Nair
LOG-000716 | PRJ-2024026 | 2025-04-19 | 19 | 66 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Deepa Nair
LOG-000717 | PRJ-2024026 | 2025-04-26 | 20 | 69 | Green | Weekly governance call held with client stakeholders | 5 | Deepa Nair
LOG-000718 | PRJ-2024026 | 2025-05-03 | 22 | 75 | Green | Equipment dispatch completed; installation team mobilized | 5 | Deepa Nair
LOG-000719 | PRJ-2024026 | 2025-05-10 | 24 | 80 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Deepa Nair
LOG-000720 | PRJ-2024026 | 2025-05-17 | 24 | 83 | Green | Survey activities progressing as per plan across allocated sites | 7 | Deepa Nair
LOG-000721 | PRJ-2024026 | 2025-05-24 | 26 | 89 | Amber | Survey activities progressing as per plan across allocated sites | 0 | Deepa Nair
LOG-000722 | PRJ-2024026 | 2025-05-31 | 28 | 95 | Green | Survey activities progressing as per plan across allocated sites | 7 | Deepa Nair
LOG-000723 | PRJ-2024026 | 2025-06-07 | 29 | 97 | Green | Weekly governance call held with client stakeholders | 1 | Deepa Nair
LOG-000724 | PRJ-2024026 | 2025-06-14 | 29 | 99 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Deepa Nair
LOG-000725 | PRJ-2024026 | 2025-06-21 | 30 | 100 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Deepa Nair
LOG-000726 | PRJ-2024026 | 2025-06-28 | 30 | 100 | Green | Resource constraint flagged; additional field engineer requested | 5 | Deepa Nair
LOG-000727 | PRJ-2024026 | 2025-07-05 | 30 | 100 | Amber | Vendor escalation raised for delayed circuit provisioning | 6 | Deepa Nair
LOG-000728 | PRJ-2024026 | 2025-07-12 | 30 | 100 | Green | Survey activities progressing as per plan across allocated sites | 0 | Deepa Nair
LOG-000729 | PRJ-2024027 | 2025-06-14 | 1 | 1 | Green | Client UAT sign-off received for batch of completed sites | 0 | Deepa Nair
LOG-000730 | PRJ-2024027 | 2025-06-21 | 2 | 2 | Red | Weekly governance call held with client stakeholders | 3 | Deepa Nair
LOG-000731 | PRJ-2024027 | 2025-06-28 | 4 | 4 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Deepa Nair
LOG-000732 | PRJ-2024027 | 2025-07-05 | 8 | 8 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000733 | PRJ-2024027 | 2025-07-12 | 9 | 9 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Deepa Nair
LOG-000734 | PRJ-2024027 | 2025-07-19 | 13 | 13 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000735 | PRJ-2024027 | 2025-07-26 | 17 | 17 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Deepa Nair
LOG-000736 | PRJ-2024027 | 2025-08-02 | 21 | 21 | Green | Equipment dispatch completed; installation team mobilized | 0 | Deepa Nair
LOG-000737 | PRJ-2024027 | 2025-08-09 | 26 | 26 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Deepa Nair
LOG-000738 | PRJ-2024027 | 2025-08-16 | 27 | 27 | Green | Client UAT sign-off received for batch of completed sites | 1 | Deepa Nair
LOG-000739 | PRJ-2024027 | 2025-08-23 | 33 | 33 | Amber | Survey activities progressing as per plan across allocated sites | 4 | Deepa Nair
LOG-000740 | PRJ-2024027 | 2025-08-30 | 36 | 36 | Amber | Weekly governance call held with client stakeholders | 4 | Deepa Nair
LOG-000741 | PRJ-2024027 | 2025-09-06 | 37 | 37 | Green | Resource constraint flagged; additional field engineer requested | 1 | Deepa Nair
LOG-000742 | PRJ-2024027 | 2025-09-13 | 42 | 42 | Red | Equipment dispatch completed; installation team mobilized | 0 | Deepa Nair
LOG-000743 | PRJ-2024027 | 2025-09-20 | 47 | 47 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Deepa Nair
LOG-000744 | PRJ-2024027 | 2025-09-27 | 48 | 48 | Green | Client UAT sign-off received for batch of completed sites | 7 | Deepa Nair
LOG-000745 | PRJ-2024027 | 2025-10-04 | 50 | 50 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Deepa Nair
LOG-000746 | PRJ-2024027 | 2025-10-11 | 52 | 52 | Green | Vendor escalation raised for delayed circuit provisioning | 5 | Deepa Nair
LOG-000747 | PRJ-2024027 | 2025-10-18 | 53 | 53 | Amber | Resource constraint flagged; additional field engineer requested | 6 | Deepa Nair
LOG-000748 | PRJ-2024027 | 2025-10-25 | 55 | 55 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Deepa Nair
LOG-000749 | PRJ-2024027 | 2025-11-01 | 56 | 56 | Green | Weekly governance call held with client stakeholders | 0 | Deepa Nair
LOG-000750 | PRJ-2024027 | 2025-11-08 | 58 | 58 | Green | Resource constraint flagged; additional field engineer requested | 8 | Deepa Nair
LOG-000751 | PRJ-2024027 | 2025-11-15 | 62 | 62 | Amber | Survey activities progressing as per plan across allocated sites | 0 | Deepa Nair
LOG-000752 | PRJ-2024027 | 2025-11-22 | 66 | 66 | Amber | Equipment dispatch completed; installation team mobilized | 6 | Deepa Nair
LOG-000753 | PRJ-2024027 | 2025-11-29 | 67 | 67 | Green | Equipment dispatch completed; installation team mobilized | 2 | Deepa Nair
LOG-000754 | PRJ-2024027 | 2025-12-06 | 69 | 69 | Green | Client UAT sign-off received for batch of completed sites | 7 | Deepa Nair
LOG-000755 | PRJ-2024027 | 2025-12-13 | 73 | 73 | Green | Survey activities progressing as per plan across allocated sites | 4 | Deepa Nair
LOG-000756 | PRJ-2024027 | 2025-12-20 | 78 | 78 | Green | Equipment dispatch completed; installation team mobilized | 7 | Deepa Nair
LOG-000757 | PRJ-2024028 | 2025-11-24 | 0 | 1 | Amber | Equipment dispatch completed; installation team mobilized | 3 | Karthik Subramanian
LOG-000758 | PRJ-2024028 | 2025-12-01 | 2 | 3 | Green | Weekly governance call held with client stakeholders | 7 | Karthik Subramanian
LOG-000759 | PRJ-2024028 | 2025-12-08 | 6 | 9 | Red | Vendor escalation raised for delayed circuit provisioning | 7 | Karthik Subramanian
LOG-000760 | PRJ-2024028 | 2025-12-15 | 11 | 15 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Karthik Subramanian
LOG-000761 | PRJ-2024028 | 2025-12-22 | 12 | 16 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Karthik Subramanian
LOG-000762 | PRJ-2024028 | 2025-12-29 | 15 | 21 | Red | Weekly governance call held with client stakeholders | 8 | Karthik Subramanian
LOG-000763 | PRJ-2024028 | 2026-01-05 | 19 | 26 | Green | Client UAT sign-off received for batch of completed sites | 8 | Karthik Subramanian
LOG-000764 | PRJ-2024028 | 2026-01-12 | 21 | 28 | Green | Client UAT sign-off received for batch of completed sites | 1 | Karthik Subramanian
LOG-000765 | PRJ-2024028 | 2026-01-19 | 23 | 31 | Green | Survey activities progressing as per plan across allocated sites | 1 | Karthik Subramanian
LOG-000766 | PRJ-2024028 | 2026-01-26 | 25 | 34 | Green | Weekly governance call held with client stakeholders | 4 | Karthik Subramanian
LOG-000767 | PRJ-2024028 | 2026-02-02 | 26 | 35 | Green | Equipment dispatch completed; installation team mobilized | 8 | Karthik Subramanian
LOG-000768 | PRJ-2024028 | 2026-02-09 | 28 | 38 | Green | Equipment dispatch completed; installation team mobilized | 6 | Karthik Subramanian
LOG-000769 | PRJ-2024028 | 2026-02-16 | 31 | 42 | Green | Survey activities progressing as per plan across allocated sites | 3 | Karthik Subramanian
LOG-000770 | PRJ-2024028 | 2026-02-23 | 34 | 46 | Green | Weekly governance call held with client stakeholders | 7 | Karthik Subramanian
LOG-000771 | PRJ-2024028 | 2026-03-02 | 39 | 52 | Green | Survey activities progressing as per plan across allocated sites | 0 | Karthik Subramanian
LOG-000772 | PRJ-2024028 | 2026-03-09 | 43 | 58 | Amber | Client UAT sign-off received for batch of completed sites | 5 | Karthik Subramanian
LOG-000773 | PRJ-2024028 | 2026-03-16 | 45 | 61 | Green | Weekly governance call held with client stakeholders | 0 | Karthik Subramanian
LOG-000774 | PRJ-2024028 | 2026-03-23 | 49 | 66 | Green | Client UAT sign-off received for batch of completed sites | 0 | Karthik Subramanian
LOG-000775 | PRJ-2024028 | 2026-03-30 | 51 | 68 | Green | Survey activities progressing as per plan across allocated sites | 1 | Karthik Subramanian
LOG-000776 | PRJ-2024028 | 2026-04-06 | 55 | 74 | Green | Client UAT sign-off received for batch of completed sites | 6 | Karthik Subramanian
LOG-000777 | PRJ-2024028 | 2026-04-13 | 56 | 75 | Amber | Survey activities progressing as per plan across allocated sites | 6 | Karthik Subramanian
LOG-000778 | PRJ-2024028 | 2026-04-20 | 57 | 76 | Green | Weekly governance call held with client stakeholders | 0 | Karthik Subramanian
LOG-000779 | PRJ-2024028 | 2026-04-27 | 57 | 77 | Green | Weekly governance call held with client stakeholders | 2 | Karthik Subramanian
LOG-000780 | PRJ-2024028 | 2026-05-04 | 60 | 81 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Karthik Subramanian
LOG-000781 | PRJ-2024028 | 2026-05-11 | 61 | 82 | Red | Weekly governance call held with client stakeholders | 1 | Karthik Subramanian
LOG-000782 | PRJ-2024028 | 2026-05-18 | 64 | 86 | Green | Survey activities progressing as per plan across allocated sites | 3 | Karthik Subramanian
LOG-000783 | PRJ-2024028 | 2026-05-25 | 66 | 89 | Amber | Vendor escalation raised for delayed circuit provisioning | 6 | Karthik Subramanian
LOG-000784 | PRJ-2024028 | 2026-06-01 | 69 | 92 | Amber | Equipment dispatch completed; installation team mobilized | 0 | Karthik Subramanian
LOG-000785 | PRJ-2024029 | 2025-11-03 | 0 | 1 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Deepa Nair
LOG-000786 | PRJ-2024029 | 2025-11-10 | 3 | 7 | Green | Equipment dispatch completed; installation team mobilized | 2 | Deepa Nair
LOG-000787 | PRJ-2024029 | 2025-11-17 | 5 | 11 | Green | Weekly governance call held with client stakeholders | 7 | Deepa Nair
LOG-000788 | PRJ-2024029 | 2025-11-24 | 8 | 16 | Green | Resource constraint flagged; additional field engineer requested | 4 | Deepa Nair
LOG-000789 | PRJ-2024029 | 2025-12-01 | 8 | 17 | Green | Client UAT sign-off received for batch of completed sites | 4 | Deepa Nair
LOG-000790 | PRJ-2024029 | 2025-12-08 | 9 | 19 | Green | Resource constraint flagged; additional field engineer requested | 2 | Deepa Nair
LOG-000791 | PRJ-2024029 | 2025-12-15 | 11 | 22 | Green | Resource constraint flagged; additional field engineer requested | 1 | Deepa Nair
LOG-000792 | PRJ-2024029 | 2025-12-22 | 12 | 25 | Amber | Equipment dispatch completed; installation team mobilized | 4 | Deepa Nair
LOG-000793 | PRJ-2024029 | 2025-12-29 | 15 | 31 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Deepa Nair
LOG-000794 | PRJ-2024029 | 2026-01-05 | 17 | 34 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Deepa Nair
LOG-000795 | PRJ-2024029 | 2026-01-12 | 18 | 36 | Green | Weekly governance call held with client stakeholders | 6 | Deepa Nair
LOG-000796 | PRJ-2024029 | 2026-01-19 | 19 | 39 | Green | Weekly governance call held with client stakeholders | 1 | Deepa Nair
LOG-000797 | PRJ-2024029 | 2026-01-26 | 20 | 40 | Amber | Vendor escalation raised for delayed circuit provisioning | 4 | Deepa Nair
LOG-000798 | PRJ-2024029 | 2026-02-02 | 22 | 44 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Deepa Nair
LOG-000799 | PRJ-2024029 | 2026-02-09 | 24 | 49 | Green | Survey activities progressing as per plan across allocated sites | 5 | Deepa Nair
LOG-000800 | PRJ-2024029 | 2026-02-16 | 27 | 54 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Deepa Nair
LOG-000801 | PRJ-2024029 | 2026-02-23 | 30 | 60 | Amber | Client UAT sign-off received for batch of completed sites | 5 | Deepa Nair
LOG-000802 | PRJ-2024029 | 2026-03-02 | 31 | 62 | Green | Resource constraint flagged; additional field engineer requested | 7 | Deepa Nair
LOG-000803 | PRJ-2024029 | 2026-03-09 | 32 | 65 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Deepa Nair
LOG-000804 | PRJ-2024029 | 2026-03-16 | 33 | 67 | Green | Survey activities progressing as per plan across allocated sites | 6 | Deepa Nair
LOG-000805 | PRJ-2024029 | 2026-03-23 | 35 | 70 | Red | Resource constraint flagged; additional field engineer requested | 5 | Deepa Nair
LOG-000806 | PRJ-2024029 | 2026-03-30 | 35 | 71 | Amber | Survey activities progressing as per plan across allocated sites | 5 | Deepa Nair
LOG-000807 | PRJ-2024029 | 2026-04-06 | 38 | 77 | Green | Survey activities progressing as per plan across allocated sites | 1 | Deepa Nair
LOG-000808 | PRJ-2024029 | 2026-04-13 | 41 | 83 | Green | Client UAT sign-off received for batch of completed sites | 1 | Deepa Nair
LOG-000809 | PRJ-2024029 | 2026-04-20 | 42 | 85 | Green | Weekly governance call held with client stakeholders | 6 | Deepa Nair
LOG-000810 | PRJ-2024029 | 2026-04-27 | 45 | 91 | Green | Weekly governance call held with client stakeholders | 1 | Deepa Nair
LOG-000811 | PRJ-2024029 | 2026-05-04 | 48 | 97 | Green | Client UAT sign-off received for batch of completed sites | 8 | Deepa Nair
LOG-000812 | PRJ-2024029 | 2026-05-11 | 50 | 100 | Green | Weekly governance call held with client stakeholders | 7 | Deepa Nair
LOG-000813 | PRJ-2024030 | 2025-08-14 | 3 | 5 | Amber | Vendor escalation raised for delayed circuit provisioning | 5 | Manish Agarwal
LOG-000814 | PRJ-2024030 | 2025-08-21 | 6 | 9 | Amber | Survey activities progressing as per plan across allocated sites | 1 | Manish Agarwal
LOG-000815 | PRJ-2024030 | 2025-08-28 | 10 | 14 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Manish Agarwal
LOG-000816 | PRJ-2024030 | 2025-09-04 | 12 | 17 | Green | Weekly governance call held with client stakeholders | 5 | Manish Agarwal
LOG-000817 | PRJ-2024030 | 2025-09-11 | 17 | 23 | Green | Weekly governance call held with client stakeholders | 4 | Manish Agarwal
LOG-000818 | PRJ-2024030 | 2025-09-18 | 20 | 27 | Green | Resource constraint flagged; additional field engineer requested | 7 | Manish Agarwal
LOG-000819 | PRJ-2024030 | 2025-09-25 | 21 | 29 | Green | Equipment dispatch completed; installation team mobilized | 3 | Manish Agarwal
LOG-000820 | PRJ-2024030 | 2025-10-02 | 24 | 32 | Red | Client UAT sign-off received for batch of completed sites | 3 | Manish Agarwal
LOG-000821 | PRJ-2024030 | 2025-10-09 | 27 | 36 | Red | Client UAT sign-off received for batch of completed sites | 0 | Manish Agarwal
LOG-000822 | PRJ-2024030 | 2025-10-16 | 27 | 37 | Amber | Vendor escalation raised for delayed circuit provisioning | 5 | Manish Agarwal
LOG-000823 | PRJ-2024030 | 2025-10-23 | 29 | 39 | Green | Resource constraint flagged; additional field engineer requested | 3 | Manish Agarwal
LOG-000824 | PRJ-2024030 | 2025-10-30 | 30 | 40 | Amber | Resource constraint flagged; additional field engineer requested | 5 | Manish Agarwal
LOG-000825 | PRJ-2024030 | 2025-11-06 | 30 | 41 | Green | Survey activities progressing as per plan across allocated sites | 3 | Manish Agarwal
LOG-000826 | PRJ-2024030 | 2025-11-13 | 33 | 45 | Green | Survey activities progressing as per plan across allocated sites | 1 | Manish Agarwal
LOG-000827 | PRJ-2024030 | 2025-11-20 | 37 | 50 | Green | Vendor escalation raised for delayed circuit provisioning | 6 | Manish Agarwal
LOG-000828 | PRJ-2024030 | 2025-11-27 | 41 | 55 | Red | Weekly governance call held with client stakeholders | 7 | Manish Agarwal
LOG-000829 | PRJ-2024030 | 2025-12-04 | 43 | 58 | Green | Weekly governance call held with client stakeholders | 5 | Manish Agarwal
LOG-000830 | PRJ-2024030 | 2025-12-11 | 45 | 60 | Red | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000831 | PRJ-2024030 | 2025-12-18 | 49 | 66 | Green | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000832 | PRJ-2024030 | 2025-12-25 | 52 | 70 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 8 | Manish Agarwal
LOG-000833 | PRJ-2024030 | 2026-01-01 | 53 | 71 | Red | Equipment dispatch completed; installation team mobilized | 7 | Manish Agarwal
LOG-000834 | PRJ-2024030 | 2026-01-08 | 57 | 77 | Green | Client UAT sign-off received for batch of completed sites | 6 | Manish Agarwal
LOG-000835 | PRJ-2024030 | 2026-01-15 | 61 | 82 | Green | Client UAT sign-off received for batch of completed sites | 3 | Manish Agarwal
LOG-000836 | PRJ-2024030 | 2026-01-22 | 66 | 88 | Red | Vendor escalation raised for delayed circuit provisioning | 2 | Manish Agarwal
LOG-000837 | PRJ-2024030 | 2026-01-29 | 68 | 91 | Green | Client UAT sign-off received for batch of completed sites | 1 | Manish Agarwal
LOG-000838 | PRJ-2024030 | 2026-02-05 | 69 | 92 | Red | Equipment dispatch completed; installation team mobilized | 4 | Manish Agarwal
LOG-000839 | PRJ-2024030 | 2026-02-12 | 69 | 93 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Manish Agarwal
LOG-000840 | PRJ-2024030 | 2026-02-19 | 73 | 98 | Red | Survey activities progressing as per plan across allocated sites | 8 | Manish Agarwal
LOG-000841 | PRJ-2024031 | 2025-09-08 | 2 | 5 | Green | Client UAT sign-off received for batch of completed sites | 8 | Farah Khan
LOG-000842 | PRJ-2024031 | 2025-09-15 | 2 | 7 | Green | Resource constraint flagged; additional field engineer requested | 1 | Farah Khan
LOG-000843 | PRJ-2024031 | 2025-09-22 | 3 | 9 | Green | Client UAT sign-off received for batch of completed sites | 5 | Farah Khan
LOG-000844 | PRJ-2024031 | 2025-09-29 | 5 | 14 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Farah Khan
LOG-000845 | PRJ-2024031 | 2025-10-06 | 6 | 16 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Farah Khan
LOG-000846 | PRJ-2024031 | 2025-10-13 | 7 | 18 | Green | Client UAT sign-off received for batch of completed sites | 7 | Farah Khan
LOG-000847 | PRJ-2024031 | 2025-10-20 | 8 | 22 | Green | Equipment dispatch completed; installation team mobilized | 0 | Farah Khan
LOG-000848 | PRJ-2024031 | 2025-10-27 | 11 | 28 | Green | Vendor escalation raised for delayed circuit provisioning | 5 | Farah Khan
LOG-000849 | PRJ-2024031 | 2025-11-03 | 12 | 32 | Green | Client UAT sign-off received for batch of completed sites | 2 | Farah Khan
LOG-000850 | PRJ-2024031 | 2025-11-10 | 15 | 38 | Amber | Weekly governance call held with client stakeholders | 1 | Farah Khan
LOG-000851 | PRJ-2024031 | 2025-11-17 | 16 | 41 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Farah Khan
LOG-000852 | PRJ-2024031 | 2025-11-24 | 17 | 43 | Amber | Weekly governance call held with client stakeholders | 7 | Farah Khan
LOG-000853 | PRJ-2024031 | 2025-12-01 | 18 | 45 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Farah Khan
LOG-000854 | PRJ-2024031 | 2025-12-08 | 20 | 51 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Farah Khan
LOG-000855 | PRJ-2024031 | 2025-12-15 | 21 | 54 | Green | Resource constraint flagged; additional field engineer requested | 1 | Farah Khan
LOG-000856 | PRJ-2024031 | 2025-12-22 | 24 | 60 | Green | Weekly governance call held with client stakeholders | 2 | Farah Khan
LOG-000857 | PRJ-2024031 | 2025-12-29 | 24 | 61 | Red | Equipment dispatch completed; installation team mobilized | 2 | Farah Khan
LOG-000858 | PRJ-2024031 | 2026-01-05 | 24 | 62 | Amber | Vendor escalation raised for delayed circuit provisioning | 3 | Farah Khan
LOG-000859 | PRJ-2024031 | 2026-01-12 | 26 | 66 | Green | Survey activities progressing as per plan across allocated sites | 5 | Farah Khan
LOG-000860 | PRJ-2024031 | 2026-01-19 | 28 | 72 | Red | Client UAT sign-off received for batch of completed sites | 1 | Farah Khan
LOG-000861 | PRJ-2024031 | 2026-01-26 | 30 | 77 | Red | Equipment dispatch completed; installation team mobilized | 2 | Farah Khan
LOG-000862 | PRJ-2024031 | 2026-02-02 | 32 | 80 | Green | Resource constraint flagged; additional field engineer requested | 5 | Farah Khan
LOG-000863 | PRJ-2024031 | 2026-02-09 | 34 | 85 | Green | Weekly governance call held with client stakeholders | 5 | Farah Khan
LOG-000864 | PRJ-2024031 | 2026-02-16 | 34 | 87 | Green | Resource constraint flagged; additional field engineer requested | 5 | Farah Khan
LOG-000865 | PRJ-2024031 | 2026-02-23 | 36 | 90 | Red | Client UAT sign-off received for batch of completed sites | 7 | Farah Khan
LOG-000866 | PRJ-2024031 | 2026-03-02 | 38 | 95 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Farah Khan
LOG-000867 | PRJ-2024031 | 2026-03-09 | 39 | 98 | Green | Client UAT sign-off received for batch of completed sites | 3 | Farah Khan
LOG-000868 | PRJ-2024031 | 2026-03-16 | 40 | 100 | Red | Equipment dispatch completed; installation team mobilized | 7 | Farah Khan
LOG-000869 | PRJ-2024032 | 2025-08-09 | 0 | 2 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Karthik Subramanian
LOG-000870 | PRJ-2024032 | 2025-08-16 | 0 | 6 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Karthik Subramanian
LOG-000871 | PRJ-2024032 | 2025-08-23 | 1 | 7 | Green | Equipment dispatch completed; installation team mobilized | 1 | Karthik Subramanian
LOG-000872 | PRJ-2024032 | 2025-08-30 | 1 | 8 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Karthik Subramanian
LOG-000873 | PRJ-2024032 | 2025-09-06 | 1 | 9 | Green | Survey activities progressing as per plan across allocated sites | 7 | Karthik Subramanian
LOG-000874 | PRJ-2024032 | 2025-09-13 | 1 | 12 | Green | Equipment dispatch completed; installation team mobilized | 0 | Karthik Subramanian
LOG-000875 | PRJ-2024032 | 2025-09-20 | 2 | 14 | Green | Client UAT sign-off received for batch of completed sites | 4 | Karthik Subramanian
LOG-000876 | PRJ-2024032 | 2025-09-27 | 2 | 19 | Green | Weekly governance call held with client stakeholders | 1 | Karthik Subramanian
LOG-000877 | PRJ-2024032 | 2025-10-04 | 3 | 21 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Karthik Subramanian
LOG-000878 | PRJ-2024032 | 2025-10-11 | 3 | 23 | Green | Resource constraint flagged; additional field engineer requested | 2 | Karthik Subramanian
LOG-000879 | PRJ-2024032 | 2025-10-18 | 3 | 24 | Red | Client UAT sign-off received for batch of completed sites | 3 | Karthik Subramanian
LOG-000880 | PRJ-2024032 | 2025-10-25 | 4 | 29 | Green | Weekly governance call held with client stakeholders | 7 | Karthik Subramanian
LOG-000881 | PRJ-2024032 | 2025-11-01 | 4 | 30 | Red | Equipment dispatch completed; installation team mobilized | 3 | Karthik Subramanian
LOG-000882 | PRJ-2024032 | 2025-11-08 | 5 | 35 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Karthik Subramanian
LOG-000883 | PRJ-2024032 | 2025-11-15 | 5 | 36 | Red | Equipment dispatch completed; installation team mobilized | 8 | Karthik Subramanian
LOG-000884 | PRJ-2024032 | 2025-11-22 | 6 | 40 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Karthik Subramanian
LOG-000885 | PRJ-2024032 | 2025-11-29 | 6 | 45 | Green | Survey activities progressing as per plan across allocated sites | 3 | Karthik Subramanian
LOG-000886 | PRJ-2024032 | 2025-12-06 | 6 | 46 | Amber | Resource constraint flagged; additional field engineer requested | 8 | Karthik Subramanian
LOG-000887 | PRJ-2024032 | 2025-12-13 | 7 | 48 | Green | Client UAT sign-off received for batch of completed sites | 0 | Karthik Subramanian
LOG-000888 | PRJ-2024032 | 2025-12-20 | 7 | 53 | Green | Vendor escalation raised for delayed circuit provisioning | 3 | Karthik Subramanian
LOG-000889 | PRJ-2024032 | 2025-12-27 | 8 | 57 | Green | Equipment dispatch completed; installation team mobilized | 1 | Karthik Subramanian
LOG-000890 | PRJ-2024032 | 2026-01-03 | 9 | 62 | Green | Survey activities progressing as per plan across allocated sites | 7 | Karthik Subramanian
LOG-000891 | PRJ-2024032 | 2026-01-10 | 10 | 67 | Green | Equipment dispatch completed; installation team mobilized | 8 | Karthik Subramanian
LOG-000892 | PRJ-2024032 | 2026-01-17 | 10 | 72 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Karthik Subramanian
LOG-000893 | PRJ-2024032 | 2026-01-24 | 11 | 74 | Amber | Weekly governance call held with client stakeholders | 4 | Karthik Subramanian
LOG-000894 | PRJ-2024032 | 2026-01-31 | 12 | 80 | Amber | Weekly governance call held with client stakeholders | 3 | Karthik Subramanian
LOG-000895 | PRJ-2024032 | 2026-02-07 | 12 | 85 | Green | Survey activities progressing as per plan across allocated sites | 3 | Karthik Subramanian
LOG-000896 | PRJ-2024032 | 2026-02-14 | 13 | 87 | Amber | Survey activities progressing as per plan across allocated sites | 4 | Karthik Subramanian
LOG-000897 | PRJ-2024033 | 2025-06-18 | 0 | 5 | Green | Client UAT sign-off received for batch of completed sites | 2 | Ananya Joshi
LOG-000898 | PRJ-2024033 | 2025-06-25 | 0 | 8 | Green | Equipment dispatch completed; installation team mobilized | 4 | Ananya Joshi
LOG-000899 | PRJ-2024033 | 2025-07-02 | 0 | 9 | Amber | Resource constraint flagged; additional field engineer requested | 7 | Ananya Joshi
LOG-000900 | PRJ-2024033 | 2025-07-09 | 1 | 10 | Green | Equipment dispatch completed; installation team mobilized | 3 | Ananya Joshi
LOG-000901 | PRJ-2024033 | 2025-07-16 | 1 | 13 | Green | Weekly governance call held with client stakeholders | 8 | Ananya Joshi
LOG-000902 | PRJ-2024033 | 2025-07-23 | 1 | 18 | Green | Resource constraint flagged; additional field engineer requested | 3 | Ananya Joshi
LOG-000903 | PRJ-2024033 | 2025-07-30 | 2 | 21 | Red | Weekly governance call held with client stakeholders | 1 | Ananya Joshi
LOG-000904 | PRJ-2024033 | 2025-08-06 | 2 | 27 | Green | Resource constraint flagged; additional field engineer requested | 8 | Ananya Joshi
LOG-000905 | PRJ-2024033 | 2025-08-13 | 2 | 28 | Red | Resource constraint flagged; additional field engineer requested | 2 | Ananya Joshi
LOG-000906 | PRJ-2024033 | 2025-08-20 | 3 | 33 | Green | Vendor escalation raised for delayed circuit provisioning | 5 | Ananya Joshi
LOG-000907 | PRJ-2024033 | 2025-08-27 | 3 | 34 | Green | Weekly governance call held with client stakeholders | 8 | Ananya Joshi
LOG-000908 | PRJ-2024033 | 2025-09-03 | 3 | 37 | Amber | Client UAT sign-off received for batch of completed sites | 8 | Ananya Joshi
LOG-000909 | PRJ-2024033 | 2025-09-10 | 3 | 39 | Green | Vendor escalation raised for delayed circuit provisioning | 7 | Ananya Joshi
LOG-000910 | PRJ-2024033 | 2025-09-17 | 4 | 45 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 7 | Ananya Joshi
LOG-000911 | PRJ-2024033 | 2025-09-24 | 4 | 46 | Green | Client UAT sign-off received for batch of completed sites | 4 | Ananya Joshi
LOG-000912 | PRJ-2024033 | 2025-10-01 | 4 | 47 | Green | Resource constraint flagged; additional field engineer requested | 3 | Ananya Joshi
LOG-000913 | PRJ-2024033 | 2025-10-08 | 4 | 49 | Green | Client UAT sign-off received for batch of completed sites | 0 | Ananya Joshi
LOG-000914 | PRJ-2024033 | 2025-10-15 | 5 | 53 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-000915 | PRJ-2024033 | 2025-10-22 | 5 | 54 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 3 | Ananya Joshi
LOG-000916 | PRJ-2024033 | 2025-10-29 | 5 | 55 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Ananya Joshi
LOG-000917 | PRJ-2024033 | 2025-11-05 | 6 | 61 | Amber | Weekly governance call held with client stakeholders | 1 | Ananya Joshi
LOG-000918 | PRJ-2024033 | 2025-11-12 | 6 | 62 | Red | Equipment dispatch completed; installation team mobilized | 5 | Ananya Joshi
LOG-000919 | PRJ-2024033 | 2025-11-19 | 6 | 68 | Green | Survey activities progressing as per plan across allocated sites | 3 | Ananya Joshi
LOG-000920 | PRJ-2024033 | 2025-11-26 | 7 | 72 | Green | Weekly governance call held with client stakeholders | 1 | Ananya Joshi
LOG-000921 | PRJ-2024033 | 2025-12-03 | 7 | 74 | Green | Weekly governance call held with client stakeholders | 0 | Ananya Joshi
LOG-000922 | PRJ-2024033 | 2025-12-10 | 7 | 76 | Amber | Client UAT sign-off received for batch of completed sites | 1 | Ananya Joshi
LOG-000923 | PRJ-2024033 | 2025-12-17 | 8 | 80 | Green | Resource constraint flagged; additional field engineer requested | 3 | Ananya Joshi
LOG-000924 | PRJ-2024033 | 2025-12-24 | 8 | 84 | Red | Weekly governance call held with client stakeholders | 3 | Ananya Joshi
LOG-000925 | PRJ-2024034 | 2025-07-13 | 0 | 1 | Amber | Survey activities progressing as per plan across allocated sites | 8 | Manish Agarwal
LOG-000926 | PRJ-2024034 | 2025-07-20 | 4 | 6 | Green | Survey activities progressing as per plan across allocated sites | 0 | Manish Agarwal
LOG-000927 | PRJ-2024034 | 2025-07-27 | 6 | 9 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Manish Agarwal
LOG-000928 | PRJ-2024034 | 2025-08-03 | 7 | 10 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Manish Agarwal
LOG-000929 | PRJ-2024034 | 2025-08-10 | 10 | 14 | Green | Resource constraint flagged; additional field engineer requested | 4 | Manish Agarwal
LOG-000930 | PRJ-2024034 | 2025-08-17 | 13 | 18 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Manish Agarwal
LOG-000931 | PRJ-2024034 | 2025-08-24 | 16 | 22 | Red | Equipment dispatch completed; installation team mobilized | 7 | Manish Agarwal
LOG-000932 | PRJ-2024034 | 2025-08-31 | 18 | 24 | Green | Equipment dispatch completed; installation team mobilized | 5 | Manish Agarwal
LOG-000933 | PRJ-2024034 | 2025-09-07 | 18 | 25 | Amber | Equipment dispatch completed; installation team mobilized | 2 | Manish Agarwal
LOG-000934 | PRJ-2024034 | 2025-09-14 | 22 | 30 | Red | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000935 | PRJ-2024034 | 2025-09-21 | 27 | 36 | Green | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000936 | PRJ-2024034 | 2025-09-28 | 30 | 41 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Manish Agarwal
LOG-000937 | PRJ-2024034 | 2025-10-05 | 33 | 45 | Green | Weekly governance call held with client stakeholders | 0 | Manish Agarwal
LOG-000938 | PRJ-2024034 | 2025-10-12 | 37 | 50 | Green | Client UAT sign-off received for batch of completed sites | 8 | Manish Agarwal
LOG-000939 | PRJ-2024034 | 2025-10-19 | 42 | 56 | Red | Survey activities progressing as per plan across allocated sites | 3 | Manish Agarwal
LOG-000940 | PRJ-2024034 | 2025-10-26 | 44 | 59 | Green | Survey activities progressing as per plan across allocated sites | 8 | Manish Agarwal
LOG-000941 | PRJ-2024034 | 2025-11-02 | 45 | 60 | Red | Vendor escalation raised for delayed circuit provisioning | 6 | Manish Agarwal
LOG-000942 | PRJ-2024034 | 2025-11-09 | 48 | 65 | Green | Equipment dispatch completed; installation team mobilized | 5 | Manish Agarwal
LOG-000943 | PRJ-2024034 | 2025-11-16 | 51 | 69 | Green | Weekly governance call held with client stakeholders | 7 | Manish Agarwal
LOG-000944 | PRJ-2024034 | 2025-11-23 | 56 | 75 | Red | Resource constraint flagged; additional field engineer requested | 1 | Manish Agarwal
LOG-000945 | PRJ-2024034 | 2025-11-30 | 60 | 81 | Amber | Equipment dispatch completed; installation team mobilized | 4 | Manish Agarwal
LOG-000946 | PRJ-2024034 | 2025-12-07 | 62 | 83 | Green | Equipment dispatch completed; installation team mobilized | 4 | Manish Agarwal
LOG-000947 | PRJ-2024034 | 2025-12-14 | 63 | 84 | Green | Survey activities progressing as per plan across allocated sites | 5 | Manish Agarwal
LOG-000948 | PRJ-2024034 | 2025-12-21 | 67 | 90 | Green | Client UAT sign-off received for batch of completed sites | 7 | Manish Agarwal
LOG-000949 | PRJ-2024034 | 2025-12-28 | 69 | 93 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Manish Agarwal
LOG-000950 | PRJ-2024034 | 2026-01-04 | 70 | 94 | Green | Weekly governance call held with client stakeholders | 6 | Manish Agarwal
LOG-000951 | PRJ-2024034 | 2026-01-11 | 75 | 100 | Amber | Resource constraint flagged; additional field engineer requested | 5 | Manish Agarwal
LOG-000952 | PRJ-2024034 | 2026-01-18 | 75 | 100 | Red | Weekly governance call held with client stakeholders | 3 | Manish Agarwal
LOG-000953 | PRJ-2024035 | 2025-08-01 | 0 | 1 | Green | Survey activities progressing as per plan across allocated sites | 3 | Sandeep Rao
LOG-000954 | PRJ-2024035 | 2025-08-08 | 1 | 4 | Green | Equipment dispatch completed; installation team mobilized | 0 | Sandeep Rao
LOG-000955 | PRJ-2024035 | 2025-08-15 | 1 | 7 | Red | Survey activities progressing as per plan across allocated sites | 6 | Sandeep Rao
LOG-000956 | PRJ-2024035 | 2025-08-22 | 3 | 13 | Amber | Survey activities progressing as per plan across allocated sites | 1 | Sandeep Rao
LOG-000957 | PRJ-2024035 | 2025-08-29 | 4 | 16 | Green | Client UAT sign-off received for batch of completed sites | 5 | Sandeep Rao
LOG-000958 | PRJ-2024035 | 2025-09-05 | 4 | 19 | Red | Equipment dispatch completed; installation team mobilized | 0 | Sandeep Rao
LOG-000959 | PRJ-2024035 | 2025-09-12 | 5 | 20 | Green | Survey activities progressing as per plan across allocated sites | 4 | Sandeep Rao
LOG-000960 | PRJ-2024035 | 2025-09-19 | 5 | 21 | Green | Equipment dispatch completed; installation team mobilized | 6 | Sandeep Rao
LOG-000961 | PRJ-2024035 | 2025-09-26 | 6 | 24 | Green | Equipment dispatch completed; installation team mobilized | 7 | Sandeep Rao
LOG-000962 | PRJ-2024035 | 2025-10-03 | 7 | 28 | Red | Resource constraint flagged; additional field engineer requested | 3 | Sandeep Rao
LOG-000963 | PRJ-2024035 | 2025-10-10 | 7 | 31 | Red | Resource constraint flagged; additional field engineer requested | 7 | Sandeep Rao
LOG-000964 | PRJ-2024035 | 2025-10-17 | 8 | 34 | Green | Equipment dispatch completed; installation team mobilized | 6 | Sandeep Rao
LOG-000965 | PRJ-2024035 | 2025-10-24 | 8 | 35 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Sandeep Rao
LOG-000966 | PRJ-2024035 | 2025-10-31 | 9 | 38 | Amber | Client UAT sign-off received for batch of completed sites | 2 | Sandeep Rao
LOG-000967 | PRJ-2024035 | 2025-11-07 | 10 | 41 | Amber | Client UAT sign-off received for batch of completed sites | 0 | Sandeep Rao
LOG-000968 | PRJ-2024035 | 2025-11-14 | 10 | 42 | Green | Vendor escalation raised for delayed circuit provisioning | 0 | Sandeep Rao
LOG-000969 | PRJ-2024035 | 2025-11-21 | 12 | 48 | Amber | Vendor escalation raised for delayed circuit provisioning | 5 | Sandeep Rao
LOG-000970 | PRJ-2024035 | 2025-11-28 | 13 | 54 | Green | Survey activities progressing as per plan across allocated sites | 8 | Sandeep Rao
LOG-000971 | PRJ-2024035 | 2025-12-05 | 13 | 55 | Green | Weekly governance call held with client stakeholders | 1 | Sandeep Rao
LOG-000972 | PRJ-2024035 | 2025-12-12 | 14 | 59 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Sandeep Rao
LOG-000973 | PRJ-2024035 | 2025-12-19 | 15 | 60 | Red | Weekly governance call held with client stakeholders | 1 | Sandeep Rao
LOG-000974 | PRJ-2024035 | 2025-12-26 | 15 | 63 | Red | Equipment dispatch completed; installation team mobilized | 0 | Sandeep Rao
LOG-000975 | PRJ-2024035 | 2026-01-02 | 16 | 66 | Green | Survey activities progressing as per plan across allocated sites | 5 | Sandeep Rao
LOG-000976 | PRJ-2024035 | 2026-01-09 | 16 | 67 | Amber | Resource constraint flagged; additional field engineer requested | 1 | Sandeep Rao
LOG-000977 | PRJ-2024035 | 2026-01-16 | 17 | 71 | Green | Survey activities progressing as per plan across allocated sites | 6 | Sandeep Rao
LOG-000978 | PRJ-2024035 | 2026-01-23 | 19 | 77 | Green | Client UAT sign-off received for batch of completed sites | 7 | Sandeep Rao
LOG-000979 | PRJ-2024035 | 2026-01-30 | 20 | 83 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Sandeep Rao
LOG-000980 | PRJ-2024035 | 2026-02-06 | 22 | 89 | Green | Weekly governance call held with client stakeholders | 3 | Sandeep Rao
LOG-000981 | PRJ-2024036 | 2025-03-02 | 0 | 2 | Green | Survey activities progressing as per plan across allocated sites | 7 | Ananya Joshi
LOG-000982 | PRJ-2024036 | 2025-03-09 | 1 | 6 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Ananya Joshi
LOG-000983 | PRJ-2024036 | 2025-03-16 | 2 | 9 | Green | Client UAT sign-off received for batch of completed sites | 1 | Ananya Joshi
LOG-000984 | PRJ-2024036 | 2025-03-23 | 3 | 13 | Red | Equipment dispatch completed; installation team mobilized | 4 | Ananya Joshi
LOG-000985 | PRJ-2024036 | 2025-03-30 | 4 | 16 | Amber | Vendor escalation raised for delayed circuit provisioning | 6 | Ananya Joshi
LOG-000986 | PRJ-2024036 | 2025-04-06 | 5 | 19 | Green | Resource constraint flagged; additional field engineer requested | 8 | Ananya Joshi
LOG-000987 | PRJ-2024036 | 2025-04-13 | 7 | 24 | Green | Equipment dispatch completed; installation team mobilized | 4 | Ananya Joshi
LOG-000988 | PRJ-2024036 | 2025-04-20 | 7 | 25 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Ananya Joshi
LOG-000989 | PRJ-2024036 | 2025-04-27 | 9 | 30 | Green | Resource constraint flagged; additional field engineer requested | 1 | Ananya Joshi
LOG-000990 | PRJ-2024036 | 2025-05-04 | 9 | 32 | Amber | Weekly governance call held with client stakeholders | 2 | Ananya Joshi
LOG-000991 | PRJ-2024036 | 2025-05-11 | 10 | 35 | Green | Resource constraint flagged; additional field engineer requested | 7 | Ananya Joshi
LOG-000992 | PRJ-2024036 | 2025-05-18 | 12 | 41 | Red | Resource constraint flagged; additional field engineer requested | 2 | Ananya Joshi
LOG-000993 | PRJ-2024036 | 2025-05-25 | 13 | 46 | Amber | Weekly governance call held with client stakeholders | 5 | Ananya Joshi
LOG-000994 | PRJ-2024036 | 2025-06-01 | 15 | 51 | Green | Weekly governance call held with client stakeholders | 4 | Ananya Joshi
LOG-000995 | PRJ-2024036 | 2025-06-08 | 16 | 54 | Red | Vendor escalation raised for delayed circuit provisioning | 4 | Ananya Joshi
LOG-000996 | PRJ-2024036 | 2025-06-15 | 16 | 55 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Ananya Joshi
LOG-000997 | PRJ-2024036 | 2025-06-22 | 17 | 59 | Green | Resource constraint flagged; additional field engineer requested | 8 | Ananya Joshi
LOG-000998 | PRJ-2024036 | 2025-06-29 | 18 | 62 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Ananya Joshi
LOG-000999 | PRJ-2024036 | 2025-07-06 | 20 | 68 | Green | Vendor escalation raised for delayed circuit provisioning | 8 | Ananya Joshi
LOG-001000 | PRJ-2024036 | 2025-07-13 | 21 | 72 | Red | Survey activities progressing as per plan across allocated sites | 7 | Ananya Joshi
LOG-001001 | PRJ-2024036 | 2025-07-20 | 22 | 74 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-001002 | PRJ-2024036 | 2025-07-27 | 23 | 78 | Green | Resource constraint flagged; additional field engineer requested | 7 | Ananya Joshi
LOG-001003 | PRJ-2024036 | 2025-08-03 | 24 | 80 | Amber | Vendor escalation raised for delayed circuit provisioning | 0 | Ananya Joshi
LOG-001004 | PRJ-2024036 | 2025-08-10 | 24 | 83 | Green | Equipment dispatch completed; installation team mobilized | 2 | Ananya Joshi
LOG-001005 | PRJ-2024036 | 2025-08-17 | 25 | 86 | Green | Vendor escalation raised for delayed circuit provisioning | 1 | Ananya Joshi
LOG-001006 | PRJ-2024036 | 2025-08-24 | 27 | 91 | Amber | Survey activities progressing as per plan across allocated sites | 6 | Ananya Joshi
LOG-001007 | PRJ-2024036 | 2025-08-31 | 27 | 93 | Red | Vendor escalation raised for delayed circuit provisioning | 7 | Ananya Joshi
LOG-001008 | PRJ-2024036 | 2025-09-07 | 28 | 96 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Ananya Joshi
LOG-001009 | PRJ-2024037 | 2025-01-12 | 4 | 4 | Amber | Weekly governance call held with client stakeholders | 6 | Chinmay Deshpande
LOG-001010 | PRJ-2024037 | 2025-01-19 | 5 | 5 | Red | Survey activities progressing as per plan across allocated sites | 1 | Chinmay Deshpande
LOG-001011 | PRJ-2024037 | 2025-01-26 | 10 | 10 | Green | Equipment dispatch completed; installation team mobilized | 2 | Chinmay Deshpande
LOG-001012 | PRJ-2024037 | 2025-02-02 | 14 | 14 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 5 | Chinmay Deshpande
LOG-001013 | PRJ-2024037 | 2025-02-09 | 19 | 19 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Chinmay Deshpande
LOG-001014 | PRJ-2024037 | 2025-02-16 | 23 | 23 | Amber | Resource constraint flagged; additional field engineer requested | 7 | Chinmay Deshpande
LOG-001015 | PRJ-2024037 | 2025-02-23 | 24 | 24 | Red | Resource constraint flagged; additional field engineer requested | 5 | Chinmay Deshpande
LOG-001016 | PRJ-2024037 | 2025-03-02 | 28 | 28 | Amber | Equipment dispatch completed; installation team mobilized | 1 | Chinmay Deshpande
LOG-001017 | PRJ-2024037 | 2025-03-09 | 29 | 29 | Green | Resource constraint flagged; additional field engineer requested | 6 | Chinmay Deshpande
LOG-001018 | PRJ-2024037 | 2025-03-16 | 35 | 35 | Green | Resource constraint flagged; additional field engineer requested | 6 | Chinmay Deshpande
LOG-001019 | PRJ-2024037 | 2025-03-23 | 39 | 39 | Green | Weekly governance call held with client stakeholders | 4 | Chinmay Deshpande
LOG-001020 | PRJ-2024037 | 2025-03-30 | 42 | 42 | Amber | Client UAT sign-off received for batch of completed sites | 7 | Chinmay Deshpande
LOG-001021 | PRJ-2024037 | 2025-04-06 | 43 | 43 | Green | Survey activities progressing as per plan across allocated sites | 5 | Chinmay Deshpande
LOG-001022 | PRJ-2024037 | 2025-04-13 | 47 | 47 | Amber | Survey activities progressing as per plan across allocated sites | 2 | Chinmay Deshpande
LOG-001023 | PRJ-2024037 | 2025-04-20 | 50 | 50 | Green | Weekly governance call held with client stakeholders | 1 | Chinmay Deshpande
LOG-001024 | PRJ-2024037 | 2025-04-27 | 53 | 53 | Green | Equipment dispatch completed; installation team mobilized | 4 | Chinmay Deshpande
LOG-001025 | PRJ-2024037 | 2025-05-04 | 58 | 58 | Green | Survey activities progressing as per plan across allocated sites | 8 | Chinmay Deshpande
LOG-001026 | PRJ-2024037 | 2025-05-11 | 61 | 61 | Amber | Resource constraint flagged; additional field engineer requested | 5 | Chinmay Deshpande
LOG-001027 | PRJ-2024037 | 2025-05-18 | 63 | 63 | Green | Client UAT sign-off received for batch of completed sites | 3 | Chinmay Deshpande
LOG-001028 | PRJ-2024037 | 2025-05-25 | 67 | 67 | Green | Equipment dispatch completed; installation team mobilized | 8 | Chinmay Deshpande
LOG-001029 | PRJ-2024037 | 2025-06-01 | 70 | 70 | Green | Equipment dispatch completed; installation team mobilized | 5 | Chinmay Deshpande
LOG-001030 | PRJ-2024037 | 2025-06-08 | 76 | 76 | Amber | Client UAT sign-off received for batch of completed sites | 6 | Chinmay Deshpande
LOG-001031 | PRJ-2024037 | 2025-06-15 | 78 | 78 | Green | Resource constraint flagged; additional field engineer requested | 5 | Chinmay Deshpande
LOG-001032 | PRJ-2024037 | 2025-06-22 | 84 | 84 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 0 | Chinmay Deshpande
LOG-001033 | PRJ-2024037 | 2025-06-29 | 90 | 90 | Green | Survey activities progressing as per plan across allocated sites | 5 | Chinmay Deshpande
LOG-001034 | PRJ-2024037 | 2025-07-06 | 92 | 92 | Green | Weekly governance call held with client stakeholders | 7 | Chinmay Deshpande
LOG-001035 | PRJ-2024037 | 2025-07-13 | 94 | 94 | Amber | Weekly governance call held with client stakeholders | 7 | Chinmay Deshpande
LOG-001036 | PRJ-2024037 | 2025-07-20 | 96 | 96 | Red | Weekly governance call held with client stakeholders | 2 | Chinmay Deshpande
LOG-001037 | PRJ-2024038 | 2025-08-23 | 8 | 4 | Amber | Vendor escalation raised for delayed circuit provisioning | 5 | Sandeep Rao
LOG-001038 | PRJ-2024038 | 2025-08-30 | 20 | 10 | Red | Vendor escalation raised for delayed circuit provisioning | 7 | Sandeep Rao
LOG-001039 | PRJ-2024038 | 2025-09-06 | 22 | 11 | Red | Vendor escalation raised for delayed circuit provisioning | 4 | Sandeep Rao
LOG-001040 | PRJ-2024038 | 2025-09-13 | 26 | 13 | Amber | Resource constraint flagged; additional field engineer requested | 6 | Sandeep Rao
LOG-001041 | PRJ-2024038 | 2025-09-20 | 28 | 14 | Green | Client UAT sign-off received for batch of completed sites | 6 | Sandeep Rao
LOG-001042 | PRJ-2024038 | 2025-09-27 | 38 | 19 | Red | Survey activities progressing as per plan across allocated sites | 2 | Sandeep Rao
LOG-001043 | PRJ-2024038 | 2025-10-04 | 46 | 23 | Amber | Weekly governance call held with client stakeholders | 4 | Sandeep Rao
LOG-001044 | PRJ-2024038 | 2025-10-11 | 52 | 26 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 4 | Sandeep Rao
LOG-001045 | PRJ-2024038 | 2025-10-18 | 56 | 28 | Green | Survey activities progressing as per plan across allocated sites | 0 | Sandeep Rao
LOG-001046 | PRJ-2024038 | 2025-10-25 | 64 | 32 | Red | Resource constraint flagged; additional field engineer requested | 6 | Sandeep Rao
LOG-001047 | PRJ-2024038 | 2025-11-01 | 66 | 33 | Amber | Equipment dispatch completed; installation team mobilized | 3 | Sandeep Rao
LOG-001048 | PRJ-2024038 | 2025-11-08 | 74 | 37 | Amber | Resource constraint flagged; additional field engineer requested | 7 | Sandeep Rao
LOG-001049 | PRJ-2024038 | 2025-11-15 | 86 | 43 | Red | Equipment dispatch completed; installation team mobilized | 2 | Sandeep Rao
LOG-001050 | PRJ-2024038 | 2025-11-22 | 92 | 46 | Amber | Survey activities progressing as per plan across allocated sites | 6 | Sandeep Rao
LOG-001051 | PRJ-2024038 | 2025-11-29 | 98 | 49 | Red | Survey activities progressing as per plan across allocated sites | 1 | Sandeep Rao
LOG-001052 | PRJ-2024038 | 2025-12-06 | 106 | 53 | Green | Weekly governance call held with client stakeholders | 6 | Sandeep Rao
LOG-001053 | PRJ-2024038 | 2025-12-13 | 116 | 58 | Green | Survey activities progressing as per plan across allocated sites | 7 | Sandeep Rao
LOG-001054 | PRJ-2024038 | 2025-12-20 | 120 | 60 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Sandeep Rao
LOG-001055 | PRJ-2024038 | 2025-12-27 | 126 | 63 | Green | Survey activities progressing as per plan across allocated sites | 6 | Sandeep Rao
LOG-001056 | PRJ-2024038 | 2026-01-03 | 136 | 68 | Green | Equipment dispatch completed; installation team mobilized | 6 | Sandeep Rao
LOG-001057 | PRJ-2024038 | 2026-01-10 | 146 | 73 | Amber | Vendor escalation raised for delayed circuit provisioning | 0 | Sandeep Rao
LOG-001058 | PRJ-2024038 | 2026-01-17 | 154 | 77 | Red | Vendor escalation raised for delayed circuit provisioning | 2 | Sandeep Rao
LOG-001059 | PRJ-2024038 | 2026-01-24 | 158 | 79 | Green | Client UAT sign-off received for batch of completed sites | 0 | Sandeep Rao
LOG-001060 | PRJ-2024038 | 2026-01-31 | 160 | 80 | Red | Survey activities progressing as per plan across allocated sites | 3 | Sandeep Rao
LOG-001061 | PRJ-2024038 | 2026-02-07 | 164 | 82 | Green | Resource constraint flagged; additional field engineer requested | 0 | Sandeep Rao
LOG-001062 | PRJ-2024038 | 2026-02-14 | 168 | 84 | Green | Resource constraint flagged; additional field engineer requested | 7 | Sandeep Rao
LOG-001063 | PRJ-2024038 | 2026-02-21 | 174 | 87 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Sandeep Rao
LOG-001064 | PRJ-2024038 | 2026-02-28 | 184 | 92 | Green | Resource constraint flagged; additional field engineer requested | 4 | Sandeep Rao
LOG-001065 | PRJ-2024042 | 2025-06-01 | 12 | 5 | Green | Survey activities progressing as per plan across allocated sites | 8 | Sandeep Rao
LOG-001066 | PRJ-2024042 | 2025-06-08 | 15 | 6 | Green | Weekly governance call held with client stakeholders | 6 | Sandeep Rao
LOG-001067 | PRJ-2024042 | 2025-06-15 | 30 | 12 | Red | Weekly governance call held with client stakeholders | 5 | Sandeep Rao
LOG-001068 | PRJ-2024042 | 2025-06-22 | 42 | 17 | Red | Survey activities progressing as per plan across allocated sites | 1 | Sandeep Rao
LOG-001069 | PRJ-2024042 | 2025-06-29 | 57 | 23 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Sandeep Rao
LOG-001070 | PRJ-2024042 | 2025-07-06 | 67 | 27 | Green | Survey activities progressing as per plan across allocated sites | 3 | Sandeep Rao
LOG-001071 | PRJ-2024042 | 2025-07-13 | 70 | 28 | Green | Vendor escalation raised for delayed circuit provisioning | 2 | Sandeep Rao
LOG-001072 | PRJ-2024042 | 2025-07-20 | 82 | 33 | Amber | Vendor escalation raised for delayed circuit provisioning | 1 | Sandeep Rao
LOG-001073 | PRJ-2024042 | 2025-07-27 | 90 | 36 | Amber | Equipment dispatch completed; installation team mobilized | 5 | Sandeep Rao
LOG-001074 | PRJ-2024042 | 2025-08-03 | 92 | 37 | Green | Weekly governance call held with client stakeholders | 2 | Sandeep Rao
LOG-001075 | PRJ-2024042 | 2025-08-10 | 95 | 38 | Green | Resource constraint flagged; additional field engineer requested | 3 | Sandeep Rao
LOG-001076 | PRJ-2024042 | 2025-08-17 | 107 | 43 | Green | Equipment dispatch completed; installation team mobilized | 6 | Sandeep Rao
LOG-001077 | PRJ-2024042 | 2025-08-24 | 117 | 47 | Amber | Weekly governance call held with client stakeholders | 4 | Sandeep Rao
LOG-001078 | PRJ-2024042 | 2025-08-31 | 122 | 49 | Green | Vendor escalation raised for delayed circuit provisioning | 4 | Sandeep Rao
LOG-001079 | PRJ-2024042 | 2025-09-07 | 127 | 51 | Red | Weekly governance call held with client stakeholders | 3 | Sandeep Rao
LOG-001080 | PRJ-2024042 | 2025-09-14 | 142 | 57 | Amber | Equipment dispatch completed; installation team mobilized | 4 | Sandeep Rao
LOG-001081 | PRJ-2024042 | 2025-09-21 | 147 | 59 | Red | Vendor escalation raised for delayed circuit provisioning | 4 | Sandeep Rao
LOG-001082 | PRJ-2024042 | 2025-09-28 | 157 | 63 | Green | Client UAT sign-off received for batch of completed sites | 7 | Sandeep Rao
LOG-001083 | PRJ-2024042 | 2025-10-05 | 162 | 65 | Green | Weekly governance call held with client stakeholders | 8 | Sandeep Rao
LOG-001084 | PRJ-2024042 | 2025-10-12 | 177 | 71 | Green | Survey activities progressing as per plan across allocated sites | 3 | Sandeep Rao
LOG-001085 | PRJ-2024042 | 2025-10-19 | 180 | 72 | Green | Resource constraint flagged; additional field engineer requested | 7 | Sandeep Rao
LOG-001086 | PRJ-2024042 | 2025-10-26 | 190 | 76 | Green | Weekly governance call held with client stakeholders | 1 | Sandeep Rao
LOG-001087 | PRJ-2024042 | 2025-11-02 | 200 | 80 | Red | Last mile delays reported in 2-3 sites due to local ROW issues | 1 | Sandeep Rao
LOG-001088 | PRJ-2024042 | 2025-11-09 | 210 | 84 | Green | Equipment dispatch completed; installation team mobilized | 0 | Sandeep Rao
LOG-001089 | PRJ-2024042 | 2025-11-16 | 217 | 87 | Green | Last mile delays reported in 2-3 sites due to local ROW issues | 2 | Sandeep Rao
LOG-001090 | PRJ-2024042 | 2025-11-23 | 227 | 91 | Amber | Vendor escalation raised for delayed circuit provisioning | 2 | Sandeep Rao
LOG-001091 | PRJ-2024042 | 2025-11-30 | 235 | 94 | Green | Weekly governance call held with client stakeholders | 8 | Sandeep Rao
LOG-001092 | PRJ-2024042 | 2025-12-07 | 240 | 96 | Amber | Last mile delays reported in 2-3 sites due to local ROW issues | 6 | Sandeep Rao

## Date_Dimension
Date | Year | MonthNumber | MonthName | MonthYear | Quarter | FiscalYear | WeekNumber | DayName
2024-07-01 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Monday
2024-07-02 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Tuesday
2024-07-03 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Wednesday
2024-07-04 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Thursday
2024-07-05 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Friday
2024-07-06 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Saturday
2024-07-07 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 27 | Sunday
2024-07-08 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Monday
2024-07-09 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Tuesday
2024-07-10 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Wednesday
2024-07-11 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Thursday
2024-07-12 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Friday
2024-07-13 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Saturday
2024-07-14 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 28 | Sunday
2024-07-15 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Monday
2024-07-16 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Tuesday
2024-07-17 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Wednesday
2024-07-18 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Thursday
2024-07-19 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Friday
2024-07-20 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Saturday
2024-07-21 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 29 | Sunday
2024-07-22 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Monday
2024-07-23 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Tuesday
2024-07-24 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Wednesday
2024-07-25 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Thursday
2024-07-26 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Friday
2024-07-27 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Saturday
2024-07-28 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 30 | Sunday
2024-07-29 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 31 | Monday
2024-07-30 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 31 | Tuesday
2024-07-31 | 2024 | 7 | Jul | Jul-2024 | Q3 | FY2024-25 | 31 | Wednesday
2024-08-01 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 31 | Thursday
2024-08-02 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 31 | Friday
2024-08-03 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 31 | Saturday
2024-08-04 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 31 | Sunday
2024-08-05 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Monday
2024-08-06 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Tuesday
2024-08-07 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Wednesday
2024-08-08 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Thursday
2024-08-09 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Friday
2024-08-10 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Saturday
2024-08-11 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 32 | Sunday
2024-08-12 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Monday
2024-08-13 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Tuesday
2024-08-14 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Wednesday
2024-08-15 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Thursday
2024-08-16 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Friday
2024-08-17 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Saturday
2024-08-18 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 33 | Sunday
2024-08-19 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Monday
2024-08-20 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Tuesday
2024-08-21 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Wednesday
2024-08-22 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Thursday
2024-08-23 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Friday
2024-08-24 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Saturday
2024-08-25 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 34 | Sunday
2024-08-26 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 35 | Monday
2024-08-27 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 35 | Tuesday
2024-08-28 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 35 | Wednesday
2024-08-29 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 35 | Thursday
2024-08-30 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 35 | Friday
2024-08-31 | 2024 | 8 | Aug | Aug-2024 | Q3 | FY2024-25 | 35 | Saturday
2024-09-01 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 35 | Sunday
2024-09-02 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Monday
2024-09-03 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Tuesday
2024-09-04 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Wednesday
2024-09-05 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Thursday
2024-09-06 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Friday
2024-09-07 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Saturday
2024-09-08 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 36 | Sunday
2024-09-09 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Monday
2024-09-10 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Tuesday
2024-09-11 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Wednesday
2024-09-12 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Thursday
2024-09-13 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Friday
2024-09-14 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Saturday
2024-09-15 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 37 | Sunday
2024-09-16 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Monday
2024-09-17 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Tuesday
2024-09-18 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Wednesday
2024-09-19 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Thursday
2024-09-20 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Friday
2024-09-21 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Saturday
2024-09-22 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 38 | Sunday
2024-09-23 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Monday
2024-09-24 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Tuesday
2024-09-25 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Wednesday
2024-09-26 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Thursday
2024-09-27 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Friday
2024-09-28 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Saturday
2024-09-29 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 39 | Sunday
2024-09-30 | 2024 | 9 | Sep | Sep-2024 | Q3 | FY2024-25 | 40 | Monday
2024-10-01 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 40 | Tuesday
2024-10-02 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 40 | Wednesday
2024-10-03 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 40 | Thursday
2024-10-04 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 40 | Friday
2024-10-05 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 40 | Saturday
2024-10-06 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 40 | Sunday
2024-10-07 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Monday
2024-10-08 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Tuesday
2024-10-09 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Wednesday
2024-10-10 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Thursday
2024-10-11 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Friday
2024-10-12 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Saturday
2024-10-13 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 41 | Sunday
2024-10-14 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Monday
2024-10-15 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Tuesday
2024-10-16 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Wednesday
2024-10-17 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Thursday
2024-10-18 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Friday
2024-10-19 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Saturday
2024-10-20 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 42 | Sunday
2024-10-21 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Monday
2024-10-22 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Tuesday
2024-10-23 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Wednesday
2024-10-24 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Thursday
2024-10-25 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Friday
2024-10-26 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Saturday
2024-10-27 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 43 | Sunday
2024-10-28 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 44 | Monday
2024-10-29 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 44 | Tuesday
2024-10-30 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 44 | Wednesday
2024-10-31 | 2024 | 10 | Oct | Oct-2024 | Q4 | FY2024-25 | 44 | Thursday
2024-11-01 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 44 | Friday
2024-11-02 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 44 | Saturday
2024-11-03 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 44 | Sunday
2024-11-04 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Monday
2024-11-05 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Tuesday
2024-11-06 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Wednesday
2024-11-07 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Thursday
2024-11-08 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Friday
2024-11-09 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Saturday
2024-11-10 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 45 | Sunday
2024-11-11 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Monday
2024-11-12 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Tuesday
2024-11-13 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Wednesday
2024-11-14 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Thursday
2024-11-15 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Friday
2024-11-16 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Saturday
2024-11-17 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 46 | Sunday
2024-11-18 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Monday
2024-11-19 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Tuesday
2024-11-20 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Wednesday
2024-11-21 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Thursday
2024-11-22 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Friday
2024-11-23 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Saturday
2024-11-24 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 47 | Sunday
2024-11-25 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 48 | Monday
2024-11-26 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 48 | Tuesday
2024-11-27 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 48 | Wednesday
2024-11-28 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 48 | Thursday
2024-11-29 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 48 | Friday
2024-11-30 | 2024 | 11 | Nov | Nov-2024 | Q4 | FY2024-25 | 48 | Saturday
2024-12-01 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 48 | Sunday
2024-12-02 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Monday
2024-12-03 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Tuesday
2024-12-04 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Wednesday
2024-12-05 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Thursday
2024-12-06 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Friday
2024-12-07 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Saturday
2024-12-08 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 49 | Sunday
2024-12-09 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Monday
2024-12-10 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Tuesday
2024-12-11 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Wednesday
2024-12-12 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Thursday
2024-12-13 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Friday
2024-12-14 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Saturday
2024-12-15 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 50 | Sunday
2024-12-16 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Monday
2024-12-17 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Tuesday
2024-12-18 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Wednesday
2024-12-19 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Thursday
2024-12-20 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Friday
2024-12-21 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Saturday
2024-12-22 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 51 | Sunday
2024-12-23 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Monday
2024-12-24 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Tuesday
2024-12-25 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Wednesday
2024-12-26 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Thursday
2024-12-27 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Friday
2024-12-28 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Saturday
2024-12-29 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 52 | Sunday
2024-12-30 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 1 | Monday
2024-12-31 | 2024 | 12 | Dec | Dec-2024 | Q4 | FY2024-25 | 1 | Tuesday
2025-01-01 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 1 | Wednesday
2025-01-02 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 1 | Thursday
2025-01-03 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 1 | Friday
2025-01-04 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 1 | Saturday
2025-01-05 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 1 | Sunday
2025-01-06 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Monday
2025-01-07 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Tuesday
2025-01-08 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Wednesday
2025-01-09 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Thursday
2025-01-10 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Friday
2025-01-11 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Saturday
2025-01-12 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 2 | Sunday
2025-01-13 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Monday
2025-01-14 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Tuesday
2025-01-15 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Wednesday
2025-01-16 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Thursday
2025-01-17 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Friday
2025-01-18 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Saturday
2025-01-19 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 3 | Sunday
2025-01-20 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Monday
2025-01-21 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Tuesday
2025-01-22 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Wednesday
2025-01-23 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Thursday
2025-01-24 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Friday
2025-01-25 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Saturday
2025-01-26 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 4 | Sunday
2025-01-27 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 5 | Monday
2025-01-28 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 5 | Tuesday
2025-01-29 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 5 | Wednesday
2025-01-30 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 5 | Thursday
2025-01-31 | 2025 | 1 | Jan | Jan-2025 | Q1 | FY2024-25 | 5 | Friday
2025-02-01 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 5 | Saturday
2025-02-02 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 5 | Sunday
2025-02-03 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Monday
2025-02-04 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Tuesday
2025-02-05 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Wednesday
2025-02-06 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Thursday
2025-02-07 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Friday
2025-02-08 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Saturday
2025-02-09 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 6 | Sunday
2025-02-10 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Monday
2025-02-11 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Tuesday
2025-02-12 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Wednesday
2025-02-13 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Thursday
2025-02-14 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Friday
2025-02-15 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Saturday
2025-02-16 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 7 | Sunday
2025-02-17 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Monday
2025-02-18 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Tuesday
2025-02-19 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Wednesday
2025-02-20 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Thursday
2025-02-21 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Friday
2025-02-22 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Saturday
2025-02-23 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 8 | Sunday
2025-02-24 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 9 | Monday
2025-02-25 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 9 | Tuesday
2025-02-26 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 9 | Wednesday
2025-02-27 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 9 | Thursday
2025-02-28 | 2025 | 2 | Feb | Feb-2025 | Q1 | FY2024-25 | 9 | Friday
2025-03-01 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 9 | Saturday
2025-03-02 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 9 | Sunday
2025-03-03 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Monday
2025-03-04 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Tuesday
2025-03-05 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Wednesday
2025-03-06 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Thursday
2025-03-07 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Friday
2025-03-08 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Saturday
2025-03-09 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 10 | Sunday
2025-03-10 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Monday
2025-03-11 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Tuesday
2025-03-12 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Wednesday
2025-03-13 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Thursday
2025-03-14 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Friday
2025-03-15 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Saturday
2025-03-16 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 11 | Sunday
2025-03-17 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Monday
2025-03-18 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Tuesday
2025-03-19 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Wednesday
2025-03-20 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Thursday
2025-03-21 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Friday
2025-03-22 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Saturday
2025-03-23 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 12 | Sunday
2025-03-24 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Monday
2025-03-25 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Tuesday
2025-03-26 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Wednesday
2025-03-27 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Thursday
2025-03-28 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Friday
2025-03-29 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Saturday
2025-03-30 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 13 | Sunday
2025-03-31 | 2025 | 3 | Mar | Mar-2025 | Q1 | FY2024-25 | 14 | Monday
2025-04-01 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 14 | Tuesday
2025-04-02 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 14 | Wednesday
2025-04-03 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 14 | Thursday
2025-04-04 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 14 | Friday
2025-04-05 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 14 | Saturday
2025-04-06 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 14 | Sunday
2025-04-07 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Monday
2025-04-08 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Tuesday
2025-04-09 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Wednesday
2025-04-10 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Thursday
2025-04-11 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Friday
2025-04-12 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Saturday
2025-04-13 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 15 | Sunday
2025-04-14 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Monday
2025-04-15 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Tuesday
2025-04-16 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Wednesday
2025-04-17 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Thursday
2025-04-18 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Friday
2025-04-19 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Saturday
2025-04-20 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 16 | Sunday
2025-04-21 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Monday
2025-04-22 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Tuesday
2025-04-23 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Wednesday
2025-04-24 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Thursday
2025-04-25 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Friday
2025-04-26 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Saturday
2025-04-27 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 17 | Sunday
2025-04-28 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 18 | Monday
2025-04-29 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 18 | Tuesday
2025-04-30 | 2025 | 4 | Apr | Apr-2025 | Q2 | FY2025-26 | 18 | Wednesday
2025-05-01 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 18 | Thursday
2025-05-02 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 18 | Friday
2025-05-03 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 18 | Saturday
2025-05-04 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 18 | Sunday
2025-05-05 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Monday
2025-05-06 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Tuesday
2025-05-07 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Wednesday
2025-05-08 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Thursday
2025-05-09 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Friday
2025-05-10 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Saturday
2025-05-11 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 19 | Sunday
2025-05-12 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Monday
2025-05-13 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Tuesday
2025-05-14 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Wednesday
2025-05-15 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Thursday
2025-05-16 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Friday
2025-05-17 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Saturday
2025-05-18 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 20 | Sunday
2025-05-19 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Monday
2025-05-20 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Tuesday
2025-05-21 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Wednesday
2025-05-22 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Thursday
2025-05-23 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Friday
2025-05-24 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Saturday
2025-05-25 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 21 | Sunday
2025-05-26 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 22 | Monday
2025-05-27 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 22 | Tuesday
2025-05-28 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 22 | Wednesday
2025-05-29 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 22 | Thursday
2025-05-30 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 22 | Friday
2025-05-31 | 2025 | 5 | May | May-2025 | Q2 | FY2025-26 | 22 | Saturday
2025-06-01 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 22 | Sunday
2025-06-02 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Monday
2025-06-03 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Tuesday
2025-06-04 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Wednesday
2025-06-05 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Thursday
2025-06-06 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Friday
2025-06-07 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Saturday
2025-06-08 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 23 | Sunday
2025-06-09 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Monday
2025-06-10 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Tuesday
2025-06-11 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Wednesday
2025-06-12 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Thursday
2025-06-13 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Friday
2025-06-14 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Saturday
2025-06-15 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 24 | Sunday
2025-06-16 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Monday
2025-06-17 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Tuesday
2025-06-18 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Wednesday
2025-06-19 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Thursday
2025-06-20 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Friday
2025-06-21 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Saturday
2025-06-22 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 25 | Sunday
2025-06-23 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Monday
2025-06-24 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Tuesday
2025-06-25 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Wednesday
2025-06-26 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Thursday
2025-06-27 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Friday
2025-06-28 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Saturday
2025-06-29 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 26 | Sunday
2025-06-30 | 2025 | 6 | Jun | Jun-2025 | Q2 | FY2025-26 | 27 | Monday
2025-07-01 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 27 | Tuesday
2025-07-02 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 27 | Wednesday
2025-07-03 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 27 | Thursday
2025-07-04 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 27 | Friday
2025-07-05 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 27 | Saturday
2025-07-06 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 27 | Sunday
2025-07-07 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Monday
2025-07-08 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Tuesday
2025-07-09 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Wednesday
2025-07-10 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Thursday
2025-07-11 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Friday
2025-07-12 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Saturday
2025-07-13 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 28 | Sunday
2025-07-14 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Monday
2025-07-15 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Tuesday
2025-07-16 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Wednesday
2025-07-17 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Thursday
2025-07-18 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Friday
2025-07-19 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Saturday
2025-07-20 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 29 | Sunday
2025-07-21 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Monday
2025-07-22 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Tuesday
2025-07-23 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Wednesday
2025-07-24 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Thursday
2025-07-25 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Friday
2025-07-26 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Saturday
2025-07-27 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 30 | Sunday
2025-07-28 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 31 | Monday
2025-07-29 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 31 | Tuesday
2025-07-30 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 31 | Wednesday
2025-07-31 | 2025 | 7 | Jul | Jul-2025 | Q3 | FY2025-26 | 31 | Thursday
2025-08-01 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 31 | Friday
2025-08-02 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 31 | Saturday
2025-08-03 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 31 | Sunday
2025-08-04 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Monday
2025-08-05 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Tuesday
2025-08-06 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Wednesday
2025-08-07 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Thursday
2025-08-08 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Friday
2025-08-09 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Saturday
2025-08-10 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 32 | Sunday
2025-08-11 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Monday
2025-08-12 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Tuesday
2025-08-13 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Wednesday
2025-08-14 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Thursday
2025-08-15 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Friday
2025-08-16 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Saturday
2025-08-17 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 33 | Sunday
2025-08-18 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Monday
2025-08-19 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Tuesday
2025-08-20 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Wednesday
2025-08-21 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Thursday
2025-08-22 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Friday
2025-08-23 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Saturday
2025-08-24 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 34 | Sunday
2025-08-25 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Monday
2025-08-26 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Tuesday
2025-08-27 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Wednesday
2025-08-28 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Thursday
2025-08-29 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Friday
2025-08-30 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Saturday
2025-08-31 | 2025 | 8 | Aug | Aug-2025 | Q3 | FY2025-26 | 35 | Sunday
2025-09-01 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Monday
2025-09-02 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Tuesday
2025-09-03 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Wednesday
2025-09-04 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Thursday
2025-09-05 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Friday
2025-09-06 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Saturday
2025-09-07 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 36 | Sunday
2025-09-08 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Monday
2025-09-09 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Tuesday
2025-09-10 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Wednesday
2025-09-11 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Thursday
2025-09-12 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Friday
2025-09-13 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Saturday
2025-09-14 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 37 | Sunday
2025-09-15 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Monday
2025-09-16 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Tuesday
2025-09-17 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Wednesday
2025-09-18 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Thursday
2025-09-19 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Friday
2025-09-20 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Saturday
2025-09-21 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 38 | Sunday
2025-09-22 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Monday
2025-09-23 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Tuesday
2025-09-24 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Wednesday
2025-09-25 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Thursday
2025-09-26 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Friday
2025-09-27 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Saturday
2025-09-28 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 39 | Sunday
2025-09-29 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 40 | Monday
2025-09-30 | 2025 | 9 | Sep | Sep-2025 | Q3 | FY2025-26 | 40 | Tuesday
2025-10-01 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 40 | Wednesday
2025-10-02 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 40 | Thursday
2025-10-03 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 40 | Friday
2025-10-04 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 40 | Saturday
2025-10-05 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 40 | Sunday
2025-10-06 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Monday
2025-10-07 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Tuesday
2025-10-08 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Wednesday
2025-10-09 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Thursday
2025-10-10 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Friday
2025-10-11 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Saturday
2025-10-12 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 41 | Sunday
2025-10-13 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Monday
2025-10-14 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Tuesday
2025-10-15 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Wednesday
2025-10-16 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Thursday
2025-10-17 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Friday
2025-10-18 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Saturday
2025-10-19 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 42 | Sunday
2025-10-20 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Monday
2025-10-21 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Tuesday
2025-10-22 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Wednesday
2025-10-23 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Thursday
2025-10-24 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Friday
2025-10-25 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Saturday
2025-10-26 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 43 | Sunday
2025-10-27 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 44 | Monday
2025-10-28 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 44 | Tuesday
2025-10-29 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 44 | Wednesday
2025-10-30 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 44 | Thursday
2025-10-31 | 2025 | 10 | Oct | Oct-2025 | Q4 | FY2025-26 | 44 | Friday
2025-11-01 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 44 | Saturday
2025-11-02 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 44 | Sunday
2025-11-03 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Monday
2025-11-04 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Tuesday
2025-11-05 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Wednesday
2025-11-06 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Thursday
2025-11-07 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Friday
2025-11-08 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Saturday
2025-11-09 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 45 | Sunday
2025-11-10 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Monday
2025-11-11 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Tuesday
2025-11-12 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Wednesday
2025-11-13 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Thursday
2025-11-14 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Friday
2025-11-15 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Saturday
2025-11-16 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 46 | Sunday
2025-11-17 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Monday
2025-11-18 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Tuesday
2025-11-19 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Wednesday
2025-11-20 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Thursday
2025-11-21 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Friday
2025-11-22 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Saturday
2025-11-23 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 47 | Sunday
2025-11-24 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Monday
2025-11-25 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Tuesday
2025-11-26 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Wednesday
2025-11-27 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Thursday
2025-11-28 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Friday
2025-11-29 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Saturday
2025-11-30 | 2025 | 11 | Nov | Nov-2025 | Q4 | FY2025-26 | 48 | Sunday
2025-12-01 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Monday
2025-12-02 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Tuesday
2025-12-03 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Wednesday
2025-12-04 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Thursday
2025-12-05 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Friday
2025-12-06 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Saturday
2025-12-07 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 49 | Sunday
2025-12-08 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Monday
2025-12-09 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Tuesday
2025-12-10 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Wednesday
2025-12-11 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Thursday
2025-12-12 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Friday
2025-12-13 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Saturday
2025-12-14 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 50 | Sunday
2025-12-15 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Monday
2025-12-16 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Tuesday
2025-12-17 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Wednesday
2025-12-18 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Thursday
2025-12-19 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Friday
2025-12-20 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Saturday
2025-12-21 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 51 | Sunday
2025-12-22 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Monday
2025-12-23 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Tuesday
2025-12-24 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Wednesday
2025-12-25 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Thursday
2025-12-26 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Friday
2025-12-27 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Saturday
2025-12-28 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 52 | Sunday
2025-12-29 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 1 | Monday
2025-12-30 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 1 | Tuesday
2025-12-31 | 2025 | 12 | Dec | Dec-2025 | Q4 | FY2025-26 | 1 | Wednesday
2026-01-01 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 1 | Thursday
2026-01-02 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 1 | Friday
2026-01-03 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 1 | Saturday
2026-01-04 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 1 | Sunday
2026-01-05 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Monday
2026-01-06 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Tuesday
2026-01-07 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Wednesday
2026-01-08 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Thursday
2026-01-09 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Friday
2026-01-10 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Saturday
2026-01-11 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 2 | Sunday
2026-01-12 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Monday
2026-01-13 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Tuesday
2026-01-14 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Wednesday
2026-01-15 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Thursday
2026-01-16 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Friday
2026-01-17 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Saturday
2026-01-18 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 3 | Sunday
2026-01-19 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Monday
2026-01-20 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Tuesday
2026-01-21 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Wednesday
2026-01-22 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Thursday
2026-01-23 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Friday
2026-01-24 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Saturday
2026-01-25 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 4 | Sunday
2026-01-26 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 5 | Monday
2026-01-27 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 5 | Tuesday
2026-01-28 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 5 | Wednesday
2026-01-29 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 5 | Thursday
2026-01-30 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 5 | Friday
2026-01-31 | 2026 | 1 | Jan | Jan-2026 | Q1 | FY2025-26 | 5 | Saturday
2026-02-01 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 5 | Sunday
2026-02-02 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Monday
2026-02-03 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Tuesday
2026-02-04 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Wednesday
2026-02-05 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Thursday
2026-02-06 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Friday
2026-02-07 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Saturday
2026-02-08 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 6 | Sunday
2026-02-09 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Monday
2026-02-10 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Tuesday
2026-02-11 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Wednesday
2026-02-12 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Thursday
2026-02-13 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Friday
2026-02-14 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Saturday
2026-02-15 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 7 | Sunday
2026-02-16 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Monday
2026-02-17 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Tuesday
2026-02-18 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Wednesday
2026-02-19 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Thursday
2026-02-20 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Friday
2026-02-21 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Saturday
2026-02-22 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 8 | Sunday
2026-02-23 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 9 | Monday
2026-02-24 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 9 | Tuesday
2026-02-25 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 9 | Wednesday
2026-02-26 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 9 | Thursday
2026-02-27 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 9 | Friday
2026-02-28 | 2026 | 2 | Feb | Feb-2026 | Q1 | FY2025-26 | 9 | Saturday
2026-03-01 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 9 | Sunday
2026-03-02 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Monday
2026-03-03 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Tuesday
2026-03-04 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Wednesday
2026-03-05 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Thursday
2026-03-06 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Friday
2026-03-07 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Saturday
2026-03-08 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 10 | Sunday
2026-03-09 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Monday
2026-03-10 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Tuesday
2026-03-11 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Wednesday
2026-03-12 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Thursday
2026-03-13 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Friday
2026-03-14 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Saturday
2026-03-15 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 11 | Sunday
2026-03-16 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Monday
2026-03-17 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Tuesday
2026-03-18 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Wednesday
2026-03-19 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Thursday
2026-03-20 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Friday
2026-03-21 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Saturday
2026-03-22 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 12 | Sunday
2026-03-23 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Monday
2026-03-24 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Tuesday
2026-03-25 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Wednesday
2026-03-26 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Thursday
2026-03-27 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Friday
2026-03-28 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Saturday
2026-03-29 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 13 | Sunday
2026-03-30 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 14 | Monday
2026-03-31 | 2026 | 3 | Mar | Mar-2026 | Q1 | FY2025-26 | 14 | Tuesday
2026-04-01 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 14 | Wednesday
2026-04-02 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 14 | Thursday
2026-04-03 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 14 | Friday
2026-04-04 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 14 | Saturday
2026-04-05 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 14 | Sunday
2026-04-06 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Monday
2026-04-07 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Tuesday
2026-04-08 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Wednesday
2026-04-09 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Thursday
2026-04-10 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Friday
2026-04-11 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Saturday
2026-04-12 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 15 | Sunday
2026-04-13 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Monday
2026-04-14 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Tuesday
2026-04-15 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Wednesday
2026-04-16 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Thursday
2026-04-17 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Friday
2026-04-18 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Saturday
2026-04-19 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 16 | Sunday
2026-04-20 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Monday
2026-04-21 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Tuesday
2026-04-22 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Wednesday
2026-04-23 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Thursday
2026-04-24 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Friday
2026-04-25 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Saturday
2026-04-26 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 17 | Sunday
2026-04-27 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 18 | Monday
2026-04-28 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 18 | Tuesday
2026-04-29 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 18 | Wednesday
2026-04-30 | 2026 | 4 | Apr | Apr-2026 | Q2 | FY2026-27 | 18 | Thursday
2026-05-01 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 18 | Friday
2026-05-02 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 18 | Saturday
2026-05-03 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 18 | Sunday
2026-05-04 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Monday
2026-05-05 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Tuesday
2026-05-06 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Wednesday
2026-05-07 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Thursday
2026-05-08 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Friday
2026-05-09 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Saturday
2026-05-10 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 19 | Sunday
2026-05-11 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Monday
2026-05-12 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Tuesday
2026-05-13 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Wednesday
2026-05-14 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Thursday
2026-05-15 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Friday
2026-05-16 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Saturday
2026-05-17 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 20 | Sunday
2026-05-18 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Monday
2026-05-19 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Tuesday
2026-05-20 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Wednesday
2026-05-21 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Thursday
2026-05-22 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Friday
2026-05-23 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Saturday
2026-05-24 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 21 | Sunday
2026-05-25 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Monday
2026-05-26 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Tuesday
2026-05-27 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Wednesday
2026-05-28 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Thursday
2026-05-29 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Friday
2026-05-30 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Saturday
2026-05-31 | 2026 | 5 | May | May-2026 | Q2 | FY2026-27 | 22 | Sunday
2026-06-01 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Monday
2026-06-02 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Tuesday
2026-06-03 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Wednesday
2026-06-04 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Thursday
2026-06-05 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Friday
2026-06-06 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Saturday
2026-06-07 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 23 | Sunday
2026-06-08 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Monday
2026-06-09 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Tuesday
2026-06-10 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Wednesday
2026-06-11 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Thursday
2026-06-12 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Friday
2026-06-13 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Saturday
2026-06-14 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 24 | Sunday
2026-06-15 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Monday
2026-06-16 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Tuesday
2026-06-17 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Wednesday
2026-06-18 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Thursday
2026-06-19 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Friday
2026-06-20 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Saturday
2026-06-21 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 25 | Sunday
2026-06-22 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Monday
2026-06-23 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Tuesday
2026-06-24 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Wednesday
2026-06-25 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Thursday
2026-06-26 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Friday
2026-06-27 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Saturday
2026-06-28 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 26 | Sunday
2026-06-29 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 27 | Monday
2026-06-30 | 2026 | 6 | Jun | Jun-2026 | Q2 | FY2026-27 | 27 | Tuesday
2026-07-01 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 27 | Wednesday
2026-07-02 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 27 | Thursday
2026-07-03 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 27 | Friday
2026-07-04 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 27 | Saturday
2026-07-05 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 27 | Sunday
2026-07-06 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Monday
2026-07-07 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Tuesday
2026-07-08 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Wednesday
2026-07-09 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Thursday
2026-07-10 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Friday
2026-07-11 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Saturday
2026-07-12 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 28 | Sunday
2026-07-13 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Monday
2026-07-14 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Tuesday
2026-07-15 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Wednesday
2026-07-16 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Thursday
2026-07-17 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Friday
2026-07-18 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Saturday
2026-07-19 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 29 | Sunday
2026-07-20 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Monday
2026-07-21 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Tuesday
2026-07-22 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Wednesday
2026-07-23 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Thursday
2026-07-24 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Friday
2026-07-25 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Saturday
2026-07-26 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 30 | Sunday
2026-07-27 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 31 | Monday
2026-07-28 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 31 | Tuesday
2026-07-29 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 31 | Wednesday
2026-07-30 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 31 | Thursday
2026-07-31 | 2026 | 7 | Jul | Jul-2026 | Q3 | FY2026-27 | 31 | Friday
2026-08-01 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 31 | Saturday
2026-08-02 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 31 | Sunday
2026-08-03 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Monday
2026-08-04 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Tuesday
2026-08-05 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Wednesday
2026-08-06 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Thursday
2026-08-07 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Friday
2026-08-08 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Saturday
2026-08-09 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 32 | Sunday
2026-08-10 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Monday
2026-08-11 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Tuesday
2026-08-12 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Wednesday
2026-08-13 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Thursday
2026-08-14 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Friday
2026-08-15 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Saturday
2026-08-16 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 33 | Sunday
2026-08-17 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Monday
2026-08-18 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Tuesday
2026-08-19 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Wednesday
2026-08-20 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Thursday
2026-08-21 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Friday
2026-08-22 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Saturday
2026-08-23 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 34 | Sunday
2026-08-24 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Monday
2026-08-25 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Tuesday
2026-08-26 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Wednesday
2026-08-27 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Thursday
2026-08-28 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Friday
2026-08-29 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Saturday
2026-08-30 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 35 | Sunday
2026-08-31 | 2026 | 8 | Aug | Aug-2026 | Q3 | FY2026-27 | 36 | Monday
2026-09-01 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 36 | Tuesday
2026-09-02 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 36 | Wednesday
2026-09-03 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 36 | Thursday
2026-09-04 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 36 | Friday
2026-09-05 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 36 | Saturday
2026-09-06 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 36 | Sunday
2026-09-07 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Monday
2026-09-08 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Tuesday
2026-09-09 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Wednesday
2026-09-10 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Thursday
2026-09-11 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Friday
2026-09-12 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Saturday
2026-09-13 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 37 | Sunday
2026-09-14 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Monday
2026-09-15 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Tuesday
2026-09-16 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Wednesday
2026-09-17 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Thursday
2026-09-18 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Friday
2026-09-19 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Saturday
2026-09-20 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 38 | Sunday
2026-09-21 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Monday
2026-09-22 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Tuesday
2026-09-23 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Wednesday
2026-09-24 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Thursday
2026-09-25 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Friday
2026-09-26 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Saturday
2026-09-27 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 39 | Sunday
2026-09-28 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 40 | Monday
2026-09-29 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 40 | Tuesday
2026-09-30 | 2026 | 9 | Sep | Sep-2026 | Q3 | FY2026-27 | 40 | Wednesday
2026-10-01 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 40 | Thursday
2026-10-02 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 40 | Friday
2026-10-03 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 40 | Saturday
2026-10-04 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 40 | Sunday
2026-10-05 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Monday
2026-10-06 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Tuesday
2026-10-07 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Wednesday
2026-10-08 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Thursday
2026-10-09 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Friday
2026-10-10 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Saturday
2026-10-11 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 41 | Sunday
2026-10-12 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Monday
2026-10-13 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Tuesday
2026-10-14 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Wednesday
2026-10-15 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Thursday
2026-10-16 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Friday
2026-10-17 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Saturday
2026-10-18 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 42 | Sunday
2026-10-19 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Monday
2026-10-20 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Tuesday
2026-10-21 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Wednesday
2026-10-22 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Thursday
2026-10-23 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Friday
2026-10-24 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Saturday
2026-10-25 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 43 | Sunday
2026-10-26 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 44 | Monday
2026-10-27 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 44 | Tuesday
2026-10-28 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 44 | Wednesday
2026-10-29 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 44 | Thursday
2026-10-30 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 44 | Friday
2026-10-31 | 2026 | 10 | Oct | Oct-2026 | Q4 | FY2026-27 | 44 | Saturday
2026-11-01 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 44 | Sunday
2026-11-02 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Monday
2026-11-03 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Tuesday
2026-11-04 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Wednesday
2026-11-05 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Thursday
2026-11-06 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Friday
2026-11-07 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Saturday
2026-11-08 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 45 | Sunday
2026-11-09 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Monday
2026-11-10 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Tuesday
2026-11-11 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Wednesday
2026-11-12 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Thursday
2026-11-13 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Friday
2026-11-14 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Saturday
2026-11-15 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 46 | Sunday
2026-11-16 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Monday
2026-11-17 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Tuesday
2026-11-18 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Wednesday
2026-11-19 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Thursday
2026-11-20 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Friday
2026-11-21 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Saturday
2026-11-22 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 47 | Sunday
2026-11-23 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Monday
2026-11-24 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Tuesday
2026-11-25 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Wednesday
2026-11-26 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Thursday
2026-11-27 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Friday
2026-11-28 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Saturday
2026-11-29 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 48 | Sunday
2026-11-30 | 2026 | 11 | Nov | Nov-2026 | Q4 | FY2026-27 | 49 | Monday
2026-12-01 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 49 | Tuesday
2026-12-02 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 49 | Wednesday
2026-12-03 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 49 | Thursday
2026-12-04 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 49 | Friday
2026-12-05 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 49 | Saturday
2026-12-06 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 49 | Sunday
2026-12-07 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Monday
2026-12-08 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Tuesday
2026-12-09 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Wednesday
2026-12-10 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Thursday
2026-12-11 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Friday
2026-12-12 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Saturday
2026-12-13 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 50 | Sunday
2026-12-14 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Monday
2026-12-15 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Tuesday
2026-12-16 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Wednesday
2026-12-17 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Thursday
2026-12-18 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Friday
2026-12-19 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Saturday
2026-12-20 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 51 | Sunday
2026-12-21 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Monday
2026-12-22 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Tuesday
2026-12-23 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Wednesday
2026-12-24 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Thursday
2026-12-25 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Friday
2026-12-26 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Saturday
2026-12-27 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 52 | Sunday
2026-12-28 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 53 | Monday
2026-12-29 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 53 | Tuesday
2026-12-30 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 53 | Wednesday
2026-12-31 | 2026 | 12 | Dec | Dec-2026 | Q4 | FY2026-27 | 53 | Thursday